PROGRESS REPORT

Project to support the reestablishment of the Haitian National Police (HNP) in areas liberated from gang occupation

March – June 2025

- Context and justification

Haiti is currently experiencing a severe security crisis, marked by the growing power of armed groups that control several areas of the country, particularly in Port-au-Prince. This situation has led to the progressive collapse of police presence in certain regions, with the targeted destruction of numerous infrastructures belonging to the Haitian National Police (HNP), leaving entire communities unprotected and increasingly vulnerable to violence and insecurity.

The HNP is facing significant challenges in fulfilling its public security mandate. Numerous police stations, sub-stations, and other police facilities have been attacked, set on fire, or destroyed in several departments, particularly in the West. As a result, large areas are now completely devoid of law enforcement presence, exposing residents to heightened levels of violence and insecurity.

In response, the rehabilitation of police stations is a critical priority to restore public order, strengthen HNP capacity, and support the resumption of local economic activity.

With funding from the Government of Japan, UNDP is implementing with a budget of 1,067,094 USD, aimed at enhancing security in gang-free areas. This initiative will enable the HNP to enhance the protection of lives and property, in alignment with Sustainable Development Goal (SDG) 16 on peace, justice, and strong institutions. It will also contribute to the resumption of community-level economic activities, supporting poverty reduction and economic growth in line with SDGs 1 and 8.

During the project design phase, three priority police stations were identified by the HNP, two of which were initially planned for rehabilitation. However, due to security constraints in some of these areas, implementation has proven to be unfeasible. Additionally, following the destruction of the IGPNH facilities, the HNP requested the project's support to rehabilitate a building to accommodate the institution. This request justifies the inclusion of the IGPNH rehabilitation within the framework of the project. A second site will be selected by the HNP at a later stage, should the security situation prevent intervention at one of the originally planned locations.

- Progress of activities

As part of the rehabilitation of the identified site, several activities have been undertaken to ensure its rapid and functional deployment, in close coordination with the technical team of the Haitian National Police (PNH).

An initial technical assessment of the site was conducted jointly with HNP engineers, serving as the foundation for subsequent interventions. Based on this, technical studies are currently underway, led by the project team with support from HNP engineers. These studies focus on two (2) key areas:

- Physical rehabilitation of the facility, and

- Building’s energy supply system.

In response to the HNP’s urgency to take possession of the site, the project has prioritized the establishment of a reliable energy supply system. Terms of Reference for the procurement and installation of a 100 KVA generator have been finalized and submitted to the procurement unit. The procurement process is ongoing, with delivery expected by August 2025.

To reduce reliance on fossil fuels and promote environmental sustainability, the project also includes a renewable energy component. A corresponding request has been submitted to Procurement to initiate the acquisition and installation of the required equipment.

Regarding the physical rehabilitation of the building, the technical documentation is currently under final review by the project’s engineering team and HNP focal point.

- Challenges

Several constraints have impacted the pace and implementation of project activities, particularly regarding site rehabilitation and the building’s energy supply:

- Unstable Security Context: Ongoing insecurity in and around the intervention zones has restricted access for technical teams and caused delays in site visits and field assessments.

- Logistical Constraints and Heightened Security Requirements: Secure access to project sites has required specialized logistical arrangements, including the use of armored vehicles and police escorts for technical team movements. The limited availability of these resources has led to delays in conducting technical missions.

- Delays in Procurement Processes: Procurement procedures particularly for the generator and renewable energy equipment have been delayed due to specific technical requirements and administrative approval bottlenecks at the HNP level. These factors have slightly shifted the implementation timeline.

- Activities in perspective (Short term)

In the next phase of implementation, several key activities are planned to advance the operationalization of the site and support the project’s overall objectives. These include:

- Finalization and Launch of the Call for Tenders for Building Rehabilitation Works: The tender dossier for the rehabilitation works is currently being finalized. This will allow rehabilitation activities to begin, following the technical specifications agreed with the HNP.

- Procurement and Installation of the Generator and Solar Power System: The procurement process for the 100 KVA generator is underway, with delivery and installation expected in the coming weeks. In parallel, procurement and installation procedures for a solar photovoltaic system are being initiated to ensure reliable and sustainable energy supply while reducing reliance on fossil fuels.

- Results framework

| EXPECTED OUTPUTS | Output | Target | Archived value as of 30 June 2025 | Means of verification | Notes |
| --- | --- | --- | --- | --- | --- |
| 1. Preparation and planning | 1.1 Conduct a detailed assessment of the destroyed police stations to determine the extent of repairs needed. | 1 |  |  | The evaluations could not be conducted due to the security situation. |
|  | 1.2 Organize meetings with police forces, local authorities, community representatives and international partners to discuss needs and priorities | 6 | 2 meetings held | Meetings minutes | Meeting organized with the HNP, including the HNP focal point for the program and the HNP focal point for infrastructure. |
|  | 1.3 Develop a detailed rehabilitation plan including costs, resources and work schedule. | 1 | 1 Validation in progress. | ToR | The team developed the Terms of Reference for the recruitment of a firm to carry out the rehabilitation of the IGPNH. |
| 2. 2 Infrastructure réhabilitation | 2.1 Rebuild police stations in compliance with security standards and incorporate modern elements to improve their functionality. | 2 | 1 scheduled |  | Due to security constraints, the identified sites could not be initiated, as the areas are inaccessible. Based on the current needs of the HNP, the project redirected one of the planned rehabilitations to the IGPNH, which was vandalized by gangs. A new facility has been identified in the commune of Tabarre. |
|  | 2.2 Install security systems such as fencing, surveillance cameras, and lighting. | 1 set |  |  | Not yet programmed |
| 3. Provision of materials and equipment | 3.1 Prepare specifications with the HNP | 1 set | 1 | ToR | Technical specifications have been developed in collaboration with the HNP for the acquisition of an electrical system and a photovoltaic system to power the IGPNH. |
|  | 3.2 Acquire and install office equipment and trained police officers to manage them; | 1 set |  |  | Not yet programmed |

- Risk monitoring and mitigation

| # | Identified risk | Likelihood | Impact | Mitigation measures | Status |
| --- | --- | --- | --- | --- | --- |
| 01 | Deterioration of the security context | High | High | - Regular security monitoring in coordination with the HNP -Flexible planning of field missions -Use of police escorts and armored vehicles when required | Ongoing |
| 02 | Procurement process delays | Medium | High | - Close coordination with the procurement Unit - Early preparation of technical documentation - Follow-up with suppliers to accelerate processes | Planned |
| 03 | Logistical constraints for delivery and installation | Medium | Medium | - Advance coordination with HNP -Engage the HNP systematically at each phase of planning and implementation - Regular communication with PNH on timelines. | Planned |
| 04 | Technical risks related to energy system installation | Low | Medium | - Detailed technical studies - Engagement of energy experts - Pilot testing before full deployment | Planned |

- Work plan

| Expected results | Planned activities | Timeframe 2025 |  |  |  |  |  | Timeframe 2026 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar |
| 1. Improved PNH infrastructure in recovered areas | Generator supply and installation |  |  |  |  |  |  |  |  |  |
|  | Photovoltaic system supply and installation |  |  |  |  |  |  |  |  |  |
|  | Call for tenders and award of contract for building rehabilitation work |  |  |  |  |  |  |  |  |  |
|  | Execution of work |  |  |  |  |  |  |  |  |  |
| 2. Increasing police presence in recovered areas | Office equipment and supplies |  |  |  |  |  |  |  |  |  |

** It should be noted that the second site to be rehabilitated has not yet been identified due to ongoing instability in the areas where the initially targeted police stations are located. Discussions are currently underway with the Haitian National Police (HNP).

- Financial situation

The total budget allocated to the project amounts to USD 1,067,094. To date, no expenditures have been incurred. However, the procurement process is currently underway for the acquisition of a generator and the installation of a photovoltaic system as part of the rehabilitation of the IGPNH police station. This critical step will initiate the disbursement of project funds.

It is worth noting that a rigorous budget monitoring system is in place to ensure the efficient use of resources, in line with sound financial management practices.

- Conclusions

The project has achieved several key preparatory milestones despite the complex security context. The technical assessment of the site for the relocation of the IGPNH police station, the engagement of stakeholders, and progress in the procurement procedures for energy equipment represent important benchmarks. The urgent need for the Haitian National Police (HNP) to take possession of the site required a rapid reprogramming of priorities, with immediate focus on the energy supply system before finalizing other technical components. This operational pressure necessitated an adjustment to the project’s activity sequencing.

However, challenges related to security instability and logistical constraints have impacted the pace of implementation. Appropriate mitigation measures have been put in place, including strengthened coordination with the HNP and planning adapted to on-the-ground realities.

Upcoming activities, notably the finalization of technical studies, the launch of rehabilitation works, and the installation of equipment, will accelerate the effective implementation of the project. Rigorous monitoring, both operational and financial, remains a priority to ensure transparency, efficiency, and sustainability of the interventions.

The project remains firmly committed to supporting the strengthening of the HNP’s capacities and the restoration of a secure environment conducive to sustainable development.