## Sheet1
"EU Support to Confidence Building in the Western Bakans"
2025 Annual Work Plan
NO. | DESCRIPTION | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
Output 1 - Western Balkans judicial authorities are better equipped to handle war crimes. | [13 empty] | Description
1.1 | Assessment study of needs and capacities of the beneficiaries’ authorities (courts, prosecution services, police war crimes investigation units, witness protection services, and other as relevant), including gender analysis, to handle and process war crimes cases
1.2 | Provision of expert and technical support to line ministries for improving domestic legal framework (laws, bylaws, regulations) strategies and protocols | [12 empty] | Possible support to the Prosecution office in facilitating the development of the next Action Plan for War Crimes Investigation Strategy 2026-2027. Support in drafting/amending the Law on Protection Programme for participants In Criminal Proceedings
1.3 | Knowledge transfer for prosecution offices (PO), courts, police, defence attorneys, and other relevant authorities as appropriate | [12 empty] | Trainings with Centre for trainings of judges and prosecutors - training about stress and case management in the II i IV Q2025 - will know more details after the adoption of the annual programme. Development of e-learning module on application of IHL in domestic war crimes proceedings. Supervision and dealing with burnout: workshop for police officers dealing with war crimes.
1.4 | Internal cross-sectoral co-ordination meetings between judicial, law enforcement and other authorities towards enhancing practices and jurisprudence for handling war crimes | [12 empty] | After the training with IRMCT in the first half of 2025, it would be good to organize a cross-sectoral meeting, like a follow-up knowledge-sharing discussion on challenges . Participants of the training in Hague can share their experince in this meeting and what they've learned. Policy paper on international legal assistance and improvement of regional cooperation in legal matters. Internal cross-sectoral co-ordination meeting between Witness Protection Unit (Ministry of Interior), WCPO and other ministries involved in Witness Protection Program.
1.5 | Regional peer-to peer knowledge and experience sharing meetings on handling war crimes cases, particularly targeting young professionals in the authorities
Staff costs, office cost
Output 2 - Improved conditions for regional cooperation on war crimes
2.1 | Regional (multilateral and bilateral) technical peer-to-peer meetings,dialogues and mutual working visits of prosecutors and judicial officials, victim and witness support and protection services, police, defence counsels, and representatives of other relevant authorities to advance regional co-operation | [12 empty] | Study visit. Bilateral peer-to-peer meeting of representatives of the Court of BiH and Belgrade’s High Court (discussion on new agreement on cooperation in area of witness and victim support)
2.2 | Regional (multilateral and bilateral; technical and high-level) policy dialogues: meetings of judicial practitioners and line ministries and other authorities for improving regional co-operation in war crimes proceedings and cross-sectoral transitional justice co-operation (with participation of the IRMCT) | [12 empty] | IRMCT training of MNE and Kosovo delegation. Participation of the relevant stakeholders to the Annual Europe Victim Support Conference
2.3 | Technical advice for developing and/or amending policy and legal frameworks to further foster cross-border co-operation on war crimes handling | [12 empty] | The drafting of the Guidelines for the Search for Disappeared Persons has been initiated in accordance with the 'Guiding Principles for the Search for Disappeared Persons' adopted by the Committee on Enforced Disappearances and other relevant international standards. Possible support in translating, or revising it.
Staff costs, office cost
Output 3 - Increased delivery of gender sensitive support services to victims and witnesses of war crimes and stronger capacity of relevant actors
3.1 | (Inception phase): Update of UNDP’s 2019 regional needs assessment report on institutional capacities and needs in the area of victim support (with special attention to gender responsive justice for women victims and survivors of armed conflicts) to tailor the activities and streamline interventions with EU acquis in the area
3.2 | Capacity building to strengthen support for victims of CRSV and other war crimes and to enhance capacity of victim and witness support services from relevant authorities | [12 empty] | Study visit of Serbian Witness Protection Unit to WPU in Europe/USA
3.3 | Regional (multilateral, bilateral) peer-to-peer meetings of victim and witness support services (from courts, prosecution offices, police, and other relevant authorities) | [12 empty] | Annual Regional meeting for Witness and Victims Support services. Regional meeting of representatives of the Victim and Witness Services.
3.4 | Regional and domestic cross-sectoral policy dialogues of authorities and victim groups on improving victim support mechanisms available to victims and their families | [12 empty] | Local level meeting intersectoral consultations for Serbian Missing Persons Commission, line ministries (of labour and social rights, interior, justice, minority and human rights, and their local detachments) and responsible for applying new Law on Missing Persons in Serbia
3.5 | Provision of expertise for improving policy and legal framework for victims support and victims reparations (laws, bylaws, protocols for supporting victims, reparations strategies and policies), gender mainstreaming, and aligning them with EU acquis | [12 empty] | Provision of expertise for improving draft Law on Missing Persosns, organization of roundtable discussions on the draft Law on Missing Persons
3.6 | Technical assistance for developing and providing information materials to victims and their families as right holders (toolkits, booklets, print and online materials on their rights in criminal proceeding, access to existing reparations, access to services, etc.).
3.7 | Sub-grants for CSOs, including victims associations, for assisting victims and survivors and their families, in a gender-informed and -sensitive manner - locally or regionally
3.8 | Surveys among victims, using focus groups, and other data collection for updating needs assessment and evaluation of the project implementation
Staff costs, office cost
Output 4 - Grassroots actors better equipped to raise public awareness and foster mutual understanding through fact-based dialogues about crimes committed during the 1990s conflicts on the territory of the former Yugoslavia
4.1 | Regional study on public perceptions, behavioural insights and communications needs regarding war crimes trials and other transitional justice processes
4.2 | Development of victim-centered and gender informed communication strategies to help identify training/learning support, advocacies, and communications initiatives targeting common awareness and understanding of war crimes
4.3 | Sub-grants for civil society (CSOs, including victims associations, think tanks, academia , media associations, culture operators, etc.), especially at grassroots level, for dealing with legacies of the conflicts and promoting reconciliation (e.g. cross-societal and cross-generational dialogue, transitional justice education, youth engagement, improving public awareness of war crimes and trials, conducting and publicising research.
4.4 | Policy and communication dialogue – cross-sectoral and between justice authorities and the media – to increase public information and outreach on war crimes and transitional justice
4.5 | Training of journalists on gender responsive reporting on war crimes and transitional justice issues
4.6 | Training for CSO activists, bloggers/vloggers, media influencers, and young professionals engaged in public advocacy and activism of promoting reconciliation and dealing with the past (on public advocacy skills and techniques, use of social media, designing and conducting campaigns, targeted fundraising and activity planning etc.), with an aim to strengthen CSOs and grass-root level sustainability.
4.7 | Media monitoring (including monitoring traditional media reporting, political and official statements, new media and social media, and big data) to identify trends and issues in transitional justice and evaluate progress and impact of the project
4.8 | Targeted regional and national experience sharing and peer-to-peer meetings of various stakeholders involved in public awareness raising about recent past, promoting reconciliation, and addressing misinformation and disinformation | [12 empty] | Screening of the documentary theatre play "My land - What Young People Think About Patriotism" in Skopje (North Macedonia) and Podgorica (Montenegro). Transitional Justice Seminar for future decision-makers. Regional Transitional Justice Study Visit for young activists and future decision-makers
Staff costs, office cost