## Sheet1
"EU Support to Confidence Building in the Western Bakans"
|  | 2025 | 2026 Annual Work Plan
NO. | DESCRIPTION | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
Output 1 - Western Balkans judicial authorities are better equipped to handle war crimes.
1.1 | Assessment study of needs and capacities of the beneficiaries’ authorities (courts, prosecution services, police war crimes investigation units, witness protection services, and other as relevant), including gender analysis, to handle and process war crimes cases COMPLETED
1.2 | Provision of expert and technical support to line ministries for improving domestic legal framework (laws, bylaws, regulations) strategies and protocols
1.2b | Provision of expert and technical support to line ministries and other institutions for improving technical capacities for war crimes investigations and search for missing persons
1.3 | Knowledge transfer for prosecution offices (POs), courts, police, defence attorneys, and other relevant authorities as appropriate
1.4 | Internal cross-sectoral co-ordination meetings between judicial, law enforcement and other authorities towards enhancing practices and jurisprudence for handling war crimes
1.5 | Regional peer-to peer knowledge and experience sharing meetings on handling war crimes cases, particularly targeting young professionals in the authorities
Staff costs, office cost
Output 2 - Improved conditions for regional cooperation on war crimes
2.1 | Regional (multilateral and bilateral) technical peer-to-peer meetings,dialogues and mutual working visits of prosecutors and judicial officials, victim and witness support and protection services, police, defence counsels, and representatives of other relevant authorities to advance regional co-operation
2.2 | Regional (multilateral and bilateral; technical and high-level) policy dialogues: meetings of judicial practitioners and line ministries and other authorities for improving regional co-operation in war crimes proceedings and cross-sectoral transitional justice co-operation (with participation of the IRMCT)
2.3 | Technical advice for developing and/or amending policy and legal frameworks to further foster cross-border co-operation on war crimes handling
Staff costs, office cost
Output 3 - Increased delivery of gender sensitive support services to victims and witnesses of war crimes and stronger capacity of relevant actors
3.1 | (Inception phase): Update of UNDP’s 2019 regional needs assessment report on institutional capacities and needs in the area of victim support (with special attention to gender responsive justice for women victims and survivors of armed conflicts) to tailor the activities and streamline interventions with EU acquis in the area
3.2 | Capacity building to strengthen support for victims of CRSV and other war crimes and to enhance capacity of victim and witness support services from relevant authorities
3.3 | Regional (multilateral, bilateral) peer-to-peer meetings of victim and witness support services (from courts, prosecution offices, police, and other relevant authorities)
3.4 | Regional and domestic cross-sectoral policy dialogues of authorities and victim groups on improving victim support mechanisms available to victims and their families
3.5 | Provision of expertise for improving policy and legal framework for victims support and victims reparations (laws, bylaws, protocols for supporting victims, reparations strategies and policies), gender mainstreaming, and aligning them with EU acquis
3.6 | Technical assistance for developing and providing information materials to victims and their families as right holders (toolkits, booklets, print and online materials on their rights in criminal proceeding, access to existing reparations, access to services, etc.).
3.7 | Sub-grants for CSOs, including victims associations, for assisting victims and survivors and their families, in a gender-informed and -sensitive manner - locally or regionally
3.8 | Surveys among victims, using focus groups, and other data collection for updating needs assessment and evaluation of the project implementation
Staff costs, office cost
Output 4 - Grassroots actors better equipped to raise public awareness and foster mutual understanding through fact-based dialogues about crimes committed during the 1990s conflicts on the territory of the former Yugoslavia
4.1 | Analysing perceptions, behavioural patterns and communications among societal groups in relation to confidence building, social cohesion, transitional justice processes, regional cooperation and other topics as relevant, including addressing misinformation/disinformation
4.2 | Development of victim-centered and gender informed communication strategies to help identify training/learning support, advocacies, and communications initiatives targeting common awareness and understanding of war crimes
4.3 | Sub-grants for civil society (CSOs, including victims associations, think tanks, academia , media associations, culture operators, etc.), especially at grassroots level, for dealing with legacies of the conflicts and promoting reconciliation (e.g. cross-societal and cross-generational dialogue, transitional justice education, youth engagement, improving public awareness of war crimes and trials, conducting and publicising research.
4.4 | Policy and communication dialogue – cross-sectoral and between justice authorities and the media – to increase public information and outreach on war crimes and transitional justice
4.5 | Training of journalists on gender responsive reporting on war crimes and transitional justice issues
4.6 | Training for CSO activists, bloggers/vloggers, media influencers, and young professionals engaged in public advocacy and activism of promoting reconciliation and dealing with the past (on public advocacy skills and techniques, use of social media, designing and conducting campaigns, targeted fundraising and activity planning etc.), with an aim to strengthen CSOs and grass-root level sustainability.
4.7 | Media monitoring (including monitoring traditional media reporting, political and official statements, new media and social media, and big data) to identify trends and issues in transitional justice and evaluate progress and impact of the project
4.8 | Targeted regional and national experience sharing and peer-to-peer meetings of various stakeholders involved in public awareness raising about recent past, promoting reconciliation, and addressing misinformation and disinformation
Staff costs, office cost
Output 5: Accounting for missing persons in the region and stakeholders’ engagement and dialogue sustained and enhanced
5.1 | Strengthening regional cooperation in the missing persons processes, including through the regional Missing Persons Group and the coordination of the families, supporting the stakeholders' active dialogue and engagement in the process locally, regionally and internationally, and informing the public
Note on B44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Activity reformulated