## JSB1 Overview (hidden)
UNDP'S CLIMATE PROMISE: FROM PLEDGE TO IMPACT JSB PROGRESS REPORT: OVERVIEW
Reporting Guidance
Reporting Deadline | 15 April, 2023 (for the final version approved by the country coordinator)
What should be reported | 1) Please fill out information in this "JSB Overview" tab. Information below on expenditure + commitment to date is cummulative (for the entire project period up to date). Add specific values for indicators in the table below on CORE INDICATORS. These should include figures describing all achieved results during implementation of the project activities. 2) Then fill information in the next tab "JSB" tab on Q1 2023 activities under your JSB Work Plan. For any information that has been pre-filled, please review and edit if necessary highlighting the changes. Q3 and Q4 2022 information is given for your information. Please pay special attention to the rows "Summary of Progress" where you should highlight the biggest achievements up to date (focusing on the entire project) and "Partnership" where you should present details on the progress of building partnerships with Japanese counterparts - this information will be included in the global reporting to the donor.
Overview
Country name | Serbia
Project ID/Output ID - JSB | 130768
Budget | 1010000
Expenditure + commitment to date | 1010000
Delivery rate | 100%
Report completion
Report completed by | Smiljka Živanović, Project Manager
Status (select "completed" to confirm CO submission) | Completed
Report reviewed by | Snezana Marstijepovic, Country Coordinator
Status (select "completed" to confirm quality assurance of report) | Completed
CORE INDICATORS[1] | DATA SOURCE | BASELINE |  | Pillar 1 |  |  | Pillar 2
|  | Value | Year | 1.1 Driving investment in clean energy sectors and infrastructure | 1.2 Support to Ministries of Energy, Finance, Environment and Planning to address key energy-related decisions on COVID-19 recovery | 1.3 Alignment of energy targets in NDCs with net-zero pathways | 2.1 Scaling-up adaptation, resilience, and disaster risk reduction tools and ensuring they are available to marginalized groups | 2.2 Aligning targets in NDCs with national adaptation strategies and plans, including COVID-19 recovery
1.1 Tonnes of CO2 emissions avoided or reduced | National GHG Inventory | 0 | 2020 | 12.745 t/CO2 in 1st year for eight projects that have been finalized.
1.2 Megawatts of renewable or low-emission energy capacity installed, generated or rehabilitated |  |  |  | 7882 KW or 7,882MW for eight projects that have been finalized.
1.3 Number of beneficiaries with new access to green/sustainable energy (disaggregated by: male, female, youth (15-24) and indigenous people) | Yearly Report of the Government | 0 | 2021 | 110 beneficiaries: - Toyo Tire project - 13, Milsped project -3, Usce project - 15, Inovation Center MF project -3, TRAKEN project - 22, Heliant project - 5, CORE - 2, Higijena - 30
2.0 Number of direct beneficiaries with increased resilience to climate change (i.e. more resilient physical and natural assets, diversified and strengthened livelihoods and sources of income, new/improved climate information systems) (disaggregated by: male, female, youth (15-24) and indigenous people)
3.0 Number of green/sustainable jobs created (disaggregated by: male, female, youth (15-24) and indigenous people) | Yearly Statistical Office Report | 0 | 2021 | 25
4.0 Number of people trained/educated/informed through technical transfers, dialogues, workshops, campaigns, and other efforts (disaggregated by: male, female, youth (15-24) and indigenous people) | Training Reports | NA | 2021 |  | 541 overall: 81 - participants of Info days for Challenge Calls 132 - participants in National dialogue on just transition 38 - trained through Accelerator for decarbonisation and just transition 15 - trained for KAIZEN methodology 110 - trained through co-financed projects 25 - company representtaives included in the project implementation 40- participants in local dialogues on just transition 100 - participants in corporate dialoge on just transition
5.0 Number of development or sectoral policies/plans/budgets that integrate NDC targets or net-zero goals | [5 empty] | 3
Legislation | Yearly Report of the Government | 1 | 2021 |  |  | 1 - Just Transition Plan to a Low Carbon Economy in Serbia
Covid-19 response measures or
assessments
Development plans or roadmaps | Yearly Report of the Government | 0 | 2021 |  |  | 1 - socio-economic analysis for the sectors and communities most impacted by NDC’s targets
Sectoral policies and plans
National or sectoral budgets
Financial instruments or models
Subsidy reforms
Others (specify) | [5 empty] | 1 - Compilation report
6.0 Number of partnerships with Japanese organizations |  |  |  | 3 - 3 merger of companies from Serbia and Japan | 3 - Japanese Embassy in Serbia, JBAS, Kaizen Institute in Coratia
Private Sector | Project Report | 0 | 2021 | 3 - merger of companies from Serbia and Japan in 3 decarbonization projects
JICA/University/technical experts | Project Report | 0 | 2021 |  | 2 - JBAS; KAIZEN Institute in Croatia
Other |  |  |  |  | 1 - Japanese Embassy in Serbia

## JSB2 Overview
UNDP'S CLIMATE PROMISE: FROM PLEDGE TO IMPACT JSB PROGRESS REPORT: OVERVIEW
Reporting Guidance
Reporting Deadline | 14 July, 2023 (for the final version approved by the country coordinator)
What should be reported | 1) Please fill out information in this "JSB2 Overview" tab. Information below on expenditure + commitment to date is cummulative (for the entire project period up to date). Add specific values for indicators in the table below on CORE INDICATORS. These should include figures describing all achieved results during implementation of the project activities. 2) Then fill information in the next tab "JSB2" tab on Q2 2023 activities under your JSB Work Plan. For any information that has been pre-filled, please review and edit if necessary highlighting the changes. Please pay special attention to the rows "Summary of Progress" where you should highlight the biggest achievements up to date (focusing on the entire project) and "Partnership" where you should present details on the progress of building partnerships with Japanese counterparts - this information will be included in the global reporting to the donor.
Overview JSB2
Country name | Serbia
Project ID/Output ID - JSB | 130768
Budget | 1000000
Expenditure + commitment to date | 3404
Delivery rate | 0.3404%
Report completion
Report completed by | Smiljka Živanović, Project Manager
Status (select "completed" to confirm CO submission) | Completed
Report reviewed by | Snezana Marstijepovic, Country Coordinator
Status (select "completed" to confirm quality assurance of report) | Completed

## JSB2
Summary of Progress (Provide an overall project implementation progress and the biggest achievements that need to be showcased to the donor, covering the entire project period (but focusing on Q2 2023 if possible) | The project started in May 2023. At the very beginning of the project implementation, the Project Implementation Unit (PIU) prepared a procurement plan and timeline of the project implementation. The Project Steering Committee who will provide overall guidance and will be responsible for making management decisions for the project will be established and consisted of the same institutions like in the previous project (Ministry of Mining and Energy and Ministry of Environmental Protection), and will meet at least twice during project implementation period. UNDP established cooperation with the Embassy of Japan and other national partners – Chamber of Commerce and Industry of the Republic of Serbia and Japanese Business Alliance in Serbia (JBAS). In the first phase of project implementation, focus was on the preparation, launching and promotion of the Challenge Call for Innovative business models that diversify electricity generation mix, reduce energy intensity of the economy or enables clean energy, especially for the vulnerable consumers. UNDP organized six information sharing sessions (info days) with public, private companies and research community, to familiarize potential beneficiaries with the Challenge Call criteria. The so called "Info days" were organized in different regions of Serbia, focusing particularly on regions, sectors, local communities who are economically dependent on the intensive use of fossil fuels or that rely on the carbon intensive industries that cause high level of pollution of the environment.
Partnership (Provide concrete examples of partnerships with Japanese counterparts (Embassy of Japan, JICA, academic, private sector, NGOs, governmental organisations of Japan etc) | The project continues intensive collaboration with the Embassy of Japan in Serbia and relevant ministries – Ministry of Mining and Energy and Ministry of Environmental Protection of the Republic of Serbia. UNDP promoted the Challenge Call in cooperation with the Chamber of Commerce and Industry of Serbia (and their regional branches) and the Japanese Business Alliance in Serbia (JBAS) in order to encourage cooperation between companies from Serbia and companies from Japan that operate in Serbia. The main goal is to promote potential implementation of the Japanese green technologies and products, application of the related knowledge and experience in the process of green transformation of the economy. As the team of the Embassy of Japan has changed and new Japanese Ambassador in Serbia (H.E. Mr. Akira Imamura) has been nominated, UNDP decided to postpone organization of the kick-off meeting of the project to September 2023, when Embassy`s team will be operational and Accelerator will be launched.
JSB Project Work Plan | [5 empty] | ENTER Q2-2023 PROGRESS REPORT HERE
Expected Outputs | CO Indicators | Baseline | Targets | Activity Result | Actions | Status as of Q2 2023 | Comments | Link to FINAL documents/products
Please do not edit | Please do not edit | Please do not edit | Please do not edit | Please do not edit | Please do not edit | Select from dropdown menu | Please provide Q2 2023 activity progress details here according to each activity targets (include quantitative results where available) | Click here to upload visibility efforts, knowledge management products, PRs (If files are posted in an existing website please share URL links in the rows below)
Country Output 1 Innovative business models that reduce import dependency, diversify electricity generation mix, reduce energy intensity of the economy or enable access to clean and affordable energy for vulnerable population, intended for individual households (prosumers), public and private business sector, identified and deployed Global Output: 1.1 Driving investment in clean energy | Number of applications to the Challenge Call received | NA | 20 | 1.1. Activity Result - Innovation Challenge Call to support investments and innovative business models that reduce import dependency, diversify electricity generation mix, reduce energy intensity of the economy or enable access to clean and affordable energy for vulnerable population, intended for individual households (prosumers), public and private business sector conducted | Preparation of Innovation Challenge Call (including elaboration of criteria, as well as gender sensitive evaluation criteria) | Completed | The Project Team prepared the Challenge Call with evaluation criteria. The aim of the “Challenge Call for Innovative business models that diversify electricity generation mix, reduce energy intensity of the economy or enables clean energy, especially for the vulnerable consumers” was to invite Serbian private and public sector companies to propose innovative solutions that contribute to the green transformation of the economy, energy security of the country and the prevention of energy poverty. The Challenge Call in particular targeted businesses and sectors still relying on the intensive use of fossil fuels. Potential applicants were encouraged to consider integration of just transition elements into their proposals, such as reskilling, upskilling of the workforce, re-employment, support to affected regions etc., but also applications that include elements such as depollution of the environment, economy decarbonization, decreasing energy intensity of the economy, enabling affordable supply of clean energy, especially for vulnerable consumers, and encouragement of women`s entrepreneurship and new industry branches as an alternative to the coal industry. As evaluation criteria, among others, the following criteria are listed: established cooperation between companies from Serbia and companies from Japan that operate in Serbia in order to encourage the use of Japanese green technologies and products, application of knowledge and experience in the process of green transformation of the economy; does the project encourage the retraining of workers and the development of new skills that are needed for the modern labour market? Does the project have elements of support for women’s entrepreneurship in the process of green transformation of the economy? Is the project’s impact on managing the social and economic effects of a just green transition in the coal regions and/or energy poverty demonstrated?
| Number of information sharing sessions organized | NA | At least 2 |  | Lunching Innovation Challenge Call and organizing at least two information sharing sessions | On Track (In Progress) | The Challenge Call was launched on May, 25, 2023. The application deadline is July 12, 2023. Reporting period, six info days related to promotion of the Challenge Call and discussion with potential project promoters, were organized. First Info Day was organized in Belgrade on March 25 with 37 participants, in cooperation with JBAS and with presence more than 30 Japanese companies that operate in Serbia. Second Info day was organized in Zlatibor, on 31 May, during the conference “Mining in Serbia” with presence of 42 participants (35 men and 7 women). Third info day was organized in Zaječar on June 21 with presence of 30 participants (34 men and 6 women). Forth info day was organized in Pančevo, on June 27 with presence of 10 participants (7 men and 3 women). Fifth info day was organized in Valjevo on June 28 with presence of 24 participants (18 men and 6 women). Sixth info day was organized on June 29 in Novi Sad with presence of 18 participants (11 men and 7 women). | https://www.undp.org/serbia/news/call-innovative-solutions-production-electrical-energy-renewable-sources-and-reduction-energy-consumption https://zajecar.pks.rs/vesti/u-rpk-zajecar-predstavljen-program-ujedinjenih-nacija-za-razvoj-undp-za-inovativne-poslovne-modele-u-cilju-poboljsanja-energetske-efikasnosti-8571 https://pancevo.pks.rs/vesti/odrzan-info-dan-u-okviru-javnog-poziva-koji-sprovodi-program-ujedinjenih-nacija-za-razvoj-undp-8590 https://valjevo.pks.rs/vesti/info-dan-u-okviru-javnog-poziva-za-inovativne-poslovne-modele-8593
[5 empty] | Evaluation of the applications submitted to the Challenge Call completed and innovative solutions selected for further development in the acceleration process | On Track (Planned) | NA
| Number of workshops organized | NA | At least 5 |  | Incubation/acceleration process conducted (mentorship, couching workshops including KAIZEN management, identifying co-financing sources for selected teams), including integration of gender elements | On Track (Planned) | NA
| Number of most innovative decarbonization/green transformation solutions deployed | NA | At least 5 | 1.2. Activity Result - Financial agreements for the implementation of the projects innovative business models that reduce import dependency, diversify electricity generation mix, reduce energy intensity of the economy or enable access to clean and affordable energy for vulnerable population, completed | Most mature projects ready for co-financing selected (paying attention to strengthened support provided to women-led business projects) - Low-Value Performance-based Payment Agreements issued (including due diligence process, defining outcomes and set of indicators which would trigger payments) - Monitoring of the implementation of selected projects | On Track (Planned) | NA
| Number of public outreach events organized | NA | 2 | 1.3. Activity Result - Public outreach events to disseminate results and encourage replication of innovative solutions conducted | Public outreach campaign conducted to disseminate results and encourage the replication of pilot projects (including the use of social media, TV, radio, articles in printed media and video coverage) | On Track (Planned) | NA
[5 empty] | 2 events to present project results to specific target groups organized (public and private business sector) | On Track (Planned) | NA
Country Output 2 Improvements of legal and policy system on just green transition identified Global Output: 1.2 Support to Ministries of Energy, Finance, Environment and Planning to address key energy-related decisions towards just transition | Legal gap assessments report developed | No | Yes | 2.1. Activity Result - Legal gap assessments to identify all necessary changes and amendments in the legislation relevant for the just green transition issues developed | Identification of laws and other legislation relevant for the just green transition that need to be improved - Preparation of Legal gap assessments report | On Track (Planned) | NA
| Number of people (representatives of relevant stakeholders) engaged in dialogue on green transition | NA | Males: 50 Females: 50 | 2.2. Activity Result – Recommendations for establishing system of monitoring, reporting and updating the relevant documents (Action plan etc…) on just green transition, with gender disaggregated data, prepared | Organizing at least 3 stakeholder dialogues | On Track (Planned) | NA
| Number of dialogues | NA | At least 3 |  | Providing support to the Ministry of Mining and Energy in developing public call for local self-governments (LSGO) to improve energy efficiency in public and residential buildings, through awarding subsidies to citizens for implementation of EE measures | On Track (Planned) | NA
| Number of developed public call for LGSO | 0 | At least 1 |  | Conducting analyses of established monitoring and reporting system on just green transition from developed countries, including Japan | On Track (Planned) | NA
| Report with recommendations prepared | No | Yes |  | Preparation of Report with recommendations for establishment system of monitoring, reporting and updating the relevant documents on just green transition (including gender disaggregated data) | On Track (Planned) | NA
Country Output 3 Strengthened national capacities for monitoring and reducing the energy poverty and vulnerable consumers Global Output: 1.3 Alignment of energy targets in NDCs with net-zero pathways | Number of people interviewed | NA | Males: 100 Females: 100 | 3.1. Activity Result - Research of energy poverty and vulnerable consumers conducted, and Report prepared | Conduct analyses of number of households falling under energy poverty and number and type of vulnerable consumers, existing national measures etc. | On Track (Planned) | NA
| Legal gap assessments report developed | No | Yes | 3.2. Activity Result - Legal gap assessments and cost analyses to identify all necessary changes and amendments in the legislation relevant for the energy poverty issues developed | Identification of laws and other legislation relevant for the energy poverty issues that need to be improved | On Track (Planned) | NA
[5 empty] | Preparation of Legal gap assessments report | On Track (Planned) | NA
| Number of people engaged in dialogue on energy poverty |  |  | 3.3. Activity Result - Report with recommendations for implementation of measures (gender sensitive), with examples of good practice relevant for reducing energy poverty, and for establishing system of monitoring and reporting on energy poverty developed | Organizing at least 3 stakeholder dialogues | On Track (Planned) | NA
| Number of LSGO applications for improvement energy efficiency in public and residential buildings, evaluated | NA | at least 30 |  | Providing support to the Ministry of Mining and Energy in conducting public calls for local self-governments to improve energy efficiency in public and residential buildings, as mechanism for preventing energy poverty and to monitor the implementation of the Ministry`s program at the LSGO level. | On Track (Planned) | NA
[5 empty] | Collecting examples of good practice from developed countries, including Japan | On Track (Planned) | NA
[5 empty] | Conducting analyses of established monitoring and reporting system on energy poverty from developed countries, including Japan | On Track (Planned) | NA
| Report with recommendations prepared | No | Yes |  | Preparation of Report with recommendations for establishment of energy poverty reporting system | On Track (Planned) | NA

## JSB1 (hidden)
Summary of Progress (Provide an overall project implementation progress and the biggest achievements that need to be showcased to the donor, covering the entire project period (but focusing on Q1 2023 if possible) | Related to project contribution to the regulatory policy on just transition, project provided socio-economic analysis, conclusions and recommendations from the dialogues conducted with stakeholders at national, local and corporate level on green transition, Just Transition Plan to a Low Carbon Economy in Serbia, which will combined with "Diagnostic Study of Just Transition in Serbia", implemented by EBRD, support the Government of Serbia in defining the necessary comprehensive public policy document on green and just transition. The JSB project results inspired other projects to replicate best practices. The "EU for Green Agenda in Serbia" project, financed by different donors (EU, European Investment Bank, Governments of Sweden, Switzerland, and Serbia) published a new Innovation Challenge Call, which will drive new investments in clean energy by supporting innovative ideas that can contribute effectively to achieving the NDC’s target in reducing GHG emissions while also ensuring financial sustainability. Eight (8) decarbonization projects are successfully finalized (Toyo Tire, Milsped, USCE, ICFoME, Higijena, TRAKEN TECH, CORE and Heliant). Together, they will increase national RES installed capacities for additional 7,8 MW of solar power, and contribute to decreasing CO2 emissions for 12.745 tCO2/year, with which they are supporting the Government of Serbia in meeting its eNDC target of 13.2 % reduction of GHG emissions by 2030, compared to 2010. 110 participants have been trained through co-financed projects and 25 new jobs were established for new employees for the jobs such as: maintenance of the solar power plants, organic waste management, compost machine area maintenance, researchers to be involved in the R&D activities of the zero CO2 emission ICE, software and Blockchain developers. Some of the specific project results during the implementation period are: 1) Organization of two dialogues on just green transition at the local level - in Obrenovac and Pozarevac, on 21 and 22 February 2023 and gathered about 40 local actors – representatives of the local self-governments, vocational and technical schools, PE Elektroprivreda Srbije, TPP Kostolac, PE UCE Resavica, TPP Morava, and civil society organizations, as well as international and national experts and representatives of Chamber of Commerce. These local communities, situated in the coal mining and carbon-intensive industrialized regions of Kolubara, Kostolac and Resavica, are identified as potentially the most vulnerable to the effects of the green transition process. Participants had an opportunity to propose (with the guidance of the national experts) a potential scenario/solution, that would be the most effective for their local economies, workforce and society. Some of the conclusions: a) Establish a Local Council for a Just Green Transition in local self-governments that will be most affected, which would include representatives of all interested parties, b) Proceed with the development of Plans for a Just Local Transition in local self-governments that will be most affected, v) to establish a functional and purpose-specific Local Fund for a Just Green Transition, especially in local self-governments that will be most affected, d) the importance of active citizen engagement was emphasized (currently, civic activism is weak because there are no open communications with decision-makers), e) to consider the possibility of establishing Training Centers for Education in local self-governments that will be most affected. 2) Organization of "Dialogue on the role of the economy in a just green transition" in Belgrade on 20 March 2023, in cooperation with Chamber of Commerce and Industry of Serbia and gathered more than 100 representatives from different sectors of the economy with the crucial role in the green transition: from the large manufacturers, big consumers of electrical energy, and industrial plants, to small and medium size enterprises, as well as representatives of unions, academic community and civil society. The event was organized as participatory dialogue with relevant stakeholders on how to implement a green transition in practice to make it fair with focus on understanding how companies will prepare in the coming period as well as on overview at socio-economic aspects, needed jobs, qualifications, skills and education. Some of recommendations: a) to improve regulatory framework in a way to include just transition principles in all relevant strategic documents, b) the importance of partnership between employers and employees in the transition process was emphasized, c) the biggest challenge in education, including retraining and reskilling programmes, is the reform of the education system, i.e. how to integrate the green transition priorities into our education system. Youth should be included in these processes. d) the green skills will be included in the qualification standards. What needs to be done is to set up a qualifications database with retraining options., e) Improve and adjust statistics, and make estimates about the number of persons, but also the structure of those who can potentially lose their jobs in the processes of the green transition. 3) Compilation Report with examples of good practice from developed countries, including Japan; socio-economic analysis for the sectors and communities most impacted by NDC’s targets and Just Transition Plan to a Low Carbon Economy in Serbia were developed based on desk research, statistical analysis, survey results, conclusions and recommendations from the dialogues with representatives of key sectors and communities that are affected by the green transition in Serbia.
Partnership (Provide concrete examples of partnerships with Japanese counterparts (Embassy of Japan, JICA, academic, private sector, NGOs, governmental organisations of Japan etc) | Project continued very intensive collaboration with the Embassy of Japan in Serbia, emphasizing their important role as a donor and partner in building trust and the opportunity to work with Japanese partners towards a green and just transition and transformation of Serbia. The Ambassador of Japan in Serbia, H.E. Takahiko Katsumata gave an opening speech during the "Dialogue on the role of the economy in a just green transition" on 20th March 2023 as well as on the press conference which was presented on the prime time news “Dnevnik 2” on the Serbian Broadcasting Corporation Radio Television of Serbia. Japanese Business Alliance in Serbia (JBAS) stay a very important project partner in strengthening cooperation between companies from Japan with the Serbian companies. The projects which were co-financed and included collaboration with Japanese partners or companies are: 1) project "Toyo Tire Taiyo" solar power plant, company Toyo Tyre d.o.o.Serbia, 2) project: “Telemedicine for inflammatory bowel diseases”, company “Heliant” in cooperation with Japanese pharmaceutical company “Takeda”, 3) project “Introduction of a system of primary separation of packaging waste from municipal waste in the territory of the city of Pančevo”, company Public Utility Company "Higijena" Pančevo in cooperation with Japanese experts. Collaboration with Japanese partners will be continued through the new JSB 2022 project “Innovative and Just Green Transition as Tool for Securing Systemic Energy Security and Reducing Energy Poverty” that will be implemented in the period March 2023-April 2024.
JSB Project Work Plan | [5 empty] | Q3-2022 PROGRESS: For reference- DO NOT UPDATE |  |  | Q4-2022 PROGRESS: For reference- DO NOT UPDATE |  |  | ENTER Q1-2023 PROGRESS REPORT HERE
Expected Outputs | CO Indicators | Baseline | Targets | Activity | Actions | Status as of Q3 2022 | Comments | Link to FINAL documents/products | Status as of Q4 2022 | Comments | Link to FINAL documents/products | Status as of Q1 2023 | Comments | Link to FINAL documents/products
Please do not edit | Please do not edit | Please do not edit | Please do not edit | Please do not edit | Please do not edit | Select from dropdown menu | Please provide Q3 2022 activity progress details here according to each activity targets (include quantitative results where available) | Click here to upload visibility efforts, knowledge management products, PRs (If files are posted in an existing website please share URL links in the rows below) | Select from dropdown menu | Please provide Q4 2022 activity progress details here according to each activity targets (include quantitative results where available) | Click here to upload visibility efforts, knowledge management products, PRs (If files are posted in an existing website please share URL links in the rows below) | Select from dropdown menu | Please provide Q1 2023 activity progress details here according to each activity targets (include quantitative results where available) | Click here to upload visibility efforts, knowledge management products, PRs (If files are posted in an existing website please share URL links in the rows below)
Country Output 1 Just Transition Plan developed through stakeholder engagement to ensure just implementation of Serbia's NDC Global Output 1.3 Alignment of energy targets in NDCs with net-zero pathways | Number of people (representatives of national and local authorities, workers and employers unions) engaged in dialogue on green transition | NA | Males: 50 Females: 50 | 1.1. Activity Result: Dialogues conducted with stakeholders at national and local level on green transition for increased climate ambition and implementation of NDC | At least 20 national and 20 local stakeholders relevant for NDC implementation identified | Completed | The list with identified all possible group of stakeholders that will be invited in dialogues conducted with stakeholders at national and local level on green transition for increased climate ambition and implementation of NDC is developed. Due to the Just Transition Dialogue complexity in its nature, the Project team identified the following key groups of stakeholders, as priority aggregates based on their type, roles and responsibilities: Ministries, Governmental Institutions and Regulatory Bodies, City Administrations and Local Governments, Corporate sector, Trade Unions, Business and professional organizations, Academia and scientific institutions, Non-governmental organizations, Financing institutions etc. Each group of actors has a certain capability to impact the successful just transition process from various perspectives and with diverse levels of knowledge and experience. It was identified more than 30 national stakholders and more than 20 local stakeholders relevant for the NDC implementation. | N/A | Completed | The National Dialogue on Just Green Transition in Serbia which was held on October 17th, 2022 in Belgrade gathered more than 130 participants: representatives of the ministries responsible for energy, environmental protection, labour and education, as well as representatives of employers, trade unions, civil society and international organisations, media etc. The interest of the public and media for the national event was much higher than expected. The list of identified all possible group of stakeholders on local and stakeholder level is developed. | Please add link to your post on UNDP Serbia website re this event | Completed | For the NDC implementation, relevant stakeholders were identified: Level 1. Directly involved •Directly involved in the transition process government institutions (which includes ministries and government institutions / organizational units) •Local governments of cities, •Local corporations identified as directly affected by the process •Unions, Level 2. Other institutions/organizations associated with the project •Other ministries/indirectly involved ministries, •Other institutions, unions, associations, •Corporations associated with the process. •Academy, •NGO for environment and local development •Level 3. Other institutions. Standing conference of cities and municipalities, •Academy / institutes, •Serbian Chamber of Commerce and other relevant business/industrial associations, •The media, •The others | n/a
| Number of people (representatives of national and local authorities, workers and employers unions) engaged in dialogue on green transition |  |  | 1.1. Activity Result: Dialogues conducted with stakeholders at national and local level on green transition for increased climate ambition and implementation of NDC | Scenario for dialogues prepared with identified topics relevant for NDC implementation | Completed | The Project team developed scenario for national and local dialogues that includes three relevant topics with sub-themes for each: 1) Decarbonisation and just transition concept (Decarbonisation process including discussion on carbon-intensive sectors and need for climate action; Just Transition principles including discussion on inclusive and fair people-centred transition toward low-carbon economy; Governance framework including discussion on stakeholders’ roles and responsibilities; Roadmap and planning including discussion on unlocked potentials and opportunities, as well as major challenges, barriers and threats), 2) Post-transition economy (Diversification of national economy including dialogue on transformation of high carbon-producing economic system to low-carbon economic activities with focus on strengthening communities; Social stability dimension including dialogue on securing the prosperity and perspective of the community by minimizing the risks of job losses, social inequality and poverty, migrations, gender equality, etc.; Outlook of future labour market including dialogue on inter-sectoral shifts and rethinking of job creation through reforms toward green jobs creation requiring extensive re-skilling process and reform of education; Sustainability of concept including dialogue on the need for long-term inter-sectoral national-scale and local-level planning), 3) Funding and reskilling needs for green just transition (Financing options including discussion on available sources and potential funding models; Cooperative development approach including discussion on the role of financing institutions, as well as proactive roles of public and private sectors in scaling up investments; Investing in education and training including discussion on the need for boosting research and development activities, as well as innovation and entrepreneurship; National qualification framework restructuring and need for new accredited educational programs in accordance with the new needs of the labor market (e.g. Green jobs)). | N/A | Completed | The Scenario for the National Dialogue on Just Green Transition in Serbia included 3 panels sessions with relevant topics (organized in October 17th, 2022): 1) Panel 1 “How to implement decarbonization in practice in order to achieve just green transition” with the following topics: Decarbonisation process including discussion on carbon-intensive sectors and need for climate action; Just Transition principles including discussion on inclusive and fair people-centred transition toward low-carbon economy; Governance framework including discussion on stakeholders’ roles and responsibilities;  Roadmap and planning including discussion on unlocked potentials and opportunities, as well as major challenges, barriers and threats, 2) Panel 2 “Post-green transition economy” with the following topics: Diversification of national economy including dialogue on transformation of high carbon-producing economic system to low-carbon economic activities with focus on strengthening communities; Social stability dimension including dialogue on securing the prosperity and perspective of the communities in carbon-intensive regions by minimizing the risks of job losses, social inequality and poverty, migrations, ensuring gender equality, etc.;  Outlook of the future labour market including dialogue on inter-sectoral shifts and rethinking of job creation through reforms toward green jobs creation requiring extensive re-skilling process and reform of education; Sustainability of post-green transition economy including dialogue on the need for long-term inter-sectoral national and local-level planning, 3) Panel 3 “Funding and reskilling needs for just green transition” with the following topics:  Financing options including discussion on available sources and potential funding models, which include dimension of just green transition;  Cooperative development approach including discussion on the role of financing institutions, as well as proactive roles of public and private sectors in scaling up green investments and green transformation of economy, the importance of respecting the just transition principles;  Investing in education and training including discussion on the need for boosting research and development activities, as well as innovation and entrepreneurship;  National qualification framework restructuring and need for new accredited educational programs in accordance with the new needs for the new green jobs in the labour market. The scenarios for local dialogues and dialogues with stakeholders are developed. | Please add links to twitter and facebook posts about this sessions | Completed | The Project team developed scenario for local dialogues that includes relevant topics with sub-themes for each: 1) How do you understand the process of green transition in all sectors of the industry that is now working in your municipality and surroundings - how will the industry and services look like in 10, 20, 50 years., 2) Roles and responsibilities of stakeholders in the realization of a just transition - how do you think you can get involved and become co-authors, or co-creators of a just transition, 3) Roadmap and planning including discussion of unused potentials and opportunities as well as major challenges, obstacles and threats, 4) How do you see your role in ensuring the prosperity and perspective of the municipality and its surroundings, by minimizing the risk of job losses, social inequality and poverty, migration, gender equality, etc, 5) What new job openings do you see in the next 10, 20, 50 years, and how do you see your participation in timely retraining and education reform at all levels, 6) Whether and how to ensure long-term intersectoral planning at the municipal level. | n/a
| Number of people (representatives of national and local authorities, workers and employers unions) engaged in dialogue on green transition |  |  | 1.1. Activity Result: Dialogues conducted with stakeholders at national and local level on green transition for increased climate ambition and implementation of NDC | Compilation Report with examples of good practice from developed countries, including Japan, prepared | On Track (In Progress) | The preparation of the Compilation report with examples of good practice from developed countries, including Japan is in progress and will be completed until the end of October 2022. | N/A | On Track (In Progress) | The preparation of the Compilation report with examples of good practice from developed countries, including Japan is in progress and will be completed until the end of January 2023. It will include examples of case studies in different countries and compile information such as description, targets groups, stakeholder engagement, expected results and results achieved so far, observations etc. International consultant for realization of this activity is contracted and is already working on this report. | n/a | Completed | The compilation report of international case studies (including Japan) to support Serbia’s transition to a low carbon development was developed and includes a choice of international case studies related to just transition. The case studies included in this report cover the following topics: 1) Mainstreaming (integration) of just transition provision in the climate change mitigation policy documents. 2) People centered just transition – ensuring people are at the core of the decision-making process, participating actively in the design of their future; 3) Political uncertainty: the effects on the community of political uncertainty /lack of a clear message or decision related to the transition. 4) Recovering from unplanned transition: sometimes action to ensure no one is left behind comes late, but it’s never too late. 5) Economic diversification: is key in communities dependent on fossil fuels (namely coal). 6) Private sector action: companies need not wait or rely on action by the government – their survival may depend on their own actions to ensure a smooth transition. 7) Small and medium enterprises transition: many impacted stakeholders are SMEs, many of them are only indirectly related to the fossil fuel sector, but they also employ people and may be at the heart of the economic diversification. | n/a
| Number of people (representatives of national and local authorities, workers and employers unions) engaged in dialogue on green transition |  |  | 1.1. Activity Result: Dialogues conducted with stakeholders at national and local level on green transition for increased climate ambition and implementation of NDC | At least 3 stakeholder engagement dialogues (two local and one national dialogues) organized | On Track (In Progress) | The dialogue process will start with the National Just Transition Dialogue which will be held on October 17th, 2022, as a high level event which will gather more than 100 representatives of various relevant key groups of stakeholders. After this national event, the two local-level dialogues will be repeatedly held in defined communities during the November and December 2022. | The press conference will be organized within the national just transition dialogue, which will be held on 17th October, with the high level officials: H.E. Takahiko Katsumata, Ambassador of Japan to Serbia, Ms. Zorana Mihajlović, Deputy Prime Minister and Minister of Mining and Energy, Ms. Irena Vujović, Minister of Environmental Protection, Mr. Yakup Beris, Resident Representative UNDP Serbia | On Track (In Progress) | In order to support the Government of Serbia in the development of Just Transition Plan towards a low-carbon economy, the project started with the organization of the dialogue process which aims at creating a joint approach of the Serbian society towards the green transition, at both national and local levels, having in mind the international obligations and commitments of the Republic of Serbia. The National Dialogue on Just Green Transition in Serbia was held on October 17th, 2022 in Belgrade and gathered more than 130 participants: representatives of the ministries responsible for energy, environmental protection, labour and education, as well as representatives of employers, trade unions, civil society and international organisations, media etc. The interest of the public and media for the national event was much higher than expected. The aim of the dialogue was to find a collective response and initiate dialogue with the whole of society on how to reduce potential job losses, undertake reskilling of the workforce in a timely manner, and diversify economies (sources of income) in towns and municipalities that depend on coal production, so that all relevant stakeholders can be involved and no one is left behind in this process. The dialogue started with the press conference and official speeches with the high level officials: H.E. Takahiko Katsumata, Ambassador of Japan to Serbia, Ms. Zorana Mihajlović, Deputy Prime Minister and Minister of Mining and Energy, Mr. Anas Quarman, Deputy Resident Representative UNDP Serbia and continued with presentation of the study: “Initiating the Just Transition in Serbia” - Leaving no one behind in the coal intensive regions and communities in Serbia, presented by Mr. Gonçalo Cavalheiro, author of the study and expert on just green transition and presentation of the project “Serbia Just Transition Diagnostics” and draft “Just Transition Action Plan”, Milena Popović Martinelli, European Bank for Reconstruction and Development. In the second part of the dialogue, 3 panel sessions were organized with the relevant stakeholders, such as: 1) Panel 1: Ministry of Mining and Energy; Trade Union Confederation „Nezavisnost“; International Labour Organization; NGO RES Foundation, 2) Panel 2: Ministry of Labour, Employment, Veteran and Social Policy; Chamber of Commerce and Industry of Serbia; Confederation of Autonomous Trade Unions of Serbia; UN Women; NGO Belgrade Open School, 3) Panel 3: Ministry of Education, Science and Technological Development; European Bank for Reconstruction and Development; Qualifications Agency; NGO Belgrade Fund for Political Excellence; Serbian Association of Employers. The process of evaluation and selection of bidder who will implement local-level dialogues is ongoing. The two local-level dialogues will be repeatedly held in defined communities during January and February 2023. | https://www.linkedin.com/posts/undp-serbia_dijalog-o-zelenoj-tranziciji-gost-%C5%BEarko-activity-7014200934704537600-jUMJ https://www.undp.org/serbia/news/dialogues-just-green-transition-commence https://www.undp.org/sr/serbia/news/poceo-dijalog-o-pravednoj-zelenoj-tranziciji-u-srbiji https://www.rts.rs/page/magazine/sr/story/2953/priroda/4987641/zelena-tranzicija-srbije-po-receptu-eu.html https://www.vesti.rs/Ekonomija/UNDP-Poceo-dijalog-o-pravednoj-zelenoj-tranziciji-u-Srbiji.html https://www.ekapija.com/news/3878203/poceo-dijalog-o-pravednoj-zelenoj-tranziciji-u-srbiji-kako-to-rade-japanci https://www.krstarica.com/vesti/ekonomija/zelena-tranzicija-ne-sme-nikoga-da-ostavi-bez-posla/ https://bizinfo.rs/undp-poceo-dijalog-o-pravednoj-zelenoj-tranziciji-u-srbiji/ https://www.tvmost.info/post/mihajlovic-zelena-tranzicija-ne-sme-nikoga-da-ostavi-bez-posla https://naslovi.net/2022-10-17/rts/zelena-tranzicija-srbije-po-receptu-eu/31785525 https://www.industrija.rs/vesti/clanak/poceo-dijalog-o-pravednoj-zelenoj-tranziciji-u-srbiji https://www.energetskiportal.rs/mihajlovic-energetska-tranzicija-je-pravedna-zelena-tranzicija-okrenuta-prema-ljudima/ https://naslovi.net/2022-10-17/ekapija/poceo-dijalog-o-pravednoj-zelenoj-tranziciji-u-srbiji-kako-to-rade-japanci/31785503 https://energijabalkana.net/poceo-dijalog-o-pravednoj-zelenoj-tranziciji-u-srbiji-kako-to-rade-japanci/ | Completed | Besides the National Dialogue on Just Green Transition in Serbia which was organized in the last quarter, project has organized two dialogues on just green transition at the local level - in Obrenovac and Pozarevac, on 21 and 22 February 2023 and gathered about 40 local actors – representatives of the local self-governments, vocational and technical schools, PE Elektroprivreda Srbije, TPP Kostolac, PE UCE Resavica, TPP Morava, and civil society organizations, as well as international and national experts and representatives of Chamber of Commerce. These local communities, situated in the coal mining and carbon-intensive industrialized regions of Kolubara, Kostolac and Resavica, are identified as potentially the most vulnerable to the effects of the green transition process. Both dialogues started with the official speeches of the Government representatives (Ministry of Mining and Energy and Ministry of Environemntal Protection) and UNDP representative. During the dialogues, international and national experts presented to the local actors how Just Transition was conducted successfully, like Genk in Belgium, which was once a mining town. Participants had an opportunity to propose (with the guidance of the national experts) a potential scenario/solution. Some of the proposals for the next steps were: - Establish a Local Council for a Just Green Transition in local self-governments that will be most affected, which would include representatives of all interested parties (the Council could, for example, organize information days for young people). - Proceed with the development of Plans for a Just Local Transition in local self-governments that will be most affected -It would be significant to establish a functional and purpose-specific Local Fund for a Just Green Transition, especially in local self-governments that will be most affected. - The importance of active citizen engagement was emphasized. In this sense, it is better to inform citizens in a timely manner (currently, civic activism is weak because there are no open communications with decision-makers). -It is suggested to consider the possibility of establishing Training Centers for Education in local self-governments that will be most affected, as these municipalities will gain valuable experiences in the process of green transition that could be shared with other municipalities and individuals (for example, for organic food production, sustainable tourism development, nature conservation, etc.). | https://www.undp.org/serbia/news/two-local-level-dialogues-just-green-transition
| Number of people (representatives of corporate sector) engaged in the dialogue | NA | Males: 50 Females: 50 | 1.2. Activity Result: Dialogue with corporate sector conducted (both, public and private companies) to ensure knowledge and skills needed for green transition & increased climate ambition | At least 100 corporate sector representatives identified for inclusion in the dialogue | On Track (In Progress) | The project team will identify representatives of the different corporate sectors which could be mostly affected by the green transformation, in cooperation with the engaged project experts during the November 2022. | N/A | On Track (In Progress) | The identifiaction of representatives of the corporate sector which could be mostly affected by the green transformation, with support of engaged project expert is underway. | n/a | Completed | For inclusion in the dialogues relevant stakeholders were identified: Level 1. Directly involved •Directly involved in the transition process: i) government institutions (which includes ministries and government institutions / organizational units), ii) Local governments of cities, iii) Local corporations identified as directly affected by the process, iv) Unions Level 2. Other institutions/organizations associated with the project: •Other ministries/indirectly involved ministries, •Other institutions, unions, associations, •Corporations associated with the process, •Academy, •NGO for environment and local development Level 3. Other institutions. Standing conference of cities and municipalities, •Academy / institutes, •Serbian Chamber of Commerce and other relevant business/industrial associations, •The media, •The others | n/a
| Number of people (representatives of corporate sector) engaged in the dialogue |  |  | 1.2. Activity Result: Dialogue with corporate sector conducted (both, public and private companies) to ensure knowledge and skills needed for green transition & increased climate ambition | Scenario for dialogues prepared with identified topics relevant for NDC implementation | On Track (In Progress) | The scenarios for the dialogue with the corporate corporate sector will be prepared in cooperation with the engaged project experts during the November 2022. | N/A | On Track (In Progress) | Draft concept note for each stakeholder consultation, including identifcation and description of issues to be adressed, information to share and goals of the meeting in terms of inputs to collect from stakeholders, are prepared. The 10 stakeholder dialogues will be held in a consecutive manner during January and February 2023. | n/a | Completed | The Project team developed scenario for corporate dialogue that includes relevant topics: 1) How do you understand the process of green transition for companies - what will your company and services (public energy production companies, public and private companies with high electricity consumption, industrial plants, small and medium enterprises, etc.) look like in 10, 20, 50 years, i.e. in a climate neutral era, 2) Do you already have relevant adaptation plans for a green just transition?, 3) Roadmap and planning including discussion of legislative/regulatory environment, standards and supply chains, as well as other major challenges, 4) The role of financial institutions, as well as the proactive role of the public and private sectors, 5) How do you see ensuring the prosperity and perspective of the company with minimizing the risk of job losses, gender inequality, etc, 6) Overview of new jobs and prequalification, whether new jobs are needed and how you see your company's participation in timely prequalification and education reform (at all levels); education and training, including the need to strengthen research and development activities, as well as innovation and entrepreneurship. | n/a
| Number of people (representatives of corporate sector) engaged in the dialogue |  |  | 1.2. Activity Result: Dialogue with corporate sector conducted (both, public and private companies) to ensure knowledge and skills needed for green transition & increased climate ambition | Compilation Report with examples of good practice from developed countries, including Japan, prepared | On Track (Planned) | The preparation of the Complilation report with examples of good practice from developed countries, including Japan is in progress and expected to be developed until the end of November 2022. | N/A | On Track (In Progress) | The preparation of the Compilation report with examples of good practice from developed countries, including Japan, is in progress. The Report will be completed until the end of January 2023. It will include examples and case studies from different countries and compile relevant information concerning targets groups, stakeholder engagement mechanisms, expected results and results achieved so far, observations etc. | n/a | Completed | The compilation report of international case studies (including Japan) to support Serbia’s transition to a low carbon development was developed and includes a choice of international case studies related to just transition. The case studies included in this report cover the following topics: 1) Mainstreaming (integration) of just transition provision in the climate change mitigation policy documents. 2) People centered just transition – ensuring people are at the core of the decision-making process, participating actively in the design of their future; 3) Political uncertainty: the effects on the community of political uncertainty /lack of a clear message or decision related to the transition. 4) Recovering from unplanned transition: sometimes action to ensure no one is left behind comes late, but it’s never too late. 5) Economic diversification: is key in communities dependent on fossil fuels (namely coal). 6) Private sector action: companies need not wait or rely on action by the government – their survival may depend on their own actions to ensure a smooth transition. 7) Small and medium enterprises transition: many impacted stakeholders are SMEs, many of them are only indirectly related to the fossil fuel sector, but they also employ people and may be at the heart of the economic diversification. | n/a
| Number of people (representatives of corporate sector) engaged in the dialogue |  |  | 1.2. Activity Result: Dialogue with corporate sector conducted (both, public and private companies) to ensure knowledge and skills needed for green transition & increased climate ambition | At least 10 targeted dialogues with representatives of selected companies organized | On Track (Planned) | This activity will be completed during November and December 2022. |  | On Track (In Progress) | The process of evaluation and selection of bidder who will implement this activity is ongoing. The 10 stakeholder dialogues will be rorganized in a consecutive manner during January and February 2023. | n/a | Completed | Instead of 10 separate stakeholder dialogues, project organized one high level event "Dialogue on the role of the economy in a just green transition" in Belgrade on 20th March 2023, in cooperation with Chamber of Commerce and Industry of Serbia and gathered more than 100 representatives from different sectors of the economy with the crucial role in the green transition: from the large manufacturers, big consumers of electrical energy, and industrial plants, to small and medium size enterprises, as well as representatives of unions, academic community and civil society. The dialogue started with the press conference and official speeches with the high level officials: H.E. Takahiko Katsumata, Ambassador of Japan to Serbia, Ms. Sandra Dokić, State Secretary of the Ministry of Environmental Protection,Ms. Jovana Joklsimovic, Assistant minister in the Ministry of Mining and Energy, Mr. Anas Quarman, Deputy Resident Representative UNDP Serbia and Mihailo Vesović, Director of the Sector for Strategic Analyses, Services and Internationalisation of the Chamber of Commerce of Serbia and continued with presentation of the conclusions from the already conducted dialogues and participatory dialogue on how to implement a green transition in practice to make it fair with focus on understanding how companies will prepare in the coming period as well as on overview at socio-economic aspects, needed jobs, qualifications, skills and education. | https://www.undp.org/serbia/news/dialogue-role-economy-just-green-transition https://bizinfo.rs/privreda-srbije-pred-teskim-izazovom-ko-ce-pretrpeti-najvece-promene/ https://www.krstarica.com/vesti/ekonomija/zelena-tranzicija-nezaustavljiva-potrebna-strategija-da-bi-bila-i-pravedna/ http://www.sattelevizija.com/vesti/jedna_vest/privreda_srbije_pred_teskim_izazovom__ko_ce_pretrpeti_najvece_promene_23321104523 https://beta.rs/zelena-srbija/zs-srbija/178353-ministarstvo-ekologije-vazno-da-privreda-pokaze-ambiciju-za-smanjenje-efekta-staklene-baste https://energetskiportal.rs/odrzan-dijalog-o-ulozi-privrede-u-pravednoj-zelenoj-tranziciji/ https://ekolist.org/dijalog-o-ulozi-privrede-u-pravednoj-zelenoj-tranziciji/ https://ekolist.org/dijalog-o-ulozi-privrede-u-pravednoj-zelenoj-tranziciji/ https://srpskaekonomija.rs/vesti/10/1//30720/Zelena-tranzicija-je-na%C5%A1a-nova-realnost-
| Just Transition Plan prepared | No | Yes | 1.3. Activity Result: Just Transition Plan to a Low Carbon Economy in Serbia developed based on conducted dialogues and shared among all stakeholders | Socio-economic analysis for the sectors and communities most impacted by NDC’s targets prepared | On Track (Planned) | This activity will be completed until the end of January 2023. |  | On Track (In Progress) | Socio-economic analysis for the sectors and communities most impacted by NDC’s targets will include desk research, statistical analysis as well as survey results of key sectors and communities that are affected by the green transition. The process of evaluation and selection of bidder who will implement this activity is ongoing and will be finalized in January 2023. Socio-economic analysis will be completed until the end of February 2023. | n/a | Completed | Socio-economic analysis for the sectors and communities most impacted by NDC’s targets were conducted, included desk research, statistical analysis as well as survey results of key sectors and communities that are affected by the green transition. The project area stretched out to the municipalities with the most carbon intensive economic sector activities. (municipalities of Kostolac, Lazarevac, Lajkovac, Obrenovac, Ljig, Ub, Svilajnac, Arandjelovac, Požarevac and Despotovac). It included: 1) Socio-economic structure (including demography, employment and unemployment by sector, economic activity by sector), 2) Energy sector overview, analysis, projections, 3) Legal and institutional framework for environmental protection and other relevant legislature, 4) Just Transition – Impacts and challenges (including territorial social and economic impacts,eEffects to local communities and underlying challenges, population most affected etc.). | n/a
| Just Transition Plan prepared |  |  | 1.3. Activity Result: Just Transition Plan to a Low Carbon Economy in Serbia developed based on conducted dialogues and shared among all stakeholders | Set of recommendations, with mitigation measures, prepared to ensure just transition for each sector, including gender analysis | On Track (Planned) | This activity will be completed until the end of February 2023. |  | On Track (In Progress) | The Report with recommendation of mitigation measures for ensuring the just transition for each sector, including gender analysis, will contribute to the development of the Just Transition Plan to a Low Carbon Economy. UNDP will prepare this report in cooperation with UNDP and relevant ministries (Ministry of Mining and Energy and Ministry of Environmental Protection). The process of evaluation and selection of bidder who will implement this activity is ongoing and the selection process will be finalized soon. This Report will be complited until the end of February 2023. | n/a | Completed | Set of recommendations, with mitigation measures including gender analysis was prepared as part of Socio-economic analysis. It includes socio-economic analysis based on the latest available data of the official statistics (results of the 2022 Census), such as: 1) employment and unemployment per gender; share in total employed population, 2) Businesses and entrepreneurs - gender structure, 3) At-Risk of poverty rate, by activity and gender. Some of the recommendations are: 1) Relevant ministries to prepare adequate inclusive strategies for women to the decent employment, education and health, 2) Initiate entrepreneurship as a possibility for more work. 3) Consider the possibility of establishing Training Centers for education in the local governments that will be most affected, given that these municipalities will gain experience in the green transition process that is important to share with other municipalities and individuals (for example, for organic food production, development of sustainable tourism, protection of natural entities) | n/a
| Just Transition Plan prepared |  |  | 1.3. Activity Result: Just Transition Plan to a Low Carbon Economy in Serbia developed based on conducted dialogues and shared among all stakeholders | Just Transition Plan to a Low Carbon Economy in Serbia prepared | On Track (Planned) | This activity will be completed until the end of February 2023. |  | On Track (In Progress) | Just Transition Plan to a Low Carbon Economy in Serbia will be prepared until the end of the project, based on the following: proceedings of the dialogues, Compilation Report with examples of good practices, Socio-economic analysis, Report with recommendations as well as the results of the project “Serbia Just Transition Diagnostics” (implemented by EBRD and the Ministry of Mining and Energy of the Republic of Serbia). International consultant for completion of this activity is contracted and prepares the draft document. | n/a | Completed | Based on the stakeholder engagement, starting in 2020 with the preparation of the report “Initiating the Just Transition in Serbia – Leaving no one behind in the coal intensive regions and communities in Serbia”, results of socio-economic analysis, conclusions and recommendations from the dialogues conducted with stakeholders at national, local and corporate level on green transition, Just Transition Plan to a Low Carbon Economy in Serbia was prepared. It includes: 1) The policy framework for the transition to a low carbon economy in Serbia, 2) Social, environmental and economic challenges and opportunities of the transition to a low carbon economy in Serbia, 3) Vision on a just transition to a low carbon development in Serbia, 4) Objectives of the plan, 5) Measures to achieve the objectives, 6) Monitoring and evaluation of the plan. The plan rely on the specific objectives, such as: 1) Diversify the economy of the communities, cities and regions dependant on coal and other fossil fuels 2) Promote the resilience of certain sectors of the economy more exposed to the impacts of the transition to a low carbon development 3) Increase access to labour markets by enhancing the match between skills needed and skills trained in the education system, including through reskilling of workers of carbon intensive sectors 4) Promote entrepreneurship, including of women, youth and of minorities 5) Create an environment conducive to investments supporting economic diversification and a just transition 6) Enhance Institutional Capacity for the Just Transition Process 7) Enhance awareness on Just Transition Developed "Just Transition Plan to a Low Carbon Economy in Serbia", combined with "Diagnostic Study of Just Transition in Serbia", implemented by EBRD, will support the Government of Serbia in defining the necessary comprehensive public policy document on green and just transition. | n/a
Country Output 2 Green and decarbonization technology investments and innovative business models in support of NDC implementation identified and deployed Global Output 1.1 Driving investment in clean energy | Number of applications to the Challenge Call received | NA | 20 | 2.1. Activity Result: Innovation Challenge Call prepared to support green transition and decarbonization for corporate sector | Innovation Challenge Call prepared (including elaboration of criteria) | Completed | The Project Team prepared the Challenge Call with evaluation criteria. The aim of the “Challenge Call for Innovative Solutions for Just Green Transition and Decarbonisation in Serbia” was to invite Serbian private and public sector companies to propose innovative solutions for the decarbonisation of the economy and industry. The Challenge Call in particular targeted businesses and sectors still relying on the intensive use of fossil fuels. The public call promoteed advanced business and technological solutions from developed countries such as Japan and EU member countries and strengthens business to business cooperation. Also, potential applicants was encouraged to consider integration of Just Transition elements into their proposals, such as reskilling, upskilling of the workforce, re-employment, support to affected regions etc. As evaluation criteria, among others, the following criteria are listed: estalished cooperation between companies from Serbia and companies from Japan and the European Union that apply the green business principles; does the project encourage the retraining of workers and the development of new skills that are needed for the modern labour market? Is the project’s impact on managing the social and economic effects of a just green transition of the coal regions demonstrated (if applicable). | https://www.undp.org/sr/serbia/news/otvoren-javni-poziv-za-inovativna-re%C5%A1enja-za-dekarbonizaciju-i-pravednu-zelenu-tranziciju, https://www.mre.gov.rs/aktuelnosti/vesti/otvoren-javni-poziv-za-inovativna-resenja-za-dekarbonizaciju-i-pravednu-zelenu-tranziciju | Completed | The “Challenge Call for innovative solutions for decarbonization that contribute to a just green transition in Serbia” was conducted in the period July 7th – August, 23rd, 2022. Through this public call, the Serbian public and private companies nominated 31 projects that promote innovative solutions for decarbonisation and expressed their interest to contribute to national and global efforts of decarbonization and green transformation as well as NDC implementation. The total investment value of all eligible applications (29 applications) amounts app 18,2 million USD, while the co-financing amount required from the project is over 2 million of USD. | Otvoren javni poziv za inovativna rešenja za dekarbonizaciju i pravednu zelenu tranziciju ¦ United Nations Development Programme (undp.org) | Completed | Completed in earlier quarters. | n/a
| Number of applications to the Challenge Call received |  |  | 2.1. Activity Result: Innovation Challenge Call prepared to support green transition and decarbonization for corporate sector | Innovation Challenge Call launched and at least two information sharing sessions organized | Completed | The Challenge Call was launched in the "Jevremovac” Botanical Gardens in Belgrade, on July, 7th, 2022, within the ceremony of celebrating traditional Japanese "Tanabata" festival and 140th anniversary of the establishment of official diplomatic relations between Japan and Serbia. Ambassador of the Japan, Minister of Labor, Employment, Veterans and Social Affairs as well as representatives of Ministry of Mining and Energy and Ministry of Environmental protection and other participants from Japanese and Serbian business sector, in accordance with Japanese tradition, wrote their wishes for a greener, healthier and economically stronger Serbia. During the Challenge Call which was opened until August, 23rd, three info days related to promotion of the Challenge Call and discussion with potential project promoters, were organized. First Info day was organized in Belgrade, UN House on July 20th with 23 participants, second info day was organised in the city of Nis within the Science and Technology Park Nis, on the 27th of July 2022 with 40 participants and third info day of the Challenge Call was organised in the city of Čačak within the Science and Technology Park Čačak, on the 8th of August 2022 with 18 participants. The Challenge Call was also promoted in cooperation with relevant Serbian partners: relevant ministries, Chamber of Commerce and Industry of Serbia National Association for Local Economic Development (NALED), Employers Union, as well as Japanese partners: Embassy of Japan in Serbia and Japanese Business Alliance in Serbia (JBAS). | https://www.undp.org/serbia/news/call-innovative-solutions-decarbonisation-contribute-just-green-transition-serbia https://www.undp.org/sr/serbia/news/traze-se-inovativna-resenja-za-dekarbonizaciju-koja-doprinose-pravednoj-zelenoj-tranziciji-u-srbiji | Completed | The Challenge Call was promoted particularly in cooperation with the relevant ministries, Embassy of Japan in Serbia and Japanese Business Alliance in Serbia (JBAS). | https://www.undp.org/serbia/news/call-innovative-solutions-decarbonisation-contribute-just-green-transition-serbia https://www.undp.org/sr/serbia/news/traze-se-inovativna-resenja-za-dekarbonizaciju-koja-doprinose-pravednoj-zelenoj-tranziciji-u-srbiji | Completed | Completed in earlier quarters. | n/a
| Number of applications to the Challenge Call received |  |  | 2.1. Activity Result: Innovation Challenge Call prepared to support green transition and decarbonization for corporate sector | Evaluation of the applications submitted to the Challenge Call completed and innovative solutions selected for further development in the acceleration process | Completed | In total, 31 project applications were received on the Challenge Call. The total investment value of all eligible applications (29 applications) amounts app 18,2 million of USD, while the co-financing amount required from the project is over 2 million of USD 2%). Available fund for co-financing at least 5 applications through the project is 600,000 USD. The received applications were evaluated by independent evaluators and results were presented on the Project Steering Committee meeting which was held on September, 19th, 2022. Project Steering Committee selected 21 project ideas which will start with the acceleration process through which the technical support and capacity building will be provided to the selected project teams. The project ideas which proposed collaboration with Japanese partners or companies are: 1) project "Toyo Tire Taiyo" solar power plant, company Toyo Tyre d.o.o.Serbia, 2) project: “Telemedicine for inflammatory bowel diseases”, company “Heliant” in cooperation with Japanese pharmaceutical company “Takeda”, 3) project “Introduction of a system of primary separation of packaging waste from municipal waste in the territory of the city of Pančevo”, company Public Utility Company "Higijena" Pančevo in cooperation with Japanese experts. | https://www.undp.org/serbia/news/selected-best-innovations-contribute-energy-saving-and-production-renewable-sources-waste-reduction-and-just-green-transition-serbia https://www.undp.org/sr/serbia/news/izabrane-najbolje-inovacije-koje-doprinose-ustedi-i-proizvodnji-energije-iz-obnovljivih-izvora-smanjenju-otpada-i-pravednoj-zelenoj | Completed | Out of 31 project applications received on the Challenge Call, 21 project ideas are selected by the Project Steering Committee (PSC) to start with the acceleration process. Technical assistance received through the acceleration provcess will assist the applicants to transform their project ideas and business proposals into deployable businesses that contribute to decarbonization of the economy. | https://www.undp.org/serbia/news/selected-best-innovations-contribute-energy-saving-and-production-renewable-sources-waste-reduction-and-just-green-transition-serbia https://www.undp.org/sr/serbia/news/izabrane-najbolje-inovacije-koje-doprinose-ustedi-i-proizvodnji-energije-iz-obnovljivih-izvora-smanjenju-otpada-i-pravednoj-zelenoj | Completed | Completed in earlier quarters. | n/a
| Number of applications to the Challenge Call received |  |  | 2.1. Activity Result: Innovation Challenge Call prepared to support green transition and decarbonization for corporate sector | Incubation/acceleration process conducted (mentorship, couching workshops, identifying co-financing sources for selected teams) | On Track (In Progress) | The acceleration process will last for approximately three months, until mid of December 2022 and will provide technical support and capacity building to the selected teams. Acceleration activities will support synergies between the decarbonization and just transition principles and help participants think systematically in a new manner. Also, the accelerator will also provide capacity building in cross-cutting topics. During the Acceleration phase, the project will also establish the collaboration with KAIZEN Service Provider concerning capacity building of Serbian companies. Implementing Japanese KAIZEN management methodology and tools will assist companies jumpstart their efforts to decrease their carbon footprint longterm through process and resources optimization. The accelerator will enable participants to turn their projects and businesses towards decarbonization. For easier communication with selected teams and document management, the Acceleration Online Platform – „BABELE“ was developed. The two project workshops were organized: “Project cycle management”, on October, 7th and “Strategic framework, mechanisms and principles of decarbonization”, on 13th, October 2022. The project teams were invited on the two online webinars, organized within the other accelerator: Webinar on integrating a gender approach into the project proposals, October, 11th and Webinar on the public performance and presentation of the project idea to potential donors, October 12th, 2022. |  |  | The project developed Accelerator for Decarbonisation and Just transition and provide series of capacity building workshops during the October and November 2022. The accelerator assisted selected SMEs to improve their performance and business proposals in the context of green transformation, triggered their active involvement, as well as it assisted SMEs in applying the principles of energy transition and socio-economic aspects of green transformation (including the creation of green jobs, fairness and inclusiveness). The following workshops have been organized: 26th September, 2022 - Kick-off meeting of project Accelerator 7th October, 2022 - Development of project ideas into project documents 13th October, 2022 - Decarbonisation – 1st part - International and National Legislative and Regulatory Framework, Principles and Mechanisms of Decarbonisation 19th October, 2022 - Decarbonisation – 2nd part - Carbon Footprint, Quantification Methodology and Examples 26th October, 2022 - Just Transitiont - Just Transition Concept, Best Practices and Project-Specific Quantification 24th October - 9th December, 2022 - KAIZEN certification program for 15 representatives of national administration and SMEs •Since the acceleration process supports synergies between the decarbonization and just transition principles and help the selected SMEs adopt new ways of systematic thinking, UNDP Serbia in cooperation with UNDP Bosnia and Herzegovina jointly procure services of KAIZEN Institute ltd Croatia, who implemented a series of trainings to SMEs in Serbia and in Bosnia and Herzegovina. The goals of the trainings was to increase capacities and skills needed for lowering CO2 emissions and taking a turn towards green(er) economy. This blended learning approach consisted of 6 modules combining e-learning, live session sprint workshops, practical assignments and included a live virtual tour to a Japanese Company Avex to showcase application of KAIZEN methodology and tools in practice. Upon finalizing the trainings, the KAIZEN Institute issued certificates to 5 training participants who successfully finished the training, with great expectations that the Japanese KAIZEN management methodology and tools will assist companies jumpstart their efforts to decrease their carbon footprint long-term through process and resources optimization. This new approach with strengthening regional cooperation and joint efforts in identification and implementation of technologies and innovative business models in those priority sectors that are most affected by increased climate ambition and mitigation of greenhouse gas emissions brings new energy in achieving a common goal of lowering regional CO2 emission and taking a turn towards green(er) economy. | CP Coordinators - 20_Kaizen training - All Documents (sharepoint.com); (1) UNDP in Serbia on Twitter: "Today we held kick-off mtng of Accelerator within "Just Green Transition &amp; Decarbonization in 🇷🇸" project. Tgt w @SerbianGov &amp; Embassy of Japan 🇯🇵 we are working to improve policy that promotes just &amp; green transformation of 🇷🇸 economy &amp; society. https://t.co/2rQ9KGpjRo" / Twitter; (20) Post ¦ Feed ¦ LinkedIn (1) UNDP Bosnia and Herzegovina – Posts ¦ Facebook; https://twitter.com/UNDPTokyo/status/1612641447890812928 https://www.facebook.com/UNDPTokyo/posts/pfbid02i5Ascmeg1eXJPqRyjAF9rpX8RTYgPkF4Pyws26PMZbZQBnT2qMpTg9HKUTwrmHsZl | Completed | Completed in earlier quarters. | n/a
| Number of most innovative decarbonization/green transformation solutions deployed | NA | at least 5 | 2.2. Activity Result: Financial agreements for the implementation of the projects and business solutions to support green transition and decarbonization for corporate sector completed | Most mature projects ready for co-financing selected | On Track (In Progress) | Only projects which successfully finalise the acceleration process (at least 5 innovative solutions and business ideas that combine several elements of green transformation and decarbonization) will be considered and selected for performance-based co-financing support. The implementation of selected projects will start this year and be finalized until February 2023. Depending on the majority, the project documents will be prepared in cooperation between the project teams and acceleration mentors. Some project which are ready for co-financing (such as project: "Toyo Tire Taiyo" solar power plant, company Toyo Tire Serbia d.o.o. Serbia, and project: Green approach: Supplying electricity to consumers in the Group's business system, generated from solar photovoltaic panels, company: Company for freight services and trade Milšped d.o.o. Belgrade) will be recommended for co-financing and presented on the Project Steering Committee meeting which will be organized at the end of October 2022. The rest of the project which are ready for the implementation until the end of February will be selected until the end of November 2022. |  |  | Based on the achieved scores as the outcome of the acceleration phase, and having in mind expected positive environmental and other impacts these projects will have, on 18th of November the PSC selected 8 best ranked projects to be further supported through the Performance Based Payment Agreements which will enable co-financing in total amount of 600.000 USD: 1. company: Toyo Tire Serbia Ltd Inđija, project: "Toyo Tire Taiyo solar plant", PBP Agreement value: 175.000 USD 2. company: Company for freight services and trade Milšped DOO Belgrade, project: "MILŠPED SOLAR POWER PLANT 2022", PBP Agreement value: 100.000 USD 3. company: UŠĆE SHOPPING CENTER d.o.o. Belgrade, project: "UŠĆE SHOPPING CENTER Compost machine", PBP Agreement value: 50.000 USD 4. company: Innovation Centre, Faculty of Mechanical Engineering, University of Belgrade, project: "Building R&D capacities for zero carbon emission IC engines (Internal Combustion Engines) in the transport sector", PBP Agreement value: 90.000 USD 5. company: Public utility company "HIGIJENA" Pančevo, project: "Introduction of primary separation of waste from communal waste on the territory of the City of Pančevo", PBP Agreement value: 70.000 USD 6. company: TRAKEN TECH Belgrade, project: "TRAKEN - Blockchain platform for aggregation and capacity utilization of renewable energy sources", PBP Agreement value: 40.000 USD 7. company: Center for Sustainable Development of Energy – CORE, Niš, project: "Photovoltaic power plant with chargers for electric cars - residential complex MAGDON NIŠ", PBP Agreement value: 40.000 USD 8. company: Heliant d.o.o. Belgrade, project: "Telemedicine IBD", PBP Agreement value: 35.000 USD | https://www.linkedin.com/posts/mpc-properties-bg_compostmachine-organicwaste-decarbonization-activity-7018220368876220417-Utwr?utm_source=share&utm_medium=member_ios https://www.instagram.com/p/CnMrxF5MxGc/?igshid=MDJmNzVkMjY= https://www.instagram.com/p/CnMf6EdtgqO/?igshid=MDJmNzVkMjY= | Completed | Completed in earlier quarters. | n/a
| Number of most innovative decarbonization/green transformation solutions deployed |  |  | 2.2. Activity Result: Financial agreements for the implementation of the projects and business solutions to support green transition and decarbonization for corporate sector completed | Low-Value Performance-based Payment Agreements issued (including due diligence process, defining outcomes and set of indicators which would trigger payments) | On Track (Planned) | At least five projects, that are technically and business-wise most mature and advanced, will be selected for co-financing, though Low-Value Performance-Based Payments Agreements (PBP Agreements). All PBP Agreements will be signed at last in December 2022. |  | Completed | UNDP Serbia signed PBP Agreements with selected companies in December 2022. Selected projects will reduce GHG emissions for more than 12845,95 t/CO2 by the end of the project. Decarbonization projects: 1. "Toyo Tire Solar Plant" project - building and installing a solar power plant total installed capacity of 7,2MW 2. "Milsped Solar power plant 2022" project - building and installing a solar power plant total installed capacity of 600kW 3. "Usce Shopping Center Compost Machine" project - installation of an ECOCREATION compost machine, type EC-100 4. "Building R&D capacities for zero carbon emission IC engines in the transport sector" project - building an R&D infrastructure for testing and developing novel technologies for future hydrogen-fueled IC engines by upgrading the existing ICE testing laboratory at the Innovation Center of the Faculty of Mechanical Engineering at Belgrade University 5. "Primary separation of waste in Pancevo" project - installation of scales on one of the new automakers, and purchase and distribution of DRY waste containers to the remaining 4 zones of Pancevo city 6. "TRAKEN" project - building a software infrastructure on Blockchain to facilitate the encrypted secure and transparent access to prosumer's smart meters and metering records 7. "Photovoltaic power plant with chargers for electric cars - residential complex MAGDON Nis" project - installation of 75kW of photovoltaic powerplant, installation of 3 chargers for electric and plug-in hybrid cars with individual power of 22kW 8. "Telemedicine IBD" project - this project will provide patients with inflammatory bowel diseases with a possibility of performing their check-ups with dedicated specialists over videocall | https://www.toyotires.eu/news/ceremony-observed-for-a-new-tire-plant-in-serbia; https://undp.sharepoint.com/sites/EU4GreenAgendainSerbia/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FEU4GreenAgendainSerbia%2FShared%20Documents%2FGeneral%2F13%2E%20JAPAN%20%2D%20Project%20Just%20Green%20Transition%2FOne%20Pageri&p=true&ga=1 https://www.ras.gov.rs/en/toyo-tire-breaks-ground-on-the-plant-in-serbia-380-million-investment https://energijabalkana.net/pocinje-izgradnja-prve-bifacijalne-i-trenutno-najvece-solarne-elektrane-u-srbiji/ https://rs.linkedin.com/company/toyo-tire-serbia-d-o-o https://bizportal.rs/energetika/srbija-na-pragu-energetske-revolucije-pocinje-izgradnja/ | Completed | Completed in earlier quarters. | n/a
| Number of most innovative decarbonization/green transformation solutions deployed |  |  | 2.2. Activity Result: Financial agreements for the implementation of the projects and business solutions to support green transition and decarbonization for corporate sector completed | Monitoring of the implementation of selected projects | On Track (Planned) | The selected projects will be implementing until the end of February 2023 and their progress will be monitored. They will contribute to the reduction of greenhouse gas emissions (GHG) and the reduction of environmental pollution, encourage the development of new branches of the economy as alternatives to the coal industry, and to support the retraining of workers from regions and sectors which are economically dependent on the intensive use of fossil fuels, in order to develop new skills needed in the modern labour market. |  | On Track (In Progress) | Implementation of the 8 projects are ongoing, 2 projects are finalized, 4 are in final implementation phase, while implementation of 2 remaining projects is in progress. The 6 finalized and almost finalized projects, together will increase national RES installed capacities for additional 7,8 MW of solar power, and contribute to decreasing CO2 emissions for 12563,45 tCO2/year. 61 participants have been trained through co-financed projects. Payments for the realization of first deliverables for the 6 projects have been realized in the total amount of 272.209 USD. |  | Completed | Remaining 6 projects are successfully finalized. Together, they will increase national RES installed capacities for additional 7,8 MW of solar power, and contribute to decreasing CO2 emissions for 12.745 tCO2/year. 110 participants have been trained through co-financed projects. Payments for the realization of all remaining deliverables for the 8 supported projects have been realized in the total amount of 327.791 USD. Main project results: 1. "Toyo Tire Solar Plant" project - solar power plant total installed capacity of 7,2MW was built and installed, 8 workers were trained for installation of solar panels, 5 engineers and 2 interns were trained employees for solar plant operation and maintenance. The produced electricity will primarily be used to power the plant's operations and minimize the use of electricity from the grid. The estimated reduction of emissions in first year of operation is 11.153 t CO2e. 2. "Milsped Solar power plant 2022" project - solar power plant total installed capacity of 600kW was built and installed, 3 employees were trained for supervision, control, and maintenance of the solar plants. The produced energy will be primarily used for charging systems of batteries used in forklifts and other means of internal transport. The company owns electric forklifts (75 units) in the batteries of which energy would be stored in the intervals when production is greater than consumption. The estimated reduction of emissions in first year of operation is 775 t CO2e. 3. "Usce Shopping Center Compost Machine" project - installation of an ECOCREATION compost machine, type EC-100, which digests any kind of organic waste, cellulose-based disposables, and various plastics within 24 hours, thus reducing weight and volume by more than 85%. The project will enable composting of 96,000 kg of organic waste on annual level, having a positive impact on environment and contributing to decarbonization process by transforming organic waste into a valuable resource such as compost. The machine with its technology decreases 94kg of CO2 / 1000kg of waste, EC - 100 machine that processes 100.000kg of waste annually reduces 10t of CO2 emissions per year. 15 workers were trained for the organic waste management, compost machine area maintenance, compost storage / packaging / distribution. 4. "Building R&D capacities for zero carbon emission IC engines in the transport sector" project - R&D infrastructure for testing and developing novel technologies for future hydrogen-fueled IC engines was built by upgrading the existing ICE testing laboratory at the Innovation Center of the Faculty of Mechanical Engineering at Belgrade University. It would be the first facility in Serbia with operational Hydrogen based ICE. Being in exclusive partnership with one of the largest and most significant powertrain development companies – with the AVL List GmbH (Graz, Austria) ICED Lab has already been providing tests and results for various technologies of the ICE of the future. The estimated annual emissions reduction is 74.56 tCO2e. Project enabled new 3 young researchers to be involved in the R&D activities of the zero CO2 emission ICE of the future and build a strong base of the Hydrogen ICE knowledge hub in Serbia. 5. 5. "Primary separation of waste in Pancevo" project - project enabled installation of scales on one of the new trucks, procurement of "DRY" waste bins, which were fitted with RFID chips for recording the mass of waste in order to measure the amount of waste per household and purchase and distribution of WET waste containers to the remaining 4 zones of Pančevo city. The project relied on experiences in waste separation from Japan. Informal collectors are also included, among whom there are many women and young people that through their representatives, organized into working groups, they collect packaging from households, transfer it from house to house and hand it over to PUC "Higijena" for money, and in "Higijena" through the implementation of projects in the field of recycling, the possibility of employment, i.e. project employment persons who did not have a job until then (fourteen persons in PUC so far). 6. "TRAKEN" project - software infrastructure on Blockchain was developed to facilitate the encrypted secure and transparent access to prosumer's smart meters and metering records. Project was implemented in cooperation with the SEEPEX a.d. Beograd, as a formal market operator for an organized electricity market/power exchange. As a pilot project, the TRAKEN project initially included 1 solar power plant of 8 kW under for proof of concept purposes. The impact of the project in terms of decarbonization is estimated to be at an annual level of 10.9 tCO2e. The project has onboarded 4 additional energy producers, all producing electrical energy from renewable sources, from solar energy. Project created job opportunities for two new employees at the Junior Blockchain developer position. 7. 7. "Photovoltaic power plant with chargers for electric cars - residential complex MAGDON Nis" project - built photovoltaic powerplant installed capacity of 75kW, 3 chargers for electric and plug-in hybrid cars with individual power of 22kW were installed. The power plant is connected according to EDS approval to the power system according to the "prosumer" model. The project will contribute to the preservation of the environment by reducing GHG emissions by 1,500 tCO2eq during the working life of the photovoltaic power plant. The professional training of the 2 personnel for the maintenance of the solar power plant and chargers were carried out in parallel with the construction process. 8. "Telemedicine IBD" project – project provided patients with Inflammatory bowel diseases with a possibility of performing their regular check-ups with their specialist via video-call that is fully incorporated in Heliant’s Health informational system. This kind of check-up is fully recognized as a regular health check up by Ministry of Health and is legally equal to check-up performed in person. The software is installed in 4 health institutions in Serbia. Training for 20 healthcare workers in 5 health institutions was performed. | https://www.toyotires.rs/sr_RS/news/serbian-solar-plant- https://www.linkedin.com/posts/toyo-tire-serbia-d-o-o_solarenergy-pvsolar-solarpower-activity-7018194199065853953-Wygk?utm_source=share&utm_medium=member_desktop https://www.instagram.com/p/CnMf6EdtgqO/?utm_source=ig_web_copy_link https://www.facebook.com/plugins/post.php?href=https%3A%2F%2Fwww.facebook.com%2Ftoyotireserbia%2Fposts%2Fpfbid02Q9r74JCA1bTPFEjLTgJMXECEoQtdcV1sXMt426w3C2taWC5MJFyJYJBwc2jVgM6bl&show_text=true&width=500 https://www.gradnja.rs/toyo-tire-indjija-solarna-elektrana-test-staza/ https://www.linkedin.com/posts/mt-komex_solarenergy-pvsolar-solarpower-activity-6996902124961869826-Qq5d?utm_source=share&utm_medium=member_desktop https://www.instagram.com/p/CoNXHH4qQEZ/ https://www.linkedin.com/posts/mil-ped_climatepromiseproject-justtransition-decarbonization-activity-7027331380522954755-BNKl?utm_source=share&utm_medium=member_android https://www.nedeljnik.rs/milsped-group-30-godina-na-putu-oko-sveta/ https://blok-vesti.com/milsped-neighborhood-30-godina-na-putu-oko-sveta/ https://plutonlogistics.com/zelena-logistika/milsped-postavlja-solarnu-elektranu-na-krovove-svojih-objekata/ https://www.ekapija.com/news/4032679/milsped-postavlja-solarnu-elektranu-na-krovove-svojih-objekata https://www.milsped.com/post/milsped-solar-plant https://www.linkedin.com/posts/mpc-properties-bg_climatepromiseproject-justtransition-decarbonization-activity-7034161998212784128-_t0d?utm_source=share&utm_medium=member_desktop https://www.linkedin.com/feed/update/urn:li:activity:703118197849002803 https://www.linkedin.com/feed/update/urn:li:activity:7025879842378133504 https://www.linkedin.com/feed/update/urn:li:activity:7018220368876220417 https://www.instagram.com/p/Co97e_psEC0/?igshid=MDJmNzVkMjY= https://www.instagram.com/p/CoowkxxMrYl/?igshid=MDJmNzVkMjY= https://www.instagram.com/p/CnMrxF5MxGc/?igshid=MDJmNzVkMjY= https://www.instagram.com/p/CoDE_J8s3vv/?igshid=MDJmNzVkMjY= https://m.facebook.com/story.php?story_fbid=pfbid0d61RDjUMyYUJc3w3L7Zo31yjszfr5RXdqBB2QP2LVqmHnjshqB1iAP6pTk2gzQDxl&id=100057059155338&mibextid=qC1gEa https://m.facebook.com/story.php?story_fbid=pfbid0xj4ysZMisbTw8XFLmDRNSe4m1YL5q4vXU3yXbJTAVLCWSki2m8VzyMSo8VnaghtSl&id=100057059155338&mibextid=qC1gEa https://m.facebook.com/story.php?story_fbid=pfbid0PCUTerYiKcqXdxpw2NmxqhqLEq2KYD8h4kh89jjb2BxxYeGZ4CgRmvrMuQYKFkvVl&id=100057059155338&mibextid=qC1gEa https://energetskiportal.rs/kompostiranje-kao-deo-skalirane-cirkularne-ekonomije/ https://www.linkedin.com/posts/energetski-portal-bb8720133_kompostiranje-kao-deo-skalirane-cirkularne-activity-7032030840133935104-haQ3?utm_source=share&utm_medium=member_desktop https://reciklaza.biz/drugi-pisu/kompostiranje-kao-deo-skalirane-cirkularne-ekonomije/ https://www.instagram.com/reel/CocuApOouJP/?igshid=MDJmNzVkMjY= https://www.instagram.com/p/CoXpbw3I2f0/?igshid=MDJmNzVkMjY= https://www.en.mas.bg.ac.rs/category/events-gallery/ https://www.en.mas.bg.ac.rs/building-rd-capacities-for-zero-carbon-emission-internal-combustion-engines-in-the-transport-sector/ https://m.facebook.com/story.php?story_fbid=pfbid02CsEzXWK3N9tT3h8EP5c88YXo7Hzn13N4fHGMgfyGgaWHFbWEYFNezA2oMRn8SqUWl&id=100057120683637&mibextid=Nif5oz https://m.facebook.com/story.php?story_fbid=pfbid02zx3tiqLN7sY1Zm2cf19vPdECRLVd7JBGWAGKQ3vi52rSooAKAG6gPzg2jPiuztn5l&id=100057120683637&mibextid=Nif5oz https://m.facebook.com/story.php?story_fbid=pfbid02cJMxxwdNmKfabuWBK5sSeATnKUWPsasXCHnajmWV9scXC1taGWtMwUQQN1VfuPvol&id=100057120683637&mibextid=Nif5oz https://www.pancevac-online.rs/253824/253824/ https://zeleniminuti.rs/zelena-ekonomija/reciklaza/item/1585-za-deo-stanovnistva-u-pancevu-stiglo-300-kanti-za-komunalni-otpad http://pancevo.mojkraj.rs/vesti/drustvo/item/17921-jkp-higijena-za-deo-stanovnistva-u-pancevu-stiglo-300-kanti-za-komunalni-otpad https://vojvodinauzivo.rs/jkp-higijena-za-deo-stanovnistva-u-pancevu-stiglo-300-kanti-za-komunalni-otpad/ https://epancevo.rs/jkp-higijena-za-deo-stanovnistva-u-pancevu-stiglo-300-kanti-za-komunalni-otpad/ http://pancevo.mojkraj.rs/vesti/drustvo/item/17914-jkp-higijena-u-pancevu-postavljene-kucice-za-privremeno-skladistenje-ambalaze https://zeleniminuti.rs/zelena-ekonomija/reciklaza/item/1584-u-pancevu-postavljene-kucice-za-privremeno-skladistenje-ambalaze https://epancevo.rs/jkp-higijena-u-pancevu-postavljene-kucice-za-privremeno-skladistenje-ambalaze/ https://vojvodinauzivo.rs/jkp-higijena-u-pancevu-postavljene-kucice-za-privremeno-skladistenje-ambalaze/ http://pancevo.mojkraj.rs/vesti/drustvo/item/17922-japanski-strucnjaci-preneli-u-pancevu-svoja-znanja-o-razvrstavanju-i-ekoloskim-navikama https://zeleniminuti.rs/zelena-ekonomija/reciklaza/item/1586-japanski-strucnjaci-preneli-u-pancevu-svoja-znanja-o-razvrstavanju-i-ekoloskim-navikama https://www.linkedin.com/company/19096211 https://www.linkedin.com/feed/update/urn:li:activity:7036286634333474816 https://twitter.com/Traken90473930/status/1630918391362887680 https://www.linkedin.com/feed/update/urn:li:activity:7037357515772182528 https://twitter.com/Traken90473930/status/1631593790682062849 https://heliant.rs/2023/02/13/projekat-telemedicine-doprinosi-smanjenju-emisije-co2/
| Number of public outreach events organized | NA | 2 | 2.3. Activity Result: Public outreach conducted to disseminate results and encourage replication of innovative solutions | Public outreach campaign conducted to disseminate results and encourage the replication of pilot projects (including the use of social media, TV, radio, articles in printed media and video coverage) | On Track (In Progress) | The project kick-off meeting was organized on April, 14th with the high level officials: H.E. Takahiko Katsumata, Ambassador of Japan to Serbia, Ms. Zorana Mihajlović, Deputy Prime Minister and Minister of Mining and Energy, Ms. Jovanka Atanacković, State Secretary in the Ministry of Mining and Energy, Ms. Sandra Dokić, Assistent Minister of Environmental Protection, Ms. Francine Pickup, UNDP Serbia Resident Representative. This project activity will be constantly implemented during the implementation of the selected projects in cooperation with the UNDP Communication team and company`s PR services. | Initiative for a Just Green Transition and Decarbonization in Serbia ¦ United Nations Development Programme (undp.org) | On Track (In Progress) | This project activities are being implemented for all selected projects with strong involvement of UNDP Communication team and company`s PR services. 77 articles have been posted on local and international printed and online media up until now. Launching of the just transition dialogue was announced on the Serbia's public broadcaster / RTS by UNDP Team Leader for Resilient Development. The project was included in 2 publications developed by UNDP Climate Promise initiative: 1) the Just Transition publication, and 2) MANGA Report ”Steps Ahead: Leveraging Nationally Determined Contributions (NDCs) to Achieve Net-Zero Emissions and Climate-Resilient Development”. In the context of the presentation of the project “Toyo Tire solar plant” during the opening of the new factory in Serbia, the project team has developed promo video material which presents the results of the project. | https://climatepromise.undp.org/news-and-stories/what-just-transition-and-why-it-important https://climatepromise.undp.org/research-and-reports/steps-ahead-leveraging-nationally-determined-contributions-ndcs-achieve-net Initiative for a Just Green Transition and Decarbonization in Serbia ¦ United Nations Development Programme (undp.org) https://www.undp.org/serbia/news/dialogues-just-green-transition-commence Otvoren javni poziv za inovativna rešenja za dekarbonizaciju i pravednu zelenu tranziciju ¦ United Nations Development Programme (undp.org) https://www.instagram.com/reel/CmMF7whsdTL/?igshid=YWJhMjlhZTc%3D https://www.linkedin.com/posts/undp-serbia_dijalog-o-zelenoj-tranziciji-gost-%C5%BEarko-activity-7014200934704537600-jUMJ | Completed | This project activities are being implemented for all selected projects with strong involvement of UNDP Communication team and company`s PR services. 118 articles have been posted on local and international printed and online media and more than 50 social media posts, up until now.. Press conference related to the just transition dialogue process was organized od 20th March. Report about the project and corporate dialogue event was presented on the prime time news “Dnevnik 2” on the Serbian Broadcasting Corporation Radio Television of Serbia. | https://climatepromise.undp.org/news-and-stories/what-just-transition-and-why-it-important https://climatepromise.undp.org/research-and-reports/steps-ahead-leveraging-nationally-determined-contributions-ndcs-achieve-net Initiative for a Just Green Transition and Decarbonization in Serbia ¦ United Nations Development Programme (undp.org) https://www.undp.org/serbia/news/dialogues-just-green-transition-commence Otvoren javni poziv za inovativna rešenja za dekarbonizaciju i pravednu zelenu tranziciju ¦ United Nations Development Programme (undp.org) https://www.instagram.com/reel/CmMF7whsdTL/?igshid=YWJhMjlhZTc%3D https://www.linkedin.com/posts/undp-serbia_dijalog-o-zelenoj-tranziciji-gost-%C5%BEarko-activity-7014200934704537600-jUMJ https://www.undp.org/serbia/news/two-local-level-dialogues-just-green-transition https://www.undp.org/serbia/news/dialogue-role-economy-just-green-transition
| Number of public outreach events organized |  |  | 2.3. Activity Result: Public outreach conducted to disseminate results and encourage replication of innovative solutions | 2 events to present project results to specific target groups organized (business community and local communities) | On Track (In Progress) | It is expecting that the first public event (as a high level event) will be organized in December 2022, during the opening of the "Toyo Tire Taiyo" solar power plant, company Toyo Tire Serbia d.o.o. Serbia in Indjija. The second event will be organized during January/February 2023. |  | On Track (In Progress) | Toyo Tire Corporation and its manufacturing subsidiary Toyo Tire Serbia LLC Belgrade organized ceremony of opening new factory in the City of Indjija in Serbia, including the installed solar power plant supported through this project. Approximately 40 high level guests, including Mr. Aleksandar Vucic - President of the Republic of Serbia, Mayor Vladimir Gak of Indjija City, and Mr. Takahiko Katsumata, Ambassador Extraordinary and Plenipotentiary of Japan to the Republic of Serbia. Public event for the presentation of the main project results will be organized until the end of the project. | https://www.toyotires.eu/news/ceremony-observed-for-a-new-tire-plant-in-serbia | Completed | Launching of the just transition dialogue was announced on the Serbia's public broadcaster / RTS by UNDP Team Leader for Resilient Development. Press conference related to the just transition dialogue process was organized od 20th March. Report about the project and corporate dialogue event was presented on the prime time news “Dnevnik 2” on the Serbian Broadcasting Corporation Radio Television of Serbia. Project results were presented during the "Dialogue on the role of the economy in a just green transition" held on 20th March 2023, which was gathered high level officials from the Embassy of Japan, Government of the Republic of Serbia, UNDP relevant institutions, as well as more than 100 representatives from different sectors of the economy with the crucial role in the green transition: from the large manufacturers, big consumers of electrical energy, and industrial plants, to small and medium size enterprises, as well as representatives of unions, academic community and civil society. | http://streaming.ninamedia.rs/uploads/2023/03/20/310E3804-534D-4DDC-84C0-C5C22131D496.mp4

## Drop-down (hidden)
Funding Source | Thematic Tagging | Region | Link | RBA | RBAP | RBAS | RBEC | RBLAC | Strategic Plan Indicators | Status of Activities | Core Indicator | Pillar
NDCSP-BMU | Net-zero Pathways (LTS/LEDS) | RBA | https://undocs.org/DP/RPD/RBA/4 | Output 3.1. Regional institutions capacities enhanced to advance effective climate adaptation, disaster risk reduction, early warning and resilience building policies, strategies, and programmes | Output 1.1. Enabling environment strengthened for planning and budgeting and to expand public and private sector investments and innovative financing, including through integrated national financing frameworks within national development frameworks, for prosperity and climate- and gender-responsive achievement of the SDGs | Output 1.1. The 2030 Agenda and other intergovernmentally agreed frameworks integrated in national and local development plans, measures to accelerate progress put in place, and budgets and progress assessed using data-driven solutions | Output 1.1: The 2030 Agenda, Paris Agreement and other intergovernmentallyagreed frameworks integrated in national and local development plans, measures to accelerate progress put in place and budgets and progress assessed using datadriven solutions. | Output 3.1: Development vision, strategies and decision-making aligned with climate change mitigation and adaptation, nature protection, disaster risk reduction and resilience objectives | 1.1.1 Number of countries that have development plans and budgets that integrate intergovernmentally-agreed frameworks across the whole-of-government: • 2030 Agenda for Sustainable Development • Paris Agreement • Beijing Declaration and Platform for Action • SAMOA Pathway • Istanbul Programme of Action for the Least Developed Countries • Vienna Programme of Action for Landlocked Developing Countries • African Union Agenda 2063 | On Track (Planned) | 1.1 Tonnes of CO2 emissions avoided or reduced | 1.1 Driving investment in clean energy sectors and infrastructure | Completed
NDCSP-BMZ | Adaptation and Resilience | RBAP | https://undocs.org/DP/RPD/RAP/4 | Output 3.2. Relevant stakeholders across Africa have the capacity to implement sustainable and green energy innovations | Output 1.4. Sustainable, scalable and innovative solutions and strategies for nature, climate and energy transformation strengthened through enhanced ‘climate promise’, nature-based solutions, and transitioning to clean energy and zero-carbon development. | Output 2.2. Capacities for conflict prevention, resilience and peacebuilding strengthened at regional, national, and subnational levels and across borders (Resilience includes risk-informed climate adaptation and mitigation, and environmental security). | Output 1.3: Transition to renewable energy accelerated capitalizing on technological gains, clean energy innovations and new financing mechanisms to support green recovery | Output 3.2: Mechanisms and tools to support financial strategies and budget allocations for the transition of key economic sectors towards green and climate-resilient development. | 3.1.1 Number of risk-informed development strategies and plans in place at: • regional level • national level • sub-national level • sectoral level | On Track (In Progress) | 1.2 Megawatts of renewable or low-emission energy capacity installed, generated or rehabilitated | 1.2 Support to Ministries of Energy, Finance, Environment and Planning to address key energy-related decisions on COVID-19 recovery
NDCSP-EU | Green Jobs and Just Transition | RBAS | https://undocs.org/DP/RPD/RAS/5 | Output 3.3. Member states have the capacity to prepare, communicate and maintain successive nationally determined contributions (NDC) in the context of the Paris Agreement | Output 3.2. Governments in Asia-Pacific at all levels have improved capacities, data and systems to better anticipate, respond to, recover from and mitigate multi-dimensional risks, shocks and crises, leaving no-one behind. | Output 3.1. Public and private investment mechanisms mobilized for biodiversity, water, oceans, and climate solutions. | Output 1.7: Public and private financing for the achievement of the SDGs expanded at regional levels | Output 3.3: Diverse stakeholders equipped with strengthened capacities and opportunities to foster sustainable development solutions and enhance their resilience | 3.1.2 Number of countries with early warning and preparedness measures in place to manage impact of conflicts, disasters, pandemics and other shocks | Delayed | 1.3 Number of beneficiaries with new access to green/sustainable energy (disaggregated by: male, female, youth (15-24) and indigenous people) | 1.3 Alignment of energy targets in NDCs with net-zero pathways
NDCSP-Spain | Youth | RBEC | https://undocs.org/DP/RPD/REC/5 | Output 3.4. Regional actors have improved capacity and relevant tools to access and manage natural resource assets, including water, forests, and land |  | Output 3.2. Energy gap reduced | Output 3.1: Institutional systems to manage multidimensional risks and shocks strengthened at regional levels |  | 3.1.3 Number of gender-responsive conflict sensitive development policies, cross-border initiatives, plans, or institutions in place to: • address conflict drivers • strengthen social cohesion • prevent risk of conflict, including climate security | Completed | 2.0 Number of direct beneficiaries with increased resilience to climate change (i.e more resilient physical and natural assets, diversified and strengthened livelihoods and sources of income, new/improved climate information systems) (disaggregated by: male, female, youth (15-24) and indigenous people) “X” | 2.1 Scaling-up adaptation, resilience, and disaster risk reduction tools and ensuring they are available to marginalized groups
CP1-Sweden | Gender | RBLAC | https://undocs.org/DP/RPD/RLA/4 |  |  | Output 3.3. Transition to renewable energy accelerated capitalizing on technological gains, clean energy innovations and new financing mechanisms to support green recovery. | Output 3.4: Natural resources protected and managed to enhance sustainable productivity and livelihoods |  | 3.2.1 Number of cross-border, regional, national, and sub-national policies, strategies, and action plans for conflict prevention and peacebuilding: • Prevention of violent extremism • Reconciliation • Reintegration • Climate change | Cancelled | 3.0 Number of green/sustainable jobs created (disaggregated by: male, female, youth (15-24) and indigenous people) | 2.2 Aligning targets in NDCs with national adaptation strategies and plans, including COVID-19 recovery
CP1-Sida | Indigenous People | [7 empty] | 4.1.1 Number of people directly benefitting from initiatives to protect nature and promote sustainable use of resources | n.a. | 4.0 Number of people trained/educated/informed through technical transfers, dialogues, workshops, campaigns, and other efforts (disaggregated by: male, female, youth (15-24) and indigenous people)
CP1-Core (11888, Trac etc.) | Climate Finance | [7 empty] | 4.1.2 Natural resources that are managed under a sustainable use, conservation, access, and benefit-sharing regime: • Area of terrestrial and marine protected areas created or under improved management practices (hectares) • Number of shared water ecosystems (fresh or marine) under new or improved cooperative management • Coverage and scale of ecosystems with enhanced resilience to climate change (hectares and kilometres) • Area of forest and forest land restored (hectares) • Areas of landscapes under improved practices, excluding protected areas (hectares) • Amount of chemicals reduced, disposed or avoided (metric tons) |  | 5.0 Number of development or sectoral policies/plans/budgets that integrate NDC targets or net-zero goals (Legislation)
CP1-BMZ-GreenRecovery | Circular Economy | [7 empty] | 4.2.1 Number of people directly benefitting from mechanisms for biodiversity, water, oceans, and climate solutions funded by public and/or private sector resources |  | 5.0 Number of development or sectoral policies/plans/budgets that integrate NDC targets or net-zero goals (Covid-19 response measures or assessments)
CP2-BMU | COVID-19 Recovery | [7 empty] | 4.2.2 Number of people with enhanced resilience of health, food, and water security, and/or livelihoods due to public and/or private resources |  | 5.0 Number of development or sectoral policies/plans/budgets that integrate NDC targets or net-zero goals (Development plans or roadmaps)
CP2-BMZ | Energy | [7 empty] | 5.1.1 Number of people, who gained access to clean, affordable and sustainable energy |  | 5.0 Number of development or sectoral policies/plans/budgets that integrate NDC targets or net-zero goals (Sectoral policies and plans)
CP2-Sweden | Forest | [7 empty] | 5.1.2 Number of people, who benefitted from services from clean, affordable and sustainable energy |  | 5.0 Number of development or sectoral policies/plans/budgets that integrate NDC targets or net-zero goals (National or sectoral budgets)
CP2-Sweden/Stockholm+50 | Food and Agriculture | [7 empty] | 5.2.1 Increase (in megawatt) in installed renewable energy capacity per technology: • Solar • Wind • Biomass • Hydro • Geothermal |  | 5.0 Number of development or sectoral policies/plans/budgets that integrate NDC targets or net-zero goals (Financial instruments or models)
CP2-Iceland | Oceans and Water | [7 empty] | 5.2.2 Amount of energy saved (in megajoule) |  | 5.0 Number of development or sectoral policies/plans/budgets that integrate NDC targets or net-zero goals (Subsidy reforms)
CP2-JSB | Other Nature-Based Solutions | [7 empty] | 5.2.3 Volume of investment leveraged to support green recovery (in US dollars) |  | 5.0 Number of development or sectoral policies/plans/budgets that integrate NDC targets or net-zero goals (Others)
CP2-UK | Urban | [9 empty] | 6.0 Number of partnerships with Japanese organizations (Private Sector)
Other | Transparency | [9 empty] | 6.0 Number of partnerships with Japanese organizations (JICA/University/technical experts)
| Climate Security | [9 empty] | 6.0 Number of partnerships with Japanese organizations (Other)