MAJOR RESULTS ACHIEVED (max 400 words)

Activities in Annual Work Plan for 2025

- 3-day training for postgraduate students – Gaziantep

- Training and panel on new legislation for wooden buildings - Ankara

- 2-day training for electrical and mechanical engineers - Kahramanmaraş

- 3-day introductory wood construction training for architects and civil engineers – May 2025

- Capacity Building for construction material suppliers on certification - Ankara

- 3-day introductory wood construction training for architects and civil engineers – June 2025

- Capacity Building for construction material suppliers on certification - Istanbul

- 3-day training for GDF’s civil engineers on design – Antalya

- EN 14080 (CE marking of structural timber) Training - Ankara

- Preparation of project video

- Report on Building Fire and Training on Building Fire Code

- Continuation of Co-Financed activities

Achievements in 2025

- A three-day training session for postgraduate students was successfully conducted in Gaziantep, drawing 54 participants (EV-01)

- In Ankara, a well-attended training and panel on the new wooden building legislation was held, engaging 109 participants. (EV-02)

- Electrical and mechanical engineers participated in a two-day focused training in Kahramanmaraş, accounting for 40 participants (EV-03)

- The project initiated a three-day introductory wood construction training in May 2025 for architects and civil engineers, with 22 participants. (EV-04)

- Capacity-building efforts focusing on certification for construction material suppliers took place in Ankara, attended by 51 participants. (EV-05)

- The introductory three-day wood construction training for architects and civil engineers was repeated in June 2025, once again instructing 22 participants. (EV-06)

- A capacity-building event for construction material suppliers, focused on certification, was organized in Istanbul. (EV-07)

- In Antalya, a three-day training on design principles was specifically delivered to 40 civil engineers from the General Directorate of Forestry (GDF). (EV-08)

- A specialized training session on EN 14080 (CE marking of structural timber) was carried out in Ankara, educating 30 participants. (EV-09)

- The project proceeded with the preparation and production of a project video. (EV-10)

- The project prepared a Report on Building Fire and delivered training on the Building Fire Code. (EV-11)

- The Co-Financed activities initiated by the project's main partner continued to make substantial progress throughout this period. (EV-12)

During 2025, the project maintained a strong focus on capacity-building, training, and awareness-raising, targeting a diverse group of stakeholders, including students in engineering and architecture, public institutions involved in building legislation, and private sector actors. Recognizing a major lack of technical knowledge, the team initiated legislative activities and conducted multiple field visits to General Directorate of Forestry (GDF) construction sites. These visits provided participants with valuable hands-on experience by showcasing some of the largest wooden construction projects ever undertaken in Türkiye. In parallel, GDF, the project's main co-financer, continued to make substantial progress on its own construction activities.

Component 1 - Legislation

The project faced significant procurement challenges, primarily delaying activities related to Outcome 1 (Enhanced Legislation and Regulation), including key reports and policy documents. As a result, most activities within this component were postponed by approximately one year.
Due to procurement challenges and administrative processes, the project fell behind its initial work plan schedule, particularly in activities under Outcome 1. However, mitigation measures have been initiated to recover progress in 2026. Despite these delays, progress was made through partial agreements with national consultants and academicians to support legislative revisions. A key priority was assisting the Disaster and Emergency Management Authority (AFAD) in revising Türkiye's Earthquake Regulation for Buildings, as current limitations impede the construction of wooden structures. The project formally requested this code revision and held an event to introduce new wooden construction legislation. While procurement difficulties persist in finalizing formal contracts, preliminary work has advanced, and an initial draft for revising the earthquake code is now prepared. Strengthening institutional capacity remains crucial for future strategy development.

Component 2 - Pilot Projects

The General Directorate of Forestry (GDF), as the project's primary co-financer, achieved a major milestone by completing and registering 36,987 square meters of wooden buildings, which included 142 personnel apartments and 11 office structures. These buildings, particularly important for resilience in earthquake-affected regions, marked Türkiye's most extensive use of Glued Laminated Timber (GLT) for the column-beam systems in multi-story construction to date. Furthermore, the initiative, which was supported by a previous UNDP-GDF project, successfully promoted the production and acceptance of local wooden materials under the Eurocode standards, a breakthrough with critical implications for future post-disaster rebuilding efforts.

Component 3 - Training and Awareness Raising

The project executed extensive capacity-building, training, and awareness activities, reaching a diverse group of stakeholders, including public institutions, academics, students, and the private sector. Officially recording 444 participants from 29 universities, multiple governmental authorities, and 56 private companies, the initiative also fostered collaboration with eight municipalities interested in co-financed projects. This inclusive approach significantly enhanced the wooden construction ecosystem of Türkiye.

Building on these achievements, upcoming project activities are now positioned to effectively assist the Government of Türkiye in reaching the main target: expanding the use of wood in the Turkish building sector.

PROBLEM SOLVING AND LESSONS LEARNED – max 150 words

The UNDP and GDF teams overcame initial procurement delays by forging a strong partnership, allowing them to initiate and implement activities effectively. This was achieved by prioritizing work that fit within GDF's procurement rules and breaking down tasks into smaller work packages for quicker execution.

STATISTICS ON END BENEFICIARIES (IF APPLICABLE) -max 150 words

Female 105

Male 405

Total 510

During year 2025, the project continued to deliver capacity-building, training, and awareness-raising activities targeting a broad range of stakeholders and beneficiaries. These included graduate and postgraduate students in civil engineering, architecture, and forest industry programs, public institutions involved in public building construction and related legislation, as well as private sector actors such as architecture and engineering firms, contractors, and construction material suppliers.

GENDER EQUALITY (Answer only if your Project is GEN2 and GEN3, check the GEN table sent to you) -max 300 words

During this reporting period, the project prioritized engaging with stakeholders through various meetings. While the wood sector in Türkiye is predominantly male, the project actively promoted the involvement of women in its meetings and activities. For instance, the trainings, capacity building and awareness raising activities conducted during 2025, achieved 105 female participants which is 21% of all participants. The project also highlighted the importance of gender-responsive approaches in sustainable construction, encouraging institutions and private companies to promote equal opportunities within their technical teams. Moving forward, the project aims to further increase women’s participation in training and decision-making processes, ensuring more inclusive sectoral development.

PARTNERSHIPS (please pay special attention if you have NGO and private sector partner or your Project promotes/expands partnerships beyond your implementing partners) -max 150 words

The project maintained a broad and inclusive approach by actively continuing its collaboration with a diverse range of stakeholders, including academia, NGOs (such as TORID and UAB), and the private sector. Critically, it engaged numerous public institutions to ensure comprehensive reach and support, including the Ministry of Education, the Ministry of Environment, Urbanization and Climate Change, and AFAD (Türkiye Disaster and Emergency Management Presidency). This inclusive strategy, which also involves entities like the Presidency of Strategy and Budget, TOKİ (Housing Development Administration), and the Grand National Assembly of Türkiye (TBMM), is foundational to the project's success and will continue as a key focus moving forward.

EVIDENCE SECTION

EV 1: Gaziantep Training Attendance Sheet

EV 2: Ankara New Legislation for Wooden Structures Training Panel Attendance Sheet

EV 3: Kahramanmaraş Training Attendance Sheet

EV 4: İstanbul Introductory Wood Construction Training-1 Attendance Sheet

EV 5: Ankara Construction Material Suppliers Capacity-building Training Attendance Sheet

EV6: İstanbul Introductory Wood Construction Training 2 Attendance Sheet

EV 7: İstanbul Construction Material Suppliers Capacity-Building Training Agenda

EV 8: Antalya Training for GDF’s Civil Engineers on Design Attendance Sheet

EV 9: Ankara EN 14080 Training Attendance Sheet

EV 10: Project Video

EV 11: Report on Building Fire and Training on Building Fire Code

EV 12: GDF Wooden Building Construction Tracking Table – September 2025