Annual Progress Report

United Nations Development Programme Albania

Skills Development for Employment Programme

Exit Phase 2023 - 2027

December 2025

| Reporting Period | 1st January – 31st December 2025 |
| --- | --- |
| Donor | Swiss Development Cooperation |
| SDC Domain | Outcome 1: People benefit from inclusive, effective, and democratic institutions. Outcome 2: Economic Development and Employment |
| Country | Albania |
| Project Title | Skills Development for Employment – Exit Phase 2023-2027 |
| Project ID | 01000856 |
| Outputs Strategic Plan and/or CPD Outcomes | Outcome 2: By 2026 innovative and integrated policy solutions accelerate sustainable, productive, and inclusive economic development, enhancing climate change adaptation and mitigation and transition to a green and blue economy. Output 2.4. Employment and Skills Development: Government institutions increased capacities to strengthen policies and services addressing skills mismatch and increase labour force participation and decent work, especially for young people, vulnerable groups, and the long term unemployed. |
| Implementing Partner(s) | Ministry of Economy and Innovation |
| Project Start Date | 3rd July 2023 |
| Project End Date | 30th June 2027 |
| Total resources required | 500,000 CHF |
| Revenue received | - Regular 1,733,387.07 USD - Other - Donor USD - Trust Fund Cost Sharing USD - Thematic Trust Fund C/S USD - Special Activities USD - EU funding USD - Total1,733,387.07 USD |
| UNDP Contact Person | Randi Davis Resident Representative UNDP Albania Email: randi.davis@undp.org |

Acronyms

| ALMP/ALMM | Active Labour Market Programme/Measure |
| --- | --- |
| AI | Artificial Intelligence |
| AQF | Albanian Qualifications Framework |
| CEP | Community Employment Programme |
| CSO | Civil Society Organization |
| EURES | European Employment Services - a network of employment services that facilitates the free movement of workers across the EU |
| ERP | Enterprise Resource Planning |
| GoA | Government of Albania |
| LFS | Labour Force Survey |
| MECI | Ministry of Economy, Culture, and Innovation |
| MEI | Ministry of Economy and Innovation |
| NESS 2030 | National Employment and Skills Strategy 2023-2030 |
| NAES | National Agency for Employment and Skills |
| NEET | Not in Employment, Education or Training |
| NE | Ndihma ekonomike (cash assistance) |
| NAVETQ | National Agency for VET and Qualifications |
| OJT | On-the-Job Training |
| PwD | Person with disability |
| RPL | Recognition of Prior Learning / see also VFNIL |
| SDC | Swiss Development Cooperation |
| SD4E | Skills Development for Employment Programme |
| SFUVET | Swiss Federal University for Vocational Education and Training |
| S4J | Skills for Jobs Project |
| SiD | Situationsdidaktik (situated-based didactics) |
| ToC | Theory of Change |
| UNDP | United Nations Development Programme |
| YG | Youth Guarantee |
| VET | Vocational Education and Training |
| VFNIL | Validation of Non-Formal and Informal Learning |

Table of Content

I.	Executive summary	5

II.	Background	7

A.	Labour Market Context	7

B.	Goal and Objectives for the SD4E Exit Phase	9

III.	Progress Review	10

A.	Progress review for actions under Outcome 1	10

B.	Progress review for Actions under Outcome 2	17

C.	Progress Review for Actions under Outcome 3	23

IV.	Project Risks and Issues	31

V.	Lessons Learned	32

VI.	Financial Status	34

VII.	Annexes	35

Annex 1: SD4E Yearly Plan of Operations 1st January – 31st December 2025	35

Annex 2: Minutes of Meeting of the Third Joint Steering Committee, December 11, 2025	43

# Executive summary

In 2025, the Skills Development for Employment Programme (SD4E) continued to support the Government of Albania in advancing an integrated reform agenda in employment, and vocational education and training (VET).

The year marked significant progress in strengthening sector governance, consolidating skills intelligence, enhancing the quality and relevance of VET provision, and improving the effectiveness of Active Labour Market Policies (ALMPs).

SD4E’s support was closely aligned with the implementation of the National Employment and Skills Strategy 2023–2030 (NESS 2030), the EU Reform Agenda under the Growth Plan for the Western Balkans, and Albania’s EU accession negotiations under Cluster 3 (Chapters 19 and 26).

The project delivered substantial contributions to improving sector governance, policy coordination, and the regulatory environment. A key achievement was the effective functioning of the Integrated Policy Management Group (IPMG) on Human Capital Development, supported by the regular functioning of the Thematic Group on Employment, Skills and Decent Work. These platforms enabled integrated cross-ministerial dialogue on employment, education, youth, social protection, gender equality, and child protection.

SD4E also played a central role in coordinating the annual monitoring of NESS 2030, supporting institutions to prepare the NESS Annual Progress Report 2024 and assess progress across priority measures.

Important advances were made in modernising the regulatory framework for VET. SD4E supported the Ministry and NAVETQ in the revision and adoption of the updated Quality Assurance Framework, including new self-assessment guidelines, a renewed accreditation order for VET institutions, and integrated processes reflecting the introduction of lifelong learning qualifications and Validation of Prior Learning (VNFIL/RPL). These reforms lay the foundation for a more diversified, quality-assured VET and lifelong learning system.

Although the formal implementation of the VET Optimisation Plan remained slow, the system saw meaningful progress through the expansion of dual VET (to 10 programmes across 14 providers in 2025–2026) and the inclusion of lifelong learning qualifications into the Albanian Qualifications Framework (AQF).

A major achievement during 2025 was SD4E’s contribution to strengthening skills intelligence at national level. Working jointly with NAES, NAVETQ, and INSTAT, SD4E supported the implementation of two flagship studies:

- Skills Needs Assessment (SNA) 2025, which surveyed 2,185 enterprises and provided updated insights on workforce structure, skills gaps, recruitment challenges, mobility, and training patterns. The SNA confirms persistent skills shortages, limited employer-VET collaboration, and structural recruitment difficulties, underscoring the need for targeted interventions in skills development, work-based learning, and lifelong learning.

- Digitalization Impact Assessment of Key Priority Sectors (tourism, energy, ICT), which mapped digital maturity levels across 100 companies. Findings indicate that most firms remain at early stages of digital transformation, with very low adoption of cloud computing, AI, robotics, or advanced data systems. The report underscores critical digital skills shortages and the need to strengthen both coding and non-coding digital professions to boost sector competitiveness.

Together, these studies expand the evidence base for policy making, support NESS 2030 monitoring, and guide future planning of VET and ALMP interventions.

In parallel, SD4E strengthened the institutional capacity of NAES to design and implement more effective Active Labour Market Programmes.

A crucial milestone was the Impact Assessment of ALMPs 2021–2024, which used quasi-experimental methods and beneficiary surveys to assess six programmes. The findings provide a solid evidence base for rebalancing the ALMP portfolio and improving targeting, employer engagement, and monitoring.

Additionally, SD4E provided targeted coaching and technical guidance to NAES, enabling the successful initial roll-out of the new ALMP for vulnerable jobseekers. This support allowed NAES to enrol its first 80 beneficiaries in 2025, meeting an important EU Reform Agenda milestone by June 2025.

SD4E significantly advanced Albania’s VET Quality Assurance and Development Framework. In collaboration with NAVETQ and the Ministry, the project supported a comprehensive review of QA instruments, including accreditation criteria, self-assessment guidelines, and the integration of new types of VET offer. By the end of 2025, 18 VET providers had participated in accreditation processes, demonstrating growing system commitment to a culture of continuous improvement.

Capacity building for NAVETQ was reinforced through a strategic partnership with the Swiss Federal University for Vocational Education and Training (SFUVET). In 2025, NAVETQ specialists completed a multi-module training programme on Situationsdidaktik (SiD) and symmetric pedagogy, and eight specialists participated in the Skills in Switzerland programme, gaining direct exposure to leading VET institutions and companies. This collaboration greatly strengthened national capacities in competence-based curriculum design, quality assurance, and international benchmarking.

SD4E also supported the preparation for implementation of Validation of Prior Learning (VNFIL/RPL) by contributing to the development and consultation with stakeholders of a national roadmap and supporting regulatory adoption. The updated Instruction No. 1109 (December 2024) and follow-up preparatory work in 2025 created the foundation for piloting validation of non-formal and informal learning (VFNIL/RPL) in selected occupations in the coming year.

# Background

## Labour Market Context

Labour market conditions improved, unemployment edged down, and employment rose. Service sector hiring offset job losses in agri- culture in the first quarter of 2025, lowering the unemployment rate and lifting the employment rate for both men and women. Albania’s economic growth is projected to moderate to 3.7 percent in 2025 and 3.5 percent in the medium term, according to the World Bank.

According the latest annual LFS report published by INSTAT, the labour force reached about 1.29 million people, of whom 1.18 million were employed and around 110,000 unemployed. For the 15–64 age group, the employment rate rose to 68.6%, while the unemployment rate (15–74) fell to 8.7%, a decrease of 0.9 percentage points year-on-year. Men remain more integrated into the labour market (employment rate 74.9%) than women (62.4%), resulting in a gender employment gap of 12.5 percentage points.

Despite these positive trends, several structural challenges persist. Youth unemployment (15–24) remains high at 22.8%, and 22.2% of young people aged 15–29 are neither in employment, education, nor training (NEET), with young women particularly affected by inactivity due to family responsibilities. Informal employment in the non-agricultural sector still accounts for 24.7% of total employment, indicating a sizeable segment of workers with limited protection and unstable working conditions. At the same time, 24.3% of the 15–64 population is economically inactive, with students, discouraged workers and women performing unpaid domestic work forming key sub-groups. Regional disparities are notable: prefectures such as Kukës and Gjirokastër record the highest employment rates, whereas Lezhë and Vlorë lag behind and show higher unemployment. Wage dynamics also shape the context for skills and employment policies. The average gross monthly wage reached 77,485 ALL in 2024, representing an increase of about 9.8% compared to 2023; however, 22.4% of employees still earn at or below the statutory minimum wage (40,000 ALL). The gender pay gap stands at 4.9%, with men earning on average nearly 5% more than women, and is particularly pronounced in industry and energy-related activities.

These patterns underline the importance of improving the quality and relevance of VET, promoting inclusive active labour market measures, and supporting better skills matching—especially for youth, women, and vulnerable groups—as Albania advances its EU integration and implements the National Employment and Skills Strategy 2023–2030.

## Goal and Objectives for the SD4E Exit Phase

Based on the conceptual framework of the SDC’s scoping study on consolidation of Swiss VET portfolio in Albania, the country sectorial strategic framework and the results of bilateral consultations with the national partners and stakeholders, a series of working sessions with the SD4E team and S4J team took place, to jointly develop a draft programme design for both projects exit phase. The specific focus of the working sessions was to increase efficiency of collaboration between the two projects, identify areas of mutual reinforcement, identify key activities necessary to safeguard transfer and sustainability, and strengthen meso-level in terms of capacity building and organisational structures/processes.

The conceptual framework provided a heuristic framework to identify progress achieved in different intervention areas and options and potential priorities for exit phases of both projects. Having these pre-conditions identified, the statements were turned into Outputs and Activities which were, in the last step reshuffled in logical pathways to ensure the achievement of the outcomes and long-term goals, intervention areas.

The overall aim of the SD4E Exit Phase is for the Albanian VET and Employment Promotion system contribute to sustainable and inclusive economic and social development in the country.

The project goal is for young and adult women and men to have increased employability due to improved attractiveness and labour market relevance of an inclusive Employment and VET offer.

The project proposes a holistic approach that aims to strengthen the sector’s policy and monitoring framework, while at the same time support to the beneficiaries through capacity building and adoption, ownership and internalization of various system, standards and instruments contributing to the efficiency, transparency and accountability of the VET and employment service providers.

In line with this rationale, SD4E support is proposed to contribute to the following three outcomes:

Outcome 1: National institutions effectively implement the sector’s policy framework and optimize delivery with innovative tools and financing instruments.

Outcome 2: National institutions deliver individualised and data-driven employment policies and ALMMs, in partnership with the labour market ecosystem.

Outcome 3: Public and private actors involved in the VET system use a standardised and harmonised quality assurance and development framework for self-assessment, accreditation, inspection, and monitoring.

# Progress Review

## Progress review for actions under Outcome 1

Outcome 1: National institutions effectively implement the sector’s policy framework and optimize delivery with innovative tools and financing instruments.

During 2025, activities under this outcome focused on strengthening policy coordination for human capital development, supporting the implementation and annual monitoring of the National Employment and Skills Strategy 2023–2030 (NESS 2030), and further consolidating the regulatory framework needed to advance key reform priorities. This includes enhancing the quality assurance for VET through improved regulatory framework on inspection, accreditation, and self-assessment of VET providers, thereby setting the ground for enabling a more diversified and quality-assured VET and lifelong learning offer that better serves both learners and the labour market.

| Outcome 1: Status of the outcome indicators |  |  |  |
| --- | --- | --- | --- |
| Targets | Indicator status (Fully/Partially/ Not achieved) | Explain the status of the indicator | Means of Evaluation/ Verification |
| Contribution towards a more inclusive or more labour market relevant Vocational Education and Training (VET) system by supporting the implementation of 5 out of 16 NESS 2030 priority measures | Partially achieved. | Through its support to dual VET and quality assurance regulatory framework, SNA and digitalization, RPL/lifelong learning, and ALMP implementation, the SD4E project directly contributes to at least seven priority measures of NESS 2030. | NESS 2030 SD4E Annual Progress Report |
| Qualitative assessment of the legislative framework (incl. by laws) Baseline: Incomplete framework; Target: Framework complete and approved. | Achieved | During 2025, the model, standards/criteria for the accreditation were thoroughly reviewed and the new regulatory framework was accordingly adopted | Official Gazette |
| Percentage of optimisation plan / roadmaps implemented by their institutions. Baseline: 0% (2022); Target: 100% (2027) | 12% Not yet achieved. | The implementation of the VET optimisation experienced a slowdown during 2024 due to intensification of other priorities | NESS 2030 Annual Progress Report |

Output 1.1: National institutions have improved capacities to implement and improve the strategic and regulatory package for VET and employment promotion.

In line with its Annual Work Plan, the SD4E project continued to support and coordinate the monitoring of annual progress in implementing the National Employment and Skills Strategy 2023–2030 (NESS 2030). The NESS 2030 Annual Progress Report 2024, prepared jointly by the implementing institutions and the SD4E project, highlights solid progress across several strategic areas, supported by improved labour market outcomes and advancements at the priority-measure level.

In 2024, the employment rate for the 15–64 age group increased to 68.3%, surpassing the 2026 target, while the gender employment gap narrowed to 13%, already meeting its 2026 objective. Youth unemployment declined to 22.5%, reflecting steady movement toward the Strategy’s 2030 targets.

Implementation at the level of priority measures was assessed as generally satisfactory. Significant progress was made in reducing skills mismatches, strengthening labour market information systems, and enhancing employment services. Advances in employer engagement, labour market analysis, and the expansion of active labour market programmes contributed to a more effective and inclusive labour market. Priority measures under Policy Goal 2—particularly those related to mediation, profiling, and targeted support for jobseekers—also moved forward, although further efforts are required to address long-term unemployment.

Reform efforts in the Vocational Education and Training (VET) system continued, though several priority measures were identified as requiring accelerated implementation. These include the roll-out of the accreditation system, further development of the Albanian Qualifications Framework, and strengthened governance of inspection and self-assessment processes. Priority measures on lifelong learning and the validation of non-formal and informal learning are expected to enter full implementation during 2025–2026.

Overall, implementation of the NESS 2030 in 2024 was assessed as satisfactory, with key indicators progressing in line with, or surpassing, the targets set for the mid-term horizon toward the Strategy’s vision of Quality Employment and Lifelong Skills for All.

The NESS 2030 Annual Progress Report 2024 also provided an important opportunity for reflection, helping to shape and prioritise reform efforts undertaken in 2025.

Another key milestone for the country was the adoption and implementation of the EU Reform Agenda within the framework the EU Growth Plan for the Western Balkans.

The SD4E project has been instrumental in designing and advancing the implementation of several actions within the Human Capital Pillar of the EU Reform Agenda. This included strengthened implementation of Active Labour Market Programmes, progress on the Albanian Qualifications Framework, and the advancement of the Validation of Non-Formal and Informal Learning, supported by an enhanced accreditation and quality assurance regulatory framework.  Based on the collaboration between the project and the two executive agencies, two key actions: the adoption of the regulatory framework for the implementation of validation of prior non-formal and informal learning and implementation of an active labour market programme on intensive counselling, were assessed as fully achieved by the European Commission, also enabling the disbursement of related tranche payments by the European Commission within the Growth facility framework.

With SD4E’s consistent coordinating and facilitating role, the Integrated Policy Management Group (IPMG) on Human Capital Development continued its regular activity during 2025. As a result, two meetings were held, respectively in July and early December 2025. In addition, and complementary to the meetings of the IPMG, the Thematic Group on Employment, Skills and Decent Work convened regularly in June and November 2025.

During 2025, the Integrated Policy Management Group (IPMG) on Human Capital Development advanced a broad and interconnected reform agenda spanning employment, skills, education, social protection, gender equality, and child protection. The two high-level meetings of the year demonstrated strong cross-ministerial coordination and significant progress in aligning national policies with EU accession priorities. In July, the IPMG reviewed major sectoral developments, notably the opening of negotiations for Cluster 3, covering Chapter 19 (Social Policy and Employment) and Chapter 26 (Education and Culture). The adoption of the Operational Programme “Youth Employment” (IPA 2025) was presented as a core instrument for strengthening youth labour market integration and supporting EU-aligned reforms. Throughout the year, the IPMG served as a platform for inter-ministerial presentation and consultation of several key draft laws, including the draft Law on Gender Equality (MHSP) – addressing equal opportunities and gender mainstreaming; the proposed amendments to Law 15/2019 “On the Promotion of Employment” – modernizing employment services and aligning active labour market policies with EU standards; the draft Law on Alternative Care in the Family, the draft Law on Prevention and Protection from Domestic Violence, and the National Action Plan for the European Child Guarantee – expanding protections for children, families, and survivors of violence. The Ministry of Education and Sports presented important reforms related to Continuous Professional Development of Teachers, digitalization of pre-university education and education of students with disabilities and emerging priorities for inclusive teaching and learning. Including detailed review of implementation progress of sectoral Strategies and National Plans, including the annual review of NESS 2030 and the presentation of the implementation progress of the National Youth Guarantee Plan, reaffirmed the IPMG’s role in overseeing evidence-based implementation and ensuring coherence across policies.

The IPMG platform was utilized to promote integrated social protection approaches, such as the Joint UN and World Bank initiative on building a disability-inclusive social protection system and improving integration between social assistance, social services, and social insurance.

Overall, the IPMG’s 2025 work reflected a consolidated, multisector effort to deepen EU alignment, modernize employment and education systems, strengthen social protection, and promote equality and inclusion. The group provided an effective governance platform for policy dialogue, monitoring, and cross-institutional coordination—positioning human capital development as a central pillar of Albania’s EU integration and socio-economic transformation.

| Status on Output 1.1. Indicators |  |  |  |
| --- | --- | --- | --- |
| Indicator | Target 2025 | Status (Fully/Partially/ Not achieved) | Means of Verification |
| Mechanisms developed to monitor the sector strategic framework Baseline: No Target: Yes | Yes | Fully Achieved | NESS 2030 M&E Framework Document NESS2030 Annual Progress Report 2023 NESS 2030 Annual Progress Report 2024 |
| Number of meetings per year of the Integrated Policy Management Group (IPMG) (coordination mechanism) Baseline: 0 Target: 8 (2 annually) | 2 (5 cummulative 2nd half 2023, 2024, and 2025) | Fully Achieved | Agenda + Minutes of Meetings of IPMG “Human Capital Development” and Thematic Group “Employment, Skills & Decent Work |
| A roadmap for the advancement of the VET reform beyond 2026 is agreed by all VET actors. Baseline: No; Target: Yes (2026) | N/A | Not achieved | VET Review report Roadmap submitted and endorsed by key stakeholders |

Output 1.2: Key actors support a participatory approach in the implementation of an optimized VET system.

Optimisation of the VET providers’ network

In 2025, progress on the direct implementation of the Optimization Plan adopted in 2022 remained limited, resulting in a temporary stagnation of the formal optimization process. Nonetheless, substantial advances were made in diversifying and modernizing the VET offer. Notably, the dual VET initiative expanded significantly during the 2025–2026 academic year, reaching 10 VET programmes across 14 VET providers, while the inclusion of lifelong learning qualifications—specifically short-term training programmes offered by non-public VET providers—into the Albanian Qualifications Framework marked an important step toward broadening learning pathways and strengthening system responsiveness.

Against this backdrop, the SD4E Programme concentrated its efforts on supporting the establishment of the inspection unit within the Ministry and on reviewing quality assurance processes to ensure that both lifelong learning qualifications and the validation of non-formal learning are delivered in a quality-assured manner. Working jointly with NAVETQ and NAES, the Programme contributed to identifying the key milestones required to advance the optimization process.

The partners agreed that strong institutional structures within optimized VET providers, together with the consolidation of a coherent remuneration and career system for all professional categories (management, teaching staff, development units, VNFIL-related personnel, etc.), are essential prerequisites to transforming the optimization into a dynamic and continuous quality development process, rather than a purely structural merging of institutions. Moreover, successful implementation requires sustained political commitment, coordinated action, and engagement from all partners at both central and provider levels.

The SD4E Programme remains committed to supporting the optimization agenda, while acknowledging that its effective implementation ultimately depends on the continued willingness, ownership, and commitment of key national stakeholders.

With regard to innovative financing mechanisms for employment and skills development, UNDP Albania—through the SD4E programme—was approached by the Government of Albania to explore models that mobilize additional resources and encourage private sector participation in skills development. In line with its commitment to expanding private sector engagement in VET delivery, a prerequisite for building sustainable and industry-responsive systems, SD4E examined opportunities to leverage diversified funding sources and to introduce new financing instruments capable of channeling and managing resources more effectively.

Among the policy options proposed were training funds, widely used internationally as dedicated financing instruments for skills development. A training fund constitutes a stock or flow of financing outside standard government budgetary channels, earmarked specifically for developing productive, work-related skills. Such funds aim to strengthen productivity, competitiveness, and income-generating opportunities for enterprises and individuals by offering access to relevant training. They are often financed through levies or contributions from enterprises and employees, but may also be supplemented by public subsidies, donor financing, or philanthropic sources.

However, the creation of an extrabudgetary training fund requires a significantly higher level of political negotiation, social partner consensus, and institutional commitment. Levy-grant systems or cost-sharing mechanisms can only succeed when there is strong willingness from enterprises—and, where relevant, trade unions—to contribute financially and engage in structured social dialogue. Such arrangements must be anchored in robust tripartite or sectoral bargaining processes to ensure shared ownership, transparency, and trust.

The Ministry of Economy, Culture and Innovation’s initiative to establish a National Training Fund under the Employment Promotion Law has faced legal and structural constraints. According to the Law on the Management of the Budgetary System, any Special Fund must be created through a separate, dedicated law initiated by the Minister responsible for finance, rather than through amendments to existing legislation. This legal requirement underscores the complexity of moving toward an extrabudgetary funding model.

Against this backdrop, the SD4E programme remains keen to support and further explore innovative financing opportunities that can advance employment and skills development priorities. At the same time, SD4E recognises that the successful creation of such mechanisms depends on deeper policy dialogue, commitment from the responsible Ministry, and strong bargaining processes with social partners. In this context, SD4E will continue to facilitate evidence-based dialogue, support institutional coordination, and encourage internal deliberations within the Government-led working groups.

| Status on Output 1.2. Indicators |  |  |  |
| --- | --- | --- | --- |
| Indicator | Target 2025 | Status (Fully/Partially/ Not achieved) | Means of Verification |
| Number of roadmaps / optimisations plans for VET providers reorganisation developed Baseline: 0 (2022); Target: 31 (2026) | 6 | Not achieved | Roadmaps |
| 1.2.2 Sectoral INFF as financing mechanism developed and consulted Baseline: No; Target: Yes (2025) | No | Not Achieved | SD4E Progress Reports Policy Notes |
| Number of consultation meetings in the frame of the optimization process as per the consultation process as per guidelines. Baseline: 0 (2022); Target 10 (2026) | 2 | Not achieved |  |

Output 1.3: Labour market ecosystem engages to promote VET and Employment offer at the national and regional level.

No activities were carried out during the reporting period.

| Status on Output 1.3. Indicators |  |  |  |
| --- | --- | --- | --- |
| Indicator | Target 2024 | Status (Fully/Partially/ Not achieved) | Means of Verification |
| Increased engagement of the private sector beyond the delivery of WBL and percentage piloted with NAES Baseline: No Target: Yes (2025) | N/A | Not achieved | NAES Annual Report NESS 2030 Annual Progress Report |
| Number of national dialogues on VET and Employment Baseline: 1 (2022) Target: 3 (2027) | 1 | Achieved | NESS 2030 Annual Report National VET Conference Proceedings |

## Progress review for Actions under Outcome 2

Outcome 2: National institutions design and deliver individualised and data-driven employment policies and ALMPs, in partnership with the labour market ecosystem.

Activities under this outcome focused on strengthening skills intelligence to better inform decision-making on the key priorities of Albania’s employment and skills development reforms. Parallel to this, the programme continued to build the capacities of the National Agency for Employment and Skills (NAES) at central, regional, and local levels to ensure more efficient and effective implementation of Active Labour Market Programmes.

Throughout 2025, SD4E worked intensively with the Ministry, NAES and NAVETQ to advance both objectives, supporting the consolidation of a more robust skills intelligence system and promoting greater use of evidence in shaping employment and skills development policies.

| Outcome 2: Status of the outcome indicators |  |  |  |
| --- | --- | --- | --- |
| Targets | Indicator status (Fully/Partially/ Not achieved) | Explain the status of the indicator | Means of Evaluation/ Verification |
| Percentage of unemployed jobseekers benefiting from ALMMs, by vulnerable group vs. registered unemployed Baseline: 17,8% (2022); Target: 25% (2026) Women baseline: 16,3% (2022): Target: 28% (2027) PwD: 55,3% (2022): Target: 56% Roma & Egyptians: 7,8% (2022) Target: 10% (2027) NE: 5,5% (2022) Target: 13% | The target for 2025 was partially achieved |  | NAES, Administrative Data NAES, Administrative Data |
| Number of Skills Needs Assessment (SNA) led by national institutions that are published. Baseline: 0 (2022) Target: 3 (2027) | Partially achieved | The SNA 2024/5 has been carried out during 2025 | Published SNA and official records. |

Output 2.1: Intelligence on skills development and employment in Albania is regularly available to policy makers.

During 2025, the SD4E programme prepared two key assessments to analyse the demand of the labour market across economic sectors (Skills Needs Analysis 2025) and the assessment of the impact that digitalization has on key priority economic sectors, with a special focus on the exposure of the Albanian economic sectors to digitalization professions.

Digitalization Impact on Key Priority Sectors

In collaboration with Alcognition GmbH, SD4E carried out a comprehensive assessment of the digital maturity of three priority sectors of the Albanian economy—tourism, energy, and ICT—as part of its contribution to strengthening skills intelligence, supporting the digital transition, and informing VET and workforce development policies.

The study evaluated the extent to which companies in the three sectors have been integrating digital technologies into their operations, services, and organizational processes. It assessed digital maturity across four levels—from basic digital infrastructure to fully digital organizations—based on a structured survey of 100 companies (50% tourism, 20% energy, 30% ICT) and in-depth interviews.

The research aligns with Albania’s commitments under the EU Digital Strategy and the 2030 Digital Compass, while responding to skills shortages and labour market needs identified across sectors.

Across all sectors, most companies are positioned at Level 1 or Level 2 of digital maturity, indicating early or intermediate progress. Tourism and energy companies show very limited advancement beyond basic digital infrastructure, while the ICT sector is more developed but not uniformly so.

Key cross-sector findings include 88% of companies have a website and 85% report high use of mobile devices with internet access; over 50% of companies have no knowledge of digital business models; over 70% do not use cloud or edge computing, and 84% have never implemented projects using robotics, IoT, predictive analytics, or machine learning; over 70% do not use AI in their products or services.

Sector specific findings highlight that tourism businesses widely use websites, social media, and booking platforms but remain largely non-digitalized internally. There is minimal use of Enterprise Resource Planning (ERP) systems, AI-enabled tools, cloud services, or advanced data analytics. Digital skills gaps are significant, and structured digital training is rare.

The energy sector shows the lowest digital maturity: nearly 30% of companies are non-digitalized, and none have reached higher digital maturity levels (3 or 4). Use of AI, cloud, edge computing, predictive analytics, and Internet of Things (IoT) is extremely limited. Workforce ageing and insufficient digital competencies further constrain transformation.

While the ICT sector displays higher digital maturity overall—including the only company reaching Level 4—it faces acute shortages in specialized digital profiles (AI, DevOps, cybersecurity). High turnover, limited research & development investment, and uneven internal capabilities hinder sustained advancement.

Digital skills shortages remain a system-wide challenge. Most training is informal or absent, with employees learning through peers or practice. There is a severe shortage of non-coding digital professions (e.g., product owners, UX designers, technical writers), which are essential for digital transformation processes.

A mature digital ecosystem requires balanced development of coding and non-coding digital professions—currently underdeveloped in Albania.

The Skills Needs Assessment (SNA) 2025 represents the fourth national survey implemented as part of Albania’s skills intelligence system and is one of the most comprehensive instruments for assessing labour market dynamics and employer needs. Building on the methodologies established in previous cycles and refined through continuous collaboration with NAES, NAVETQ, INSTAT, and the SD4E team, the SNA 2025 provides an updated and statistically robust picture of the structure of enterprises, employment trends, skills gaps, recruitment challenges, and training patterns across the Albanian economy.

A strengthened evidence base for policy-making

The 2025 SNA surveyed 2,185 enterprises, representing 75.9% of the initial sample, and generated estimates for a final Frame of 53,982 active enterprises employing 504,572 people. Compared to SNA 2017, the results indicate a 26.1% increase in the workforce, driven by both employment growth and job formalization. The Central region continues to dominate Albania’s economic landscape, hosting 64.3% of all enterprises and 70.2% of the workforce.

The survey confirms substantial sectoral shifts: while most sectors experienced employment growth, the strongest contributions came from Construction and Accommodation and Food Services, while Real Estate and Professional and Technical Services showed the fastest relative expansion.

Persistent skills gaps and structural challenges

The SNA 2025 highlights the continued misalignment between skills supply and demand. Although only 10.3% of the workforce is estimated to lack essential skills, a significant 43.5% of enterprises report skill deficiencies among their staff. The most frequently lacking competencies include professional skills (41.4%), organizational skills (40.8%), and teamwork abilities (36.1%).

Employers also continue to voice concerns about inadequate qualifications, low labour supply, and high employee mobility. Notably, 12.7% of employees left their jobs over the past year, including 10,551 individuals who emigrated—indicating sustained outward labour mobility.

Recruitment difficulties and limited collaboration with the VET system

Recruitment remains a major challenge: 31.7% of enterprises reported vacancies, and 94.9% faced difficulties filling them. Most enterprises rely primarily on personal networks (70.5%) to recruit staff, while employment portals remain a first step but are insufficient on their own.

Engagement with the VET system remains limited. 61.2% of enterprises have never collaborated with VET institutions, though a minority (18.9%) expresses interest in doing so in the future. This highlights a continued gap between providers and employers, despite the growing need for structured work-based learning and responsive training provision.

Training behaviour and enterprise investment in skills

Training remains largely informal, with on-the-job training being the most common form (52.1% of enterprises). Only one-third of enterprises organized structured training, reaching around 91,487 employees (18.1% of the workforce). Barriers include high labour turnover and limited training budgets.

Foreign-owned enterprises showed higher training participation rates (27.2%) compared to fully Albanian-owned firms (16.7%), suggesting stronger incentives or capacities for workforce development among foreign investors.

Both studies reinforce the need for targeted interventions to address persistent skills shortages, stronger employer–VET collaboration, more systematic and systemic investment in lifelong learning, improved outreach and employment services, continued modernization and alignment of qualifications and education and training offer.

Moreover, the digitalization impact assessment emphasizes the need for supporting sectoral digital transformation, particularly through skills development, which is crucial for Albania’s response to the EU Digital Agenda.

| Status on Output 2.1. Indicators |  |  |  |
| --- | --- | --- | --- |
| Indicator | Target 2025 | Status (Fully/Partially/ Not achieved) | Means of Verification |
| Number of studies and briefs on labour market and skills needs published through the Labour Market Information Observatory Baseline: 0 (2021); Target: 4 by 2027 | N/A | Partially achieved | Study Briefs published |
| Number of Employment Policy Review published Baseline: No (2023); Target: 1 by 2025 | N/A | Postponed | Employment Policy review published |

Output 2.2:  NAES structures have the capacity to facilitate labour market integration of unemployed jobseekers.

Impact Assessement of Active Labour Market Programmes (ALMPs)

In view of the long-standing support that UNDP has provided to the reform of Active Labour Market Programmes, in 2025 UNDP engaged international expertise to carry out an impact assessment of the ALMPs implemented during 2020–2024.

The 2025 Impact Assessment of Albania’s Active Labour Market Programmes (ALMPs), applied quasi-experimental methods and a dedicated survey of programme participants and matched control groups to evaluate six national programmes implemented between 2020 and 2024. The assessment provides the first robust evidence on programme effectiveness, using employment status, labour force activity, wages, and self-perceived prospects as outcome indicators, complemented by a cost–benefit analysis from a social perspective.

Findings show significant differences in programme performance.

The Internship Programme demonstrated the strongest positive impact, increasing employment by 8.5–15.8 p.p. and wages by 4,200 ALL, while the IT Programming Courses also generated a substantial employment effect.

Other programmes showed mixed or limited results: Wage Subsidy and On-the-Job Training shifted from negative to modestly positive effects once baseline corrections were made, but produced no wage gains.

The Self-Employment Programme increased the likelihood of self-employment but had no statistically significant overall impact on employment or earnings.

The Community Employment Programme (CEP) showed consistently negative labour-market effects, confirming its role as a social inclusion rather than an employment reintegration measure.

Cost–benefit results reinforce these findings, demonstrating net positive returns only for the Internship and IT training programmes.

The assessment recommends rebalancing ALMP investments toward programmes with proven impact—particularly Internships and digital skills programmes—and re-designing or restructuring weaker interventions such as OJT, Wage Subsidy, and Self-Employment to improve targeting, employer engagement, and post-programme sustainability.

CEP should be formally repositioned as a social activation measure with separate objectives. Strengthening NAES data quality, introducing regular impact evaluations, and improving employer monitoring and programme governance are essential to ensure more efficient use of public funds and better alignment with labour market needs. These results directly support Albania’s evidence-based policymaking efforts under NESS 2030 and EU Chapter 19.

Capacity building for implementing new ALMPs

The capacity-building support provided by the SD4E Programme to the National Agency for Employment and Skills (NAES) has been pivotal in enabling the effective roll-out of the new Active Labour Market Integration Programme for vulnerable jobseekers, which offers up to six months of intensive counselling, profiling, and individualized support. Through a combination of tailored coaching sessions, technical guidance on case management, and operational support in refining programme workflows and documentation, SD4E strengthened NAES’s institutional readiness to implement the measure in line with EU standards on personalised employment assistance.

| Status on Output 2.2. Indicators |  |  |  |
| --- | --- | --- | --- |
| Indicator | Target 2024 | Status (Fully/Partially/ Not achieved) | Means of Verification |
| 2.2.1 Number of individualised ALMMs available to jobseekers Baseline: 6 (2023) Target: 9 (2026) | 7 (1 new) | Fully Achieved | Official Gazette NAES Admin. Data |
| 2.2.2 Number of NAES staff that are engaged in the community of Practices. Baseline: 0 (2023); Target: 120 all frontline staff (2027) | 40 | Not achieved | CoP meetings minutes |
| 2.2.3 Number of non-public providers trained to offer ALMPs/Career services. Baseline: 0 (2022); Target:20 (2027) | 3 | Not achieved | NAES Admin Data |

## Progress Review for Actions under Outcome 3

Activities under Outcome 3 of the project marked significant strides in building capacities of national key stakeholders (MECI, NAVETQ and VET providers) towards improved quality  in vocational education and training.

| Outcome 3: Status of the outcome indicators |  |  |  |
| --- | --- | --- | --- |
| Targets | Indicator status (Fully/Partially/ Not achieved) | Explain the status of the indicator | Means of Evaluation/ Verification |
| Number of VET providers undergoing the accreditation process every year (Disag. by Public and Private and % accredited). Baseline: 6 (5 Pub. and 1 Prv.) (2022); Target: 31 public VET providers by 2027 | Partially achieved | By the end of 2025, a total of 18 VET providers (public and private) have undergone /are undergoing the accreditation process | NESS 2030 Annual Progress Reports NAVETQ website |
| Number of people certified through a pilot implementation of the agreed RPL policy model Baseline: 0 (2022); target: 150 (2027) | In progress | The pilot implementation of RPL commenced with the revision of the quality assurance tools and development of a roadmap in 2025 | NAVETQ website |
| A standardized procedure for the development and validation of the Vocational Qualifications is officially adopted by the Ministry. Baseline: No (2022); Target: Yes (2024) | Fully Achieved | The Minister’s Instruction on the Procedures of Validation has been adopted as of 16.12.2024 | Official Gazette |

Output 3.1: National institutions and VET providers can implement and advance the national model of QA in the Albanian VET system.

The SD4E project continued to support the National Agency for VET and Qualifications (NAVETQ) and VET providers in strengthening the quality assurance (QA) and institutional development framework of the Albanian VET system. Project interventions focused on enhancing QA mechanisms through targeted technical assistance to support the effective implementation of self-assessment as a core instrument for internal monitoring, institutional learning, and self-control.

Within this framework, a key area of support was the provision of technical expertise to NAVETQ for the further development and consolidation of the national model for the accreditation of VET providers. The accreditation model was informed by practical experience gained through several years of self-assessment implementation and aligned with the agreed quality areas, which are now widely accepted by VET schools and systematically applied through their institutional development units.

Building on the accumulated experience from the implementation of self-assessment and the initial rounds of VET provider accreditation, the project identified the need to revise the standards and criteria underpinning both processes. This revision was essential to ensure continued relevance, coherence, and alignment with evolving VET practices, as well as with recent policy and regulatory developments.

Review of the VET Quality Assurance Framework

During 2025, the SD4E project placed particular emphasis on strengthening both internal and external QA processes within VET institutions, ensuring that newly introduced measures—such as Recognition of Prior Learning (RPL) and lifelong learning provisions—are effectively embedded in institutional practice. Albania undertook a comprehensive revision of its QA instruments, encompassing both self-assessment and accreditation mechanisms, which together constitute the backbone of the national VET Quality Assurance Framework. Since the adoption of the self-assessment regulation in 2018 and the accreditation model in 2021, the system has followed a structured, continuous improvement-oriented approach to quality assurance.

Key policy developments—including the National Employment and Skills Strategy 2023–2030, the integration of lifelong learning qualifications into the Albanian Qualifications Framework (AQF), and the establishment of the regulatory framework for the Validation of Non-Formal and Informal Learning (VNFIL)—made the updating of these instruments both timely and necessary.

In close cooperation with NAVETQ and with the support of an external consultant, the SD4E project facilitated a comprehensive review of the self-assessment and accreditation instruments. As a result, in 2025:

- a revised accreditation order for VET institutions was approved.

- the official self-assessment guidelines were updated.

- new forms of VET provision, including lifelong learning and RPL-related pathways, were integrated into the QA framework.

- evaluation criteria were streamlined and clarified, improving usability and consistency; and

- the foundations for a strengthened culture of continuous quality improvement among VET providers were further reinforced.

Accreditation of VET Providers

The accreditation of VET providers continued to progress steadily in 2025, reflecting the gradual consolidation of the national quality assurance framework. Since the initiation of this process, a total of 22 accreditation procedures have been launched, of which 17 have been completed, while 5 remain ongoing.

Among the completed procedures:

- 10 VET providers were granted full accreditation;

- 1 provider did not meet the accreditation requirements; and

- 6 providers were granted accreditation with conditions, requiring follow-up actions and subsequent reaccreditation to fully comply with the established standards.

| Status on Output 3.1. Indicators |  |  |  |
| --- | --- | --- | --- |
| Indicator | Target 2025 | Status (Fully/Partially/ Not achieved) | Means of Verification |
| Qualitative assessment of the Quality Assurance and Development in VET and roadmap for further harmonisation Baseline: No (2022) Target: A harmonised roadmap is agreed by all (2027) | Fully Achieved | Fully Achieved | Official Gazette NESS 2030 Annual Progress Report |
| Number of VET providers aware of the accreditation process Baseline: 6; Target: all public and private VET providers participate in information sessions by 2024 | 18 VET providers (accredited or under accreditation) | Partially achieved | NAVETQ Website NESS 2030 Annual Progress Report |

Output 3.2: NAVETQ develops an efficient and transparent process for quality assurance and development of vocational qualifications.

Capacity Development for VET Specialists

Within the framework of support to NAVETQ and drawing on the expertise of the Swiss Federal University for Vocational Education and Training (SFUVET), a comprehensive capacity development program for VET specialists was implemented in Albania in 2025. The program consisted of three training blocks, each lasting two and a half days, held in December 2024, January, May, and September 2025. The central focus was on integrating real-life professional situations into vocational education, ensuring that learning remains meaningful, practical, and competence based.

The training introduced participants to the core principles of Situation-based Didactics (SiD), demonstrating how authentic professional scenarios can effectively link theory with practice. Through examples from multiple vocational fields, participants explored the main conceptual elements and planning stages of Situationsdidaktik (SiD) and discussed challenges in balancing theoretical foundations with hands-on learning.

In parallel, the program emphasized symmetric pedagogy, highlighting its distinction from traditional top-down approaches. Participants were encouraged to foster collaborative teacher–student relationships and design learning situations that actively engage learners. Practical exercises illustrated how symmetric pedagogy, supported by tools such as SiD, strengthens competence-based education and nurtures a culture of lifelong learning.

The cycle concluded with a fourth training block in September 2025, where participants consolidated their learning and reflected on practical applications in their respective fields. At the end of the program, 14 NAVETQ specialists were awarded certificates recognizing their active participation, the acquired skills, commitment, and continuous engagement throughout the training cycle.

Skills in Switzerland – Training Course for International VET Experts by SFUVET

In September 2025, eight NAVETQ specialists took part in the “Skills in Switzerland” course organized by SFUVET in Lausanne. The program aimed to provide participants with an in-depth understanding of the key success factors of the Swiss Vocational Education and Training (VET) system through direct exposure to leading institutions, companies, and training centers.

The four-day course combined presentations, institutional visits, and participation in a national skills competition. It began with a welcome session and an introduction to the Swiss VET system, including SFUVET’s contribution to its development and quality assurance.

Participants visited the Ecole Hôtelière de Lausanne (EHL), a globally recognized hospitality business school offering both vocational and academic pathways. The program continued with a visit to the École Technique Vallée de Joux (ETVJ), a prominent vocational institution specializing in watchmaking and technical professions.

Additional activities included visits to VET schools and well-established companies with strong apprenticeship systems, along with a sector-based training centre operated by a professional association that equips apprentices with labour-market-relevant skills.

A highlight of the course was the guided visit to the Swiss Skills Competition in Bern, where participants observed national skills championships and gained firsthand insight into how Switzerland promotes excellence and innovation in vocational practice.

The course concluded with a wrap-up session focused on the elements that contribute to successful VET implementation. Participants reflected on the practices and mechanisms that could be meaningfully adapted to the Albanian context. Certificates were awarded upon completion.

Overall Reflection on the Value of Cooperation with SFUVET

The collaboration between SD4E and SFUVET during 2025 significantly strengthened NAVETQ’s institutional and human capacities. Through a combination of theoretical grounding, practical exposure, and international benchmarking, the activities helped build a shared understanding of competence-based learning, strengthened methodological expertise, and offered firsthand insights into one of the world’s most successful VET systems.

The structured approach—integrating in-country training with international study visits—ensured that participants not only learned new concepts but also observed their practical application. This creates favorable conditions for informed decision-making, improved curriculum design, and more effective implementation of Albania’s VET reforms.

Looking ahead, continuing collaboration with SFUVET would be highly beneficial. Their expertise, long-standing experience, and proven methodologies could further support Albania’s efforts to modernize its VET system, strengthen institutional capacities, and sustain the momentum generated in 2025. Ongoing cooperation would provide continuity, deepen professional competencies, and reinforce NAVETQ’s role in steering high-quality, competence-based vocational education.

| Status on Output 3.2. Indicators |  |  |  |
| --- | --- | --- | --- |
| Indicator | Target 2024 | Status (Fully/Partially/ Not achieved) | Means of Verification |
| A standardized procedure for the development and validation of the Vocational Qualifications is designed and endorsed by NAVETQ. Baseline: No standardized procedure; Target: Procedure exists and is consulted with NAVETQ Baseline: No; Target: Yes by 2024 | Yes | Fully achieved | Official Gazette NESS 2030 Annual Progress Report |
| 3.2.2 Number of NAVETQ staff/assessors trained to apply the standardised procedures for development and validation of the occupational standards/qualifications. Baseline: 0; Target: 7 (2026) | N/A | Partially achieved | SD4E Reports NAVETQ records |

Output 3.3: National institutions pilot and consolidate a quality assured model of Recognition of Prior Learning (RPL)

Albania has now established a comprehensive national framework for the Recognition of Prior Learning (RPL), also known as Validation of Non-formal and Informal Learning (VNFIL).
This system enables adults with work experience or informal learning backgrounds to obtain recognized professional qualifications aligned with the Albanian Qualifications Framework (AQF), at levels 2–5.

The most recent regulatory act, the Instruction No. 1109, approved in December 2024 — defines the detailed procedures for assessment, certification, and quality assurance. Together with previous acts (notably DCM No. 756, dated 9 December 2021), it provides a solid legal and procedural basis for a transparent, quality-assured, and accessible RPL system, fully aligned with European lifelong learning standards.

The national legal framework clearly defines the roles of all institutions involved in the Validation of Non-formal and Informal Learning (VNFIL). The responsible Ministry for VET (currently the Ministry of Economy and Innovation) oversees regulatory approval and supports system digitalization. NAVETQ is responsible for developing methodological guidelines, accrediting VET providers, maintaining the National Catalogue of Qualifications, and training assessors. NAES contributes human and financial resources, refers candidates—especially jobseekers—and monitors implementation. Accredited VET providers carry out the validation process through internal and external assessment structures and ensure quality assurance.

The validation process follows four stages: i) identification of the qualification path, ii) documentation of evidence through a Skills Portfolio, iii) assessment by trained assessors, and iv) certification issued by the External Assessment Commission. The duration varies by qualification level, ranging from 4 to 18 months.

To support the transition from the regulatory framework to implementation, a national roadmap for VNFIL was developed in 2025. It includes: (1) an awareness and capacity-building phase with information sessions and training for providers; (2) pilot planning and identification of priority target groups and qualifications; (3) development of an information and management system through a dedicated working group; (4) implementation support for providers, including a handbook, a first round of candidate validation, and ongoing coaching; and (5) a monitoring and evaluation phase focused on quality assurance, technical reporting, and supporting providers in developing self-assessment and annual reports. This structured roadmap ensures a coordinated, phased introduction of VNFIL across Albania.

Figure 1: VFNIL Implementation Building Blocks

Following completion of the roadmap, the SD4E project supported a national consultation process in December 2025 to build institutional ownership and readiness for piloting. On 17 December 2025, a consultation meeting was convened with representatives of government institutions, VET providers, social partners, and the private sector. Discussions focused on the proposed implementation model, quality assurance arrangements, institutional roles and responsibilities, and the next steps for piloting the VNFIL system. The consultation served as an important milestone in the transition from policy development to operationalisation.

This initiative represents a significant step towards the establishment of an inclusive, quality-assured lifelong learning system in Albania. It contributes directly to the implementation of the National Employment and Skills Strategy 2023–2030 and strengthens the link between skills development, employability, and labour market needs by enabling the formal recognition and certification of skills acquired through work experience and lifelong learning pathways.

| Status on Output 3.3. Indicators |  |  |  |
| --- | --- | --- | --- |
| Indicator | Target 2024 | Status (Fully/Partially/ Not achieved) | Means of Verification |
| A draft RPL model is developed and endorsed by all stakeholders. Baseline: No Model; Target: Model developed/endorsed. | Yes | Fully Achieved | Official Gazette |
| A roadmap for the implementation of the RPL model is agreed by all stakeholders. Baseline: No; Target: Yes (2024) | Yes | Fully Achieved | SD4E Progress Reports |
| Number of qualification(s)/occupation included in the RPL pilot implementation. Baseline: 0; Target: 1 (2025 and 2026) | N/A | Not started | NAVETQ Website |

# Project Risks and Issues

In 2025, the SD4E Programme maintained regular monitoring and mitigation of contextual, institutional, and programmatic risks. Overall, no risks materialised in a way that adversely affected the delivery of project outputs or the achievement of annual results. Risk treatment remained systematic throughout the year, informed by continuous dialogue with national institutions, implementing partners, and the donor, as well as lessons emerging from the evolving reform context.

Contextual Risks

Macroeconomic developments remained broadly stable, with economic growth projected at 3–4 percent annually and labour market conditions improving.

As a result, the risk of deterioration in the macroeconomic environment remained low probability / medium impact, requiring only standard monitoring.

Risks related to migration of skilled workers, the potential distorting effects of passive labour market measures, and donor coordination challenges were assessed as medium probability. These risks were mitigated through SD4E’s support to improved ALMP design, participation in IPMG-level donor coordination, and continued analysis of labour market trends through the SNA and digitalization assessments. No significant disruptions occurred in 2025.

Institutional Risks

From the institutional risks’ perspective, conflicting or overlapping donor initiatives, particularly in VET, remained a high-probability, high-impact risk. Switzerland’s well-established position through its Vocational Skills Portfolio in Albania and UNDP’s active engagement in sector coordination helped reduce fragmentation and ensured alignment with national priorities.

Programmatic Risks

On the programmatic risks account, limited private sector engagement, identified as a medium-probability risk, was partially addressed through stronger employer involvement in dual VET expansion, accreditation processes, and efforts to design innovative financing mechanisms with the participation of the private sector.

Based on the analysis and regular treatment, risk levels for SD4E remain manageable and broadly stable. No critical disruptions were recorded in 2025. However, several high-impact risks—particularly those concerning institutional capacities, donor coordination, and the implementation of complex reforms such as VET optimisation and VNFIL—require continued attention. Going into 2026, SD4E will prioritise strengthening institutional ownership of reforms, most notably of NESS 2030, Quality Assurance Framework, ALMP restructuring, and VFNIL/RPL implementation.

# Lessons Learned

- Integrated Policy Coordination is Essential but Requires Sustained Institutional Commitment

The Integrated Policy Management Group (IPMG) on Human Capital Development proved to be an effective mechanism for aligning reforms across employment, skills, education, social protection, gender equality, and child protection. The 2025 cycle demonstrated the value of a structured governance platform in facilitating EU-aligned policy dialogue (e.g., amendments to Law 15/2019, Gender Equality Law, Alternative Care Law, and the National Action Plan on the European Child Guarantee). At the same time, effective cross-ministerial coordination required extensive facilitation by SD4E. Going forward, the sustainability of the IPMG model depends on stronger internal ownership, systematic follow-up to decisions, and clearer division of responsibilities between line ministries and implementing agencies.

- Skills Intelligence Strengthens Policy Making, but System Integration Remains a Challenge

The 2025 Skills Needs Assessment (SNA), alongside the Digitalization Impact Assessment, significantly deepened evidence on labour market dynamics, skills shortages, recruitment challenges, and digital skills gaps. The studies confirmed persistent misalignment between workforce qualifications and enterprise needs, limited employer–VET collaboration, and major sectoral constraints in digital readiness.

However, transforming this data into systematic, institutionalized decision-making remains a major challenge. National partners require dedicated capacities, analytical skills, and coordination mechanisms to ensure that skills intelligence is regularly used to plan VET pathways, design ALMPs, and update qualifications.

Building institutional capability to interpret, communicate, and act upon evidence is as important as collecting it.

- ALMP Effectiveness Varies—Evidence Must Guide Portfolio Rebalancing

The 2025 Impact Assessment of ALMPs demonstrated significant differences in programme performance. A key lesson is the importance of programme design and targeting: interventions aligned with private-sector demand and skills development consistently perform better. The assessment clearly showed that without rigorous monitoring, annual evaluations, and evidence-based revisions, inefficiencies accumulate and public resources may not yield intended results.

- VET Quality Assurance Reforms Require Continuous Accompaniment and Institutional Uptake

The comprehensive revision of the VET Quality Assurance Framework—including self-assessment guidelines, accreditation criteria, and integration of lifelong learning and VFNIL/RPL—demonstrated the system’s capacity to adapt to evolving VET and labour market needs. However, implementation across VET providers remains uneven. Many institutions require sustained mentoring, training, and operational support to internalize quality assurance practices. Strengthening development units and ensuring a consistent approach to accreditation, inspection, and self-assessment are essential for the long-term success of the reforms.

- Dual VET and Provider Optimization Require Systemwide Coherence, Not Isolated Interventions

While dual VET expanded significantly in 2025 and continues to demonstrate strong potential, the broader Optimization Plan advanced slowly. Stakeholders increasingly recognize that optimization is not merely a structural exercise but a systemic quality-improvement process requiring stronger governance, better remuneration and career pathways, and clear role definitions at provider level.

The lesson is that optimization must be accompanied by broader system reforms, including sustainable financing models, clarified mandates, and consolidated legal framework and institutional capacities.

- Implementation of Validation of Prior Non-Formal and Informal Learning (VFNIL)

The strengthening of the regulatory framework for validation of non-formal and informal learning (Instruction No. 1109/2024) and the development of a national roadmap in 2025 laid critical foundations for future implementation. However, institutional capacities to operationalize VFNIL—and public awareness of its benefits—remain limited. Piloting the model will require intensive coaching, continuous quality assurance, harmonized assessment procedures, and a capacity-building programme targeted at VET providers and assessors.

- Capacity-Building Investments Yield Value When Combined with Practical Application

The collaboration with SFUVETproved highly effective in strengthening NAVETQ’s methodological and pedagogical capacities. The experience showed that paired training formats (theoretical modules, international exposure, and follow-up practical application) generate deeper system learning. A consistent lesson is that capacity building must be connected to real institutional responsibilities and reform tasks to ensure sustainability and know-how transferability.

# Financial Status

Insert Cumulative Project Interim Financial Report (CPFR) here.  Include the disclaimer below.    For details of these reports, please refer User Guide.

| Funding source | Funding received | Disbursed as of 31-Dec-2025 | Commitments | Total disbursed and committed (USD) | Total disbursed and committed (%) |
| --- | --- | --- | --- | --- | --- |
|  | (USD) |  |  |  |  |
| SDC | 1,733,387.07 | 1,486,110.01 | 22,352.32 | 1,508,462.33 | 87.02% |

# Annexes

## Annex 1: SD4E Yearly Plan of Operations 1st January – 31st December 2025

| Overall Objective | Key Indicators |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| The Albanian VET and Employment Promotion system contribute to sustainable and inclusive economic and social development in the country | 1. Human Development Index Baseline: 0.796 (2021); Target: increasing trend 2. Overall financing of Employment and Skills development (NESS2030) Baseline: 5,8 billion ALL (2023); Target: 9,6 billion ALL (2026); 3. Employment rate (NESS) Baseline 2021: 63,5%; Target: increase by 1,0% annually 4. Youth employment rate (NESS) Baseline 2021 43,7%; Target: increase by 1,5% annually 5. Lifelong learning participation rate Baseline: 9.2% (2017); Target: 15% (2025) |  |  |  |  |  |  |  |  |  |  |  |
| Programme Purpose | Key Indicators |  |  |  |  |  |  |  |  |  |  |  |
| Young and adult women and men have increased employability due to improved attractiveness and labour market relevance of inclusive Employment services and VET offer | 1. Percentage of students enrolled in upper secondary VET compared to the respective cohort Baseline: 17,7% (2021); Target: increased by 0,5 pp annually 2. Employment rate of VET graduates (excluding those that continue higher education), by gender. Baseline: 57,5 (2022); Target: 65% (by gender) 3. Employment rate of ALMM participants, by type of programme. |  |  |  |  |  |  |  |  |  |  |  |
| Outcome 1 | Outcome Indicators |  |  |  |  |  |  |  |  |  |  |  |
| National institutions effectively implement the sector’s policy framework and optimize delivery with innovative tools and financing instruments. | 1.1 Number of contributions towards a more inclusive or more labour market relevant Vocational Education and Training (VET) system. Baseline: 0/16 (National VET Conference); Target: 5 out of 16 policy responses of the NESS 2030 1.2 Qualitative assessment of the legislative framework (incl. by laws) Baseline: Incomplete framework; Target: Framework complete and approved. 1.3 Percentage of optimisation plan / roadmaps implemented by their institutions. Baseline: 0% (2022); Target: 100% (2027) |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1 | Output Indicators |  |  |  |  |  |  |  |  |  |  |  |
| National institutions have improved capacities to implement and improve the strategic and regulatory package for VET and employment promotion. | 1.1.1 Mechanisms developed to monitor the sector strategic framework Baseline: No (2022); Target: YES (2024) 1.1.2 Number of meetings per year of the the Integrated Policy Management Group (coordination mechanism) Baseline: 0; Target: 2 annually / 8 meetings by 2027 1.1.3 A roadmap for the advancement of the VET reform beyond 2026 is agreed by all VET actors. Baseline: No; Target: YES (2026) |  |  |  |  |  |  |  |  |  |  |  |
| Activities | January - December 2025 |  |  |  |  |  |  |  |  |  |  |  |
|  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |
| - Optimise capacities to document the process of monitoring and coordinating the implementation of NESS 2030 through the IPMG annually, to meet the EU requirements on the sector (Monitoring of Sector Strategy, Budget Support, and EU accession) |  |  |  |  |  |  |  |  |  |  |  |  |
| - Provide technical assistance to revise and consolidate the legal framework in the VET and employment (VET Law revision, dual VET, Quality Assurance Framework, including self-assessment, accreditation, inspection, recognition of prior learning, National Training Fund / deployment of the quota levy system, ALMPs etc.), in line with the NESS 2030 strategic framework and priority measures. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2 | Output Indicators |  |  |  |  |  |  |  |  |  |  |  |
| Key actors support a participatory approach in the implementation of an optimized VET system. | 1.2.1 Number of roadmaps / optimisations plans for VET providers reorganisation developed. Baseline: 0 (2022); Target: 31 (2026) 1.2.2 Sectoral INFF as financing mechanism developed and consulted. Baseline: No; Target: Yes (2025) 1.2.3 Number of consultation meetings in the frame of the optimization process as per the consultation process as per guidelines. Baseline: 0 (2022); Target 10 (2026) |  |  |  |  |  |  |  |  |  |  |  |
| Activities | January - December 2025 |  |  |  |  |  |  |  |  |  |  |  |
|  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |
| - Identify financing mechanisms for skills development system in Albania (sectoral INFF) and develop a roadmap to untap new financing mechanisms, especially in the context of designing and establishing a National Training Fund. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.3 | Output Indicators |  |  |  |  |  |  |  |  |  |  |  |
| Labour market ecosystem actively engages to promote VET and Employment offer at the national and regional level | 1.3.1. Increased engagement of the private sector beyond the delivery of WBL and percentage piloted with NAES Baseline: No Target: Yes (2025) 1.3.2. Number of national dialogues on VET and Employment Baseline: 1 (2022) Target: 3 (2027) |  |  |  |  |  |  |  |  |  |  |  |
| Activities | January - December 2025 |  |  |  |  |  |  |  |  |  |  |  |
|  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |
| - Conduct an assessment study of the private sector engagement level at VET provision level and a roadmap for its consolidation and further improvement, in cooperation with S4J |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome 2 | Outcome Indicators |  |  |  |  |  |  |  |  |  |  |  |
| National institutions design and deliver individualised and data-driven employment policies and ALMPs, in partnership with the labour market ecosystem | 2.1. Percentage of unemployed jobseekers benefiting from ALMMs, by vulnerable group vs. registered unemployed Baseline: 17,8% (2022); Target: 25% (2026) Women Baseline: 16,3% (2022): Target: 28% (2027) PwD: 55,3% (2022): Target: 56% Roma & Egyptians: 7,8% (2022) Target: 10% (2027) NE: 5,5% (2022) Target: 13% 2.2 Number of Skills Needs Assessment (SNA) led by national institutions that are published. Baseline: 0 (2022) Target: 3 (2027) |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1 | Output Indicators |  |  |  |  |  |  |  |  |  |  |  |
| Intelligence on skills development and employment in Albania is available to policy makers | 2.1.1 Number of studies and briefs on labour market and skills needs published through the Labour Market Information Observatory Baseline: 0 (2021); Target: 4 by 2027 2.1.2 Number of Employment Policy Review published Baseline: No (2023); Target: 1 by 2025 |  |  |  |  |  |  |  |  |  |  |  |
| Activities | January - December 2025 |  |  |  |  |  |  |  |  |  |  |  |
|  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |
| - Conduct an Albania Employment Policy Review 2025, in the context of the respective EU policy, and EU accession negotiations, and the Reform Agenda for Growth |  |  |  |  |  |  |  |  |  |  |  |  |
| - Enhance the methodology and – jointly with the national institutions and employment services offices – conduct the Skills Needs Analysis 2023-2024 through a national-scale survey. |  |  |  |  |  |  |  |  |  |  |  |  |
| - Design, and implement analysis on emerging digital skills in economic priority sectors (ICT, tourism, energy, and agriculture) |  |  |  |  |  |  |  |  |  |  |  |  |
| - Prepare and publish periodic labour market briefs based on administrative and survey data |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.2. | Output Indicators |  |  |  |  |  |  |  |  |  |  |  |
| NAES structures have the capacity to facilitate labour market integration of unemployed jobseekers | 2.2.1 Number of individualised ALMMs available to jobseekers Baseline: 6 (2023) Target: 9 (2026) 2.2.2 Number of NAES staff that are engaged in the community of Practices. Baseline: 0 (2023); Target: 120 all frontline staff (2027) 2.2.3 Number of non-public providers trained to offer ALMPs / Career services. Baseline: 0 (2022); Target:20 (2027) |  |  |  |  |  |  |  |  |  |  |  |
| Activities | January - December 2025 |  |  |  |  |  |  |  |  |  |  |  |
|  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |
| - Conduct Impact assessment of new ALMM 2019-2022, and 2023-2026 |  |  |  |  |  |  |  |  |  |  |  |  |
| - Establish NAES Communities of Practice in 4 thematic areas: employment services, ALMMs, digitalization and institutional marketing (promotion) |  |  |  |  |  |  |  |  |  |  |  |  |
| - Co-design new ALMMs, by first assessing the needs of the jobseekers and partner employers for VET graduates, youth, women, people with disabilities and long-term unemployed (individualised ALMMs) |  |  |  |  |  |  |  |  |  |  |  |  |
| - Deliver capacity development programmes to MECI/NAES working groups to draft regulations and train the staff for the implementations of new ALMMs. |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome 3 | Outcome Indicators |  |  |  |  |  |  |  |  |  |  |  |
| The VET system features a standardized and harmonized Quality Assurance and Development Framework for impact on VET provider's development processes. | 3.1 Number of VET providers undergoing the accreditation process every year (Disag. by Public and Private and % accredited). Baseline: 6 (5 Pub. and 1 Prv.) (2022); Target: 31 public VET providers by 2027 3.2 Number of people certified through a pilot implementation of the agreed RPL policy model Baseline: 0 (2022); target: 150 (2027) 3.3 A standardized procedure for the development and validation of the Vocational Qualifications is officially adopted by the Ministry. Baseline: No (2022); Target: Yes (2024) |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.1 | Output Indicators |  |  |  |  |  |  |  |  |  |  |  |
| National institutions and VET providers are able to implement and advance the national model of QA in the Albanian VET system | 3.1.1 Qualitative assessment of the Quality Assurance and Development in VET and roadmap for further harmonisation Baseline: No (2022) Target: A harmonised roadmap is agreed by all (2027) 3.1.2 Number of VET providers aware of the accreditation process Baseline: 6; Target: all public and private VET providers participate in information sessions by 2024 |  |  |  |  |  |  |  |  |  |  |  |
| Activities | January - December 2025 |  |  |  |  |  |  |  |  |  |  |  |
|  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | QA |
| - Support the implementation of the Accreditation Roadmap 2022-2027 (developed with the support of SD4E 2019-2022) – information, awareness raising on the relevance of quality assurance / accreditation in VET. |  |  |  |  |  |  |  |  |  |  |  |  |
| - Conduct a formative assessment of the Albanian QAD model, in comparison to the EU and other models & Develop roadmap towards Quality Assurance and Development in VET (Quality areas, processes and procedures) |  |  |  |  |  |  |  |  |  |  |  |  |
| - Conduct VET review issue nr. 2 (2026) with a focus on the VET Quality Areas in Albania, compared to the EU and the region (capitalisation report) |  |  |  |  |  |  |  |  |  |  |  |  |
| - Deliver capacity development programme for MECI, NAVETQ and NAES (coaching, joint documentation, peer learning, communities of practice in Quality Assurance and Development), with a focus on inspection functions and the harmonization with all dimensions of the QAD |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.2 | Output Indicators |  |  |  |  |  |  |  |  |  |  |  |
| NAVETQ delivers an efficient and transparent process for quality assurance and development of vocational qualifications | 3.2.1 A standardized procedure for the development and validation of the Vocational Qualifications is designed and endorsed by NAVETQ. Baseline: No standardized procedure; Target: Procedure exists and is consulted with NAVETQ 3.2.2 Number of NAVETQ staff/assessors trained to apply the standardised procedures for development and validation of the occupational standards/qualification Baseline: 0; Target: 7 (2026) |  |  |  |  |  |  |  |  |  |  |  |
| Activities | January - December 2025 |  |  |  |  |  |  |  |  |  |  |  |
|  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |
| - Review the current model for the development of vocational qualifications, in comparison to other regional and EU models (implemented with SFUVET) |  |  |  |  |  |  |  |  |  |  |  |  |
| - Provide technical support to improve the Albanian model including amendments in the regulatory framework and capacity building of NAVETQ staff (implemented with SFUVET and aligned with S4J) |  |  |  |  |  |  |  |  |  |  |  |  |
| - Promote the Albanian Qualifications Framework, targeted to teachers, private sector, education institutions, students, parents, etc. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.3 | Output Indicators |  |  |  |  |  |  |  |  |  |  |  |
| National institutions pilot and consolidate a quality assured model of Recognition of Prior Learning (RPL) | I1: A draft RPL model is endorsed by all stakeholder Baseline: No Model; Target: Model endorsed. I2: A roadmap for the implementation of the RPL model is agreed by all stakeholders Baseline: No; Target: Yes (2024) |  |  |  |  |  |  |  |  |  |  |  |
| Activities |  |  |  |  |  |  |  |  |  |  |  |  |
|  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |
| 3.3.2. Design a roadmap to its pilot implementation of one selected occupation (based on the model proposed in output 3.2) |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.3. Develop accreditation process for RPL (VET providers) centers and capacities, in line with the provisions in the Law on VET (nr.15/2017) and the approved instruction of the Minister. |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.4. Prepare and coordinate the pilot implementation for 100 adults to undergo the RPL process in the selected occupation |  |  |  |  |  |  |  |  |  |  |  |  |

| Project Management |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Management: UNDP ensures efficient and effective implementation of the SD4E Exit Phase |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 0.1 Project Management |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities | January - December 2025 |  |  |  |  |  |  |  |  |  |  |  |
|  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |
| 0.1.1 Hiring of responsible staff as per the programme management structure and UNDP rules and procedures |  |  |  |  |  |  |  |  |  |  |  |  |
| 0.1.3 Hiring consultancies and services to ensure efficienct implementation of activities under the three outcomes, as outlined in the work plan. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 0.2 Project Monitoring |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities | January - December 2025 |  |  |  |  |  |  |  |  |  |  |  |
|  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |
| 0.2.4 Technical Committee Meetings |  |  |  |  |  |  |  |  |  |  |  |  |
| 0.2.5. Steering Committee Meetings |  |  |  |  |  |  |  |  |  |  |  |  |
| 0.2.6. SDC Coordination Platform |  |  |  |  |  |  |  |  |  |  |  |  |
| 0.2.7 Progress Reports |  |  |  |  |  |  |  |  |  |  |  |  |

## Annex 2: Minutes of Meeting of the Third Joint Steering Committee, December 11, 2025

Skills Development for Employment Programme (SD4E) and Skills for Jobs (S4J) Project

3rd Joint Steering Committee Meeting

Maritim Plaza Hotel, Dora D’Istria Room

Thursday, 11th December 2025, 10:00 – 12:30

Minutes

Opening remarks

Mr. Eno Ngjela, Inclusive Growth and Employment Programme Specialist, UNDP Albania, opened the third Joint Steering Committee meeting in his capacity as moderator. He warmly welcomed the members and expressed his appreciation to all participants for taking the time to attend the third meeting of the Joint Steering Committee.

Mr. Ngjela informed the Steering Committee members that the meeting had been preceded by a Joint Technical Working Group meeting of both projects.

He then invited Ms. Olta Manjani, Deputy Minister of Economy and Innovation, and Mr. Philipp Arnold, Deputy Head of Mission at the Embassy of Switzerland, to deliver their opening remarks and formally address the meeting.

In her opening remarks, Ms. Manjani expressed appreciation to UNDP Albania and Swisscontact for establishing the practice of convening the Joint Steering Committee at the end of the year, noting its value as an opportunity for reflection and coordinated planning.

Ms. Manjani emphasized that both projects have worked in close cooperation with the relevant institutions, reflecting the Swiss Development Cooperation’s commitment to supporting reforms in the employment and VET sector in Albania.

She further highlighted the active role of the Skills Development for Employment Programme in supporting the development of the legal framework, the dual VET initiative, system optimisation, and employment promotion, with a clear expected contribution in 2026, particularly in relation to legal framework support, capacity building, and EU accession.

With regard to the Skills for Jobs project, Ms. Manjani underlined its support to the modernization of VET providers, including the extension of support to four additional partner schools in 2025, the digitalization of VET, and continued assistance in the development and implementation of new dual VET qualifications. The intention to continue support in 2026 was noted, with a focus on ensuring sustainable transfer and institutional anchoring of results within the responsible institutions.

Mr. Philipp Arnold, Deputy Head of Mission of the Embassy of Switzerland, and Co-Chair of the Joint Steering Committee extended a warm welcome to the Members of the Joint Steering Committee on behalf of the Swiss Embassy. He highlighted the strong progress achieved by both projects over the past two years of implementation, while noting that continued and sustained efforts remain essential, as the journey is not yet complete.

Presentation of Annual Progress and Yearly Operational Plans of the Projects

Following the opening remarks by the Co-Chairs of the Joint Steering Committee, Mr. Ngjela proceeded to the next agenda item by first providing an overview of Albania’s macroeconomic and labour market context. He highlighted the positive performance observed in recent years, while also outlining the persisting challenges that need to be taken into consideration.

Building on the general context overview, Mr. Ngjela then handed over to Ms. Sonila Limaj, Skills Development for Employment Programme Coordinator, to present the key results of the SD4E project implementation in 2025, as well as the proposed Yearly Plan of Operations for 2026.

Ms. Limaj highlighted the achievements made possible through close collaboration with the Ministry and the executive agencies, in particular the work of the IPMG on Human Capital Development as a platform for policy exchange and coordination; improvements to the legal framework for quality assurance in VET; strengthened skills intelligence and knowledge products (Skills Needs Analysis 2025, Assessment of Digitalization Impact on Priority Economic Sectors, and Impact Assessment of Active Labour Market Programmes); the comprehensive review and enhancement of the VET quality assurance framework, including arrangements for the implementation of validation of non-formal and informal learning; collaboration with the Swiss Federal University for Vocational Education and Training (SFUVET) to build the capacities of NAVETQ experts; and support to NAES in initiating the implementation of Active Labour Market Programmes with a focus on the most vulnerable jobseekers.

In addition, Ms. Limaj presented the Yearly Plan of Operations for the Skills Development Programme for 2026, outlining the key milestones. These include support for reviewing and further developing the regulatory framework and strengthening policy coordination; support to VET optimisation, including the development of guidelines for managing generated income by VET providers; dissemination of skills assessment results; design and capacity building for new Active Labour Market Programmes; support to NAES in aligning employment services with EURES; continued support for the implementation of the quality assurance framework, with a particular focus on promoting accreditation; as well as support for piloting the system for the validation of non-formal and informal learning. For further details, please refer to the attached presentation and the Annual Work Plan 2026.

Mr. Ngjela then handed over to Mr. Fation Dragoshi, Project Manager of the Skills for Jobs project at Swisscontact, to present the project’s implementation progress in 2025 and the Yearly Plan of Operations for 2026.

In his presentation, Mr. Dragoshi underlined the project’s efforts to ensure horizontal transfer and anchoring of know-how. With regard to horizontal transfer, he highlighted the integration of four additional partner VET providers—Vocational School “Stiliano Bandilli”, Berat; Technical School of Korça; Vocational School “Arben Broci”, Shkodër; and Vocational School “Nazmi Rushiti”, Peshkopi. As a result, the project is supporting 178 teachers and 1,473 students across these schools.

Furthermore, when referring to implementation progress during 2025, Mr. Dragoshi emphasized the project’s efforts in digitalization, most notably through the expansion and increased use of the MesoVET platform. A significant number of S4J partner schools are now using the platform for final examinations. Overall, the platform is actively used by more than 10,000 users, including both teachers and students across the VET system.

In addition, substantial support has been provided through the introduction of the digitalization coordinator role in all public VET schools.

Mr. Dragoshi also emphasized the ongoing collaboration with the private sector, particularly in relation to the implementation of dual VET programmes, which are currently offered by 14 schools. He noted that the increasing number of VET providers, companies, and apprentices engaged in dual VET places the system in a continuous working and scaling-up mode.

For 2026, the S4J project plans to continue its support for organizational development, particularly through assistance to development units, support to NAES in enhancing the annual planning cycle for VET providers, strengthened support for the functioning of VET providers’ management boards, and infrastructure assessment.

With regard to digitalization, Mr. Dragoshi highlighted continued support for improving the quality of MesoVET platform usage, capacity building, and the gradual handover of the platform.

Regarding the dual VET initiative, Mr. Dragoshi outlined planned activities including the development of initial VET qualifications, the organization of regional business forums, and continued support to VET providers to further strengthen collaboration with companies. For further details, please refer to the attached presentation and the Yearly Plan of Operations.

Open Discussion

Moving to the next agenda item, Mr. Ngjela invited the Steering Committee Members to engage in an open discussion and feedback session.

In her intervention, Ms. Olta Manjani thanked both projects for sharing their Annual Work Plans with the Steering Committee in advance. She reiterated the importance of early sharing to ensure improved coordination and to avoid potential overlaps between interventions.

Ms. Manjani provided detailed feedback and highlighted several important developments, milestones, and priorities of the Ministry, which she invited both projects to take into consideration when finalizing their plans for 2026.

With regard to the Skills Development for Employment Programme, Ms. Manjani highlighted the following priority areas where project support would be particularly beneficial.
First, on behalf of the Government, the Ministry is seeking to conclude international agreements for workforce deployment, particularly to address short-term skills shortages that are difficult to meet through domestic resources.

Second, Ms. Manjani underlined the rapid pace of technological developments and stressed the need to draw lessons from other countries on the effective use of artificial intelligence in employment policies.

Third, she reiterated the importance of workforce development, particularly in the tourism sector, and called on the projects to take into account the training needs of the tourism workforce.

Lastly, Ms. Manjani emphasized the need for capacity building and institutional support within the Ministry, particularly in the context of the EU integration process.

In her feedback regarding the Skills for Jobs project, Ms. Manjani emphasized the importance of supporting Albania’s membership in WorldSkills and of preparing VET schools to participate in international competitions.

Furthermore, Ms. Manjani referred to the study visit to the École hôtelière de Lausanne, organized within the framework of the International VET Congress in September 2025, which she described as highly impressive. She emphasized the importance of enabling representatives of the Hospitality and Tourism School in Tirana to visit and benefit from the experience of this internationally renowned institution.

Mr. Eno Ngjela provided a brief response to the priorities outlined and the potential areas of support by UNDP Albania through the SD4E project.

He emphasized that the first two requests—namely, international agreements for the deployment of the workforce and addressing the impact of artificial intelligence on employment and skills policies—could be incorporated into the Annual Work Plan for 2026, subject to endorsement by the Steering Committee.

With regard to workforce development in the tourism sector, Mr. Ngjela noted that this may fall outside the scope of the SD4E project, while highlighting that UNDP is seeking to address this area through other interventions.

In her remarks, Ms. Ejvis Gishti, General Director of NAVETQ, thanked both projects for the comprehensive information shared during the two presentations and emphasized the good communication maintained with both projects throughout the year. She expressed her appreciation that both projects highlighted achievements as joint results with the Ministry and the agencies, which she considered a meaningful outcome of the collaboration.

Ms. Gishti continued by highlighting several key milestones for support and collaboration in the coming year. Following the successful adoption and deployment of the regulatory framework for the Validation of Prior Non-Formal and Informal Learning, she reiterated the need for digitalization and technological support during the implementation phase of validation.

In addition, in the context of further improving the legal framework, Ms. Gishti underlined the importance of coordinating efforts with the Ministry of Education, particularly with regard to shaping the Vocational Matura and bridge courses within the framework of the joint working group.

Ms. Gishti also emphasized the need not only to increase the number of teachers in VET - as part of the commitments undertaken by the Ministry within the framework of negotiations under Chapter 26 - but also to intensify continuous professional development measures, supported by digitalization and technology.

Another important aspect highlighted by Ms. Gishti was the need to engage business partners already at the design phase of vocational qualifications, enabling them to contribute to defining both the required skills and the workload necessary to acquire those skills.

In his feedback, Mr. Klevis Hysa, General Director of the National Agency for Employment and Skills, thanked both projects and SDC for the support provided throughtout the years. Mr. Hysa appreciated the receipt of the Yearly Plans of Operations by both projects, while underlining the importance of coordination for activities to be effective.

He appreciated the support by the SD4E project for the roll-out of Employment Promotion Programmes, and the S4J project for the support at the school level, highlighting the support of 4 new schools that were included in 2025.

Looking ahead to 2026, Mr. Hysa emphasized the importance of mapping planned activities in line with the Action Plan of the National Employment and Skills Strategy 2030 (NESS). He noted that NAES has already established a template with clear guidance on the information to be shared with the Ministry regarding requested support and areas for collaboration.

In this context, he requested closer collaboration with both projects across a range of activities planned for 2026, including capacity building for skills assessments; support to the NAES department responsible for employer relations; and support to schools and employment offices to strengthen mediation with businesses and facilitate the transfer of know-how related to the tracing system to be implemented by the VET management department within NAES.

Ms. Manjani further noted that it would be important to revive the National Council for VET in 2026 and to ensure the broad and inclusive participation of all relevant stakeholders.

In his response to the feedback from the Steering Committee members, Mr. Fation Dragoshi stated that he had taken extensive notes, highlighting the idea of using digitalization in business processes related to VET delivery.

With regard to participation in WorldSkills, Mr. Dragoshi emphasized that Switzerland has substantial experience to share and can provide meaningful support in this area.

Regarding the revival of the National VET Council, Mr. Dragoshi noted that it would be appropriate for both projects to work jointly on this.

In terms of sharing work plans and terms of reference, Mr. Dragoshi highlighted the nature of the project’s work, noting that its theory of change requires in-depth interventions which can at times be complex.

In his intervention, Mr. Eno Ngjela of UNDP Albania explained that UNDP’s modus operandi requires terms of reference to be consulted with beneficiaries. For this reason, he noted that it would not be an issue for UNDP to share draft terms of reference in advance with the Ministry and the agencies, as required.

Ms. Manjani reiterated that whenever projects plan new activities, these should be shared with the relevant counterparts to avoid overlaps, ensure better alignment, and support effective decision-making.

Presentation of dual VET Roadmap

Proceeding to the next agenda item, Mr. Eno Ngjela, UNDP Albania, introduced the engagement of both projects in supporting the implementation of the dual VET initiative, following the meeting with the Prime Minister in 2024. He emphasized that the technical teams of both projects have worked jointly to support the development and adoption of the regulatory framework, while the Skills for Jobs (S4J) project has continued to provide support at the implementation level.

Mr. Fation Dragoshi then presented the building blocks and key features of the Dual VET Roadmap, which is based on a conceptual framework developed by Mr. Dieter Euler, Senior Expert in dual VET from the University of St. Gallen, Switzerland.

According to the conceptual framework, the roadmap is structured around four main areas: governance, including the legal framework and financing; Capacity building, focusing on the professionalization of VET schools and businesses; On-site implementation, including engagement of the business sector and development of VET schools; and Conceptual foundations, covering curriculum development, alignment with the education system, and quality development.

An additional key dimension of the roadmap is the implementation timeline. The roadmap foresees the development of the four implementation areas across three milestone periods: 2024–2027, concluding with the end of SDC support; 2028–2030, aligned with achieving the targets of the National Employment and Skills Strategy (NESS) 2030; and the period beyond 2031–2037, corresponding to the subsequent policy cycle, acknowledging that education reforms require longer timeframes to generate impact.

Mr. Dragoshi noted that the development of the Dual VET Roadmap document would require approximately two to three months, with the finalized document to be presented to stakeholders by March 2026. He invited Steering Committee Members to provide feedback on the roadmap, as it is subject to their endorsement.

In her feedback, Ms. Olta Manjani expressed appreciation for the progress achieved in the implementation of dual VET and the development of the roadmap. She agreed to continue the work towards finalizing the strategic roadmap and expressed her appreciation for the support provided by both projects.

Reflections and feedback by UNDP Albania and Swisscontact

Mr. Francisco Roquette, UNDP Deputy Resident Representative in Albania, thanked the members of the Joint Steering Committee for the rich exchanges and constructive discussions held during the meeting.

Mr. Roquette highlighted his key takeaways regarding the implementation progress of the SD4E project, notably the role of the IPMG on Human Capital Development as an effective platform for policy coordination, the advancement of the legal and regulatory framework, and the collaboration with the Swiss Federal University for Vocational Education and Training (SFUVET) in strengthening capacity building and expertise within Albania’s VET system.

In addition, Mr. Roquette welcomed the emergence of new ideas during the discussion, including the request to explore the impact of artificial intelligence on employment and skills policies.

In concluding his remarks, Mr. Roquette congratulated the SD4E project team for its work and for effectively integrating the project’s interventions within the broader framework of UNDP’s engagement in Albania.

Ms. Grazhdani then took the floor and thanked the Steering Committee members, particularly the representatives of the Government, for the clear articulation of needs, the guidance provided, and for openly communicating the feedback and concerns received from beneficiaries. She also highlighted the excellent collaboration between the two implementing organizations.

Ms. Grazhdani emphasized Swisscontact’s commitment, as an organization, to continue its engagement in Albania beyond 2027. In closing, she congratulated the Skills for Jobs team for their energy, dynamism, and dedication, and expressed appreciation to SDC and the Government of Albania for their continued support.

Concluding Remarks

In his concluding remarks, Mr. Philipp Arnold, Deputy Head of Mission of the Embassy of Switzerland in Albania, emphasized that the rich discussion had covered a wide range of important topics. He underlined the need to keep in mind the broader context of Albania’s EU integration process, highlighting in particular the contribution of both projects to the targets under the Human Capital Pillar of the EU Reform Agenda, which he encouraged the projects to continue supporting.

At the same time, Mr. Arnold noted that these developments add to the complexity of the reform agenda and require careful alignment of interventions with the specific mandates and implementation timelines of both projects. While acknowledging the strong progress achieved, he stressed the importance of respecting the distinct mandates of each project.

Mr. Arnold expressed his appreciation to the Government counterparts for taking the lead in the reform process, while noting that the teams of both projects, together with SDC and the two implementing organizations, provide support in understanding the starting point and direction of reforms—most notably through the provision of skills intelligence for evidence-based policymaking, which he described as a key legacy of the projects.

Mr. Arnold further highlighted that the main challenge lies in balancing the pace of reforms with the respective stages of implementation of both projects. He noted that while flexibility would be applied to address certain requests, this would need to be done within the framework of available resources.

As SDC’s support to vocational skills development in Albania is approaching its endline, Mr. Arnold welcomed the fact that the strategic roadmap for dual VET foresees actions beyond 2028.

In concluding his remarks, he emphasized the importance of ensuring that the results and progress achieved by both projects are fully owned by the Government partners, with SDC providing support. He thanked the teams of both projects and the Government partners for their commitment and collaboration.

Ms. Olta Manjani, Deputy Minister of Economy and Innovation, concluded the meeting by thanking all participants for the collaboration, and in particular the Ministry team and the two agencies for their work during 2025, which contributed to achieving the milestone of one in five students attending VET in 2025. She expressed her confidence that, with the continued support of the two projects, further progress would be achieved in 2026.

Mr. Eno Ngjela then formally closed the meeting and invited all participants to a joint lunch and networking.

Annexes to the Minutes of Meeting – Third Joint Steering Committee, December 11, 2025

- List of Participants

- Presentation of Annual Progress 2025 and Yearly Plan of Operations 2026 – SD4E

- Presentation of Annual Progress 2025 and Yearly Plan of Operations 2026 – S4J

- Yearly Plan of Operations (Annual Work Plan) 2026 – SD4E

- Yearly Plan of Operations 2026 – S4J

- Presentation on dual VET Roadmap

List of participants

| - Ms. Olta Manjani | Deputy Minister, Ministry of Finance and Economy (MEI) |
| --- | --- |
| - Mr. Philipp Arnold | Deputy Head of Mission, Embassy of Switzerland |
| - Mr. Francisco Roquette | Deputy Resident Representative, UNDP Albania |
| - Ms. Argjentina Grazhdani | Country Director, Swisscontact in Albania |
| - Ms. Silvana Mjeda | National Programme Officer, Embassy of Switzerland |
| - Mr. Albin Gega (Apologized) | Director General, Employment, VET and Social Insurances Policies, MEI |
| - Ms. Jorgjeta Marko | Director of Employment and Migration Policies, MEI |
| - Ms. Stavri Lako | Director of VET Policies, MEI |
| - Ms. Ejvis Gishti | Director General, National Agency for VET and Qualifications (NAVETQ) |
| - Mr. Klevis Hysa | Director General, National Agency for Employment and Skills (NAES) |
| - Mr. Eno Ngjela | Inclusive Growth and Employment Programme Specialist, UNDP |
| - Mr. Fation Dragoshi | Project Manager, S4J, Swisscontact |
| - Ms. Sonila Limaj | Programme Coordinator, SD4E, UNDP |
| - Ms. Silvana Haxhiaj | VET Coordinator, SD4E, UNDP |
| - Ms. Aleka Papa | Transferability Portfolio Manager, S4J, Swisscontact |
| - Mr. Oltjon Valisi | Key Expert on dual VET, S4J, Swisscontact |
| - Ms. Eriola Shingjergji | Line Manager for Digitalization of VET, S4J, Swisscontact |
| - Ms. Edi Bregu | Project Assistant, SD4E, UNDP |

World Bank, 7 October 2025, Western Balkans Regular Report No.28, Fall 2025, Albania Factsheet, https://thedocs.worldbank.org/en/doc/7d1d0d8ab5c519adee05b0519352f840-0080012025/original/WB28-FC-EN-01-1-ALB.pdf

INSTAT, Labour Market 2024, https://www.instat.gov.al/en/publications/books/2025/labour-market-2024/

The target is “Partially achieved” when 60% of target is reached; Target is “Not Achieved” when less than 60% of target is achieved; target is “Fully achieved” when 100% or more of target is achieved.

The target is “Partially achieved” when 60% of target is reached; Target is “Not Achieved” when less than 60% of target is achieved; target is “Fully achieved” when 100% or more of target is achieved.

All indicators mentioning vulnerable groups will be disaggregated by groups, i.e.: Ndihma ekonomike, PwD, Roma and Egyptians, long-term unemployed, women and other.

The target is “Partially achieved” when 60% of target is reached; Target is “Not Achieved” when less than 60% of target is achieved; target is “Fully achieved” when 100% or more of target is achieved.

## Disclaimer: Data contained in this financial report section is an extract of UNDP financial records. All financial provided above is provisional.

The impact on employment and the employment rate of beneficiaries of the cohort 2020-2022 will be assessed in view the ALMP Impact Asssesmsent by Q4 2024. This impact assessment will serve to define national baseline and set the target.