# Annex: 12

# Project Title:

# Generating multiple benefits through strengthened protection of primary forest landscape in Lao PDR

# Process Framework

United Nations Development Programme-Laos

Department of Forest, Ministry of Agriculture and Forestry

May 2024

Abbreviations

| DAFO | District Agriculture and Forestry Office |
| --- | --- |
| DoF | Department of Forestry |
| DoNRE | District Natural Resource and Environment |
| EIA | Environmental Impact Assessment |
| ESMF | Environmental and Social Management Framework |
| FGD | focus group discussion |
| FPIC | free, prior and informed consent |
| GAP | Gender Action Plan |
| GRM | grievance redress mechanism |
| IPPF | Indigenous Peoples Policy Framework |
| LAF | Livelihoods Action Framework |
| M&E | Monitoring and Evaluation |
| NTFP | non-timber forest product |
| PA | protected area |
| PF | Process Framework |
| PIU | Project Implementation Unit |
| PMU | Project Management Unit |
| REDD+ | Reducing Emissions from Deforestation and Forest Degradation |
| SEP | Stakeholder Engagement Plan |
| SES | Social and Environmental Standards |
| UNDP | United Nations Development Programme |

Contents

Abbreviations	i

Contents	ii

Annexes:	iv

Figures	iv

Table	iv

1	Introduction	5

1.1	Project description	5

1.2	Project components	6

2	Participation implementation	7

2.1	Assessment	7

2.2	Participation processes	7

2.3	Key stakeholders	8

3	Potential impacts and affected persons	9

3.1	Potential adverse impacts	10

3.2	Potential positive impact	11

4	Eligibility criteria	12

4.1	Avoidable criteria	12

4.2	Acceptable criteria	13

4.3	Eligible livelihoods assistance	13

4.4	Ineligible livelihoods assistance	14

4.5	Cut-off date	15

5	Mitigation measures and alternative livelihoods assistance	15

5.1	Assessment measures	15

5.2	Mitigation measures	16

5.3	Potential livelihood options	16

6	Grievance redress mechanism	19

7	Implementation and monitoring arrangements	20

7.1	Implementation arrangements	20

7.2	The role of UNDP	21

7.3	Project Management Unit (PMU)	21

7.4	Environmental and social team	21

7.5	Project coordination	22

8	MONITORING, EVALUATION AND REPORTING	23

Annexes:

Annex 1: Conducting the FPIC process.	27

Annex 2: Facilitator’s guide for conducting meaningful consultation with ethnic minority peoples	29

Annex 3 Grievance Redress Mechanism	32

Annex 4: Proposed consultation approach with community members	42

Figures

Figure 1: Organization chart	19

Table

Table 1. Demography of potentially affected populations	8

Table 2: Potential livelihood activities	15

Table 3: SES implementation responsibilities	21

Table 4: Monitoring and Evaluation Plan	23

# Introduction

This Process Framework (PF) is developed for the project “Generating multiple benefits through strengthened protection of primary forest landscape in Lao PDR”. The purpose of the PF is to establish a process for members of potentially affected communities to participate in the design of project components, and to determine measures necessary to address the requirements of UNDP SES Standard 5 in the implementation and monitoring of relevant project activities. It focuses on addressing potential restrictions on access to natural resources in the proposed project-protected areas and primary forest landscapes.

In addressing situations where project activities might limit access to natural resources within protected areas, the framework ensures that the rights and interests of local communities, especially ethnic groups, women and other marginalized groups who depend on these resources are considered and addressed throughout the project cycle. The PF expects to assist the project to:

Promote social equity by ensuring that the voices and needs of local ethnic groups and communities are heard and considered in decision-making processes related to protected areas/primary forest landscapes;

Mitigate negative impacts by helping to minimize potential disruptions to livelihoods caused by limitations on resource access; and

Enhance project sustainability by fostering community ownership and participation, the framework contributes to the long-term success of conservation efforts within protected areas/primary forest landscapes.

The PF provides a description of the project and the specific components or activities that might lead to limitations on resource access within the scope of project influence. The framework provides a structured approach for involving communities that may be affected by the project in its decision-making process. This includes conducting consultations with community members to gain an understanding of their dependence on specific resources, their traditional practices, and any potential concerns they may have regarding access restrictions. The project will pay attention to the process of reaching joint decision-making by working collaboratively with communities to determine:

Potential restrictions to access and use of resources in forest areas/primary forest landscapes resulting from project activities

Potential positive and negative risks and impacts

Avoidable and acceptable levels of resource use within the restricted areas

Measures to address the potential negative impacts on livelihoods caused by access limitations

Management arrangements to ensure sustainable use and conservation of primary forest landscapes.

## Project description

The project “Generating multiple benefits through strengthened protection of primary forest landscape in Lao PDR” is part of the regional GEF-8 Indo-Malay Critical Forest Biome Integrated Program. The overall objective is to generate multiple benefits through strengthened protection of primary forest landscapes in Lao PDR.

The project will be implemented as a 6-year programme from 2025 to 2030 in, and around, four protected areas (Pas), also known as National Protected Areas (NPAs). Three PAs – Phu Xang He (114,951 ha), Xe Bang Nouan (129,790 ha), and Phu Xiang Thong (105,996 ha) – were established through Decree No. 164 on October 29, 1993. The fourth PA – Xe Sap (152,959 ha) – was established through Decree No. 210 on February 9, 1996.

## Project components

The project is composed of six components which are briefly outlined below. For further details please see the UNDP Project Document.

Component 1: Enabling environment for ensuring durable protection of primary forests landscapes. This component comprises four outputs. Output 1.1: Formulate national policy linked to 2035 NFS to formally recognize primary forest landscapes; Output 1.2: Primary forest landscapes incorporated into landscape planning mechanisms; Output 1.3: Development and roll-out of capacity-building programme on emerging tools and approaches to primary forest landscape integration into land use planning mechanisms and; Output 1.4: An integrated management strategy for Annamite Range developed. Combined the project outputs are expected to deliver the following outcome: Enabling environment strengthened for integrating primary forest landscapes into forest management and land use planning.

Component 2: Strengthening management and governance capacities for empowering local communities for management of protected areas. This component comprises five outputs. Output 2.1: Area-based conservation approaches promoted for ensuring improved management of primary forest landscapes; Output 2.2: Strengthened management of protected areas; Output 2.3: Training to strengthen management and governance capacities delivered; Output 2.4: Local communities, women and ethnic groups empowered through sustainable livelihood opportunities and collaborative management approaches; and Output 2.5: Gap analysis conducted and opportunities to strengthen the protected area network through creation of corridors and other effective area-based conservation mechanisms.

Component 3: Improved/inclusive management of primary forests outside PAs, including buffers and connectivity corridors. This component comprises four outputs. Output 3.1: Create effective collaboration with multiple stakeholders to recognize and integrate primary forest landscapes in development decision-making; Output 3.2: Village management plans for improving management practices and restoration of primary forest landscape edge areas developed and implemented; Output 3.3: Good agricultural practices adopted and producer-public-private partnerships in forest and agricultural value chains facilitated; and Output 3.4: Feasibility assessment to recognize other effective area-based conservation mechanisms (OECMs) as long-term strategy though community conserved areas (CCAs), indigenous and community conserved areas (ICCAs), sacred forests and other categories.

Component 4: Strengthen sustainable PA financing and reduce the financial gap and scaling-up investments for primary forest conservation. This component comprises three outputs. Output 4.1: Conservation financing expanded and diversified; Output 4.2: Feasibility of innovative financing instruments tested and applied; and Output 4.3: Capacity-building to assess and apply financial instruments for primary forest conservation.

Component 5: Coordination, knowledge management and strengthened effective regional cooperation on durability of primary forests. This component comprises three outputs. Output 5.1: Project communication and awareness strategy and action plan implemented; Output 5.2: Implementation of knowledge management activities; and Output 5.3: Participation in, and contribution to Integrated Program Community of Practice ensured.

Component 6: Project monitoring, evaluation and reporting ensured. This component has one output. Output 6.1: Project monitoring and reporting.

# Participation implementation

This PF will be implemented in parallel with the project’s Environmental and Social Management Framework (ESMF), Livelihoods Action Framework (LAF), Stakeholder Engagement Plan (SEP), and Gender Action Plan (GAP). The SEP outlines a structured approach to engaging various stakeholders meaningfully, effectively and inclusively throughout the project life cycle. It serves as a road map for communication, collaboration and decision-making with individuals or groups who may be affected by or can influence the project's success. The SEP aims to ensure that projects are designed and implemented in a way that is inclusive, responsive and sustainable, and promotes positive social and environmental outcomes for all stakeholders involved.

## Assessment

The Project has conducted a social and environmental screening procedure, consulting and engaging with 44 communities to provide basic information about the project. Consultations were conducted to understand the socio-economic situation and available livelihood resources in the target areas. The project identified that most people that potentially could be negatively affected by project activities belong to various ethnic groups, which share similar characteristics to indigenous people as defined by UNDP SES Standard 6 on indigenous peoples. The consulted communities were engaged in the inception workshop and during field missions. Focus group discussions (FGDs) were categorized into four types of community characteristics: (1) village authority group; (2) general women's group; (3) general men's group; and (4) vulnerable group. The vulnerable group comprised representatives of households that have insufficient income generation for sustaining livelihoods, insufficient rice production for consumption, female heads of households, limited labour in households, or disabled individuals in their families.

Due to the current social and cultural situations of ethnic communities in the target areas, decision-making is normatively dominated by men and the elderly. Therefore, there is a lack of representation from women and youth in the PPG-defined group discussions. The project, therefore, will ensure that youth, women and vulnerable groups are included in the participation and consultation process to empower them to be part of the decision-making processes.

## Participation processes

The Project has been rated Substantial Risk due to the impact on ethnic groups. Since the Project is classified as Substantial, UNDP SES standards require scoped environmental and social impact assessment of appropriate scale and elaboration of an Ethnic Groups Planning Framework (EGPF) and FPIC processes. Targeted assessments may also be conducted to address certain potential specific risks related to ethnic groups spiritual sites and intangible cultural heritage, including traditional knowledge; ethnic group’s traditional forest management and forest despondency. The Project has developed an EGPF and SEP, which also include the FPIC process and meaningful consultation procedures to effectively engage potential economically displaced persons. The FPIC processes outlined in Annex 1 and the meaningful consultation described in Annex 2 will enable affected individuals and communities to collaborate with the Project. This collaboration will involve identifying forest areas for conservation and management, mapping, zoning, planning, determining potential access restrictions, agreeing on mutually acceptable levels of resource use, establishing management arrangements, and devising measures/livelihood options to address the impacts on affected communities and individuals. During this process, the Project and affected communities will also identify areas for co-management as it is expected that some of the identified forest landscape areas will contain plots that are currently used by the communities (such as paddy fields inside primary forest landscapes). The Project can then include these areas in its management/protected targets.

FPIC safeguards the collective rights of ethnic groups, ensuring their self-determination, consultation and participation in decisions affecting them, especially regarding their lands and forest resources. The process is crucial for protecting vulnerable groups and their environments. Conducting FPIC demonstrates respect for local communities and fosters inclusive decision-making. It improves project design by incorporating diverse perspectives, identifying risks, and fostering support and long-term success through engagement and addressing concerns.

Meaningful consultation encompasses a two-way communication process that (a) will begin early in the project’s activity/interventions implementation design to gather initial views on the main aspects of the project activities/interventions and their design; (b) encourages stakeholder feedback, particularly as a way of informing said design and engagement by stakeholders in the identification and mitigation of environmental and social risks and impacts; (c) continues on an ongoing basis as risks and impacts arise; (d) is based on prior disclosure and dissemination of relevant, transparent, objective, meaningful and easily accessible information in a timeframe that enables meaningful consultation with project stakeholders in a format culturally appropriate, in relevant local language(s) and is understandable to stakeholders; (e) considers and responds to feedback; (f) supports active and inclusive engagement with project-affected parties; (g) is free of external manipulation, interference, coercion, discrimination and intimidation; and (h) is documented and disclosed by the project.

The Project will carry out meaningful consultation as described above before each project activity to ensure inclusiveness, transparency and effectiveness with stakeholders throughout the project life cycle. This will be monitored through lists of invitations and participation in various activities together with the meeting records of issues discussed and how the Project addresses issues and concerns raised by various actors.

Guidelines on how to effectively engage various key affected communities are included in Annex 4 and steps/strategies on how to incorporate the view of vulnerable and marginalized groups are included in Section 5.3 of the SEP.

## Key stakeholders

The project SEP which will be used in parallel with this PF has analysed and identified key relevant stakeholders. The SEP includes roles and responsibilities and how each stakeholder is associated with the project, as well as the methods of participation and decision-making processes., This PF aligns with the project ESMF and SEP and pays particular attention to the processes of how to effectively engage women, ethnic groups, youth, people with disabilities and other marginalized groups. Decision-making may include the establishment of representative local structures, the use of open meetings, and the involvement of existing local institutions, ensuring that marginalized/vulnerable groups (such as women and youth) can participate in decision-making processes. Methods of consultation and participation are designed to be gender sensitive and culturally appropriate for affected communities.

Key actors to be engaged in the consultation and decision-making processes (including FPIC) will include but are not limited to the following: (1) representatives of the Project at the local level, including the social and environmental focal points; (2) representatives of ethnic groups; (3) village authorities; (4) youth; (5) women; (6) men; (7) vulnerable groups; and (8) other relevant government authorities such as land and forest authorities. The engagement of key relevant actors will help the Project to establish a transparent and participatory process for addressing restrictions of access to natural resources within the project’s proposed forest areas. This process ensures that the rights and interests of local communities, especially ethnic groups, women and other marginalized groups, who depend on these resources are considered and addressed throughout the project cycle.

# Potential impacts and affected persons

With a risk rating of Substantial based on the SESP, the Project has the potential to affect 156 villages, 22,406 households, and a population of 127,374 (including 64,278 females). At the same time, villages both inside and outside the PA will benefit from the sustainable financial programme for forest management in the long term, as well as receive livelihood support from the programme.

Project areas are located in rural forested areas where rural ethnic communities reside. As such, vulnerable and poor households make up a significant part of the project’s intended beneficiaries. Vulnerable groups are more likely to be adversely affected by restrictions of access and loss of customary tenure. They are likely to have limited ability to re-establish their livelihoods or improve their status. These include female-headed households with no labour, households headed by a person with a disability, households headed by the elderly with no labour, households with an annual rice deficit for more than seven months or households with a monthly income per capita below the national poverty line. The assessment found villages inside the protected areas have more vulnerable households than those in the buffer zone.

Detailed descriptions of how to engage vulnerable households as key beneficiaries are provided in the project SEP. However, it is important to note that lessons learned, desk reviews and field assessments suggested that the poorest and most vulnerable families often do not join meetings or take part in project activities. This could be because of a lack of confidence or lack of time as they must be working in the field. It is also possible that they have had adverse experiences when they do join a meeting, such as being excluded and not being respected by other members of the group or being discouraged from joining the discussion by other members. The SEP has included special measures on how to effectively engage the vulnerable and poor in all project activities identified that will potentially affect them.

Table 1. Demography of potentially affected populations

| Categories | Phou Xang He | Xe Bang Nouane | Phou Xieng Thong | Xe Sup | Total |
| --- | --- | --- | --- | --- | --- |
| Areas (ha) | 114,951 | 129,790 | 105,996 | 152,959 | 503,696 |
| No. district | 4 | 6 | 3 | 3 | 16 |
| No. villages | 48 | 37 | 47 | 24 | 156 |
| Villages inside | 4 | 3 | 6 | 7 | 20 |
| Villages surrounding and nearby | 44 | 34 | 41 | 17 | 136 |
| No. household | 6,370 | 5,415 | 9,075 | 1,546 | 22,406 |
| Total population | 38,276 | 31,456 | 47,119 | 10,523 | 127,374 |
| Female | 19,370 | 15,694 | 24,100 | 5,114 | 64,278 |

## Potential adverse impacts

Inside the PAs, the population comprises various ethnic groups that depend heavily on forests, lands and other natural resources. These ethnic groups are highly dependent on the forest and natural resources. They mostly belong to the Mon-Khmer ethnic group (such as the Brue/Brow, Katang and Makong) and often have lower incomes as well as lower social and political status (partly due to isolation and language barriers) and experience difficulties due to access, culture and language differences when compared to the Lao-Tai groups such as the Lao and the Phouthay. The Project may generate adverse impacts on these ethnic villagers who live in the target areas, including the PAs. The UNDP SESP identified a total of 11 risks, two of which has been rated as Substantial, six Moderate, and three as Low:

Risk 1: Enabling regulations, policies, and land planning activities (Components 1 and 2) aimed at ensuring the integration of primary forest landscapes in the mainstream of government decision-making may restrict current access to resources, leading to economic displacement and changes to customary rights to land, territories and/or resources (Standard 5.2 and 5.4), which could have adverse impacts on the intangible cultural heritage and food security of communities, including vulnerable groups. This risk triggered SES Standard 5 and is rated as Substantial.

Risk 2: Project activities (such as Activities 1.1.3; 1.4.2; 2.1.2; 2.3.1-2; 3.2.3-4) may lead to discrimination against ethnic minority groups (within a village with mixed different ethnic groups), vulnerable or marginalized groups or other key stakeholders (women, youth, people with disabilities) (P.5), leading to their exclusion from project activities, thus preventing them from accessing project benefits. This risk triggered SES Standards 6 and 7 and is rated as Substantial.

Risk 3: Project interventions (Component 2, Activity 3.3.8 and Output 5.2) may not fully integrate or reflect the views of women and girls (P.10) and may not guarantee equitable opportunities for their involvement and capture of project benefits. This risk triggered SES Standard 6 and is rated as Moderate.

Risk 4: Some of Component 2 and Component 3 activities may reinforce existing gender-based inequalities (P.12) related to access to natural resources and benefits. This risk triggered the SES overarching principle of Human Rights and is rated as Moderate.

Risk 5: Project activities (such as Activities 2.1.3; 2.4.3; 3.1.4) may have an impact on intangible Cultural Heritage, disturbing sacred /spiritually significant forests/sites, thus weakening bonds between ethnic communities and their ancestors, and breaking down traditional values and cultural diversity. This risk triggered SES Standard 4 and is rated as Moderate.

Risk 6: Project on-the-ground activities under Component 2 and 3 (Activities 2.1.4; 2.2.3; 3.3.1) may expose villagers/farmers vulnerability to the impact of climate change – including extreme weather events such as flood, storm and drought hazards (Outputs 2.1 and 2.2) thereby reducing local resilience and adaptation potential. This risk triggered SES Standard 2 and is rated as Moderate.

Risk 7: Project activities associated with law enforcement and monitoring framework (Activities 2.2.3; 2.3.2) could lead to human rights abuse by poorly trained rangers (3.8), especially in social, cultural and conflict management skills. This risk triggered SES Standard 3 and is rated as Moderate.

Risk 8: Promoting small agriculture and tourism entrepreneurs at the community/district level, as well as livelihood support programme under components 2 and 3 (e.g. Activity 2.4.5) could unintentionally involve child labour (7.3). This triggered SES Standard 7 and is rated as Moderate.

Risk 9: There is a risk that alternative livelihood activities to be introduced at demonstration sites (Activities 3.3.1–8) may exacerbate environmentally sensitive areas or biodiversity (S1.1), leading to adverse impacts to habitat loss, modified forest landscapes, ecosystems and ecosystem services, fragmentation and hydrological changes. This risk triggered SES Standard 1 and is rated as Low.

Risk 10: Private sector involvement (Activity 1.3.3) for potential record of human rights violations (P.4) may cause social or environmental harm in the project areas. This risk triggered the SES overarching principle of Human Rights and is rated as Low.

Risk 11: Some project Output Activities (2.1; 2.2.2, 2.2.3 and 3.3.1) may facilitate wildlife trading and may lead to extraction of natural resources such as honey, wild orchid and other NTFPs. These activities may also have an impact on endangered species, invasive alien species (IAS), changing soil and forest landscape formation and other unintended impacts may also increase. This risk triggered SES Standard 1 and is rated as Low.

## Potential positive impact

The Project will allocate significant resources to communities and villagers who live inside or near the four PAs. This includes women, men and young people. The Project aims to improve the livelihoods of villagers through the sustainable management of resources. They will receive financial support for forest restoration, forest maintenance, and both technical and financial assistance for resilient livelihoods.

The Project aims to create an inclusive environment for PA management, involving women, youth, and vulnerable groups. They will have the opportunity for capacity-building and possible benefits from participating in decentralized forest management (Activities 2.1.2., 2.2.2., 2.2.5., 2.3.4. and 2.4.6.).

In the target areas, the Project will support the development of sustainable livelihoods programmes for all communities. These communities will receive capacity-building in agriculture, livestock, sustainable harvesting of non-timber forest products (NTFPs), eco-tourism, and value chains related to significant products in their communities. The Project will provide technical and financial support to help communities build better livelihoods, improve food security, access better financial sources, enhance agriculture and livestock products, and gain better access to markets and networks (Activities 3.3.1., 3.3.2., 3.3.3., 3.3.4. and 3.3.5.).

The Project will also contribute to job creation in forest restoration, forest connectivity programmes, forest conservation and forest monitoring. These efforts are part of a long-term financially sustainable framework where communities can benefit from Payment for Ecosystem Services (PES), Reducing Emissions from Deforestation and Forest Degradation (REDD+), carbon credit, and Clean Development Mechanism programmes (Activities 3.2.4., 3.2.5., 3.2.6., 4.1.4., 4.2.2. and 4.3.2.

Additionally, the project aims to support the documentation and conservation of traditional knowledge among ethnic groups. It also has the potential to disseminate the best traditional knowledge of ethnic people, including rituals, herbal medicine and other practices (Activities 5.3.3. and 5.3.4.).

Overall, the Project expected that the primary forests will be restored, enriching biodiversity and ecosystems in the target areas, thereby generating more food sources, income sources and material sources for the long term. Consequently, community livelihoods will improve, enhancing resilience to climate change.

# Eligibility criteria

In the processes of identifying primary forest landscapes for sustainable management, the Project will promote practices that ensure the long-term health and productivity of the forest ecosystem. Restrictions on accessibility to natural resources are difficult to avoid and it may involve techniques like selective collection of NTFPs, reduced hunting, fishing, logging and reforestation efforts. The access restrictions can be managed through a benefit-sharing plan that contains regulations on avoidable and acceptable levels of resource use within the restricted areas. The Project will ensure that benefits derived from the forest, NTFPs and carbon credits, should be shared equitably among stakeholders. This helps ensure local communities have a vested interest in the sustainable management of the forest. The Project will also ensure transparency in decision-making processes and accountability for all stakeholders involved. This includes mechanisms for monitoring progress, reporting on impacts and addressing grievances.

## Avoidable criteria

To avoid adding pressure to existing issues or causing tension and conflicts, the Project must follow certain criteria when identifying forest landscapes for conservation, biodiversity corridors, mapping, zoning and forest/land use planning. At all times, the Project will not involve land acquisition, structures, and/or physical resettlement. And throughout the project cycle, the Project will not include forest/land that is:

legally, illegally, or in use through customary rights, with or without any disputes, and/or have paid land tax, to avoid land acquisition;

affecting a structural asset of an individual, community and/or entity;

currently used by individuals, communities, entities and/or organizations for commercial plantations such as rubber, cassava, eucalyptus, etc.;

large areas of paddy land customary owned by the affected communities inside and adjacent to the protected areas;

used by vulnerable households;

preserved for national security and/or military purposes;

planned for economic development zones;

under concession agreements of any kind (hydropower development, mining extraction, etc.);

planned for resettlement either resulting from development investment projects or government relocation policies;

at risk from project activities that potentially damage or cause loss to cultural property, such as archaeological, palaeontological, historical, religious and cultural sites, as well as sites with unique natural value;

community forest/land such as grazing land, fishpond, temples,

if the identified forest landscapes, project activities and interventions have the potential to result in affecting land acquisition, land tenure rearrangement and/or asset, the activities must be cancelled.

## Acceptable criteria

Although some restrictions will be in place for primary forest landscapes selected by the project, the community still has the right to continue using the forest areas as specified in the forest management plan. The acceptable levels of resource use and collection within the restricted areas should meet the following criteria:

Selective collection: Collection should target specific resources in a way that minimizes damage to the ecosystem (e.g. broom grass and/or forest resources that are agreed upon among the community and the Project during FPIC processes).

Livelihood needs: Collection should primarily support the livelihoods of local communities who depend on the forest for subsistence or income generation.

Minimized impact: Collection methods should be employed that minimize negative environmental impacts, such as avoiding soil erosion, wildlife disturbance and/or depletion of resources.

Sustainable levels: Collection should occur at levels that allow for forest regeneration and do not lead to depletion of resources.

Co-forest management: If the project identifies forest landscapes for project activities, which are owned by individual households/communities, the Project may engage them through a project co-forest management scheme whereby they can continue to use the forestland while benefiting from conservation development to ensure sustainable use and increase carbon stock in the target areas.

Compliance with regulations: Collection must comply with all relevant UNDP SES standard requirements, national laws and regulations governing forest resource use and the project’s co-forest management plan.

## Eligible livelihoods assistance

This section describes the eligible criteria for livelihood assistance from the Project. The assistance is related to project impacts resulting from restriction of access and economic displacement. It does not apply to existing community conservation, and/or activities driven by the community that are not related to project interventions.

Livelihoods assistance will be defined based on the results of FPIC, meaningful consultation as well as feasibility studies and scoping reports for each affected PA and adjacent to the PAs. The Project has developed a standalone livelihood development framework that outlines different livelihoods assistance options, which will be tailored to the actual impacts, eligibilities and needs. For instance, assistance options for those who depend heavily on natural resources for daily subsistence may include permission to continue using selective forest resources. This option would be conditional on meeting specific acceptable criteria and combined with project assistance such as smart/stable/sustainable agriculture techniques like home gardens to secure daily food consumption.

Affected peoples (individuals, households and/or a village) will be eligible for livelihoods assistance if they meet any of the following criteria:

have lost or experienced economic displacement, where livelihoods are affected by project intervention

experience a loss of their sources of food, material and income generation due to the project intervention

have lived and stayed before the official establishment/declaration of the PA and the cut-off dates

have livelihood sources from restriction zones and corridor zones

reside inside and/or share a boundary with the PA or potential corridor areas

use resources for livelihoods and income generation from non-illegal items such as broom grass, red crab, resin, red ant eggs, frogs

own and feed cattle in identified core zones and corridor zones, but have been restricted cattle feeding in some selected zones by the project

have insufficient rice consumption for over six months per year and limited alternative livelihoods

fall under the vulnerable groups defined by the Project and government such as the poorer, female heads of households without assistance or income, and persons with disability without assistance.

other criteria which have discussed and agreed through meaning consultations and FPIC process

## Ineligible livelihoods assistance

The following criteria describe affected peoples who are ineligible for livelihoods assistance and include those who attempt to gain benefit from project interventions or engage in unsustainable use of natural resources, violate practices or reside outside of the project areas. Additionally, affected people who claim assistance from the Project after the declaration of the cut-off date will be channelled through the GRM. Ineligible affected people include:

Poachers of any kind, including those within or outside the community who engage in sport and illegal hunting for illegal business, such as hunting Eld's deer, elephants and tigers for sale.

Any individual, community and/or entity who encroaches on protected areas for clearing land for cassava plantation, rubber plantation and other activities that have been illegally implemented in recent years without historical proof of tenure rights.

Traders and poachers who generate income through active wildlife hunting for commercial purposes, including illegal logging from protected areas.

Cattle owners who live outside the target project areas/villages.

People who lose income, land tenure and assets that are not related to project interventions or project activities.

Community forest conservation, which is derived by the community, not by the Project

other criteria which have discussed and agreed through meaning consultations and FPIC process

## Cut-off date

A cut-off date will be established by the Project. It is the date of public notification regarding the specific activities such as forest landscape identification, mapping, zoning and land use planning that would cause displacement and access restrictions, regardless of the scope and size of its activities. The cut-off date will be:

announced after affected people within the project area boundaries are identified and prior to the commencement of project implementation.

specific for each community after the completion of the feasibility studies, scoping report and FPIC processes.

the date after an agreement has been reached through FPIC process (and/or meaningful consultation)– declaration letters will be issued by the district governor, with the support of the Project, and the date will be communicated within the affected community.

different for each affected area/village, as it will only be issued after the FPIC process has been concluded.

Affected persons/households who are affected resulting from project restriction and/or economic displacement after the cut-off date and are not recorded by the project will file their claim through the GRM.

# Mitigation measures and alternative livelihoods assistance

## Assessment measures

In line with the SES, and due to the Substantial overall risk category, scoped Strategic Environmental and Social Assessments (SESA) and scoped Environmental and Social Impact Assessments (ESIA), and other required targeted assessments will be undertaken by the Project.  The Project will hire qualified subcontractor (or consultants) to conduct required SESA, ESIA and other assessments, which are tailored assessments that analyzes the potential E&S impacts associated with the policy change/reform that would lead to restrictions on accessing natural resources, economic displacement and other adverse effects, which may include changes in social organization and belief/ritual systems of the communities and the ethnic groups. During these assessment processes, community consultation in the form of meaningful consultation and FPIC will be carried out. Inventories of forest resources will be developed and recorded by the Project. The project will strictly follow the UNDP SES toolkits for assessments, which include but are not limited to the following:

Legal framework related to restrictions: analyse laws, regulations, and permits governing access to the resource.

Physical restrictions: evaluate natural barriers (territories, landscapes, water bodies).

Social restrictions: assess how access restrictions disproportionately affect specific user groups, particularly vulnerable populations, traditional spiritual practices, cultural norms.

Livelihoods: evaluate how limitations affect the ability of user groups to rely on the resource for income or subsistence.

Conservation: how restricted access might affect resource management and conservation efforts.

Other methods that may be appropriate for specific types of assessments to assess cultural values and traditional knowledge, such as ethnic groups religious/beliefs, sacred sites or ancestral lands. These methods may require specific experts such as social anthropologists to carry out assessment.

## Mitigation measures

In line with UNDP SES guidance, the project will use a structured approach to environmental and social management and will apply the mitigation hierarchy whereby the project is (a) anticipating and avoiding risks and impacts; (b) where avoidance is not possible, minimizing or reducing risks and impacts; (c) once risks and impacts have been minimized or reduced, mitigating them; and (d) where residual adverse impacts remain, compensating for or offsetting them, where technically and financially feasible. The Project will also seek to enhance positive impacts where possible, and therefore maximize sustainable development gains. Mitigation measures for economic displacement and natural resource restrictions are crucial for ensuring that the Projects are conducted responsibly.

For natural resource restrictions, in line with the Project objectives, it will implement sustainable resource management practices that ensure the long-term health of the resource while allowing for continued acceptable access. The project will also explore possibilities for providing the best suitable alternative sources of income or resources for affected communities. This could involve introducing new, sustainable resource uses or facilitating access to resources in other areas and/or engaging local communities in managing the resource that aims to foster a sense of ownership and encourage sustainable practices. This process can also allow the Project to incorporate traditional knowledge and ethnic groups’ needs into forest management decisions.

## Potential livelihood options

The results of assessments will lead to the development of Livelihood Action Plan (LAP) that includes livelihood options/packages. The livelihoods described below are the results from stakeholders’ consultations and ESIA conducted in 45 villages during project preparation.  These packages will be used as guiding topics to discuss with, provide for and implement with affected peoples through meaningful consultation and FPIC process

Table 2: Potential livelihood activities

| Livelihoods options | Descriptions/associated issues/benefits | Proposed support activities |
| --- | --- | --- |
| Improved livestock package | Cattle and poultry serve as the main food source and savings accounts for villagers. Seasonal disease outbreaks in cattle and poultry disease lead to loss of food and savings every year. There are four issues related to cattle and poultry disease outbreak: inadequate veterinary services lack of knowledge about feeding techniques food shortages during the dry season insufficient water supply Poultry and cattle are in high demand and easily accessible, allowing villagers to sell their products easily. | Establish individual veterinary businesses. This could be done via financial and technical assistance. Create a network of veterinary services, so they can address animal disease outbreaks. Provide technical support for cattle and poultry feeding, including proper techniques to reduce costs, and emissions and improve productivity and the health of the animals. Provide animal feed through funding and technical support for generating food sources and storage during the dry season. For example, providing seeds and techniques for grass planting and drying for the dry season. Help identify and support water supply for animal feeding during the dry season. The four recommendations above require awareness-raising, capacity-building and both technical and financial support. |
| Industrial/economic tree species plantation | These livelihood activities will help villagers generate a savings account for long-term prosperity. It may not be suitable for all families but will be selected based on customary land rights located in the PA core zones and corridor zones. | Provide incentives for community participation in public and individual forest planting, particularly for economically valuable and endangered species such as agarwood, rosewood and Pterocarpus. |
| Agroforestry and fruit trees | Found to be most suitable for villages where water supply is available, near natural streams. | Provide agroforestry and fruit trees assistance and based on specific suitable locations with specific species that can grow together and provide short-term, medium-term and long-term benefits. Some considerations for economic tree species include rattan or shade-grown coffee and tea, or growing other root crops (sweet potato, potato), herbs and fruit trees (mango, tamarind, cashew nut, longan, rambutan, orange, lemon and even durian). |
| Food sources and alternative income |  | Build on existing NTFPs and the experience of villagers by providing technical and financial support. This can involve activities such as raising red ant eggs, red crab farming, rattan harvesting, mushroom cultivation, frog farming and growing daily vegetables like chilli, onion, garlic and ginger. Provide comprehensive and intensive support specifically targeting households with high interest and aiming at establishing a business model that can be automatically replicated by the community or villagers themselves. The market for these products must be local and resilient to ensure sustainable growth and local consumption, thereby reducing pressure on food sources from primary forest areas. |
| Aquaculture business model |  | Provide support to community businesses where farmers can specialize in aquaculture. The business model should be based on the interests of the villagers and involve providing technical support, infrastructure, equipment, initial medicine and good quality and affordable fingerlings/fry, along with other baby aquatic animals. This business model will help in reproducing food sources and provide an alternative income, indirectly reducing the pressure on forest resources in primary forest areas. |
| Non-farm and non-forest occupations as alternative livelihood support | Most villages have access to electricity and own tractors, motorcycles and electric appliances. However, there is a lack of mechanics and electricians in these communities. | Conduct a study and identify suitable locations to establish businesses that can reduce the cost of repairing and installing electric appliances. This way, communities can rely on technicians within or near their community rather than calling technicians from the city for broken appliances or electrical installations. Engage women in activities such as seam stressing or dressmaking, including weaving and adding value to existing handicrafts by modifying or redesigning them for different products to make them more attractive and unique. |
| Support sustainable forest management and NTFPs for long-term use and benefit |  | Provide specific awareness-raising, techniques for adequate harvesting, value-added processes for the products, and understanding of ecosystem rehabilitation and resilience to climate change. These livelihood activities will ensure the sustainable use and long-term benefits of existing resources while building resilience to climate change. |
| Engage women, youth and men in project activities | This will help ensure the protection and regeneration of primary forests, promoting their health and biodiversity. | Employ women, youth, and men for forest patrolling, reforestation, and reporting illegal activities and encroachments in core-zones and corridor zones. |
| Village Livelihood Fund | This is to activate livelihood activities related to reforestation, agroforestry promotion and climate change mitigation. | Provide initial financial support for villagers who already have customary land use rights. This will allow them to access the Village Livelihood Fund for certain livelihood improvement activities. Provide clear guidelines on how to utilize funds for forest restoration, climate resilience, climate change adaptation and low carbon emission microinvestments at a small scale. |

# Grievance redress mechanism

The Project has established the GRM to meet UNDP SES requirements and is attached as Annex 3. With the updated GRM, the Project will make the GRM easier to access for women, ethnic groups and other vulnerable groups, including those who are illiterate by making sure that VCMUs in project areas consist of females and representatives of ethnic groups. The Project Implement Unit (PMU) will provide training to VCMUs on how to use the GRM and/or assist in processing a complaint from the village, district or province to the national supreme court level. In general, the grievance redress procedures are expected to:

Address concerns promptly and effectively, in a transparent manner that is gender sensitive and culturally appropriate and readily accessible to all project-affected parties, at no cost and without retribution. The GRM process or procedure will not prevent access to judicial or administrative remedies.

PMU will not only provide training to the VCMU but also inform the project-affected parties about the GRM process in the course of FPIC and other community engagement activities, and will make a record publicly available documenting the responses to all grievances received.

PMU will handle grievances in a manner that is gender sensitive and culturally appropriate and is discreet, objective, sensitive and responsive to the needs and concerns of the affected people. The GRM will also allow for anonymous complaints to be made and addressed.

The project GRM includes:

Different ways in which users can submit their grievances, which may include submissions in person, by phone, WhatsApp, text message, mail, email, project website or via the UNDP SES Accountability Mechanism;

A log where grievances are registered in writing and maintained as a database;

Public announcement of procedures, setting out length of time complainants can expect to wait for acknowledgement, response and resolution of their grievances;

Transparency about the grievance procedure, governing structure and decision makers;

An appeals process (including the national judiciary) to which unsatisfied grievances may be referred when resolution of grievance has not been achieved; and

An option where complainants who are not satisfied with the proposed resolution could seek resolution through mediation.

Grievances can be submitted if anyone believes the Project is having a detrimental impact on the community, the environment or on their quality of life. They can also submit comments and suggestions. The PMU will be responsible for receiving and resolving all concerns or complaints with the following broad responsibilities:

Updating, developing and publicizing the grievance management procedures

Receiving, reviewing, investigating and keeping track of grievances

Adjudicating grievances

Monitoring and evaluating fulfilment of agreements achieved through the grievance mechanism.

# Implementation and monitoring arrangements

## Implementation arrangements

Project governance and management arrangements are described in detail in the Project ProDocs. The Project will be implemented in partnership between UNDP and the Department of Forestry, Ministry of Agriculture and Forestry (MAF).

Figure 1: Organization chart

Project Governance Arrangements

Project Board

Development Partner (Supplier)

UNDP Resident Representative- UNDP LAO PDR

Project Executive

Vice-Minister, Ministry of Agriculture and Forestry

Beneficiary Representative

MPI, MoNRE, LCSCC, NGOs, CSOs, Communities in project target areas

Project Assurance

Programme Analyst, NRM, CC and DRR Unit

Head of Programme Support Unit (PSU)

The UNDP CO Focal Point will not be the same person/team as those providing oversight of CO or supporting the RR on Project Board

Implementing Partner

National Project Director (NPD)

Director General, Department of Forestry

Project Support

Project Management Unit (PMU)

- Project Coordinator

- International Technical Specialist

- Admin & Finance Assistant

- M&E Specialist (part-time)

- Safeguards Specialist (part-time)

- Gender Specialist (part-time)

Country Office Support to Implementing Partner

- Operations Manager

- Procurement Analyst

- Finance Analyst

- Administration Associate

- HR Analyst

- ICT Analyst

Theses persons will not be the same person/team as the project assurance or providing programmatic oversight support to the RR.

Responsible Party A

Responsible Party B

Responsible Party C

## The role of UNDP

UNDP is accountable to the GEF for the implementation of this project. This includes overseeing project execution undertaken by the Implementing Partner to ensure that the project is being carried out in accordance with UNDP and GEF policies and procedures and the standards and provisions outlined in the Delegation of Authority (DOA) letter for this project. The UNDP GEF Executive Coordinator, in consultation with UNDP Bureaux and the Implementing Partner, retains the right to revoke the project DOA, suspend or cancel this GEF project. UNDP is responsible for the Project Assurance function in the project governance structure and presents to the Project Board and attends Project Board meetings as a non-voting member. For project SES implementation, the UNDP Social and Environmental Compliance Unit (SECU) will supervise the Project and ensure accountability to individuals and communities. Where applicable, SECU will take the lead in investigating all alleged non-compliance with UNDP’s Social and Environmental Standards and Screening Procedure from project-affected stakeholders and recommends measures to address findings of non-compliance.

## Project Management Unit (PMU)

MAF (and DoF) or the implementing partner is the lead agency responsible for overall project implementation. MAF will provide strategic direction and guidance in project implementation through its Administrative Board which will be established by the Prime Minister. MAF is a secretariat for the government and is responsible for the macromanagement of agriculture, forestry, primary agricultural processing, technical science research, biotechnology, agricultural and forest biodiversity and rural development across the country. DoF will work closely with other MAF departments, which include Department of Agriculture, Department of Agriculture Extension and Cooperatives, National Agriculture and Forestry Research Institute, and Department of Planning and Cooperation. These departments will play a crucial role in coordinating with other sectors to provide updated information on implementation related to forest restoration and water source protection/biodiversity, especially on greenhouse gas emissions from deforestation and forest degradation, and promote carbon credit trading, under the green sustainable direction. The departments will support the Project on matters related to climate change adaptation and resilience of local communities by promoting technical innovative support, technology for cultivation, livestock raising and processing, and organizing farmers in groups or cooperatives. They will give insights on scientific research and technology related to agriculture, forestry, ecology and ecotechnology and rural development.

## Environmental and social team

The Project will recruit an Environmental and Social Specialist who will support PMU in the SESA, ESIA and other targeted assessments to support the development and/or updating of various required SES documents. These may include but are not limited to: ethnic groups assessment, traditional knowledge assessment, restrictions of access and economic displacement assessment, cumulative assessment, social and environmental management plans, community engagement plan, gender action plan, and livelihood action plan. The Project will also recruit a National Social Development Specialist specialized in gender, ethnic groups, livelihoods development and economic displacement. S/he will be supported by environmental and social focal points from each targeted Provincial Department of Forestry and targeted District Department of Forestry. Since all environmental and social focal point persons are existing government staff, they will be required to attend SES training and capacity-building activities, as specified in the project ESMF. The Environmental and Social Specialist and National Social Development Specialist will work closely with the Regional Environmental and Social Specialist to provide support and oversee all SES-related activities and engage on a part-time basis throughout the project cycle. The appointed environmental and social focal points at the provincial and district offices will help oversee all matters related to safeguards on a daily basis and maintain harmonious relationships between various stakeholders, ensuring that the local community is engaged in a gender-responsive and culturally appropriate manner. The recruited environmental and social specialists are responsible for overall planning, supervision, implementation, capacity-building/training and compliance monitoring and reporting of implementation of SES documents (ESMF, IPPF, PF, LAF, SEP, GAP, etc.).

## Project coordination

1. National Project Coordination: Based at DoF in Vientiane Capital and part of the PMU to manage the Project and to coordinate project activities with other ministries, departments and provincial and district line agencies. Each line ministry will have a dedicated project coordination focal point networked to the Project to form a robust multisector team that regularly exchanges relevant information across institutions and sectors. For SES implementation and monitoring, this unit will be intermittently supported by the Senior Environmental and Social Specialist and a National Social Development Specialist who will also be assisting on an intermittent basis.

2. Provincial Project Coordination: A focal point will be appointed in each of the four participating provinces (Savannakhet, Salavan, Sekong and Champasak) at the Provincial Agriculture and Forestry Office (PAFO) to assist in the implementation and monitoring activities, as well as to coordinate work programmes with relevant line agencies and all technical teams at the province and district levels. The tasks also include reporting, convening meetings and workshops, and liaising with provincial and district authorities. For SES, the Project will be supported by Environmental and Social Focal Points from each province.

3. District Project Coordination: A focal point will also be appointed in 16 target districts from the District Agriculture and Forestry Offices (DAFO) to assist and coordinate work plans, reporting, training and tasks with provincial and district staff, as well as assisting in coordinating village-level activities. They will be supported by technical assistance based on requirements and local capacity. At the implementation level, they will be the main taskforce for carrying out ground-level project activities and will be the key actors for liaison with affected communities. For SES, they will be supported by the Environmental and Social Focal Points based at the provincial and national levels.

Table 3: SES implementation responsibilities

| Entity | Main responsibilities and tasks |
| --- | --- |
| DoF/PMU | Overall responsibility for SES management and performance of the project. Ensure that commitments as of risk register are fulfilled and that SES requirements are complied with. Oversee ESMF, SEP, GAP, RAF and IPPF implementation by coordinating related activities with environmental and social focal points, review/ refine ESMF, SEP, GAP and IPPF. Appoint one environmental and social focal point at the central level, recruit and oversee SES consultants to be based at the central and local levels . Ensure cooperation/ coordination of SES-related activities with relevant entities (especially MONRE, LWU, Lao Youth Union) and relevant organizations. Coordinate policy-related activities, cumulative assessments, and related studies. Ensure that SES-related activities, budgets, and other means are included in overall project work plans/ budgets. Ensure that SES-related information is disclosed and managed in an appropriate way Organize events, host in-country study exchange and participate in regional and national workshops. Report SES-related activities and compliance in the context of period project reporting to MAF and UNDP, seek clearance for revised ESMF, IPPF, GAP, SEP and other SES documents from UNDP. Collaborate with Regional Project Office personnel and Regional Environmental and Social Specialist. GRM oversight, respond to/ address complaints, report to MAF and UNDP. |
| Environmental and Social Team | Prepare SES-related workplans and budgets, submit to NPCU management. Conduct request assessments, scoped SESA/ESIA, and targeted assessments. Coordinate SES-related activities with provincial environmental and social focal points (e.g. events, work plans, reporting). Develop and support training/ awareness materials, as well as organize and conduct SES trainings as specified in the ESMF. Backstop provincial environmental and social focal points, especially related to project-specific assessments and safeguard compliance. Ensure that SES requirements such as Codes of Conduct and list of Dos and Don’ts are included in contracts, supervise that involved project personnel fulfil contractually specified SES requirements (contracted by PMU). Ensure meaningful consultations and FPIC are carried out as instructed in the ESMF, IPPF and SEP. Ensure adequate participation of women, ethnic groups and other marginalized groups. Compile/ prepare SES-related information to be disclosed by DoF and store/ manage appropriately. Compile/ report complaints to NPMU. Coordinate inputs provided by SES experts/ subject matter specialists. Prepare periodic reports on SES implementation and compliance, submit to PMU management. |

# MONITORING, EVALUATION AND REPORTING

The Project’s monitoring and evaluation (M&E) and reporting system is designed to track project progress towards its set objectives, measuring both outputs (activities delivered) and outcomes (changes achieved) for all SES documents and activities. Although different aspects of ESMF, PF, LAF, EGPF, GAP will be assessed, monitored and evaluated, the Project will following the same Monitoring and Evaluation Plan in Table 5 below.  This M&E and reporting system promotes accountability and transparency by providing evidence and data to demonstrate the effectiveness of project interventions to stakeholders, including the affected communities. It also helps to inform decision-making and foster learning and knowledge-sharing, as well as contributing to sustainable long-term development. The social and environmental specialists/team will be the key persons in charge of reporting and tracking whether required assessments are conducted, management plans are developed, and mitigation measures are put in place and reported back to PMU and UNDP. Table 5 provides a summary overview of the project monitoring and evaluation plan and associated budget.

Table 4: Monitoring and Evaluation Plan

| Monitoring and evaluation activities | Description | Frequency / timeframe | Expected action | Roles and responsibilities | Cost in USD |
| --- | --- | --- | --- | --- | --- |
| Track the progress of ESMF as well as implementation of PF, LAF, SEP, EGPF, etc | Implementation of the project ESMF and report to the Steering Committee on an annual basis | Biannually | Required ESMF steps are completed in a timely manner. | PMU with support from and Project M&E/SES specialists | None |
| Conduct scoped SESA/ESIA (including SESA for the integrated Annamite management strategy); targeted impact assessments such as ethnic groups; traditional knowledge; and livelihood assessments, and census of affected households/individuals Develop reports and ESMP | Carry out in a participatory manner, in-depth analysis of potential E&S and livelihoods impacts, as well as identification /validation of mitigation measures, drafted in a participatory manner | Quarters 1,2 and 3 of project implementation | Risks and potential impacts related to policy reform, primary forest management and economic displacement around PAs are assessed with the support of E&S consultants and the participation of the project team and stakeholders/villagers /ethnic groups; management actions are identified and incorporated into project implementation strategies. | External service providers (environmental and social) With guidance from UNDP, Project Manager, and Project M&E/SES specialists | 150,000 is allocated for recruiting E&S consultants to carry out these tasks, etc |
| Implementation of mitigation measures and monitoring of potential impacts identified in targeted assessments and per the subsequent ESMP | Participatory implementation and monitoring of impacts and mitigation measures, as instructed in the ESMP (to be prepared together with targeted assessments) | Continuous, once targeted assessments are completed and ESMP is in place | Implementation of ESMP; participatory monitoring of targeted assessment finding; integration of ESMP into project implementation strategies. Monitoring of E&S risks, and corresponding management plans as relevant | PMU M&E/SES specialists provincial and district coordinators, oversight by UNDP CO and the Steering Committee | 82,000 is allocated for these activities |
| SES Capacity Building and Learning | SES capacity-building activities at the regional programme and in-country levels. to equip PMU staff members and E&S focal points with the knowledge, skills and tools to understand, integrate and effectively apply the SES principles throughout the project cycle, from design to monitoring and evaluation. | At least annually | Relevant lessons are captured by the project teams and used to inform management decisions as instructed in the ESMF | PMU and SES specialists | 100,000 is allocated for in-and-out-of-country exchange learning; training on SES instruments as per ESMF instructions |
| Annual project quality assurance | The quality of the project will be assessed against UNDP’s quality standards to identify project strengths and weaknesses and to inform management decision-making to improve the project | Annually | Areas of strength and weakness will be reviewed and used to inform decisions to improve project performance | UNDP CO, Program Alignment Officer, with support from PMU and Project M&E/SES specialists | None |
| Review and make course corrections | Internal review of data and evidence from all monitoring actions to inform decision-making | At least annually | Performance data, risks, lessons and quality will be discussed by the project steering committee and used to make course corrections | Project Steering Committee | None |
| Annual project implementation reports | As part of the progress report to be presented to the Project Steering Committee and key stakeholders, analysis, updating and recommendations for risk management will be included | Annually | Updates on the progress of ESMF/ESMP will be reported in the project’s annual GEF Project Implementation Report. A summary of the avoidance and mitigation of potential E&S impacts will be included in the programme annual report, sharing best practices and lessons learned across the programme. | UNDP CO, UNDP-GEF RTA, PMU | None |
| Project review | The Project Steering Committee will consider updated analysis of risks and recommended risk mitigation measures at all meetings | At least annually | Any risks and/ or impacts that are not adequately addressed by national mechanisms or the PMU will be discussed in project steering committee. Recommendations will be made, discussed and agreed upon. | Project Steering Committee, PMU | None |

## Annex 1: Conducting the FPIC process.

The Project will follow the suggested six FPIC steps summarized below, as instructed by the United Nations Permanent Forum on Indigenous Issues.

Step 1: Scoping

Identify any customary forest, land and/or resources claims by the affected ethnic group communities in the proposed project areas.

Identify any sites, resources, habitats, and landscapes of national cultural, archaeological, or historical significance, and/or of critical cultural, ecological, economic, or religious/sacred importance for the traditional cultures of local communities or ethnic group peoples which may be impacted by the proposed activity. These sites should be identified through engagement with these local communities or ethnic group peoples.

Identify whether the proposed activity may diminish the rights, claims, or interests identified in Steps 1 –This is the case in circumstances including, but not limited to, the following:

Forest/land currently used by communities, or members of a community, for primary subsistence activities would no longer be available to these people for these activities. For instance, forestland that they are is to be preserved or restored by the project.

Communities, or members of a community, would cease to have access, or would have diminished access, to natural resources used for local consumption or subsistence. For instance, if: (i) access to traditional hunting or fishing areas would be eliminated or diminished, (ii) access to, or rights to extract, plants, or plant parts such as firewood, medicinal plants, or fruits would be eliminated or diminished.

Communities, or members of a community, would cease to have access, or would have diminished access, to sites with religious/sacred or cultural importance. For instance, if they were unable to access sites where traditional ceremonies are held.

The sites, resources, habitats, and landscapes of national cultural, archaeological, or historical significance, and/or of critical cultural, ecological, economic, or religious/sacred importance for the traditional cultures of local communities or ethnic group peoples must be identified through engagement with these local communities or ethnic group peoples.

Step 2: Planning and Assessment

Conduct participatory mapping of forest land and natural resource use.

Assess potential impacts (positive and negative) of the project.

Where needed, recruit ethnic groups expert to support the mapping and assessment process.

Re-define and revise the project, if necessary, to address potential impacts relative to the customary rights of ethnic group peoples and local communities.

Step 3: Consultation

Send out traditional official notification letters to the effected villages and to arrange the meeting with the representatives of the ethnic groups’ community of the. Allow at least 7-14 days before conducting a village consultation.

Conduct a Village Meeting and provide community representatives with a description of project activities, potential benefits, and impacts (presented in a manner that is easy to understand and appropriate to community representatives’ education levels and to the cultural context)

Allow at least 14 days for the community to consult internally regarding the acceptability of the proposed project activities.

Return to consult with the ethnic groups’ community to determine if they will or will not agree to the proposed activities and under what conditions.

Re-define and revise the project activities, if necessary, to address the concerns raised by the ethnic groups’ community during the consultation.

Step 4: Negotiation

If ethnic groups’ community is agreed to the project activities, negotiate terms of agreement for proceeding, including provisions such as continued access to the affected forestlands and resources, just and fair compensation for loss of access and use of forestland and resources, with an equitable share in the project benefits.

Facilitate access to legal advice, especially the processes of securing forestland tenure, for ethnic groups’ communities, support them in the negotiation and legalizing process if necessary.

Develop a plan for participatory monitoring and conflict resolution, which includes an agreed mechanism for the ethnic groups’ community and its members to raise grievances and have these grievances duly considered and resolved.

Step 5: Agreement

At the end of the consultation and negotiation process, agree clearly with ethnic group community members and their representatives whether they accept the proposed activity, and the conditions that must be met for their agreement.

Finalize the agreement, including all the agreed conditions and secure endorsement from any other relevant stakeholders, such as the local authorities, as necessary.

Step 6: Implementation

Implement the agreement, including the agreed-upon forms of compensation, benefit sharing, and/or continued access or other conditions (as applicable).

Implement the participatory monitoring and GRM.

## Annex 2: Facilitator’s guide for conducting meaningful consultation with ethnic minority peoples

Introduction

This guide is to be used together with the FPIC process. It provides a brief introduction and first-hand guidance to individuals who are tasked to directly facilitate a meeting with ethnic group or are involved in a team whose task is to moderate a meeting with an individual or a group of people who are from ethnic groups. By ethnic group, it refers to those who has a spoken language other than Lao language, such as languages of the Brue, Makong, Katang, Xouy, Pacoh, Ta-Oy and Katu, and so forth.

Principles

This guide is grounded on the following key UNDP’s SES program principles and project-level standards SES 5 (Indigenous People). It is required that under the UNDP/GEF financed project, projects are expected to make every effort to:

Ensure that development process fosters full respect for the human rights, dignity, aspirations, identity, culture, and natural resource-based livelihoods of Indigenous Peoples.

Avoid adverse impacts of projects on Indigenous Peoples, or when avoidance is not possible, to minimize, mitigate and/or compensate for such adverse impacts.

Promote sustainable development benefits and opportunities for Indigenous Peoples in a manner that is accessible, culturally appropriate and inclusive.

Improve project design and promote local support by establishing and maintaining an ongoing relationship based on meaningful consultation with the Indigenous

Recognize, respect, and preserve the culture, knowledge, and practices of Indigenous Peoples/Ethnic groups (EG), and to provide them with an opportunity to adapt to changing conditions in a manner and in a timeframe acceptable to them.

Steps to engaging a meaningful consultation with ethnic groups

Step 1: Get to know about EG

- Works closely with Department of Home Affairs

- Study about EG to be consulted with

- Meet with local village chief, EG opinion leaders to learn about local practices, taboos

- Conduct field observation/ Exchange with experienced colleagues

Step 2: Prepare before fielding for consultation

- Prepare IEC materials (booklet, manuals, guidance note…)

- Prepare meeting outline, key topics, and agenda for consultation, question guide, meeting template

- Share meeting agenda and key information with EG peoples with whom the meeting will be conducted, meeting requirements under FPIC guidelines

- Make interpretation arrangement for local ethnic group language(s)

Step 3 : Meeting with target EG group/individuals

- Build rapport

- Conduct consultation (based on meeting agenda in Step 2)

- Manage and maintain a “free” conversation, as instructed in ESMF.

- Take notes

- Share/validate key consultation results with participants by the end of meeting

- Inform participants of possible next consultation to follow up on issues raised

Step 4 – Review and process consultation feedback

- Peruse and process consultation feedback

- Prepare meeting minutes/ documentation

- Share meeting minutes with relevant stakeholder (e.g. management)

Step 5 – Incorporate consultation feedback into project design/implementation

- Conduct meeting with relevant stakeholder to discuss consultation feedback

- Incorporate feedback into project activities design/implementation

- Report back to consulted people on decision/progress made as to concerns, issues, expectation raised by consultation participants.

Commonly used consultation techniques

Focus group discussion:

- A focus group discussion (FGD) is a way to gather people from similar backgrounds or experiences to discuss a specific topic of interest.

- The group of participants (8-10 persons) is guided by a moderator (facilitator) who introduces topics for discussion and helps the group to participate in a lively and natural discussion amongst themselves.

- Allow participants to agree or disagree with each other to obtain an insight into how a group thinks about an issue, about the range of opinion and ideas, and the inconsistencies and variation that exists in a particular community in terms of beliefs, experiences, and practices.

Key informant interview:

- To get information about a pressing issue or problem in the community from a limited number of well-connected and informed community experts.

- To understand the motivation and beliefs of community residents on a particular issue.

- To get information from people with diverse backgrounds and opinions and be able to ask in-depth and probing questions.

- To discuss sensitive topics, get respondents’ candid discussion of the topic, or to get the depth of information you need.

Tips for facilitators

- Preparing the room

- Arrive at least half an hour early to set up the room.

- Check your laptop, paper, pens.

Opening the session

- Introduce yourself, your assistant.

- Introduce purpose of the focus group.

- Explain to participants that they have been invited to share their opinions and that you will guide the discussion by asking the group to reflect on specific questions.

- Tell them what time the session will conclude.

Explain the ground rules for the focus group discussion.

- These will set the tone and expectations for behavior so that everyone will feel safe and willing to participate.

- Participation in the focus group is voluntary.

- It’s all right to abstain from discussing specific topics if you are not comfortable.

- All responses are welcome – are no right or wrong answers.

- Please respect the opinions of others even if you don’t agree.

- Try to stay on topic; we may need to interrupt so that we can cover all the material.

- Speak as openly as you feel comfortable.

- Avoid revealing very detailed information about your personal health.

- Help protect others’ privacy by not discussing details outside the group.

Closing the session

- End the discussion by summarizing the main points. If there is time, invite participants to reflect on the main ideas.

- Ask if they have any additional thoughts to share.

- Thank the group for participating; let them know how the discussion results will be used.

- Collect and save all notes (save the file if you type in on laptop)

- Their ideas/suggestion will be used to a) design the project, b) prepare documents that help ensure avoid/minimize the adverse impact on local people while enhancing project’s positive impacts.

List of dos and don’ts

- Show respect to consulted ethnic groups people who are the poor, vulnerable, disadvantaged people.

- Being on time.

- Speaking slowly and clearly. Repeat as necessary. Check if people understand. Explain as necessary.

- Using local ethnic spoken language if possible, or through the assistance of native interpreter, constantly check whether they understand the provided information.

- Be patient with any question and issue raised by individuals and/or community.

- Do not use slang.

- Avoid talking about issues that should not be spoken/discussed (based on initial information gathered from Step 1.

## Annex 3 Grievance Redress Mechanism

Introduction

UNDP Social and Environmental Standards (SES) require that any project categorized as complex Moderate Risk, Substantial Risk, or High Risk – as determined by the Social and Environmental Screening Procedure (SESP) – have made available an effective project-level grievance redress mechanism (GRM). The CFB-Lao Project (Generating multiple benefits through strengthened protection of primary forests in Lao PDR) has been categorized as Substantial Risk. This GRM therefore aims to support the CFB-Lao Project to meet this SES requirement to address grievances related to the social and environmental impacts of the Project. The CFB-Lao Project GRM has incorporated both UNDP SES and national legal frameworks. This document should be read and applied in conjunction with other GRM-related requirements and guidance notes.  Grievances related to other topics should be referred to the appropriate mechanisms in accordance with their mandates.

Objective

The objective of the CFB-Lao Project GRM is to provide one avenue for stakeholder engagement and the management of social and environmental risks and impacts. The mechanism can used as a platform to raise project-related concerns or grievances. However, this GRM is not a substitute for proactive outreach to stakeholders to provide information on the Project, seek input and respond to suggestions and concerns regarding social and environmental benefits, risks and impacts. This mechanism is also not a substitute for feedback, comments and suggestions related to project activities.

The GRM provides an additional formal channel for project stakeholders to register complaints about project social and environmental risks and impacts. It specifies how complaints related to the CFB-Lao Project can be made and provides forms and channels through which a complaint can be lodged. The mechanism is also to facilitate the grievance resolution process, with written acknowledgement of the grievance and specified timeframes for resolution as instructed in the national law on conflicts resolution and UNDP Enterprise Risk Management Policy.

The Project will filter cases to assess whether the complaint is project related and will refer any unrelated cases to relevant sectors/parties. The CFB-Lao Project GRM has sequential steps that an aggrieved person can follow and allows aggrieved persons to progress through the GRM hierarchy if not satisfied with the grievance resolution, or if the complaint is not resolved within the specified timeframe.

Lao PDR redress mechanism

The Government of Lao PDR has various laws and decrees that have been active to guide the implementation of the complaint resolution process. These legal instruments specify the rights of the complainants as well as the responsibilities of government agencies in complaint resolution. For instance, relevant legal documents include:

Law on Economic Conflict (amended version), No. 51/NA dated: 22 June 2018

Decree on Compensation and Resettlement Management in Development Projects, No. 84/PM, 5 April 2016

Decree on implementation of updated Law on Petition Handling, No. 106/PM, 19 August 2022

Lao PDR has three interconnected processes in the formal justice system to address grievances (see Figure 1).

Figure 1: Formal grievance mechanism pathways in Lao PDR

Source: Multi-Stakeholder Dialogue on Responsible Agriculture Investment November 2022, Ministry of Investment and Planning, Funded by FAO and GIZ https://www.fao.org/in-action/responsible-agricultural-investments/news/detail/en/c/1455582/

Executive system: Provides steps from village to national/central level for conflict mediation. The decision at each level rests with the head administrative unit, which often leads to power asymmetries or conflicts of interest. While this mechanism is available, villagers/communities often report their complaints verbally and prefer to deal with issues internally or directly with the source instead of going through the government mechanism. If a complaint goes beyond the internal village mediation step, it is often costly and time-consuming. Therefore, the CFB-Lao Project GRM is designed in such a way that the people affected by the Project can file a verbal or written complaint directly, without any administrative costs and their issues can be dealt with at the community level/project level with project assistance.

Judiciary system (court system): Provides an opportunity to file a complaint through the justice system. However, obtaining a resolution often requires legal knowledge or a lawyer and funds. This system is almost inaccessible to communities because it is costly and time-consuming (hiring a lawyer, travelling and the requirement for official documentation). In the event a project case reaches this level, the Project will assist and bear all the associated costs.

Legislative system (National Assembly): Provides an opportunity to report any abuse of power by an administrative or justice body in resolution procedures. Communities are often unfamiliar with this system as it is not available at the local level. The People’s Provincial Assemblies (PPAs) were not formed until 2016 and communities are still not familiar with taking unsolved cases to the PPA and/or National Assembly. It is unclear what the official procedures and required documents are and/or whether the cases can be submitted in written form, by an individual or group (representative), and/or the number of signatures needed. There is a lack of enabling environment and a lack of enforcement and monitoring mechanisms. In the event a Project case reaches this level, the Project will also assist with all the required processes and bear all the associated costs.

GRM mandate

The mandate of the CFB-Lao Project GRM will be to receive and seek to resolve complaints about actual or potential environmental or social harm to affected person(s) arising from the Project. In its accessibility to complainants and in its responses to complaints, the GRM will be gender-responsive, culturally sensitive, non-discriminatory, and inclusive. Complaints related to sexual harassment and sexual abuse and exploitation (SH/SEA) will be treated confidentially by PMU/the Project GRM Team and the Project will ensure referrals for safe and confidential survivor assistance.

The Project GRM will provide:

- an accessible, predictable and transparent procedure for receiving and responding to complaints

- direct engagement and dialogue with complainants to clarify issues and interests and develop mutually acceptable responses

- resolution of complaints that are equitable and rights compatible, including contribution to remedy for environmental or social harm demonstrably caused or contributed to by the Project

- opportunities for learning from complaints and their resolution in ways that contribute to improved management of environmental and social risks and ensure alignment with UNDP SES as well as applicable laws, regulations and policies.

Eligible complaints

- To be eligible for a project GRM response, the complaint must pertain to the CFB-Lao Project and its activities after signature of the Project Document and prior to project closure. In addition, the complaint must:

- indicate how project activity(ies) have caused or contributed, or may cause or contribute to social or environmental harm, cause economic displacement and/or have an impact on the traditional culture and way of life of ethnic groups

- be made by a person or people (directly or through an authorized representative such as ethnic groups representatives, village authorities, and Lao Women’s Union) who are affected by the Project and/or could plausibly be negatively affected by project activities.

- If further information is needed to determine eligibility, the GRM should seek such information from the complainant before making an eligibility determination.

- Complainants may request and receive confidentiality but the GRM cannot respond to anonymous grievances. Record keeping and information-sharing about SEA survivor assistance will adhere to the ‘do no harm’ and confidentiality principles and the survivor’s personally identifiable information will remain confidential unless the victim expressly consents to it being shared.

- With the complainant’s agreement, the GRM will refer requests alleging fraud, corruption or non-compliance with UNDP SES to the appropriate offices within UNDP and to the relevant national authority(ies).

Functions of the GRM

The GRM will function on two levels: project management level and UNDP project assurance level.

Key responsible actors at the project management level include:

- PMU Grievance Focal Points will be selected at the national, provincial and district levels. At the village level, project focal points will also be established by the Project.

- Village Mediation Committee (VMC) will consist of representatives of the affected people, Village Authority, representatives from the Village Lao Front for National Development, Village Lao Women’s Union, Village Land responsible person, Village Public Security responsible person and representatives of cluster/subdistrict authorities.

- District Mediation Committee (DMC) will consist of the District Agriculture and Forestry Office (DAFO), District Natural Resource and Environment, District Lao Front for National Development, District Lao Women’s Union and District Home Affairs. DAFO will chair the Committee.

- Provincial Mediation Committee (PMC) will consist of representatives from the concerned sectors as in the DMC. The PMU focal point to ensure the committees are functioning and effective in solving project issues. A social expert will be assigned to support the committees in understanding the procedures and requirements of project grievance procedure and the related laws of Lao PDR.

- For cases where the CFB-Lao Project GRM cannot handle an issue or when it falls beyond the responsibility of the PMU Grievance Focal Points, VMC, DMC and PMC, formal jurisdiction will be applied and will be proceed as shown in Figure 1. The Project will assist and also bear all the associated costs for both judiciary system and legislative system procedures.

UNDP project assurance

UNDP performs quality assurance and supports the Project Board (and PMU) by carrying out objective and independent project oversight and monitoring functions, including compliance with the risk management and UNDP SES. Project assurance is totally independent of project execution. For the CFB-Lao Project, a designated representative of UNDP is responsible for the project assurance function, under the direction of the UNDP Deputy Resident Representative. In addition, the UNDP corporate Accountability Mechanism (www.undp.org/secu-srm) provides additional recourse for complainants who are not satisfied with the response received from the CFB-Lao Project GRM or who are concerned about an adverse response if they raise concerns with the Project GRM.

GRM at project management level

The PMU is directly responsible for receiving and responding to complaints through direct engagement with complainants. The PMU will:

- Establish GRM Focal Points within the PMU, as well as for the VMC, DMC and PMC.

- Establish communications channels to receive complaints and identify staff responsible for documenting and responding to complaints.

- Establish procedures to engage with the complainant, seek resolution and document all complaints and responses.

- Establish procedures to ensure that complaints related to sexual exploitation and abuse are treated in a survivor-centred/confidential manner and ensure referrals for safe and confidential survivor assistance.

- When responding to complaints, engage directly with the complainant to clarify issues, identify options for resolution and provide or support remedy for any environmental or social risks or impacts that are demonstrably associated with the project.

- Inform potentially affected community members and other stakeholders (e.g. forest patrollers/workers employed in project activities) how to make a complaint about the project (including the option to bring complaints to the project management level of the GRM, the project assurance function or the UNDP Accountability Mechanism).

- Log and track all complaints received.

In line with both UNDP SES and the Lao national GRM system, as well as with other projects currently being implemented in Lao PDR, the following redress steps, procedures and principles are applied.

1 GRM related to risks and impacts caused by the Project

A complaint related to economic displacement could be resolved through the following steps in accordance with the Law on Economic Conflict No. 51/NA and the Prime Minister Decree on implementation of the updated Law on Petition Handling No 106. As stated in the law, the complainant retains the right to bypass this procedure by addressing their complaint directly to the PMU office or the National Assembly.

Step 1 	If affected persons and/or affected households are not satisfied with how the Project is handling economic displacement or its implementation, the affected parties can make an oral or written complaint to the village authority or VMC. The village should deal with verbal complaints and make written records. The village authority or VMC, together with the Grievance Focal Points should solve the complaint within 20 working days.

Step 2 	If affected parties are not satisfied with the result of step 1, the individuals or household can file an appeal with the District Office of Justice via DAFOs after the affected party receives the decision made in Step 1. The District Office of Justice should decide within 30 working days.

Step 3 	If affected parties are not satisfied with the result of step 2, the individuals or household can file an appeal with the Provincial Assembly via the Provincial Agriculture and Forestry Office for administrative arbitration after receiving the decision made by the District Office of Justice. The administrative arbitration organization should make the arbitrated decision within 30 working days.

Step 4 	If affected parties are still unsatisfied with the arbitrated decision made by the administrative arbitration organization, after receiving the arbitrated decision, the individuals or household can file a lawsuit in a civil court according to relevant laws and regulations in Lao PDR. The administrative arbitration organization should make the arbitrated decision within 45 working days.

2 GRM related to sexual abuse and exploitation

Under the CFB-Lao Project, the GRM for SH/SEA has two functions: referring complainants to a local gender-based violence service provider and recording the resolution of the complaint. The following principles, which will be applied under the Project, recognize victims as principal decision makers in their own care and treat them with agency, dignity and respect for their needs and wishes.

- Multiple channels are in place for easy access and lodge complaints;

- SH/SEA victims will be referred to a local SEA/SH service provider for immediate support if they make a complaint directly to the PMU;

- Confidentiality of victims is protected. GM operator of PMU will keep SH/SEA allegation report confidential;

- No identifiable information on the victim shall be collected and stored in the subproject grievance logbook;

For project-related cases, costs of operating the SH/SEA GRM will be financed by the project.

- Channels for lodging SH/SEA complaints:

- Channel 1: the affected party can submit a complaint, verbally or in writing, to the VMC/Village Authorities

- Channel 2: alternatively, the affected party can lodge their complaint, verbally or in writing, to the project GRM Focal Point in the PMU

- Channel 3: the affected party can submit a complaint to, or seek counselling support from, the local Lao Women’s Union, as they wish.

All grievances related to SH/SEA (no matter which channel through which their complaint is lodged) will be processed and resolved directly by LWU who will be engaged by the PMU to assist in addressing potential grievances on SEA/SH under the Counselling and Project Center for Women and Children with the below contact details:

Lao Women’s Union Hotline: 1362

Phone: 02022241362/02023241362

Police Hotline: 1300

The Project, and organizations resolving complaints and appeal processes, will not charge any fees to affected people. Any expenses incurred due to submission of complaints and/or appeals and phone calls should be classified as unintended impacts/unexpected expenses and covered by the Project.

GRM at project assurance level (in consultation with the Project Board)

adverse response, may bring their complaint to the project assurance function of the Project Board which is exercised by UNDP. In addition, UNDP project assurance will receive unresolved complaints referred to the project manager.

Complaints submitted to the UNDP project assurance function will be addressed per the procedures outlined below. UNDP will seek resolution of complaints together with national and other relevant partners (such as implementing partners or other members of the Project Board), with due consideration of confidentiality if requested by complainants. The process for addressing complaints submitted to the UNDP project assurance function would typically involve the project manager and any necessary staff and external mediators under the direction of the UNDP Resident Representative and/or Deputy Resident Representative.

For complaints referred from the project manager (or project management unit), the project assurance function will:

- Log and track the complaint.

- Review documentation received from the project manager and consult with the project manager on the case.

- Within 5 days of receipt, engage with the complainant to review and clarify the issues raised in the case and explore options for resolution (with the option to provide technical assistance to the complainant to support the complainant’s effective engagement).

- As appropriate, engage with senior representatives of the implementing partner and other Project Board members to clarify issues and explore options for resolution.

- As appropriate, play a mediating role between the parties to seek resolution of the complaint (with the option to contract with an external mediator).

- When risks are identified that may affect overall project governance (such as the potential need to put project components on hold or change the design of the project), ensure that the Project Board has full information about the risks and guides project decision-making on the appropriate response.

- Support the Project Board to address and remedy risks and harms that the project is demonstrably causing or to which it is demonstrably contributing.

- If the complaint is resolved within 60 days of receipt, document the complainant’s acceptance of resolution, and continue to monitor until all project actions that were agreed to as part of the resolution have been taken.

- If the complaint is unresolved 60 days after referral to the project assurance function (or if requested by the complainant at any time), offer the complainant the option of referral to the UNDP Accountability Mechanism and/or to any national institutions that have a mandate to address the issues raised.

For complaints received directly from complainants, the project assurance function will first make an eligibility determination on whether the complaint is project related, and if it is, then continue from point (2) of the GRM at project assurance level as outlined above.  Complaints that are received directly by the Project Assurance function will be consult with the Project Manager on the case, protecting Complainant confidentiality if requested.

Additionally, the project assurance function will perform these tasks in support of the Project Board:

- Review complaints received by the GRM and their outcomes, work with the Project Manager to identify successes, lessons learned, challenges and trends, and report its assessments to the Project Board. Should an outcome to a grievance be compensation, the UNDP project assurance function is responsible for confirming this outcome and for working with the Project Board to determine how compensation will be achieved as necessary.

- Receive quarterly reports on complaints from the project management level of the GRM, and collaborate with its staff to identify successes, challenges, trends and lessons learned in responding to complaints.

- Provide summary reports to the Project Board of all complaints received (both those received by the operational level GRM and directly by the project assurance function) with any recommended actions.

- Disclose the GRM’s work (including case registry, summary reports on individual cases, reports on trends or patterns, and actions taken in response to trends and patterns) to the Project Board and to project stakeholders, through periodic reporting (at least semi-annual) in media/forums accessible to project stakeholders and protecting confidentiality of complainant identities where necessary.

- Monitor the project manager’s efforts to inform project stakeholders about the GRM, and ensure the accessibility, predictability, transparency, legitimacy and credibility of the GRM process.

- Provide continuing education of Project Board members and their respective institutions regarding policies, procedures and capacities needed to prevent risks and impacts which could lead to complaints, and to promote the constructive resolution of complaints.

Submitting a complaint

Who can submit a complaint?

A complaint can be submitted by any individual or group of individuals that believes it has been or will be harmed by the Project.

If a complaint is to be lodged by a different individual or organization on behalf of those said to be affected, the complainant must identify the person/people on behalf of who the complaint is submitted and provide written confirmation by the person/people represented that they are giving the complainant the authority to present the complaint on their behalf. The GRM will take reasonable steps to verify this authority.

1. Project Management Unit at the Department of Forestry, Vientiane Capital:

Address:????

Phone and WhatsApp numbers:????

Email:????

Website:???

2. United Nations Development Programme

Lane Xang Avenue

P.O. Box 345 Vientiane, Lao PDR

Email: info.la@undp.org

Tel: +856 (0) 21 267 777

Fax: +856 (0) 21 267 799

In addition, project-affected individuals or communities or their authorized representative can submit a complaint to the UNDP Accountability Mechanism (Stakeholder Response Mechanism and the Social and Environmental Compliance Unit) via the following methods:

Online:https://www.undp.org/accountability/social-and-environmental-responsibility/feedback

By email to:

Social and Environmental Standards (SES) team: info.ses@undp.org

Social and Environmental Compliance Unit (SECU): secuhotline@undp.org

Stakeholder Response Mechanism (SRM): stakeholder.response@undp.org

What information should be included in a complaint?

A form to submit a complaint and guidance for establishing a project grievance logbook are provided; however, the grievance should include the following information:

- the name(s) of the person/people submitting the complaint (“the Complainant”);

- a means for contacting the Complainant (email, phone, address, other);

- if the submission is on behalf of those alleging a potential or actual harm, the identity of those on whose behalf the complaint is made, and written confirmation by those represented of the Complainant’s authority to lodge the complaint on their behalf;

- a description of the potential or actual harm;

- names of the individual(s) or institutions responsible for the risk/harm (if known), and the location(s) and date(s) of harmful activity (if Complainant states that harm has already occurred);

- what has been done by Complainant thus far to resolve the matter;

- whether the Complainant wishes for their identity to be kept confidential; and

- the specific response requested from the GRM.

However, complainants are not required to provide all of the information listed above. Initially, complainants need only provide enough information to determine eligibility. If insufficient information is provided, the GRM has an obligation to make a substantial, good faith effort to contact the complainant to request whatever additional information is needed to determine eligibility, and if eligible, to develop a proposed response.

Complainants may request and receive confidentiality, but the GRM cannot respond to anonymous grievances. With the complainant’s agreement, the GRM will refer requests alleging fraud or corruption to the appropriate offices within UNDP and to the relevant partner(s). For complaints regarding SH/SEA the GRM will ensure complete confidentiality and may refer the complainant to reportmisconduct@undp.org.

Logging, acknowledgment and tracking of complaints

The PMU will receive grievances and assign each a tracking number, record the main points electronically in a database that is shared with the project assurance function, and provide periodic updates to complainants as well as the GRM file. The project assurance function will use the same system as the project manager for tracking complaints. When a complaint comes directly to the project assurance function, it will log the case with a new case record.

Within five (5) business days from the receipt of a grievance, the GRM will send a written acknowledgement to complainants of the grievance received with the assigned tracking number. Each grievance file will contain, at a minimum:

- the date of the request as received;

- the date the written acknowledgment was sent (and oral acknowledgment if also done);

- the dates and nature of all other communications or meetings with the complainant and other relevant stakeholders;

- specific concerns raised by the complaint, and additional information regarding those concerns provided by the Project Board and any other relevant parties (if relevant);

- the eligibility determination and rationale;

- any requests, offers of, or engagements of a mediator or facilitator;

- the dates of discussions between the complainant, project manager and/or project assurance staff, and any other relevant parties related to the proposed resolution/way forward, and the main substantive points from each discussion;

- the complainant’s acceptance or objections to proposed resolutions, and the responses of other relevant parties to proposed resolutions;

- the proposed next steps if objections arose;

- the alternative resolution if renewed dialogues were pursued;

- notes regarding implementation of any agreed resolution; and

- any conclusions and recommendations arising from monitoring and follow up.

Maintaining communication and status updates

Summary documentation of each complaint will be available for review by complainants and other stakeholders involved in the complaint, or their designated representative(s). Appropriate steps will be taken to maintain the confidentiality of complainants if previously requested. The GRM will provide periodic updates to complainants regarding the status and current actions to resolve the complaint. Not including the acknowledgment of receipt of the complaint, such updates will occur within reasonable intervals (no less frequent than every forty-five (45) days).

Protection from reprisal and retaliation

UNDP seeks to identify, reduce and address the risk of retaliation and reprisals against people who may seek information on and participation in project activities, express concerns and/or access project-level grievance redress processes/mechanisms or UNDP Stakeholder Response Mechanism or Social and Environmental Compliance Unit. To minimize the risk of reprisal or retaliation, the GRM will maintain confidentiality of complainant identities when requested, will respond to complainant concerns about reprisal or retaliation and in consultation with complainants bring the complaint to the Project Board and/or the UNDP Accountability Mechanism for review and action. For complaints regarding SH/SEA, the GRM will take additional steps as necessary to protect the confidentiality of the complainant and minimize reprisal and retaliation risks.

Without prejudice

The existence and use of this GRM is without prejudice to any existing rights under any other complaint mechanisms that an individual or group of individuals may otherwise have access to under national or international law or the rules and regulations of other institutions, agencies or commissions.

Form to submit a complaint

Grievance Form ID Number: ___________		Date received: ___________

Complaints received by (please check (√) the appropriate box):

□ PMU central □ PMU local offices □ Provincial □ District □ Village □ Hotline

Complaint made via (please check (√) the appropriate box):

□ In person □ Phone □ E-mail □ SMS □ Website □WhatsApp □Messenger □Facebook □ Hotline

□ Complaint Box / Other advice □ Community/Village Meeting

□ Others______________

FULL NAME AND LAST NAME of Complainant (or Anonymous): ___________________________________________________________________

GENDER: □ Male □ Female AGE: _____________________________

CONTACT DETAILS (by post, by telephone, by e-mail, SMS, WhatsApp, Messenger, Facebook): __________________________________________________________________________________

STATEMENT OF GRIEVANCE (Reason for complaint and activity leading to complaint. Please include as many details as possible to answer the following questions: (i) what happened; (ii) when did it happen; (iii) who did it happen to; and (iv) what was the impact of what happened. Include additional information as needed/desired):

__________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

REMEDY REQUESTED BY COMPLAINT: How/in what way do you want the issue(s) to be addressed by the project?

____________________________________________________________________________________________________________________________________________________________________

__________________________________________________________________________________

SIGNATURE: _____________________ DATE: ________________________

Guidance for establishing a project grievance logbook

As soon as the Project becomes effective, a project grievance logbook (PGL) will be established by the PMU GRM Focal Point (who is appointed from within PMU). The PGL summarizes concerns/complaints received as a list, along with key statistics on the number of complaints and time spent for each complaint from receipt to final resolution. Each case should be assigned a unique number. Good practice is to assign the case by the date of receipt (such as 2022-01, 2022-02, etc.). Supporting documents associated with each case should be documented electronically or in hard copy for convenient retrieval when needed. These supporting documents may include letter, email or a record of conversations, etc.

The sample table below could be used. The table should include:

- Name and contact details of aggrieved persons;

- Details of the nature of the grievance;

- Date received;

- How it was submitted, acknowledged, resolved, and closed down.

Grievances can be submitted anonymously or the aggrieved person can also request their name be kept confidential

| Project Grievance Logbook (PGL) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Name of Complainant (or anonymous) | Sex (M/F) | Contact info | Date received | Details of the nature of the grievance (loss of income, environmental impacts, social impacts, health, etc.) | To whom was grievance submitted | Actions to resolve grievance | Date grievance was settled (and what stage) | How was the response provided? |

## Annex 4: Proposed consultation approach with community members

| No. | Groups by socioeconomic status | Characteristics | Proposed consultation strategy |
| --- | --- | --- | --- |
| 1 | Local ethnic Peoples | Most, particularly the women: Speak only their own language Have no/very limited spoken Lao language Shy and reluctant to speak in public meetings Limited mobility because of bad road conditions | Engaging potential beneficiary community members in all proposed project investment; Engaging ethnic communities’ representative bodies and organizations and other community members, where appropriate; Use of audio-visual when consulting with Ethnic Groups and translation into local ethnic language; Use also written language of Ethnic Groups where possible; Provision of sufficient time for internal decision-making process; and; Promote their effective participation during project design, particularly at village level interventions to solicit their feedback for proposed mitigation measures to site-specific risks and impacts. |
| 2 | People with disability | Could not travel to meeting places without support from their family members Hard of hearing Poor eye visuality/ blindness Speak native ethnic language only | Use of sign language and other assistive tools, as required; Translation into local language if they were from ethnic groups; Provision of transportation to the meeting venues; where possible, visit them at the home for planned consultation; Provision of sufficient time for internal decision-making process; Meeting timing and duration based are suitable to participants |
| 3 | Women |  | Having small, focused, and short meetings where women will be comfortable asking questions or raising concerns; Meeting schedules that do not to interfere with domestic activities; Venues should be located close to their homes; Translation into local language; Meetings with female participants are facilitated by female facilitators. Separate meetings for female for particular gender-sensitive discussion |
| 4 | Elderlies | Slow and have difficulties traveling on their own Hard of hearing. Speak their native language only Not familiar with new project concepts | Providing transportation to the meeting venue; Time and duration of meetings based on the input of potential participants; Translation into local language; Separate meetings for the elderlies; Option of one-on-one interviews Meeting at their home Provide more time for their understanding and inputs/advice |
| 5 | Children | Shy Not available at daytime during class hours Speak only native language | Getting verbal consent of their parents/ guardians; Ask about issues that are important to children–that are part of their day-to-day experiences; Choose a child-friendly or familiar venue; Use language that is clear, appropriate to their age, and jargon free; Separate meetings for boys and girls. |
| 6 | Disadvantaged group | Limited asset (land, animals, house type) Limited home labor (e.g. seasonal migrant workers…) Limited income generation opportunity Have members with disability/ chronic disease Lonely elderlies | In each project village, identify individuals/households that fall under this group (using characteristics in the left column Depending on their mobility, organize meeting with them at their home, or invite them to village meeting hall. Where possible, individuals/ households of this group should be invited to small group (8 max) to learn more above their current livelihoods (which make them disadvantaged, and thus marginalized) |

National poverty line is 280,910 Lao kip/month/head.

GRM-related requirements and guidance notes can be found in the UNDP Social and Environmental Standards (SES) Toolkit, including: SES Guidance Note: Stakeholder Engagement; SES Guidance Note: Stakeholder Response Mechanism; SES Supplemental Guidance: Grievance Redress Mechanisms; Summary of Steps for Setting up Stakeholder Response Mechanism.

A verbal complaint by an affected person will be converted to a written record by the Project GRM responsible persons

UNDP Enterprise Risk Management Policy, https://popp.undp.org/document/enterprise-risk-management

Remedy (or contribution to remedy when the risk/impact is not solely the responsibility of the Project) may be provided through prevention, mitigation, and/or compensation, as appropriate.

Oral acknowledgments can be used for expediency (and also recorded) but must be followed by a written acknowledgment.