Project Title: Mykolaiv Recovered

Project Number: ???

Implementing Partner: UNDP (Direct Implementtation – DIM)

Start Date: 01/07/2023		End Date: 30/06/2025			PAC Meeting date:

Brief Description

Today Ukraine is facing its most serious challenges since achieving independence in 1991. The ongoing war has already resulted in significant loss of life, unprecedented displacement, internally and towards neighbouring countries, and devastating destruction of infrastructure. The UN Ukraine Flash Appeal shows that at least 15.7 million people are in immediate need of emergency assistance and protection. Projections indicate that if the war should continue in the medium to long term, up to 90% of the Ukrainian population could face poverty and extreme economic vulnerability, and the country’s socio-economic progress could be set-back by almost 20 years. In the short-term, 62% of the population is at high risk of falling into poverty. Ukraine’s economy is set to shrink by 45% this year due to the war and even with a moderate recovery in the next few years, by 2025 the GDP would still only be two-thirds of the pre-war GDP in 2021. In addition, the country faces losses of many people’s lives and devastative destruction of infrastructures and economic bases. Currently, more than 50% of the energy infrastructure damaged, causing the massive disruption of energy supply nationwide with millions of people experiencing power outages and challenges in heating. Extensive scale of destruction of infrastructure, rehabilitating or constructing infrastructures and installing equipment with necessary supply of the materials is urgently required to restore or maintain lifeline and key basic services, followed by removal of mines and explosives as well as debris. Mykolaivska oblast is among the most affected areas, but it has been privileged with a strong support for its recovery by the Government of Denmark. The following outlines how Denmark and UNDP will jointly apply an Early Recovery approach in Mykolaiv oblast over the coming months, meeting the needs expressed by local authorities and other important stakeholders (civil society, businesses, security providers, etc.), followed by a Reconstruction Phase until mid-2025. Hence, the suggested duration will be two years – 1 July 2023 – 30 June 2025. The overall goal of this intervention is the Green recovery of Mykolaiv City and Oblast supported by new employment opportunities, restored and enhanced public and security services and an inclusive and transparent local governance.

| Contributing Outcome (UNSDCF, CPD, RPD): Indicative Output(s) with gender marker: |  | Total resources required: | DKK 35,000,000 |  |
| --- | --- | --- | --- | --- |
|  |  | Total resources allocated: | Donor: | DKK 35,000,000 |
|  |  | Unfunded: | 0 |  |

Agreed by (signatures):

UNDP

Jaco Cilliers Resident Representative, UNDP Ukraine

Date:

# Development Challenge

Today Ukraine is facing its most serious challenges since achieving independence in 1991. The ongoing war has already resulted in significant loss of life, unprecedented displacement, internally and towards neighbouring countries, and devastating destruction of infrastructure. The UN Ukraine Flash Appeal shows that at least 15.7 million people are in immediate need of emergency assistance and protection. Projections indicate that if the war should continue in the medium to long term, up to 90% of the Ukrainian population could face poverty and extreme economic vulnerability, and the country’s socio-economic progress could be set-back by almost 20 years. In the short-term, 62% of the population is at high risk of falling into poverty. Ukraine’s economy is set to shrink by 45% this year due to the war and even with a moderate recovery in the next few years, by 2025 the GDP would still only be two-thirds of the pre-war GDP in 2021.

In addition, the country faces losses of many people’s lives and devastative destruction of infrastructures and economic bases. Currently, more than 50% of the energy infrastructure damaged, causing the massive disruption of energy supply nationwide with millions of people experiencing power outages and challenges in heating. Extensive scale of destruction of infrastructure, rehabilitating or constructing infrastructures and installing equipment with necessary supply of the materials is urgently required to restore or maintain lifeline and key basic services, followed by removal of mines and explosives as well as debris.

At the request of the Cabinet of Ministers of Ukraine, UNDP is currently providing technical assistance to the development of a National Recovery and Development Strategy, with work ongoing to agree on scope, methodology and partners. UNDP is also supporting national partners with Building Damage Assessment (BDA), Human Impact Assessment (HIA) and environmental damage assessments. The strategy is to maintain and bolster the resilience of UNDP’s long-standing national and local partners in Ukraine – the Government, the private sector and civil society – ensuring that they have the capacities and resources to lead crisis response and recovery efforts in line with principles of national ownership and aspiration toward sustainable and inclusive development pathways in view of Ukraine’s commitment to the EU Green Deal and the larger EU association agreement.

In addition, and as part of the UN family, UNDP was also actively engaged in the preparation of the second Ukraine Rapid Damage and Needs Assessment February 24, 2022 – February 24, 2023 (RDNA2) jointly prepared by the Government of Ukraine, the World Bank Group, the European Union services, and the United Nations in coordination with humanitarian and development partners, academia, civil society organizations, and the private sector.

As evident from table below, Mykolaivska oblast is among the most affected areas.

Damage, loss, and needs by oblast (US$ million)

| Oblast | Damage | Loss | Needs |
| --- | --- | --- | --- |
| Cherkaska | 9.6 | 14.1 | 121.7 |
| Chernihivska | 152.0 | 19.8 | 382.2 |
| Chernivetska | 0.0 | 13.6 | 105.7 |
| Dnipropetrovska | 220.1 | 38.6 | 496.8 |
| Donetska | 994.0 | 64.7 | 1,846.6 |
| Ivano-Frankivska | 0.0 | 14.0 | 105.7 |
| Kharkivska | 834.7 | 64.6 | 1,600.2 |
| Khersonska | 294.4 | 35.0 | 636.8 |
| Khmelnytska | 5.3 | 14.0 | 114.8 |
| Kirovohradska | 12.1 | 13.1 | 127.0 |
| Kyiv (City) | 113.3 | 106.7 | 301.6 |
| Kyivska | 250.6 | 42.9 | 596.8 |
| Luhanska | 284.7 | 28.0 | 615.1 |
| Lvivska | 1.4 | 17.9 | 108.4 |
| Mykolaivska | 350.8 | 32.5 | 732.3 |
| Odeska | 29.2 | 26.4 | 156.7 |
| Poltavska | 16.9 | 14.8 | 143.6 |
| Rivnenska | 2.3 | 13.8 | 109.7 |
| Sumska | 136.4 | 18.7 | 353.9 |
| Ternopilska | 0.0 | 13.7 | 105.7 |
| Vinnytska | 12.3 | 14.5 | 126.8 |
| Volynska | 0.0 | 13.9 | 105.7 |
| Zakarpatska | 0.0 | 13.5 | 105.7 |
| Zaporizka | 578.3 | 107.3 | 1,195.9 |
| Zhytomyrska | 104.6 | 15.6 | 288.1 |
| Nationwide | - | 37.0 | 97.4 |
| Total | 4,403.2 | 808.9 | 10,680.6 |

# Strategy

Green recovery of Mykolaiv City and Oblast supported by new employment opportunities, restored and enhanced public and security services and an inclusive and transparent local governance

The Government of Denmark has been clear about its support to Ukraine, as well as supporting its bid for full EU membership. During his speech to the Danish Parliament 29 March 2022, Ukrainian president Volodymyr Zelensky requested help with the rebuilding of the city Mykolaiv. During a meeting less than a month later in Kyiv, 21 April 2022, the Danish Prime Minister officially confirmed the support to the reconstruction of Mykolaiv, among other types of support Denmark could offer Ukraine.  In light of this commitment, the project will take a needs-based deliberate approach in providing assistance to Mykolaiv city and oblast.

The following outlines UNDP’s suggestions for an Early Recovery approach in Mykolaiv oblast over the coming months, meeting the needs expressed by local authorities and other important stakeholders (civil society, businesses, security providers, etc.), followed by a Reconstruction Phase until mid-2025. Hence, the suggested duration will be two years – 1 July 2023 – 30 June 2025.

Besides a phased approach, the below envisions a Humanitarian-Development NEXUS intervention, whereby development solutions are implemented in a humanitarian setting to address urgent needs and further capacitate the local authorities and key stakeholders in addressing these needs. UNDP will therefore work closely with UN agencies (UNOPS, IOM, WHO to mention a few), and other important actors supporting Mykolaiv, such as Danish Refugee Council, the Danish Red Cross and other relevant partners to ensure that a) development lenses are adopted by all engaged in the rapid response and b) sustainable systems are put in place to complement and progressively hand over tasks and services being provided by the humanitarian community.

UNDP launched its Resilience Building and Recovery (RBR) Programme for Ukraine on April 11th, 2022, to immediately respond to the development and humanitarian challenges.  The overall objective of the Programme is to preserve development gains in Ukraine as fully as possible, mitigating risks of descent into a governance and service delivery crisis, embedding activities for recovery from the onset of the humanitarian effort, and facilitating a swift return to development pathways and processes for national attainment of the SDGs.

UNDP is well placed to deliver on a NEXUS approach for Ukraine, on the basis of long-established partnerships with the key national actors – Government, private sector and civil society – whose resilience must be bolstered to lead the country from crisis response to recovery. UNDP has a well-established and trusted relationship with the Government of Ukraine at all levels, with existing programmes and projects to support the Presidency and Cabinet of Ministers, key line ministries, and local government units encompassing over 330 municipalities; UNDP work for private sector development has been conducted with and through 27 Business Membership Organizations, on behalf of more than 15,000 micro- and small-medium enterprises (MSMEs).  Likewise, 15 different networks of civil society organizations have been supported by UNDP, helping to ensure that the views of a vibrant third sector are more clearly reflected in development processes and national democratic governance agenda.

The UNDP RBR Programme is a multi-sectoral programme comprised of three outcomes to achieve its intended results. The strategy of the Programme is to maintain and bolster the resilience of UNDP’s long-standing national and local partners in Ukraine – the Government, the private sector and civil society – ensuring that they have the capacities and resources to lead crisis response and recovery efforts in line with principles of national ownership and aspiration toward sustainable and inclusive development pathways in view of Ukraine’s commitment to the EU Green Deal, the larger EU-Ukraine association agreement and the recent EU candidate status:

Outcome 1:	Government at all levels continues to function effectively, with reinforced capacities to lead crisis response, sustain public service provision, and coordinate the delivery of assistance and recovery efforts that leave no-one behind.

Outcome 2:	Ukraine’s high human capital, productive capacities, and natural resources are leveraged to meet immediate humanitarian needs of diverse groups and strengthen social and economic recovery.

Outcome 3:	Ukrainian institutions and civil society have the capacity and resources to maintain and strengthen the social fabric, uphold human rights for all people, and ensure the inclusion, protection and empowerment of all, including population groups with intersecting and multiple vulnerabilities.

For its implementation, the Project will be fully integrated into UNDP’s existing programme, allowing for the maximization of resources as well as access to complementarities and synergies under numerous other initiatives with multiple other donors and development partners.

The project will thereby be an integral part of the UNDP Country Programme and is therefore fully aligned with the United Nations Partnership Framework (UNPF). It is part of the Inclusive Development, Recovery and Peacebuilding Portfolio (IDRPB), which is closely interlinked with the Democratic Governance and Energy & Environment Portfolios of UNDP, operating nationally and in all of Ukraine’s regions and is consistent with the SDGs, in particular SDG 16 (Peace, Justice and Strong Institutions) and SDG 5 (Gender Equality and Women’s Empowerment).

With its anchoring in UNDP, this will help ensure that governance, security and human rights issues are well covered, and the programme has close links to OHCHR, UN Women and OCHA as well as UNHCR on the NEXUS approach. A further relevant attribute of the Programme is its complementarity and active contribution to national reform processes already underway, such as decentralisation, justice reform, law enforcement, and anti-corruption .

As an area-based programme specifically developed for the conflict-affected areas of eastern Ukraine, the ongoing Recovery and Peacebuilding Programme (RPP) has accumulated a wealth of experience in addressing key stabilization, peacebuilding, economic and governance priority needs in eastern Ukraine following the start of the 2014 conflict. Following the sudden escalation of military activities in February 2022, and the corresponding increase of urgent needs in conflict-affected communities, transit hubs, and host communities, the RPP has scaled up its support to address the negative impact of the war in areas adjacent to oblasts it was previously designed to support, and in oblasts where internally displaced persons (IDPs) from the east of Ukraine had displaced to, in line with UNDP’s overall commitment to preserve development gains as fully as possible and to return Ukraine to pathways achieving the Sustainable Development Goals (SDGs) as quickly as possible.

The duration of the project: 24 months.

# Results and Partnerships

Expected Results

The Project presents the expansion and consolidation of activities related to community security and social cohesion, currently being financed by the Government of Denmark through the project “Enhanced citizen engagement for strengthened community security and increased social cohesion in eastern Ukraine” ongoing since October 2022. These directions are also identified based on the results, challenges, successes, and lessons learned throughout the implementation of RPP in eastern Ukraine and beyond. In addition, the suggested intervention builds on the activities UNDP has already successfully implemented in response to the consequences of the ongoing war in Ukraine.

The Project seeks to link local government-led mechanisms for recovery planning and public service provision (including social and administrative service provision, legal assistance and security services) to citizens’ engagement in and advocacy for the allocation and monitoring of the recovery funds. The Project will provide comprehensive support across four interlinked strategic directions: the creation of inclusive and participatory mechanism for recovery planning, implementation and monitoring; the re-establishment/enhancement of service provision, including in areas that were significantly affected by the war and temporarily not under the control of the Government of Ukraine; the support to community resilience and recovery through citizen-led action that creates and sustains the enabling conditions for citizen’s engagement in civil life, with a special focus on young women and men; and the support to local economic recovery through vocational education and training and the creation of a conducive environment for the reprise of private entrepreneurship.

Through this project, UNDP will seek to contribute to the following outcome:

To this end, the project aims to achieve the following four interconnected outputs:

- Output 1. Mykoliav Recovery Offices

- Output 2. Administrative and Social Services

- Output 3. Community Resilience and Civil Society Engagement with a Focus on Youth

- Output 4.  Vocational and Educational Training

Output 1.	Mykoliav Recovery Offices

Under this strategic direction the Project will seek to foster community recovery and resilience and engender trust of citizens towards regional and local authorities (Mykolaiv City officials) in Mykolayiv oblast by boosting their capacities to provide quality public services in gender-responsive manner that addresses the socio-economic impact of the war on local communities.

The Project will strengthen and expand in local target communities the creation and adoption of a Local Integrated Recovery and Development Model and develop local public administration capacities for the planning, implementation and monitoring of crisis response and recovery measures in local target communities with special emphasis on the City of Mykolaiv. The key beneficiaries within this strategic direction will be the Governor’s office and the Recovery Working Group established at oblast and local levels (including the city of Mykolaiv) thanks to UNDP-supported action. These stakeholders will be receiving advisory support and access to the best national and international practices and solutions, including those piloted by UNDP in other oblasts of Ukraine – thus creating space for inter-oblast exchanges and peer-to-peer learning.

The Integrated Model of community recovery and development methodology is built on multi-stakeholder cooperation of interested parties - local self-government bodies, business, public, etc. through the local office for community recovery and development. The methodology encompasses the analysis of the “state of play” within the community, the research for effective management solutions and support to their implementation to achieve sustainable development of the hromada in keeping with the principles of systematicity and good governance. The Project will ensure that the process is participatory and inclusive, and suggested measures are gender-responsive and leave no one behind.

Some of the key steps that the project will be implementing to foster and localize the Integrated Model of Community and Recovery are indicated below.

- A Community Working Group (CWG) for recovery planning will be created to lead the implementation of the model in each hromada. It will consist of representatives of local authorities' responsible for recovery and development at the hromada level, civil society representatives, business and other relevant stakeholders and supplied expert support by UNDP.

- An analysis will be performed of local economic development policies, social and humanitarian development policies, participatory and gender-based development policies, local finances, e-democracy, level of project-based development capacity.

- Representatives of the CWG will develop a Community Recovery and Development Strategy (or Plan).

- A Community Recovery and Development Office will be established to support the elaboration of and provide advisory for community development projects implementation; resource mobilization; dialogue (mediation) between the government and business and the community; etc.

- A specialized training program will be offered to representatives of local self-government and NGOs. Some of the key topics may include i) crisis management and recovery planning skills, (ii) principles of good governance, rule of law and ethical conduct/anti-corruption, (iii) meaningful engagement of citizens, (iv) human rights and gender equality, (v) integrated development and reconstruction of hromadas, (vi) project management, and (vii) civil society role and tools to advocate for and monitor funds allocation for recovery.

- The Project will advocate for the creation of a ‘Local Recovery and Development Fund’ aimed at overseeing all available resources for recovery and efficient implementation of the ‘Community Recovery and Development Strategies’. It will include costs from local, regional and national budgets, contributions from local businesses and other donors, etc.

- The Project will support the implementation of the specific activities, adopted by the Recovery Plan. These may include the establishment of Module Centres, mobile teams for damage assessment, ‘suitcases’ for administrative services delivery, information kiosks and digital queue systems, mobile teams for the provision of psychosocial support or social care, computer literacy centres, the establishment of telemedicine infrastructure, Public Health Centres, provision of specialized equipment for addressing environmental issues, small grants for local businesses and/or citizen involvement in decision-making process related to the organization and monitoring of the quality of local services, and/or implementation of environmental activities etc.

Output 2. Administrative and Social Services

Under this strategic direction the Project will seek to support counterparts at the local level to assess needs and sustain delivery of quality public services to meet increased demand in IDP-hosting and transit communities, and to assist authorities with the restoration of basic services in war-affected areas, for remaining residents.

The Project will ensure the immediate provision of equipment and the expansion of ICT infrastructure within existing Administrative Service Centres (ASCs) and other key service delivery institutions in partnership and coordination with other development actors. The Project will provide rapid support to the expansion and further digitalization of essential and priority services to address the most urgent needs of the most affected hromadas, with a specific emphasis being placed on displaced populations and returnees requiring access to digital IDs, health, education or property documents already held within the existing systems. The available fleet of administrative service units will be boosted to cover service provision in Project target areas, to offer a range of priority administrative services (primarily focused on social protection, pension, identity documents, registration of personal and official transport), as well as legal, medical, personal care and information services; these will be provided based on the ASCs “one-stop shop” approach.

This network of integrated Services Centers will ensure the accessibility of services for all citizens, including vulnerable groups (people with disabilities etc.); support innovative solutions in the provision of integrated services through a single electronic platform, further promoting the digitalization of services provision; and implement a comprehensive information protection system.

In parallel, the Project will expand and strengthen ongoing activities assisting the Ministry of Health and the National Health Service of Ukraine enhancing coordination and quality in procurement of health-related goods and equipment, an area that has seen dramatic scale-up to meet immediate needs in the aftermath of the war. The Project will take a two-pronged approach that focus, on the one hand, on capacity development of healthcare professionals; and on the other on the refurbishment and upgrade of medical facilities.

The Project will be supporting five Primary Health Care facilities of Mykolaiv city, Novyi Buh, Snihurivka, Bashtanka and Mostove in the creation of the enabling conditions for the provision of quality, gender-responsive physical and mental health and psychosocial support services, adapted to new challenges brought by the war (i.e., increased workload on the system, lack of staff, lack of fully equipped workplaces and medical equipment, lack of highly specialized medical care). This will include the refurbishment of medical personnel working places, rest rooms, and spaces for provision of psychological consultations.

Strengthening the accessibility of healthcare services, staff of primary healthcare institutions will be provided with vehicles, boosting the outreach of family doctors/specialists to consult patients even in remote settlements.

In Mykolaiv city and Snihurivka hromada, the Project intends to replicate the successful experience of establishing Public Health and Recovery Centres (PHRC) within the premises of medical institutions. These will be fitted with modern training equipment and furniture, as well as specialized training equipment to build the capacities of medical workers and interns to provide medical assistance.

With respect to the capacity development strategic direction, the Project will implement capacity development initiatives (study programmes) for nurses, doctors, and patients` organisations in order to improve the quality of health care provision in hospitals and improving medical capacities.

Some of the proposed topics are:

- Basic Life Support trainings and Course Stop the Bleed (twice per year).

- Psychological support training for medical workers and for people in need (twice per year).

- Oncological alertness in women and men (once per year).

- Training course in providing telemedical consultation (once per 2 years).

- Infection control training in health care facilities (infection control units) (once per year).

Output 3. Community Resilience and Civil Society Engagement with a Focus on Youth

The Project will expand the current support being provided in the area of capacity development for Civil Society Organizations (CSOs), activists and communities at large to advocate for recovery projects and monitor allocation and use of public funds for recovery – including as channeled through the national recovery plan or bilateral budgetary support at subnational level. Project will engage with active citizens and civil society stakeholders through a comprehensive series of capacity development initiatives, networking events and exchange visits within the oblast and beyond, to localize the full understanding of the (public) project implementation cycle and support the development and implementation of community-led initiatives and projects that foster community recovery and resilience, including durable solutions for displaced populations.

As part of the same strategic endeavor and in line with UNDP’s commitment to “leave no one behind” the Project will act at hromada and oblast levels, to enable the participation of youth, especially young women and men living with disabilities, in the recovery planning process. This will be achieved by supporting the adoption of an inclusive bottom-up approach through consultations, discussions, and strategic sessions, to foster a conducive platform for engagement and dialogue. This activity builds on the successful roundtable event RISE: Reaching Inclusion and Support for Everyone organized by UNDP in Mykolaiv in March 2023 in cooperation with the Black Sea National University and on the ongoing investments on developing local capacities for project management in NGOs and initiative groups working for the socialization of youth with disabilities. The activity will result in recovery initiatives designed and implemented for and by youth with disabilities.

From 2024 onwards the Project will continue and expand the initiatives set out in the inception phase to pave the ground for sustainable recovery and development through a “build back better” approach.

Citizens’ engagement in the recovery and reconstruction process will be amplified and strengthened by the introduction/restoration of participatory budgeting mechanisms in support to resilience building through citizens’ civic participation. The Project will also support service delivery at the hromada level through the introduction of a model of social contracting model  that will boost service delivery for those most in need through the engagement of civil society service providers.

In parallel, community mobilization processes will support the transition towards sustainable recovery solutions, including but not limited to the introduction of alternative energy sources for critical community infrastructure and adoption of universal design principles. Pilot green/blue recovery initiatives will be identified and implemented through recovery resource centers, and community resilience hubs.

Expanding the inception work with youth with disabilities the Project will support the establishment of a Youth Inclusive Hub to raise awareness about the rights of young people with disabilities and promote an understanding and acceptance of diversity within the community, including through the implementation of initiatives designed to bolster accessibility and participation of people with disabilities in economic and cultural events.

The Project will also assist in the reintegration of women and men veterans, through a combination of (1) capacity development for local authorities and first responders, (2) efforts geared towards advocacy and building capacities of women and men veterans in the protection of their rights, (3) through the design of service delivery mechanism that meet the specific needs of veterans and their families  and (4) through recovery initiatives designed and implemented for and by the veteran community.

Finally, in this phase the Project will seek to consolidate ongoing work that enables the re-establishment of transparent and accessible security and justice service provision through targeted technical assistance and a capacity development component designed in close coordination with local counterparts.

Beneficiaries of this support will be local courts and the Free Legal Aid System, as well as security service providers (community police officers, local departments of the State Emergency Service and firefighting teams). The goal of the expanded support is to boost capacities for more effective and timely response to the (1) emerging legal needs of conflict affected populations, including war-related crimes and (2) to emergencies including those related to environmental and chemical pollution. This strategic direction will seek to pilot alternative and innovative mechanism for legal service provision through local councils and take a system approach to civil protection through coordinated action of security stakeholders.

Human rights, gender equality, conflict-sensitive and non-discriminatory communication will be mainstreamed throughout project action, whether in the design of recovery initiatives or in the capacity development for law enforcement and legal service providers, especially those deployed in war-affected communities that were temporarily not under the control of the Government of Ukraine.

Output 4. 	Vocational and Educational Training

Under this strategic direction the Project will contribute to trigger the sustainable recovery of standards of living and create the enabling environment for a reprisal of economic activities to the benefit of women and men affected by the war in Mykolaiv city and oblast. These initiatives are framed within and benefit from the lessons learned, and experience of the broader economic recovery effort initiated by UNDP since the beginning of the war. The Project will work in two directions to stimulate economic activity and self-employment through (1) addressing the immediate needs of the oblast-level labour market and (2) support the upskilling, transformation and development of the workforce in line with the needs of the local context and strategic vision for recovery at oblast and hromada level – as identified through the recovery planning processes (point 5.1).

The skills mismatch between supply and demand for labor has widened significantly since the beginning of the war, increasing unemployment and affecting both the competitiveness and attractiveness of the existing workforce for perspective employers. This is particularly evident among the most vulnerable groups, whose perspectives are weakened, in the short term, by lost income generation opportunities and, in the longer term, by a vicious cycle that pushes them (or keeps them) towards poverty.

On a systemic level, the lack of reliable data and the chaotic changes within the labour market caused by the fluid security situation and overall economic decline across the country, have caused vocational schools to continue providing training opportunities without relevant information – including forecasts of the estimated number of workers in different professions required by local employers. Compounding these challenges, the regional and local offices of the State Employment Service are struggling to cope with the arrival of local jobseekers and IDPs who relocated from other oblasts to Mykolaiv city and oblast, and who lost their usual income sources. To address these issues, the Project will act in a holistic and synchronous fashion to support working-age women and men and institutions, addressing both individual and systemic challenges.

Project activities aiming to strengthen the oblast-level vocational and educational training (VET) system will start from an analysis of employers’ needs and a rapid assessment of the current state of the VET system itself; these will constitute the necessary validation base for, and guide prioritization of, development initiatives that enable the recovery of the VET infrastructure and enables its harmonization with the regional labour market.

In response to the data collection and analysis, rehabilitation, re-equipping, and capacity development for the managers and personnel in the selected VET schools will be initiated - prioritizing educational facilities capable and willing to train working age women and men on skills in demand, and guarantee delivery of quality, state-of-the-art educational services. The Project will in parallel seek to restore linkages between VET educational institutions and those regional enterprises best placed to be a source of employment opportunities for VET graduates through methodological and capacity development support that targets public-private partnership initiatives. The restoration of such linkages will enable a rapid flow of information on new technologies and equipment that will need to become part of the workforce training programmes and create the conditions for the launch of on-the-job training opportunities that will be offered as part of the VET curriculum and contribute to turning VET graduates into a competitive and qualified workforce.

The analysis of employers’ needs will also guide the Project’s engagement in support to regional and local offices of the State Employment Service. Specifically, the Project will assist the State Employment Service to recruit workers for understaffed businesses that are struggling to resume their operations after the tremendous outflow of former employees to other parts of the country and/or abroad.

At the individual level, Project investments will focus on workforce re-training in line with the needs of the labor market as a tangible and immediate solution likely to trigger increased employment (re)insertion and earnings.

Women and men who lost their jobs due to the destruction of production units and enterprise shutdown will be the primary beneficiaries of reskilling programmes designed in line with the identified employers’ needs and adjusted to the capacities of the VET system and ancillary training facilities. While open and accessible to the whole of the residents of Mykolaiv city and oblast, these programs will prioritize IDPs and returnees, especially women, enabling them to build a new skillset appropriate to meet changed labour market needs and respond to the new employment challenges created by the war – thus ultimately increasing their attractiveness for employers, improving employability, and supporting economic (re)integration.

Short-term professional training programmes  will be complemented by small-scale grant financial support that successful graduates of the training programs will be able to access to boost self-employment and micro-entrepreneurship, accompanied by a motivation and soft skills development campaign. The activities will be coordinated with the key labour market actors, including the Ministry of Education and Science, State Employment Service and local employers.

Stakeholder Engagement

The following stakeholders have been identified as being important for successful implementation and for enabling national ownership of the project deliverables.

Stakeholders that Contribute to Implementation at Institutional Level and Ensure the Relevance of Programming:

- Subnational state administrations; local authorities at various levels, incl. municipal and hromada levels in frontline; civil society sector, incl. CSOs networks, associations, advisory bodies;

- Ministries and other central executive bodies (together with their branches at the subnational and local level), incl. the Ministry for Reintegration of the Temporarily Occupied Territories; Ministry for Communities, Territories and Infrastructure Development; Ministry of Veterans Affairs; Ministry of Social Policy; Ministry of Justice, Ministry of Youth and Sports, Coordination Centre for Legal Aid Provision, State Judiciary Administration of Ukraine, and the Office of the Government Commissioner for Gender Equality Policy.

Institutional Beneficiaries:

- National, subnational and local administrations;

- Territorial Communities;

- Community based organizations, civil society organizations, citizen initiative groups, including youth, women’s and ex-combatant’s self-help groups.

The final beneficiaries are conflict affected populations at large, including women, youth, elderly, ex-combatants, and other vulnerable groups (including for example people with disabilities) and civil society organizations, and residents in general.

Knowledge

Sustainability and Scaling UP

# Project Management

The UNDP implementation team will ensure the Project’s overall implementation, its administration, financing management, communications, monitoring and reporting. It will also be responsible for communications with representatives of key national, regional and local stakeholders, for organizing Programme Board meetings as well as for ensuring synergies between similar projects within the RPP and/or across the UN system. UNDP Country Office Support Services will be also provided to the Project on an on-going basis.

Being fully integrated into the existing Programme and efforts on the ground, the Project will be implemented in a cost efficient and effective manner.

From a cost efficiency and value for money point of view:

- The Project will share office premises established in Dnipro, Poltava, and Odessa. These costs will be charged to the Project at the rate of up to 15% of total office costs.

- All procurement procedures will be conducted, as required by UNDP procurement regulations, on the basis of the best value for money.

From an effectiveness point of view:

- The Project will have immediate access to the UNDP knowledge base as well as to UNDP’s partners (government and civil society) at local, regional and national levels.

- Through joint implementation and office sharing, it will be able to easily and regularly cooperate and coordinate activities with other and similar projects.

# Results Framework

Intended Outcome as stated in the UNSDCF/Country [or Regional] Programme Results and Resource Framework:

Outcome indicators as stated in the Country Programme [or Regional] Results and Resources Framework, including baseline and targets:

Applicable Output(s) from the UNDP Strategic Plan:

Project title and Quantum Project Number:

| EXPECTED OUTPUTS | OUTPUT INDICATORS | DATA SOURCE | BASELINE |  | ## TARGETS (by frequency of data collection) |  |  |  |  |  | ## DATA COLLECTION METHODS & RISKS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Value | Year | Year 1 | Year 2 | Year 3 | Year 4 | Year … | ## FINAL |  |
| Output 1 Mykoliav Recovery Offices | 1.1 State each output indicator. |  |  |  |  |  |  |  |  |  |  |
|  | 1.2 |  |  |  |  |  |  |  |  |  |  |
|  | 1.3 |  |  |  |  |  |  |  |  |  |  |
|  | 1.4 |  |  |  |  |  |  |  |  |  |  |
| Output 2 Administrative and Social Services | 2.1 |  |  |  |  |  |  |  |  |  |  |
|  | 2.2 |  |  |  |  |  |  |  |  |  |  |
|  | 2.3 |  |  |  |  |  |  |  |  |  |  |

| Output 3. Community Resilience and Civil Society Engagement with a Focus on Youth | 2.1 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2.2 |  |  |  |  |  |  |  |  |  |  |
|  | 2.3 |  |  |  |  |  |  |  |  |  |  |

| Output 4. Vocational and Educational Training | 2.1 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2.2 |  |  |  |  |  |  |  |  |  |  |
|  | 2.3 |  |  |  |  |  |  |  |  |  |  |

# Monitoring And Evaluation

In accordance with UNDP’s programming policies and procedures, the project will be monitored through the following monitoring and evaluation plans: [Note: monitoring and evaluation plans should be adapted to project context, as needed]

Monitoring Plan

| Monitoring Activity | Purpose | Frequency | Expected Action | Partners (if joint) | Cost (if any) |
| --- | --- | --- | --- | --- | --- |
| Track results progress | Progress data against the results indicators in the RRF will be collected and analysed to assess the progress of the project in achieving the agreed outputs. | Quarterly, or in the frequency required for each indicator. | Slower than expected progress will be addressed by project management. | UNDP |  |
| Monitor and Manage Risk | Identify specific risks that may threaten achievement of intended results. Identify and monitor risk management actions using a risk log. This includes monitoring measures and plans that may have been required as per UNDP’s Social and Environmental Standards. Audits will be conducted in accordance with UNDP’s audit policy to manage financial risk. | Quarterly | Risks are identified by project management and actions are taken to manage risk. The risk log is actively maintained to keep track of identified risks and actions taken. | UNDP |  |
| Learn | Knowledge, good practices and lessons will be captured regularly, as well as actively sourced from other projects and partners and integrated back into the project. | At least annually | Relevant lessons are captured by the project team and used to inform management decisions. | UNDP |  |
| Annual Project Quality Assurance | The quality of the project will be assessed against UNDP’s quality standards to identify project strengths and weaknesses and to inform management decision making to improve the project. | Annually | Areas of strength and weakness will be reviewed by project management and used to inform decisions to improve project performance. | UNDP |  |
| Review and Make Course Corrections | Internal review of data and evidence from all monitoring actions to inform decision making. | At least annually | Performance data, risks, lessons and quality will be discussed by the project board and used to make course corrections. | UNDP and Project Board |  |
| Project Report | A progress report will be presented to the Project Board and key stakeholders, consisting of progress data showing the results achieved against pre-defined annual targets at the output level, the annual project quality rating summary, an updated risk long with mitigation measures, and any evaluation or review reports prepared over the period. | Annually, and at the end of the project (final report) |  | UNDP |  |
| Project Review (Project Board) | The project’s governance mechanism (i.e., project board) will hold regular project reviews to assess the performance of the project and review the Multi-Year Work Plan to ensure realistic budgeting over the life of the project. In the project’s final year, the Project Board shall hold an end-of project review to capture lessons learned and discuss opportunities for scaling up and to socialize project results and lessons learned with relevant audiences. | Specify frequency (i.e., at least annually) | Any quality concerns or slower than expected progress should be discussed by the project board and management actions agreed to address the issues identified. | UNDP |  |

Evaluation Plan

| Evaluation Title | Partners (if joint) | Related Strategic Plan Output | UNDAF/CPD Outcome | Planned Completion Date | Key Evaluation Stakeholders | Cost and Source of Funding |
| --- | --- | --- | --- | --- | --- | --- |
| Mid-Term Review | MFA, Dennmark |  |  | June 2024 | UNDP, MFA, Dennmark | MFA, Dennmark |
| Final Evaluation | MFA, Dennmark |  |  | June 2025 | UNDP, MFA, Dennmark | Project |

# Multi-Year Work Plan

All anticipated programmatic and operational costs to support the project, including development effectiveness and implementation support arrangements, need to be identified, estimated and fully costed in the project budget under the relevant output(s). This includes activities that directly support the project, such as communication, human resources, procurement, finance, audit, policy advisory, quality assurance, reporting, management, etc. All services which are directly related to the project need to be disclosed transparently in the project document.

| EXPECTED OUTPUTS | PLANNED ACTIVITIES | Planned Budget by Year |  |  |  | RESPONSIBLE PARTY | PLANNED BUDGET |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Y1 | Y2 | Y3 | Y4 |  | Funding Source | Budget Description | Amount |
| Output 1: Gender marker: | 1.1 Activity |  |  |  |  |  |  |  |  |
|  | 1.2 Activity |  |  |  |  |  |  |  |  |
|  | 1.3 Activity |  |  |  |  |  |  |  |  |
|  | MONITORING |  |  |  |  |  |  |  |  |
|  | Sub-Total for Output 1 |  |  |  |  |  |  |  |  |
| Output 2: Gender marker: | 2.1 Activity |  |  |  |  |  |  |  |  |
|  | 2.2 Activity |  |  |  |  |  |  |  |  |
|  | 2.3 Activity |  |  |  |  |  |  |  |  |
|  | MONITORING |  |  |  |  |  |  |  |  |
|  | Sub-Total for Output 2 |  |  |  |  |  |  |  |  |
| Evaluation (as relevant) | EVALUATION |  |  |  |  |  |  |  |  |
| General Management Support |  |  |  |  |  |  |  |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  |

# Governance and Management Arrangements

VIII.1 	Implementation modality

This project will be implemented under UNDP’s existing Recovery and Peacebuilding Programme (RPP) using Direct Implementation Modality (DIM). Details of the Project implementation modality are provided below (VIII.2 and VIII.3).

Project implementation will be governed by the provisions of the present Project Document and its annexes, as well as by UNDP’s Programme & Operations Policy & Procedures (POPP). Governance of the Project will be supported through annual work planning as well as reporting and monitoring the delivery of results and impact on the basis of the results framework. The annual work plans as well as progress reporting will be the responsibility of the Project management in close consultation with UNDP. The work plan will be implemented upon its endorsement by the RPP Programme Board.

VIII.2	Governance and management set-up

The Programme Board

The RPP Board is the governing body of the project and with RPP’s management team reporting directly to the board on delivery. A designated RPP Programme Manager, supervising dedicated programme component leads, will be responsible for the components financed under this agreement. Major procurements, grants and financing arrangements are launched and implemented by the RPP management team directly.

The RPP Board consists of representatives of UNDP in Ukraine, participating donors and representatives of the Recovery and Peacebuilding Programme beneficiaries/implementing partners.

The Board’s membership includes the following components:

- Executive (role represented by UNDP), that holds the project ownership and chairs the group

- Senior Supplier (role represented by DMFA who provides financial and/or technical support for the Project) that provides guidance regarding the technical and financial feasibility of the Project;

- Senior Beneficiary (role represented by Mykolaiv Oblast Administrations and Mykolaiv City Council). The Senior Beneficiary may also include local authorities from the communities (‘hromadas’) where the Project will be implemented and Central Authorities when/if required - the Ministry of Justice, Ministry of Internal Affairs, National Police of Ukraine, the State Court Administration, the Ministry for Reintegration of the Temporary Occupied Territories, the Ministry for Communities and Territories Development. The Senior Beneficiary ensures the realisation of the Project benefits from the perspective of Project beneficiaries.

- In the context of this Project’s implementation, the RPP Board will hold meetings on an annual basis, or more frequently if deemed necessary. Senior representatives of the Project Beneficiary, Suppliers and Executive must attend the meeting.  Relevant documents will be sent to each Board member at least one week before the meeting takes place. RPP Board will monitor the overall programme’s progress; decide on strategic decisions to ensure the continued coherence between implementation and goals and objectives; approve annual work plans and budgets; and review project delivery.

The RPP Board will approve the visibility, advocacy and communication plans with the intention that such activities are coordinated with senior management of participating donors and implementing partners.

Amendments to the budget, including use of contingencies, will be subject to the approval of the RPP Board.

In addition to RPP Board meetings, UNDP will organize periodical meetings and/or field visits (at least twice a year as a minimum) with its international partners/donors on the Project to discuss, in a less formal set-up, results achieved, constraints met, solutions identified, etc.

Project Assurance is the responsibility of each RPP Board member, but the role can be delegated.  The Project Assurance role supports the Board by carrying out objective and independent project oversight and monitoring functions. This role ensures appropriate project management milestones are managed and completed.

Project implementation will be governed by the provisions of the Project Document and UNDP Operations Manual. The project will utilize a direct payment modality.

Or new Board?

# Legal Context

This project document shall be the instrument referred to as such in Article 1 of the Standard Basic Assistance Agreement between the Government of Ukraine and UNDP, signed on 18 June 1993. All references in the SBAA to “Executing Agency” shall be deemed to refer to “Implementing Partner.”

This project will be implemented by UNDP (“Implementing Partner”) in accordance with its financial regulations, rules, practices and procedures.

# Risk Management

UNDP (DIM)

- UNDP as the Implementing Partner will comply with the policies, procedures and practices of the United Nations Security Management System (UNSMS.)

- UNDP as the Implementing Partner will undertake all reasonable efforts to ensure that none of the project funds are used to provide support to individuals or entities associated with terrorism , that the recipients of any amounts provided by UNDP hereunder do not appear on the United Nations Security Council Consolidated Sanctions List, and that no UNDP funds received pursuant to the Project Document are used for money laundering activities. The United Nations Security Council Consolidated Sanctions List can be accessed via https://www.un.org/securitycouncil/content/un-sc-consolidated-list. This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document.

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

- UNDP as the Implementing Partner will: (a) conduct project and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

- In the implementation of the activities under this Project Document, UNDP as the Implementing Partner will handle any sexual exploitation and abuse (“SEA”) and sexual harassment (“SH”) allegations in accordance with its regulations, rules, policies and procedures.

- All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any programme or project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

- UNDP as the Implementing Partner will ensure that the following obligations are binding on each responsible party, subcontractor, and sub-recipient:

  - Consistent with the Article III of the SBAA [or the Supplemental Provisions to the Project Document], the responsibility for the safety and security of each responsible party, subcontractor and sub-recipient and its personnel and property, and of UNDP’s property in such responsible party’s, subcontractor’s and sub-recipient’s custody, rests with such responsible party, subcontractor and sub-recipient.  To this end, each responsible party, subcontractor and sub-recipient shall:

    - put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

    - assume all risks and liabilities related to such responsible party’s, subcontractor’s and sub-recipient’s security, and the full implementation of the security plan.

  - UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the responsible party’s, subcontractor’s and sub-recipient’s obligations under this Project Document.

  - Each responsible party, subcontractor and sub-recipient (each a “sub-party” and together “sub-parties”) acknowledges and agrees that UNDP will not tolerate sexual harassment and sexual exploitation and abuse of anyone by the sub-parties, and other entities involved in Project implementation, either as contractors or subcontractors and their personnel, and any individuals performing services for them under the Project Document.

(a) In the implementation of the activities under this Project Document, each sub-party shall comply with the standards of conduct set forth in the Secretary General’s Bulletin ST/SGB/2003/13 of 9 October 2003, concerning “Special measures for protection from sexual exploitation and sexual abuse” (“SEA”).

(b) Moreover, and without limitation to the application of other regulations, rules, policies and procedures bearing upon the performance of the activities under this Project Document, in the implementation of activities, each sub-party, shall not engage in any form of sexual harassment (“SH”). SH is defined as any unwelcome conduct of a sexual nature that might reasonably be expected or be perceived to cause offense or humiliation, when such conduct interferes with work, is made a condition of employment or creates an intimidating, hostile or offensive work environment. SH may occur in the workplace or in connection with work. While typically involving a pattern of conduct, SH may take the form of a single incident. In assessing the reasonableness of expectations or perceptions, the perspective of the person who is the target of the conduct shall be considered.

  - In the performance of the activities under this Project Document, each sub-party shall (with respect to its own activities), and shall require from its sub-parties (with respect to their activities) that they, have minimum standards and procedures in place, or a plan to develop and/or improve such standards and procedures in order to be able to take effective preventive and investigative action. These should include: policies on sexual harassment and sexual exploitation and abuse; policies on whistleblowing/protection against retaliation; and complaints, disciplinary and investigative mechanisms. In line with this, sub-parties will and will require that their respective sub-parties will take all appropriate measures to:

(i) Prevent its employees, agents or any other persons engaged to perform any services under this Project Document, from engaging in SH or SEA;

(ii) Offer employees and associated personnel training on prevention and response to SH and SEA, where sub-parties have not put in place its own training regarding the prevention of SH and SEA, sub-parties may use the training material available at UNDP;

(iii) Report and monitor allegations of SH and SEA of which any of the sub-parties have been informed or have otherwise become aware, and status thereof;

(iv) Refer victims/survivors of SH and SEA to safe and confidential victim assistance; and

(v) Promptly and confidentially record and investigate any allegations credible enough to warrant an investigation of SH or SEA. Each sub-party shall advise UNDP of any such allegations received and investigations being conducted by itself or any of its sub-parties with respect to their activities under the Project Document, and shall keep UNDP informed during the investigation by it or any of such sub-parties, to the extent that such notification (i) does not jeopardize the conduct of the investigation, including but not limited to the safety or security of persons, and/or (ii) is not in contravention of any laws applicable to it. Following the investigation, the relevant sub-party shall advise UNDP of any actions taken by it or any of the other entities further to the investigation.

  - Each sub-party shall establish that it has complied with the foregoing, to the satisfaction of UNDP, when requested by UNDP or any party acting on its behalf to provide such confirmation. Failure of the relevant sub-party to comply of the foregoing, as determined by UNDP, shall be considered grounds for suspension or termination of the Project.

  - Each responsible party, subcontractor and sub-recipient will ensure that any project activities undertaken by them will be implemented in a manner consistent with the UNDP Social and Environmental Standards and shall ensure that any incidents or issues of non-compliance shall be reported to UNDP in accordance with UNDP Social and Environmental Standards.

  - Each responsible party, subcontractor and sub-recipient will take appropriate steps to prevent misuse of funds, fraud, corruption or other financial irregularities, by its officials, consultants, subcontractors and sub-recipients in implementing the project or programme or using the UNDP funds.  It will ensure that its financial management, anti-corruption, anti-fraud and anti money laundering and countering the financing of terrorism policies are in place and enforced for all funding received from or through UNDP.

  - The requirements of the following documents, then in force at the time of signature of the Project Document, apply to each responsible party, subcontractor and sub-recipient: (a) UNDP Policy on Fraud and other Corrupt Practices (b) UNDP Anti-Money Laundering and Countering the Financing of Terrorism Policy; and (c) UNDP Office of Audit and Investigations Investigation Guidelines. Each responsible party, subcontractor and sub-recipient agrees to the requirements of the above documents, which are an integral part of this Project Document and are available online at www.undp.org.

  - In the event that an investigation is required, UNDP will conduct investigations relating to any aspect of UNDP programmes and projects. Each responsible party, subcontractor and sub-recipient will provide its full cooperation, including making available personnel, relevant documentation, and granting access to its (and its consultants’, subcontractors’ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with it to find a solution.

  - Each responsible party, subcontractor and sub-recipient will promptly inform UNDP as the Implementing Partner in case of any incidence of inappropriate use of funds, or credible allegation of fraud, corruption other financial irregularities with due confidentiality.

Where it becomes aware that a UNDP project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption, each responsible party, subcontractor and sub-recipient will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). It will provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

  - Choose one of the three following options:

Option 1: UNDP will be entitled to a refund from the responsible party, subcontractor or sub-recipient of any funds provided that have been used inappropriately, including through fraud corruption, other financial irregularities or otherwise paid other than in accordance with the terms and conditions of this Project Document.  Such amount may be deducted by UNDP from any payment due to the responsible party, subcontractor or sub-recipient under this or any other agreement.  Recovery of such amount by UNDP shall not diminish or curtail any responsible party’s, subcontractor’s or sub-recipient’s obligations under this Project Document.

Option 2: Each responsible party, subcontractor or sub-recipient agrees that, where applicable, donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities which are the subject of the Project Document, may seek recourse to such responsible party, subcontractor or sub-recipient for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud corruption or other financial irregularities or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Option 3: UNDP will be entitled to a refund from the responsible party, subcontractor or sub-recipient of any funds provided that have been used inappropriately, including through fraud corruption or other financial irregularities, or otherwise paid other than in accordance with the terms and conditions of the Project Document.  Such amount may be deducted by UNDP from any payment due to the responsible party, subcontractor or sub-recipient under this or any other agreement.

Where such funds have not been refunded to UNDP, the responsible party, subcontractor or sub-recipient agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Project Document, may seek recourse to such responsible party, subcontractor or sub-recipient for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud, corruption or other financial irregularities, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Note:  The term “Project Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Project Document, including those with responsible parties, subcontractors and sub-recipients.

  - Each contract issued by the responsible party, subcontractor or sub-recipient in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from it shall cooperate with any and all investigations and post-payment audits.

  - Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the project or programme, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

  - Each responsible party, subcontractor and sub-recipient shall ensure that all of its obligations set forth under this section entitled “Risk Management” are passed on to its subcontractors and sub-recipients and that all the clauses under this section entitled “Risk Management Standard Clauses” are adequately reflected, mutatis mutandis, in all its sub-contracts or sub-agreements entered into further to this Project Document.

# ANNEXES

- Project Quality Assurance Report

- Social and Environmental Screening Template [English] [French] [Spanish], including additional Social and Environmental Assessments or Management Plans as relevant. (NOTE: The SES Screening is not required for projects in which UNDP is Administrative Agent only and/or projects comprised solely of reports, coordination of events, trainings, workshops, meetings, conferences, preparation of communication materials, strengthening capacities of partners to participate in international negotiations and conferences, partnership coordination and management of networks, or global/regional projects with no country level activities).

- Risk Analysis. Use the standard Risk Register template. Please refer to the Deliverable Description of the Risk Register for instructions

- Capacity Assessment: Results of capacity assessments of Implementing Partner (including Partner Capacity Assessment Tool (PCAT) and HACT Micro Assessment)

- Project Board Terms of Reference and TORs of key management positions. The standard Project Board TOR can be found here.

- On-Granting Provisions Applicable to the Implementing Partner. On-granting clauses for non-UNDP Implementing Partners can be found here.

The Gender Marker measures how much a project invests in gender equality and women’s empowerment. Select one for each output: GEN3 (Gender equality as a principle objective); GEN2 (Gender equality as a significant objective); GEN1 (Limited contribution to gender equality); GEN0 (No contribution to gender quality)

Ukraine - Rapid Damage and Needs Assessment: February 2022 – 2023; https://documents.worldbank.org/en/publication/documents-reports/documentdetail/099184503212328877/p1801740d1177f03c0ab180057556615497

Ibid; p.45.

UNDP publishes its project information (indicators, baselines, targets and results) to meet the International Aid Transparency Initiative (IATI) standards.  Make sure that indicators are S.M.A.R.T. (Specific, Measurable, Attainable, Relevant and Time-bound), provide accurate baselines and targets underpinned by reliable evidence and data, and avoid acronyms so that external audience clearly understand the results of the project.

It is recommended that projects use output indicators from the Strategic Plan IRRF, as relevant, in addition to project-specific results indicators. Indicators should be disaggregated by sex or for other targeted groups where relevant.

Optional, if needed

Cost definitions and classifications for programme and development effectiveness costs to be charged to the project are defined in the Executive Board decision DP/2010/32

Changes to a project budget affecting the scope (outputs), completion date, or total estimated project costs require a formal budget revision that must be signed by the project board. In other cases, the UNDP programme manager alone may sign the revision provided the other signatories have no objection. This procedure may be applied for example when the purpose of the revision is only to re-phase activities among years.

Applicable for non-UNDP Implementing Partner as Grant Making Institution facilitating on-granting.