## Summary
UK PACT Financial Reporting Template - Interim GRCF
Project name: | Improving forest monitoring capabilities and supporting deforestation reduction in Bolivia
Project reference number: | MRV\80
Lead implementer (organisation) name: | UNDP
Report period: | July - September
Financial year: | 2024/25
Financial report summary
Q1
Principal expert | #REF!
Senior expert | #REF!
Expert | #REF!
Junior expert | #REF!
Assistant to expert | #REF!
Project Manager | #REF!
Support Staff | #REF!
Admin assistant | #REF!
Travel international | #REF!
Travel domestic | #REF!
Accommodation and subsistence | #REF!
Workshop/Event | #REF!
Translation and interpretation | #REF!
Print Fees | #REF!
Other | #REF!
Other - Communications | #REF!
Other - Capital | #REF!
Total Direct costs | 66786.7754
Overheads total | 0
Grand total | 66786.7754
Q2
Total Direct costs | 96437.1678
Overheads total | 0
Grand total | 96437.1678
Q3
Total Direct costs | 42696.9359
Overheads total | 0
Grand total | 42696.9359
Q4
Total Direct costs | 194038.3195
Overheads total | 0
Grand total | 194038.3195
Grand total Q1 + Q2 + Q3 + Q4 | 399959.1985
GMS + Levy (9%) | 35996.3279
Total | 435955.5263
% Executed | 99.93%
Underspend | 293.8015 | > Recurso no utilizado
GMS + Levy (9%) | 26.4421 | > Corresponde al recurso no utilizado
Total | 320.2437 | > Por resolver. Reembolsar a FCDO
% Not Executed | 0.0734%

## Advance Payments (hidden)
Advance payment reconcilitation
| Payment 1 | Payment 2 | Payment 3 | Payment 4 | Payment 5 | Payment 6 | Payment 7 | Payment 8 | Payment 9 | Payment 10
Total Forecast Expenditure
Adjustment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total for Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Expenditure
Value remaining | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on B6: Autor: Should be taken from Row 27 of the "Actuals + Forecast" tab
Note on B7: Autor: The figure added/removed from the forecast. Based on the value remaining from the previous quarter
Note on B8: Autor: This is the value the invoice for the quarter should have.
Note on B9: Autor: The actual amount spent for the quarter, should match the total from Row 36 of the summary
Note on B10: Autor: The difference between the amount advanced and what was actually spent

## Actuals + Forecast (hidden)
Expenditure forecasts
Expenditure by category |  | Expenditure prior to Q4 22/23 | [5 empty] | Q4 FY22/23 | [5 empty] | Q1 FY23/24 | [5 empty] | Q2 FY23/24 | [5 empty] | Q3 FY23/24 | [5 empty] | Q4 FY23/24 | [5 empty] | FY 2024/2025 | [5 empty] | FY 2025/2026 | [5 empty] | Total Expenditure
Category | Sub-Category | Total per grant agreement | Total Claimed | Variance | Variance % | Cumulative Variance | Cumulative Variance % | Total for quarter per grant agreement | Total Claimed /Latest Forecast | Quarterly Variance | Quarterly Variance % | Cumulative Variance | Cumulative Variance % | Total for quarter per grant agreement | Total Claimed /Latest Forecast | Quarterly Variance | Quarterly Variance % | Cumulative Variance | Cumulative Variance % | Total for quarter per grant agreement | Total Claimed /Latest Forecast | Quarterly Variance | Quarterly Variance % | Cumulative Variance | Cumulative Variance % | Total for quarter per grant agreement | Total Claimed /Latest Forecast | Quarterly Variance | Quarterly Variance % | Cumulative Variance | Cumulative Variance % | Total for quarter per grant agreement | Total Claimed /Latest Forecast | Quarterly Variance | Quarterly Variance % | Cumulative Variance | Cumulative Variance % | Total for year per grant agreement | Latest Forecast | Quarterly Variance | Quarterly Variance % | Cumulative Variance | Cumulative Variance % | Total for year per grant agreement | Latest Forecast | Quarterly Variance | Quarterly Variance % | Cumulative Variance | Cumulative Variance % | Grand total per grant agreement | Total Claimed + Latest Forecast | Variance
Personnel | Principal expert |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% | 0 | 0 | 0
Personnel | Senior expert |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% | 0 | 0 | 0
Personnel | Expert |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% | 0 | 0 | 0
Personnel | Junior expert |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% | 0 | 0 | 0
Personnel | Assistant to expert |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% | 0 | 0 | 0
Personnel | Project Manager |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% | 0 | 0 | 0
Personnel | Support Staff |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% | 0 | 0 | 0
Personnel | Admin assistant |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% | 0 | 0 | 0
Travel international |  |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% | 0 | 0 | 0
Travel domestic |  |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% | 0 | 0 | 0
Accommodation and subsistence |  |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% | 0 | 0 | 0
Workshop/Event |  |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% | 0 | 0 | 0
Translation and interpretation |  |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% | 0 | 0 | 0
Print Fees |  |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% | 0 | 0 | 0
Other |  |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% | 0 | 0 | 0
Other - Communications |  |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% | 0 | 0 | 0
Other - Capital |  |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% | 0 | 0 | 0
Subtotal |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0 | 0
Overheads total |  |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% |  |  | 0 | 0% | 0 | 0% | 0 | 0 | 0
Grand total |  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Transaction list
Transaction list
Line | Task name | Date completed | Evidence supplied for task completion | Planned total expenditure (GBP) | Total direct expenditure Q1 (GBP) | Total direct expenditure Q2 (GBP)2 | Total direct expenditure Q3 (GBP)3 | Total direct expenditure Q4 (GBP)4 | Overhead % | Overhead Q1 total | Overhead Q2 total2 | Overhead Q3 total3 | Actual total expenditure (Dec2023) Q1 | Actual total expenditure (Mar2024) Q2 | Actual total expenditure (Jun2024) Q3 | Actual total expenditure (Sep2024) Q4 | Total expenditure Q1+Q2+Q3+Q4 | Variance | Expenditure in percentage | Palladium Notes | UNDP Notes | Notes3 | Notes3 | UNDP Notes
1.1. | Developing the design for Calibration/Validation, overseeing measurements, preparing data analysis, and documenting outcomes | Q2 and ongoing |  | 6900 | 0 | 1037.4608 | 0 | 3348.6705 | 0% | 0 | 0 | 0 | 0 | 1037.4608 | 0 | 3348.6705 | 4386.1313 | 2513.8687 | 63.57% | Proporcione una breve explicación de por qué no utilizaron todo el recurso en esta actividad. Ok, solved. | El presupuesto asignado para esta actividad, estaba planificado antes de recibir los recursos de UK. La sede de UK realizó el desembolso de GBP 436,276.57, monto que ingresó a la cuenta del PNUD en fecha 28/09/2023 a un tipo de cambio, haciendo un total de USD 522,906.70. |  |  | "The budget allocated for this activity was planned before receiving the resources from the UK. The UK headquarters disbursed GBP 436,276.57, an amount that entered the UNDP account on 28/09/2023 at an exchange rate, making a total of USD 522,906.70."
1.2. | Arranging logistical aspects of on-site measurements, documenting sites and measurements, and consolidating measurements | Q2 and ongoing |  | 6210 | 0 | 4740.3428 | 0 | 1735.8674 | 0% | 0 | 0 | 0 | 0 | 4740.3428 | 0 | 1735.8674 | 6476.2102 | -266.2102 | 104.3%
1.3. | Logging measurement records (dbh) | Q2 and ongoing |  | 4830 | 0 | 3436.3422 | 1483.5197 | 117.375 | 0% | 0 | 0 | 0 | 0 | 3436.3422 | 1483.5197 | 117.375 | 5037.2369 | -207.2369 | 104.3%
1.4. | Gauging log height | Q2 and ongoing |  | 4830 | 0 | 3436.3422 | 0 | 1600.6806 | 0% | 0 | 0 | 0 | 0 | 3436.3422 | 0 | 1600.6806 | 5037.0228 | -207.0228 | 104.3%
1.5. | Identifying and enrolling tree species | Q2 and ongoing |  | 4830 | 0 | 2370.1714 | 0 | 2666.6942 | 0% | 0 | 0 | 0 | 0 | 2370.1714 | 0 | 2666.6942 | 5036.8656 | -206.8656 | 104.3%
1.6. | Enrolling data | Q2 and ongoing |  | 4830 | 0 | 592.5428 | 0 | 2016.2541 | 0% | 0 | 0 | 0 | 0 | 592.5428 | 0 | 2016.2541 | 2608.797 | 2221.203 | 54.01% | Proporcione una breve explicación de por qué no utilizaron todo el recurso en esta actividad. Ok, solved. | El presupuesto asignado para esta actividad, estaba planificado antes de recibir los recursos de UK. La sede de UK realizó el desembolso de GBP 436,276.57, monto que ingresó a la cuenta del PNUD en fecha 28/09/2023 a un tipo de cambio, haciendo un total de USD 522,906.70. |  |  | "The budget allocated for this activity was planned before receiving the resources from the UK. The UK headquarters disbursed GBP 436,276.57, an amount that entered the UNDP account on 28/09/2023 at an exchange rate, making a total of USD 522,906.70."
1.7. | Preparing the site | Q3 and ongoing |  | 14400 | 0 | 0 | 0 | 14801.4084 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 14801.4084 | 14801.4084 | -401.4084 | 102.8% | ¿Puedes enviar la factura GBP 14K? Ok, solved. | Se envía en el link adjunto al correo |  |  | No individual expenditure above GBP 10k
1.8. | Creating the LiDAR processing sequence, processing LiDAR canopy height measurements, and harmonizing LiDAR, SAR and ground measurements in aerial and spatial contexts | Q2 and ongoing |  | 24400 | 0 | 6136.3966 | 2090.2975 | 17217.7886 | 0% | 0 | 0 | 0 | 0 | 6136.3966 | 2090.2975 | 17217.7886 | 25444.4827 | -1044.4827 | 104.3% | ¿Puedes enviar la factura GBP 16K? Ok, solved. | Se envía en el link adjunto al correo |  |  | No individual expenditure above GBP 10k
1.9. | Constructing the emissions monitoring framework for degradation-related assessments, charting burned forest extent and logging effects, delineating annual degradation, and computing associated emissions | Q3 and ongoing |  | 12000 | 0 | 0 | 0 | 12513.1611 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 12513.1611 | 12513.1611 | -513.1611 | 104.3% | ¿Puedes enviar la factura GBP 11k? Ok, solved. | Se envía en el link adjunto al correo |  |  | No individual expenditure above GBP 10k
1.10. | Detecting land cover via LiDAR sensors | Q2 and ongoing | Evidence 1.10 folder | 75768 | 0 | 28806.6494 | 3827.9375 | 46377.8092 | 0% | 0 | 0 | 0 | 0 | 28806.6494 | 3827.9375 | 46377.8092 | 79012.3961 | -3244.3961 | 104.3% | ¿Puedes enviar todas las facturas GBP 3K y 44k? Ok, solved. | Se envía en el link adjunto al correo |  |  | No individual expenditure above GBP 10k
1.11. | Developing progress reports and results monitoring in each area | Q3 and ongoing |  | 4250 | 0 | 0 | 0 | 3921.3396 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 3921.3396 | 3921.3396 | 328.6604 | 92.27% | Proporcione una breve explicación de por qué no utilizaron todo el recurso en esta actividad. Ok, solved. | El presupuesto asignado para esta actividad, estaba planificado antes de recibir los recursos de UK. La sede de UK realizó el desembolso de GBP 436,276.57, monto que ingresó a la cuenta del PNUD en fecha 28/09/2023 a un tipo de cambio, haciendo un total de USD 522,906.70. |  |  | "The budget allocated for this activity was planned before receiving the resources from the UK. The UK headquarters disbursed GBP 436,276.57, an amount that entered the UNDP account on 28/09/2023 at an exchange rate, making a total of USD 522,906.70."
1.12. | Establishing GESI Initiative 1: Mainstreaming Inclusion | Q3 and ongoing |  | 2250 | 0 | 0 | 0 | 2384.4915 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 2384.4915 | 2384.4915 | -134.4915 | 106%
1.13. | Establishing GESI Initiative 2: Diverse and Representative Teams | Q3 and ongoing |  | 2250 | 0 | 0 | 0 | 2273.284 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 2273.284 | 2273.284 | -23.284 | 101%
1.14. | Formulating the conceptual and analytical framework | Q2 and ongoing |  | 12750 | 0 | 5682.205 | 4017.5552 | 2621.6967 | 0% | 0 | 0 | 0 | 0 | 5682.205 | 4017.5552 | 2621.6967 | 12321.4569 | 428.5431 | 96.64% | Proporcione una breve explicación de por qué no utilizaron todo el recurso en esta actividad. Ok, solved. | El presupuesto asignado para esta actividad, estaba planificado antes de recibir los recursos de UK. La sede de UK realizó el desembolso de GBP 436,276.57, monto que ingresó a la cuenta del PNUD en fecha 28/09/2023 a un tipo de cambio, haciendo un total de USD 522,906.70. |  |  | "The budget allocated for this activity was planned before receiving the resources from the UK. The UK headquarters disbursed GBP 436,276.57, an amount that entered the UNDP account on 28/09/2023 at an exchange rate, making a total of USD 522,906.70."
1.15. | Overseeing and tracking the work plan | Q2 and ongoing |  | 10800 | 0 | 3341.6498 | 1577.0569 | 1572.4253 | 0% | 0 | 0 | 0 | 0 | 3341.6498 | 1577.0569 | 1572.4253 | 6491.132 | 4308.868 | 60.1% | Proporcione una breve explicación de por qué no utilizaron todo el recurso en esta actividad. Ok, solved. | El presupuesto asignado para esta actividad, estaba planificado antes de recibir los recursos de UK. La sede de UK realizó el desembolso de GBP 436,276.57, monto que ingresó a la cuenta del PNUD en fecha 28/09/2023 a un tipo de cambio, haciendo un total de USD 522,906.70. |  |  | "The budget allocated for this activity was planned before receiving the resources from the UK. The UK headquarters disbursed GBP 436,276.57, an amount that entered the UNDP account on 28/09/2023 at an exchange rate, making a total of USD 522,906.70."
1.16. | Managing technical and administrative aspects | Q2 and ongoing |  | 2800 | 0 | 336.1665 | 0 | 1082.4511 | 0% | 0 | 0 | 0 | 0 | 336.1665 | 0 | 1082.4511 | 1418.6176 | 1381.3824 | 50.66% | Proporcione una breve explicación de por qué no utilizaron todo el recurso en esta actividad. Ok, solved. | El presupuesto asignado para esta actividad, estaba planificado antes de recibir los recursos de UK. La sede de UK realizó el desembolso de GBP 436,276.57, monto que ingresó a la cuenta del PNUD en fecha 28/09/2023 a un tipo de cambio, haciendo un total de USD 522,906.70. |  |  | "The budget allocated for this activity was planned before receiving the resources from the UK. The UK headquarters disbursed GBP 436,276.57, an amount that entered the UNDP account on 28/09/2023 at an exchange rate, making a total of USD 522,906.70."
1.17. | Devising training programs | Q3 and ongoing |  | 2310 | 0 | 0 | 1310.457 | 511.2601 | 0% | 0 | 0 | 0 | 0 | 0 | 1310.457 | 511.2601 | 1821.7171 | 488.2829 | 78.86% | Proporcione una breve explicación de por qué no utilizaron todo el recurso en esta actividad. Ok, solved. | El presupuesto asignado para esta actividad, estaba planificado antes de recibir los recursos de UK. La sede de UK realizó el desembolso de GBP 436,276.57, monto que ingresó a la cuenta del PNUD en fecha 28/09/2023 a un tipo de cambio, haciendo un total de USD 522,906.70. |  |  | "The budget allocated for this activity was planned before receiving the resources from the UK. The UK headquarters disbursed GBP 436,276.57, an amount that entered the UNDP account on 28/09/2023 at an exchange rate, making a total of USD 522,906.70."
1.18. | Assembling and refining technical and financial reports | Q2 and ongoing |  | 5500 | 0 | 1683.6244 | 1176.4847 | 538.6792 | 0% | 0 | 0 | 0 | 0 | 1683.6244 | 1176.4847 | 538.6792 | 3398.7883 | 2101.2117 | 61.8% | Proporcione una breve explicación de por qué no utilizaron todo el recurso en esta actividad. Ok, solved. | El presupuesto asignado para esta actividad, estaba planificado antes de recibir los recursos de UK. La sede de UK realizó el desembolso de GBP 436,276.57, monto que ingresó a la cuenta del PNUD en fecha 28/09/2023 a un tipo de cambio, haciendo un total de USD 522,906.70. |  |  | "The budget allocated for this activity was planned before receiving the resources from the UK. The UK headquarters disbursed GBP 436,276.57, an amount that entered the UNDP account on 28/09/2023 at an exchange rate, making a total of USD 522,906.70."
1.19. | Formulating administrative procedures | Q2 and ongoing |  | 4800 | 0 | 1947.621 | 1620.241 | 1401.3578 | 0% | 0 | 0 | 0 | 0 | 1947.621 | 1620.241 | 1401.3578 | 4969.2197 | -169.2197 | 103.5%
1.20. | Creating financial reports | Q2 - Q3 and ongoing |  | 5400 | 0 | 2133.434 | 1699.3998 | 1501.4306 | 0% | 0 | 0 | 0 | 0 | 2133.434 | 1699.3998 | 1501.4306 | 5334.2644 | 65.7356 | 98.78%
2.1. | Creating Quality Assurance/Quality Control (QA/QC) procedures | Q1 - Q2 and ongoing | Evidence 2.1 folder | 26100 | 12556.0725 | 3600.3581 | 3605.6142 | 7456.815 | 0% | 0 | 0 | 0 | 12556.0725 | 3600.3581 | 3605.6142 | 7456.815 | 27218.8598 | -1118.8598 | 104.3%
2.2. | Compiling geodatabases, programming web interfaces, and configuring the Geoserver | Q1 - Q2 and ongoing | Evidence 2.2 folder | 17625 | 11173.4797 | 2656.9198 | 2660.7985 | 1889.8068 | 0% | 0 | 0 | 0 | 11173.4797 | 2656.9198 | 2660.7985 | 1889.8068 | 18381.0049 | -756.0049 | 104.3%
2.3. | Collecting Landsat/Sentinel 2 time series data for Pando, conducting land use classification after deforestation, and assessing thematic accuracy of maps | Q1 - Q2 and ongoing |  | 15600 | 9265.8207 | 2656.9198 | 2660.7985 | 1685.6076 | 0% | 0 | 0 | 0 | 9265.8207 | 2656.9198 | 2660.7985 | 1685.6076 | 16269.1466 | -669.1466 | 104.3%
2.4. | Collecting Landsat/Sentinel 2 time series data for Charagua, conducting land use classification after deforestation, and assessing thematic accuracy of maps | Q1 - Q2 and ongoing |  | 15600 | 7247.9309 | 2078.2594 | 2081.2929 | 4861.1966 | 0% | 0 | 0 | 0 | 7247.9309 | 2078.2594 | 2081.2929 | 4861.1966 | 16268.6797 | -668.6797 | 104.3%
2.5. | Identifying annual degradation patterns and evaluating thematic precision of maps in Pando | Q1 - Q2 and ongoing |  | 15600 | 6668.0777 | 1911.9834 | 1914.7745 | 5773.642 | 0% | 0 | 0 | 0 | 6668.0777 | 1911.9834 | 1914.7745 | 5773.642 | 16268.4775 | -668.4775 | 104.3%
2.6. | Identifying annual degradation patterns and evaluating thematic precision of maps in Charagua | Q1 - Q2 and ongoing |  | 15600 | 6668.0777 | 1911.9834 | 1914.7745 | 5773.642 | 0% | 0 | 0 | 0 | 6668.0777 | 1911.9834 | 1914.7745 | 5773.642 | 16268.4775 | -668.4775 | 104.3%
2.7. | Developing progress reports and results monitoring in each area | Q2 and ongoing |  | 4250 | 0 | 3308.1172 | 827.8782 | 180.148 | 0% | 0 | 0 | 0 | 0 | 3308.1172 | 827.8782 | 180.148 | 4316.1434 | -66.1434 | 101.6%
2.8. | Establishing GESI Initiative 3: Participation and Empowerment | Q3 and ongoing |  | 2250 | 0 | 0 | 1193.1135 | 1153.4328 | 0% | 0 | 0 | 0 | 0 | 0 | 1193.1135 | 1153.4328 | 2346.5463 | -96.5463 | 104.3%
2.9. | Establishing GESI Initiative 4: Data Collection for Informed Action | Q3 and ongoing |  | 2250 | 0 | 0 | 0 | 2346.5463 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 2346.5463 | 2346.5463 | -96.5463 | 104.3%
2.10. | Creating consultation modules for Charagua and Pando | Q3 and ongoing |  | 11700 | 0 | 0 | 0 | 11678.8883 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 11678.8883 | 11678.8883 | 21.1117 | 99.82% | ¿Puedes enviar la factura GBP 11k? Ok, solved. Ok, solved. | Se envía en el link adjunto al correo |  |  | No individual expenditure above GBP 10k
2.11. | Conducting training workshops | Q2 and ongoing |  | 2310 | 0 | 967.7409 | 0 | 1438.0088 | 0% | 0 | 0 | 0 | 0 | 967.7409 | 0 | 1438.0088 | 2405.7498 | -95.7498 | 104.1%
2.12. | Ticket handling | Q2 and ongoing |  | 920 | 0 | 514.2171 | 107.9157 | 305.8204 | 0% | 0 | 0 | 0 | 0 | 514.2171 | 107.9157 | 305.8204 | 927.9532 | -7.9532 | 100.9%
2.13. | Managing travel expenses | Q2 and ongoing |  | 2800 | 0 | 602.5823 | 40.597 | 2155.6919 | 0% | 0 | 0 | 0 | 0 | 602.5823 | 40.597 | 2155.6919 | 2798.8712 | 1.1288 | 99.96%
3.2. | Formulating the legal and institutional structure for safeguards | Q3 and ongoing |  | 7040 | 0 | 0 | 0 | 7342.0826 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 7342.0826 | 7342.0826 | -302.0826 | 104.3%
3.3. | Providing technical support for safeguard management | Q1 - Q2 and ongoing |  | 12000 | 8917.6185 | 2536.3058 | 0 | 1060.9893 | 0% | 0 | 0 | 0 | 8917.6185 | 2536.3058 | 0 | 1060.9893 | 12514.9136 | -514.9136 | 104.3%
3.4. | Enhancing and building local governance capabilities | Q3 and ongoing |  | 7500 | 0 | 0 | 0 | 7808.1611 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 7808.1611 | 7808.1611 | -308.1611 | 104.1%
3.5. | Fostering coordination within the territory | Q2 and ongoing |  | 4800 | 2263.6903 | 2612.8637 | 0 | 129.4785 | 0% | 0 | 0 | 0 | 2263.6903 | 2612.8637 | 0 | 129.4785 | 5006.0325 | -206.0325 | 104.3%
3.6. | Delivering specialized technical training programs | Q1 - Q2 and ongoing |  | 9450 | 2026.0074 | 625.6812 | 2004.9452 | 5109.4204 | 0% | 0 | 0 | 0 | 2026.0074 | 625.6812 | 2004.9452 | 5109.4204 | 9766.0542 | -316.0542 | 103.3%
3.7. | Developing progress reports and results monitoring in each area | Q3 and ongoing |  | 2050 | 0 | 0 | 1698.3572 | 416.9135 | 0% | 0 | 0 | 0 | 0 | 0 | 1698.3572 | 416.9135 | 2115.2707 | -65.2707 | 103.2%
3.8. | Establishing GESI Initiative 5: Enhancing Capacity and Opportunities | Q3 and ongoing |  | 1250 | 0 | 0 | 0 | 1303.6368 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 1303.6368 | 1303.6368 | -53.6368 | 104.3%
3.9. | Establishing GESI Initiative 6: Promoting GESI Awareness | Q3 and ongoing |  | 2250 | 0 | 0 | 0 | 2372.302 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 2372.302 | 2372.302 | -122.302 | 105.4%
3.10. | Administrative assistance | Q2 and ongoing |  | 9200 | 0 | 4772.287 | 3183.1266 | 1591.9638 | 0% | 0 | 0 | 0 | 0 | 4772.287 | 3183.1266 | 1591.9638 | 9547.3773 | -347.3773 | 103.8%
| Total |  |  | 400253 | 66786.7754 | 96437.1678 | 42696.9359 | 194038.3195 |  | 0 | 0 | 0 | 66786.7754 | 96437.1678 | 42696.9359 | 194038.3195 | 399959.1985 | 293.8015
|  |  | Informado en el informe anterior > | 400253 | 64038.8998 | 92469.37 | 40940.2 | 185923.39 |  | 0 | 0 | 0 | 64038.8998 | 92469.37 | 40940.2 | 185923.39 | 383371.8598 | 16881.1402
| LEVY 1% SEGÚN DOCUMENTO DE PROYECTO FIRMADO (COBRADO AL MOMENTO DE DEPOSITO) |  | 1% | 4002.53 | [9 empty] | Valor del informe anterior ↑ | Valor del informe anterior ↑ | Valor del informe anterior ↑ | Valor del informe anterior ↑ | Underspend del informe anterior ↑
| GMS SEGÚN DOCUMENTO DE PROYECTO 8% (SE COBRARA A MEDIDA QUE SE REALICE EL GASTO) |  | 8% | 32020.24
[14 empty] | Valor más alto reportado ahora ↓ | Valor más alto reportado ahora ↓ | Valor más alto reportado ahora ↓ | Valor más alto reportado ahora ↓ | Valor más bajo reportado ahora ↓
|  | 1.1986 | TOTAL ACUERDO | 436275.77 | [8 empty] | 522907.0496 | 3967.7978 | 1756.7359 | 8114.9295 | 16587.3386 | -16587.3386
|  |  | Correct total acuerdo | 436276.57 | [9 empty] | ↑ Reporte Reconciliado (GBP 1.00 a USD 1.19857). Este monto se genero debido a la diferencia de tipo de cambio, utilizado en el momento del reporte a UK 1 dolar por 0.8 libra a Marzo de 2024, tipo de cambio errado ya que el desembolso de UK (pago adelantado) fue de 1 libra a 1.19857 dólares americanos. | ← Misma explicación. | ← Misma explicación. | ← Misma explicación. | ← Misma explicación.
Palladium note (09/09/2024):
| The total project value was paid 100% in advance. OH 8% and Levy 1% were charged, totaling 9%. The project budget includes OH and Levy on the total project value and not on each output task, so we are removing this from the Financial Report column J, to have only the expense value, since HO and Levy are highlighted in the lines at the end of the FR (lines 50-51). Note that with this adjustment, the % of resource usage of each line reduces in column S, but we understand that all the resource available to the project will be used until the end of the project implementation. | Nota: La celda H39 reporta una ejecución de 2,431.95 libras esterlinas conforme a las actividades del proyecto, sin embargo, se ha generado un gasto por tipo de cambio de USD. 286,25 equivalentes a 229 libras esterlinas, este monto no cobra GMS, razón por la cual en la celda K39 no figura una fórmula.
|  | Fórmula (celda K39) |  | 184.5845
|  | USD 30/10/24 | 1.2985 | 436275.77 | [8 empty] | 566499.7246
|  | USD 30/10/24 | 1.1986 | 436275.77 | [8 empty] | 522907.0496
[17 empty] | Underspend final > | 293.8015
Veré cómo resolver esto.
[12 empty] | 0 | INCORRECTO |  |  | CORRECTO
[13 empty] | MONTO CALCULADO POR UKPACT EN SU SISTEMA |  |  | MONTO SEGÚN ACUERDO UK EFECTIVAMENTE EJECUTADO |  | ERROR GENERADO
[13 empty] | Monto del acuerdo GBP | 436275.77 |  | Monto del acuerdo GBP | 436275.77
[13 empty] | Monde ejecucion 9% GBP | 400253 |  | Monte ejecucion GBP | 399959.2 | 293.8
[13 empty] | GMS 8% GBP | 32020.24 |  | Monto de GMS 8% GBP | 31996.736 | 23.504
[13 empty] | Monto Total EJECUCION GBP | 432273.24 |  | Monto Total EJECUCION GBP | 431955.936
[13 empty] | Monto levy 1% GBP | 4002.53 |  | Monto levy 1% GBP | 4319.5594
Nota: Según acuerdo no hay un cobro general de 9% El GMS 8% solo se cobra de la ejecucion del proyecto sin levy
[13 empty] | Cobro levy 1% | 436275.77
Note on F46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This value would need to be included. To do this, you would need to reduce some other line(s) that are underspending in the same proportion.

## Variance (hidden)
Variance Justification
In the following box can you please provide justification for any variance in spend from your previous forecast, that was provided through the Budget on Summary tab.
Ex: In the previous quarter, an expenditure of GBP xxx was forecast for this quarter, however tasks x-y-z (list task name/number) were not carried out, due to factors a-b-c, leading to an underspend of GBP xxx. (it serves to justify an entire task, which was planned and was not executed - details about underspend for an executed task will be described in the "Transaction list" tab). The tasks and their respective costs were relocated to the x-y-z quarter and are adjusted in the current Budget, thus providing a new forecast. (remember to adjust the other QPR documents, Annex 8, Results Report, GESI Assessment, etc., so that they also reflect the new deadlines where tasks are expected). List measures being taken to avoid similar delays in the future (if any that are within your control). The same example can be used (with some adjustments) in the case of overspend, if activities are carried out ahead of schedule, thus anticipating costs that were expected for the coming quarters.

## Eligible costs guidance (hidden)
Direct Costs Range Guidance and Evidence Requirements
Important: Budgets, including day rates, will be assessed as part of the call for proposals process. Day rates should be in line with local market rates and should also provide value for money – allowing projects to hire the right staff, with the right skills, at the right price. The suggested price ranges for personnel provided below include a cap for the maximum cost of day rates we will accept as part of proposals. Please bear in mind that this is ODA funding so value for money will be subject to high levels of scrutiny. Prices must reflect the accurate costs of delivering particular outputs or activities and costs must be able to be evidenced and justified. Attention should be paid to the types of evidence that will be required when completing grant claims for each cost.
Cost Category | Indicative Cost Range | Note | Types of evidence that should be retained
Profit | N/A | The UK PACT Country Programmes does not count profit as an eligible cost either within direct costs or within overheads. | N/A
Desktops, laptops, printers, scanners, cameras, etc | N/A | The UK PACT Country Programmes does not support this category. If the project needs to purchase items in this category, please seek funding from other sources. | N/A
Office rental | N/A | The UK PACT Country Programmes does not support this category. If the project needs to purchase items in this category, please seek funding from other sources. This cost is eligible as an overhead. | N/A
Salaries (excluding labour charged by day rate – please see below) | N/A | The UK PACT Country Programmes does not support this category. If the project needs to purchase items in this category, please seek funding from other sources. | N/A
Payment for Beneficiaries and/or Government officials to attend meetings, seminars, etc. | N/A | The UK PACT Country Programmes does not support this category. If the project needs to purchase items in this category, please seek funding from other sources. | N/A
Communications costs | N/A | Communications and branding costs count as Direct Project Costs and therefore should be included in budget. However, please note, there is limited available budget for communications costs within UK PACT budgets. All communications costs are allocated from a finite central budget which covers all UK PACT programmes. The overarching principle that indicates whether costs should be classified as communications is that costs directly related to disseminating project outputs should not be classified as communications, whereas costs relating to the wider promotion of your project would be classified as communications. For further guidance please see the UK PACT Country Programmes Applicant Handbook in the Country Programmes Opportunities Portal. | N/A
Principal expert/day (8 hours) (expert who provides essential international expertise needed for the research/study) | Dependant on cost of employment (maximum £1000) | The level of pay across the project team should reflect the nature of work and seniority of implementers. All rates must be based on the cost of employing that specific individual on the project. UK PACT may carry our own benchmarking to ensure the rates proposed represent Value for Money. | Timesheet
Senior expert/day (8 hours) (expert who provides key consultancy and analytical work for the research/study) | Dependant on cost of employment (maximum £800) |  | Timesheet
Expert/day (8 hours) (expert who provides general consultancy and analytical work for the research/study) | Dependant on cost of employment (maximum £550) |  | Timesheet
Junior expert/day (8 hours) (personnel that provide entry-level analytical and consultancy work for the research/study) | Dependant on cost of employment (maximum £450) |  | Timesheet
Assistant to expert/day (8 hours) (assist the experts to collect information, carry out research, interviews, etc.) | Dependant on cost of employment (maximum £350) |  | Timesheet
Project manager/day (8 hours) | Dependant on cost of employment (maximum £500) |  | Timesheet
Support staff/day (8 hours) | Dependant on cost of employment (maximum £400) |  | Timesheet
Admin assistant/day (8 hours) | Dependant on cost of employment (maximum £150) |  | Timesheet
The person day consultancy cost shall be based on accumulative basis. For example, if the person spends 2 hours a day for project and rest of 6 hours on non-project work, the total cost for 4 working days shall be calculated in the budget as 1 person day (counting 8 working hours as 1 full working day).
Accommodation and subsistence per person/day. | Hotel: Market rate - Maximum £120 Meals: Market rate - Maximum £30 | Prices are the maximum allowed to spend per day, per person. But costs should reflect the market rate. Note that meals include: breakfast, lunch and dinner. Costs are expected to be reasonable and accurate | Original itemised receipt provided by the vendor or customer’s copy of charge/credit card slip
Domestic Travel | Travel costs, including taxis to/from airports, hotels, project events or beneficiary meetings can be reimbursed with evidence of need.
Flights | All need to take economy class for both domestic and international flights. |  | Original itemised receipt provided by the vendor, or a credit card statement if a receipt is not available and an itemised receipt is not required, or a passenger invoice/itinerary
Event venue cost per person/Day | Market rate. Cost may vary, but evidence on Value for money should be provided. (e.g. requesting 3 quotes) | This should be the baseline standard that includes: 1 meeting conference room for 8 hours; 1 buffet lunch; 2 coffee/snack breaks; basic audio-visual equipment; pen, writing pads, and iced water etc. | Payment receipt along with the conference agenda showing the cost breakdowns (including receipts where applicable), topic of discussion and proof of payment
Consecutive and simultaneous interpretation | Market rate - Maximum £325 | This applies to interpretation carried out within the target country and internationally for one full working day | Timesheet or Invoice of services
Translation
Print fees | Market rate |  | Itemised receipt from vendor
Other | If you select "other" under cost category, please provide a description of the costs relevance to the project. |  | Relevant evidence, dependent on cost type
Note 1: Administrative cost/overheads should be reasonable and will be reviewed by the UK PACT Team. Costs included as direct project costs must not be duplicated as overheads – for example, a specific member of staff's salary should be removed from indirect costs if it is being charged as a direct cost for this project. For more details on what constitutes an eligible cost, please refer to the UK PACT Country Programmes Applicant Handook which you will find on the Country Programmes Opportunities Portal.
Permanent
Fixed term
Sub-contractor
National (Personnel based in country where project is being delivered)
International (Personnel based outside country where project is being delivered)

## Reporte final UK 30SEP (hidden)
Transaction list
Line | Task name | Date completed | Evidence supplied for task completion | Planned total expenditure (GBP) | Total direct expenditure Q1 (GBP) | Total direct expenditure Q2 (GBP)2 | Total direct expenditure Q3 (GBP)3 | Total direct expenditure Q4 (GBP)4 | Overhead % | Overhead Q1 total | Overhead Q2 total2 | Overhead Q3 total3 | Actual total expenditure (Dec2023) Q1 | Actual total expenditure (Mar2024) Q2 | Actual total expenditure (Jun2024) Q3 | Actual total expenditure (Jun2024) Q4 | Total expenditure Q1+Q2+Q3+Q4 | Variance | Expenditure in percentage | Notes | Notes2 | Notes3 | Notes3
1.1. | Developing the design for Calibration/Validation, overseeing measurements, preparing data analysis, and documenting outcomes | Q2 and ongoing |  | 6900 | 0 | 994.78 | 0 | 3210.89 | 0% | 0 | 0 | 0 | 0 | 994.78 | 0 | 3210.89 | 4205.67 | 2694.33 | 60.95%
1.2. | Arranging logistical aspects of on-site measurements, documenting sites and measurements, and consolidating measurements | Q2 and ongoing |  | 6210 | 0 | 4545.31 | 0 | 1664.45 | 0% | 0 | 0 | 0 | 0 | 4545.31 | 0 | 1664.45 | 6209.76 | 0.24 | 100%
1.3. | Logging measurement records (dbh) | Q2 and ongoing |  | 4830 | 0 | 3294.96 | 1422.48 | 112.55 | 0% | 0 | 0 | 0 | 0 | 3294.96 | 1422.48 | 112.55 | 4829.99 | 0.01 | 100% | The line is overspending. Explain here why more resources were used for this activity. Note that you will have to spend less on some other line, to stay within the Budget, or else, assume the extra expenses with your own resources. | Según el presupuesto aprobado por UK, el sobregiro es de GBP 264.84, monto que se encuentra por debajo de GBP 10k autorizados por UK. | Las variaciones inferiores o superiores al 10% (del monto total aprobado en el presupuesto para la línea) deben justificarse. En este caso no procede la justificación, pero hay que tener en cuenta que se gastaron 264,84 GBP más que la cantidad presupuestada. UK PACT no pagará este aumento de gastos y UNDP tendrá que ahorrar esta cantidad en algún otro gasto del proyecto, o pagarlo con sus propios recursos. | El monto no está sobregirado porque esta partida fue reformulada
1.4. | Gauging log height | Q2 and ongoing |  | 4830 | 0 | 3294.96 | 0 | 1534.82 | 0% | 0 | 0 | 0 | 0 | 3294.96 | 0 | 1534.82 | 4829.78 | 0.22 | 100%
1.5. | Identifying and enrolling tree species | Q2 and ongoing |  | 4830 | 0 | 2272.65 | 0 | 2556.98 | 0% | 0 | 0 | 0 | 0 | 2272.65 | 0 | 2556.98 | 4829.63 | 0.37 | 99.99%
1.6. | Enrolling data | Q2 and ongoing |  | 4830 | 0 | 568.16 | 0 | 1933.3 | 0% | 0 | 0 | 0 | 0 | 568.16 | 0 | 1933.3 | 2501.46 | 2328.54 | 51.79%
1.7. | Preparing the site | Q3 and ongoing |  | 14400 | 0 | 0 | 0 | 14192.42 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 14192.42 | 14192.42 | 207.58 | 98.56%
1.8. | Creating the LiDAR processing sequence, processing LiDAR canopy height measurements, and harmonizing LiDAR, SAR and ground measurements in aerial and spatial contexts | Q2 and ongoing |  | 24400 | 0 | 5883.92 | 2004.29 | 16509.38 | 0% | 0 | 0 | 0 | 0 | 5883.92 | 2004.29 | 16509.38 | 24397.59 | 2.41 | 99.99%
1.9. | Constructing the emissions monitoring framework for degradation-related assessments, charting burned forest extent and logging effects, delineating annual degradation, and computing associated emissions | Q3 and ongoing |  | 12000 | 0 | 0 | 0 | 11998.32 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 11998.32 | 11998.32 | 1.68 | 99.99%
1.10. | Detecting land cover via LiDAR sensors | Q2 and ongoing | Evidence 1.10 folder | 75768 | 0 | 27621.43 | 3670.44 | 44469.64 | 0% | 0 | 0 | 0 | 0 | 27621.43 | 3670.44 | 44469.64 | 75761.51 | 6.49 | 99.99% | Inform if this is a single expense up to 10k, if yes, will require evidence. | Se adjunta evidencia | ¿Puedes enviar la factura? | Se adjunta factura
1.11. | Developing progress reports and results monitoring in each area | Q3 and ongoing |  | 4250 | 0 | 0 | 0 | 3760 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 3760 | 3760 | 490 | 88.47%
1.12. | Establishing GESI Initiative 1: Mainstreaming Inclusion | Q3 and ongoing |  | 2250 | 0 | 0 | 0 | 2286.38 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 2286.38 | 2286.38 | -36.38 | 101.6%
1.13. | Establishing GESI Initiative 2: Diverse and Representative Teams | Q3 and ongoing |  | 2250 | 0 | 0 | 0 | 2179.75 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 2179.75 | 2179.75 | 70.25 | 96.88%
1.14. | Formulating the conceptual and analytical framework | Q2 and ongoing |  | 12750 | 0 | 5448.42 | 3852.26 | 2513.83 | 0% | 0 | 0 | 0 | 0 | 5448.42 | 3852.26 | 2513.83 | 11814.51 | 935.49 | 92.66%
1.15. | Overseeing and tracking the work plan | Q2 and ongoing |  | 10800 | 0 | 3204.16 | 1512.17 | 1507.73 | 0% | 0 | 0 | 0 | 0 | 3204.16 | 1512.17 | 1507.73 | 6224.06 | 4575.94 | 57.63%
1.16. | Managing technical and administrative aspects | Q2 and ongoing |  | 2800 | 0 | 322.34 | 0 | 1037.91 | 0% | 0 | 0 | 0 | 0 | 322.34 | 0 | 1037.91 | 1360.25 | 1439.75 | 48.58%
1.17. | Devising training programs | Q3 and ongoing |  | 2310 | 0 | 0 | 1256.54 | 490.22 | 0% | 0 | 0 | 0 | 0 | 0 | 1256.54 | 490.22 | 1746.76 | 563.24 | 75.62%
1.18. | Assembling and refining technical and financial reports | Q2 and ongoing |  | 5500 | 0 | 1614.35 | 1128.08 | 516.52 | 0% | 0 | 0 | 0 | 0 | 1614.35 | 1128.08 | 516.52 | 3258.95 | 2241.05 | 59.25%
1.19. | Formulating administrative procedures | Q2 and ongoing |  | 4800 | 0 | 1867.49 | 1553.58 | 1343.7 | 0% | 0 | 0 | 0 | 0 | 1867.49 | 1553.58 | 1343.7 | 4764.77 | 35.23 | 99.27%
1.20. | Creating financial reports | Q2 - Q3 and ongoing |  | 5400 | 0 | 2045.66 | 1629.48 | 1439.66 | 0% | 0 | 0 | 0 | 0 | 2045.66 | 1629.48 | 1439.66 | 5114.8 | 285.2 | 94.72%
2.1. | Creating Quality Assurance/Quality Control (QA/QC) procedures | Q1 - Q2 and ongoing | Evidence 2.1 folder | 26100 | 12039.4655 | 3452.22 | 3457.26 | 7150.01 | 0% | 0 | 0 | 0 | 12039.4655 | 3452.22 | 3457.26 | 7150.01 | 26098.9555 | 1.0445 | 100% | Inform if this is a single expense up to 10k, if yes, will require evidence. | Se adjunta evidencia | ¿Puedes enviar la factura? | Se adjunta factura
2.2. | Compiling geodatabases, programming web interfaces, and configuring the Geoserver | Q1 - Q2 and ongoing | Evidence 2.2 folder | 17625 | 10713.76 | 2547.6 | 2551.32 | 1812.05 | 0% | 0 | 0 | 0 | 10713.76 | 2547.6 | 2551.32 | 1812.05 | 17624.73 | 0.27 | 100% | Inform if this is a single expense up to 10k, if yes, will require evidence. | Se adjunta evidencia | ¿Puedes enviar la factura? | Se adjunta factura
2.3. | Collecting Landsat/Sentinel 2 time series data for Pando, conducting land use classification after deforestation, and assessing thematic accuracy of maps | Q1 - Q2 and ongoing |  | 15600 | 8884.5878 | 2547.6 | 2551.32 | 1616.25 | 0% | 0 | 0 | 0 | 8884.5878 | 2547.6 | 2551.32 | 1616.25 | 15599.7578 | 0.24223 | 100%
2.4. | Collecting Landsat/Sentinel 2 time series data for Charagua, conducting land use classification after deforestation, and assessing thematic accuracy of maps | Q1 - Q2 and ongoing |  | 15600 | 6949.722 | 1992.75 | 1995.66 | 4661.19 | 0% | 0 | 0 | 0 | 6949.722 | 1992.75 | 1995.66 | 4661.19 | 15599.322 | 0.67801 | 100%
2.5. | Identifying annual degradation patterns and evaluating thematic precision of maps in Pando | Q1 - Q2 and ongoing |  | 15600 | 6393.7263 | 1833.32 | 1835.99 | 5536.09 | 0% | 0 | 0 | 0 | 6393.7263 | 1833.32 | 1835.99 | 5536.09 | 15599.1263 | 0.87369 | 99.99%
2.6. | Identifying annual degradation patterns and evaluating thematic precision of maps in Charagua | Q1 - Q2 and ongoing |  | 15600 | 6393.7263 | 1833.32 | 1835.99 | 5536.09 | 0% | 0 | 0 | 0 | 6393.7263 | 1833.32 | 1835.99 | 5536.09 | 15599.1263 | 0.87369 | 99.99%
2.7. | Developing progress reports and results monitoring in each area | Q2 and ongoing |  | 4250 | 0 | 3172.01 | 793.82 | 41.32 | 0% | 0 | 0 | 0 | 0 | 3172.01 | 793.82 | 41.32 | 4007.15 | 242.85 | 94.29% | The line is overspending. Explain here why more resources were used for this activity. Note that you will have to spend less on some other line, to stay within the Budget, or else, assume the extra expenses with your own resources. | Según el presupuesto aprobado por UK, el sobregiro es de GBP 33.10, monto que se encuentra por debajo de GBP 10k autorizados por UK. | El mismo comentario hecho en la celda V7 se aplica aquí. | No Corresponde a un gasto de FAN
2.8. | Establishing GESI Initiative 3: Participation and Empowerment | Q3 and ongoing |  | 2250 | 0 | 0 | 1144.02 | 1105.98 | 0% | 0 | 0 | 0 | 0 | 0 | 1144.02 | 1105.98 | 2250 | 0 | 100%
2.9. | Establishing GESI Initiative 4: Data Collection for Informed Action | Q3 and ongoing |  | 2250 | 0 | 0 | 0 | 2250 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 2250 | 2250 | 0 | 100%
2.10. | Creating consultation modules for Charagua and Pando | Q3 and ongoing |  | 11700 | 0 | 0 | 0 | 11198.37 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 11198.37 | 11198.37 | 501.63 | 95.71%
2.11. | Conducting training workshops | Q2 and ongoing |  | 2310 | 0 | 927.92 | 0 | 1378.84 | 0% | 0 | 0 | 0 | 0 | 927.92 | 0 | 1378.84 | 2306.76 | 3.24 | 99.86%
2.12. | Ticket handling | Q2 and ongoing |  | 920 | 0 | 493.06 | 103.48 | 293.24 | 0% | 0 | 0 | 0 | 0 | 493.06 | 103.48 | 293.24 | 889.78 | 30.22 | 96.72%
2.13. | Managing travel expenses | Q2 and ongoing |  | 2800 | 0 | 577.79 | 38.93 | 2067 | 0% | 0 | 0 | 0 | 0 | 577.79 | 38.93 | 2067 | 2683.72 | 116.28 | 95.85%
3.2. | Formulating the legal and institutional structure for safeguards | Q3 and ongoing |  | 7040 | 0 | 0 | 0 | 7040 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 7040 | 7040 | 0 | 100%
3.3. | Providing technical support for safeguard management | Q1 - Q2 and ongoing |  | 12000 | 8550.712 | 2431.95 | 0 | 1017.34 | 0% | 0 | 0 | 0 | 8550.712 | 2431.95 | 0 | 1017.34 | 12000.002 | -0.002 | 100%
3.4. | Enhancing and building local governance capabilities | Q3 and ongoing |  | 7500 | 0 | 0 | 0 | 7486.9 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 7486.9 | 7486.9 | 13.1 | 99.83%
3.5. | Fostering coordination within the territory | Q2 and ongoing |  | 4800 | 2170.552 | 2505.36 | 0 | 124.15 | 0% | 0 | 0 | 0 | 2170.552 | 2505.36 | 0 | 124.15 | 4800.062 | -0.062 | 100% | The line is overspending. Explain here why more resources were used for this activity. Note that you will have to spend less on some other line, to stay within the Budget, or else, assume the extra expenses with your own resources. | Según el presupuesto aprobado por UK, el sobregiro es de GBP 2,344.12, monto que se encuentra por debajo de GBP 10k autorizados por UK. (Se espera respuesta de la FAN) | ¡Quizás aquí tengamos un malentendido! Un gasto individual que cueste más de 10.000 GBP debe tener un documento contable justificativo (factura, etc.). Se deberán justificar variaciones inferiores o superiores al 10% (del importe total aprobado en el supuesto de la línea). El monto gastado en esta línea es un 49 % superior al monto presupuestado, así que solo proporcione una oración que explique por qué ocurrió este gasto adicional. UK PACT no pagará este aumento de gasto y el PNUD tendrá que ahorrar esta cantidad en algún otro gasto del proyecto, o pagarlo con sus propios recursos. | Esta partida fue reformulada
3.6. | Delivering specialized technical training programs | Q1 - Q2 and ongoing |  | 9450 | 1942.648 | 599.94 | 1922.45 | 4899.2 | 0% | 0 | 0 | 0 | 1942.648 | 599.94 | 1922.45 | 4899.2 | 9364.238 | 85.762 | 99.09%
3.7. | Developing progress reports and results monitoring in each area | Q3 and ongoing |  | 2050 | 0 | 0 | 1628.48 | 399.76 | 0% | 0 | 0 | 0 | 0 | 0 | 1628.48 | 399.76 | 2028.24 | 21.76 | 98.94%
3.8. | Establishing GESI Initiative 5: Enhancing Capacity and Opportunities | Q3 and ongoing |  | 1250 | 0 | 0 | 0 | 1250 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 1250 | 0 | 100%
3.9. | Establishing GESI Initiative 6: Promoting GESI Awareness | Q3 and ongoing |  | 2250 | 0 | 0 | 0 | 2274.7 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 2274.7 | 2274.7 | -24.7 | 101.1%
3.10. | Administrative assistance | Q2 and ongoing |  | 9200 | 0 | 4575.94 | 3052.16 | 1526.46 | 0% | 0 | 0 | 0 | 0 | 4575.94 | 3052.16 | 1526.46 | 9154.56 | 45.44 | 99.51%
|  | 0 |  | 400253 | 64038.8998 | 92469.37 | 40940.2 | 185923.39 |  | 0 | 0 | 0 | 64038.8998 | 92469.37 | 40940.2 | 185923.39 | 383371.8598 | 16881.1402
| LEVY 1% SEGÚN DOCUMENTO DE PROYECTO FIRMADO (COBRADO AL MOMENTO DE DEPOSITO) |  |  | 4002.53
| GMS SEGÚN DOCUMENTO DE PROYECTO 8% (SE COBRARA A MEDIDA QUE SE REALICE EL GASTO) |  |  | 32020.24 | [8 empty] | 5123.112 | 7397.5496 | 3275.216 | 14873.8712 | 30669.7488
|  |  | TOTAL ACUERDO | 436275.77
DETALLE PRESUPUESTO PROYECTO EN LIBRAS Y DOLARES AMERICANOS
|  |  | PRESUPUESTO EN LIBRAS ESTERLINAS | [9 empty] | PRESUPUESTO EN DOLARES AMERICANOS | DESEMBOLSO RECIBIDO EN DOLARES AMERICANOS DE UK
|  | Ejecución | Fórmula (celda K39) | 400253 | [8 empty] | 519428.86 | 479378.7
|  | GMS |  | 32020.24 | [8 empty] | 41554.3088 | 38350.296
|  | Levy |  | 4002.53 | [8 empty] | 5609.83 | 5177.29
|  | Total |  | 436275.77 | [8 empty] | 566592.9988 | 522906.286
Palladium note (09/09/2024):
The total project value was paid 100% in advance. OH 8% and Levy 1% were charged, totaling 9%. The project budget includes OH and Levy on the total project value and not on each output task, so we are removing this from the Financial Report column J, to have only the expense value, since HO and Levy are highlighted in the lines at the end of the FR. Note that with this adjustment, the % of resource usage of each line reduces in column S, but we understand that all the resource available to the project will be used until the end of the project implementation.
Formulas:
Date completed = SUBTOTAL(109,Table13[Date completed])
Note on F46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This value would need to be included. To do this, you would need to reduce some other line(s) that are underspending in the same proportion.

## Staff list (hidden)
Staff list
Name Name and surname of person | Sub-Category Role of personnel on project | Day Rate in Local Currency The cost to the organisation to emply that individual for one day | Number of Days Worked Number of days the employee has worked on the project to date | Organisation Which consortium member the individual will be employed by | Location Where the person is based | Employment Type The contract type under which the individual is employed by the organisation | Start date Date the employee began working on the project | End date Date the employee ceased working on the project
Please add more rows as necessary