Project Title: Strengthening Justice and Security Sector Governance in Pakistan (Rule of Law Programme)

Project Number: 01001551

Implementing Partner: United Nations Development Programme (UNDP), Pakistan

Start Date:	01 January 2024		End Date: 	31 December 2027

PAC Meeting date: 10 November 2023

Brief Description

The 2030 Sustainable Development Goals (SDG) 16 and 5 re-affirm that peace, stability, accountable governance, adherence to the rule of law and achieving gender equality and empowering women and girls are essential pre-requisites for sustainable development. Strong and inclusive institutions, good governance, access to justice and security for all, and a stable economy are essential pre-requisites to achieve durable peace, development, and stability in Pakistan. A major factor in the country's transition to long-term peace, security, stability, and development will be the state’s ability to strengthen justice and security sector governance, and the reasonable delivery of these services to the people of Pakistan, However, Pakistan is at a crossroads, facing a myriad of challenges relating to political instability, armed conflict and violent extremism, weak governance and institutions, lack of inclusive justice and security for all, high vulnerability to climate disasters, and a crisis hit economy with rapidly receding foreign reserves, rising levels of public debt, and high inflation pushing millions into poverty. Moreover, as a crucial complement to a functioning justice and security sector, people need to regain their trust and confidence that access to justice and security going forward will be timely, inclusive, affordable, and accessible to all especially for women and the most marginalized and vulnerable groups, as well as meeting international standards of due process, human rights principles, and full compliance with the rule of law. Against this backdrop, the new Rule of Law Programme phase of UNDP Pakistan builds on its foundational work since 2013 with the judiciary, prosecution services, bar associations, law enforcement agencies (i.e. Police, Anti-Narcotics Force (ANF) and Excise, Taxation & Anti-Narcotics (ETAN) Department, and a range of civil society organizations (CSOs) in Khyber Pakhtunkhwa (KP) including Merged Districts (MDs), Balochistan, Gilgit Balochistan (GB), Sindh, and the Federal Capital Territory of Islamabad. The overall Rule of Law Programme of work aims to enhance security and justice sector governance to sustain peace and stability for the long-term in Pakistan by improving the efficiency and effectiveness of institutions to deliver accountable and affordable security and justice services to the people with specific emphasis on women and the most marginalized and vulnerable groups, and digital technologies. In the new phase, UNDP will continue to support the government’s efforts to implement justice and security sector reforms at federal, provincial, and district levels by providing a comprehensive support package that combines the following methodologies: - Technical advice and assistance on policy/strategy review and development, institutional skill-building through training and mentoring, community/public legal awareness raising/advocacy on referral pathways to access justice and security services, and piloting new approaches to improve timely, affordable, and accessible people-centered justice and security provision to all. - Women friendly and gender-responsive security and justice infrastructure rehabilitation and development (i.e., new constructions, rehabilitation/upgrade of old infrastructure), and the provision of essential equipment (e.g., furniture and Information and Communications Technology (ICT)), and flood resilient and green energy support, including solarization.

| Contributing Outcome (UNSDCF, CPD): UNSDCF/CPD outcome involving UNDP No. 1. By 2027, the people of Pakistan, especially women, children, and the most vulnerable and marginalized, have increased access to fundamental rights, gender equality and fundamental freedom through inclusive, accountable, effective, and evidence-driven governance systems and rule-of-law institutions at all levels of government, contributing to good governance and stability. Indicative Output(s) with gender marker: Project Output 1: Policy, legal and regulatory frameworks strengthened to warrant people-centered, equitable, timely, affordable justice and security delivery to all people with an emphasis on women, marginalized and vulnerable groups, and digital technologies. (Gen-2) Project Output 2: Capacity of justice and security stakeholders (duty bearers) enhanced to deliver inclusive, timely, and accessible services to all people with an emphasis on women and digital technologies. (Gen-2) Project Output 3: Capacity of women, and the most vulnerable and marginalized (rights holders) strengthened to access referral pathways to justice and security. (Gen-2) Project Output 4: Justice and security sector institutional facilities enhanced to deliver inclusive, timely, and accessible justice and security services, through women friendly and gender-responsive infrastructure development support with an emphasis on flood resilience and green energy. (Gen-2) |  | Total resources required: | US$32,500,362 |  |
| --- | --- | --- | --- | --- |
|  |  | Total resources allocated: |  |  |
|  |  |  | UNDP TRAC: | 00 |
|  |  |  | Donor: | EU: US$4,878,513 US – INL: US$3,532,000 |
|  |  |  | Government: |  |
|  |  |  | In-Kind: | USD$910,000 |
|  |  | Unfunded: | US$23,179,849 |  |

Agreed by (signatures):

| Government | UNDP |
| --- | --- |
| Print Name: | Print Name: |
| Date: | Date: |

# I. Development Challenge

A vital precondition for long-term peace, stability, security, development, and a stable economy is the rule of law. The UNDP Rule of Law Programme's ongoing M&E, context analysis, assessments, and research, however, show that Pakistan's justice and security sectors continue to be constrained by a number of challenges, including those relating to out-of-date policy and legislation, capacity restrictions, including a lack of technical expertise, the majority of the current infrastructure in need of rehabilitation, and a lack of new infrastructure to address emerging requirements including digital technologies. These challenges exacerbate the insecurity perceived by people in the absence of access to expedient and equitable justice and security particularly for women, transgender persons, religious minorities, and other marginalized and vulnerable people. According to a recent study of the UNDP Rule of Law Programme, less than half of the respondents in Balochistan (42%) and KP (38%) confirmed access to justice. In the Global Rule of Law Index 2022 Pakistan ranked 129th out of 140 countries, and 145th out of 146 countries on the Global Gender Parity Index. Pakistan’s crime statistics for 2021-2022 reveal 1,086,204 cases, with KP, Punjab, Sindh, and Balochistan most affected.

Against this backdrop, the majority of policy, legal and regulatory frameworks in place to guide governance functions and the work of justice and security sector institutions in Pakistan are outdated and require revisions and updates to ensure that they correspond with real time needs and priorities. Similarly, the majority of them also do not have any form of implementation mechanisms/action plans to translate these policies and laws into tangible actions, thus resulting in often dormant policies and strategies that continually fail to make a positive difference in enhancing justice and security sector governance and service delivery to people. There is also a gap in tailored policies, strategies, and legal/regulatory frameworks specific to judiciaries, prosecution services, prison services, and law enforcement agencies (e.g., police), as well as their consistent application across provinces. In addition to the security and justice sector capacity gaps, there is fragmentation and inconsistency in quality, standards, and methods of training between national and provincial levels, as well as at intra-provincial levels. As a result, it is also difficult to assess and appraise training and learning effectiveness across provinces because course curricula and training in justice and rule of law institutions are not harmonized. Similarly, outdated, and poor conditions of justice and security infrastructure severely undermine the ability to run an efficient and motivated judiciary, prosecution, and law enforcement services that are women friendly and people-centered.

Furthermore, the number of pending cases in formal courts highlights the struggles of Pakistan’s judicial system in delivering timely, fair, and affordable justice to people. Data from 2022 reveals a backlog of 2,144,318 cases: 51,766 in the Supreme Court, 337,605 in the provincial high courts, and 1,754,947 cases in the district courts. Unfortunately, the lack of gender segregated data makes it difficult to assess the percentage of cases involving women as case parties. The informal justice mechanisms (e.g., Alternative Dispute Resolution and Dispute Resolution Committees) that are intended to reduce the caseload of superior courts while also dispensing inexpensive and speedy justice to people, require combined policy and implementation support to produce substantial results. Similarly, despite efforts to create independent prosecution services in Pakistan, there is not a visible change in the service delivery of these institutions. In certain areas (i.e., Islamabad Capital Territory and GB), prosecution and police services still overlap, which calls into question the independent prosecution service, right to a fair trial, equality before the law and equal protection of the law guaranteed by the Constitution of Pakistan and international human rights standards for criminal trials. In addressing these gaps, both the judiciary and prosecution services in Pakistan need long-term reform support in terms of building institutional capacity and the capacity of judges, lawyers, prosecutors, and court staff to deliver speedy and affordable justice services, combined with policy/legislative support, as well as infrastructure/rehabilitation support, including through digitalization of court proceedings (i.e. virtual courts and digital case management systems) to strengthen accessibility and accountability. Another persistent challenge is the lack of equitable representation and opportunities within the justice system for women despite government quotas, as well as for other marginalized and vulnerable groups. For example, political, legal, and socioeconomic marginalization and exclusion underpinned by the patriarchal social structures discourage and disempower women from becoming lawyers/judges (duty bearers) and seeking redress from the justice system (right holders). In the Merged Districts (MDs) of Khyber Pakhtunkhwa (KP), there are currently four women (184 men) enrolled as lawyers and 19 women (308 men) practicing as advocates. In Balochistan, women lawyers comprise only 15% of the Bar enrolment (350 women lawyers out of a total 5,380 lawyers). In this context, women and most marginalized groups are less likely to report crimes or seek legal redress for property, family, or inheritance claims; crimes against women and girls, transgender persons, and people from marginalized groups are less likely to be adequately investigated or prosecuted. Therefore, another essential long-term reform objective in Pakistan is the empowerment of women and the most marginalized/vulnerable groups and enhancing their meaningful participation in the justice system and access to its services.

Forensic services are essential to examine crime scene evidence, and they play an important role in criminal investigations and prosecutions. However, the provinces of KP, Gilgit Baltistan (GB), and Balochistan face a serious lack of independent forensic services. For example, in KP the forensic services are under the provincial police department, which raises questions as to the admissibility of evidence in courts. The KP government aspires to establish an independent forensic service, through the Forensic Services Act 2020, but funding constraints, lack of technical expertise, and forensic laboratory custodianship disagreements hinder progress. The post-merger KP caseload is expected to reach 110,000 cases by 2030 and 170,000 by 2050 in comparison with the reported 74,759 cases in 2021. Pakistan’s provinces need comprehensive support packages to improve forensic services with technical assistance, training, infrastructure, and equipment. Similarly, improving the local police services, which are also the primary provider of public safety and security in Pakistan, necessitates long-term reform support particularly in the post-merger KP province. For example, the 23,000 former Levies and Khasadars inducted into the KP Police need to regularly receive training and mentoring to learn and advance their skills in core policing functions, such as community policing, crime management, responsive and preventative policing, security and protection management, and gender-responsive policing. To this end, KP and other provinces (e.g., GB and Balochistan) need long-term policy, capacity building, and infrastructure rehabilitation/development support to improve core policing functions and ensure that they are people-centered, accountable, and accessible to all. At the same time, they must also pilot new strategies and initiatives to establish people-centered policing in the MDs through initiatives like model police stations.

The corrections services in Pakistan (i.e., prisons, reclamation, probation, and probation), which are the end of the criminal justice system, are the weakest and most ignored institutions. Pakistan also has a large number of under-trial prisoners. Out of the total prison population of 88,687 persons (e.g., the majority (85,858) are adult men), 59,902 (71 percent) are under-trial prisoners (e.g. KP province 82 percent; Sindh 76 percent, Punjab 66 percent, and Balochistan 60 percent). Immediate areas of reform and support include policy, legislative, training and infrastructural support to enhance prison services and lower the number of under-trial prisoners.

Recognizing the rule of law, access to justice, and security challenges Pakistan is facing, the new Rule of Law  Programme phase aims to facilitate a convergence between people’s expectations for a just and secure society and the institutional capacities necessary to deliver essential justice services, which in the long term will promote peace, stability, and development in the country.

# II. Strategy

Since 2013, the UNDP Pakistan Rule of Law Programme has actively engaged with key stakeholders to strengthen people’s access to justice and security and enhance the capacity of rule of law institutions to deliver people-centered justice and security services. To this end, the Rule of Law Programme has been working with the judiciaries, home and tribal affairs departments, prosecution services, reclamation and probation services, bar councils and bar associations, law enforcement agencies, such as the Police, Anti-Narcotics Force (ANF) and Excise, Taxation & Anti-Narcotics (ETAN) Department, as well as informal justice forums, like Dispute Resolution Councils (DRCs) and court-annexed mediation. UNDP has also collaborated with UNODC and UN Women and civil society organizations (CSOs) in Pakistan to improve justice and security service delivery to people, with specific emphasis on women and the most vulnerable and marginalized communities. The Rule of Law Programme activities are carried out throughout Pakistan, including Balochistan, Gilgit Balochistan (GB), Khyber Pakhtunkhwa (KP) including the Merged Districts (MD), Sindh, and the Federal Capital Territory of Islamabad. In line with its new plan and strategy for the period of 2023 – 2027, the UNDP Rule of Law Programme will further expand its reach to encompass Sindh, Punjab, and AJ&K.

Key learnings from the previous Rule of Law Programme phase highlight that poorly governed justice and security sector institutions in Pakistan are persistent key drivers of flawed rule of law, weak civil justice, a deficient criminal justice system, and scant safety and security in Pakistan. In turn, justice and security service delivery is often slow, not inclusive, inaccessible, and unfeasible for many, including most women, transgender persons, and the most vulnerable and marginalized people. Strengthening the rule of law, justice, and security sector governance in Pakistan is a long-term reform priority that will necessitate the following parallel and multiple support areas: improvements to policy, legal, and regulatory frameworks (rules and processes) in accordance with international norms, principles, and best practices to hold duty bearers accountable for serving and protecting citizens; upskill duty bearers with new knowledge and skills to ensure due process and efficient service delivery (process); infrastructure development and rehabilitation support to improve rule of law, justice, and security service facilities to people (process); and empower rights holders, with a focus on women and the most vulnerable and marginalized people, to exercise their right to seek and access justice and security. Furthermore, the Rule of Law Programme’s learnings and evidence from the field to date suggest that often it is not gender inequality itself that fuels insecurity, injustice, and conflict, but the underlying norms that form the basis for gender inequality. For example, norms of what it means to be a man or woman promote behaviors and practices that might encourage the use of discrimination and violence to resolve issues. Therefore, gender equality as well as women's and girls' empowerment considerations must continue to cut across all project outputs. Moreover, the new strategy has also considered the recommendations of the 2019 Rule of Law Programme Impact Evaluation, which included strengthening policies, regulatory and legal frameworks, capacity building for duty bearers, and empowering rights holders as key elements in advancing the rule of law.

The strategy of the new phase of the Rule of Law Programme therefore builds on UNDP’s foundational work and learnings from the previous Rule of Law Programme phase (2019-2023) and broadens its scope and outreach as follows. The strategy of the new Rule of Law Programme phase will aim to amplify its focus on gender mainstreaming and social inclusion, aligning with UN Security Council Resolution 1325 and Pakistan's National Gender Policy Framework. The new phase will also aim to broaden its scope by using digital technologies to improve people's access to justice while also replicating best practices from the previous Rule of Law Programme phase. The Rule of Law Programme results framework integrates gender equality results into indicators, baseline data, and targets, with a minimum of 50% women beneficiaries.

Work Strand 1: Strengthen policy, legal, and regulatory frameworks through technical advice and assistance to ensure people-centered, equitable, timely, affordable justice and security service delivery to all people: The Rule of Law Programme will continue to focus on strengthening priority policy, legal, and regulatory frameworks through policy/strategy development/drafting (new), revisions/updates (of existing frameworks). Additionally, in the new phase the Rule of Law Programme will also enhance and develop provincial judiciaries, prosecution services, and law enforcement agencies (LEAs) implementation mechanisms/actions plans to translate these new/updated polices/strategies into action. In doing so, the new phase will also invest in efforts to foster harmonization and consistency across provinces to the extent possible.

Work Strand 2: Enhance capacity of justice and security stakeholders (duty bearers) to deliver inclusive, timely, and accessible services to all people: UNDP support in capacity building of rule of law, justice and security stakeholders (i.e. judiciary, prosecution, prisons, reclamation and probation services, bar councils and LEAs (i.e. Police, ETAN Department, and ANF) to date has been primarily in a facilitator role by providing logistical support to these institutions to deliver pre- and in-service trainings, and specialized and training of trainers (TOTs) trainings. The new Rule of Law Programme phase will advance this role into providing technical expertise to develop new training curricula, review/update existing curricula, formulate integrated frameworks and strategies to harmonize training at national and provincial levels, and deliver trainings through national and international subject experts. Where possible, UNDP will also provide mentoring support to master trainers of the justice and security sectors to enhance their capacities and skills to impart transferable new knowledge and learning to stakeholders from the judiciary, prosecution, and LEAs. Where possible, UNDP technical expertise on TOTs may also extend to combined training and mentoring of master trainers in justice and security training academies. The above approach will allow UNDP to ensure justice and security stakeholders receive the same high-quality training and maintain consistency in imparting new learning and skills across provinces. Similarly, the integrated/harmonized approach will also help to set a structured and reliable method of training and learning at an institutional level. It is a necessity to sustain these efforts in the long-term.

Work Strand 3: Empower women, and the most vulnerable and marginalized communities (rights holders) to access referral pathways to justice and security: UNDP will continue to focus on empowering women to seek and exercise their right to access referral pathways to justice and security. UNDP will engage with communities and civil society organizations to increase awareness of laws and rights, and enhance access to justice for all, especially women and the most marginalized groups including transgender persons. The Rule of Law Programme will also continue to support informal justice mechanisms (i.e., District Legal Empowerment Committees (DLECs) , Provincial Justice Committees (PJCs), Legal Aid and Justice Authority (LAJA), Dispute Resolution Committees (DRCs), Court-annexed mediation forums, provincial Alternative Dispute Resolution (ADR) bodies, provincial legal aid agencies, and bar councils). Building on this work, the new phase will broaden its scope by piloting innovative approaches to support new women lawyers/apprentices to commence their legal careers. The apprentice initiative will comprise of training, mentoring and work placement opportunities, engage mid-career women lawyers as trainers and mentors, and engage apprentices to deliver legal awareness and outreach sessions to school students and communities at provincial and district levels. In the case of LEAs, UNDP will extend its scope from technical support to develop gender-responsive strategies to implement them (i.e., ANF Gender Strategy (2022), KP Police Gender Strategy (2024), and KP Rule of Law Roadmap (2023)).

Work Strand 4: Enhance justice and security sector institutional facilities through infrastructure development/rehabilitation support to deliver inclusive, timely, and accessible justice and security services to all people: UNDP recognizes that functional and well-developed rule of law infrastructure also plays a crucial role in efficient and timely service delivery. The new phase will continue to support justice and security infrastructure development/rehabilitation, including essential equipment. The Rule of Law Programme will also continue to invest in further efforts to promote women friendly and gender-responsive rule of law infrastructure. Amongst other efforts, it will include dedicated residential accommodation for women in training academies, women-only rest and washrooms that consider their safety concerns, addressing the needs of persons with disabilities (PWDs) especially women with disabilities and childcare facilities to help maintain work-life balance for women law enforcement officers and lawyers. In the new phase, interventions will be broadened to place specific emphasis on self-reliance through green energy and flood and earthquake-resilient infrastructure development and rehabilitation to the extent possible. It will serve as a crucial mitigation strategy to minimize and prevent damage from possible future climate shocks/disasters to judiciary, prosecution, and LEA infrastructure in Pakistan. In terms of green energy, the Rule of Law Programme will particularly invest in installing hybrid solar systems, to increase green energy efficiency of rule of law infrastructure. It will thus allow justice and security stakeholders to maintain uninterrupted service delivery to people during climate calamities to the extent possible. Furthermore, where possible, in the new phase, UNDP will also aim to adopt a more integrated approach through a value-added accompaniment process from infrastructure development/rehabilitation support (hardware) to capacity building and policy and legislation support (softer components). Thus, building synergies to complement work strand 4 with work strands 1-3 where possible and feasible.

Figure 1: Strategy

## Theory of Change

The theory of change for the new Rule of Law Programme is based on the premise that Pakistan's justice and security sectors face numerous institutional challenges, including outmoded policies and legislation, a lack of technical expertise and capacity, gender equality and disparity, outdated infrastructure, and a lack of modern infrastructure to improve service efficiency and accountability (i.e., digital technologies). These problems hinder Pakistan's long-term peace, stability, and development and intensify people's feelings of insecurity, especially among vulnerable and disadvantaged groups including women, transgender persons, and religious minorities. In light of this, strengthening justice and security sector governance in Pakistan is a long-term reform priority and parallel and multiple support areas consisting of technical advice and assistance are needed to strengthen policy, legal, and regulatory frameworks for equitable, women friendly, and gender-responsive service delivery and people’s access to these services.

IF “justice and security stakeholder (duty bearers) and institutional capacities are increased to deliver people-centered, accountable, and efficient services to people (rights holders),

AND women and marginalized and vulnerable communities (rights holders) are empowered to exercise their rights to access these services,

THEN it will enhance justice and security sector governance and people’s right to access security and justice services, particularly for women and marginalized and vulnerable communities in Pakistan,

BECAUSE justice and security stakeholders (duty bearers) and institutions are upskilled to deliver people-centered, accountable, timely, and affordable services, and people, including women and the most marginalized and vulnerable communities, are able and empowered to seek and access referral pathways to security and justice.”

To this end, the new phase of the Rule of Law Programme will be implemented to achieve the following outputs with corresponding gender markers:

Project Output 1: Policy, legal and regulatory frameworks strengthened to warrant people-centered, equitable, timely, affordable justice and security delivery to all people with an emphasis on women, marginalized and vulnerable groups, and digital technologies. (Gen-2)

Project Output 2: Capacity of justice and security stakeholders (duty bearers) enhanced to deliver inclusive, timely, and accessible services to all people with an emphasis on women and digital technologies. (Gen-2)

Project Output 3: Capacity of women, and the most vulnerable and marginalized (rights holders) strengthened to access referral pathways to justice and security. (Gen-2)

Project Output 4: Justice and security sector institutional facilities enhanced to deliver inclusive, timely, and accessible justice and security services, through women friendly and gender-responsive infrastructure development support with an emphasis on flood resilience and green energy. (Gen-2)

Assumption: Pakistan’s justice and security sectors face numerous institutional challenges, such as outdated policies, limited technical expertise, gender inequality, and outdated infrastructure. These issues hinder peace, stability, and development particularly for women, and marginalized and vulnerable groups. Therefore, strengthening the rule of law and security sector governance is a necessity and a long-term reform priority to ensure people-centred, equitable, accountable and affordable justice and security service delivery and people’s access to these services in Pakistan.

Theory of Change:

IF “justice and security stakeholder (duty bearers) and institutional capacities are increased to deliver people-centered, accountable and efficient services to people (rights holders), and women and marginalized and vulnerable communities (rights holders) are empowered to exercise their rights to access these services,

THEN it will enhance justice and security sector governance and people’s right to access security and justice services, particularly for women and the most marginalized and vulnerable communities in Pakistan,

BECAUSE justice and security stakeholders (duty bearers) and institutions are upskilled to deliver people-centered, accountable, timely and affordable services, and people, including women and the most marginalized and vulnerable communities, are able and empowered to seek and access referral pathways to security and justice.”

Project Strategy:

1.Strengthen policy, legal and regulatory frameworks through technical advice and assistance to ensure people-centered, equitable, timely, affordable justice and security service delivery to all people.

2.Enhance capacity of justice and security stakeholders (duty bearers) to deliver inclusive, timely and accessible services to all people.

3.Empower women, and the most vulnerable and marginalized communities (rights holders) to access referral pathways to justice and security.

4.Enhance justice and security sector institutional facilities through infrastructure development/rehabilitation support to delivery inclusive, timely, and accessible justice and security services to people.

UNSDCF/CPD outcome involving UNDP No. 1.

By 2027, the people of Pakistan, especially women, children, and the most vulnerable and marginalized, have increased access to fundamental rights, gender equality and fundamental freedom through inclusive, accountable, effective, and evidence-driven governance systems and rule-of-law institutions at all levels of government, contributing to good governance and stability.

UNDP Strategic Plan Signature Solution 2: Governance

Output 2.2 (2022 – 2025)

Civic space and access to justice expanded, racism and discrimination addressed, and rule of law, human rights and equity strengthened.

Figure 2: Theory of Change

# III. Results and Partnerships

## Expected Results

The Rule of Law Programme aims to achieve the result of improved capacity of justice and security sector institutions to provide a safe and secure environment for the people of Pakistan.

Rule of Law Programme Output 1: Policy, legal and regulatory frameworks strengthened to warrant people-centered, equitable, timely, affordable justice and security delivery to all people with an emphasis on women, marginalized and vulnerable groups, and digital technologies. (Gen-2)

Expected results:

- Strengthened the legislation governing prisons and the lawful treatment of prisoners (e.g., the new Prisons Act and Prison Rules - KP, and the new Probation Act and Rules - Balochistan).

- Enhanced people’s access to court annexed Alternative Dispute Resolution (ADR) (e.g., ADR Act Amendment and Rules – Balochistan).

- Increased people’s access to justice through improved management of the virtual courts system (e.g., New Regulatory Frameworks on virtual courts - Balochistan and Sindh).

- Enhanced justice and security sector coherence, coordination, and reform implementation by rule of law institutions (Revised KP Rule of Law Road Map with new implementation framework, and new sectoral strategies and implementation plans; GB Rule of Law Road Map implementation framework).

- Strengthened policy framework to improve justice service delivery at High Courts and district judiciaries and people’s access to these services (e.g., New multi-year strategic plans - Sindh and Balochistan).

Rule of Law Programme Output 2: Capacity of justice and security stakeholders (duty bearers) enhanced to deliver inclusive, timely, and accessible services to all people with an emphasis on women and digital technologies. (Gen-2)

Expected results:

- Enhanced skills and knowledge of policewomen and men on core policing functions including gender-responsive and preventive policing (e.g., KP Police).

- Strengthened skills and knowledge of ANF officers (women and men) in countering supply and demand reduction of illicit narcotics and drugs (e.g., ANF).

- Enhanced capacities of the Excise, Taxation & Anti-Narcotics (ETAN) department officers (men and women) in drugs and substance control (e.g., ETAN – Balochistan (ETAN-B)).

- Increased training expertise and quality of training courses of KP Police, ANF, and ETAB- B (e.g., develop new training curricula, review/update existing curricula, formulate integrated frameworks and strategies to harmonize training at national and provincial levels, and training of trainers (TOTs) through national and international subject experts).

- Strengthened the capacities of forensic specialists in the analysis and examination of crime scene evidence (e.g., KP forensic services).

- Increased skills of women lawyers in case preparation and handling, counselling, court hearings (e.g., legal ethics, legal drafting, client and expert witness interview techniques, court presentation, and women protection laws).

- Increased training expertise and course quality of training for judges, lawyers, and court staff (women and men) of judicial training academies in Balochistan and Sindh (e.g., develop new training curricula on virtual courts system, formulate integrated frameworks and strategies to harmonize training between the two provinces, and training of trainers (TOTs) through national and international subject experts).

- Strengthened capacities of the Provincial Justice Committees (PJCs) and Criminal Justice Coordination Committees (CJCCs) for improved coordination and collaboration among justice sector institutions for efficient service delivery.

- Strengthened the capacity of ADR mediation forums and District Legal Empowerment Committees (DLECs), enabling affordable, time-efficient and fair dispute resolution at the local level (e.g., KP and Balochistan).

- Enhanced skills of prison officers (women and men) in prison management and lawful treatment of prisoners (e.g., KP Prisons Department).

- Increased capacities of reclamation and probation officers in the supervision, monitoring, and rehabilitation of probationers (e.g., Reclamation and Probation Departments - KP and Balochistan).

Rule of Law Programme Output 3: Capacity of women, and the most vulnerable and marginalized (rights holders) strengthened to access referral pathways to justice and security. (Gen-2)

Expected results:

- Enhanced legal empowerment of women, and the most vulnerable and marginalized groups including transgender people through increased knowledge and awareness of available justice referral pathways, how to access them, and related laws; right to access justice and security (rights holders); and duties of justice and rule of law providers (duty bearers) (e.g., KP and Balochistan).

- Improved access to affordable justice for women and marginalized and vulnerable groups including transgender people through collaborative partnerships and joint advocacy with informal justice mechanisms, such as the DLECs, PJCs, CJCCs, Legal Aid and Justice Authority (LAJA), provincial legal aid agencies, DRCs, court annexed mediation forums and ADR bodies, and bar councils (e.g., KP and Balochistan).

- Strengthened women’s representation in the justice system (duty bearers) by piloting an initiative of legal empowerment, knowledge sharing, and mentoring for new women lawyers, apprentices, and law students (e.g., KP and Balochistan).

- Enhanced women’s representation in the police (duty bearers) through a joint advocacy campaign on women police officer recruitment with KP Police (e.g., KP).

- Enhanced gender sensitization and awareness among LEAs (i.e., ANF and KP Police) through the implementation of ANF and KP Police Gender Strategies and the KP Rule of Law Roadmap.

Rule of Law Programme Output 4: Justice and security sector institutional facilities enhanced to deliver inclusive, timely, and accessible justice and security services, through women friendly and gender-responsive infrastructure development support with an emphasis on flood resilience and green energy. (Gen-2)

Expected results:

- Increased people’s accessibility to police and efficiency in police service delivery through newly constructed and rehabilitated gender-responsive infrastructure. (e.g., KP and Balochistan)

- Enhanced police training facilities through a newly constructed and rehabilitated training center/school and hostel for women and men (e.g., KP and Balochistan).

- Strengthened LEAs (i.e., ANF and ETAN- B) training facilities through a newly constructed training center and academy (e.g., Islamabad and Balochistan).

- Increased facilities to analyze and examine crime scene evidence through a newly built forensic science lab (e.g., KP).

- Increased people’s accessibility to justice service delivery through newly constructed and rehabilitated gender-responsive infrastructure (e.g., KP and Balochistan).

- People’s access to justice is enhanced through digital justice, especially the virtual courts system and cash flow management (e.g., KP, Balochistan, Sindh, and GB).

- Enhanced training facilities for prison officers and living conditions for inmates through new and upgraded prison infrastructure (e.g., KP).

- Increased access to vocational training opportunities for women in order to eradicate poppy and cannabis cultivation and narcotics trade through the construction of new residential training centers (e.g., KP).

(For further details on activities and annual targets and indicators please see Section VII: Multi-Year Work Plan and Section V: Results Framework)

UNSDCF/CPD outcome involving UNDP

No.1: By 2027, the people of Pakistan, especially women, children, and the most vulnerable and marginalized, have increased access to fundamental rights, gender equality, and fundamental freedoms through inclusive, accountable, effective and evidence-driven governance systems and rule of law institutions at all levels of government, contributing to good governance and stability.

Integrated Results and Resources Framework (IRRF) (2022 – 2025)

IRRF 2.2.3 Number and proportion of people supported who have access to justice.

IRRF 2.2.1: Existence of strengthened institutions, systems, or stakeholders with capacities to support fulfilment of nationally and internationally ratified rule of law and justice obligations.

IRRF 6.2.1: Number of measures to advance women´s leadership and equal participation in decision-making (Gender).

IRRF 6.2.2: Number of partnerships with women-led civil society organizations and other bodies and networks to advance women’s leadership and participation and gender equality (Gender).

IRRF E.1.2: Number of justice and security institutions that leverage digital technologies in ways that improve people’s lives.

IRRF E.1.3: People using digital technologies and services in ways that improve their lives.

UNDP Strategic Plan Signature Solution 2: Governance Output 2.2 (2022 – 2025)

Civic space and access to justice expanded, racism and discrimination addressed, and rule of law, human rights and equity strengthened.

UNDP Country Programme Document – CPD Output 1.2 (2023-2027)

Justice systems are more accessible, efficient, and affordable.

Output 1

Policy, legal and regulatory frameworks strengthened to warrant people-centred, equitable, timely, affordable justice and security delivery to all people with an emphasis on women, marginalized and vulnerable groups, and digital technologies.

Output 2

Capacity of justice and security stakeholders (duty bearers) enhanced to deliver inclusive, timely, and accessible services to all people with an emphasis on women and digital technologies.

Output 3

Capacity of women, and the most vulnerable and marginalized (rights holders) strengthened to access referral pathways to justice and security.

Output 4

Justice and security sector institutional facilities enhanced to deliver inclusive, timely, and accessible justice and security services, through women friendly and gender-responsive infrastructure development support with an emphasis on flood resilience and green energy.

Figure 3: Summary of the Results Chain

## Resources Required to Achieve the Expected Results

The Rule of Law Programme is estimated to require US$ 32,500,362 to achieve its results during the new phase of the Rule of Law Programme period from January 2024 – December 2027. As such donor/financial contributions to the Rule of Law Programme will be channeled through and managed by UNDP as one. In its resource mobilization efforts, the Rule of Law Programme will look into government cost-sharing opportunities whenever available. While the Rule of Law Programme proposes and encourages non-earmarking of financial resources to better enable the Rule of Law Programme to be responsive and flexible in its approach, donors that seek to earmark contributions to specific outputs may do so. The Rule of Law Programme will be managed by a high-caliber team, including national and international staff, consultants, civil engineers, and a quantity survey. The finance and operations team will collaborate with the UNDP Pakistan Country Office (CO) for timely support. Programme personnel will be based in multiple locations, including Peshawar, Islamabad, and Quetta, with remote working options.

(For further details please see Section IV: Project Management and Section VII: Multi-Year Work Plan)

## Partnerships

The strategy emphasizes partnership building and collaborative engagement for the Rule of Law Programme’s successful implementation, sustainability, and scalability. The Rule of Law Programme’s new phase will broaden its partner engagement to enhance partner capacities in evidence-based research, analysis, monitoring, and evaluation. Building on best practices and lessons learned to date, the new phase will apply the following guiding principles for partnerships:

a) Engage, partner, and collaborate with the government to secure institutional buy-in and stakeholder ownership from the onset: The Rule of Law Programme will partner with provincial judiciaries, prosecution services, prisons, reclamation and probation services, bar councils, law schools, forensic services, LEAs (i.e. Police, ETAN-B, and ANF), judicial and LEAs training academies, DRCs, PJCs, LAJA, court-annexed mediation forums, and provincial ADR bodies in the target locations.

b) Engage, partner, and collaborate with new power actors and influencers: To upstream UNDP’s policy agenda and influence by increasing strategic engagement with key stakeholders, including donors, parliamentarians, policymakers, civil servants, provincial government stakeholders, the judiciary, law enforcement, and civil society organizations and networks, think tanks, media, and religious leaders/Ulema. The new phase will broaden its outreach to explore possible partnerships with the private sector, including tech-startups.

c) Engage, partner, and collaborate with UN agencies and civil society: Work with UN agencies and civil society actors and organizations (i.e., UNODC, UN Women, NGOs, INGOs, academia, digital and print media, women, youth, minority groups, etc.) to promote and advocate for people’s equitable access to justice and security, women's empowerment, gender equality, and digitalization. The new phase will broaden its scope to collaborate with digital media and influences for greater outreach and increase the impact of its interventions, particularly awareness-raising and knowledge-building activities amongst rights holders. Similarly, the new phase will extend its outreach to identify possible partnerships with the private sector, including tech startups.

To this end, the UNDP Pakistan Rule of Law Programme will work with a range of partners to implement its  activities as follows:

| List of Partners | Expected Results/Output |
| --- | --- |
| Government - Law and Justice Commission - Ministry of Interprovincial Coordination - Ministry of Law and Justice - Supreme Court of Pakistan - Supreme Court Appellate Court of GB - Federal Judicial Academy - Pakistan Bar Council - Ministry of States and Frontier Regions - Anti-Narcotics Force - Excise Taxation and Anti-Narcotics Department Balochistan International Development Partners - European Union (EU) - United States Bureau of International Narcotics and Law Enforcement Affairs (US-INL) - Embassy of Japan | Output 1: Policy, legal and regulatory frameworks strengthened to warrant people-centered, equitable, timely, affordable justice and security delivery to all people with an emphasis on women, marginalized and vulnerable groups, and digital technologies. |
| Government - All four provincial governments and the Government of Gilgit Baltistan - All provincial/regional Assembly Standing Committees on Law Reforms - Law, Parliamentary Affairs and Human Rights Departments - Home and Tribal Affairs Departments - Anti-Narcotics Force - Excise Taxation and Anti-Narcotics Department Balochistan International Development Partners - European Union (EU) - United States Bureau of International Narcotics and Law Enforcement Affairs (US-INL) - Embassy of Japan Other - UN agencies - Civil society actors and organizations - Private sector including tech startups - Digital and print media | Output 2: Capacity of justice and security stakeholders (duty bearers) enhanced to deliver inclusive, timely, and accessible services to all people with an emphasis on women and digital technologies. |
| Government - All four provincial governments and the Government of Gilgit Baltistan - All provincial/regional Assembly Standing Committees on Law Reforms - Law, Parliamentary Affairs and Human Rights Departments - Home and Tribal Affairs Departments - KP Bar council - Law and Justice Authority Islamabad International Development Partners - European Union (EU) - United States Bureau of International Narcotics and Law Enforcement Affairs (US-INL) - Embassy of Japan Other - UN agencies - Civil society organizations and networks - Digital media and influences - Private sector including tech startups | Output 3: Capacity of women, and the most vulnerable and marginalized (rights holders) strengthened to access referral pathways to justice and security. |
| Government - All five High Courts and Gilgit Baltistan Chief Court - All provincial judicial academies - All provincial and regional Police Departments - All provincial Prosecution and Law Departments - All provincial and regional bar councils - All provincial and regional Local Government Departments - Anti-Narcotics Force - Excise Taxation and Anti-Narcotics Department Balochistan International Development Partners - European Union (EU) - United States Bureau of International Narcotics and Law Enforcement Affairs (US-INL) - Embassy of Japan | Output 4: Justice and security sector institutional facilities enhanced to deliver inclusive, timely, and accessible justice and security services, through women friendly and gender-responsive infrastructure development support with an emphasis on flood resilience and green energy. |

## Risks and Assumptions

The following key assumptions and risks have been identified in the Rule of Law Programme:

Assumptions: The security and political context remain stable and there will be no heightened conflicts and public unrest turning violent, ensuring no delays to project implementation. The Rule of Law Programme’s target areas continue to be accessible without restrictions. Financial resources are received on time, human resources are in place, and key stakeholders are responsive and cooperative. The Rule of Law Programme’s target groups benefit from enhanced expertise and support. UNDP civil work Invitations to Bid (ITBs) receive qualified bids, allowing for a competitive process to select experienced service providers.

Risks: Changes in the social and political situations both at national and local levels are a key anticipated risk. The Rule of Law Programme could be at risk of militant groups targeting civilians and government institutions, attacks targeting rule of law infrastructure development, and restricted access to project locations due to lockdowns and natural disasters. Changes in government priorities and duty bearers may also affect the project's success. The Rule of Law Programme may also face exclusion and discrimination of women beneficiaries, failure to prioritize gender equality and their limited legal awareness. Another possible risk is increased inflation and overspending or underspending funds. The Rule of Law Programme may also negatively impact the environment, cause poor construction work, use poor materials, and create unsafe working conditions for on-site workers.

Mitigation: To mitigate these risks, UNDP will keep up its routine context analysis and regular consultations with the Rule of Law Programme partners at the national and provincial levels. This will be done to review implementation plans and budgets, spot any potential or upcoming challenges, and take corrective action. Similarly, UNDP will also maintain a high level of flexibility to alter the Rule of Law Programme design, scope, and activities where needed to effectively respond to emergent changes in the operational context through regular meetings with key stakeholders, partners, and donors. The application of the Health, Safety, Security, and Environment (HSSE) protocols for civil work projects will be further strengthened including through routine monitoring and course correction. Additionally, the new phase of the Rule of Law Programme will draw on the lessons learnt and best practices from its previous phase (2018–2023), where activities were carried out despite the difficult and highly political and demanding nature of the operating environment.

(For further details on assumptions, risks, impact, and mitigation please see Annex III Risk Log)

## Stakeholder Engagement

To ensure greater outreach, coherence, and inclusivity, the Rule of Law Programme will engage with a range of stakeholders involving both right holders and duty bearers in the target locations at the federal and provincial levels. Key stakeholders of the Rule of Law Programme include the target provincial governments, judiciaries, prosecution services, LEAs (i.e., Police, ANF, and ETAN Departments), Prisons Department, and Reclamation and Probation Departments in the provinces of KP, Balochistan, Sindh, GB and the Islamabad Capital Territory as well as UNODC and UN Women in Pakistan. Primary beneficiaries of the Rule of Law Programme are judges, lawyers, prosecutors, forensic experts, prison officials, court staff, and law students (women and men); members of bar associations, DRCs, PJCs, LAJA, court-annexed mediation forums and provincial ADR bodies (women and men); judicial and LEA training academies; police, ANF, and ETAN-B officers (women and men); people of the project’s target locations with a focus on women and the most marginalized and vulnerable groups; and  civil society in the provinces of KP, Balochistan, Sindh, and GB.

(For further details please see Annex VII Stakeholder Engagement Plan)

## South-South and Triangular Cooperation (SSC/TrC)

The project has already established strong links with the UNDP Regional Bureau for Asia and the Pacific, as well as the UNDP Global Rule of Law Programme at HQ level, thus allowing for information sharing and learning beyond the UNDP Pakistan Country Office. Furthermore, through partnerships between the Peshawar High Court and the Supreme People’s Court of China, the project enabled knowledge and experience exchange on case management and court automation. Building on this foundational work the Rule of Law Programme will continue to explore potential opportunities and entry points to strengthen SSC/TrC going forward.

## Digital Solutions

The Rule of Law Programme recognizes the transformative potential of digital technologies in the rule of law sector in Pakistan. The previous Rule of Law Programme phase strategically leveraged digital solutions by establishing 36 virtual courts and 75 virtual points in KP, including in the MDs, and three virtual courts in GB, as well as providing technical support to the KP and GB judiciaries in strengthening the case flow management system (CFMS). It has digitalized the CFMS from the case filing process to the delivery of judgements, providing timely and greater access to case documents through digital copies. The CFMS has significantly improved the efficiency, transparency, and accountability of court proceedings. The KP virtual courts system was connected to the Prison Department by establishing an additional 21 virtual points in six districts. Furthermore, during the COVID-19 health pandemic lockdown in Pakistan, the virtual courts system allowed business continuity at the Peshawar and GB High Courts, thus delivering uninterrupted justice services to people to the extent possible. As of date, the KP and GB virtual courts have conducted 22,000 and 1,500 case hearings respectively.

Building on this foundational work, the new phase of the Rule of Law Programme aims to strengthen judicial and court proceedings and improve capacity for faster justice services through digital solutions, particularly in KP, Balochistan and Sindh provinces. It includes digital solutions support packages to assist the judiciaries to scale up the virtual courts system, develop standard operating procedures, multi-year strategic plans and regulatory frameworks, and provide standardized training to judges, court staff, and lawyers on digital solutions. It will benefit litigants, witnesses, suspects, judges, prosecutors, and lawyers by accelerating case disposal, reducing litigation costs, providing a safer environment for women and marginalized groups, and allowing flexible time scheduling to hear cases. It will also reduce costs, case backlogs, and delays, ensuring timely court proceedings during stable times and future crises.

To this end, the new phase will also explore opportunities to expand its partners into the private sector, including tech startups, as well as collaborate with UNDP innovation and experimentation labs. Similarly, the Rule of Law Programme’s interventions to promote digital solutions will contribute to achieving UNDPs Strategic Plan Output E.1, which aims to equip people and institutions with enhanced digital capabilities and promote opportunities for their participation in and benefit from inclusive digital societies. The Rule of Law Programme's impact will be measured through the IRRF indicators E.1.2 and E.1.3. (i.e. the number of both public and private institutions that harness digital technologies to enhance the quality of people's lives, and the increasing number of individuals who actively engage with digital technologies and services to improve their own lives) as evidenced by the successful installation of virtual courts, The new phase will empower litigants, witnesses, suspects, judges, prosecutors, and lawyers alike by expediting case disposals, reducing litigation costs, ensuring safer environments, and facilitating flexible scheduling for court proceedings driving the proliferation of digital solutions for the betterment of society, and promoting an inclusive and digitally empowered Pakistan.

## Knowledge

The Rule of Law Programme aims to develop lessons learned briefs on innovative approaches to strengthening justice and security sector governance in Pakistan, focusing on both rights holders and duty bearers with an emphasis on women and the most marginalized groups. Case studies and policy briefs will be developed to share key findings from the Rule of Law Programme assessments, research studies, and surveys. The Rule of Law Programme will also have a communications and visibility plan to guide the Rule of Law Programme’s media and outreach activities (i.e., launches, inauguration events, high level visits to the Rule of Law Programme sites, press releases and tweets using social and digital media, and human stories documenting the experiences of beneficiaries, target groups, and implementing partners).

## Sustainability and Scaling Up

The Rule of Law Programme is designed to bring about sustainability and up scaling through multiple means. The new phase of the Rule of Law Programme is developed based on government endorsed national initiatives, reform agendas, and strategies; provide technical advice and assistance to national and provincial government stakeholders (duty bearers) so they are effective, responsive, and accountable to people's needs (rights holders), and their actions help to improve justice and security service delivery in Pakistan; leverage civic space by supporting civil society and people in the target locations to influence and promote effective responses to people’s justice and security needs; collaborate and engage with a range of diverse partners and stakeholders so they operate in a way that supports the Rule of Law Programme’s development change; undertake pilot initiatives with plans to scale up based on lessons learned and best practices; and integrate digital solutions to enhance people’s access to justice.

The Rule of Law Programme beneficiaries, partners, and stakeholders will learn from each other and increase learning at an institutional level more broadly in the long-term; training and mentoring methodologies will allow learning and impact to be had beyond the direct target groups and will serve as an ongoing resource for future initiatives; advocacy, awareness raising, and lessons learned products will enhance knowledge and may trigger new undertakings by UNDP and key stakeholders, including gathering donor support within and beyond this phase; and initiatives supporting gender mainstreaming and women's empowerment, participatory and inclusive approaches, and flood-resistant infrastructure and green energy are, by extension, replicable more broadly and are not just restricted to the rule of law sector.

The Rule of Law Programme emphasizes continual learning and assessment as part of its commitment to sustainability and scaling up. Throughout the Rule of Law Programme's lifecycle, rigorous assessments will be conducted to measure the impact and effectiveness of its interventions. These evaluations will provide significant insights by identifying gaps in the interventions and areas for improvement. The recommendations resulting from these evaluations will be pivotal in ensuring the Rule of Law Programme's long-term sustainability by guiding strategic modifications and enhancements where needed. Similarly, the findings will also help to inform the Rule of Law Programme’s scalability in terms of new areas of intervention, replication of best practices, and geographic extension among other things.

# IV. Project Management

## Cost Efficiency and Effectiveness

The overall Rule of Law Programme management approach ensures UNDP's organizational value for money criteria (VFM) - economy, efficiency, and cost-effectiveness as well as through its extensive geographic outreach extending to the provinces of KP including Merged Districts, Balochistan, GB, Sindh, and the Islamabad Capital Territory (ICT).

- This new phase of the Rule of Law Programme builds on a vital capacity foundation laid by the previous phase (2019-2023).

- From the new Rule of Law Programme design phase, required commitment and ownership are secured from national partners to achieve the outputs highlighted in the Results Framework/Log Frame.

- Overall Rule of Law Programme budget costs are estimated under each output, and to corresponding activities with itemized costing to ensure economy, efficiency, and cost-effectiveness.

- The Rule of Law Programme implementation to support the justice and rule of law sector in Pakistan requires stringent quality assurance and having in place appropriate technical staff and monitoring systems (i.e., investment in qualified and experienced hybrid project teams consisting of national and international professional staff). This in turn will warrant effective use of resources, time efficiency and quality completion of work.

- Competitive procurement processes will be relied upon to ensure equity and draw in competitive offers. Competitive processes also enable assessment of the range, quality and pricing available in the market.

- Procurement of goods and equipment will be undertaken following a strategic planning exercise to consolidate procurement actions. For example, regarding external travel (flights), UNDP procurement policies and procedures require at least three itemized quotations from UNDP-approved vendors, and to rank selection based on the following VFM criteria: economy, efficiency, and cost-effectiveness. Furthermore, when hiring consultants, the detailed pricelist, and the deliverable methodology is an essential evaluation criterion in the selection process.

- To provide time sensitive responses with the provision of goods and services, the project will also rely on the UNDP Crisis Bureau Express Roster of pre-vetted technical experts/consultants, and service contracts with qualified national companies.

- To enhance efficiency and access to a diverse pool of expertise, the Rule of Law Programme will actively promote the recruitment of United Nations Volunteers (UN Volunteers) who can offer valuable skills and expertise.

- Consolidated operations and administration support teams working across the Rule of Law Programme, Democratic Governance Unit (DGU), and the broader Country Office (CO) will contribute to consistency in processes and save time and resources.

- The Rule of Law Programme will actively seek opportunities for collaboration and synergy with other projects and initiatives within the UNDP Pakistan CO and in the Rule of Law Programme’s target regions. By coordinating efforts, resources, and expertise with complementary projects, it will improve resource usage and avoid duplication of efforts.

## Project Management

The Rule of Law Programme will be implemented by the UNDP Pakistan CO by the Rule of Law Programme team under the overall oversight of the DGU. It will be implemented through the Direct Implementation Modality (DIM). The Rule of Law Programme management team, led by the Programme Manager (PM), will be responsible for the overall implementation of the project including Annual Work Plans, Project Review Board (PRB) recommendations as well drafting periodic progress reports including quarterly, by-annual and annual project progress reports in line with donor commitments and UNDP Programme and Operations Policies and Procedures (POPP). Similarly, the PM is also responsible for regularly monitoring risk and challenges that may impact progress and take remedial action as needed. The PM is also responsible for providing regular project progress updates to the Assistant Resident Representative (ARR), DGU and other key project stakeholders where appropriate. The Programme Analyst, DGU is responsible for the project’s quality assurance, including monitoring progress on project results and overall delivery (e.g., resource utilization under the overall guidance and oversight of ARR, DGU). Furthermore, the project is also composed of a dedicated monitoring and evaluation (M&E) team, and they are responsible for undertaking regular monitoring of all project activities through field and remote data collection and documentation to assess changes, report results, and identify challenges and risks including possible solutions to overcome/mitigate them.

The Rule of Law Programme will be managed and coordinated from three main UNDP Offices in Pakistan, located in Peshawar, Balochistan, and Islamabad. While most of the Rule of Law Programme staff will be based in the UNDP sub-office in Peshawar, the Rule of Law Programme will also have a presence in the Islamabad head office as well as in the UNDP sub-office in Quetta, with backend support roles such as finance, communications and donor reporting based at the head office in Islamabad. The Rule of Law Programme’s overall team will consist of approximately 20 dedicated national and international technical experts, including the Rule of Law Programme subject matter experts, M&E, communications & outreach, and finance & operations experts, and civil engineers composed of field and oversight engineers and a quantity surveyor. The Rule of Law Programme team will be integrated within the UNDP Pakistan Rule of Law Programme, while also operationally supported by the DGU, Finance, Administration, Human Resources, and Procurement units, as well as benefiting from CO shared services such as IT, Communications, and Security.

Where appropriate, UNDP will enter into contractual agreements with qualified third-party service providers (e.g., construction and design companies) and specialist consultants to assist in project implementation. Third-party service providers will be selected in keeping with UNDP’s established policies and procedures, to take advantage of their specialized skills, achieve high-quality and time-efficient results, mitigate risks, and strengthen administrative efficiencies. To this end, the PM is responsible for managing all third-party contracts/agreements in close coordination and with support from the Rule of Law Programme’s operations and finance team as well as the CO operational unit. Through the DIM modality, the Rule of Law Programme will apply its technical and administrative capacities to mobilize necessary resources and technical know-how to the target locations, implementing partners, and beneficiaries to achieve its expected outputs, targets and results in line with UNDP POPP. The DIM modality also allows the Rule of Law Programme to engage with responsible parties/service providers/vendors, as well as with other UN Agencies through written agreements and/or contracts to purchase goods and services for the purpose of project activity implementation. All responsible parties and third-party contractors are subject to the rules and obligations set out in UNDP POPP.

In line with UNDP corporate policies and procedures, Direct Project Costing will be applied to the project for the aforementioned support services provided by the UNDP Pakistan CO. Direct Project Costs (DPC) are organizational costs incurred in the implementation of the Rule of Law Programme activities and/or services that can be directly traced and attributed to those activities and/or services. These costs, therefore, are included in the Rule of Law Programme budget and charged directly to the Rule of Law Programme budget. The objective of DPC is to reflect in the appropriate budget of the Rule of Law Programme the true direct costs of achieving relevant results and objectives of the Rule of Law Programme funded from regular (core) and other (non-core) resources. Therefore, as per UNDP programme and operations policies and procedures, UNDP will incorporate DPC charges in the annual Rule of Law Programme budget based on the standard price list and prior experience. DPC, together with the minimum General Management Support (GMS) (indirect cost), which covers the organization’s costs in support of corporate structures, enables full implementation of costs to be reflected, and fully costed to projects by UNDP for implementation of its project activities and services.

As a DIM Project, the Rule of Law Programme will be audited as determined by the UNDP Office of Audit and Investigations (OAI).

Programme Manager

FTA – P5 (Peshawar)

Communications and Programme Support Analyst - NPSA-8

(Islamabad)

Donor Coordination and Reporting Officer - NPSA-9

(Islamabad)

Senior Rule of Law and Justice Reform Expert - FTA-P4

(Islamabad)

Deputy Programme Manager

NPSA-11

(Peshawar)

International Police Expert

FTA-P3

(Peshawar)

Senior Project Engineer- NPSA-11

(Peshawar)

Vacant

M&E Specialist

NPSA-9

(Peshawar)

Manager Operations and Finance

NPSA-11

(Islamabad)

Project Engineer

NPSA-9

(Peshawar)

Project Engineer

NPSA-9

(Quetta)

Project Engineer

NPSA-9

(Peshawar)

UNV Engineer

(Peshawar)

Project Engineer

NPSA-8

(Islamabad)

UNV Engineer

(Islamabad)

Senior M&E Associate

NPSA-7

(Peshawar)

Gender Expert

NPSA-9

(Peshawar)

Access to Justice Officer

NPSA-8

(Peshawar)

Prosecution Specialist

NPSA-9

(Peshawar)

Project Training Officer

NPSA-9

(Peshawar)

Rule of Law Specialist

NPSA-10

(Peshawar)

Finance Associate

NPSA-6

(Islamabad)

Vacant

Operations Clerk

NPSA-4

(Peshawar)

Vacant

Project Procurement Officer

NPSA-8

(Peshawar)

Senior Operation Associate

NPSA-7

(Islamabad)

Project Finance Analyst

NPSA-9

(Peshawar)

Figure 4: Rule of Law Programme Organogram

# V. Results Framework

Intended Outcome as stated in the UNSDCF/Country [or Regional] Programme Results and Resource Framework: PRIMARY OUTCOME: UNSDCF OUTCOME INVOLVING UNDP No. 1. By 2027, the people of Pakistan, especially women, children, and the most vulnerable and marginalized, have increased access to fundamental rights, gender equality and fundamental freedoms through inclusive, accountable, effective, and evidence-driven governance systems and rule-of-law institutions at all levels of government, contributing to good governance and stability. SECONDARY OUTCOME: UNSDCF OUTCOME INVOLVING UNDP No. 4. Gender equality and women’s empowerment: By 2027, more women and girls at greatest risk of being left behind are able to benefit from and contribute to an environment in which they are empowered to exercise their fundamental rights, agency and decision-making power over all aspects, towards lives free from all forms of discrimination, violence and harmful practices.

Primary Outcome indicators as stated in the Country Programme [or Regional] Results and Resources Framework, including baseline and targets: Outcome Indicator 5.1. Government effectiveness, rule of law, political, stability, and accountability. Baseline (2020): Government effectiveness: -0.5; Political stability: -1.85; Rule of law: -0.7; Voice and accountability: -0.88. Target (2028): Government effectiveness: -0.3; Political stability: -1.00; Rule of law: -0.5; Voice and accountability: -0.5. Secondary Outcome indicators as stated in the Country Programme [or Regional] Results and Resources Framework, including baseline and targets: Strategic Plan/SDG 5.1.1. Percentage of achievement of legal frameworks in place to promote, enforce and monitor gender equality and nondiscrimination on the basis of sex in the areas of: (a) Public life (b) Violence against women (c) Employment and economic benefits (d) Marriage and family (UNSDCF indicator 2.1) Baseline (2018): (a) 50% (b) 75% (c) 10% (d) 54.6% Target (2027): (a): 60% (b): 85% (c): 20% (d): 65%

Applicable Output(s) from the UNDP Strategic Plan: Output 2.2: Civic space and access to justice expanded, racism and discrimination addressed, and rule of law, human rights and equity strengthened. Output 6.2: Women’s leadership and participation advanced through implementing affirmative measures, strengthening institutions and civil society, and addressing structural barriers, in order to advance gender equality, including in crisis contexts. Output E.1: People and institutions equipped with strengthened digital capabilities and opportunities to contribute to and benefit from inclusive digital societies. Signature Solutions: 2- Governance 3- Resilience and 6- Gender Equality Enabler: Digitization

Project Title: Strengthening Justice and Security Sector Governance in Pakistan (Rule of Law Programme) Quantum Project Number: 01001551

| EXPECTED OUTPUTS | OUTPUT INDICATORS | DATA SOURCE | BASELINE |  | TARGETS (by frequency of data collection) |  |  |  |  | ## DATA COLLECTION METHODS & RISKS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Value | Year | Year 1 | Year 2 | Year 3 | Year 4 | ## FINAL |  |
| Output 1: Policy, legal and regulatory frameworks strengthened to warrant people-centered, equitable, timely, affordable justice and security delivery to all people with an emphasis on women, marginalized and vulnerable groups, and digital technologies. (Gen-2) | 1.1 # of gender-sensitive laws, rules, strategies, policies, manuals, and standard operating procedures drafted/amended/implemented. | Working group meeting minutes; drafts and final versions of policy/legal documents; project progress reports; project progress review meeting minutes; Government of Pakistan notifications. | 20 5 Rules [KP bar council rules; service rules under the newly passed KP Forensic Science Agency (FSA) Act 2020; operation rules under the KP FSA Act 2020; Dispute Resolution Council (DRC) rules – KP; court-annexed mediation rules under the ADR Act. 3 SOPs [KP virtual courts system; KP prosecution training academy; KP Police gender desks under the gender-responsive policing policy] 2 Strategies [KP prosecution training academy; ANF gender strategy (2022); ANF advocacy plan (2021)] 1 Legislative Act [Prison Act, KP] 1 Bill [Prosecution Academy Bill] 7 Strategic Plans (Policing plan for Bajaur, Khyber, Kurram, Mohmand, Orakzai, North and South Waziristan MDs) 1 Policy (Prison training academy Haripur) | 2023 | 4 1 Policing Framework and Strategy 1 Probation Act -Balochistan 1 Rules Document on Balochistan Probation Act 1 Rules Document on Balochistan ADR Act | 4 1 Regulatory Framework on Virtual Courts – Balochistan 1 Regulatory Framework on Virtual Courts – Sindh 2 Multi-Year Gender Strategies for Rule of Law institutions in project’s target locations | 6 3 KP Sectoral Strategies 1 KP Rule of Law Road Map Implementation Plan 1 Multi-Year Justice Sector Strategic Plan -Balochistan 1 Multi-Year Justice Sector Strategic Plan -Sindh | 4 3 Multi-Year Gender Strategies for Rule of Law institutions in project’s target locations 1 Sectoral Strategy | 18 2 Rules 15 Strategies 1 Rule of Law Roadmap implementation plan | Working group meeting minutes; end-user feedback; Rule of Law Programme progress reports; Government of Pakistan notifications. Risks: Refer to Annex III – Risk Log. |
|  | 1.2 Level of institutional capacity and readiness for policy/strategy implementation and enforcement From a scale of 1- low level (limited or inadequate capacity; 2 -moderate level (some capacity and readiness but improvements are needed) ;3-Substantial level (significant capacity and readiness) ;4-high level (strong capacity and readiness); 5-excellent level (exceptional capacity and readiness) | Evaluation studies, document analysis, and external assessments | Scale -1: Low level - limited or inadequate capacity and readiness to effectively implement and enforce policies/ strategies. | 2023 | Scale -2: Moderate level -some capacity and readiness, but improvements are needed for more effective policy/strategy implementation and enforcement] | Scale-3 Substantial level -: significant capacity and readiness enabling relatively effective policy/strategy implementation and enforcement | Scale-4 High: Strong capacity and readiness, leading to proficient policy implementation and enforcement | Scale-5 Excellent level: Exceptional capacity and readiness | Scale-5 Excellent level: Exceptional capacity and readiness | Evaluation studies, document analysis, and external assessments Risks: Refer to Annex III – Risk Log. |
|  | 1.3 (IRRF 6.2.1): Number of measures to advance women´s leadership and equal participation in decision-making. | Working group meeting minutes; drafts and final versions of policy/legal documents; project progress reports; project progress review meeting minutes; Government of Pakistan notifications. | 2 [Gender Strategy, Gender-responsive policing policy] | 2023 |  | 2 Multi-Year Gender Strategies for Rule of Law institutions in project’s target locations |  | 3 Multi-Year Gender Strategies for Rule of Law institutions in project’s target locations | 5 Multi-Year Gender Strategies for Rule of Law institutions in project’s target locations | Working group meeting minutes; end-user feedback; Rule of Law Programme progress reports; Government of Pakistan notifications. |
| Output 2: Capacity of justice and security stakeholders (duty bearers) enhanced to deliver inclusive, timely, and accessible services to all people with an emphasis on women and digital technologies. (Gen-2) | 2.1 # of justice and security personnel trained/up skilled. (Disaggregated by gender and institution) a) Judges - # men; # women b) Court Staff - # men; # women c) Lawyers - # men; # women d) Prosecutors - # men; # women. e) R&P Staff - # men; # women. f) Prison Staff - # men; # women. g) Police - # men; # women. h) ANF Officers - # men; # women. i) ETAN staff - # men; # women | Training reports (including training agenda, photos, participants’ attendance records, pre- and post-training assessment results); project progress reports; project progress review meetings. | a) Judges: 72 (men: 45; women: 27) b) Court Staff: 43 (men: 38; women: 5) c) Lawyers: 24 (men: 0; women: 24) d) Prosecutors: 10 (men: 10; women: 0) e) R&P Staff: 15 (men: 10; women: 5) d) Prison Staff: 0 (men: 0; women: 0) e) Police: 1,230 (men: 1,135; women: 95) f) ANF Officers: 0 (men: 0; women: 0) i) ETAN Staff: 0 (men: 0; women: 0) | 2023 | a) Judges 200 b) Court Staff 200 c) Prosecutors 100 d) R&P Staff 50 e) Prison Staff 50 f) Police 500 g) ANF Officers 250 i) ETAN Staff 300 *May include minimum 10% or more women to the extent possible. | a) Judges 200 b) Court Staff 200 c) Prosecutors 100 d) R&P Staff 50 e) Prison Staff 50 f) Police 500 g) ANF Officers 0 i) ETAN Staff 0 *May include minimum 10% or more women to the extent possible. | a) Judges 200 b) Court Staff 200 c) Prosecutors 100 d) R&P Staff 50 e) Prison Staff 50 f) Police 500 g) ANF Officers 0 i) ETAN Staff 0 *May include minimum 10% or more women to the extent possible. | a) Judges 200 b) Court Staff 200 c) Prosecutors 100 d) R&P Staff 50 e) Prison Staff 50 f) Police 500 g) ANF Officers 0 i) ETAN Staff 0 *May include minimum 10% or more women to the extent possible. | a) Judges 800 b) Court Staff 800 c) Prosecutors 400 d) R&P Staff 100 e) Prison Staff 200 f) Police 2000 g) ANF Staff 250 i) ETAN Staff 300 *May include minimum 10% or more women to the extent possible. | Rule of Law Programme progress reports; Rule of Law Programme review meetings; training reports; participants feedback; best practice case studies; training workshop and certificate ceremony photos. Risks: Refer to Annex III – Risk Log. |
|  | 2.2 # of justice and security sector institutions supported in creating an enabling environment for the staff to perform their duties and tasks effectively and efficiently. (Disaggregated by institutions and type/nature of support) a) Digitalization support to: Judiciary; Prosecution; Prisons; Police; ANF; ETAN; KP Bar Association b) Equipment Support to: Judiciary; Prosecution; Prisons; Police; ANF; ETAN; KP Bar Association c) Training manual development support to: Judiciary; Prosecution; Prisons; Police; ANF; ETAN; Reclamation and Probationary Department (R&P) | Workshop meeting minutes; project progress reports; project progress review meetings; beneficiary/ end-user feedback. | a) Digitalization support to: Judiciary: 6; Prosecution: 3; Prisons: 1; Police: 4; ANF: 1; ETAN: 0; KP Bar Association: 1 b) Equipment Support to: Judiciary: 4; Prosecution: 1; Prisons: 0; Police: 2; ANF: 0; ETAN: 0; KP Bar Association: 0 c) Training manual development support to: Judiciary: 1; Prosecution: 2; Prisons: 1; Police: 0; ANF: 0; ETAN: 0; R&P: 1 | 2023 | a) Digitalization support to: Prisons: 1; R&P: 1 b) Equipment Support to: Judiciary: 2: Prison: 1; Police: 2 c) Training manual development support to: Judiciary: 1: Prisons: 1; Police: 1: ANF: 1; ETAN: 1; R&P: 1 | a) Digitalization support to: Judiciary: 1; Police: 1 b) Equipment Support to: Judiciary: 2; Prison: 1; Police: 2 c) Training manual development support to: Judiciary: 1: Prisons: 1; Police: 1; R&P: 1 | a) Digitalization support to: Judiciary: 1; Police: 1; ANF: 1 b) Equipment Support to: Judiciary: 2; Prison: 1; Police: 2 c) Training manual development support to: Judiciary: 1: Prisons: 1; Police: 1; R&P: 1 | a) Digitalization support to: Judiciary: 1; Police: 1 b) Equipment Support to: Judiciary: 2; Prison: 1; Police: 2 c) Training manual development support to: Judiciary: 1: Prisons: 1; Police: 1; R&P: 1 | a) Digitalization support to: Judiciary: 3; Prisons: 1: Police: 3; ANF: 1; R&P: 1 b) Equipment Support to: Judiciary: 6; Prisons: 4; Police: 8 c) Training manual development support to: Judiciary: 4; Prisons: 4; Police: 4; ANF: 1; ETAN: 1; R&P: 4 | Rule of Law Programme progress reports; Rule of Law Programme progress review meetings; participants feedback; best practice case studies; workshop minutes; handing over/inauguration ceremony photos and related communications and outreach documents. Risks: Refer to Annex III – Risk Log. |
| Output 3: Capacity of women, and the most vulnerable and marginalized (rights holders) strengthened to access referral pathways to justice and security. (Gen-2) | 3.1 (IIRF 2.2.3) # of people supported to access justice through legal awareness sessions, legal aid, and Dispute Resolution Councils (DRCs). (Disaggregated by gender) a) Legal Awareness Sessions in Balochistan and KP: # Women; # Men b) Legal Aid Desks in Balochistan and KP: # Women; # Men c) DRCs in Balochistan and KP: # Women; # Men | Workshop meeting minutes; project progress reports; project progress review meetings; beneficiary/ end-user feedback. | a) Legal Awareness Sessions in Balochistan and KP: 18,099 (Women 4,013; Men 14,086) b) Legal Aid Desks in Balochistan and KP: 197 (Women 160; Men 37) c) DRCs in Balochistan and KP: 13,064 (Women 3,900; Men 9,164) | 2023 | a) Legal Awareness Sessions in Balochistan and KP: 10,000 (Women 4,000; Men 6,000) b) Legal Aid Desks in Balochistan and KP: 550 (Women 300; Men 250) c) DRCs in Balochistan and KP: 1,500 (Women 500; Men 1000) | a) Legal Awareness Sessions in Balochistan and KP: 10,000 (Women 4,000; Men 6,000) b) Legal Aid Desks in Balochistan and KP: 550 (Women 300; Men 250) c) DRCs in Balochistan and KP: 1,500 (Women 500; Men 1000) | a) Legal Awareness Sessions in Balochistan and KP: 10,000 (Women 4,000; Men 6,000) b) Legal Aid Desks in Balochistan and KP: 550 (Women 300; Men 250) c) DRCs in Balochistan and KP: 1,500 (Women 500; Men 1000) | a) Legal Awareness Sessions in Balochistan and KP: 10,000 (Women 4,000; Men 6,000) b) Legal Aid Desks in Balochistan and KP: 550 (Women 300; Men 250) c) DRCs in Balochistan and KP: 1,500 (Women 500; Men 1000) | a) Legal Awareness Sessions in Balochistan and KP: 40,000 (Women 20,000; Men 30,000) b) Legal Aid Desks in Balochistan and KP: 2,200 (Women 1,200; Men 1,000) c) DRCs In Balochistan and KP: 6,000 (Women 2,000; Men 4,000) | Rule of Law Programme progress reports; Rule of Law Programme progress review meetings; beneficiary/ end-user feedback; field monitoring reports; best practice/lessons learned case studies. Risks: Refer to Annex III – Risk Log. |
|  | 3.2 # of women law students and graduates supported through coaching sessions, scholarships, and stipends to advance in their legal careers a) # Scholarships (Balochistan, KP, Sindh, and GB) b) # Stipends (Balochistan, KP, Sindh, and GB) c) # Coaching sessions (Balochistan, KP, Sindh, and GB) | Coaching workshop /meeting minutes; scholarship and stipend recipient records; project progress reports; project progress review meetings; beneficiary/ end-user feedback. | a) Scholarship: 81 (Balochistan:0; KP: 81 Sindh: 0; GB: 0) b) Stipends: 24 (Balochistan: 0; KP: 24; Sindh: 0; GB: 0) c) # Coaching sessions: 0 (Balochistan: 0; KP: 0; Sindh: 0; GB: 0) | 2023 | a) Scholarships: 60 (Balochistan: 15; KP:15 Sindh: 15; GB: 15) b) Stipends: 40 (Balochistan: 10; KP: 10; Sindh: 10; GB:10) c) Coaching sessions: 120 (Balochistan: 30; KP: 30; Sindh: 30; GB: 30) | a) Scholarships: 60 (Balochistan: 15; KP: 15 Sindh: 15; GB: 15) b) Stipends: 40 (Balochistan: 10; KP: 10; Sindh: 10; GB: 10) c) Coaching sessions: 120 (Balochistan: 30; KP: 30; Sindh: 30; GB: 30) | a) Scholarships: 60 (Balochistan: 15; KP: 15 Sindh: 15; GB: 15) b) Stipends: 40 (Balochistan: 10; KP: 10; Sindh: 10; GB:10) c) Coaching sessions: 120 (Balochistan: 30; KP:30; Sindh: 30; GB: 30) | a) Scholarships: 60 (Balochistan: 15; KP: 15 Sindh: 15; GB: 15) b) Stipends: 40 (Balochistan: 10; KP: 10; Sindh: 10; GB:10) c) Coaching sessions: 120 (Balochistan: 30; KP:30; Sindh: 30; GB: 30) | a) Scholarships: 240 (Balochistan: 60; KP: 60 Sindh: 60; GB: 60) b) Stipends: 160 (Balochistan: 40; KP: 40; Sindh: 40; GB: 40) c) Coaching sessions: 500 (Balochistan: 120; KP: 120; Sindh: 120; GB: 120) | Rule of Law Programme progress reports; Rule of Law Programme progress review meetings; beneficiary/ end-user feedback; field monitoring reports; best practice and success story case studies. Risks: Refer to Annex III – Risk Log. |
|  | 3.3 % Career advancement rate of scholarship and stipend recipients Scale: The advancement rate is presented as a percentage (%) to measure the extent of career advancement/ progress for women law students and graduate beneficiaries. | Post- scholarship and stipend distribution/award monitoring survey. | 50% Career advancement rate of scholarship and stipend recipients Source: Post- scholarship and stipend distribution monitoring survey (2022, UNDP) | 2022 | 10% Increase in the advancement rate | 15% Increase in the advancement rate | 20% Increase in the advancement rate | 25% Increase in the advancement rate | 25% Increase in the advancement rate | Post distribution/award monitoring survey by UNDP Risks: Refer to Annex III – Risk Log. |
|  | 3.4 (IRRF 6.2.2): Number of partnerships with women-led civil society organizations and other bodies and networks to advance women’s leadership and participation and gender equality. | Coaching workshop /meeting minutes; scholarship and stipend recipient records; project progress reports; project progress review meetings; beneficiary/ end-user feedback | 5 [KP Bar Council, Balochistan Bar Council, SRSP, Peace and Justice Network, WESS Balochistan] | 2023 | 5 [KP Bar Council, Balochistan Bar Council, SRSP, Peace and Justice Network, WESS Balochistan] | 5 [KP Bar Council, Balochistan Bar Council, SRSP, Peace and Justice Network, WESS Balochistan] | 5 [KP Bar Council, Balochistan Bar Council, SRSP, Peace and Justice Network, WESS Balochistan] | 5 [KP Bar Council, Balochistan Bar Council, SRSP, Peace and Justice Network, WESS Balochistan] | 20 [KP Bar Council, Balochistan Bar Council, SRSP, Peace and Justice Network, WESS Balochistan] | Rule of Law Programme progress reports; Rule of Law Programme progress review meetings; beneficiary/ end-user feedback; field monitoring reports; best practice and success story case studies. Risks: Refer to Annex III – Risk Log. |
| Output 4: Justice and security sector institutional facilities enhanced to deliver inclusive, timely, and accessible justice and security services, through women friendly and gender- responsive infrastructure development support with an emphasis on flood resilience and green energy. (Gen-2) | 4.1 # of justice and security sector facilities constructed, and infrastructure improved/restored (Disaggregated by institution and location) a) # Judicial infrastructure facilities. b) # Prosecution infrastructure facilities. c) # Police infrastructure facilities. d) # ETAN infrastructure facilities. e) # ANF infrastructure facilities. f) # Other infrastructure facilities. | Site inspections; Technical Working Group meetings; third party monitoring (where appropriate); site inspections; feasibility study reports; remote monitoring of daily progress through Kobo Collect; end- user and beneficiary feedback. | a) Judicial infrastructure facilities: 112 (1 Provincial Justice Committee (PJC) Secretariate Peshawar High Court – KP; 36 Virtual Courts - KP, 75 Virtual Points – KP) b) Prosecution infrastructure facilities: 1 Prosecution Academy (KP) c) Prisons infrastructure and facilities: 2 (2 Prison Health Facilities – KP) d) Police infrastructure facilities: 11 (KP -1 Joint Police Training Center; MD/KP -2 Model Police Stations; 1 Police Training College -KP, 1 Police Directorate of Public Relations -KP; 4 Gender Police Desks – KP; 1 Police Training Center solarization – KP; 1 Police School of Investigation solarization – KP) e) # ETAN infrastructure facilities: 0 f) # ANF infrastructure facilities: 1 Women Hostel (Islamabad) g) # Other infrastructure facilities: 5 (3 Agriculture Training Centers (MD/KP), 1 Rule of Law Delivery Unit – GB; 1 Rule of Law Delivery Unit – KP) | 2023 | a) Judicial infrastructure facilities: 47 (15 Litigant waiting areas (KP), 12 Court Houses and Information Centers – Balochistan, KP, GB; 20 Virtual Courts – KP, Balochistan, GB, Sindh) b) Prosecution infrastructure facilities: 1 (KP) c) Prisons infrastructure and facilities: 3 (Prison Health Facilities – KP) d) Police infrastructure facilities: 2 Gender and Persons with Disabilities (PWD) sensitive Infrastructure (MD/KP), 1 refurbishment) f) ANF infrastructure facilities: 2 (1 Women Hostel -Islamabad; 1 Academic Block -Islamabad) g) Other infrastructure facilities: 10 (1 Forensic Science Lab – KP; 2 Vocational Centers for Women (MD/ KP), 2 ADR Centers – KP ; 5 Bar Rooms KP) | a) Judicial infrastructure facilities: 47 (15 Litigant waiting areas (KP), 12 Court Houses and Information Centers – Balochistan, KP, GB; 20 Virtual Courts – KP, Balochistan, GB, Sindh) b) Prosecution infrastructure facilities: 1 (MD/KP) d) Police infrastructure facilities: 2 Gender and Persons with Disabilities (PWD) sensitive Infrastructure (MD/KP), 1 facility refurbished (KP) e) ETAN infrastructure Facilities: 1 (1 Training Center – Balochistan) g) Other infrastructure facilities: 8 (1 Lawyers Training Academy – KP), (2 ADR Centers – KP; 5 Bar Rooms – KP) | a) Judicial infrastructure facilities: 47 (15 Litigant waiting areas (KP), 12 Court Houses and Information Centers Balochistan, KP, GB; 20 Virtual Courts – KP, Balochistan, GB, Sindh) b) Prosecution infrastructure facilities: 1 (GB) d) Police infrastructure facilities: 2 (1 Gender and Persons with Disabilities (PWD) sensitive Infrastructure (MD/KP), 1 facility refurbished in KP) g) Other infrastructure facilities: 7 (2 ADR Centers – KP; 5 Bar Rooms - KP) | a) Judicial infrastructure facilities: 47 (15 Litigant waiting areas (KP), 12 Court Houses and Information Centers Balochistan, KP, GB; 20 Virtual Courts – KP, Balochistan, GB, Sindh) b) Prosecution infrastructure facilities: 1 (Balochistan) d) Police infrastructure facilities: 2 (1 Gender and Persons with Disabilities (PWD) sensitive Infrastructure (MD/KP), 1 police facility refurbished in KP) g) Other infrastructure facilities: 7 (2 ADR Centers – KP; 5 Bar Rooms - KP) | a) Judicial infrastructure facilities: 188 (60 Litigant waiting areas (KP), 48 Court Houses and Information Centers Balochistan, KP, GB; 80 Virtual Courts – KP, Balochistan, GB, Sindh) b) Prosecution infrastructure facilities: 4 (KP, MD/KP, GB, Balochistan) c) Prisons infrastructure and facilities: 3 (Prison Health Facilities – KP) d) Police infrastructure facilities: 8 (4 Gender and Persons with Disabilities (PWD) sensitive Infrastructure (MD/KP), 4 police facility refurbished in KP) e) ETAN infrastructure facilities: 1 (Balochistan) e) ANF infrastructure facilities: 2 (Islamabad) g) Other infrastructure facilities: 32 (1 Forensic Science Lab – KP; 2 Vocational Centers for Women (MD/ KP), 8 ADR Centers – KP ; 20 Bar Rooms KP, 1 lawyer training academy KP) | Line plans; final drawings; inspection reports; reports from test results; punch lists; substantial completion certificates; final completion certificates; Rule of Law Programme progress reports; Rule of Law Programme progress review meetings. Risks: Refer to Annex III – Risk Log. |
|  | 4.2 (IRRF E.1.2) Number of justice and security institutions that leverage digital technologies in ways that improves people’s lives at: •Regional level •National level • Sub-national level | Government of KP official data and open-source reports/ publications, UNDP M&E reports. | 134 [35 Virtual courts and 96 virtual points - KP 03 Virtual courts and 0 virtual points – GB 0 Virtual courts and 0 virtual points - Balochistan 0 Virtual courts and 0 virtual points – Sindh] | 2022 | 2 Virtual courts and 1 virtual point – Balochistan 2 Virtual courts and 1 virtual point – Sindh 2 Virtual courts and 0 virtual point – KP 1 Virtual court and 1 virtual point – GB | 2 Virtual courts and 1 virtual point - Balochistan 2 Virtual courts and 1 virtual point – Sindh 2 Virtual courts and 0 virtual point – KP 2 Virtual court and 2 virtual points – GB | 3 Virtual courts and 2 virtual points – Balochistan 3 Virtual courts and 2 virtual points – Sindh 2 Virtual court and 2 virtual points – GB | 2 Virtual court and 2 virtual points – GB | 70 [55 Virtual courts and 15 virtual points in KP, Balochistan, Sindh, and GB] | Government of KP official data and open-source reports/ publications, Risks: Refer to Annex III – Risk Log. |
|  | 4.3 (IRRF E.1.3) # People using digital technologies and services in ways that improves their lives. | Provincial High Courts Reports in KP, Balochistan, Sindh, and GB | 23,500 cases heard through the virtual courts system in KP and GB | 2022 | 22,000 cases in KP, Balochistan, Sindh and GB | 27,000 cases in KP, Balochistan, Sindh and GB | 28,000 cases in KP, Balochistan, Sindh and GB | 30,000 cases in KP, Balochistan, Sindh and GB | 1,25,000 cases in KP, Balochistan, Sindh and GB | Provincial High Courts administrative data in KP, Balochistan, Sindh and GB Risks: Refer to Annex III – Risk Log. |
|  | 4.4 (IRRF 2.2.1): Existence of strengthened institutions, systems, or stakeholders with capacities to support fulfilment of nationally and internationally ratified rule of law and justice obligations. Rating scale: 0 = Not in place, 1 = Capacity low, 2 = Capacity neither low nor high, 3 = Capacity high, 4 = Capacity very high | Programme administrative data, programme evaluations | 1 = Capacity low | 2022 | 2= Capacity neither low nor high | 2= Capacity neither low nor high | 3 = Capacity high | 3 = Capacity high | 3 = Capacity high | Rule of Law Programme progress reports; Rule of Law Programme progress review meetings; participants feedback; best practice case studies Risks: Refer to Annex III – Risk Log. |

# VI. Monitoring and Evaluation

In accordance with UNDP’s programming policies and procedures, the project will be monitored through the following monitoring and evaluation plans:

## Monitoring Plan

| Monitoring Activity | Purpose | Frequency | Expected Action | Partners (if joint) | Cost (if any) |
| --- | --- | --- | --- | --- | --- |
| Track results progress | Progress data against the results indicators in the RRF will be collected and analyzed to assess the progress of the project in achieving the agreed outputs. | Quarterly, or in the frequency required for each indicator. | Slower than expected progress will be addressed by the project management. | UNDP |  |
| Monitor and Manage Risk | Identify specific risks that may threaten achievement of intended results. Identify and monitor risk management actions using a risk log. This includes monitoring measures and plans that may have been required as per UNDP’s Social and Environmental Standards. Audits will be conducted in accordance with UNDP’s audit policy to manage financial risk. | Quarterly | Risks are identified by project management and actions are taken to manage risk. The risk log is actively maintained to keep track of identified risks and actions taken. | UNDP |  |
| Learn | Knowledge, good practices and lessons will be captured regularly, as well as actively sourced from other projects and partners and integrated back into the project. | At least annually | Relevant lessons are captured by the project team and used to inform management decisions. | UNDP | $25000 Annually |
| Annual Project Quality Assurance | The quality of the project will be assessed against UNDP’s quality standards to identify project strengths and weaknesses and to inform management decision making to improve the project. | Biannually | Areas of strength and weakness will be reviewed by project management and used to inform decisions to improve project performance. | UNDP |  |
| Review and Make Course Corrections | Internal review of data and evidence from all monitoring actions to inform decision making. | At least annually | Performance data, risks, lessons and quality will be discussed by the project board and used to make course corrections. | UNDP |  |
| Project Report | A progress report will be presented to the project Board and key stakeholders, consisting of progress data showing the results achieved against pre-defined annual targets at the output level, the annual project quality rating summary, an updated risk long with mitigation measures, and any evaluation or review reports prepared over the period. | Annually, and at the end of the project (final report) |  | UNDP |  |
| Project Review (Project Board) | The project’s governance mechanism (i.e., project board) will hold regular project reviews to assess the performance of the project and review the Multi-Year Work Plan to Ensure realistic budgeting over the life of the project. In the project’s final year, the project Board shall hold an end-of project review to capture lessons learned and discuss opportunities for scaling up and to socialize project results and lessons learned with relevant audiences. | At least annually | Any quality concerns or slower than expected progress should be discussed by the project board and management actions agreed to address the issues identified. | UNDP | $10000 Annually |

## Evaluation Plan

| Evaluation Title | Partners (if joint) | Related Strategic Plan Output | UNSDCF/CPD Outcome | Planned Completion Date | Key Evaluation Stakeholders | Cost and Source of Funding |
| --- | --- | --- | --- | --- | --- | --- |
| Mid-Term Evaluation | UNDP | Output 2.2: Civic space and access to justice expanded, racism and discrimination addressed, and rule of law, human rights and equity strengthened. | By 2027, the people in Pakistan, especially women, children, the most vulnerable and marginalized, have increased access to fundamental rights, gender equality and fundamental freedom through inclusive, accountable, effective and evidence-driven governance systems and rule-of-law institutions at all levels of government, contributing to good governance and stability | September 2025 | Project’s target provincial government and federal justice and security institutions/ agencies. | Cost: 60,000 Source: Multiple donors |
| End-of-term Evaluation | UNDP | Output 2.2: Civic space and access to justice expanded, racism and discrimination addressed, and rule of law, human rights and equity strengthened. | By 2027, the people in Pakistan, especially women, children, the most vulnerable and marginalized, have increased access to fundamental rights, gender equality and fundamental freedom through inclusive, accountable, effective, and evidence-driven governance systems and rule-of-law institutions at all levels of government, contributing to good governance and stability | June 2027 | Project’s target provincial government and federal justice and security institutions/ agencies. | Cost: 60,000 Source: Multiple donors |

# VII. Multi-Year Work Plan

| EXPECTED OUTPUTS | PLANNED ACTIVITIES | Planned Budget by Year |  |  |  | RESPONSIBLE PARTY | PLANNED BUDGET |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Y1 | Y2 | Y3 | Y4 |  | Funding Source | Budget Description | Amount |
| Output 1: Policy, legal and regulatory frameworks strengthened to ensure, equitable, timely, affordable justice and security delivery to all people with an emphasis on women, marginalized and vulnerable groups, and digital technologies. (Gen-2) | 1.1 Provide technical advice and assistance in drafting the new Prisons Act and Prison Rules, new Probation Act for Balochistan, rules under the Balochistan Probation Act and rules under the Balochistan ADR Act. | 30000 | 10000 | 10000 | 10000 | UNDP | TBC | Technical Assistance, Consultations | 30,000 |
|  |  |  |  |  |  |  | EU |  | 30,000 |
|  | 1.2 Technical support to develop regulatory frameworks for virtual courts in Balochistan and Sindh. | 15000 | 10000 | 10000 | 5000 | UNDP | TBC | Technical Assistance | 40,000 |
|  | 1.3 Technical support to revise and update the KP Rule of Law Road Map and notification of the departmental committees to oversee the implementation of relevant sections of the Roadmap in KP and the MDs. | 35000 | 70000 | - | - | UNDP | EU | Technical Assistance, Workshop | 105,000 |
|  | 1.4 Provide technical assistance in developing a justice sector 5-year strategic plan for Sindh and Balochistan judiciaries. | 20000 | 20000 | - | - | UNDP | TBC | Technical Assistance | 40,000 |
|  | 1.5 Conduct gender assessments and develop 5-year gender strategies for Rule of Law institutions in the project’s target locations. |  | 150000 | 150000 | 100000 | UNDP | TBC | Technical Assistance | 400,000 |
|  | 1.6 Support the development of sectoral strategies and implementation plans for KP Rule of Law institutions. | 18000 | - | - | - | UNDP | EU | Technical Assistance | 18,000 |
|  | 1.7 Technical support to the judiciary in development of rules/SOPs/laws to implement the GB Rule of Law Roadmap. | 35000 | 65000 | 45000 | 105000 | UNDP | TBC | Technical Assistance | 250,000 |
|  | MONITORING | 30000 | 30000 | 30000 | 30000 | UNDP | TBC |  | 120,000 |
|  | Sub-Total for Output 1 | 183000 | 355,000 | 245000 | 250000 |  |  |  | 1,033,000 |
| Output 2: Capacity of justice and security stakeholders (duty bearers) enhanced to deliver inclusive, timely, and accessible services to all people with an emphasis on women and digital technologies (Gen-2) | 2.1 Trainings for police officers (women and men) on public dealings, departmental rules and regulations, gender sensitization and mainstreaming. | 30,000 | 30,000 | 30,000 | 30,000 | UNDP | TBC | Trainings | 120,000 |
|  | 2.2 Trainings for senior police officers (women and men) on gender sensitization and gender mainstreaming. | 30,000 | 30,000 | 30,000 | 30,000 | UNDP | TBC | Trainings | 90,000 |
|  |  |  |  |  |  |  | EU |  | 30,000 |
|  | 2.3 Train Khasadars and Levies integrated into KP Police on investigations, riot management, and other co- policing functions. | 100000 | 100000 | - | - | UNDP | EU | Trainings | 200,000 |
|  | 2.4 Upskill women lawyers on legal ethics, client interview techniques, court presentation, women protection laws, and legal drafting. |  | 150000 | 150000 | 100000 | UNDP | TBC | Trainings | 400,000 |
|  | 2.5 Provide technical support for police service delivery, including orientation sessions on public outreach and digital technologies. | 55000 | 90000 | - | - | UNDP | EU | Technical Assistance, Workshops | 145,000 |
|  | 2.6 Support the KP Home Department to operationalize the Delivery Unit. | 25000 | 31000 | 17000 | 17000 | UNDP | TBC | Technical Assistance | 34,000 |
|  |  |  |  |  |  |  | EU |  | 56,000 |
|  | 2.7 Develop training manuals for Excise Taxation and Anti-Narcotics Balochistan (ETAN-B) in specialized areas and conduct training for force staff on field operations, intelligence gathering, legal framework, trend analysis, and research methodologies. | 351500 | - | - | - | UNDP | INL | Technical Assistance, Training, Workshops | 351,500 |
|  | 2.8 Provide financial support for women's representation in the justice sector, including education and mentoring programs. | - | 75000 | 75000 | 50000 | UNDP | TBC | Technical Assistance | 200,000 |
|  | 2.9 Develop training manuals, conduct TOTs and impart trainings in specialized areas for Sindh, KP, GB and Balochistan judiciaries. | - | 150000 | 150000 | 100000 | UNDP | TBC | Technical Assistance, Training, Workshops | 400,000 |
|  | 2.10 Organize a national-level conference for women judges to discuss challenges and opportunities in the justice sector. | 50000 | - | - | 50000 | UNDP | TBC | Technical Assistance, Training, Workshops | 100,000 |
|  | 2.11 Strengthen the functioning of Provincial Justice Committees and Criminal Justice Coordination Committees. | 40000 | 15000 | 15000 | 10000 | UNDP | TBC | Technical Assistance | 40,000 |
|  |  |  |  |  |  |  | EU |  | 40,000 |
|  | 2.12 Establish a probation case management system (PCMS) in Balochistan and KP Probation Services. | - | 75000 | 75000 | 50000 | UNDP | TBC | Technical Assistance | 200,000 |
|  | 2.13 Train ANF staff on basic skills, money laundering and terrorism financing, crime scene investigation, cybercrime, and new psychoactive substances. | 377137 | 377137 | - | - | UNDP | INL | Technical Assistance, Training, Workshops | 754,274 |
|  | 2.14 Enhance service delivery of the judiciary through new curricula and training provided by the Khyber Pakhtunkhwa Judicial Academy (KPJA) and Balochistan Judicial Academy (BJA), on case management, forensics, gender-based violence (GBV), information technology (IT), and ADR. Promote cross-provincial learning and exchange, including a national judicial syndicate and TOT for master trainers. | 86000 | 118000 | 118000 | 118000 | UNDP | TBC | Technical Assistance, Training, Workshops | 354,000 |
|  |  |  |  |  |  |  | EU |  | 86,000 |
|  | 2.15 Enhance service delivery of the KP Prison and Prosecution Department through training needs assessment, training policy development, new curriculum implementation, and training conducted at the Haripur Prison Training Academy. | - | 800000 | 750000 | 786000 | - | TBC | Technical Assistance, Training, Workshops | 2,336,000 |
|  |  |  |  |  |  |  | EU |  | 44,000 |
|  | 2.16 Enhance service delivery of the Reclamation and Probation Department in KP and Balochistan through a training needs assessment, training policy development, new curriculum implementation, and cross-provincial training and exchange, including collaboration with the judiciary. Promote cross-provincial learning and exchange opportunities. | 75000 | 65000 | 80000 | 65000 | UNDP | TBC | Technical Assistance, Training, Workshops | 285,000 |
|  | MONITORING | 30000 | 30000 | 30000 | 30000 | UNDP | TBC |  | 120,000 |
|  | Sub-Total for Output 2 | 1243637 | 2186137 | 1520000 | 1,436,000 |  |  |  | 6,385,774 |
| Output 3: Capacity of women, and the most vulnerable and marginalized (rights holders) strengthened to access referral pathways to justice and security with an emphasis on flood resilience and green energy. (Gen-2) | 3.1 Recruitment drives for induction of additional women in the Police. | - | 150000 | 150000 | 100000 | UNDP | TBC | Technical Assistance | 400,000 |
|  | 3.2 Support women law students and graduates by providing scholarships, apprenticeships, promoting peer support networks, and organizing learning exchange events. | - | 520000 | 500000 | 200000 | UNDP | TBC | Technical Assistance | 1,220,000 |
|  | 3.3 Raise community awareness on available justice referral pathways, how to access them, and related laws; right to access to justice and security (rights holders); and duties of justice and rule of law providers (duty bearers). | 95000 | 100000 | 100000 | 110000 | NGO, Bar Council | TBC | Workshops | 310,000 |
|  |  |  |  |  |  |  | EU |  | 95,000 |
|  | 3.4 Provide support to Legal Aid and Justice Authority Pakistan and other entities (i.e. bar councils, NGOs) to provide legal assistance/representation at the district level. | 100000 | 57000 | - | - | UNDP | EU | Technical Assistance | 157,000 |
|  | 3.5 Empower women to participate in rule of law institutions through capacity building. | 50000 | 50000 | 50000 | 60000 | UNDP | TBC | Technical Assistance, Workshops | 210,000 |
|  | 3.6 Enhance capacity of ADR and court-annexed mediation forums within human rights and constitutional frameworks. | 92500 | 92500 | - | - | UNDP | EU | Technical Assistance | 185,000 |
|  | 3.7 Strengthen bar councils and associations, including law libraries and pro bono support. | 50000 | 50000 | 50000 | 50000 | UNDP | TBC | Technical Assistance | 200,000 |
|  | 3.8 Expand women lawyers' network and promote their professional development. | 50000 | - | 50000 | - | UNDP | TBC | Technical Assistance | 100,000 |
|  | 3.9 Strengthen the functioning of District Resolution Councils through capacity development support | 64000 | 64000 | - | - | UNDP | EU | Technical Assistance | 128,000 |
|  | 3.10 Operationalization of District Legal Empowerment Committees (DLECs) in KP and MDs. | 150000 | 100000 | - | - | UNDP | EU | Technical Assistance | 250,000 |
|  | 3.11 Conduct evaluation studies to measure the level of awareness of people on women protection laws and rights. | 50000 | 50000 | - | - | UNDP | TBC | Technical Assistance, Surveys | 100,000 |
|  | 3.12 Conduct baseline study of current legal advisory and legal aid. | 20000 | - | - | - | UNDP | EU | Technical Assistance, Surveys | 20,000 |
|  | MONITORING | 30000 | 30000 | 30000 | 30000 | UNDP | TBC |  | 120,000 |
|  | Sub-Total for output 3 | 751500 | 1263500 | 930000 | 550000 |  |  |  | 3,495,000 |
| Output 4: Justice and security sector institutional facilities to deliver inclusive, timely, and accessible justice and security services, enhanced through infrastructure development support. (Gen-2) | 4.1: Construction/upgrade of new/existing police infrastructure (including police stations, hostels, offices, daycare centers etc.) to make them gender and Persons with Disabilities (PWD) inclusive. | 250000 | 250000 | 250000 | 250000 | UNDP | TBC | Infrastructure | 1,000,000 |
|  | 4.2 Construct a new training center for the Department of ETAN-B in Quetta, Balochistan. | 555886 | 555866 | - | - | UNDP | TBC | Infrastructure | 1,111,752 |
|  | 4.3 Improve prison and sub-jail conditions, including basic facilities, healthcare facilities, and Haripur Training Academy facilities | 100000 | 38000 | - | - | UNDP | EU | Repair and Renovations | 138,000 |
|  | 4.4 Construct residential and training facilities in vocational education training centers in Bajaur and Kurram. | 556500 | - | - | - | UNDP | INL | Infrastructure | 556,500 |
|  | 4.5 Construction of additional residential facilities to extend existing residential and training facilities at the Anti-Narcotics Force (ANF) in Islamabad | 539000 | 400000 | - | - | UNDP | INL | Infrastructure | 939,000 |
|  | 4.6 Refurbish litigants waiting areas and bar rooms for women lawyers in KP. | 77000 | 80000 | 80000 | 20000 | UNDP | EU | Repair and Renovations | 77,000 |
|  |  |  |  |  |  |  | TBC |  | 200,000 |
|  | 4.7 Construct the Forensic Science Lab in Peshawar, KP. | - | 1000000 | 1000000 | 1000000 | UNDP | TBC | Infrastructure | 3,000,000 |
|  | 4.8 Refurbish court-houses and information centers in KP and Balochistan. | 57500 | 57500 | 57500 | 57500 | UNDP | TBC | Repair and Renovations | 230,000 |
|  | 4.9 Refurbish ADR centers in Balochistan and KP. | - | - | 1400000 | 1300000 | 1300000 | TBC | Repair and Renovations | 4,000,000 |
|  | 4.10 Support to KP, Balochistan, Sindh and Gilgit Baltistan for strengthening the case flow management system (CFMS) and establishing virtual courts. | 150000 | 149580 | - | - | UNDP | TBC | Technical Assistance, Repair and Renovations | 299,580 |
|  | Monitoring and oversight (including through engaging third-party engineering consulting firms) | 20000 | 20000 | 20000 | 20000 | UNDP | TBC |  | 80,000 |
|  | Site Assessment | 10000 | 10000 | 10000 | 10000 | UNDP | TBC |  | 40,000 |
|  | Sub-Total for Output 4 | 2065886 | 4105946 | 2842500 | 2657500 |  |  |  | 11,671,832 |
| Evaluation (as relevant) | Evaluation |  | 60000 |  | 60000 |  |  |  | 120,000 |
| Total Programme Cost |  | 4244023 | 7910583 | 5537500 | 4893500 |  |  |  | 22,705,606 |
| Staffing and operations Cost | 5.1 PMU and Operations | 2,060,575 | 2,060,575 | 1277679 | 1188116 | - | EU, INL, TBC |  | 6,586,945 |
| General Management Support (EU) | @ 7% | 177743 | 141413 | - | - | UNDP | EU |  | 319,155 |
| General Management Support (INL, TBC) | @ 8% | 301234 | 640878 | 545214 | 491329 | UNDP | INL, TBC |  | 1,978,655 |
| TOTAL |  |  |  |  |  |  |  |  | 31,590,362 |
| In- Kind |  |  |  |  |  |  |  |  | 910,000 |
| GRAND TOTAL |  |  |  |  |  |  |  |  | 32,500,362 |

# VIII. Governance and Management Arrangements

## Management Arrangements

UNDP project management and implementation are subject to the results-based management (RBM) approach to development. Therefore, each intervention proposed by UNDP Pakistan has clear and verifiable results (outputs and outcomes), with a direct link to the country-level outcomes proposed in the Country Programme Document (CPD), United Nations Sustainable Development Cooperation Framework (UNSDCF) and UNDP Global Strategic Plan.

The project will be guided by the Project Review Board, and it will provide strategic direction, oversight, and necessary approvals to implement specific tasks/activities where appropriate. The Project Review Board will comprise of senior officials from UNDP, donors, and government stakeholders of the project.

The main responsibilities of the Project Review Board are to:

- Review and endorse necessary approvals/requests in a timely manner to commence/undertake project activities, including budgets, workplans, and civil work design plans.

- Review project progress reports and related information against target results and provide strategic guidance and direction.

- Provide oversight and assess the quality of project implementation.

- Where appropriate, review assessments, evaluations, and recommendations related to project activities, and provide strategic guidance, as required.

- Assess and decide on substantive changes to the project (i.e., project strategy, outputs, and activity results) stemming from unforeseen/unexpected changes to the operational context.

- Recommend new or revised policy guidance/direction in terms of project planning and implementation due to unforeseen/unexpected possible changes to the operational context.

- Ensure that resources are made available in a timely manner to implement the project.

The Project Review Board will meet annually or at a frequency mutually agreed upon between UNDP and the rest of the Project Review Board members. The Project Review Board will comprise of the UNDP Resident Representative, Government Economic Affairs Division ( Co- Chair) along with the donors and rule of law government departments/institutions.

The Co-Chair of the Project Review Board will have ultimate responsibility for the project. As part of the responsibilities of the Project Review Board, the Co-Chair will ensure that the project is focused throughout the project cycle on achieving its outputs and targets. Additional responsibilities include monitoring and controlling the progress of the project at a strategic level; ensuring that risks are being tracked and mitigated as effectively as possible; and chairing and ensuring that the Project Review Board meet in a timely manner, as stipulated in the project document. The Co-Chair will be responsible for approving the project’s multi-year and/or annual work plans.

The Senior Beneficiary will be represented by senior officials from the justice and security institutions including Economic Affairs Division, Planning & Development Departments, Finance Departments and Home & Trial Affairs Departments representing the interests of those who will ultimately benefit from the project. The primary function of the Senior Beneficiary within the Project Review Board is to ensure the realization of the project results from the perspective of project beneficiaries.

The Senior Supplier will represent the interests of those parties concerned with providing funding and/or technical expertise to the project. The primary function and responsibility of the Senior Supplier is to provide guidance regarding the technical feasibility of the project. As part of the responsibilities of the Project Review Board, the Senior Supplier will advise on the identification of strategies, design, and methods to carry out project actions. Within the context of the Project Review Board, the Senior Supplier is also responsible for ensuring that progress towards outputs remains consistent; contributing the supplier’s perspective and opinions on implementing any proposed changes; and arbitrating on and ensuring resolution of input/resource related priorities or conflicts.

The Project Assurance role will be delegated by the Project Review Board to the Democratic Governance Unit (DGU) of UNDP Pakistan CO. The Project Assurance role must be independent of the RoL Programme Manager. The Project Assurance role supports the Project Review Board by carrying out objective and independent project oversight and monitoring functions. This role ensures appropriate project management milestones are managed and completed. The Project Assurance role needs to be engaged throughout the project as part of ensuring that it remains relevant, follows the approved plans and continues to meet the planned targets with quality. The Project Assurance role is required to ensure beneficiary needs and expectations are being met or managed; risks are being controlled; adherence to the project justification (business case); the right people are being involved; an acceptable solution is being developed; the project remains viable; applicable UNDP rules and regulations are being observed; adherence to monitoring and reporting requirements and standards of the donor; quality management procedures are properly followed; and the Project Review Board’s decisions are followed and revisions are managed in line with the required procedures.

The Rule of Law Programme’s Programme Manager (PM) is responsible for the successful management of project outputs and contribution to the achievement of project outcomes. The PM will have the responsibility to run the project on a day-to-day basis on behalf of and within the framework outlined by the Project Review Board. The PM is responsible for working in coordination with the co-chair and rest of the Project Review Board to ensure project implementation, financial management, administration, monitoring, and reporting takes place in a timely manner. Under the guidance of the Co-Chairs, the PM shall ensure efficient coordination efforts between the stakeholders of the project. The PM will be responsible for managing the realization of project outputs and targets through actions as specified in the Annual Work Plan. This includes: planning activities/actions; preparing annual work plans; overseeing the implementation of activities/actions (including liaising with service providers to mobilize goods and services); managing financial resources and accounting to ensure accuracy and reliability of financial reports; updating the monitoring plan; managing, monitoring and updating the project risks; identifying new risks and alerting the Project Steering Committees (federal and provincial levels) to consider and decide on possible actions; managing issues and requests for change (including maintaining an Issues Log); and oversee the preparation of project progress reports (i.e. Annual Progress Narrative Report and Final Report) for submission to the Project Steering Committees. The PM will be supported by a Project Administration and Operations Support Team and a Technical Advisory Team (TAT), in carrying out his/her function.

Project Review Board

Oversight

Implementation

Development Partner (Supplier)

[European Union, Embassy of Japan, US-INL]

Beneficiary Representative

[Police, Judiciary, Prosecution, Prison, Anti-Narcotics Force]

Project Executive

[UNDP Resident Representative]

Project Assurance- DGU

Programme Manager

Technical Experts Judiciary

Technical Experts Prosecution and Prison

Technical Experts Law Enforcement and Police

Technical Experts Gender

Technical Experts Civil Engineers

Technical Experts M&E, Knowledge Management & Communications

Operations and Finance support team

Figure 5: Rule of Law Programme Organization Structure

# IX. Legal Context

Option b. Where the country has NOT signed the Standard Basic Assistance Agreement (SBAA)

The project document shall be the instrument envisaged and defined in the Supplemental Provisions to the Project Document, attached hereto and forming an integral part hereof, as “the Project Document”.

This project will be implemented by UNDP through the direct implementation modality (DIM) in accordance with its financial regulations, rules, practices, and procedures, as defined in the UNDP programme and perations policies and procedures.

# X. Risk Management

Option b. UNDP (DIM)

- UNDP as the Implementing Partner will comply with the policies, procedures and practices of the United Nations Security Management System (UNSMS.)

- UNDP as the Implementing Partner will undertake all reasonable efforts to ensure that none of the [project funds] [UNDP funds received pursuant to the Project Document] are used to provide support to individuals or entities associated with terrorism, that the recipients of any amounts provided by UNDP hereunder do not appear on the United Nations Security Council Consolidated Sanctions List, and that no UNDP funds received pursuant to the Project Document are used for money laundering activities. The United Nations Security Council Consolidated Sanctions List can be accessed via https://www.un.org/securitycouncil/content/un-sc-consolidated-list. This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document.

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

- UNDP as the Implementing Partner will: (a) conduct project and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

- In the implementation of the activities under this Project Document, UNDP as the Implementing Partner will handle any sexual exploitation and abuse (“SEA”) and sexual harassment (“SH”) allegations in accordance with its regulations, rules, policies and procedures.

- All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any programme or project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

- UNDP as the Implementing Partner will ensure that the following obligations are binding on each responsible party, subcontractor, and sub-recipient:

  - Consistent with the Article III of the SBAA [or the Supplemental Provisions to the Project Document], the responsibility for the safety and security of each responsible party, subcontractor and sub-recipient and its personnel and property, and of UNDP’s property in such responsible party’s, subcontractor’s and sub-recipient’s custody, rests with such responsible party, subcontractor and sub-recipient. To this end, each responsible party, subcontractor, and sub-recipient shall:

    - put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

    - assume all risks and liabilities related to such responsible party’s, subcontractor’s and sub-recipient’s security, and the full implementation of the security plan.

  - UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the responsible party’s, subcontractor’s and sub-recipient’s obligations under this Project Document.

  - Each responsible party, subcontractor and sub-recipient (each a “sub-party” and together “sub-parties”) acknowledges and agrees that UNDP will not tolerate sexual harassment and sexual exploitation and abuse of anyone by the sub-parties, and other entities involved in Project implementation, either as contractors or subcontractors and their personnel, and any individuals performing services for them under the Project Document.

(a) In the implementation of the activities under this Project Document, each sub-party shall comply with the standards of conduct set forth in the Secretary General’s Bulletin ST/SGB/2003/13 of 9 October 2003, concerning “Special measures for protection from sexual exploitation and sexual abuse” (“SEA”).

(b) Moreover, and without limitation to the application of other regulations, rules, policies and procedures bearing upon the performance of the activities under this Project Document, in the implementation of activities, each sub-party, shall not engage in any form of sexual harassment (“SH”). SH is defined as any unwelcome conduct of a sexual nature that might reasonably be expected or be perceived to cause offense or humiliation, when such conduct interferes with work, is made a condition of employment or creates an intimidating, hostile or offensive work environment. SH may occur in the workplace or in connection with work. While typically involving a pattern of conduct, SH may take the form of a single incident. In assessing the reasonableness of expectations or perceptions, the perspective of the person who is the target of the conduct shall be considered.

  - In the performance of the activities under this Project Document, each sub-party shall (with respect to its own activities), and shall require from its sub-parties (with respect to their activities) that they, have minimum standards and procedures in place, or a plan to develop and/or improve such standards and procedures in order to be able to take effective preventive and investigative action. These should include: policies on sexual harassment and sexual exploitation and abuse; policies on whistleblowing/protection against retaliation; and complaints, disciplinary and investigative mechanisms. In line with this, sub-parties will and will require that their respective sub-parties will take all appropriate measures to:

(i) Prevent its employees, agents or any other persons engaged to perform any services under this Project Document, from engaging in SH or SEA;

(ii) Offer employees and associated personnel training on prevention and response to SH and SEA, where sub-parties have not put in place its own training regarding the prevention of SH and SEA, sub-parties may use the training material available at UNDP;

(iii) Report and monitor allegations of SH and SEA of which any of the sub-parties have been informed or have otherwise become aware, and status thereof;

(iv) Refer victims/survivors of SH and SEA to safe and confidential victim assistance; and

(v) Promptly and confidentially record and investigate any allegations credible enough to warrant an investigation of SH or SEA. Each sub-party shall advise UNDP of any such allegations received and investigations being conducted by itself or any of its sub-parties with respect to their activities under the Project Document, and shall keep UNDP informed during the investigation by it or any of such sub-parties, to the extent that such notification (i) does not jeopardize the conduct of the investigation, including but not limited to the safety or security of persons, and/or (ii) is not in contravention of any laws applicable to it. Following the investigation, the relevant sub-party shall advise UNDP of any actions taken by it or any of the other entities further to the investigation.

  - Each sub-party shall establish that it has complied with the foregoing, to the satisfaction of UNDP, when requested by UNDP or any party acting on its behalf to provide such confirmation. Failure of the relevant sub-party to comply of the foregoing, as determined by UNDP, shall be considered grounds for suspension or termination of the Project.

  - Each responsible party, subcontractor and sub-recipient will ensure that any project activities undertaken by them will be implemented in a manner consistent with the UNDP Social and Environmental Standards and shall ensure that any incidents or issues of non-compliance shall be reported to UNDP in accordance with UNDP Social and Environmental Standards.

  - Each responsible party, subcontractor and sub-recipient will take appropriate steps to prevent misuse of funds, fraud, corruption, or other financial irregularities, by its officials, consultants, subcontractors and sub-recipients in implementing the project or programme or using the UNDP funds. It will ensure that its financial management, anti-corruption, anti-fraud, and anti-money laundering and countering the financing of terrorism policies are in place and enforced for all funding received from or through UNDP.

  - The requirements of the following documents, then in force at the time of signature of the Project Document, apply to each responsible party, subcontractor, and sub-recipient: (a) UNDP Policy on Fraud and other Corrupt Practices (b) UNDP Anti-Money Laundering and Countering the Financing of Terrorism Policy; and (c) UNDP Office of Audit and Investigations Investigation Guidelines. Each responsible party, subcontractor and sub-recipient agrees to the requirements of the above documents, which are an integral part of this Project Document and are available online at www.undp.org.

  - In the event that an investigation is required, UNDP will conduct investigations relating to any aspect of UNDP programmes and projects. Each responsible party, subcontractor and sub-recipient will provide its full cooperation, including making available personnel, relevant documentation, and granting access to its (and its consultants’, subcontractors’ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with it to find a solution.

  - Each responsible party, subcontractor and sub-recipient will promptly inform UNDP as the Implementing Partner in case of any incidence of inappropriate use of funds, or credible allegation of fraud, corruption other financial irregularities with due confidentiality.

Where it becomes aware that a UNDP project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption, each responsible party, subcontractor and sub-recipient will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). It will provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

  - Choose one of the three following options:

Option 1: UNDP will be entitled to a refund from the responsible party, subcontractor or sub-recipient of any funds provided that have been used inappropriately, including through fraud corruption, other financial irregularities or otherwise paid other than in accordance with the terms and conditions of this Project Document. Such amount may be deducted by UNDP from any payment due to the responsible party, subcontractor or sub-recipient under this or any other agreement. Recovery of such amount by UNDP shall not diminish or curtail any responsible party’s, subcontractor’s or sub-recipient’s obligations under this Project Document.

Option 2: Each responsible party, subcontractor or sub-recipient agrees that, where applicable, donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities which are the subject of the Project Document, may seek recourse to such responsible party, subcontractor or sub-recipient for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud corruption or other financial irregularities or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Option 3: UNDP will be entitled to a refund from the responsible party, subcontractor, or sub-recipient of any funds provided that have been used inappropriately, including through fraud corruption or other financial irregularities, or otherwise paid other than in accordance with the terms and conditions of the Project Document. Such amount may be deducted by UNDP from any payment due to the responsible party, subcontractor or sub-recipient under this or any other agreement.

Where such funds have not been refunded to UNDP, the responsible party, subcontractor or sub-recipient agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Project Document, may seek recourse to such responsible party, subcontractor or sub-recipient for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud, corruption or other financial irregularities, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Note: The term “Project Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Project Document, including those with responsible parties, subcontractors and sub-recipients.

  - Each contract issued by the responsible party, subcontractor, or sub-recipient in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from it shall cooperate with any and all investigations and post-payment audits.

  - Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the project or programme, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover, and return any recovered funds to UNDP.

  - Each responsible party, subcontractor and sub-recipient shall ensure that all of its obligations set forth under this section entitled “Risk Management” are passed on to its subcontractors and sub-recipients and that all the clauses under this section entitled “Risk Management Standard Clauses” are adequately reflected, mutatis mutandis, in all its sub-contracts or sub-agreements entered into further to this Project Document.

XI. ANNEXES

| Annex I: Rule of Law Programme Quality Assurance Report |  |
| --- | --- |
| Annex II: Rule of Law Programme Social and Environmental Screening Report |  |
| Annex III: Rule of Law Programme Risk Analysis |  |
| Annex IV: Rule of Law Programme Board Terms of Reference and TORs of Key Management Positions. |  |
| Annex V: Rule of Law Programme Gender Analysis and Action Plan |  |
| Annex VI: Rule of Law Programme Delegation of Authority (DOA) |  |
| Annex VII: Rule of Law Programme Stakeholder Engagement Plan |  |
| Annex VIII: Rule of Law Programme Feasibility Study of Construction Activities |  |

Land provided by the government end users to implement rule of law infrastructure projects under Output 4.

Baseline study to evaluate citizens’ legal awareness and perception of the rule of law and access to justice in Khyber Pakhtunkhwa (KP) and Balochistan, UNDP, 2022.

World Justice Report 2022.

Global Gender Gap Report.

https://www.balochistanpolice.gov.pk/allcrime; https://www.pbs.gov.pk/node/1100

https://www.dawn.com/news/1699337

Government of Pakistan Cabinet Secretariat Establishment Division notification number 4/15/2006-R-2 dated 22 May 2007.

The KP Government Tribal Decade Strategy 2020-2030 and the Balochistan Rule of Law Roadmap.

The KP Rule of Law Roadmap.

Representative from Balochistan Bar Council, November 2022.

Home Department data – unpublished.

FSL Peshawar data 2019 and data predicted for 2030 & 2050 using moving averages and equations.

https://pakistan.asia-news.com/en_GB/articles/cnmi_pf/features/2020/02/03/feature-02

https://www.prisonstudies.org/country/pakistan; https://www.dawn.com/news/1659482.

Impact evaluation of strengthening rule of law programme in selected districts of Khyber Pakhtunkhwa, UNDP, 2019.

UNDP Pakistan Rule of Law Programme provided technical assistance to GB Government to draft its first ever Rule of Law Road Map from 2020-2022 and it was endorsed by the GB Government cabinet in May 2023.

This list will be updated as and when additional partners may be added subject to project’s resource mobilization efforts going forward.

Ibid

Ibid

Ibid

Contributing donors: UNDP Global Fund and USAID

https://popp.undp.org/SitePages/POPPRoot.aspx

Ibid

Ibid

Formula: Advancement Rate = (# scholarship and stipend recipients advancing in the legal career / total # scholarship and stipend recipients) * 100

To be used where UNDP is the Implementing Partner

To be used where the UN, a UN fund/programme or a specialized agency is the Implementing Partner