Ukraine Joint Programme on CRSV

MPTF OFfice GENERIC programme NARRATIVE progress report

REPORTING PERIOD: 1 january – 31 March 2025

| Programme Title & Project Number |  |  | Country, Locality(s), Priority Area(s) / Strategic Results |  |
| --- | --- | --- | --- | --- |
| - Programme Title: Ukraine Joint Programme on CRSV - Programme Number (if applicable) - MPTF Office Project Reference Number: 00140541 |  |  | Country/Region Ukraine |  |
|  |  |  | Priority area/ strategic results: Outcomes(s): United Nations in Ukraine - Transitional Framework (September 2022-December 2023): Strategic Priority 2.1: National capacities are strengthened and use data for efficient crisis response and recovery planning Strategic Priority 3.1: Early recovery interventions are effective in increasing inclusive human development, promoting a sustainable green economy, and building a resilient society |  |
| Participating Organization(s) |  |  | Implementing Partners |  |
| - Office of the Special Representative of the Secretary General on Sexual Violence in Conflict (OSRSG-SVC) - United Nations Development Programme (UNDP) in Ukraine - United Nations Entity for Gender Equality and the Empowerment of Women (UN Women) in Ukraine - United Nations Population Fund (UNFPA) in Ukraine |  |  | - Office of the United Nations High Commissioner for Human Rights (OHCHR) in Ukraine - Office of the Deputy Prime Minister for European and Euro-Atlantic Integration (DPM/EEAI) - Office (Apparatus) of the Government Commissioner for Gender Equality Policy (GC/GEP) - Office of the Ombudsperson (OOP) - Ministry of Social Policy (MSP) - National Social Service of Ukraine (NSSU) - Ministry of Internal Affairs (MIA) - National Police of Ukraine (NPU) |  |
| Programme/Project Cost (US$) |  |  | Programme Duration |  |
| Total approved budget as per project document: MPTF /JP Contribution: - by Agency (if applicable) | $2,333,100.00 |  | Overall Duration (months) | 18 months |
| Agency Contribution - by Agency (if applicable) | $470,241.35 |  | Start Date (dd.mm.yyyy) | 16.01.2024 |
| Government Contribution (if applicable) | $0.00 |  | Original End Date (dd.mm.yyyy) | 31.05.2025 |
| Other Contributions (donors) (if applicable) | 0.00 |  | Current End date(dd.mm.yyyy) | 15.06.2024 |
| TOTAL: | $2,803,341.35 |  |  |  |
| Programme Assessment/Review/Mid-Term Eval. |  |  | Report Submitted By |  |
| Assessment/Review - if applicable please attach Yes No Date: dd.mm.yyyy Mid-Term Evaluation Report – if applicable please attach Yes No Date: dd.mm.yyyy |  |  | - Name: - Title: - Participating Organization (Lead): Office of the Special Representative of the Secretary General on Sexual Violence in Conflict - Email address: |  |

(DELETE BEFORE SUBMISSION) Guidelines: The Narrative Progress Report template is based on the UNDG 2003 template, which is currently under review and is in line with the UNDG Results Based Management Handbook (October 2011). https://unsdg.un.org/resources/unsdg-results-based-management-handbook Building on continued efforts made in the UN system to produce results-based reports, the progress report should describe how the activities (inputs) contributed to the achievement of specific short-term outputs during the twelve month reporting period, and to demonstrate how the short-term outputs achieved in the reporting period collectively contributed to the achievement of the agreed upon outcomes of the applicable Strategic (UN) Planning Framework guiding the operations of the Fund. In support of the individual programme reports, please attach any additional relevant information and photographs, assessments, evaluations and studies undertaken or published. Where available, the information contained in the Programme Summaries and Quarterly and/or Semi-Annual Updates prepared by the Participating Organizations may be useful in the preparation of the Annual Narrative Progress Report. These Summaries and Updates, where applicable, are available in the respective Fund sections of the MPTF Office GATEWAY (http://mptf.undp.org/).

Formatting Instructions: - The report should be between 10-15 pages. Include a list of the main abbreviations and acronyms that are used in the report. - Number all pages, sections and paragraphs as indicated below. - Format the entire document using the following font: 12point _ Times New Roman and do not use colours. - The report should be submitted in one single Word or PDF file. - Annexes can be added to the report but need to be clearly referenced, using footnotes or endnotes within the body of the narrative.

# NARRATIVE REPORT FORMAT

# EXECUTIVE SUMMARY

In ¼ to ½ a page, summarise the most important achievements of Programme during the reporting period and key elements from your detailed report below. Highlight in the summary, the elements of the main report that you consider to be the most critical to be included in the MPTF Office Consolidated Annual Report.

Ukraine Joint Programme on CRSV (CRSV JP) was designed to provide both strategic and technical support to the roll-out of the Joint Implementation Action Plan (JIAP) developed following the adoption of the Framework of Cooperation (FoC) on the Prevention and Response to Conflict-Related Sexual Violence (CRSV) in Ukraine. The CRSV JP envisions the provision of technical support and expertise to several Government of Ukraine (GOU) institutions and relevant UN entities, which will work in collaboration with civil society organisations (CSOs) and first responders in implementing the FoC through: (i) policy development, (ii) training/awareness raising, and (iii) support to survivors.

In January-March 2025, the key achievements associated with the EU Service for Foreign Policy Instruments (FPI) sponsored assistance were:

  - …

…

There are still significant CRSV knowledge gaps and a large potential for CRSV prevention and response failures due to persistent underreporting of CRSV cases (driven by survivors' mistrust of institutions and stigma), the lack of specialised legal aid, the lack of clear referral pathways for CRSV survivors, and limited CRSV and GBV response integration.

# Purpose

Provide the main objectives and expected outcomes of the programme in relation to the appropriate Strategic UN Planning Framework (e.g. UNDAF) and project document (if applicable) or Annual Work Plan (AWP).

Ukraine CRSV JP was designed to provide both strategic and technical support to the roll-out of the FoC JIAP developed following the adoption of the FoC on the Prevention and Response to CRSV in Ukraine. The CRSV JP envisions the provision of technical support and expertise to several GOU’s institutions and relevant UN entities, which will work in collaboration with CSOs and first responders in implementing the FoC through: (i) policy development, (ii) training/awareness raising, and (iii) support to survivors.

The CRSV JP main objective was formulated to read as follows: ‘Strengthened and coordinated CRSV prevention and response in Ukraine.’ It is dependent on the following three outcomes:

- Improved coordination among government entities to ensure policy consistency in the prevention and response to CRSV based on accurate and objective data.

- Increased capacity of stakeholders involved in the roll out of the implementation plan in developing programmes using a survivor-centred approach based on accurate and objective date.

- Improved accessibility of services for survivors.

The CRSV JP is contributing to achieving two of the three strategic priorities - Strategic Priority 2.1 ‘Community recovery interventions are effective in increasing resilience and addressing displacement through the adoption of nexus approaches in key sectors, promoting rights-based, peoplecentred, inclusive and gender-responsive human development’ and Strategic Priority 3.1 ‘National and sub-national capacities and systems are strengthened and are informed by data underpinning efficient, inclusive, and gender-responsive crisis response, recovery planning and green economic growth’ - of the UN in Ukraine Transitional Framework (2022-2024) and more broadly to achieving the SDG 16 ‘Peace, Justice and Strong Institutions’.

# Results

This section is the most important in the Report and particular attention should be given to reporting on results / and changes that have taken place rather than on activities. It has three parts to help capture this information in different ways (i. Narrative section; ii. Indicator based performance assessment; and iii. A specific story).

- Narrative reporting on results:

From January to March 2025, respond to the guiding questions indicated below to provide a narrative summary of the results achieved. The aim here is to tell the story of change that your Programme has achieved in January-March 2025. Make reference to the implementation mechanism utilised and key partnerships.

Outcomes: Outcomes are the strategic, higher level of change that your Programme is aiming to contribute towards. Provide a summary of progress made by the Programme in relation to planned outcomes from the Project Document / AWP, with reference to the relevant indicator(s) in these documents. Describe if any targets were achieved or explain any variance in achieved versus planned results during the reporting period. Explain who the main beneficiaries were.

Outcome 1 – Improved coordination among government entities to ensure policy consistency in the prevention and response to CRSV based on accurate and objective data

In January-March 2025, the key Outcome 1 achievements associated with the EU FPI-sponsored assistance were:

  - …

Outcome 2 – Increased capacity of stakeholders involved in the roll out of the implementation plan in developing programmes using a survivor-centred approach based on accurate and objective data

In January-March 2025, the EU FPI-sponsored assistance helped …

Outcome 3 – Improved accessibility of services for (CRSV) survivors

In January-March 2025, the EU FPI-sponsored assistance helped …

Outputs: Outputs are the more immediate results that your Programme is responsible for achieving. Report on the key outputs achieved in the reporting period, in relation to planned outputs from the Project Document, with reference to the relevant indicator(s) in these documents. Describe if any targets were achieved or explain any variance in achieved versus planned results during the reporting period. If possible, include the percentage of completion of the outputs and the type and number of beneficiaries.

Output 1.1 Strategic and technical capacity of national authorities enhanced in the prevention and response to CRSV (All PUNOs)

In January-March 2025, the CRSV JP helped …

In January-March 2025, PUNO’s assistance efforts in CRSV were informed and advanced by the group of international advisors - the Senior Women Protection Advisor (Senior WPA or SWPA) hired by UNDP and embedded in the Regional UN Coordinator Office (RCO), a WPA hired by UNFPA and seconded to the local OHCHR Team, and another WPA hired and embedded in the local UN Women Team. Their work contribute to strengthening national responses and ensuring more effective support mechanisms for CRSV survivors.

At the end of March 2025, PUNOs continued funding several local experts who served either as advisors or coordinators and augmented capacities of seven GOU organisations: two experts supporting the DPM/EEAI Office, two experts supporting the GC/GEP Office (often called Apparatus), an expert supporting the Ombudsperson’s Office, an expert supporting the MIA and the NPU (a MIA-subordinated organisation), two experts supporting the MSP, and an expert supporting the NSS (a MSP-subordinated organisation). Local experts were supported by three aforementioned WPAs embedded in PUNOs.

To ensure close coordination of PUNO’s assistance efforts, PUNO representatives and PUNO-funded WPAs held a meeting of the UN CRSV Working Group (CRSV WG) created to coordinate design and implementation of the CRSV-related activities amongst UN organisations.

Abovementioned PUNO’s coordination efforts were complementary to the work of the UN/Ukraine CRSV Technical Group (TG) co-chaired by the GC/GEP and the Acting SWPA. This TG includes PUNO representatives, PUNO-funded international and national CRSV advisors, and representatives of the assisted GOU organisations. The first 2025 TG meeting is scheduled for April 30, 2025.

The UNDP-funded MIA/NPU Advisor supported the MIA in developing methodological recommendations on: (a) interaction between investigators and psychologists in criminal proceedings related to sexual violence; (b) compliance with international protocols for the safe, ethical collection, use, exchange, and analysis of data on sexual violence cases reported to the NPU, MIA, and NPU hotline; and (c) the identification of the subject and object of the offense in sexual violence cases, in accordance with the IHL norms and practices. To enhance the practical value of these methodological recommendations, survivors of CRSV (both men and women), psychologists involved in relevant criminal proceedings and providing assistance to survivors, as well as investigators from the NPU, participated in their preparation. The recommendations will be completed in 2025.

…

Output 1.2 The monitoring, analysis and reporting arrangements (MARA) mechanism is strengthened, in line with relevant Security Council resolutions, including resolutions #1960 (2010) and #2467 (2019) *(All PUNOs).

The PUNO-funded WPA embedded with the local OHCHR Team helped it prepare a quarterly Report on the Human Rights Situation in Ukraine, which included CRSV data and its analysis.

| Report Title | Period Covered | Link |
| --- | --- | --- |
| The impact of the armed conflict and occupation on children’s rights in Ukraine (24 February 2022 – 31 December 2024) | February 2022 -December 2024 | https://www.ohchr.org/en/documents/country-reports/impact-armed-conflict-and-occupation-childrens-rights-ukraine-24-february |

Members of the CRSV WG conducting two joint field visits in early 2025. Those joint visits were used to assess local capacity to identify, report, and respond to CRSV cases and identify gaps and challenges that local institutions face in identifying and processing CRSV cases …

The UNDP-funded MIA/NPU Advisor designed and conducted six (?) webinars on international protocols for the safe, ethical collection, use, exchange and analysis of CRSV data for entities that are engaged in reporting at the NPU.

…

Output 2.1 Stakeholders involved in the response to CRSV trained to develop and implement CRSV-related policies using a survivor-centred approach (UNDP & UN Women)

The UNDP-funded MIA/NPU Advisor will conduct two training events for police investigators and psychologists on using psychologist's expertise in CRSV criminal proceedings and one training event for the NPU on CRSV crime qualification (as a crime against humanity), CRSV evidence collection, team work, and use of OSINT in identifying perpetrators in 2025. There are also plans to develop a training program for regional representatives of the Verkhovna Rada of Ukraine (VRU) Human Rights Commissioner (HRC) on overseeng executive branch CRSV prevention and response efforts.

Those training events were structured around nine training modules (listed below) developed by the UNDP-funded MIA/NPU Advisor in 2024:

- CRSV as a Psychologically Traumatic Factor;

- Fundamentals of International Humanitarian Law (IHL) | CRSV: Elements of the Crime & Evidence | Ukraine, the International Criminal Court (ICC) and other international institutions;

- Review of Current Legislative Activities Associated with Introduction of IHL Requirements in Ukrainian Legislation and Related Changes to the Criminal Proceedings;

- Use of Open-Source Intelligence (OSINT) in CRSV Cases;

- Using Forensic Medicine in CRSV Criminal Proceedings;

- Using a CRSV Survivor-Centered Approach in Identifying (CRSV) Survivors and Conducting a CRSV Case Investigation;

- Collaboration of an Investigator, Operational Officer, and a Psychologist in a CRSV Criminal Proceedings;

- Setting an Interview Room and Use of Audio/Video/Other Means of Verification in Conducting an Interview; and

- Conducting Survivors’ Interviews in CRSV Criminal Proceedings.

…

Output 2.2 All stakeholders involved in the monitoring, analysis and reporting are highly trained to ensure reliable data and information on CRSV (UNFPA & UN Women)

…

Output 3.1 All services available to CRSV survivors are identified and referral pathways are coordinated to connect CRSV survivors to appropriate, quality and multi-sectoral services (UNFPA)

…

Output 3.2 All services available to CRSV survivors follow a standard procedure for ensuring the delivery needs-oriented assistance to CRSV survivors (UNDP)

In early 2025, UNDP hired a consultant to support the MSP in developing (a) a protocol for working with CRSV survivors and a reporting form for assistance provided to a survivor, and (b) a program to assist CRSV survivors.

Output 3.3 Supporting institutions working on CRSV cases/providing support to CRSV survivors (UNDP & UNFPA)

In 2024, UNDP helped the NPU identify equipment that would facilitate CRSV case processing and service provision at 12 NPU oblast-level offices, and initiated procurement of the equipment in December 2024. The procurement will be completed in May-June 2025.

…

Describe any delays in implementation, challenges, lessons learned & best practices: If there were delays, explain the nature of the constraints and challenges, actions taken to mitigate future delays and lessons learned in the process. Provide an updated risk analysis (have any of the risks identified during the project design materialized or changed? Are there any new risks?). Were there any programmatic revisions undertaken during the reporting period? Please also include experiences of failure, which often are the richest source of lessons learned.

Delays in implementation

...

Challenges

…

Lessons learned

- Original CRSV JP cost estimates were not fully aligned with the adjustments made to its planned interventions and required significant revision.

- High flexibility integrated in the CRSV JP design and EU FPI’s commitment to support important social service reforms contributed a lot into CRSV JP successful implementation in unpredictable war-shaped environment.

- Despite of important achievements in CRSV response in Ukraine, there are still significant CRSV knowledge gaps and a large potential for failures in CRSV prevention and response due to persistent underreporting of CRSV cases (driven by survivors' mistrust of institutions and stigma), the lack of specialised legal aid, the lack of clear referral pathways for CRSV survivors, and limited CRSV and GBV response integration.

Qualitative assessment: Provide a qualitative assessment of the level of overall achievement of the Programme. Highlight key partnerships and explain how such relationships impacted on the achievement of results. Explain cross-cutting issues pertinent to the results being reported on. For Joint Programmes, highlight how UN coordination has been affected in support of achievement of results.

…

ii) Indicator Based Performance Assessment:

Using the Programme Results Framework from the Project Document / AWP - provide an update on the achievement of indicators at both the output and outcome level in the table below. Where it has not been possible to collect data on indicators, clear explanation should be given explaining why, as well as plans on how and when this data will be collected.

| Outcomes & Outputs Indicators & Baselines & Targets | Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source(s) of Verification |
| --- | --- | --- | --- |
| Outcome 1 - Improved coordination among government entities to ensure policy consistency in the prevention and response to CRSV based on accurate and objective data |  |  |  |
| Indicator 1.1: The Joint Secretariat is established in support of the IAWG for the roll-out of the JIAP for the FoC on CRSV Baseline: Meetings of the IAWG are held on an irregular basis Planned Target: The IAWG is meeting on a regular basis and provides accurate guidance in the roll-out of the JIAP based on accurate and objective data | The IAWG met two times in 2024. IAWG meetings were useful. The JIAP has been implemented with some delays. | The IAWG is controlled by the GOU. It includes representatives of more than 80 organisations. The GOU slowly adopts modern planning and programming methods. | Key informant interviews (KIIs), mass media posts; meeting reports; attendance lists; observations; |
| Output 1.1 - Strategic and technical capacity of national authorities enhanced in the prevention and response to CRSV |  |  |  |
| Indicator 1.1.1 - Number of coordination meetings conducted by the IAWG and/or its subgroups (amended in August 2024) Baseline: at least two IAWG meetings per year Planned Target: 10 meetings | The IAWG met two times in 2024. Each of five IAWG subgroups met at least once in 2024. The UN CRSV WG met four times in 2024 and one time in 2025. | No variance is observed. | Mass media posts; meeting reports; attendance lists. |
| Indicator 1.1.2 - Number of guidance notes, recommendation and/or methodology documents produced (amended in August 2024) Baseline: 0 Planned Target: 10 | One guidance note was prepared in 2024. Three documents have already been developed in 2025. | No variance is observed. | KIIs, Guidance Notes; workplans (roadmaps) of CRSV JP funded advisors |
| Indicator 1.1.3 - Number of governmental institutions (Ministry/Other national level authority) receiving ongoing support from PUNO-hired experts (added in August 2024) Baseline: 0 Planned Target: 6 | The CRSV JP supported the DPM/EEAI Office, the GC/GEP Office (Apparatus), the Ombudsperson’s Office, the Ministry of Social Policy & the National Social Service, and the Ministry of Internal Affairs & the National Police. | The target is exceeded. | KIIs, workplans (roadmaps) of CRSV JP funded advisors |
| Indicator 1.1.4 - Number of IAWG Annual Reports (added in March 2025) Baseline: 0 Planned Target: 2 | Annual Report of IAWG subgroup #4 (Security and Defense) & Annual Report of IAWG subgroup #5 (Reparations) were prepared. | No variance is observed. | Draft Annual Reports |
| Output 1.2 - The monitoring, analysis and reporting arrangements (MARA) mechanism is strengthened, in line with relevant Security Council resolutions, including resolutions #1960 (2010) and #2467 (2019) |  |  |  |
| Indicator 1.2.1 - Number of OHCHR public reports including information and analysis on CRSV in Ukraine (amended in August 2024) Baseline: 0 Planned Target: four per year | A special OHCHR report published in early 2025 included information and analysis on CRSV in Ukraine. | The Q1 OHCHR Human Rights Report is being drafted. | OHCHR public reports |
| Indicator 1.2.2 - Inputs from UN Country Team provided to the SRSG/SVC Office for the Secretary General's Annual Report on CRSV (added in August 2024) Baseline: 0 Planned Target: once a year | The 2024 Annual Narrative Report is expected to be used to inform preparation of the Secretary General's Annual Report on CRSV. | No variance is observed. | Annual Narrative Report |
| Indicator 1.2.3 - Number of updates to the CRSV WG on OHCHR-documented CRSV cases, including statistics and analysis of patterns and trends (added in August 2024) Baseline: 0 Planned Target: four times per year | Two updates were made in 2024. No updates were made in 2025. | The 2024 target was met. | Meeting reports |
| Indicator 1.2.4 - Number of updates to the IAWG supporting implementation of the FoC on OHCHR-documented CRSV cases, including statistics and analysis of patterns and trends (added in August 2024, amended in March 2025) Baseline: 0 Planned Target: once a year | One update was made in 2024. No update was made in early 2025. | No variance is observed. | Meeting reports |
| Indicator 1.2.5 - Number of field visits to identify gaps, challenges, recommendations related to CRSV monitoring, analysis and reporting arrangements (amended in August 2024) Baseline: 0 Planned Target: 3 | Two visits were conducted in early 2025. | No variance is observed. | Field visit reports |
| Indicator 1.2.6 - Number of webinars and/or workshops on CRSV data protection and exchange methodologies (amended in August 2024 and March 2025). Baseline: 0 Planned Target: 2 | … webinars/workshops were conducted in early 2025. | No variance is observed. | Webinar agendas, attendance lists, presentations, post-training assessments |
| Indicator 1.2.7 - Terms of Reference for CRSV WG and data sharing protocol developed (added in August 2024). Baseline: 0 Planned Target: 2 (Terms of Reference & Data Sharing Protocol) | Terms of Reference for CRSV Working Group were developed in 2024. Data sharing protocol will be developed in 2025. |  | Terms of Reference, Data Sharing Protocol |

| Outcome 2 - Increased capacity of stakeholders involved in the roll out of the implementation plan in developing programmes using a survivor-centred approach based on accurate and objective data |  |  |  |
| --- | --- | --- | --- |
| Indicator 2.1 - Percentage of actors reporting improved knowledge in working with CRSV cases/delivering services to CRSV survivors Baseline 1: Limited level of knowledge on the principles of the survivor-centred approach and holistic care in the development and delivery of trainings Planned Target 1: Based on questionnaires, over 80% of actors reached by the project’s trainings report improved knowledge as a result of trainings | Over 80% of participants of UNDP-sponsored training events reported improved knowledge of CRSV-specific crime investigation in 2024. | The 2024 target was met. | KIIs, focus group discussions (FGDs), attendance lists, presentations, post-training assessments |
| Indicator 2.1 - Percentage of actors reporting improved knowledge in working with CRSV cases/delivering services to CRSV survivors Baseline 2: Insufficient involvement of survivors in the development and verification of training programmes Planned Target 2: Relevant interventions integrate survivors’ own experiences and input within respective initiatives as part of the Implementation Plan | Many CRSV JP-funded interventions reflected survivors’ experiences and input. | The 2024 target was met. | KIIs, presentations, attendance lists, post-training assessments |
| Indicator 2.2 - Reach of specific training on the monitoring, analysis and reporting arrangements (MARA) mechanism Baseline: 0 Planned Target: Relevant personnel is trained, meetings are held on a regular basis, and quarterly reports are prepared | The EU FPI-sponsored assistance helped 145 public sector specialists increase their capacities in CRSV case identification and registration in 2024. | The 2024 target was met. | KIIs, FGDs, presentations, post-training assessments |
| Output 2.1 - Stakeholders involved in the response to CRSV trained to develop and implement CRSV-related policies using a survivor-centred approach |  |  |  |
| Indicator 2.1.1 - Specialized information and training material for institutions working on CRSV cases and/or involved in service provision to survivors are developed (amended in August 2024) Baseline: 0 Planned Target: 2 | One set of training materials for institutions that work on CRSV cases was developed in 2024. | The 2024 target (adjusted) was met. | KIIs, training and other informational materials |
| Indicator 2.1.2 - Number of beneficiaries trained Baseline: 0 Planned Target: 231 | 62 MIA/NPU employees were trained in 2024. | The 2024 target (adjusted) was met. | Training agenda, attendance lists, post-training assessments |
| Indicator 2.1.3 - Number of trainings for institutions working on CRSV cases and/or involved in service provision to survivors conducted (added in August 2024) Baseline: 0 Planned Target: 11 | The CRSV JP sponsored two training events in 2024. | The 2024 target (adjusted) was met. | KIIs, training agendas, attendance lists, post-training assessments |
| Output 2.2 - All stakeholders involved in the monitoring, analysis and reporting are highly trained to ensure reliable data and information on CRSV |  |  |  |
| Indicator 2.2.1 – Structured presentations/workshop materials for stakeholders involved in the monitoring, analysis and reporting of CRSV cases are developed (amended in August 2024) Baseline: 0 Planned Target: 2 | One set of structured presentations/workshop materials for stakeholders involved in the monitoring, analysis and reporting of CRSV cases was developed in 2024. | The 2024 target (adjusted) was met. | Training and other informational materials |
| Indicator 2.2.2 - Number of beneficiaries trained Baseline: 0 Planned Target: 210 | 145 public sector specialists were trained in CRSV case identification and registration in 2024. | The 2024 target (adjusted) was met. | Training agenda, attendance lists, post-training assessments |
| Indicator 2.2.3 - Number of trainings for stakeholders involved in the monitoring, analysis and reporting of CRSV cases conducted (added in August 2024) Baseline: 0 Planned Target: 8 | Seven training events were conducted in 2024. | The 2024 target (adjusted) was met. | KIIs, training agenda, attendance lists, post-training assessments |
| Outcome 3 - Improved accessibility of services for (CRSV) survivors |  |  |  |
| Indicator 3.1 - Referral mechanism(s) for providing a coordinated and timely assistance to CRSV survivors are improved Baseline: availability of operating service providers is not clearly identified Planned Target: operating service providers (government-funded and non-government funded) are identified and continuously mapped | The EU FPI-sponsored assistance helped the GOU and other CRSV stakeholders assess the progress made in adaptation of the existing GBV referral mechanism to the CRSV-specific needs in 2024. | The 2024 target (adjusted) was met. | KIIs, FGDs, Assessment Report, Guidance Note(s), regulations |
| Indicator 3.2 - Percentage of actors reporting improved knowledge in working with CRSV cases/delivering services to CRSV survivors Baseline: insufficient level of qualifications of specialists working with CRSV survivors Planned Target: Based on questionnaires, over 80% of actors reached by the project’s trainings report improved knowledge as a result of trainings | Almost 100 Ukraine’s social service specialists improved their knowledge of CRSV case identification and registration in 2024. | The 2024 target (adjusted) was met. | KIIs, FGDs, training agendas, attendance lists, post-training assessments |
| Indicator 3.3 - Institutions working on CRSV cases/providing support to CRSV survivors report having enhanced capacity Baseline: Institutions that are authorised to work on CRSV cases and/or support CRSV survivors have very limited CSRV-specific capacity Planned Target: Institutions that received support within the Programme report having enhanced capacity | Institutions working on CRSV cases and/or providing support to CRSV survivors reported on enhancing their capacities in 2024. | The 2024 target (adjusted) was met. | KIIs, FGDs |
| Output 3.1 - All services available to CRSV survivors are identified and referral pathways are coordinated to connect CRSV survivors to appropriate, quality and multi-sectoral services |  |  |  |
| Indicator 3.1.1 - Number of beneficiaries trained (amended in August 2024) Baseline: 0 Planned Target: 200 | 96 people attended training sessions in interagency coordination designed to facilitate functional referrals in GBV/CRSV cases in 2024. | The 2024 target (adjusted) was met. | Training agendas, attendance lists, post-training assessments |
| Indicator 3.1.2 - Number of trainings using a certified training course on interagency coordination to facilitate functional referrals in GBV/CRSV cases (added in August 2024) Baseline: 0 Planned Target: 10 | Four training sessions were conducted in 2024. | The 2024 target (adjusted) was met. | KIIs, training agendas, attendance lists, post-training assessments |
| Indicator 3.1.3 - Number of field visits to CRSV survivor centres/service providers/other institutions working with CRSV cases (amended in August 2024) Baseline: 0 Planned Target: 5 | Eight field visits to CRSV survivor centres were conducted in 2024. | The 2024 target was exceeded. | Field visit reports |
| Indicator 3.1.4 - A standard process for monitoring and analysing the availability and capabilities of the existing support services is developed Baseline: 0 Planned Target: 1 | A standard process for monitoring and analysing the availability and capabilities of the existing support services is being developed. | A standard process for monitoring and analysing the availability and capabilities of the existing support services will be developed in … 2025. | KIIs, Guidance Note(s), regulations |
| Output 3.2 - All services available to CRSV survivors follow a standard procedure for ensuring the delivery needs-oriented assistance to CRSV survivors |  |  |  |
| Indicator 3.2.1 - Standard procedures for delivering needs-oriented assistance to CRSV survivors are developed (amended in August 2024) Baseline: 0 Planned Target: 2 | Standard procedures for delivering CRSV needs-oriented assistance to CRSV survivors are being developed. | Standard procedures for delivering CRSV needs-oriented assistance to CRSV survivors will be developed in … 2025. | KIIs, Guidance Note(s), regulations |
| Output 3.3 - Supporting institutions working on CRSV cases/providing support to CRSV survivors |  |  |  |
| Indicator 3.3.1 - Number of institutions working on CRSV cases/providing support to CRSV survivors receiving material and/or technical support to enhance their capacity (amended in August 2024) Baseline: 0 Planned Target: 5 | Most institutional needs were identified and procurement was initiated. | Material and/or technical (equipment) support will be provided in … 2025. | KIIs, invoices, property transfer documents |

iii) A Specific Story (Optional)

This could be a success or human story. It does not have to be a success story – often the most interesting and useful lessons learned are from experiences that have not worked. The point is to highlight a concrete example with a story that has been important to your Programme in the reporting period.

In ¼ to ½ a page, provide details on a specific achievement or lesson learned of the Programme. Attachment of supporting documents, including photos with captions, news items etc, is strongly encouraged. The MPTF Office will select stories and photos to feature in the Consolidated Annual Report, the GATEWAY and the MPTF Office Newsletter.

Problem / Challenge faced: Describe the specific problem or challenge faced by the subject of your story (this could be a problem experienced by an individual, community or government). Programme Interventions: How was the problem or challenged addressed through the Programme interventions? Result (if applicable): Describe the observable change that occurred so far as a result of the Programme interventions. For example, how did community lives change or how was the government better able to deal with the initial problem? Lessons Learned: What did you (and/or other partners) learn from this situation that has helped inform and/or improve Programme (or other) interventions?

III.	Other Assessments or Evaluations (if applicable)

•	Report on any assessments, evaluations or studies undertaken.

No specific assessments or evaluations were conducted during the reporting period except for UNFPA’s technical support provided to the GOU for assessing the range of and capacity to provide services to CRSV survivors. Results are expected in spring 2025.

IV.	Programmatic Revisions (if applicable)

•	Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place.

The JP Team proposes a four-month no-cost extension (NCE) of Ukraine CRSV JP. The FoC Implementation Plan on CRSV prevention and response – which the JP is intended to support – has been extended to December 2025 by the GOU. In order to ensure continuity of support to the GOU for the maximum duration possible, and following consultation with representatives of the DPM/EEAI Office, and of the GC/GEP Office, it is proposed to have a four-month NCE. All PUNOs have sufficient funds to cover an additional four-month period of CRSV JP expenses, calculating staff and national expert capacity until mid-September (3.5 months approximately), followed by a two-week period at the completion of the project for the convening and administrative agents to close the CRSV JP.

The four-month NCE will allow PUNOs to achieve all originally planned results, including promotion of amendments to Ukrainian legislation and institutional internal regulations, enhance GOU internal coordination, train at least 300 people and strengthen the use of CRSV survivor-centred approach and improvements in CRSV survivors' access to referral and protection services, modern CRSV monitoring and assessing tools, and reliable CRSV data collection and protection methods.

V. 	Resources (Optional)

•	Provide any information on financial management, procurement and human resources.

•	Indicate if the Programme mobilized any additional resources or interventions from other partners.

The term “programme” is used for programmes, joint programmes and projects.

Strategic Results, as formulated in the Strategic UN Planning Framework (e.g. UNDAF) or project document;

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as  “Project ID” on the project’s factsheet page the MPTF Office GATEWAY

The MPTF or JP Contribution, refers to the amount transferred to the Participating UN Organizations, which is available on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.