Multi-year Work Plan

year: 2024

| Expected Outputs | Planned Activities | Timeframe |  |  |  | Budget Estimate |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 1Q | 2Q | 3Q | 4 Q | Responsible Agency | Funding Source | Budget description | Amount (USD) |
| Output 1: Assistance in the implementation of the SDGs, improvement of financing issues to strengthen the financial basis of national development strategies in the context of the implementation of the SDGs provided. | 1.1 Assist in the preparation of drafts of periodic national reports on the progress of SDGs in Turkmenistan. |  |  |  |  | UNDP | Government of Turkmenistan | 71300 National expert (1 expert х 50 days) | 5,000 |
|  |  |  |  |  |  |  |  | 74200 Translation/ interpretation services | 1,100 |
|  | 1.2 Provide support in the development of the key directions of the national finance strategy. Provide consultations on the study of international experience in the development of a financing strategy and the implementation of the INFF. |  |  |  |  | UNDP | Government of Turkmenistan | 71200 International expert (1 expert х 15 days) | 9,000 |
|  |  |  |  |  |  |  |  | 71600 Transportation costs (1 expert х 1 trip х 5 days) | 2,481 |
|  |  |  |  |  |  |  |  | 71300 National expert (1 expert х 60 days) | 6,000 |
|  |  |  |  |  |  |  |  | 75700 Seminar/workshop | 1,085 |
|  |  |  |  |  |  |  |  | 74500 Operational costs | 1,107 |
|  | Sub-total for Output 1 |  |  |  |  |  |  |  | 25,773 |
|  | GMS (General management support – Administrative costs) 7% |  |  |  |  |  | Government of Turkmenistan | 75100 GMS | 1,804 |
|  | Total for the Output 1, including 7% GMS |  |  |  |  |  |  |  | 27,577 |
| Output 2: National capacity for WTO accession enhanced. | 2.1 Development of a draft regulatory act on internal regulation in the field of services and investments, defining the basic principles and conditions for the implementation of regulatory activities in accordance with the obligations under the GATS. |  |  |  |  |  | Government of Turkmenistan | 71200 International expert (1 expert х 20 days) | 12,000 |
|  |  |  |  |  |  |  |  | 71300 National consultant (1 consultant х 50 days) | 5,000 |
|  |  |  |  |  |  |  |  | 74200 Translation/ interpretation services | 330 |
|  |  |  |  |  |  |  | Government of Turkmenistan | 74500 Operational costs | 539 |
|  | Sub-total for Output 2 |  |  |  |  |  |  |  | 17,869 |
|  | GMS (General Management Support) 7% |  |  |  |  |  |  | 75100 GMS | 1,251 |
|  | Total for the Output 2, including GMS 7% |  |  |  |  |  |  |  | 19,120 |
| PROJECT MANAGEMENT | Salary for the Project staff |  |  |  |  | UNDP | Government of Turkmenistan | 71400 Salary (Project Manager 50%) | 6,666 |
|  |  |  |  |  |  |  | UNDP | 71400 Salary (Project Manager) | 7,500 |
|  |  |  |  |  |  |  | Unfunded funds |  | 16,000 |
|  |  |  |  |  |  |  | Government of Turkmenistan | 71400 Salary (Project Assistant - 35%) | 6,300 |
|  | Office expenses |  |  |  |  |  | Government of Turkmenistan | 72500 Office supplies | 350 |
|  |  |  |  |  |  |  |  | 72400 Communications and Internet | 1,056 |
|  |  |  |  |  |  |  |  | 74500 Operational costs | 770 |
|  | Sub-total for project management Government of Turkmenistan |  |  |  |  |  | Government of Turkmenistan |  | 15,142 |
|  | GMS (General Management Support) 7% |  |  |  |  |  | Government of Turkmenistan | 75100 GMS | 1,060 |
|  | Total for Project management (Government of Turkmenistan including GMS) |  |  |  |  |  | Government of Turkmenistan |  | 16,202 |
|  | Sub-total for project management UNDP |  |  |  |  |  | UNDP |  | 7,500 |
| TOTAL FOR THE PROJECT, 2024 Government of Turkmenistan, including GMS (General Management Support), 7%: |  |  |  |  |  |  |  |  | 62,899 |
| TOTAL FOR THE PROJECT, 2024, UNDP |  |  |  |  |  |  |  |  | 7,500 |
| UNFUNDED FUNDS, 2024 |  |  |  |  |  |  |  |  | 16,000 |
| GRAND TOTAL FOR THE PROJECT, 2024 |  |  |  |  |  |  |  |  | 86,399 |