Annual Work Plan

YEAR: 2025

| Expected Outputs | Planned Activities | Timeframe |  |  |  | Budget Estimate |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 1Q | 2Q | 3Q | 4Q | Responsible Agency | Funding Source | Budget description | Amount (USD) |
| Output 1: Assistance provided in the implementation of the SDGs, improvement of financing issues to strengthen the financial basis of national development strategies in the context of the implementation of the SDGs. Gender Marker: 2 | 1.1 Assist in the preparation of drafts of periodic national reports on the progress of SDG achievements in Turkmenistan. |  |  |  |  | UNDP | Government of Turkmenistan | 71300 National expert (1 expert х 55 days) | 5,500 |
|  |  |  |  |  |  |  |  | 74200 Translation/ interpretation services | 1,100 |
|  | 1.3 Provide consultations on the localization of SDGs with piloting in the new smart city of Arkadag. |  |  |  |  | UNDP | Government of Turkmenistan | 71200 International expert (1 expert х 15 days) | 9,000 |
|  |  |  |  |  |  |  |  | 71600 Transportation costs (1 expert х 1 trip х 4 days) | 2,481 |
|  |  |  |  |  |  |  |  | 75700 Seminar/workshop | 1,085 |
|  | 1.4 Organization of training visits to study the best practices of countries on the implementation of the INFF and SDGs in national financial plans and programmes. |  |  |  |  | UNDP | Government of Turkmenistan | 71600 – per diem (4 people х 7 days) | *At the expense of the national partner |
|  |  |  |  |  |  |  | Government of Turkmenistan | 74500 Operational costs | 748 |
|  | Sub-total for Output 1 |  |  |  |  |  |  |  | 19,914 |
|  | GMS (General Management Support) 7% |  |  |  |  |  | Government of Turkmenistan | 75100 GMS | 1,394 |
|  | Total for the Output 1, including 7% GMS |  |  |  |  |  |  |  | 21,308 |  |
| Output 2: National capacity for WTO accession enhanced. | 2.2. Preparation of a draft list of obligations for access to the banking, financial and other services market. |  |  |  |  | UNDP | Government of Turkmenistan | 71200 International expert (1 expert х 25 days) | 15,000 |
|  |  |  |  |  |  |  |  | 71300 National consultant (1 consultant х 30 days) | 3,000 |
|  |  |  |  |  |  |  |  | 74200 Translation costs | 330 |
|  | 2.3 Analysis of the Tax Code and preparation of proposals to bring it into line with the provisions of the WTO agreements |  |  |  |  |  | Government of Turkmenistan | 71200 International expert (1 expert х 15 days) | 9,000 |
|  |  |  |  |  |  |  |  | 71300 National consultant (1 consultant х 30 days) | 3,000 |
|  |  |  |  |  |  |  |  | 74200 Translation costs | 330 |
|  |  |  |  |  |  |  | Government of Turkmenistan | 74500 Operational costs | 643 |
|  | Sub-total for Output 2 |  |  |  |  |  |  |  | 31,303 |
|  | GMS (General Management Support) 7% |  |  |  |  |  | Government of Turkmenistan | 75100 Services and Administration | 2,191 |
|  | Total for the Output 2, including 7% GMS |  |  |  |  |  |  |  | 33,494 |  |
| PROJECT MANAGEMENT | Salary for the Project staff |  |  |  |  | UNDP | Government of Turkmenistan | 71400 Salary (Project Manager, 50%) | 6,666 |
|  |  |  |  |  |  |  | UNDP | 71400 Salary (Project Manager) | 7,500 |
|  |  |  |  |  |  |  | Unfunded funds |  | 16,000 |
|  |  |  |  |  |  |  | Government of Turkmenistan | 71400 Salary (Project Assistant, 35) | 6,300 |
|  | Office expenses |  |  |  |  | UNDP | Government of Turkmenistan | 72500 Office supplies | 350 |
|  |  |  |  |  |  |  |  | 72400 Communications and Internet | 1,056 |
|  |  |  |  |  |  |  |  | 74500 Operational costs | 487 |
|  | Sub-total for the Project management, Government of Turkmenistan |  |  |  |  |  | Government of Turkmenistan |  | 14,859 |
|  | GMS (General Management Support) 7% |  |  |  |  |  | Government of Turkmenistan | 75100 GMS | 1,040 |
|  | Total for the Project management Government of Turkmenistan, including GMS |  |  |  |  |  | Government of Turkmenistan |  | 15,899 |
|  | Sub-total for the Project management, UNDP |  |  |  |  |  | UNDP |  | 7,500 |
| TOTAL FOR THE PROJECT, 2025, Government of Turkmenistan, including GMS (General Management Support), 7%: |  |  |  |  |  |  |  |  | 70,701 |
| TOTAL FOR THE PROJECT, 2025, UNDP |  |  |  |  |  |  |  |  | 7,500 |
| UNFUNDED FUNDS, 2025 |  |  |  |  |  |  |  |  | 16,000 |
| TOTAL FOR THE PROJECT, 2025 |  |  |  |  |  |  |  |  | 94,201 |