Minutes

of the Project Board meetings of the joint project between Ministry of Finance and Economy of Turkmenistan and UNDP in Turkmenistan "Partnering for SDG acceleration, phase III "

Project: TKM-01002070 "Partnering for SDG acceleration, phase III "

Venue: Building of the Ministry of Finance and Economy of Turkmenistan

Date of the event: February 12, 2025

Time: 16:00-17:00

List of participants:

From the Ministry of Finance and Economy of Turkmenistan:

- Mr. Mammetguly Astanagulov , Minister;

- Ms. Galina Romanova, Head of the Consolidated Directorate of Public Finance and Economic Policy;

- Mr. Maksat Kutlymuradov, Head of the International Department of the Consolidated Directorate of Public Finance and Economic Policy;

- Mr. Orazmukhammet Ashirov, Acting Head of the Department of Strategic and Sustainable Development;

- Mr. Begench Durdymuradov, Acting Head of the International Department of the Consolidated Directorate of Public Finance and Economic Policy;

- Mr. Shamurad Meredov, Deputy Head of the Department of Cooperation with the WTO;

- Ms. Elita Shumskaya, Chief Specialist of the Department of Strategic and Sustainable Development;

- Mrs. Kumush Soltanova , chief specialist of the international department of the Consolidated Directorate of Public Finance and Economic Policy.

From UNDP:

- Ms. Narine Saakyan, UNDP Resident Representative in Turkmenistan.

- Mrs. Gulalek Volmamedova, Program Analyst on Democratic Governance, Economic Diversification and Inclusive Growth.

- Ms. Irina Gukasova , Project Coordinator .

Agendas:

- Welcome words, objectives of the meeting.

- Summing up the results of the project work for 2024.

- Discussion of project activities planned for 2025 and agreement on the annual work plan for 2025.

- Summing up the meeting and agreeing on further steps.

1. Welcome words. Objectives of the meeting.

Mr. Mammetguly Astanagulov warmly welcomed the participants of the Project Council meeting and informed about the active cooperation between Turkmenistan and UNDP, including within the framework of the implementation of the first and second phases of the joint project between UNDP and the Ministry of Finance and Economy of Turkmenistan "Platform for the Implementation of SDGs", as well as the UNDP Country Program for Sustainable Development for the period 2021-2025. He noted that achieving the SDGs is one of the important priorities of socio-economic development for Turkmenistan, aimed at ensuring economic growth and improving the well-being of the population, and certain progress has been achieved in this direction.

This project is of great importance in the implementation of the Global Agenda for Sustainable Development until 2023 adopted by Turkmenistan, as it is aimed at increasing the potential of the Ministry of Finance and Economy of Turkmenistan, which coordinates activities to implement the SDGs in the country. and other ministries and departments of the country. An important part of this project is to increase the potential and develop strategic approaches to Turkmenistan's accession to the WTO.

Ms. Narine Sahakyan expressed gratitude to the Ministry for the effective partnership in the implementation of this project. She noted that in 2024-2025, UNDP managed to mobilize additional funding for the implementation of activities on Turkmenistan's accession to the WTO , which were prepared in 2024 and implemented in January 2025 as part of the 2025 action plan. At the same time, in 2024, international experts were attracted under the Russian Experts for International Development Program, within the framework of the partnership between UNDP and the Russian Federation. This, in turn, made it possible to free up certain financial resources planned for 2024 and 2025, which will help expand the range of project activities. It was also noted that as part of the 2025 activities, it is planned to organize a study visit, at the expense of the national partner, to one of the countries to study best practices in the implementation, coordination, financing of the SDGs, monitoring of statistical reporting on SDG indicators. In conclusion, Ms. N. Saakyan expressed gratitude for the opportunity provided by UNDP to participate as a partner of the Ministry in achieving the SDGs for the sustainable economic growth of the country. The readiness to continue to support the sustainable development of Turkmenistan in various areas was also confirmed.

2. Summing up the results of the project work for 2024.

Mrs. Irina Gukasova presented a report on the results of the activities carried out under the project for 2024.

Under component 1, a draft periodic national report on progress in achieving the SDGs in Turkmenistan for the period 2015-2023 was prepared, which was also translated into Turkmen. The report was sent to the Ministry of Finance and Economy of Turkmenistan (Note No. 1254 dated November 14, 2024). A webinar was held with the participation of an international expert and national partners on the possibility of introducing SDG-based budgeting. Work is also underway to prepare a methodology for labeling the budget classification using the UNDP rapid integrated assessment methodology to carry out further work on the implementation of Integrated National Financing Frameworks (INFF).

Under component 2, a report was prepared on “Measures to Bring Turkmenistan’s Legislation into Line with the Provisions of the WTO General Agreement on Trade in Services (GATS) and the Joint Initiative on Domestic Regulation in Services”, as well as a draft amendment to the Laws of Turkmenistan “On Licensing of Certain Types of Activities” and “On Legal Acts” Concerning WTO Domestic Regulation Disciplines. The report was sent to the Ministry of Finance and Economy of Turkmenistan (Note No. 758 dated July 19, 2024).

In addition to the planned activities under Component 2, an international expert was hired within the framework of the Russian Experts for International Development program, who conducted a webinar for national partners on the topic of “Ways to protect the services market in the context of trade liberalization within the WTO (using financial services as an example).”

It was noted that at the end of 2024, there remained an unutilized amount of financial resources for Component 2 and Project Management, totaling $ 22,796.97 (preliminary data), due to the provision of additional financial resources from UNDP sources.

Discussion of the action plan for 2025.

Ms. Irina Gukasova presented the Action Plan for 2025, which includes the following steps:

For component 1 :

  - Help in the preparation of a draft periodic national report on progress in achieving the SDGs in Turkmenistan for the period 2015-2024 and translate it into the Turkmen language.

  - Provide advice on SDG localization issues, including the preparation of a SDG localization methodology, a methodology for conducting a Regional Financing Assessment, and recommendations for integrating SDG targets and indicators at the regional level.

  - A study visit to the Republic of Belarus is planned to study the country's best practices in the implementation, coordination, financing of the SDGs, monitoring statistical reporting on SDG indicators. According to the project document, the event is to be covered by the financial resources of the national partner.

Budget 2025 for 1 component – $21,308.00.

For component 2:

2.2 Preparation of a draft list of obligations for access to the market of banking, financial and other services.

2.3 Conducting an analysis of the tax code and preparing proposals to bring it into line with the provisions of the WTO agreements

2025 Budget for Component 2 - $33,494.00.

It was noted that because of additional funding allocated by UNDP, the activities planned for 2025 under Component 2 aimed at increasing national capacity on issues of Turkmenistan's accession to the WTO were completed in January 2025. As a result, under Component 2 of the 2025 plan, an unused amount of $30,660 was accumulated.

Ms. Galina Romanova noted that the Project is relevant. Over the past period, a huge amount of work has been done, based on the results of which two Voluntary National Reviews of Turkmenistan have been prepared, support is provided in the preparation of annual national reviews on the progress of achieving the SDGs in Turkmenistan, in certain areas related to the process of Turkmenistan's accession to the WTO.

It was noted that due to the fact that additional financial resources attracted by UNDP have appeared, it is necessary to reflect them in detail in the submitted financial reports on the project. It was proposed to work out in a working order together with the specialists of the Ministry responsible for the area of activity related to the implementation of components 1 and 2, a list of additional activities that will need to be implemented during 2025. In conclusion of her speech, she expressed gratitude to the UN Development Program and personally to Ms. Narine Sahakyan for fruitful cooperation and proposed to continue the activities planned by the project. The Ministry will provide any assistance in all areas of the project. In addition, given that phase III is completed this year, it was recommended to consider the possibility of extending the project - preparing a project document for phase IV, in order to continue work on the implementation of the SDGs and the preparation of the next National Voluntary Report. Turkmenistan.

4. Summing up the meeting and agreeing on further steps.

- Taking into account the proposals of the members of the Project Council, an updated report on the financial costs of the project for 2024 should be submitted, as well as an updated version of the activities for 2025 on the activities completed in 2025. Send them officially through diplomatic channels to the Ministry of Finance and Economy of Turkmenistan.

- Conduct a budget audit based on the 2025 plan and the expenditures of the reporting year, and transfer unused budget funds to 2025.

- Prepare an Annual Work Plan (with adjustments) within the framework of the approved plan for 2025, taking into account the supplemented activities, including organizing a familiarization visit using unused funds.