| 2024 Annual Progress Report | Strengthening Capacities of the National Police of Ukraine on Reunification of Families in Ukraine |  |
| --- | --- | --- |
|  |  | ## Date: 31 December 2024 |

| Does this status report contain any information requiring specific decisions? (e.g. changes in the project’s objectives, expected output or budgets?) | No | In which point is it described? |  |
| --- | --- | --- | --- |
| 1. File no. | 403.Ukraine.1-28 |  |  |
| 2. Contact person and email | Ms Svitlana Kolyshko – Human Rights and Access to Justice Project Manager (svitlana.kolyshko@undp.org) United Nations Development Programme in Ukraine |  |  |
| 3. Programme title | Strengthening Capacities of the National Police of Ukraine on Reunification of Families in Ukraine |  |  |
| 4. Total budget USD? and accumulated expenditure by the end of reporting period. | Budget 2024-2025: USD – 2,366,558.78 Expenditures during reporting period: USD 158,163.18 (without commitments) *As per 31 December 2024 |  |  |
| - 6. Programme period |  |  |  |
| Start (day/month/year) 1 of February 2024 | Completion (day/month/year) 31 December 2025 |  |  |
| 7. Reporting period |  |  |  |
| From (day/month/year) 1 February 2024 | To (day/month/year) 31 December 2024 |  |  |
| 8. Monitoring and reviews Give an account of the main monitoring activities during the period, e.g. steering committee meetings, visits, reviews etc. (in bullet points) LPAC meeting 13 August 2024 (in the form of e-mail exchange) |  |  |  |
| 9. Assessment of external context, assumptions and risks relevant to the Programme A brief description of the national context that is relevant for the Programme. Key contextual changes and considerations The end of February 2024 marked two years since the full-scale invasion by the Russian Federation of Ukraine, and ten years since the beginning of its occupation of the Autonomous Republic of Crimea. The aftermath of February 2022 continues to be the biggest challenge to global order and peace, as well as to the national human rights agenda. The war has continued to cause widespread destruction throughout 2024, destroying lives and livelihoods, further decimating essential services, and compounding an already grave humanitarian crisis. Overview of the context Since the full-scale invasion of Ukraine by the Russian Federation on February 24, 2022, numerous reports have documented war crimes, crimes against humanity, and other serious violations of international humanitarian law and human rights law. The aggression has particularly affected children, causing mass displacement, killings, and destruction of essential infrastructure, including homes, schools, and hospitals. The Russian Federation’s actions have severely undermined the rights of children as defined by the Convention on the Rights of the Child. The occupation of Ukrainian territories, initiated in 2014 with the annexation of Crimea, escalated significantly in 2022, involving the occupation of parts of Donetsk, Luhansk, Zaporizhzhia, Kharkiv, and Kherson regions, as well as the Autonomous Republic of Crimea. As of February 2024, approximately 26% of Ukraine’s territory remains under temporary occupation. These areas are home to approximately 1.6 million children, who face heightened risks due to limited access and the lack of reliable information about their circumstances. The UN Committee on the Rights of the Child has expressed grave concerns about the impact of the armed conflict on children in Ukraine. There are credible reports of gross violations of children’s rights, including forced displacement, killings, and abductions. Almost 20,000 children from occupied territories have been transferred to Russia or territories under Russian control. These children are subjected to political re-education in camps and have, in some cases, been placed with Russian families for “foster care” or adoption. Forced separation from their families results in severe trauma and long-term harm to their mental and physical health. To address these challenges, the Ukrainian government has launched several initiatives: - Children of the War Platform: This unified platform collects data on children affected by the war, including those killed, injured, missing, or deported. It facilitates the documentation of war crimes committed against children. - Unified Register of Deported and Displaced Persons: Established under Cabinet Resolution No. 339 (April 2023), this register consolidates information on all individuals, including children, who have been deported or forcibly displaced due to Russian aggression. Data is collected from various government bodies and local authorities. - National Registry of Information on Deported Children will be established according to law that was signed by President Zelenskyy in December 2024, this registry documents violations of children’s rights, including deportations and forced transfers. It serves as a secure platform for coordinating with international organizations to locate and reunite children with their families. Moreover, the international community took a proactive position in providing support to the Ukrainian effort to return children. International Coalition for the Return of Ukrainian Children was established in 2023 and it works within President Zelenskyy’s Peace Formula to facilitate the return of abducted children. By October 2024 41 countries have joined the Coalition to provide support through advocacy, documentation, and rehabilitation efforts. The coalition operates as a platform for coordinated international action, emphasizing the need for global solidarity in addressing the unlawful deportation and forced displacement of Ukrainian children. The third plenary meeting of the Coalition held in October 2024, co-chaired by Ukraine and Canada, highlighted achievements and ongoing projects, reaffirming the global commitment to returning every Ukrainian child to their homeland. As a result of these efforts in 2024, 449 children were successfully repatriated to Ukraine. In this regard, establishment of the robust frameworks remain to be an important goal for further reunification Ukrainian children with their families in both short-term and long-term perspectives, while creation of a DNA database is pivotal to these efforts. |  |  |
| - Developments concerning important assumptions and risk While no new risks have been identified in the reporting period, some risks have changed and require revision of the initial risk management strategy. For a detailed risk matrix please see Annex C. |  |  |

10. Status – Contribution to the Programme’s outcome objectives Give an account of selected contributions to the Programme’s objectives and indicators. Project Outcome: The project has successfully built a strong foundation for the National Police of Ukraine (NPU) to apply DNA identification techniques for family reunification, particularly through the capacity development of the forensic experts. As a result, relevant expertise is now present in every oblast of Ukraine, ensuring that qualified forensic investigators are now operating across the country and ready to apply new DNA identification equipment. This widespread capacity enables the NPU to apply DNA identification methods on a larger scale and across more regions, enhancing the ability to reunify children with their families in a timely and effective manner. The expertise, developed through the UNDP-conducted training sessions, provides the NPU with a solid base to implement DNA-based identification practices in the future. While significant progress has been made in building technical expertise and laying the groundwork for genomic data systems, the next step in 2025 will involve equipping the NPU with the necessary hardware, such as DNA storage solutions and servers, and continuing the development of the genomic database system. These steps will be essential in creating a comprehensive, sustainable system capable of supporting large-scale family reunification efforts using DNA identification methods. In the reporting period project team agreed with NPU the list of the equipment and conducted relevant procurement processes to ensure delivery of the equipment in 2025. 11. Status – programme outputs Please refer to Annex B: Status in Logical Framework for detailed indicator implementation Output 1. The National Police is equipped with enhanced technical infrastructure for DNA identification. To address the NPU request for adjustments to the UFRI project, UNDP carried out a series of negotiations and technical discussions aimed at developing a solution acceptable to all stakeholders. These efforts focused on revising the equipment list and delivery schedule to better meet the operational and procedural needs of the NPU. Through detailed exchanges of positions, the project team worked closely with the NPU to identify specific issues and formulate practical solutions. The discussions revealed several challenges, including the short six-month expiration period for DNA testing chips, which required a more realistic, staggered delivery schedule. Additionally, the procedural nature of DNA sample collection, which involves obtaining consent from relatives during the identification and investigation process, highlighted the need for a flexible approach. At the time of negotiations, the NPU initiated efforts to engage families and gather consent but did not yet have a substantial pool of individuals ready to provide samples. To address these challenges, the NPU proposed modifications to the project, including increasing the number of A-type chips for broader sampling capabilities, procuring DNA storage solutions with a 10-year expiration period, and extending the project timeline by the end of 2025. Based on these consultations, the Project Document was updated to accommodate the proposed changes, including revisions to the budget and project framework. These amendments were presented and approved by both the donor and the NPU during the LPAC meeting in August 2024. In implementation, all Terms of Reference for the revised equipment were prepared and agreed upon with the NPU. Subsequently, procurement processes were finalized and contracts signed to ensure timely project delivery during the next reporting period. Output 2. The National Police is capable to apply new approaches of DNA identification and data collection: Forensic experts increased their skills in applying mobile DNA identification methods and ready for the practical application in frame of UFRI. In September and October 2024, a series of training sessions on high-speed DNA profiling were delivered to 60 forensic investigators of the National Police of Ukraine. These sessions, supported by UNDP and funded by the Government of the Netherlands, aimed at enhancing the technical expertise and operational capacities of the National Police in utilizing advanced DNA identification techniques for family reunification efforts. The training sessions were conducted in two phases: - The first session trained 27 forensic investigators. - The second session trained another 33 participants. Participants gained hands-on knowledge of innovative DNA profiling technologies, which enable the rapid creation of genetic profiles and the identification of familial relationships within minutes. These techniques are critical in locating missing persons and facilitating family reunifications during wartime. Moreover in frame of training forensic experts had an opportunity to exchange their practices and knowledge that differs in every region depending on specific context. To ensure interagency cooperation representatives of other relevant expert institutions joined the training, namely expert service under the Ministry of Internal Affairs, Ministry of Justice and Ministry of Health. Such approach is aimed to establish coherent approaches in work of different forensic and expert institutions involved in the initiative. Needs of the NPU regarding databases and verification systems of human genomic information were clarified. In the reporting period project team conducted multiple meetings and consultations with the NPU technical experts to identify specific needs for building a genomic information database. In frame of the discussion it was identified that there are several already existing international software products for potential adoption, including: - Bonaparte: Used by Interpol’s I-Familia service for familial searches. - CODIS: The DNA database system maintained by the U.S. Federal Bureau of Investigation. - iDMS: Developed and used by the International Commission on Missing Persons. - FAIRS: A familial search product by ANDE, with limitations in its graphical interface for family relationships. At the same time, all the existing software are not fully relevant to the needs of family reunification initiative. As well based on the experience of UNDP in development of software and digitalization of registers for the Government the process of approval and certification is complicated and can take more than one year. As a result of the discussion and conducted assessment of the potential software options the NPU considered to prioritize development of its own system using existing software as a foundation. Challenges and next steps: - The next steps for the project involve organizing a handover ceremony for the donation of 1500 ANDE chips to the National Police of Ukraine (NPU), with an additional 3000 chips to be delivered by July 2025. This donation is a key milestone in the UNDP project, aimed at enhancing the NPU's capacity to conduct DNA forensic investigations for war crimes and family reunification. The ceremony will include branding with UNDP and Netherlands logos on the DNA chip boxes, as well as a press wall and roll-up banners at the venue. A comprehensive communications package will be prepared, including a press release and social media posts. Media presence will be arranged in accordance with the security requirements of the NPU. The event will highlight the significance of the donation and its role in strengthening Ukraine’s forensic and family reunification efforts. - Based on conducted assessment development of the new modules of the existing software and ensure its functionality requires additional computing resources to handle the processing and storage demands of genomic data. Considering this NPU requested the project to support in provision of relevant equipment. Addressing the request of the NPU on creation of database will require revision of the initially planed activities, namely analysis of the existing international practices, and approval of these changes with the donor. Based on the preliminary market research relevant equipment can be procured in frame of the existing budget allocations. - Raising awareness component of the project was postponed in the reporting period due to revision of the delivery schedule under Output 1 and absence of the clear vision regarding support of the project to ensure relevant visibility and raising awareness of the initiative. Currently, there is limited understanding among the public about their ability to approach the police, provide DNA samples, and contribute to family reunification efforts. In this regard project team is going to conduct additional consultations with the communication experts of NPU and identify priorities in developing a strategy aimed at raising public awareness about the DNA identification initiative.

12. Deviations from planning in the original programme document Give an account of significant differences in implementation compared with the approved project document. During the reporting period, adjustments were made to the project in response to a formal request from the National Police of Ukraine (NPU) to revise the list of equipment and delivery schedule. These changes stemmed from the NPU's assessment of their existing capabilities and evolving needs. Technical discussions and official exchanges between UNDP and the NPU revealed several critical considerations: - Expiration of Chips: DNA chips have a limited expiration period of six months, necessitating a staggered delivery schedule to ensure timely utilization. - Procedural Complexity: The DNA sample collection process is tied to ongoing investigations and requires informed consent from families, which involves advocacy, identification, and legal procedures. Currently, there is no backlog of individuals ready for immediate DNA sample collection. To address these concerns, the following modifications were agreed upon and endorsed during the LPAC meeting in August: (i) adjusting the list of equipment for the NPU, (ii) extending the project timeline until the end of 2025 to enable phased and realistic delivery of chips, aligned with the procedural requirements for consent and identification. The project was subsequently extended, and the Project Document was amended to reflect these updates, ensuring that the revised approach aligns with the NPU’s operational and procedural needs while maintaining the overall objectives of the initiative.

13. Sustainability and exit strategy The sustainability of the project is embedded in its core design, ensuring that the results and impacts extend well beyond its implementation period. The project prioritizes strengthening the institutional and technical capacities of the National Police of Ukraine's forensic units to ensure long-term resilience and self-reliance. By focusing on training and capacity development, the project ensures that the skills and expertise developed among forensic experts will remain a critical asset for Ukraine's justice and accountability efforts. To date, 60 forensic experts (both male and female) have been trained in the use of innovative methods for rapid DNA profiling during two comprehensive training sessions in September and October 2024. This cohort of skilled professionals forms the foundation for sustained improvements in forensic investigations, contributing directly to justice for war-affected communities. The project also will enhance technical capacity by equipping forensic units with state-of-the-art tools and consumables, enabling them to operate with greater efficiency and accuracy. These investments in infrastructure will provide lasting value, supporting the National Police in fulfilling their mandate effectively. To ensure further sustainability, the project includes awareness-raising activities to inform the public about the enhanced forensic capabilities. Increasing awareness among beneficiaries will promote trust in the forensic process, fostering community engagement and ensuring that the strengthened system remains relevant and responsive to the needs of the people.

14. HRBA and Gender equality The project has been fully aligned with the principles of Human Rights-Based Approach (HRBA) and gender equality. Throughout its implementation, special attention was given to ensuring equal participation of women in all project activities. For example, during the training sessions for forensic investigators on DNA identification techniques, at least 30% of participants were female experts, ensuring gender balance in the development of technical capacities. This approach fosters equal opportunities for both male and female experts to enhance their skills and contribute to the project’s objectives. Additionally, the project's emphasis on family reunification, particularly for children and war-affected individuals, inherently supports the rights of all individuals, regardless of gender, by facilitating access to justice and addressing the urgent humanitarian needs of those affected by the ongoing conflict. The integration of gender-sensitive practices into the project ensures that both women and men are empowered to contribute to the successful implementation of DNA identification and reunification efforts.

15. 'Added Value' and Advisory from contract partners Provide examples of how the contract partners have provided "added value" to their partner(s) To be reported at project completion.

16. Lessons learned Through numerous discussions and consultations, the project managed to address operational challenges and adapt the project plans to the NPU’s evolving needs. Flexibility in adjusting the equipment list, delivery schedule, and project timeline based on NPU feedback was essential, particularly in response to issues like the short expiration period for DNA chips and the procedural nature of DNA sample collection. This proactive, solution-oriented approach allowed us to revise the project plan effectively, ensuring better alignment with the NPU’s requirements and ensuring the project's success. Using this approach the project underscored the critical importance of flexibility in addressing the evolving needs of beneficiaries, particularly in the dynamic context of war. The adjustments made during the reporting period highlighted two interrelated aspects of this lesson: - Flexibility to Address Real Needs: The ability to adapt project activities and resources to the actual requirements of the National Police of Ukraine ensured the relevance and effectiveness of the initiative. By revising the equipment list and delivery schedule in response to beneficiary feedback, the project avoided redundancies and aligned its support with the operational priorities of the NPU. - Adaptability to Rapid Contextual Changes: The war-driven environment necessitates agility in project planning and implementation. As circumstances and priorities shift quickly, flexibility becomes essential to respond promptly and ensure that interventions remain impactful and relevant. The rapid revision of project timelines and resource allocation in response to emerging needs exemplified this adaptability. Together, these insights emphasize that maintaining a responsive and adaptable approach is vital for achieving project objectives in a fluid and complex operational environment.

17. Comments on the financial reporting Please refer to Annex A: Financial status. Project expenses in the reporting period constituted: USD 158,163.18 * *As per 31 December 2024, without commitments under contracts that will be implemented in 2025

Annexes

Annex A. Financial status Annex B: Status in Logical Framework Annex C. Risk Analysis

Annex B: Status in Logical Framework

| EXPECTED OUTPUTS | OUTPUT INDICATORS | BASELINE | Target |  | ## Result | ## comments |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2024 | 2025 |  |  |
| Output 1 The National Police is equipped with enhanced technical infrastructure for DNA identification.. | - Number of DNA consumables delivered | 0 | n/a | ANDE I-chip – 600 ANDE A-chip – 200 ANDE Swabs - 3700 | n/a | Based on the request of the National Police of Ukraine (NPU) dated August 20, 2024, for consumables for mobile laboratories and devices (systems) for the collection and storage of biological material samples (human buccal epithelium) DNA, UNDP finalized the procurement tender procedure and concluded contracts for the supply of the respective consumables, with delivery scheduled for 2025 |
| Output 2. The National Police is capable to apply new approaches of DNA identification and data collection | 2.1 Number of trained forensic experts | 0 | 50 (at least 30% women) | 0 | 60 (37 male, 23 female) | During September and October, as part of two training sessions, 60 forensic experts (male and female) were trained in the use of innovative methods for rapid DNA profiling. The first training session trained 27 forensic experts, while the second trained 33 experts |
|  | 2.2. Number of people covered by communication campaign | 0 | 0 | 100000 | 0 | Discussion of modalities of communication support is in progress |

Annex 3. Risk Analysis

| # | Event | Risk Valid From - To | Type | Causes | Impacts & Probability | Treatments and Expected effect from treatment | Owner | Last Update | Status and Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Further deterioration of the security situation in Ukraine | January 2024 - December 2025 (end of the Project) | Safety and Security | Increased hostilities resulting in further escalation of the ongoing war in Ukraine, including in Project locations | The following potential instances of impact are envisioned under this risk: (1) enhanced security restrictions, that may weaken staff movement, mobility, and holding direct consultations with stakeholders/partners. These restrictions may lead to a reduced geographical coverage of the project and potential delays in data collection, hindering the achievement of project goals. (2) potential risk of injury, persecution or detention to project staff, contractors, partners, or beneficiaries impacting partners’ ability and commitment to execute activities In overall, the risk might result in delaying some activities and/or results, while also raising the relevance of the Project interventions. P = 3; I = 4 | UNDP will work in close coordination with UNDSS and the national government while ensuring the involvement of local authorities to secure a safe environment for the implementation of the project’s activities and working with implementing partners with good knowledge of the local context and effective presence on the ground. Project activities will take into account security situation in Ukraine and the necessary revisions will be made to ensure that project activities continue to the extent possible. Scale down of project activities in affected areas until acceptable level of stability is restored. | Project manager | December 2024 | No change the treatment doesn’t require modifications |
| 2 | Service interruptions | May 2024 - December 2025 (end of the Project) | Operational | Due to commodity shortages, stockouts, or failure to attract quality suppliers for UNDP procurement cases the might be delays in delivery of equipment. This risk also includes the possibility of substandard quality of deliverables produced by service providers | As a result of inadequate procurement planning, complex and lengthy procurement processes, and suppliers that fail to deliver on quality or meet deadlines. The risk may also be triggered by factors such as inflation and currency exchange rate fluctuations, as well as logistical challenges in highly dangerous implementation environment in Ukraine. Which will impact in delays in the delivery or installation of procured equipment or other deliverables, causing a slowdown in project activities and requiring revisions to the initial timeframes for more than one month. Moreover, it may lead to a failure to achieve the project's expected results, pose reputation risks, and potentially result in budgetary constraints. P = 3; I = 3 | to the extent possible the project will use LTAs and providers of goods and services that already proved to be reliable | Project manager | December2024 | No change the treatment doesn’t require modifications |

According to the Ombudsperson’s special Report on children rights chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://www.ombudsman.gov.ua/storage/app/media/uploaded-files/Special%20Report%20_CROSS-POLLINATED_.pdf

https://www.bringkidsback.org.ua/

https://childrenofwar.gov.ua/en/about-us/

https://www.kmu.gov.ua/npas/deiaki-pytannia-zakhystu-osib-u-tomu-chysli-ditei-deportovanykh-abo-prymusovo-peremishchenykh-u-zviazku-iz-zbroinoiu-ahresiieiu-rosiiskoi-federatsii-proty-ukrainy-i180423-339

https://zakon.rada.gov.ua/laws/show/4071-IX#Text

https://www.bringkidsback.org.ua/international-coalition

It is recommended that projects use output indicators from the Strategic Plan IRRF, as relevant, in addition to project-specific results indicators. Indicators should be disaggregated by sex or for other targeted groups where relevant.