# Country: The Gambia

# Standard Progress Report

Project Number: 01002135

Project Title: Strengthening National and Municipal Capacities for the Sound Management of PCBs and uPOPs

# Reporting Period: 1 January - 31 December 2024

# Implementation Duration: 3 years (2024-2027)

- Executive Summary

The Gambia, as a committed party to the Stockholm Convention, has pledged to eliminate the production and use of intentionally produced Persistent Organic Pollutants (POPs), reduce releases from unintentionally produced POPs, and ensure the environmentally sound management of stockpiles and wastes containing POPs. Despite significant efforts since ratifying the convention in 2003, the country continues to face challenges in ensuring the sound management of unintentional persistent organic pollutants (uPOPs) including polychlorinated biphenyls (PCBs). For instance, incomplete inventory data makes it difficult to track PCB-containing equipment, hindering waste management effort. Also, policy and regulations are insufficient to effectively address UPOPs and PCB management within the country's environmental protection framework. There is also no clear plan for decommissioning and safe disposal.

To address these challenges, the project titled "Strengthening National and Municipal Capacities for the Sound Management of PCBs and uPOPs in The Gambia" was developed. This project aims to respond directly to the identified gaps by enhancing the country's capacity to manage PCBs and uPOPs in compliance with the Stockholm Convention, thereby protecting human health and the environment from the harmful effects of these pollutants. The project is designed to achieve the following results:

Ensure the decommissioning and environmentally sound disposal of PCB waste.

Implement measures to reduce emissions and releases of uPOPs from the uncontrolled open burning of waste.

The €999,788.00 ($1,079,486.37) project, funded by the French Facility for Global Environment and supported by the French Ministry of Ecological Transition and Territorial Cohesion (MTECT) is jointly implemented by the United Nations Development Programme (UNDP) and the United Nations Institute for Training and Research (UNITAR), in partnership with the National Environmental Agency (NEA), the National Water and Electricity Company (NAWEC), the Kanifing Municipal Council (KMC), and other stakeholders.

Although the project was expected to move into the implementation phase in 2024, this was not realized. Nonetheless, the necessary preparatory work is nearly complete, and the project is expected to transition into the implementation phase by the end of the first quarter of 2025, with the official launch planned for March 2025. The key tasks completed so far include:

- Review and approval of the Project Document by the Local Appraisal Committee (LPAC).

- The Project Steering Committee (PSC) was set up and the first meeting was held in July 2024.

- The recruitment of the project management unit comprising the Project Manager, the Monitoring & Evaluation Analyst and the Project Finance & Admin. Officer was initiated and at an advanced stage.

- Procurement of furniture and office equipment for the project management unit was completed.

- A partnership agreement between UNDP and UNITAR has been signed.

- Preparation for the Project Launch and the second PSC Meeting scheduled for March 5th, 6th, and 7th, have commenced and are currently ongoing.

- Purpose

#### The Project aims to achieve results that would facilitate the implementation of the Stockholm Convention in The Gambia. This goal is expected to be achieved through the decommissioning and environmentally sound disposal of PCB waste, as well as the reduction in emissions and releases of uPOPs from the uncontrolled open burning of waste. The expected results of the projects include:

- Strengthening of legal frameworks and administrative processes for the sound management of PCBs and the reduction of releases of uPOPs strengthened.

- Environmentally Sound Management of PCBs, and PCB Contaminated Sites.

- Minimization of uPOP releases from open burning of waste.

#### The project contributes to both the United Nations Sustainable Development Cooperation Framework (UNDSCF) and the United Nations Development Programme (UNDP) Country Programme Document (CDP) indicated below:

- UNDSDCF Outcome 1.1: By 2028, women, children, displaced people, youths, and persons with disabilities (PWD), particularly in rural and urban disaster-prone and conflict-prone areas, will be resilient to climate-related and other shocks and have access to sustainable food, water, sanitation, and hygiene (WASH), health systems, education, and social protection.

- CPD Output 1.1.2: Solutions adopted for chemicals and waste management, and to achieve universal access to clean, affordable, and sustainable energy and clean cooking.

#### Project Components:

#### The project has 4 components as described below:

- Legal and Administrative Strengthening: Establish and enforce regulations and administrative procedures for PCB management and uPOPs reduction.

- Management of PCBs: Safely manage and dispose of PCB-contaminated equipment and waste and remediate contaminated sites.

- Reduction of uPOPs Emissions: Implement strategies to reduce uPOPs emissions from waste management practices, particularly open burning.

- Monitoring and Outreach: Conduct continuous monitoring, learning, adaptive feedback, and outreach activities to ensure the project's sustainability and effectiveness.

- Partnership & Coordination

The UNDP, as the implementing and coordinating unit, is directly responsible for project implementation and oversight, quality assurance, and strategic direction. The United Nations Institute for Training and Research (UNITAR) provides technical expertise and support. Other key implementing partners include the Ministry of Environment, Climate Change & Natural Resources (MECCNAR), Kanifing Municipal Council (KMC), National Water and Electricity Company Limited (NAWEC), and the National Environment Agency (NEA).

The partnership amongst the stakeholders is expected to enhance project results through leveraging each partner’s strengths, improved oversight and strategic direction. This partnership brings together financial resources, technical expertise, and influence, establishing an inclusive approach to achieving project results. For instance, international partners like the FFEM, UNDP, and UNITAR contribute financial, technical resources and global best practices, while local partners, including government agencies and CSOs, facilitate on-the-ground implementation, policy integration, and community engagement, including facilitating access to the hardest to reach in society and leveraging knowledge local to enhance decision-making. Moreover, the involvement of government agencies could facilitate tasks associated with policy and regulatory revisions and their uptake, while CSOs can mobilize communities to help drive awareness, capacity-building, and grassroots participation. Therefore, this collaborative approach is expected to lead to more effective management of PCBs and uPOPs, protecting human health and the environment.

UNDP acknowledges the need for an integrated approach to programming. As a result, UNDP will align this FFEM funded project with the ongoing GEF funded project “Capacity Building for PCBs and U-POPs in The Gambia” and ensure strong coordination between the two projects. Both projects fall under the Environment Cluster. Therefore, the two project managers will operate under the leadership of the Environment Team Lead, who will provide strategic guidance to ensure coordination. Specific steps planned to ensure strong coordination include:

- Monthly cluster meetings: This will be a platform to discuss synergies and strengthen coordination between the two projects. This will start once the project management unit is on board.

- In addition to this, some key activities of the FFEM funded project will be supported through GEF funding, specifically: 2.1 Developing a national inventory and database of electrical equipment to identify items containing or contaminated with PCBs; 2.2 Decommissioning and disposing of PCB-containing devices and decontaminating affected equipment.

- We have engaged with UNITAR to explore ways to leverage lessons learned from the GEF project and effective ways to build on the project’s results. This collaboration will remain an ongoing process.

- Additionally, opportunities to enhance coordination and optimize project resources will be a key focus in technical committee meetings.

This structured approach will enhance coordination, help align activities, maximize resource use, and enhance project impact.

- Results

During the reporting period, the focus was mainly on having the appraisal of project document by the Local Appraisal Committee (LPAC), setting up of the Project Management Unit, and transitioning into the implementation phase of the project. The key tasks completed so far include the following:

- The Project Document was reviewed and approved by the Local Appraisal Committee (LPAC).

- The Project Steering Committee was set up and the first meeting was held.

- The recruitment of the project management unit comprising Project Manager, Monitoring & Evaluation Analyst and Project Finance & Admin. Officer was initiated and at an advanced stage.

- Procurement of furniture and other office equipment for the Project Management was completed.

- A partnership agreement between UNDP and UNITAR has been signed. This collaboration establishes a framework for technical assistance and capacity-building activities.

- Preparation for the Project Launch and the second PSC Meeting have commenced and is ongoing.

It is imperative to note that the expectation to move into the implementation phase in 2024 was not met due to a number of constraints. First, the need to follow UNDP’s Programme and Operations Policies and Procedures (POPP) for establishing a development project can be time-consuming, especially due to its participatory approach. This poses challenges for complex projects involving multiple international and local partners, as coordinating stakeholder engagement can be challenging. For example, organizing the LPAC meeting and the first PSC session proved challenging due to scheduling conflicts among representatives from various organizations.

Other issues encountered was the reliance on staff outside the Environment Cluster (the unit responsible for this project in the UNDP Gambia Country Office) on certain tasks, such as the recruitment of the PMU. The availability of key personnel, such as the Human Resource focal point, was sometimes unpredictable, leading to delays in the process. A key lesson learned is the importance of proactive and periodic communication with relevant clusters, such as the Human Resource, Procurement, and Communications teams to ensure they are informed in advance and can better accommodate the project's needs within their workflows.

- Challenges, Risks & Mitigations

In addition to the constraints outlined in Section IV, progress was further impeded by insufficient institutional memory. This issue arose because key staff involved in the project's design separated from UNDP prior to its implementation. This resulted in a loss of critical context, for example, regarding the rationale behind certain budgetary decisions. Without access to detailed budget notes or clear documentation, the current team had to invest significant time in consulting widely with various partners and engaging in multiple meetings to piece together the necessary justifications. This process was essential to rationalize and finalize budget specifics, a crucial step for securing approval of project workplans and ensuring compliance with UNDP policies and procedures.

An important lesson learned from this experience is the need for documentation of key information. Moving forward, the team will ensure that all relevant details are systematically recorded and appropriately filed to maintain institutional continuity and facilitate smoother transitions. Once on board, the project management team, particularly the finance and administrative support officer will be tasked with this responsibility. This will also be an important component of knowledge management for the project.

All risks and mitigation measures submitted in the Project Proposal are still relevant and no new risks have been added. The project management unit and relevant teams as well as implementing partners and responsible parties will monitor project risks to ensure smooth implementation. This will be one of the important topics to be discussed during the inception workshop.

- Future Work Plan

The Project’s Technical Committee held a half-day working session to review the draft 2025 annual work plan for the project. Following this review, the draft plan has been shared with the UNDP Country Office Management team. Once reviewed and cleared, it will be submitted to the Project Steering Committee (PSC) for final review and approval during its second meeting in March 2025. Please refer to Table 1 for an abridged version of the 2025 annual plan, showing key activities planned for the year.

It is expected that the Project Management Unit will be on board by the end of the first quarter of 2025. The team will be responsible for the execution of project activities, coordinating activities, and ensuring that all objectives are met efficiently. To support the Project Management Unit, office supplies, including furniture and necessary gadgets, have already been purchased. These items will be handed over to the NEA (where the PMU will be housed) before the end of February 2025, ensuring that the PMU is fully equipped to begin its work without delay.

To enhance the effectiveness of the Annual Work Plan for 2025, it is recommended that the Project Management Unit collaborates with the Technical Committee to further refine the plan by breaking it down into microunits or action plans. These should detail specific activities on a quarterly and monthly basis, ensuring clearer tasks and implementation timelines. This plan should also map out the various entities involved in specific activities, extending beyond the scope of the designated responsible parties, to enhance coordination and accountability. There will be frequent thematic meetings to discuss alignment with the activities of the GEF project and how best the projects could complement each other.

In addition to the above, developing environmental and social safeguards plans/frameworks (where appropriate) including a stakeholder engagement plan and a gender action plan, will be an important priority in 2025. Furthermore, the current procurement plan will be reviewed and a more detailed action plan for procurement activities in 2025 will be prepared. A communications and knowledge management plan will also be prepared for the project.

Table 1. Annual workplan for 2025

| PLANNED ACTIVITY RESULTS | ACTIVITY | Q1 | Q2 | Q3 | Q4 | RESPONSIBLE PARTY |
| --- | --- | --- | --- | --- | --- | --- |
| Activity Result 1.1: Legal framework and admin processes strengthened for PCBs Management. | Activity 1.1: Strengthening of legal framework and administrative processes for the sound management of PCBs. |  |  |  |  | UNDP |
|  |  |  |  |  |  | UNITAR |
|  | Activity 1.2: Strengthening the capacity of national and local authorities to take action to reduce uPOP releases through better MSW management. |  |  |  |  | UNDP |
|  |  |  |  |  |  | UNITAR |
|  | Activity 1.3: Improve the financial viability of solid waste management systems and waste management actors. |  |  |  |  | UNDP |
|  |  |  |  |  |  | UNITAR |
| Activity Result 2. PCBs and PCB contaminated sites environmentally and soundly managed. | Activity 2.1: Capacity building to maintain an up-to-date national inventory and assist in the management of contaminated sites. |  |  |  |  | UNDP |
|  |  |  |  |  |  | UNITAR |
|  | Activity 2.2: Decommissioning and disposal of devices containing PCBs, decontamination of devices contaminated with PCBs. |  |  |  |  | UNDP |
|  |  |  |  |  |  | UNITAR |
|  | Activity 2.3: Risk assessment of PCB contaminated sites. |  |  |  |  | UNDP |
|  |  |  |  |  |  | UNITAR |
| Activity Results 3: Minimize uPOP releases from open burning of waste. | Activity 3.1: Reduction of uPOP emissions through effective MSW treatment systems that avoid open burning. |  |  |  |  | UNDP |
|  |  |  |  |  |  | UNITAR |
|  | Activity 3.2: Reduction in emission of persistent organic pollutants by strengthening the roles and capacities of non-governmental actors that reduce or divert waste that would otherwise be burned. |  |  |  |  | UNDP |
|  |  |  |  |  |  | UNITAR |
|  | Activity 3.3: Demonstration of POPs reduction through pilot activities of non-combustion solid waste disposal alternatives based on the 3Rs. |  |  |  |  | UNDP |
|  |  |  |  |  |  | UNITAR |
|  | Activity 3.4: Reduction of uPOP releases from agriculture by promoting non-burning alternatives for residual biomass management. |  |  |  |  | UNDP |
|  |  |  |  |  |  | UNITAR |
| Activity Result 4: Information and awareness raising, monitoring and evaluation, learning and evolving feedback strengthened. | Activity 4.1: Awareness raising on PCB phase-out. |  |  |  |  | UNDP |
|  |  |  |  |  |  | UNITAR |
|  | Activity 4.2: Awareness creation on the reduction of POPs releases from the open-air combustion of solid waste. |  |  |  |  | UNDP |
|  |  |  |  |  |  | UNITAR |
|  | Activity 4.3: Education of farmers on the need to reduce uPOP releases from agricultural biomass combustion. |  |  |  |  | UNDP |
|  |  |  |  |  |  | UNITAR |
|  | Activity 4.4: Assessment of the impact of efforts to reduce uPOP releases. |  |  |  |  | UNDP |
|  |  |  |  |  |  | UNITAR |
|  | Activity 4.5: Project monitoring and evaluation. |  |  |  |  | UNDP |
|  |  |  |  |  |  | UNITAR |
| Project Management |  |  |  |  |  | UNDP |

- Financial Status

The total committed donor contribution for the project is €999,788.00 ($1,079,486.37). As of 31 December 2024, a total of $432,964.48 had been received as contributions from the French Facility for Global Environment, with an outstanding receivable balance of $646,521.89 yet to be disbursed. No expenses were recorded under staff costs, supplies, equipment, contractual services, travel, transfers, or operating costs during this reporting period. An Amount of $120, 000 has been transferred to UNITAR but has not been liquidated. As a result, the full amount received ($432,964.48) remains unspent as of the reporting date. This is because the project has not moved into the implementation phase. With the preparations made so far, including the recruitment of the project management unit, all is set for project activities to commence in this first quarter of 2025.  A Standard Financial Statement has been attached to this report.

It is worth noting that there is a deviation from the agreed plan regarding the budget for the project coordinator. An amount of €43,800 was originally allocated for activities of the project management unit including the cost for the project coordinator, the finance and administrative support role and social and environmental safeguards. This plan was based on the idea that the Global Environment Facility (GEF) project manager will also coordinate this FFEM project. This original design was the reason the GEF project was expected to provide €192,460 to cover project management, financial assistance and social and environmental safeguards cost for this project. However, based on lessons learned from similar projects in The Gambia and elsewhere, we have found that, in projects with limited funding, it is more efficient to assign these interconnected responsibilities to a single dedicated individual rather than distributing them among multiple personnel across projects. This approach addresses both resource constraints and operational efficiency while ensuring stronger alignment with project goals. Therefore, there will be a dedicated project manager for this FFEM project whose roles will encompass three key functions: (1) project coordination, (2) technical assistance, and (3) project monitoring.

This proposed adjustment represents a slight deviation from the original project design but could offer higher benefits. By combining these roles under one position, the project manager will have a holistic understanding of the project and technical needs, leading to more informed and cohesive decision-making. A dedicated project manager will also ensure consistent support for local project partners and help build the capacity of national stakeholders to execute activities effectively. Additionally, consolidating these responsibilities minimizes communication gaps, avoids delays, and reduces administrative overhead—critical considerations for projects with limited budgets.

This new arrangement resulted in the need to cover parts of the project manager’s salary from additional budget lines, mainly the technical assistance budget and the monitoring and evaluation budget. The estimated total salary for the project manager over three years is USD 90,000, which will be distributed across various budget lines as shown in Table 2.

Table 2. Distribution of Project Manger’s Salary

| Key Budget lines | Budget (Euros) | Estimated amount of the project manager’s salary charged to the budget line (USD) | % of the project manager’s salary |
| --- | --- | --- | --- |
| Project management, financial assistance + social and environmental safeguards incl. gender action plan | 43,800 | 35,000 | ~39% |
| Technical assistance budget | 32,193 | 20,000 | ~22% |
| M&E | 80,000 | 35,000 | ~39% |

UNDP will ensure that sufficient funds remain within these budget lines to address other critical needs beyond the project manager’s responsibilities. For example, some technical assistance tasks may still require external consultants, and some budget will be preserved for that. This will also apply to the project management line for financial assistance and the gender action plan. The remaining costs for the finance and administrative support role and the Monitoring and Evaluation analyst role will be covered through UNDP’s co-financing. In fact, for 2025, UNDP has approved an amount of $42,483 from Core Resources to cover the budget gap for the project management unit.

- Expression of Thanks

We sincerely thank the FFEM for their invaluable support, not only for their generous funding but also for their active collaboration in shaping project activities. Their engagement in decision-making and their responsiveness have been instrumental in ensuring the smooth completion of key tasks, such as the preparation of the procurement plan, towards the initiation of the project. This partnership reflects a shared commitment to sustainable development and impactful environmental action.

We extend our heartfelt gratitude to all the dedicated partners and stakeholders involved in the "Strengthening National and Municipal Capacities for the Sound Management of PCBs and uPOPs in The Gambia" project, particularly, the French Ministry of Ecological Transition and Territorial Cohesion (MTECT), and to the United Nations Institute for Training and Research (UNITAR) for their invaluable support and expertise. We also acknowledge the significant contributions of the National Environmental Agency (NEA), the National Water and Electricity Company (NAWEC), and the Kanifing Municipal Council (KMC). Your unwavering commitment and collaborative efforts have been instrumental in advancing efforts to manage Persistent Organic Pollutants (POPs) in alignment with the Stockholm Convention. Together, we are making meaningful strides towards protecting human health and the environment from the harmful effects of PCBs and uPOPs. Your dedication and hard work are truly appreciated, and we look forward to continued success in our shared mission.

Please note that UNDP financial reports are issued in USD.