| Project QA Assessment: Design and Appraisal |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Overall Project |  |  |  |  |  |  |  |
| Exemplary (5) |  | Highly Satisfactory (4) | Satisfactory (3) |  | Needs Improvement (2) | Inadequate (1) |  |
| At least four criteria are rated Exemplary, and all criteria are rated High or Exemplary. |  | All criteria are rated Satisfactory or higher, and at least four criteria are rated High or Exemplary. | At least six criteria are rated Satisfactory or higher, and only one may be rated Needs Improvement. The Principled criterion must be rated Satisfactory or above. |  | At least three criteria are rated Satisfactory or higher, and only four criteria may be rated Needs Improvement. | One or more criteria are rated Inadequate, or five or more criteria are rated Needs Improvement. |  |
| DECISION |  |  |  |  |  |  |  |
| - APPROVE – the project is of sufficient quality to be approved in its current form. Any management actions must be addressed in a timely manner. - APPROVE WITH QUALIFICATIONS – the project has issues that must be addressed before the project document can be approved. Any management actions must be addressed in a timely manner. - DISAPPROVE – the project has significant issues that should prevent the project from being approved as drafted. |  |  |  |  |  |  |  |
| RATING CRITERIA For all questions, select the option that best reflects the project |  |  |  |  |  |  |  |
| Strategic |  |  |  |  |  |  |  |
| - Does the project specify how it will contribute to higher level change through linkage to the programme’s Theory of Change? - 3: The project is clearly linked to the programme’s theory of change. It has an explicit change pathway that explains how the project will contribute to outcome level change and why the project’s strategy will likely lead to this change. This analysis is backed by credible evidence of what works effectively in this context and includes assumptions and risks. - 2: The project is clearly linked to the programme’s theory of change. It has a change pathway that explains how the project will contribute to outcome-level change and why the project strategy will likely lead to this change. - 1: The project document may describe in generic terms how the project will contribute to development results, without an explicit link to the programme’s theory of change. *Note: Projects not contributing to a programme must have a project-specific Theory of Change. See alternative question under the lightbulb for these cases. |  |  |  |  |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  |  |  | - Evidence - The project is clearly linked to outcome 2 of the programmes theory of change. The theory of change underlying this outcome is that policy and regulatory reforms aimed at creating stronger conditions for economic development in the non-hydro-carbon sectors of the economy, increased private sector competitiveness and trade, and the creation of decent jobs, will result in a sustainable and diversified economic development of the country where the expected benefits of growth are more widely and fairly shared. The project will contribute by improving the statistics of foreign and domestic trade in services. The project will enable the Government of Turkmenistan to better understand the current trends, challenges, and opportunities of the service sector. The project will also help the TurkmenStat to align its methodologies with international standards for statistics on international trade in services, such as the Manual on Statistics of International Trade in Services (MSITS) 2010, which will enhance the credibility and comparability of data and facilitate its integration into the global market. Furthermore, the project will assist in improving the quality of data on the volume of passenger and cargo transportation, which is a key indicator of trade facilitation and connectivity. This will support the Government's efforts to develop its transport infrastructure and logistics services, which are essential for economic diversification and digitalization. The project is based on the results of assessment of the existing system of Turkmenistan on statistics of foreign trade in services, including the current methodology and standards for statistics on international trade in services, as well as recommendations for improving the quality of data statistics of Turkmenistan on foreign trade in services. |  |  |  |
| - Is the project aligned with the UNDP Strategic Plan? - 3: The project responds to at least one of the development settings as specified in the Strategic Plan and adapts at least one Signature Solution. The project’s RRF includes all the relevant SP output indicators. (all must be true) - 2: The project responds to at least one of the development settings as specified in the Strategic Plan4. The project’s RRF includes at least one SP output indicator, if relevant. (both must be true) - 1: The project responds to a partner’s identified need, but this need falls outside of the UNDP Strategic Plan. Also select this option if none of the relevant SP indicators are included in the RRF. |  |  |  | 3 |  |  |  |
|  |  |  |  | Evidence The project is contributing the UNDP Strategic Plan’s priority 2, contributing to the UNDP’s signature solutions for keeping people out of poverty and strengthening gender equality, along with Global Integrated Offer for mitigating COVID-19 socio-economic consequences, UNDP will support the design and implementation of policy and regulatory reforms to promote economic development and better livelihoods in the non-hydro-carbon sectors, increased private sector competitiveness and trade, innovative and effective banking, and creation of decent jobs. The project is aimed to support the existing efforts of the Government of Turkmenistan in improving statistics of foreign and domestic trade in services by strengthening institutional mechanisms, bringing national legislation in line with international standards for statistics on international trade in services, as well as improving the quality of data on the volume of passenger and freight traffic. |  |  |  |
| - Is the project linked to the programme outputs? (i.e., UNDAF Results Group Workplan/CPD, RPD or Strategic Plan IRRF for global projects/strategic interventions not part of a programme) |  |  |  | Yes Contributes to the achievement of Outcome 2 of the UNSDCF-TKM 2021-2025: “By 2025, conditions have been improved for sustainable and inclusive economic diversification by developing competitive private and financial sectors, facilitating trade and attracting investment, and introducing innovative technologies» by improving the statistics of foreign and domestic trade in services. UNDP CPD Output 2.1: Strengthening the regulatory, institutional, and human capacity of public institutions and private sector for the realization of diversification, digitalization, and trade promotion, with a focus on creating employment opportunities, including for women and vulnerable groups. The project will achieve this by developing regulatory acts, such as the development of methodologies, that will enable the collection, processing, and dissemination of high-quality data on trade in services. |  |  |  |
| Relevant |  |  |  |  |  |  |  |
| - Does the project target groups left furthest behind? - 3: The target groups are clearly specified, prioritising discriminated and marginalized groups left furthest behind, identified through a rigorous process based on evidence. - 2: The target groups are clearly specified, prioritizing groups left furthest behind. - 1: The target groups are not clearly specified. *Note: Management Action must be taken for a score of 1. Projects that build institutional capacity should still identify targeted groups to justify support |  |  |  |  |  |  |  |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | Evidence The target group as well as beneficiaries and partners are clearly defined in the Project Document. They are: staff of TurkmenStat, Central Bank, Ministry of Finance and Economy and others . |  |  |  |
| - Have knowledge, good practices, and past lessons learned of UNDP and others informed the project design? - 3: Knowledge and lessons learned backed by credible evidence from sources such as evaluation, corporate policies/strategies, and/or monitoring have been explicitly used, with appropriate referencing, to justify the approach used by the project. - 2: The project design mentions knowledge and lessons learned backed by evidence/sources, but have not been used to justify the approach selected. - 1: There is little or no mention of knowledge and lessons learned informing the project design. Any references made are anecdotal and not backed by evidence. *Note: Management Action or strong management justification must be given for a score of 1 |  |  |  |  |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  |  |  | Evidence |  |  |  |
|  |  |  |  | The knowledge and lessons learned are duly applied backed by credible evidence from the other Statistics projects. The project is based on recommendations of self-assessment |  |  |  |
| - Does UNDP have a clear advantage to engage in the role envisioned by the project vis-à-vis national/regional/global partners and other actors? - 3: An analysis has been conducted on the role of other partners in the area where the project intends to work, and credible evidence supports the proposed engagement of UNDP and partners through the project, including identification of potential funding partners. It is clear how results achieved by partners will complement the project’s intended results and a communication strategy is in place to communicate results and raise visibility vis-à-vis key partners. Options for south-south and triangular cooperation have been considered, as appropriate. (all must be true) - 2: Some analysis has been conducted on the role of other partners in the area where the project intends to work, and relatively limited evidence supports the proposed engagement of and division of labour between UNDP and partners through the project, with unclear funding and communications strategies or plans. - 1: No clear analysis has been conducted on the role of other partners in the area that the project intends to work. There is risk that the project overlaps and/or does not coordinate with partners’ interventions in this area. Options for south-south and triangular cooperation have not been considered, despite its potential relevance. *Note: Management Action or strong management justification must be given for a score of 1 |  |  |  |  |  |  |  |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | Evidence Yes. The project document describes the role of the implementing partner with clear functions of the partners contributing to the results of the project. The project document is attached. It is clear from the design stage of the project that results indicated in the project document will contribute to the ultimate goal of the project. In the frame of cooperation of UNDP with national partners the communication and raising visibility and developing press-releases on the events conducted are delivered in compliance with UNDP`s Communication Strategy. |  |  |  |
| Principled |  |  |  |  |  |  |  |
| - Does the project apply a human rights-based approach? - 3: The project is guided by human rights and incorporates the principles of accountability, meaningful participation, and non-discrimination in the project’s strategy. The project upholds the relevant international and national laws and standards. Any potential adverse impacts on enjoyment of human rights were rigorously identified and assessed as relevant, with appropriate mitigation and management measures incorporated into project design and budget. (all must be true) - 2: The project is guided by human rights by prioritizing accountability, meaningful participation and non-discrimination. Potential adverse impacts on enjoyment of human rights were identified and assessed as relevant, and appropriate mitigation and management measures incorporated into the project design and budget. (both must be true) - 1: No evidence that the project is guided by human rights. Limited or no evidence that potential adverse impacts on enjoyment of human rights were considered. *Note: Management action or strong management justification must be given for a score of 1 |  |  |  |  |  |  |  |
|  |  |  |  | Evidence The project is mainstreaming the human rights approach by strengthening the capacity of TurkmenStat in achieving sustainable development goals and improving economic and social rights of society. |  |  |  |
| - Does the project use gender analysis in the project design? - 3: A participatory gender analysis has been conducted and results from this gender analysis inform the development challenge, strategy and expected results sections of the project document. Outputs and indicators of the results framework include explicit references to gender equality, and specific indicators measure and monitor results to ensure women are fully benefitting from the project. (all must be true) - 2: A basic gender analysis has been carried out and results from this analysis are scattered (i.e., fragmented and not consistent) across the development challenge and strategy sections of the project document. The results framework may include some gender sensitive outputs and/or activities but gender inequalities are not consistently integrated across each output. (all must be true) - 1: The project design may or may not mention information and/or data on the differential impact of the project’s development situation on gender relations, women and men, but the gender inequalities have not been clearly identified and reflected in the project document. *Note: Management Action or strong management justification must be given for a score of 1 |  |  |  |  |  |  |  |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | Evidence A basic gender analysis has been carried out during the gender seal process of the UNDP country office. The results of the analysis supported to strengthen GEN2 marker of the project and advocate gender mainstreaming in the project document. In the design stage of the project CO was guided by the National Gender Equality Plan of Turkmenistan for 2021-2025, Gender Equality Strategy of UNDP for 2022-2025, Gender Equality Action Plan of UNDP Turkmenistan for 2022-2025, MICS reports of UNICEF. |  |  |  |
| 9. Did the project support the resilience and sustainability of societies and/or ecosystems? - 3: Credible evidence that the project addresses sustainability and resilience dimensions of development challenges, which are integrated in the project strategy and design. The project reflects the interconnections between the social, economic and environmental dimensions of sustainable development. Relevant shocks, hazards and adverse social and environmental impacts have been identified and rigorously assessed with appropriate management and mitigation measures incorporated into project design and budget. (all must be true). - 2: The project design integrates sustainability and resilience dimensions of development challenges. Relevant shocks, hazards and adverse social and environmental impacts have been identified and assessed, and relevant management and mitigation measures incorporated into project design and budget. (both must be true) - 1: Sustainability and resilience dimensions and impacts were not adequately considered. *Note: Management action or strong management justification must be given for a score of 1 |  |  |  |  |  |  |  |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | Evidence The project does not affect the environmental sustainability, as it is aiming at strengthening capacities of employees of the relevant departments of Turkmenstat. |  |  |  |
| 10. Has the Social and Environmental Screening Procedure (SESP) been conducted to identify potential social and environmental impacts and risks? The SESP is not required for projects in which UNDP is Administrative Agent only and/or projects comprised solely of reports, coordination of events, trainings, workshops, meetings, conferences and/or communication materials and information dissemination. [if yes, upload the completed checklist. If SESP is not required, provide the reason for the exemption in the evidence section.] |  |  |  | Yes |  |  |  |
|  |  |  |  | SESP is attached |  |  |  |
| Management & Monitoring |  |  |  |  |  |  |  |
| - Does the project have a strong results framework? - 3: The project’s selection of outputs and activities are at an appropriate level. Outputs are accompanied by SMART, results-oriented indicators that measure the key expected development changes, each with credible data sources and populated baselines and targets, including gender sensitive, target group focused, sex-disaggregated indicators where appropriate. (all must be true) - 2: The project’s selection of outputs and activities are at an appropriate level. Outputs are accompanied by SMART, results-oriented indicators, but baselines, targets and data sources may not yet be fully specified. Some use of target group focused, sex-disaggregated indicators, as appropriate. (all must be true) - 1: The project’s selection of outputs and activities are not at an appropriate level; outputs are not accompanied by SMART, results-oriented indicators that measure the expected change and have not been populated with baselines and targets; data sources are not specified, and/or no gender sensitive, sex-disaggregation of indicators. (if any is true) *Note: Management Action or strong management justification must be given for a score of 1 |  |  |  |  |  |  |  |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | Evidence Baselines, targets and data sources are fully specified in the project document with outputs accompanies by SMART. Please see attached ProDoc |  |  |  |
| 12. Is the project’s governance mechanism clearly defined in the project document, including composition of the project board? - 3: The project’s governance mechanism is fully defined. Individuals have been specified for each position in the governance mechanism (especially all members of the project board.) Project Board members have agreed on their roles and responsibilities as specified in the terms of reference. The ToR of the project board has been attached to the project document. (all must be true). - 2: The project’s governance mechanism is defined; specific institutions are noted as holding key governance roles, but individuals may not have been specified yet. The project document lists the most important responsibilities of the project board, project director/manager and quality assurance roles. (all must be true) - 1: The project’s governance mechanism is loosely defined in the project document, only mentioning key roles that will need to be filled at a later date. No information on the responsibilities of key positions in the governance mechanism is provided. *Note: Management Action or strong management justification must be given for a score of 1 |  |  |  |  |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  |  |  | Evidence The project governance mechanism is in place and fully defined in the organigram of the project document, chapter VIII Governance and Management Mechanism. TOR of the project board is attached with roles and responsibilities with project board members on their roles, and responsibilities. |  |  |  |
| 13. Have the project risks been identified with clear plans stated to manage and mitigate each risk? - 3: Project risks related to the achievement of results are fully described in the project risk log, based on comprehensive analysis drawing on the programme’s theory of change, Social and Environmental Standards and screening, situation analysis, capacity assessments and other analysis such as funding potential and reputational risk. Risks have been identified through a consultative process with key internal and external stakeholders. Clear and complete plan in place to manage and mitigate each risk, reflected in project budgeting and monitoring plans. (both must be true) - 2: Project risks related to the achievement of results are identified in the initial project risk log based on a minimum level of analysis and consultation, with mitigation measures identified for each risk. - 1: Some risks may be identified in the initial project risk log, but no evidence of consultation or analysis and no clear risk mitigation measures identified. This option is also selected if risks are not clearly identified and/or no initial risk log is included with the project document. *Note: Management Action must be taken for a score of 1 |  |  |  | 3 |  |  |  |
|  |  |  |  | Evidence Based on the theory of change, risks have been identified with clear description and outcomes of the project. Risk log of the Project is attached. |  |  |  |
| Efficient |  |  |  |  |  |  |  |
| - Have specific measures for ensuring cost-efficient use of resources been explicitly mentioned as part of the project design? This can include, for example: i) using the theory of change analysis to explore different options of achieving the maximum results with the resources available; ii) using a portfolio management approach to improve cost effectiveness through synergies with other interventions; iii) through joint operations (e.g., monitoring or procurement) with other partners; iv) sharing resources or coordinating delivery with other projects, v) using innovative approaches and technologies to reduce the cost of service delivery or other types of interventions. (Note: Evidence of at least one measure must be provided to answer yes for this question) |  |  |  | Yes (3) . The budget for planned activities were developed to ensure cost-efficiency of the project (see ProDoc). Moreover, it is planned to attract the international consultants from Russian Experts on Demand Program in order to save the project budget and allocate them for more important issues for the project, for example survey. |  |  |  |
| 15. Is the budget justified and supported with valid estimates? - 3: The project’s budget is at the activity level with funding sources, and is specified for the duration of the project period in a multi-year budget. Realistic resource mobilisation plans are in place to fill unfunded components. Costs are supported with valid estimates using benchmarks from similar projects or activities. Cost implications from inflation and foreign exchange exposure have been estimated and incorporated in the budget. Adequate costs for monitoring, evaluation, communications and security have been incorporated. - 2: The project’s budget is at the activity level with funding sources, when possible, and is specified for the duration of the project in a multi-year budget, but no funding plan is in place. Costs are supported with valid estimates based on prevailing rates. - 1: The project’s budget is not specified at the activity level, and/or may not be captured in a multi-year budget. |  |  |  |  |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  |  |  | Evidence The project budget is identified at the activity level. The project budget with funding sources is in place with budget breakdown. The costs are supported with valid country level estimated based on the prevailing rates. The project is funded with government cost-sharing |  |  |  |
| - Is the Country Office/Regional Hub/Global Project fully recovering the costs involved with project implementation? - 3: The budget fully covers all project costs that are attributable to the project, including programme management and development effectiveness services related to strategic country programme planning, quality assurance, pipeline development, policy advocacy services, finance, procurement, human resources, administration, issuance of contracts, security, travel, assets, general services, information and communications based on full costing in accordance with prevailing UNDP policies (i.e., UPL, LPL.) - 2: The budget covers significant project costs that are attributable to the project based on prevailing UNDP policies (i.e., UPL, LPL) as relevant. - 1: The budget does not adequately cover project costs that are attributable to the project, and UNDP is cross-subsidizing the project. *Note: Management Action must be given for a score of 1. The budget must be revised to fully reflect the costs of implementation before the project commences. |  |  |  |  |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  |  |  | Evidence The project activities are fully covered by the contribution of Turkmenistan government. |  |  |  |
| Effective |  |  |  |  |  |  |  |
| 17. Have targeted groups been engaged in the design of the project? - 3: Credible evidence that all targeted groups, prioritising discriminated and marginalized populations that will be involved in or affected by the project, have been actively engaged in the design of the project. The project has an explicit strategy to identify, engage and ensure the meaningful participation of target groups as stakeholders throughout the project, including through monitoring and decision-making (e.g., representation on the project board, inclusion in samples for evaluations, etc.) - 2: Some evidence that key targeted groups have been consulted in the design of the project. - 1: No evidence of engagement with targeted groups during project design. |  |  |  |  |  |  |  |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | Evidence The project contributes to capacity development of the State Statistics Committee of Turkmenistan, and marginalized and excluded population is not targeted by the project. |  |  |  |
| 18. Does the project plan for adaptation and course correction if regular monitoring activities, evaluation, and lesson learned demonstrate there are better approaches to achieve the intended results and/or circumstances change during implementation? |  |  |  | Yes (3), the project absolutely plans for adaptation and course correction based on the findings from regular monitoring activities, and lessons learned. Here's how we plan to achieve this: - According to the UNDP programming policy and procedures, the project will be monitored through indicated in the ProDoc monitoring and evaluation plans, which defines key performance indicators (KPIs) that track progress towards achieving project goals. - Regular monitoring activities: These activities will involve collecting data on KPIs, identifying emerging challenges, and assessing any changes in the project environment. - Lesson learned: We will hold regular meetings to share findings from monitoring and evaluation activities, discuss potential course corrections, and brainstorm more effective approaches based on learning and changing circumstances. - Stakeholder engagement: The project design will hold Project Board Meetings and discuss adjustments based on M&E findings. Based on meeting results, changes could be modified in issues, such as activities, resource allocation, or project timelines We will maintain open communication with stakeholders, including national partners and beneficiaries, to gather feedback and ensure their input is considered during course correction decisions. |  |  |  |
| 19. The gender marker for all project outputs are scored at GEN2 or GEN3, indicating that gender has been fully mainstreamed into all project outputs at a minimum. *Note: Management Action or strong management justification must be given for a score of “no” |  |  |  | Yes (3) |  |  |  |
|  |  |  |  | Evidence The project is scored as GEN 2 as gender has been mainstreamed into project outputs at a minimum (see ProDoc) |  |  |  |
| Sustainability & National Ownership |  |  |  |  |  |  |  |
| 20. Have national/regional/global partners led, or proactively engaged in, the design of the project? - 3: National partners (or regional/global partners for regional and global projects) have full ownership of the project and led the process of the development of the project jointly with UNDP. - 2: The project has been developed by UNDP in close consultation with national/regional/global partners. - 1: The project has been developed by UNDP with limited or no engagement with national partners. |  |  |  |  |  |  |  |
|  |  |  |  | 3 |  |  |  |
|  |  |  |  | Evidence The project was developed in close consultations with the national partners and have full ownership of the project and led the process of development and approval of the project at the government level. |  |  |  |
| 21. Are key institutions and systems identified, and is there a strategy for strengthening specific/ comprehensive capacities based on capacity assessments conducted? - 3: The project has a strategy for strengthening specific capacities of national institutions and/or actors based on a completed capacity assessment. This strategy includes an approach to regularly monitor national capacities using clear indicators and rigorous methods of data collection, and adjust the strategy to strengthen national capacities accordingly. - 2: A capacity assessment has been completed. There are plans to develop a strategy to strengthen specific capacities of national institutions and/or actors based on the results of the capacity assessment. - 1: Capacity assessments have not been carried out. |  |  |  |  |  |  |  |
|  |  |  |  | 2 |  |  |  |
|  |  |  |  | - Evidence The project is based on the results of assessment of the existing system of Turkmenistan on statistics of foreign trade in services, including the current methodology and standards for statistics on international trade in services, as well as recommendations for improving the quality of data statistics of Turkmenistan on foreign trade in services. |  |  |  |
| 22. Is there is a clear strategy embedded in the project specifying how the project will use national systems (i.e., procurement, monitoring, evaluations, etc.,) to the extent possible? |  |  |  | Yes (3) We will actively engage with national stakeholders throughout the project cycle, including national institutions involved in M&E, and other relevant areas. This ensures transparency, facilitates information sharing, and fosters collaboration at all levels. Moreover, the issues related to project management were reflected in ProDoc as well as at ToR of the Project Board Meeting |  |  |  |
| 23. Is there a clear transition arrangement/ phase-out plan developed with key stakeholders in order to sustain or scale up results (including resource mobilisation and communications strategy)? |  |  |  | Yes (3) It is expected that a clear transition arrangement/phase-out plan to ensure the sustainability or scaling up of results beyond the project cycle focused on below key areas will be discussed during the Project Board Meetings: - We will conduct targeted advocacy campaigns and engage stakeholders such as government agencies, donors, and the private sector to raise awareness about the project's benefits and encourage continued investment in sustaining or scaling up its results. - The project will create training modules and resources on key project approaches, methodologies, and best practices. These materials will be readily accessible to national counterparts for future use and knowledge dissemination. - The recommendations developed by international consultants during the project framework will provide mentorship for national counterparts to ensure they possess the necessary skills and expertise to continue project activities independently after the project ends. - The project team will facilitate networking opportunities between national stakeholders to foster knowledge exchange, collaboration, and problem-solving skills beyond the project duration. - The project team will highlight the project's successes and best practices through various communication channels to garner support and encourage stakeholders to replicate the project's positive outcomes. |  |  |  |

The three development settings in UNDP’s 2018-2021 Strategic Plan are: a) Eradicate poverty in all its forms and dimensions; b) Accelerate structural transformations for sustainable development; and c) Build resilience to shocks and crises

The six Signature Solutions of UNDP’s 2018-2021 Strategic Plan are: a) Keeping people out of poverty; b) Strengthen effective, inclusive and accountable governance; c) Enhance national prevention and recovery capacities for resilient societies; d) Promote nature based solutions for a sustainable planet; e) Close the energy gap; and f) Strengthen gender equality and the empowerment of women and girls.