Project Progress Report (2025 version)

Name of Project: UNDP DR PLANT Biodiversity Conservation and Sustainable

Utilization Project Ⅱ

Date of report: 11/11/2025

A. PROJECT PROFILES

| Quantum Project ID | 01002322 |
| --- | --- |
| Project overall duration | From 22/05/2024 to 21/05/2027 |
| Location(s) | Daka Laozhai, Gongbian New Village, Manyuan Dai Village, Yangbi County, and Lijiang City, Yunnan province |
| Implementing partner | Yunnan Academy of Forestry and Grassland |
| Responsible party (if any) |  |
| UNDP Programme Officer | Ma Chaode |

| Gender Marker (GEN 1/2/3) | GEN 2 |
| --- | --- |
| Relevant CPD 2021-2025 output | Output 2.3: Capacities of select pilots strengthened to adopt sustainable biodiversity policies. |
| Relevant SP output | Output 4.1 Natural resources protected and managed to enhance sustainable productivity and livelihoods |

***

| 2025 Annual budget in System | To be populated by UNDP China |
| --- | --- |
| 2025 Expenditure | To be populated by UNDP China |
| 2025 Delivery rate | To be populated by UNDP China |

B. RESULTS

B.1 Results Towards the Annual Work Plan

| A. Project outcome/output statement (2025AWP) | B．2025Project Results, backed up by evidence and segregated data | C. Indicator Statement (2025 AWP) | D. Baseline Level (2025AWP) | E. Annual Target (2025AWP) |  | F. Value as of 2025 |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1: Mainstreaming and integrating corporate participation in biodiversity into international standards and developing industry standards in relevant professional fields | - Developed the international standard "Guidelines on Biodiversity Conservation in the Raw Material Origin of Cosmetic Enterprises," and completed Form 4: New Work Item Proposal (NP) and Draft Outline in both Chinese and English； - Submitted the draft international standard "Guidelines on Biodiversity Conservation in the Raw Material Origin of Cosmetic Enterprises" to the domestic technical counterpart of ISO/TC331. Following discussions by the national technical expert panel in June 2025, the document was revised based on expert feedback. In September 2025, a second version of the international standard proposal, now titled "Guidelines on Biodiversity Conservation in the Raw Material Origin of Cosmetic Enterprises," along with supporting materials, was prepared； - Developed the standard "Guidelines for Enterprise Biodiversity Information Disclosure." Submitted through SAC/TC207, the proposal was approved as a National Standardization Guiding Technical Document by the Standardization Administration of China in June 2025. Documents including the project proposal, working draft, and consultation draft were completed. In October 2025, the draft was released for public consultation on the National Standard Information Public Service Platform. - Developed Draft Guidelines on Access to Biological Genetic Resources and Benefit Sharing for Enterprises. | Indicator 1: Form 4: New Work Item Proposal (NP) (Chinese, English); Draft Outline (Chinese, English); Drafting and submission of the international standard and gender-sensitive draft of Guidelines for Biodiversity Conservation in Raw Material Producing Areas of Cosmetic Enterprises. Indicator 2: The Guidelines for Enterprise Biodiversity Information Disclosure released by the relevant government departments or industry associations. Indicator 3: The gender-sensitive Guidelines for Enterprise Access to Biological Genetic Resources and Benefit Sharing were released by relevant government departments or industry associations. | No standards |  | - The Guidelines have been developed. - The Guidelines have been compiled, and the framework of the database and statistical system has begun to be established in parts of supply chains of DR PLANT. - The draft of Guidelines for Access to and Benefit-sharing of Enterprise Biological Genetic Resources developed. | Indicator 1: 100% of annual target; 80% against EOP target Indicator 2: 100% of annual target; 80% against EOP target Indicator 3: 100% of annual target; 20% against EOP target |
| Output 1.1: Compile and submit the International standard draft of Guidelines on Biodiversity Conservation in the Raw Material Origin of Cosmetic Enterprises |  |  |  |  |  |  |
| Output 1.2: Release the Guidelines for Corporate Biodiversity Information Disclosure and implement the guidelines in DR PLANT |  |  |  |  |  |  |
| Output 1.3: Release the Guidelines on Access to Biological Genetic Resources and Benefit Sharing for Enterprises. |  |  |  |  |  |  |
| Outcome 2: Community demonstration on alpine plant genetic resources and associated traditional knowledge conservation, access and benefit-sharing, and establishment of alpine plant field gene banks. | Output 2.1: Develop the distribution map of Prinsepia Utilis Royle resources in China, establish 50 mu (3.3 hectares) germplasm resource area of Prinsepia Utilis Royle in Yangbi County, Yunnan Province. Carry out the demonstration of artificial high-yield cultivation of Prinsepia Utilis Royle through the NbS method. - Prepared the application for the certification of superior clonal varieties of Prinsepia Utilis Royle 'Dianging 5' and 'Dianging 6'. The on-site inspection was completed in May 2025, followed by the panel review in October, which led to the certification of one superior clonal variety. - Published three research papers: "Grafting Seedling Techniques for Prinsepia Utilis Royle", "Breeding of the Prinsepia Utilis Royle Clone 'Dianging 2', and "Seed Quality Variation and Comprehensive Evaluation of 31 Seedling Strains from Different Origins". - Submitted a proposal for developing the technical standard "Technical Code of Practice for the Cultivation of Prinsepia Utilis Royle" as a Yunnan Provincial Local Standard, which has been advanced to the review draft stage. - Compiled and analyzed the data required for creating a distribution map of Prinsepia Utilis Royle germplasm resources in China, with the map currently in the drafting phase. - Investigated and collected 101 accessions of Prinsepia Utilis Royle germplasm resources. - Cooperated with the Lijiang Forestry Science Research Institute to establish a 100-acre ABS demonstration forest in Jiuzihai, Gucheng District, Lijiang City, with follow-up efforts extending the model to an additional 500 acres. - Establisheda technical guidance team in collaboration with the Lijiang Forestry Science Research Institute. A community demonstration agreement on benefit-sharing was reached with the Jiuzihai Village Collective Economy in Gucheng District, Lijiang City. The team provided technical guidance and services on high-yield cultivation, processing, and utilization, while also offering expertise on the sharing of traditional knowledge related to Prinsepia utilis Royle, as well as the conservation and utilization of its germplasm resources. - Completed the site selection and land preparation for a Prinsepia Utilis Royle germplasm repository and planted 121 germplasm accessions. Output 2.2: Establish a cultivation demonstration and promotion system for Adenosma buchneroides Bonati in Daka Laozhai and Gongbian New Village of Menglun Township through NbS and community participatory ways. Establish a community demonstration model on Access to and Benefit Sharing (ABS) of Adenosma buchneroides Bonati Genetic Resources and Associated Traditional Knowledge. Develop three new products made from Adenosma buchneroides Bonati and apply for Adenosma buchneroides Bonati geographical indications. - In 2025, a cumulative planting area of approximately 1000 mu (about 66.7 hectares) of Adenosma buchneroides was established across two project sites in Menglun Town and surrounding areas. During the planting period, the project team provided on-site technical guidance to villagers multiple times. - Gongbian New Village acquired two additional essential oil extraction units, and Daka Laozhai Village, with government funding, established one essential oil processing plant. - The Laisansandu Agricultural Cooperative was established in Gongbian New Village. As a result, both villages have now established their own agricultural specialized cooperatives. - Two products using Adenosma buchneroides essential oil as a raw material were developed: a mite-control spray and a children's antibacterial cream. The mite-control spray is currently on the market, while the children's antibacterial cream is still undergoing sample adjustments and preparing the necessary regulatory submission documents. - Preparations are underway to establish the Xishuangbanna Adenosma buchneroides Industry Association. The association’s name has been officially approved, and there is a plan to initiate an application for a Geographical Indication under the association's name. - Progress was made in facilitating the signing of a "Benefit-Sharing Agreement on the Cultivation and Processing of the Traditional Medicinal Plant Adenosma buchneroides" between Huangyadai Pharmaceutical Co., Ltd. and the Mengla Laisansandu Agricultural Professional Cooperative. Output 2.3: Conduct survey, collection, protection, and evaluation for 20 species of wild plant germplasm resources in Lijiang, conducting investigation and collecting research on the germplasm resources of 20 wild native tree species and their related traditional knowledge in the Lijiang area. - Conducted field surveys from August 4 to 17, 2025, and from September 8 to October 26, 2025, in locations including Yulong County (Mingyin, Daju, Blue Moon Valley, Jiushijiulongtan, Xinzhu), Yongsheng County, Huaping County, Ninglang County, and the Gucheng District of Lijiang City, Yunnan Province. Surveys were completed for ten target plant species: Prinsepia utilis, Tetracentron sinense, Euonymus tingens, Picea likiangensis, Abies forrestii, Bergenia purpurascens, Dipelta yunnanensis, and Paeonia delavayi. Propagation and conservation efforts were carried out for five of these species. - Completed resource surveys for ten target plant species, including Prinsepia utilis, Tetracentron sinense, Euonymus tingens, Picea likiangensis, Abies forrestii, Bergenia purpurascens, Dipelta yunnanensis, and Paeonia delavayi. - Through visits and engagements with individuals from the Naxi, Tibetan, Lisu, and Yi ethnic groups in the Lijiang area, conducted an investigation into the germplasm resources and associated traditional knowledge of ten wild native tree species in the region. Output 2.4: Summarize one or two feasibility technical guidelines, village rules, and other recommendations, related to the protection of the Long Mountain, promoting the mainstreaming of the Long Mountain conservation system. - Refined the scientific terminology on the educational signage at the Longshan Mountain. From February 11 to 13, 2025, the project team visited Manyuan to photograph the existing Longshan educational signage, which was produced by Jingyun Cultural Tourism Investment Development Co., Ltd., a subsidiary of the Jinghong State-owned Assets Investment Group. The team held discussions with Jingyun staff and proposed revisions to improve the scientific accuracy of the content. Following further research, the team revised the educational materials. In May 2025, these revisions were submitted to Jingyun. However, due to a shift in investment focus by the state-owned assets supervision authority, the company had subsequently halted tourism development in Manyuan. The company had previously constructed a parking lot, visitor center, and Longshan trails, and had designed and produced the educational signage. - Supported the "Longshan Protection Day" event organized by the Xishuangbanna Forestry and Grassland Bureau. On May 22, 2025, a four-person project team participated in a tree-planting activity for Longshan conservation and tropical rainforest restoration. The event was held in the Hani village, Nannuo Mountain, Menghai County. Professor Pei Shengji was invited to deliver a speech and participate in the tree planting. | Output 2.1: Indicator 4: One distribution map of Prinsepia Utilis Royle resources in China; 300 germplasm resources collected; 50 acres of Nitraria tangutorum germplasm resource nursery established in Yangbi, Yunnan. Indicator 5: 1-2 types of gender-sensitive community demonstration models conducted for fair and just access to and benefit sharing of genetic resources of Prinsepia Utilis Royle and its related traditional knowledge. Indicator 6: 100 mu of NBS-cultivated demonstration forest of Prinsepia Utilis Royle in Lijiang established, Yunnan, and scaled up to 500 mu. Output 2.2: Indicator 7: Cumulative application of NBS methods and ABS requirements for cultivation demonstration and scaled up to 1000 mu. Indicator 8: The application for Adenosma buchneroides Bonati geographical indications initiated. Indicator 9: Local communities’ income has increased by 10% through the planting of Adenosma buchneroides Bonati. (of which 20% of the total number of beneficiaries are women). Output 2.3: Indicator 10: One investigation and evaluation report developed. Indicator 11: 20 kinds of surveys of germplasm resources of wild native tree species in the Lijiang area and their related traditional knowledge, and 1 investigation report. Output 2.4: Indicator 12: One or two feasibility technical guidelines, village rules, and regulations and other policy recommendations, related to the protection of the Long Mountain. | Output 2.1: There is no resource investigation of Prinsepia utilis Royle. Output 2.2: Currently, the demonstration and promotion area of industrialized cultivation of Adenosma buchneroides Bonati is limited. It is not a geographical indication product. No survey data. Output 2.3: No baseline investigation. No investigation report. Output 2.4: No standardized documents. |  | Output 2.1: - A 50-acre germplasm resource garden of Prinsepia utilis Royle established in Yangbi, Yunnan, to cultivate and protect the planting of all available Prinsepia utilis Royle varieties. - Enterprises and communities signed 2-5 agreements on access to genetic resources and benefit sharing. - Using nature-based solutions to build demonstration forests. Output 2.2: - The industrialized cultivation demonstration and promotion system of Adenosma buchneroides Bonati in Dakalaozhai, Menglun Town, and Gongbing New Village, Menglun Town developed. 2-5 agreements on access to genetic resources and benefit sharing between enterprises and communities signed. - 3 new products with Adenosma buchneroides Bonati as the raw material developed. - The community got involved in the process of cultivating and developing new products. Output 2.3: - Carrying out the investigation, protection and evaluation of the germplasm resources of 20 wild plants in Lijiang area, and form phased results. - An investigation and assessment of the germplasm resources of 20 kinds of wild native tree species in Lijiang and their related traditional knowledge, and achieving interim results. Output 2.4: Recommendation draft. | Output 2.1: Indicator 4: 90% of annual target; 90% against EOP target Indicator 5: 80% of annual target; 80% against EOP target Indicator 6: 90% of annual target; 90% against EOP target Output 2.2: Indicator 7: 100% of annual target; 80% against EOP target Indicator 8: 100% of annual target; 60% against EOP target Indicator 9: 90% of annual target; 40% against EOP target Output 2.3: Indicator 10: 50% of annual target; 60% against EOP target Indicator 11: 50% of annual target; 60% against EOP target Output 2.4: Indicator 12: 70% of annual target; 30% against EOP target |
| Output 2.1: Develop the distribution map of Prinsepia Utilis Royle resources in China, establish 50 mu (3.3 hectares) germplasm resource area of Prinsepia Utilis Royle in Yangbi County, Yunnan Province. Carry out the demonstration of artificial high-yield cultivation of Prinsepia Utilis Royle through the NBS method. |  |  |  |  |  |  |
| Output 2.2: Establish a cultivation demonstration and promotion system for Adenosma buchneroides Bonati in Daka Laozhai and Gongbian New Village of Menglun Township through NBS and community participatory ways. Establish a community demonstration model on Access to and Benefit Sharing (ABS) of Adenosma buchneroides Bonati Genetic Resources and Associated Traditional Knowledge. Develop three new products made from Adenosma buchneroides Bonati and apply for Adenosma buchneroides Bonati geographical indications. |  |  |  |  |  |  |
| Output 2.3: Conduct survey, collection, protection, and evaluation for 20 species of wild plant germplasm resources in Lijiang, conducting investigation and collecting research on the germplasm resources of 20 wild native tree species and their related traditional knowledge in the Lijiang area. |  |  |  |  |  |  |
| Output 2.4: Summarize one or two feasibility technical guidelines, village rules and other recommendations, related to the protection of the Long Mountain, promoting the mainstreaming of the Long Mountain conservation system. |  |  |  |  |  |  |
| Outcome 3: Enhancing biodiversity awareness and capacity building in society and enterprises | Activities regarding biodiversity conservation were carried out, and the public awareness was raised. - Completed three sessions of rural science popularization training (in Mengla County, Tonghai County, and Lushui City), with female participants accounting for 62.89%. - Finalized the design of promotional brochures. - Conducted activities including botanical garden surveys, community exchanges, and engagement with primary and secondary schools. - Completed preliminary designs for cultural and creative products. - Organized a "Guardian of Biodiversity" exchange forum. - Initiated the establishment of a youth network. | Indicator 13: 1-2 capacity building activities annually, with a total training population of 2,000 (60% women). Indicator 14: Timely dissemination and promotion of the output contents of Outcomes 1, 2, and 3, as well as the excavation of five typical cases (including 1-2 gender mainstreaming cases) of organic integration of traditional ethnic culture and biodiversity conservation, Organizing 2 campus biodiversity conservation work collection exhibitions (50% women participants) and making 2-3 types of brochures. Indicator 15: Two Youth Biodiversity Action Network meetings, three biodiversity forums, three training sessions (50% women participants) and one recommendation. Indicator 16: 1 practical handbook on biodiversity conservation and utilization for local women (Published in Chinese and English versions), Conducting 3 training sessions (50% women participants). | Not Measured |  | - By leveraging the annual meeting of DR PLANT, capacity-building opportunities provided for enterprises, suppliers, and other stakeholders 1-2 times. The total number of trainees is 1000 (60% are women). - Capacity building for enterprises, suppliers and other stakeholders for one time. Timely dissemination and promotion the output contents of Outcomes 1, 2 and 3, as well as the excavation of two typical cases of organic integration of traditional ethnic culture and biodiversity conservation, Organizing 1 campus biodiversity conservation work collection exhibitions and make 1-2 types of brochures. - One Youth Biodiversity Action Network meeting, one biodiversity forum, one training. - 4. Finalizing the draft. Conduct 2 training sessions. | Indicator 13: 100% of annual target; 100% against EOP target Indicator 14: 50% of annual target; 50% against EOP target Indicator 15: 50% of annual target; 50% against EOP target Indicator 16: 60% of annual target; 60% against EOP target |
| Output 3.1: Carry out capacity building on biodiversity for the enterprises, suppliers, and customer groups of DR PLANT. |  |  |  |  |  |  |
| Output 3.2: Timely disseminate and promote the contents of Outcomes 1, 2, and 3, and explore and summarize best practices for the synergy of traditional ethnic culture and biodiversity. |  |  |  |  |  |  |
| Output 3.3: Carry out events on “Youth Biodiversity Action Network in Yunnan”, organize the Southwest Associated University High-level Forum on Biodiversity Theme, and conduct training on traditional culture and biodiversity for rural communities. |  |  |  |  |  |  |
| Output 3.4: Develop one practical handbook on biodiversity conservation and utilization for local women. Promote it and provide training sessions for women in rural communities and related units at the project sites to improve their ability. |  |  |  |  |  |  |

B.2 Project Impact

- Leading the Development of International Standards
Through proactive engagement that secured supportive feedback from the Chair of ISO/TC331 and relevant working group convenors, China has spearheaded the development of the first international standard on biodiversity conservation in the cosmetics industry to be led by China from the drafting stage (‘Guidelines on Biodiversity Conservation in the Raw Material Origin of Cosmetic Enterprises’). This initiative successfully integrates corporate biodiversity action into mainstream international standardization. It represents a significant step by China in leading the implementation of the ‘Kunming-Montreal Global Biodiversity Framework’ and is crucial for enhancing China's international leadership in this field.

- Establishing a Technical Foundation for National Policy and Markets
The national standard ‘Guidelines for Enterprise Biodiversity Information Disclosure’ provides essential policy direction and technical guidance to promote corporate engagement in biodiversity governance. Its anticipated impacts are multi-faceted: it guides companies in identifying and managing biodiversity-related risks and opportunities, thereby strengthening their long-term competitiveness, sustainable development, and brand reputation through proactive disclosure. For investors, it provides a basis for comprehensive assessment of corporate practices, fostering green finance. For regulators, it offers a consistent benchmark, improving supervisory efficiency and supporting targeted policy-making. Ultimately, it motivates proactive corporate conservation and restoration measures, advancing global and national biodiversity targets while fostering collaborative action across society.

- Innovating Technical Systems for Sustainable Development
To overcome the industrial bottlenecks hindering Prinsepia utilis cultivation, the project has selected superior varieties and established an innovative high-yield cultivation system. This breakthrough provides critical technical support for the industry's development and contributes significantly to: fostering plateau-specific characteristic agriculture, stimulating regional economic growth and rural industrial restructuring, improving the local ecological environment, and promoting poverty alleviation in mountainous regions. Moreover, the project's approach aligns with all three objectives of the Convention on Biological Diversity—conservation, sustainable use, and fair benefit-sharing—positioning it as a model with global demonstration value.

IV. Building a Pathway from Local Practice to Policy Influence
Through systematic community capacity building and public awareness campaigns, the project has established a coherent model for influencing local practices and policies, generating tangible developmental and policy impacts. Developmentally, it has cultivated cross-generational, multi-stakeholder conservation networks in target areas, embedding sustainability principles within communities and schools. This has empowered local residents, particularly rural women, to shift from passive beneficiaries to active participants, creating a social foundation for widespread sustainable practices. In terms of policy impact, the project has generated field-tested case studies, training models, and platforms like the ‘Yunnan Youth Biodiversity Action Network,’ providing local governments with replicable blueprints. These grassroots insights and consensus will form the foundation of a forthcoming ‘Policy Recommendations Report,’ which aims to integrate biodiversity conservation into local education, community planning, and corporate evaluations. This effort is expected to directly inform the ‘Ecological Civilization Construction’ agenda and the local implementation of the ‘Post-2020 Global Biodiversity Framework,’ effectively scaling the project's impact from discrete community pilots to broader regional policy adoption.

C. RISK MANAGEMENT

| # | Updates on valid risk entries on risk log with treatments | Identification of new risks emerging in 2025(if any) |
| --- | --- | --- |
| 1 | In 2025, the project team enhanced its strategy to mitigate the Operational Risk, previously recorded in the Project Document as Risk 1,Risk 2 and Risk 3. - Risk 1 (Inadequate Coordination Among Agencies) Risk Category: Institutional / Governance Risk Rating: Low Risk Assessment: The absence of formal coordination mechanisms between key implementing agencies could lead to misaligned priorities, duplicated efforts, communication gaps, and inefficiencies. This would limit the effectiveness of project implementation, delay activities, and jeopardize the achievement of planned results and impacts. Mitigation Measures: Establishing a Project Steering Committee (PSC) with decision-making authority, composed of senior representatives from all key agencies and relevant experts, to provide strategic oversight, approve work plans, and resolve issues. The Project Management Office (PMO) is specifically mandated to ensure day-to-day coordination and cooperation among all units based on PSC-approved plans. Monitoring Indicator 1: PSC is formally established, with its inaugural meeting convened and minutes documented. Monitoring Indicator 2: Under the leadership of the project’s Chief Technical Advisor, Professor Xue Dayuan, a quarterly reporting mechanism has been instituted. The meetings held under this mechanism aim to gain a clear understanding of each partner’s progress, monitor project developments in real time, and resolve any issues encountered during implementation. A summary report is produced following each of these sessions. Responsible Party: Project Management Office (PMO) Monitoring Frequency: Quarterly - Risk 2 (Limited Participation in Pilot Village) Risk Category: Social Risk Rating: Low Risk Assessment: Inadequate interest or engagement from beneficiary farmers in the pilot villages could lead to poor attendance in project activities, low adoption of demonstrated practices, and insufficient local ownership. This would directly reduce the effectiveness, quality, and sustainability of project outputs, potentially causing the pilot initiatives to fail to achieve their intended demonstration and impact goals. Mitigation Measures: Proactive and continuous community engagement built on previously positive feedback and established partnerships with local government. This is reinforced by integrating traditional knowledge, ensuring activities align with local priorities, and implementing a dedicated capacity-building program to enhance farmers' skills and confidence in participating in ABS practices and biodiversity conservation. Monitoring Indicator 1: Two community-based agricultural specialized cooperatives (one in Daka Laozhai and one in Gongbian New Village) are formally established and operational, with women holding leadership positions. Monitoring Indicator 2: At least two new products derived from Adenosma buchneroides are developed, with progress on market entry or geographical indication (GI) application preparation documented. Responsible Party: Project Management Office (PMO) Monitoring Frequency: Quarterly - Risk 3 (Prolonged Approval Timeline for an International Standard) Risk Category: Operational Risk Rating: Low Risk Assessment: The formal, multi-stage process for developing and approving a new ISO international standard is inherently lengthy and may extend beyond the project's implementation period. Failure to secure the standard's establishment by project closure would represent a major unachieved output, undermining a core project objective, limiting the long-term impact of the work, and potentially affecting the project's credibility and legacy. Mitigation Measures: Proactive and structured collaboration with the China National Institute of Standardization (CNIS) as the domestic technical counterpart. This includes a clear division of labor, adherence to a detailed, time-bound workplan to prepare all necessary technical documentation, and strict compliance with the submission protocols of both the National Standardization Administration and ISO/TC331 to expedite the process as much as possible. Monitoring Indicator 1: The complete application package for the international standard "Guidelines on Biodiversity Conservation in the Raw Material Origin of Cosmetic Enterprises" is formally submitted to the China National Institute of Standardization (CNIS). Monitoring Indicator 2: The national standard "Guidelines for Enterprise Biodiversity Information Disclosure" is officially released for public consultation on the National Standard Information Public Service Platform. Responsible Party: Project Management Office (PMO) Monitoring Frequency: Quarterly review of milestone progress against the standardization workplan. |  |

D. GENDER

Please choose the Gender marker rating of this project: ☐GEN-3; ☒GEN-2; ☐GEN-1

| Results and Contributions |  |  |
| --- | --- | --- |
| Please elaborate on the results and contributions this project has made to ONE or MULTIPLE relevant Gender Equality Strategy 2022-2025 priority areas of work during the reporting year. Please provide relevant evidence to support the claims. |  |  |
| 1 | Promote women’s economic empowerment, employment, and access to resources, and diminishing the structural barriers in economies that keep women behind. | Yes. The establishment of agricultural specialized cooperatives in the project villages provides an institutional mechanism for community members, including women, to engage in collective economic activities. Of the participants in capacity-building training, 60% are targeted to be women. This target saw preliminary results in the rural science training sessions conducted in Tonghai County and Lushui City. Additionally, activities such as community exchanges and cultural product design sessions have actively ensured gender balance and encouraged women's active participation and self-expression. |
| 2 | Support the incorporation of gender considerations into local economic and social development plans, accelerate women’s equal representation in local governance, especially in rural areas. | Yes. More than 50% of women's participation in the project was achieved mainly by providing women with more working opportunities. Women's leading role in the project was enhanced by establishing the cooperatives, publicity, etc. |
| 3 | Support building gender-responsive resilience to a wide range of shocks and crises, including conflict, climate change, disasters, environmental degradation and epidemics. |  |
| 4 | Support women’s improved access, use, and control of resources, and enhance women’s participation and leadership role in climate action. |  |
| 5 | Promote gender equality in green energy systems, policies, decision-making and ownership, as well as at the technical and service provision levels. |  |
| 6 | Raise awareness on gender equality and challenge the gender stereotype and biased social norms that limit women’s equal rights and opportunities | Through activities engaging primary and secondary schools, we promote gender equality and challenge the stereotype that environmental work is a male domain. |
| Resources Allocation |  |  |
| 7 | How much of the annual project budget/resources has been allocated to address the identified needs of women and men? If no investment has been made, does the project plan to increase project investment to support women’s empowerment and gender equality? | In Outcome 3, approximately 30% of the project budget was earmarked for activities supporting women's participation, such as women-specific training and fees for female instructors. Looking ahead, the project plans to further increase resource allocation for gender equality in the identification of exemplary cases and the development of policy recommendations. |
| Challenges & Lessons Learned |  |  |
| 8 | What are some key challenges/potential risks faced by the project in (further) promoting women's empowerment and gender equality? What are the possible mitigation measures the project will adopt to tackle those challenges? | In some rural and remote areas, some villagers still hold the traditional ideas regarding gender equality. Mitigation Measures: - Strengthen Partnerships with Local Women's Organizations: Moving beyond general collaboration, the project will engage local women's organizations (e.g., Women's Federations, women's cooperatives, community women's groups) in the co-design and review of activity plans. This ensures content is relevant to local women's practical needs and cultural context. A regular consultation mechanism will also be established, positioning these organizations as key implementation and feedback channels at the community level. - Design and Promote Women-Centered Activity Models: When planning trainings, workshops, and outreach, the project will proactively adopt the following methods to enhance accessibility and appeal: - Convenient Timing & Location: Prioritize scheduling activities at times and in places convenient for women's participation (e.g., community centers, during agricultural off-seasons). - Relevant Content: Training content will be closely aligned with the productive lives and realities of local women (e.g., agroforestry, handicraft development, natural resource management). - Participatory Approaches: Utilize participatory tools to encourage women to share experiences and voice their needs, ensuring activities address their genuine concerns and provide applicable skills. - Establish Multi-Level Incentives for Women's Participation: - Practical Incentives: Provide productive assets (e.g., quality seedlings, small-scale farming tools) as incentives for women who actively complete training programs. - Development Opportunities: Prioritize selecting engaged women for advanced training, study tours, or roles as community promoters, creating pathways for skill advancement and leadership development. |
| Knowledge Management |  |  |
| 9 | Have success story(ies) of female beneficiaries have been featured and shared as examples of the project’s key achievement in promoting women’s empowerment and gender equality? Are both women and men represented and visible in the communication products? | Yes. At Daka Laozhai and Gongbian New Village, the established cooperatives are led by women. Women are also actively involved in various stages of Adenosma buchneroides Bonati production process—including planting, weeding, and essential oil extraction—and receive corresponding remuneration (approximately 10,000 yuan per month). Additionally, the Daka Laozhai cooperative has organized over ten women to sew Adenosma buchneroides Bonati sachets. |

E. KNOWLEDGE PRODUCT & VISIBILITY

| # | Details of communications activities |  | Linked Project Result |  |  | Date | External link (if applicable) |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | The national standard project "Guidelines for Enterprise Biodiversity Information Disclosure" has been officially initiated. |  | Outcome 1 |  |  | 7/15/2025 | https://www.ynlky.org.cn/index.php?id=2061 |  |
| 2 | Reports about Prinsepia Utilis Royle | Output 2.1 | 11/3/2025 | https://www.ynlky.org.cn/index.php?id=2158 |
| 3 |  |  | 9/9/2025 | https://www.ynlky.org.cn/index.php?id=2121 |
| 4 |  |  | 8/21/2025 | https://www.ynlky.org.cn/index.php?id=2099 |
| 5 |  |  | 8/12/2025 | https://www.ynlky.org.cn/index.php?id=2087 |
| 6 |  |  | 5/28/2025 | https://www.ynlky.org.cn/index.php?id=2031 |
| 7 |  |  | 3/10/2025 | https://www.ynlky.org.cn/index.php?id=19707 |
| 8 |  |  | 1/4/2025 | https://www.ynlky.org.cn/index.php?id=1931 |
| 9 | Reports about Adenosma buchneroides | Output 2.2 | 8/11/2025 | https://mtydazzle.yntv.cn/pages/details/details.html?companyId=ysxw&productId=7F9A1B14E41B4259A34223A7D744C0DB&docid=12FBEC84A08046FAAECCDEB20D4FAAF8&isNew=yes&downloadTips=true&jumpCode=QCYD&type=news&articleType=1 |
| 10 |  |  | 9/5/2025 | https://www.peopleapp.com/column/30050172697-500007071129 |
| 11 |  |  | 9/8/2025 | https://mp.weixin.qq.com/s/nFc__bDD_x-KTmBmjUNZIA |
| 12 |  |  | 9/25/2025 | https://baijiahao.baidu.com/s?id=1844238988606164112&wfr=spider&for=pc |
| 13 |  |  | 10/17/2025 | https://ynrb-wap.yndaily.com/news_details.html?from=androidapp&eid=ba9c23076206303e&timestamp=1760802417533 |
| 14 |  |  | 10/28/2025 | https://mp.weixin.qq.com/s?__biz=MzAxNzAxOTg2Mw==&mid=2652639781&idx=3&sn=2777ee106ad7cfeceff51c55b947094f&chksm=8136b0afca298677f50440ca02f33ed8042591d98903f37e4257408ebc3131712832937c203f&scene=27 |
| 15 | Reports about Symposium on Human-Nature Harmony: Collaborative Pathways for Biodiversity | Cross-Cutting for All Outcomes | 8/8/2025 | https://www.xinhuanet.com/fashion/20250808/8747b29b91134ccba5cfdc4b8537730c/c.html |
| 16 |  |  | 8/8/2025 | https://cj.sina.com.cn/articles/view/2311077472/89c03e6002002dorg |
| 17 |  |  | 8/8/2025 | https://www.sohu.com/a/921993785_436021?scm=10001.501_13-100000-0_922.0-0.0.a2_5X162X1640 |
| 18 |  |  | 8/14/2025 | https://www.163.com/dy/article/K6TP462A0550789W.html |
| 19 |  |  | 8/12/2025 | https://www.ynlky.org.cn/index.php?id=2086 |
| 20 | Report about the 1st PSC meeting | PMO management | 1/10/2025 | https://www.ynlky.org.cn/index.php?id=1914 |
| 21 | Report about the biodiversity monitoring survey of a 1-hectare specialized observation plot in Zhugu Snow Mountain. | Output 2.3 | 10/1/2025 | http://groups.kib.cas.cn/ljz/xwgg/kydt/202510/t20251006_780520.html |
| 22 | Xishuangbanna Initiative Launched for "Sacred Natural Site" Conservation and Restoration | Output 2.4 | 5/25/2025 | https://m.yunnan.cn/system/2025/05/25/033491463.shtml |
| 23 | Report about Enhancing biodiversity awareness and capacity building | Outcome 3 |  | 7/1/2025 | https://mp.weixin.qq.com/s/um4ZuwEtopp3Tm-tr0W0bw |  |  |
| 24 |  |  |  | 9/1/2025 | https://mp.weixin.qq.com/s/35469XxWmCl0vZSHgRSejQ |  |  |
| 25 |  |  |  | 3/1/2025 | https://mp.weixin.qq.com/s/PzSclAcRjILXpSZJC4sWog |  |  |

F. LESSONS LEARNED

| # | Off-Track/Lessons Learned | Course of Action |
| --- | --- | --- |
|  | Lessons learned | - The proposal of international standards faces various challenges. Internationally, within ISO/TC331, there are dynamics and competition among member countries for leadership in setting standards. In the field of corporate biodiversity, the number of standards under development or in preparation is the highest, indicating the most intense competition. Domestically, China currently has a substantial reserve of international standard proposals, but there are potential issues with proposal strategies. To address these challenges, the project team has actively engaged with the Chair of ISO/TC331 and the convenors of relevant working groups overseeing the proposed standards, receiving supportive feedback. Additionally, the team has fully leveraged expert input, incorporating their insights to enrich and refine the project deliverables. Moving forward, continuous communication with experts from ISO/TC331 will be maintained to seek further support. Based on feedback from published and developing international standards, as well as input from domestic technical mirror committee experts, relevant research will be actively conducted to revise and improve the draft international standards and supporting materials, aiming to secure endorsement from domestic technical experts. - The project is implemented in regions with concentrated ethnic minority populations, where different ethnic groups have distinct living habits, beliefs, and cultures. During implementation, it is essential to enhance the participation of local ethnic minority communities to prevent cultural differences from hindering progress. Particularly in the Naxi community in Lijiang, given the significant role women play in daily labor, their participation should be actively encouraged, and technical training should be provided to facilitate the smooth implementation and completion of the project. - Establishing and leveraging a localized cooperation network is fundamental to the project’s success. In the early stages, close collaboration with the Xishuangbanna Tropical Botanical Garden, local schools, and community organizations helped quickly establish a foundation for work. This experience demonstrates that treating local partners as co-owners rather than mere implementers effectively utilizes their local knowledge, community trust, and existing networks, significantly improving the efficiency and engagement of activities while laying a solid foundation for the project’s sustainability. - Translating gender equality objectives into measurable activity designs is key to ensuring women’s participation. In activity planning, clear targets for female participation were set (e.g., 60% women in training sessions). This approach compelled the team to proactively consider women’s needs in areas such as promotion, recruitment, and scheduling. Experience shows that without quantifiable targets, gender mainstreaming risks becoming mere rhetoric. This good practice ensures women’s voices are not overshadowed and should be continued and extended to all sub-projects. - Combining "targeted outreach" with "educational integration" forms an effective dual-track approach to raising public awareness. On one hand, the project generated short-term impact through focused activities such as community exchange sessions and promotional brochures. On the other hand, long-term educational partnerships with primary and secondary schools enabled systematic immersion in biodiversity knowledge. Experience indicates that short-term initiatives and long-term educational mechanisms complement each other—quickly raising the project’s visibility while ensuring depth and sustainability in awareness-building. This is an effective strategy to address challenges in public engagement. |

Please refer to UNDP Gender Equality Strategy 2022-2025 for more details: https://genderequalitystrategy.undp.org/#