| EXPECTED OUTPUTS | OUTPUT INDICATORS | BASELINE |  | TARGETS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Value | Year 2023 | Year ½ 2024 | Actual | Year 2025 | Actual | Up to date | Comment |
| Output 1: Development and implementation of Community Development Plans (CDPs). Outputs: Strengthened capacities of 157 mahallas in Samarkand, Kashkadarya, and Surkhandarya regions in participatory CDP process that result in development, implementation, and oversight of climate smart CDPs focusing on improvements of infrastructure and services. | 1.1 Number of target communities identified for CDPs development in 3 targeted regions to prioritize villages with high poverty rates and underdeveloped infrastructure. Number of platforms for CDPs development and implementation enabling access of local people. | 0 |  | 157 | 157 |  |  | 157 | 2024 KPIs: 1. 157 communities identified by the Ministry of Economy and Finance and regional khokimiats. Regional and district authorities, selected communities, regional departments of line ministries, and mass media of Surkhandarya, Kashkadarya, and Samarkand regions increased awareness about project implementation activities for 2024 – 2028: - Surkhandarya region - 5 districts, 60 communities - Samarkand region - 10 districts, 52 communities - Kashkadarya region - 6 districts, 45 communities - 2025 KPIs: N/A |
|  | 1.2 Number of community leaders, CSOs members, women, young women and men, persons with disabilities trained to engage into community CDPs development, implementation, and oversight | 0 |  | 2500 | 11000 | 2,500 | 10,642 | 21,642 | 2024 KPIs: 11,000 community members trained mobilization workshops (6587 males/4413 females) - Surkhandarya 4323 people (2523 males/1800 females), - Kashkadarya 3298 people (2013 males/1285 females) - Samarkand 3379 people (2051 males/1328 females) - 2025 KPIs: 10642 participants (3764 women) -ToT for facilitators: 36 people (10 women, 26 men) - Summer school for IG members: 47 people (17 wome, 30 men) -9917 community members (3669 women, 6248 men) involved in CDP presentations -642 people of working groups participated in CDP presentations (68 women, 574 men) |
|  | 1.3 Number of participatory needs assessments – community mobilization workshops of target communities completed, based on experiences of IsDB, UNDP and WB | No capacity in targeted communities to identify priorities for interventions. |  | 77 | 157 | 80 | 0 | 157 | 2024 KPIs: 1. Mobilization workshops in 157 communities of Samarkand, Kashkadarya and Surkhandarya regions: - Surkhandarya region (60 communities) - Kashkadarya region (45 communities) - Samarkand region (52 communities) SWOT analysis completed in 157 communities in three pilot regions - 2025 KPIs: N/A |
|  | 1.4 Number of costed options – subprojects developed for community infrastructural investments through community engagement, using innovative ICT solutions. Numbers of CDP developed. | 0 |  | 150 77 | 0 0 | 164 80 | 779 157 | 0 157 | 2024 KPIs: 0 - 2025 KPIs: 779 subprojects identified and 157 CDPs developed: 1. 779 subprojects finalized and approved • - Kashkadarya – 222 subprojects • - Samarkand – 279 subprojects • - Surkhandarya – 278 subprojects • 2. 157 CDPs (41 Cluster CDPs) developed: • - Kashkadarya – 11 Cluster CDPs • - Samarkand – 16 Cluster CDPs • - Surkhandarya – 14 ClusterCDPs • Kashkadarya – 222 subprojects |
|  | 1.5 Number of community leaders, CSOs members, women, young women and men, persons with disabilities trained in M&E and other topics | 0 | 0 | 0 | 0 | 1256 | 2112 | 2112 | 2024 KPIs: 1. Development of Cluster CDPs for the 157 selected communities: Draft version of Cluster CDPs initiated on verified sub-projects chosen by 77 community members. 2. 21 Cluster CDPs of 77 communities drafted and revised - 2025 KPIs: - -ToT on Monitoring and Evaluation: 18 participants (9 women, 9 men) - -Training on M&E: 800 people (222 women, 578 men) -ToT on Project Design: 18 people (9 women, 9 men) -Training on Project Design:1294 people (395 women, 899 men) |
| Output 2: Capacity building in income generation, with focus on vulnerable groups. Outputs: Strengthened capacities of businesses and individuals such as entrepreneurs who work in agriculture complex, including the vulnerable groups in businesses development/expansion. | 2.1 Number of regional market diagnostics/assessment of local business capacities | Limited information/analysis of regional market conditions | 0 | 0 | 0 | 1 | 1 | 0 | - 2025 KPIs: -In-depth diagnostic assessment of the business opportunities and applicability of climate-resilient solutions in agriculture |
|  | 2.2 Number of local rural businesswomen and men trained, with primary focus on the poor, women who are heads of households, youth and persons with disabilities. Training topics will be informed by regional market diagnostics. Vulnerable beneficiaries to be identified by communities. Trainings can be delivered in partnership with CSOs. | Limited capacity of local rural business people to adopt modern business practices | 0 | 0 | 0 | 400 | 156 | 156 | - 2025 KPIs: - 101 women participated in trainings on business development on modern design (sewing) for rural women. - 55 young people (2 women, 53 men) from rural population participated in trainings on mobilography and SMM for rural youth |
|  | 2.3 Number of smallholder farmers trained on climate-smart solutions to increase agricultural productivity and inclusion into the value chain (e.g., water harvesting, drip irrigation, marketing) and crops diversification (e.g., fruit and nut trees). | Limited knowledge and skills of smallholder farmers to adopt climate smart solutions | 0 | 0 | 0 | 150 | 136 | 136 | 2025 KPIs: -Training Needs Assessment report including 3-year training program for 5 target groups of agriculture sector developed. -78 participants attended the training on crop diversity (13 women and 62 men). -64 participants (1 women, 63 men) attended the trainings on agroecology and innovative solutions for sustainable agriculture. |
|  | 2.4 Number of farmers, businesses and individuals who received hands-on follow up technical support on inputs and technologies, sales and marketing | 0 | 0 | 0 | 0 | 50 | 0 | 0 | - 2025 KPIs: 0 |
|  | 2.5 Number of locally relevant climate smart and energy efficient business solutions identified and promoted | 0 | 0 | 0 | 0 | 1 | 1 | 1 | - 2025 KPIs: - 9 Low-GWP (propane) air conditioners were installed at three rural medical centers |
| Output 3: Capacity building of regional and local authorities | 3.1: Number of completed functional review of local authorities and communities. | 0 |  | 5 | 0 | 13 | 18 | 18 | - 2025 KPIs: -Analytical report of a functional analysis of khokimiyats and mahallas: 15 mahalas and 3 district hokimiyats |
|  | 3.2: Number of representatives of mahalla committees and initiative groups in participatory planning, implementation, and M&E with a focus on women, youth, and vulnerable groups. | 0 | 0 | 0 | 0 | 300 |  | 0 | - 2025 KPIs: - -Training on Planning and development has been planned for 2026 |
|  | 3.3 Number of representatives of district khokimiyats and mahalla committees, and initiative groups trained on climate change adaptation and mitigation | 0 | 0 | 0 | 0 | 50 | 52 | 52 | - 2025 KPIs: -Trainings on innovative tools for PR specialists of regional and district khokimiyats: 52 representatives of press-services of regional and district khokimiyats (5 women, 47 men) trained on innovative PR tools in Samarkand, Kashkadarya, and Surkhandarya regions. |
|  | 3.4: Number of participatory ICT solutions in integrated rural development planning, accountability, and sustainable management of infrastructure implemented | Limited availability of ICT solutions | 0 | 0 | 0 | 3 | 2 | 2 | - 2025 KPIs: -ICT-solution initiative was conducted in three regions. As a result, IT equipment was delivered and installed in 6 rural schools (96 PCs, 6 LAN equipment, and 6 smartboards -15 smartboards were delivered and installed in 15 kindergartens |
|  | 3.5: Number of representatives of local CSOs, women and vulnerable groups trained on effective engagement into regional and local decision-making. Some trainings can be delivered by CSOs | 0 | 0 | 0 | 0 | 25 | 70 | 70 | - 2025 KPIs: -CDP Development training for Civil Society Organizations: 70 people (38 women, 32 men) |
|  | 3.6: Number of representatives of district khokimiyats and mahalla committees, initiative groups on maintenance schemes for all infrastructure and services created through CDPs, fostering environmentally and socially responsible approaches based on low costs and participatory approaches | 0 | 0 | 0 | 0 | 80 | 5 | 5 | - 2025 KPIs: -Certified training in Istanbul, Turkey conducted: 5 people |
|  | 3.7: Number of effective practices in integrated rural development and advocacy identified for their scale-up regionally and nationally | 0 | 0 | 0 | 0 | 2 | 0 | 0 | - 2025 KPIs: 0 |