| EXPECTED OUTPUTS | OUTPUT INDICATORS | BASELINE |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Value | Year 2023 | Year ½ 2024 | Actual | Up to date | Comment |
| Output 1: Development and implementation of Community Development Plans (CDPs). Outputs: Strengthened capacities of 157 mahallas in Samarkand, Kashkadarya, and Surkhandarya regions in participatory CDP process that result in development, implementation, and oversight of climate smart CDPs focusing on improvements of infrastructure and services. | 1.1 Number of target communities identified for CDPs development in 3 targeted regions to prioritize villages with high poverty rates and underdeveloped infrastructure. Number of platforms for CDPs development and implementation enabling access of local people. | 0 |  | 157 | 157 | 157 | 1. 157 communities identified by the Ministry of Economy and Finance and regional khokimiats. Regional and district authorities, selected communities, regional departments of line ministries, and mass media of Surkhandarya, Kashkadarya, and Samarkand regions increased awareness about project implementation activities for 2024 – 2028: - Surkhandarya region - 5 districts, 60 communities - Samarkand region - 10 districts, 52 communities - Kashkadarya region - 6 districts, 45 communities |
|  | 1.2 Number of community leaders, CSOs members, women, young women and men, persons with disabilities trained to engage into community CDPs development, implementation, and oversight | 0 |  | 2500 | 11000 | 11000 | 11,000 community members trained mobilization workshops (6587 males/4413 females) - Surkhandarya 4323 people (2523 males/1800 females), - Kashkadarya 3298 people (2013 males/1285 females) - Samarkand 3379 people (2051 males/1328 females) |
|  | 1.3 Number of participatory needs assessments – community mobilization workshops of target communities completed, based on experiences of IsDB, UNDP and WB | No capacity in targeted communities to identify priorities for interventions. |  | 77 | 157 | 157 | 1. Mobilization workshops in 157 communities of Samarkand, Kashkadarya and Surkhandarya regions: - Surkhandarya region (60 communities) - Kashkadarya region (45 communities) - Samarkand region (52 communities) SWOT analysis completed in 157 communities in three pilot regions |
|  | 1.4 Number of costed options – subprojects developed for community infrastructural investments through community engagement, using innovative ICT solutions. Numbers of CDP developed. | 0 |  | 150 77 | 0 77 | 0 77 | 1. Project technical alignment discussions conducted in three pilot regions khokimiats on final selection of subprojects for 157 communities. As a result, 780 subprojects identified 2. Study tour to Korea and Vietnam to see best practices of rural development, digitalization, energy and water efficiency projects, CDP and other best practices conducted on November 19-29, 2024 3. ToR for Baseline Assessment of 41 pilot communities in 21 districts in three pilot regions finalized and agreed by the PIU. Data collection methodology designed and the schedule for data collection set. |
|  | 1.5 Number of community leaders, CSOs members, women, young women and men, persons with disabilities trained in M&E and other topics | 0 | 0 | 0 | 0 | 0 | 1. Development of Cluster CDPs for the 157 selected communities: Draft version of Cluster CDPs initiated on verified sub-projects chosen by 77 community members. 2. 21 Cluster CDPs of 77 communities drafted and revised |
| Output 2: Capacity building in income generation, with focus on vulnerable groups. Outputs: Strengthened capacities of businesses and individuals such as entrepreneurs who work in agriculture complex, including the vulnerable groups in businesses development/expansion. | 2.1 Number of regional market diagnostics/assessment of local business capacities | Limited information/analysis of regional market conditions | 0 | 0 | 0 | 0 | N/A |
|  | 2.2 Number of local rural businesswomen and men trained, with primary focus on the poor, women who are heads of households, youth and persons with disabilities. Training topics will be informed by regional market diagnostics. Vulnerable beneficiaries to be identified by communities. Trainings can be delivered in partnership with CSOs. | Limited capacity of local rural business people to adopt modern business practices | 0 | 0 | 0 | 0 | N/A |
|  | 2.3 Number of smallholder farmers trained on climate-smart solutions to increase agricultural productivity and inclusion into the value chain (e.g., water harvesting, drip irrigation, marketing) and crops diversification (e.g., fruit and nut trees). | Limited knowledge and skills of smallholder farmers to adopt climate smart solutions | 0 | 0 | 0 | 0 | N/A |
|  | 2.4 Number of farmers, businesses and individuals who received hands-on follow up technical support on inputs and technologies, sales and marketing | 0 | 0 | 0 | 0 | 0 | N/A |
|  | 2.5 Number of locally relevant climate smart and energy efficient business solutions identified and promoted | 0 | 0 | 0 | 0 | 0 | N/A |
| Output 3: Capacity building of regional and local authorities | 3.1: Number of completed functional review of local authorities and communities. | 0 |  | 5 | 0 | 0 | Functional reviews are planned for 2025 |
|  | 3.2: Number of representatives of mahalla committees and initiative groups in participatory planning, implementation, and M&E with a focus on women, youth, and vulnerable groups. | 0 | 0 | 0 | 0 | 0 | N/A |
|  | 3.3 Number of representatives of district khokimiyats and mahalla committees and initiative groups trained on climate change adaptation and mitigation | 0 | 0 | 0 | 0 | 0 | N/A |
|  | 3.4: Number of participatory ICT solutions in integrated rural development planning, accountability, and sustainable management of infrastructure implemented | Limited availability of ICT solutions | 0 | 0 | 0 | 0 | N/A |
|  | 3.5: Number of representatives of local CSOs, women and vulnerable groups trained on effective engagement into regional and local decision-making. Some trainings can be delivered by CSOs | 0 | 0 | 0 | 0 | 0 | N/A |
|  | 3.6: Number of representatives of district khokimiyats and mahalla committees, initiative groups on maintenance schemes for all infrastructure and services created through CDPs, fostering environmentally and socially responsible approaches based on low costs and participatory approaches | 0 | 0 | 0 | 0 | 0 | N/A |
|  | 3.7: Number of effective practices in integrated rural development and advocacy identified for their scale-up regionally and nationally | 0 | 0 | 0 | 0 | 0 | N/A |