Islamic Development Bank

Ministry of Economy and Finance of the Republic of Uzbekistan

United Nations Development Programme in Uzbekistan

| Project Title: | IsDB Integrated Rural Development Project Component B: Consultancy services for rural infrastructure development – Community empowerment. |
| --- | --- |
| Country: | Uzbekistan |
| Contract Number: | Agreement for delivery outputs |
| Implementation period: | 13 May 2024 – 31 December 2028 (56 months) |

PROJECT NARRATIVE REPORT

| Reporting period: | January 1 – December 31, 2024 |
| --- | --- |
| Report prepared by: | UNDP CO Uzbekistan |

Tashkent 2024

# TABLE OF CONTENTS

TABLE OF CONTENTS	2

ABBREVIATIONS & ACRONYMS	3

TITLE LIST	4

SECTION 1. OVERALL INFORMATION	5

EXECUTIVE SUMMARY	7

SECTION 2. DESCRIPTION AND SUMMARY OF ANNUAL PROGRESS AND RESULTS	9

PROJECT IMPLEMENTATION PROGRESS	9

PROGRESS OF ACTIVITY 1.	9

PROGRESS OF ACTIVITY 2:	19

PROGRESS OF ACTIVITY 4:	21

# ABBREVIATIONS & ACRONYMS

| APA | Annual Plan of Activities |
| --- | --- |
| AWP | Annual Work Plan |
| BOA | Budget of Action |
| BPR | Business Process Re-engineering |
| CDP CDR | Community Development Plan Combined Delivery Report |
| CO | Country Office |
| ECA | Ecologic and Climate Action Cluster |
| GOU IA | Government Operations Unit Implementing Agency |
| IsDB LDP LoA | Islamic Development Bank Local Development Plan Letter of Agreement |
| M&E | Monitoring and Evaluation |
| NIM | National Implementation Modality |
| NPC | National Project Coordinator |
| MEF | Ministry of Economy and Finance |
| OPEC Fund PIR PIU | OPEC Fund for International Development Project Implementation review Project Implementation Unit |
| PM | Project Manager |
| POPP | Programme and Operations Policies and Procedures |
| QMS RBM | Quality Management System Results-Based Management |
| RIA | Regulatory Impact Assessment |
| SDG | Sustainable Development Goals |
| TOR TOT TWG | Terms of Reference Training for Trainers Technical Working Group |
| UNDP | United Nations Development Programme |
| USD | United States Dollar |
| WB | World Bank |

# TITLE LIST

| Project number and title: | 01002383 IsDB Sustainable Rural Development Project Component B: Engineering Services and Strengthening Capacity in Infrastructure Management |
| --- | --- |
| Project Starting date: | 13 May 2024 |
| Project completion date: | 31 December 2028 |
| Implementing Partner: | Ministry of Economy and Finance of the Republic of Uzbekistan |
| Donor (s): | Islamic Development Bank & OPEC Fund for International Development |
| Contract # | Agreement to delivery output between |

| Total Budget for entire project period | Original Budget (USD) | Latest Signed Revision (USD) |
| --- | --- | --- |
|  | 6,000,000.00 | 6,000,000.00 |

| Resources | Donor | Amount (USD) |
| --- | --- | --- |
|  | Islamic Development Bank | 6,000,000.00 |
|  | Government (Parallel or cost-sharing) | N/A |

| Period covered by this report: | 01.01.2024 – 31.12.2024 |
| --- | --- |
| Date of annual review (Project Board meeting): | 10.12.2024 |

| Budget for reporting period (as per the Annex III – the Budget for the Action) | Budget (USD) (01.01.2024 – 31.12.2024) | Expenditure till 31 December 2024 (USD) |
| --- | --- | --- |
|  | 742,399.45 | 616,673.07 |

# SECTION 1. OVERALL INFORMATION

PROJECT SYNOPSIS

| Project title | IsDB Integrated Rural Development Project Component B: Consultancy services for rural infrastructure development – Community empowerment. |
| --- | --- |
| Project number | 01002385 |
| Country | Republic of Uzbekistan |
| Overall objective | This UNDP Project is an integral component of the broader Uzbekistan - Integrated Rural Development Project financed by the Islamic Development Bank (IsDB) and executed by the Ministry of Economy and Finance. The overall objective of UNDP Project is to empower and build capacities of local partners (communities, architects, engineers, local authorities) in developing and implementing local development plans and promoting locally relevant green and energy efficient. "UNDP Component B: Consultancy services for rural infrastructure development - Community empowerment, Phase II" project aims to raise the living standards, build capacity, and improve the prosperity of the rural population in three targeted regions. The Project aims to build capacities of targeted communities and partners in adopting and implementing environmentally friendly solutions. The Project will also confer positive impacts on human development through increased economic opportunities and wellbeing of targeted communities. Climate-related concerns will be mainstreamed into decision-making at all levels, facilitating climate-resilient and energy efficient development from the community level up to the regional level. The project takes a people-centred, gender sensitive and climate risk-informed holistic approach. The IRD Project is targeting Samarkand, Kashkadarya and Surkhandarya regions where poverty rates are high, with 157 mahallas where infrastructure development are lagging to be supported. |
| Outcome | Number of innovative and scalable solutions applied through systems integration in the three pilot regions |
| Outputs | Output 1: Development and implementation of Community Development Plans (CDPs). Strengthened capacities of 157 mahallas in Samarkand, Kashkadarya, and Surkhandarya regions in participatory CDP process that result in development, implementation, and oversight of climate smart CDPs focusing on improvements of infrastructure and services. Output 2: Capacity building in income generation, with focus on vulnerable groups. Strengthened capacities of businesses and individuals such as entrepreneurs who work in agriculture complex, including the vulnerable groups in businesses development/expansion. Output 3: Capacity building of regional and local authorities. Strengthened capacities of officials in all targeted regional and local authorities in participatory planning, implementation, oversight, and sustainable management of the local infrastructure and services. 2. Strengthened capacities of local residents, including the vulnerable groups in participatory decision making. Output 4: Project Management |
| Activities | Output 1: (1.1) Identification of 157 villages in 3 regions through in-depth vulnerability assessment and participatory prioritization exercise to focus on villages with high poverty rates and underdeveloped infrastructure; (1.2) Establishment of the platform for CDPs development and implementation enabling access of local people. Capacity building of community leaders, CSOs, women, youth, persons with disabilities to engage into community CDPs development, implementation, and oversight; (1.3)Participatory needs assessments of target communities, based on experiences of IsDB, UNDP and WB; (1.4) Development of costed options for community infrastructural investments. Identification of preferred options through community engagement, using innovative ICT solutions; (1.5) Support IsDB PMU in implementation of infrastructure components of CDPs; Output 2: (2.1) Regional market diagnostics/assessment of local business capacitiesRegional market diagnostics/assessment of local business capacitiesRegional market diagnostics/assessment of local business capacitiesRegional market diagnostics/assessment of local business capacities; (2.2) Design and delivery of targeted training on rural business development, with primary focus on the poor, women who are heads of households, youth, and persons with disabilities. Training topics will be informed by regional market diagnostics. Vulnerable beneficiaries to be identified by communities. Trainings can be delivered in partnership with CSOs; (2.3) Training of selected smallholder farmers on climate-smart solutions to increase agricultural productivity and inclusion into the value chain (e.g., water harvesting, drip irrigation, marketing) and crops diversification (e.g., fruit and nut trees); (2.4) Hands-on follow up technical support of farmers, businesses and individuals on inputs and technologies, sales, and marketing; (2.5) Identification and promotion of locally relevant climate smart and energy efficient business solutions; Output 3: (3.1) Functional review of local authorities and communities (selected); (3.2)Training of district khokimiyats and mahalla committees, initiative groups in participatory planning, implementation, and M&E with a focus on women, youth, and vulnerable groups; (3.3) Training of district khokimiyats and mahalla committees and initiative groups on climate change adaptation and mitigation; (3.4) Implementation of participatory ICT solutions in integrated rural development planning, accountability, and sustainable management of infrastructure; (3.5) Training of local CSOs, women and vulnerable groups on effective engagement into regional and local decision-making. Some trainings can be delivered by CSOs; (3.6) Training of district khokimiyats and mahalla committees, initiative groups on maintenance schemes for all infrastructure and services created through CDPs, fostering environmentally and socially responsible approaches based on low costs and participatory approaches; (3.7) Systematic identification of effective practices in integrated rural development and advocacy on their scale-up regionally and nationally; Output 4: (4.1) Overall management and coordination of Project implementation; (4.2) Strategic technical and methodological guidance to regional implementation Units; (4.3) Final endorsement of community projects for grant award (CDPs); (4.4) Monitoring of implementation of project activities; (4.5) Provide inputs to ECA Cluster on communication and reporting to MoEF and IsDB |
| Target groups | - Population in targeted rural areas, particularly women, youth, elderly, people with disabilities - Civil servants of government organizations and private sector who work in rural areas (doctors, architectures, farmers, teachers, designers, and others) |
| Project starting date | 13 May 2024 |
| Project duration | 13 May 2024 – 31 December 2028 (56 months) |

## EXECUTIVE SUMMARY

Uzbekistan joined the Islamic Development Bank (IsDB) in 2003 year. Uzbekistan is a landlocked country strategically located in the heart of Central Asia, bordering Kazakhstan, Tajikistan, Kyrgyz Republic, Turkmenistan, and Afghanistan. It is a lower middle-income country and rich with mineral resources. With 35 million populations (2022), Uzbekistan accounts for about 45% of the Central Asian region's total population, whereas about half of population of Uzbekistan live in rural area. It has a territory of 448.9 thousand km².

The IsDB Integrated Rural Development project – “The UNDP Component B: Consultancy services for rural infrastructure development - Community empowerment, Phase II (Project) - is a timely support to the Government’s reform agenda to mprove standards of living for the rural population in targeted areas.

The project has three major objectives. The first one is to develop and implement Community Development Plans and by this capacities of 157 mahallas in Samarkand, Kashkadarya, and Surkhandarya regions in participatory CDP process that result in development, implementation, and oversight of climate smart CDPs focusing on improvements of infrastructure and services.

The second objective is to build capacities of in income generation, with focus on vulnerable groups and strengthen capacities of businesses and individuals such as entrepreneurs who work in agriculture complex, including the vulnerable groups in businesses development/expansion.

The third objective is to build the capacities of regional and local authorities and  strengthen capacities of officials in all targeted regional and local authorities in participatory planning, implementation, oversight, and sustainable management of the local infrastructure and services. To achieve main outcome and major objectives, the project has been implemented by three pillars/components and one supportive component/pillar:

Output 1: Development and implementation of Community Development Plans (CDPs). Strengthened capacities of 157 mahallas in Samarkand, Kashkadarya, and Surkhandarya regions in participatory CDP process that result in development, implementation, and oversight of climate smart CDPs focusing on improvements of infrastructure and services.

Output 2: Capacity building in income generation, with focus on vulnerable groups. Strengthened capacities of businesses and individuals such as entrepreneurs who work in agriculture complex, including the vulnerable groups in businesses development/expansion.

Output 3: Capacity building of regional and local authorities. Strengthened capacities of officials in all targeted regional and local authorities in participatory planning, implementation, oversight, and sustainable management of the local infrastructure and services. 2. Strengthened capacities of local residents, including the vulnerable groups in participatory decision-making.

Component 4: Project management

The project will find solutions for the key barriers to sustainable environmentally friendly and energy efficient development and digital solutions in rural areas supporting human development. Here are as major challenges and barriers work for:

- Insufficient knowledge base, information, and communication on the environmentally friendly, gender-sensitive, energy efficient and digital rural areas-tailored solutions in the areas of architecture, social infrastructure, and community development.

- Limited capacities and incentives for local authorities to identify, develop and implement the environmentally friendly, gender-sensitive, energy efficient and digital rural solutions in the areas of architecture, social infrastructure, and community development.

- Limited opportunities and capacities of communities to develop plans of local development.

- Lack of gender and age disaggregated data.

The project implementation has started officially on  May 13, 2024 with the annual approved budget of USD 1,060,684.53 for 2024, where the IsDB is the main donor of the project. Project is operational in 3 pilot regions of Uzbekistan: Samarkand, Surkhandarya, and Kashkadarya regions.

In the reporting period, UNDP worked jointly with the PIU under the Ministry of Economy and Finance in the selected 157 communities located in 21 districts of Samarkand, Surkhandarya, and Kashkadarya regions by implementing activities of all three components.

In 2024, the project focused on selecting 157 pilot communities and identifying the socio-economic needs of each one. Presentations about the project were organized in the regional hokimiyats of three pilot regions. Eight local facilitators and two engineers were trained in community mobilization workshops and the development of Community Development Plans (CDPs). Participants learned skills in community needs assessment, facilitation methods, planning, evaluation, and the structure and verification processes of CDP development. Community mobilization workshops were conducted in all 157 communities, reaching a total of 11,000 people, including 6,587 males and 4,413 females. Additionally, Initiative Group members were selected, totaling 1,126 individuals. Among them, 345 were females (31%), 303 were pensioners, and 15 were people with disabilities. Also, during the report period the project focused its activities on visual and technical verifications of the subprojects and verified more than 750 sites in 157 communities.

Specifically, project activities included the followings:

- Recruitment of 9 local facilitators and 2 temporary engineers with relevant competencies in 4 regions.

- ToT trainings on community mobilization & CDP development for UNDP & PIU staff and local facilitators organized by involving national consultants

- Visual and technical verification of more than 900 sites and selection of 780 construction subprojects in three pilot regions

- Study tour  to Korea and Vietnam to see best practices of rural development, digitalization, energy and water efficiency projects, CDP and other best practices conducted on November 19-29, 2024  for representatives of Ministry of Economy and Finance, pilot khokimiyats, PIU and UNDP.

Besides, project initiated and conducted several other activities during the reporting period. Specifically:

- Initiate the process of Baseline assessment in 41 pilot communities for assessing the living conditions, employment opportunities, and social well-being of people in rural areas of Uzbekistan, as well as the impact of climate change.

- Validation assessment of 157 communities of three pilot regions.

In 2024, the project developed and placed more than 100 publications in social media resources (Facebook, LinkedIn, Twitter, Instagram, and Telegram) including national and international mass media, up to 50 press releases, video, and animated videos, infographics and posters and other visibility materials.

In the project management and operations part, during the reporting period, the project finalized the recruitment process of all 21 personnel, 3 project offices for UNDP and PIU established and furnished, procured 3 new project cars. The project launch event was held in October. The first Project Board Meeting organized in December to which the representatives of national ministries, agencies, institutions, and regional authorities of Karakalpakstan, Khorezm, Bukhara and Navoi regions, IsDB, UNDP, IFIs, and Development Partners were invited. During the meeting, the project progress for 2024 and plans for 2025 were presented and discussed.

# SECTION 2. DESCRIPTION AND SUMMARY OF ANNUAL PROGRESS AND RESULTS

## PROJECT IMPLEMENTATION PROGRESS

## PROGRESS OF ACTIVITY 1.

Development and implementation of Community Development Plans (CDPs). Outputs: Strengthened capacities of 157 mahallas in Samarkand, Kashkadarya, and Surkhandarya regions in participatory CDP process that result in development, implementation and oversight of climate smart CDPs focusing on improvements of infrastructure and services.

Activity 1.1 Identification of 157 villages in 3 regions through in-depth gender-sensitive vulnerability assessment and participatory prioritization exercise to focus on villages with high poverty rates and underdeveloped infrastructure.

Progress:

- Project discussions conducted in three pilot regions khokimiats on the final selection of 157 communities

- Project introduction presentations conducted in three pilot regions (3 regional authorities, 21 districts, and 157 communities

Photos of project presentations:

Output:

- 157 communities identified by the Ministry of Economy and Finance and regional khokimiats

- Regional and district authorities, selected communities, regional departments of line ministries, and mass media of Surkhandarya, Kashkadarya, and Samarkand regions increased awareness about project implementation activities for 2024 – 2028:

- Surkhandarya region - 5 districts,  60 communities

- Samarkand region - 10 districts, 52 communities

- Kashkadarya region - 6 districts, 45 communities

LIST OF SELECTED 157 PILOT COMMUNITIES:

| # | Region | District | Community |
| --- | --- | --- | --- |
| 1. | Surkhandarya region | Boysun district | MCC Temir Darvoza |
| 2. |  |  | MCC Shifo buloq |
| 3. |  |  | MCC Darband |
| 4. |  |  | MCC Urta Machay |
| 5. |  |  | MCC Dahnayjon |
| 6. |  |  | MCC Dashtigoz |
| 7. |  |  | MCC Kovrun |
| 8. |  |  | MCC Bibishirin |
| 9. |  |  | MCC Pulhokim |
| 10. |  | Sherobod district | MCC Gurjak-2 |
| 11. |  |  | MCC Uzunsoy |
| 12. |  |  | MCC Guliston |
| 13. |  |  | MCC Kizilolma |
| 14. |  |  | MCC Korabog |
| 15. |  |  | MCC Zarabog |
| 16. |  |  | MCC Chorbog |
| 17. |  |  | MCC Nurtepa |
| 18. |  |  | MCC Hojakiya-2 |
| 19. |  |  | MCC Chukurkol |
| 20. |  |  | MCC Chomishli |
| 21. |  |  | MCC Mehnatobod |
| 22. |  |  | MCC Dostlik |
| 23. |  |  | MCC Oktepa |
| 24. |  |  | MCC Istiqbol |
| 25. |  |  | MCC Kulluksho |
| 26. |  |  | MCC Mehrobod |
| 27. |  |  | MCC Gurjak-1 |
| 28. |  |  | MCC Hakimobod |
| 29. |  |  | MCC Navbur |
| 30. |  |  | MCC Gorin-Gilambob |
| 31. |  |  | MCC Boybulok |
| 32. |  | Angor district | MCC Gilambob |
| 33. |  |  | MCC Homkon |
| 34. |  |  | MCC Guliston |
| 35. |  |  | MCC Yukori Talashon |
| 36. |  |  | MCC Dostlik |
| 37. |  |  | MCC Novshahar |
| 38. |  |  | MCC Chinobod |
| 39. |  |  | MCC Karvon |
| 40. |  |  | MCC Korabog |
| 41. |  | Muzrabot district | MCC Fayziobod |
| 42. |  |  | MCC Chegarachi |
| 43. |  |  | MCC Guliston |
| 44. |  |  | MCC Halq Yoli |
| 45. |  |  | MCC Sopollitepa |
| 46. |  |  | MCC Mehrigiyoh |
| 47. |  |  | MCC Alpomish |
| 48. |  |  | MCC Olmazor |
| 49. |  |  | MCC Mehnatobod |
| 50. |  |  | MCC Darband |
| 51. |  |  | MCC Yangiyer |
| 52. |  |  | MCC Nurli Hayot |
| 53. |  |  | MCC Fidokor |
| 54. |  |  | MCC Buyuk Ipak Yoli |
| 55. |  |  | MCC Madaniyat |
| 56. |  | Termez district | MCC Yangiobod |
| 57. |  |  | MCC At-Termiziy |
| 58. |  |  | MCC Nurafshon |
| 59. |  |  | MCC Orol |
| 60. |  |  | MCC Yangihayot |
| 61. | Kashkadarya region | Kitob district | MCC Samarkand |
| 62. |  |  | MCC Kaynar |
| 63. |  |  | MCC Sharq Yulduzi |
| 64. |  |  | MCC Istikbol |
| 65. |  |  | MCC Yangi Zamon |
| 66. |  |  | MCC Charmgar |
| 67. |  |  | MCC Bogbon |
| 68. |  |  | MCC Pahtaobod |
| 69. |  | Shahrizabz district | MCC Ravot |
| 70. |  |  | MCC Oqdaryo |
| 71. |  |  | MCC Hojahurson |
| 72. |  |  | MCC Loliston |
| 73. |  |  | MCC Hontepa |
| 74. |  |  | MCC Yangiqishloq |
| 75. |  | Yakkabog district | MCC Mevazor |
| 76. |  |  | MCC Koshchinor |
| 77. |  |  | MCC Alakuylak |
| 78. |  |  | MCC Istiqlol |
| 79. |  |  | MCC Istiqbol |
| 80. |  |  | MCC Yashnobod |
| 81. |  |  | MCC Chimkorgon |
| 82. |  |  | MCC Uchtepa |
| 83. |  |  | MCC Navruz |
| 84. |  | Guzor district | MCC Halqobod |
| 85. |  |  | MCC Yangiobod |
| 86. |  |  | MCC Muminobod |
| 87. |  |  | MCC Boston |
| 88. |  |  | MCC Humdon |
| 89. |  |  | MCC Chanoq |
| 90. |  |  | MCC Amir Temur |
| 91. |  | Dekhonobod district | MCC Uzbekiston |
| 92. |  |  | MCC Pahtachi |
| 93. |  |  | MCC Dehkonobod |
| 94. |  |  | MCC Boston |
| 95. |  |  | MCC Oydin Yol |
| 96. |  |  | MCC Yashnobod |
| 97. |  | Kamashi district | MCC Kiziltepa |
| 98. |  |  | MCC Tinchlik |
| 99. |  |  | MCC Boburtepa |
| 100. |  |  | MCC Elabod |
| 101. |  |  | MCC Bunyodkor |
| 102. |  |  | MCC Qishliq |
| 103. |  |  | MCC Yuksalish |
| 104. |  |  | MCC Oynakul |
| 105. |  |  | MCC Istikbol |
| 106. | Samarkand region | Bulungur district | MCC Olmazor |
| 107. |  |  | MCC Fozil Yoldosh |
| 108. |  |  | MCC Yangiarik |
| 109. |  |  | MCC Yangiobod |
| 110. |  | Jomboy district | MCC Dekhonobod |
| 111. |  |  | MCC Suhmon |
| 112. |  |  | MCC Nazar |
| 113. |  |  | MCC Beshbola |
| 114. |  |  | MCC Koramuyin |
| 115. |  | Ishtihon district | MCC Azamat |
| 116. |  |  | MCC Kirkyigit |
| 117. |  |  | MCC Dekhonobod |
| 118. |  |  | MCC Humo |
| 119. |  |  | MCC Besharik |
| 120. |  |  | MCC Murodobod |
| 121. |  | Kattakurgon district | MCC Polvontepa |
| 122. |  |  | MCC Koradaryo |
| 123. |  |  | MCC Balandravot |
| 124. |  |  | MCC Olmazor |
| 125. |  |  | MCC Uyshun |
| 126. |  |  | MCC Navbahor |
| 127. |  | Narpay district | MCC Sarbozor |
| 128. |  |  | MCC Turon |
| 129. |  |  | MCC Nogarahona |
| 130. |  |  | MCC Istiqlol |
| 131. |  |  | MCC Navruz |
| 132. |  | Okdaryo district | MCC Okdaryo |
| 133. |  |  | MCC Kumushkent |
| 134. |  |  | MCC Yangiobod |
| 135. |  |  | MCC Temirsak |
| 136. |  | Pahtachi district | MCC Saroy |
| 137. |  |  | MCC Mirzo Olim |
| 138. |  |  | MCC Sardoba |
| 139. |  |  | MCC Amirobod |
| 140. |  | Samarkand district | MCC Shurboyi |
| 141. |  |  | MCC Shurboyicha |
| 142. |  |  | MCC Yangiariq |
| 143. |  |  | MCC Bozi |
| 144. |  |  | MCC Kushtamgali |
| 145. |  |  | MCC Chumchukli |
| 146. |  | Tayloq district | MCC Madaniyat |
| 147. |  |  | MCC Vorsin |
| 148. |  |  | MCC Honchorbog |
| 149. |  |  | MCC Muborak |
| 150. |  | Urgut district | MCC Kenagas |
| 151. |  |  | MCC Korabuloq |
| 152. |  |  | MCC Bahrin |
| 153. |  |  | MCC Beshkon |
| 154. |  |  | MCC Jartepa |
| 155. |  |  | MCC Boybul |
| 156. |  |  | MCC Zarafshon |
| 157. |  |  | MCC Rahmatobod |

Activity 1.2 Establishment of the platform for CDPs development and implementation enabling access of local people. Capacity building of community leaders, CSOs, young women, youth, persons with disabilities to engage into community CDPs development, implementation, and oversight.

Progress:

- ToT training conducted for local facilitators, PIU and UNDP project staff from Kashkadarya, Surkhandarya and Samarkand regions on March 27-29, 2024 in Karshi city

- ToT Training conducted for local facilitators, PIU and UNDP project staff on September 4-6, 2024 in Samarkand

- Community Initiative Groups were selected by rural population in three pilot regions. There were selected 1,126 people (407 pensioners), including 781 males and 345 females.

Figure 1. Gender-disaggregated data

Output:

- 25 local facilitators, PIU and UNDP staff members trained in ToT training in Karshi regarding conducting community mobilization workshops and CDP development.

25 participants local facilitators, UNDP, and PIU staff members in ToT training in Samarkand regarding conducting community mobilization workshops and CDP development.

1.3 Participatory needs assessments of target communities, based on experiences of IsDB, UNDP, and WB.

Progress:

- Community mobilization workshops conducted in  157 communities in three pilot regions

- SWOT analysis, visual and technical verifications conducted to identify and finalize the list of subprojects

Figure 2.

Figure 3. Gender-disaggregated data

Outputs:

- Mobilization workshops in 157 communities of Samarkand, Kashkadarya and Surkhandarya regions:

- 60 communities in Surkhandarya region

- 45 communities in Kashkadarya region

- 52 communities in Samarkand region

- 11,000 community members including 6587 males and 4413 females trained in community mobilization workshops:

- 4323 people trained in Surkhandarya region including 2523 males and 1800 females

- 3298 people trained in Kashkadarya region including 2013 males and 1285 females

- 3379 people trained in Samarkand region including 2051 males and 1328 females.

- SWOT analysis completed in 157 communities in three pilot regions:

- Samarkand region – 10 district, 52 communities

- Kashkadarya region – 6 districts, 45 communities

- Surkhandarya region – 5 districts, 60 communities

- Visual and technical verifications of almost 900 subprojects completed and 780 subprojects selected (see Annex 2)

- Samarkand region –  10 district, 52 communities, 281 subprojects

- Kashkadarya region – 6 districts, 45 communities, 235 subprojects

- Surkhandarya region – 5 districts, 60 communities, 264 subprojects

Figure 4.

Figure 5.

Activity 1.4 Development of costed options for community infrastructural investments. Identification of preferred options through community engagement, using innovative ICT solutions. Development of CDPs.

Progress:

- Project technical alignment discussions conducted in three pilot regions khokimiayts on final selection of subprojects for 157 communities. As a result, 780 subprojects identified for further processing with local authorities

- Study tour  to Korea and Vietnam to see best practices of rural development, digitalization, energy and water efficiency projects, CDP and other best practices conducted on November 19-29, 2024

Photos of study tour to Korea and Vietnam:

Output: N/A

Activity 1.5 Support IsDB PIU in the implementation of infrastructure components of CDPs.

Progress:

      - Development of Cluster CDPs for the 157 selected communities: Draft version of Cluster CDPs initiated on verified sub-projects chosen by 77 communities members.

      - Technical alignment discussions with regional khokimiyats on the final selection of subprojects for 94 communities completed.

Outputs:

            - 41 Cluster CDPs of 157 communities drafted and will be finalized and submitted to PIU and IsDB in 2025 year.

Outputs:

- 21 Cluster CDPs were submitted: 5 in Surkhandarya, 6 in Kashkadarya and 10 in Samarkand regions.

- Technical alignment discussions with regional khakimiyats on the final selection of subprojects for 157 communities completed.

CDP development:

## PROGRESS OF ACTIVITY 2:

Output 2: Capacity building in income generation, with focus on vulnerable groups. Outputs: Strengthened capacities of businesses and individuals such as entrepreneurs who work in agriculture complex, including the vulnerable groups in businesses development/expansion.

Activity 2.1 Regional market diagnostics/assessment of local business capacities

Progress:

- Procurement process of consulting company on conducting in-depth diagnostic assessments of supported regions specific business opportunities and applicability of agricultural climate smart solutions started.

Outputs:

- N/A

Activity 2.2 Design and delivery of targeted training on rural business development, with primary focus on the poor, women who are heads of households, young women and men and persons with disabilities. Training topics will be informed by regional market diagnostics. Vulnerable beneficiaries to be identified by communities. Trainings can be delivered in partnership with CSO.

Progress:

- Procurement process of consulting company on conducting training needs assessment started.

Outputs:

- N/A

Activity 2.3 Training of selected smallholder farmers on climate-smart solutions to increase agricultural productivity and inclusion into the value chain (e.g., water harvesting, drip irrigation, marketing) and crops diversification (e.g., fruit and nut trees).

Progress:

- N/A.

Outputs:

- N/A

Activity 2.4 Hands-on follow up technical support of farmers, businesses and individuals on inputs and technologies, sales, and marketing.

Progress:

- N/A

Outputs:

- N/A

Activity 2.5 Identification and promotion of locally relevant climate smart and energy efficient business solutions.

Progress:

- N/A

Outputs:

- N/A

PROGRESS OF ACTIVITY 3:

Capacity building of regional and local authorities.

Activity 3.1 Functional review of local authorities and communities (selected).

Progress:

- N/A

Outputs:

- N/A

Activity 3.2 Training of mahalla committees, women advisors and initiative groups in participatory planning, implementation, and M&E with a focus on women, youth, and vulnerable group

Progress:

- N/A

Outputs:

- N/A

Activity 3.3 Training of district khokimiyats, deputies on women’s issues, mahalla committees and women’s advisors, and initiative groups on climate change adaptation and mitigation.

Progress:

- N/A

Outputs:

- N/A

Activity 3.4 Implementation of participatory ICT solutions in integrated rural development planning, accountability, and sustainable management of infrastructure

Progress:

- N/A

Outputs:

- N/A

Activity 3.5 Training of local CSOs, women activists, women and vulnerable groups on effective engagement into regional and local decision-making. Some trainings can be delivered by CSOs.

Progress:

- N/A

Outputs:

- N/A

Activity 3.6 Training of district khokimiyats, deputies on women’s issues, mahalla committees and women’s advisors, initiative groups on maintenance schemes for all infrastructure and services created through CDPs, fostering environmentally and socially responsible approaches based on low costs and participatory, gender-responsive approaches.

Progress:

- N/A

Outputs:

- N/A

Activity 3.7 Number of effective practices in integrated rural development and advocacy identified for their scale-up regionally and nationally
Progress:

- N/A

Outputs:

- N/A

## PROGRESS OF ACTIVITY 4:

Project Management

- Agreement and Project Document signed between Ministry of Economy and Finance and UNDP Uzbekistan on April 16, 2024, and came into force since May 13, 2024.

- Regional project office in process of established in Termez (Surkhandarya), Karshi (Kashkadarya) and in Samarkand (Samarkand)

- Annual Plan of Activities and budget ISDB Phase II for 2025 developed and approved by the Project Board

- IT Equipment, furniture and 3 project cars for ISDB Project Phase II procured

- UNDP staff recruitment is almost completed.

- Project launch event was organized on October 17, 2024

- 1st Project Board Meeting will be conducted on December 10, 2024

PROJECT RISKS

- Project offices establishment, project staff recruitment and procurement processes of IT equipment and projects cars would affect the on-time completion of the project activities planned for 2024 year.

CHALLENGES AND LESSONS LEARNED

- Challenges in engaging members of the Initiative Groups in volunteer project activities is linked to a lack of motivation among certain individuals

- Challenges in collecting necessary data about the community including the information about necessary infrastructure

- Challenges in engaging local authorities and working groups in making discussions of possible solutions

- Challenges in establishing collaborative work between community members and local authorities.

Annexes:

Annex 1. Project target reporting table of 2024 year

Annex 2. List of subprojects

Annex 3. List of publications

Annex 4. Donor Interim report

Annex 5. Request for 2nd installment