Country: Montenegro

Engagement Facility

Title:	   Capacity Development of Human Resource Management Authority

Expected CPD Outcome 4:	   Capacity development for gender equality

Outcome 4: By 2027, all people, especially vulnerable people, benefit from improved social cohesion, increased realization of human rights and rule of law, and accountable, gender-responsive institutions

Expected CPD Output(s):	   Output 3.1: Open and accountable national/subnational institutions strengthened to promote transparency, gender mainstreaming and rule of law

Indicators:

3.1.1. Number of institutions supported by UNDP with measures in place to mainstream gender in the internal and external aspects of their work

Baseline (2022): 0

Target (2027): 3

Source/frequency: UNDP/annually

Initiation Plan Start/End Dates:	   1 May 2024 – 31 December 2024

Implementing Partner:	   UNDP

Ekaterina Paniklova									Agron Camaj

Resident Representative of UNDP in Montenegro 		Director of Human Resources Management Authority

_____________________________		________________________________

Programme Period:		May – December 2024

Quantum Project Number:

Quantum Output Number:

Gender Marker:		GEN 3

Total resources required:		$53,648.1

Total allocated resources:		$53,648.1

- Regular:			-

- Other:

Human Resources Management Authority					$53,648.1

Unfunded budget:			$53,648.1

In-kind Contributions:		-

Brief Description

The overall objective the Engagement Facility is to support capacity development of Human Resource Management Authority. The Engagement Facility May – December 2024 will be implemented under the Direct Implementation Modality (DIM), through an agreed set of initiatives agreed by the Human Resource Management Authority and UNDP and in line with the committed strategic priorities in the UNDP’s Country Programme for 2023-2027.

Team Leader for Gender Equality in UNDP in Montenegro will be responsible for ensuring that the Engagement Facility contributes to the CPD results, to the required standard of quality, and within the specified constraints of time and cost. They will lead regular discussions and exchanges with the managers of the initiatives housed under the facility to ensure the achievement of results.

Agreed: Ekaterina Paniklova, UNDP Resident Representative in Montenegro

# Purpose and Expected Output

The establishment of a more functional public administration represents one of the key challenges of the European integration process in Montenegro, since it directly influences the capability of governments to provide public services and stimulate economic growth, competitiveness and create enabling environment for enjoyment of fundamental rights.

The Montenegrin government has been undertaking significant efforts in this area through the strategic reform process that encompasses the entire public administration system, which includes state administration, local self-government, and organizations with public powers.

One of the main pillars and centre of the efficient public administration are human resources. Civil servants are key to the successful service delivery, as well as fulfilling all the public administration functions, PAR Strategy objectives and EU Integration requirements.

Government has been committed to gender equality goals and ratified almost all international conventions, however, has not demonstrated sufficient commitment to gender mainstreaming. UNDP has been partner to the Ministry of Public Administration in conducting of the strategic goals in public administration reform and gender mainstreaming in overall policy framework in accordance with international commitments and national legal framework.

UNDP had specific project dedicated to development and integration of the gender mainstreaming as a principal criterion in policy development between 2019-2021 setting up the wide partnerships with Parliament, Government and civil society organizations offering assessment of the gender mainstreaming practices and capacities. Informed by these findings UNDP offered strategic guidelines and a number of gender mainstreaming tools, methods, and strategic discussions about needed institutional transformation. Project created clear linkages between gender mainstreaming principles and ongoing public administration reform.

Human Resource Management Authority (HRMA) was in the centre of the abovementioned assessment as a key institution responsible for the overall capacity development in the Government. This project set ideal ground for the piloting of the Gender Equality Seal in Public Institutions providing good understanding of current practices and capacities and excellent understanding of the opportunities arising from systemic gender mainstreaming in the institution.

Human Resources Management Authority is principal institution for capacity development of public employees and additionally in charge of the process of recruiting and selection withing public administration. HRMA is involved in supporting public administration reform and aims to be a modern service and initiator of changes in the field of human resources management.

The impact of HRMA is reflected in the fact that they have developed tailor made training in various areas, including gender mainstreaming, to equip public employees and decision makers with knowledge and tools that allow them to develop efficient, inclusive gender aware policies, thus contributing to achieving effective governance and strong institutions.

Strong partnership previously developed between UNDP and HRA process will contribute to making gender equality perspective an integral part of day-to-day activities, where decisions are made, resources are allocated, and norms are created, i.e. lead to inclusive development and democratic governance.

UNDP Montenegro is committed to investigating all opportunities to provide assistance to the HRMA in strengthening its capacity development initiatives, with a primary focus on institutional gender mainstreaming.

As agreed with Human Resources Management Authority, the initial actions under the Engagement Facility will be divided in the following activities:

## Tailor made trainings for HRMA

The tailor-made training program for the is thoroughly designed to elevate HRMA’s staff expertise in gender mainstreaming, aligning with the imperatives of the Agenda 2030. Throughout this comprehensive initiative, participants will engage in multifaceted activities aimed at fostering institutional and programmatic gender mainstreaming.

Central to this endeavour is the development of strategic competencies in planning and resource allocation, ensuring that gender equality initiatives are seamlessly integrated into HRMA's broader objectives. Demanding training sessions will equip staff with the tools and methodologies necessary for effective monitoring and evaluation, enabling HRMA to meticulously track progress and measure the impact of gender equality programs.

Furthermore, the program places significant emphasis on cultivating inclusive institutional frameworks, ensuring that gender considerations are integrated into all aspects of HRMA's policies and practices. Through targeted skill development activities, staff will be empowered to foster working environments that uphold human rights, thereby ensuring equity and equality of opportunities for all employees. Active engagement in the policy cycle and a culture of accountability will further fortify HRMA's commitment to advancing gender equality in line with the 2030 SDG Agenda.

## Organization of regional event

The envisaged regional event will serve as a pivotal platform for fostering dialogue and knowledge exchange among stakeholders within the region on the crucial topic of gender mainstreaming in public administration. The aim is to facilitate the sharing of best practices and experiences, leveraging existing initiatives to drive meaningful progress. Participants will engage in discussions, workshops, and collaborative sessions, gaining valuable insights into effective strategies for advancing gender equality within public administration. Through the event innovative approaches will be explored and regional partnerships strengthened, in order to contribute to the achievement of sustainable development goals.

# Management Arrangements

The Engagement Facility will be established by UNDP and funded by Human Resources Management Authority, and potentially by other donors. UNDP will assume financial responsibility and be accountable to the donor for the contributed funds. UNDP will exercise overall management, supervision, and financial control in accordance with the UNDP's Rules and Regulations and will regularly furnish progress reports on the implementation. In consultation with Human Resources Management Authority and in line with its requirements, UNDP will engage relevant expertise to advance the design and development of a comprehensive program tailored to the needs of HRMA.

# Monitoring

The monitoring of the Engagement Facility's implementation will be the responsibility of UNDP. The Head of the Gender Equality Cluster in UNDP in Montenegro will oversee the monitoring process, ensuring that activities are executed in a timely manner and that project outputs align with the planned objectives.

# IV. WORK PLAN

| EXPECTED OUTPUTS | PLANNED ACTIVITIES | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Fund. Source | Budget Description | TOTAL |
|  | List activity results and associated actions | 2024 |  |  |  | Amount |
| Capacity Development of Human Resources Management Authority | Specialised Trainings |  | UNDP | GoM | 72100 Contractual Services Companies | 29,764.87 |
|  |  |  | UNDP | GoM | 71300 Local consultant | 5,951.76 |
|  | Technical assistance for Public Seal / technical advisor |  | UNDP | GoM | 71300 Technical expertise | 14,522.00 |
|  |  |  | UNDP | GoM | 73100 - Rental & Consumables & Maint of Other Equipment | 1,800.00 |
| Total output without GMS |  |  |  |  |  | 52,038.63 |
| GMS 3% |  |  |  |  |  | 1,609.44 |
| TOTAL |  |  |  |  |  | 53,648.07 |