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RPSP SECTION 1: GENERAL INFORMATION
Please note that the report will be considered valid only after all the sections and attachments are filled with relevant details.



The GCF Readiness and Preparatory Support Programme guidebook
For more information, please refer to the GCF Readiness and Preparatory Support Programme guidebook



Approved Readiness Proposals
Please refer to the approved proposal published in the GCF Website if needed.


Please label deliverable files using the same titles as in the approved proposal






Submission date *



Initial submission date (no need to revise for resubmission)

Submission title *
2025 Annual Progress Report, APR 1

Insert the report title, e.g. 2023 Annual Progress Report, IPR 2, etc.


1.1 DP's confirmation of sharing the report with NDA(s)


By providing this information, Delivery Partner confirms that the report submitted has been shared with the NDA prior to the submission for GCF's review. Please select the name and contact e-mail of the NDA focal point(s) who have received the report.


Please indicate if this report has been shared with the relevant NDA(s)2026-03-31


Please indicate the date of submission to NDA(s)

NDA contact


Yes











Others (not listed above)Taofeq Abdulwahid Al Sharjabi (mwe@mwe-ye.org)
NDA Contact Fullname
NDA Contact Email
Description
mwe@mwe-ye.org
Taofeq Abdulwahid Al Sharjabi



Please provide the NDA contact information in this field in case you cannot find it in the above dropdown.



1.2 General Information of the Grant


Grant Agreement Number
The grant reference number as stated in the approved grant proposal

Country
The country(s) where the grant is being implementedYEM-RS-005


Delivery Partner
The name of the Delivery PartnerUnited Nations Development Programme (UNDP)
Yemen




Activity AreaNon-NAP

The activity area targeted (NAP, Non-NAP)

Approved Duration (months)
As stated in the grant legal agreement, taking into account any approved extensions

Total Amount Approved
Total approved amount in USD as stated in the grant legal agreement/proposalUSD
945,615
24




Grant Start Date for GCF-managed
	29-03-2024


 grants
Grant Effectiveness Date

Grant Start Date for UNOPS-managed grants
1st Disbursement Date

Grant End Date
As stated in the grant legal agreement, taking into account any approved extensions2026-06-29

	29-06-2026





Total Amount Disbursed
Total amounts received from the GCF from the grant start date and up to date

First Disbursement Date
The date on which the first tranche was paid to the grantUSD
472,807.5
2024-07-24






1.3 Reporting Period Details


From: *2025-01-01



The beginning of the reporting period

To: *2025-12-31


The end of the reporting period


[bookmark: _Hlk216645274]

1.4 Executive Summary
Please highlight key achievements during the reporting period.


A joint inception workshop between Ministry of Water and Environment, UN-Habitat and UNDP were held on 5 February 2025 in Aden, building on the joint workplan (submitted in APR 2024), (Deliverable 2.2.2.1a). The workshop brought together 51 stakeholders from government, civil society, the private sector, academia, and international partners, and strengthened shared understanding of project objectives, timelines, and coordination mechanisms. The workshop contributed to improved stakeholder awareness, agreement on structured coordination arrangements, and recommendations to strengthen climate governance and sectoral planning. Yemen’s subsequent submission of its NDC 3.0 Vision and Framework to the UNFCCC in November 2025 further reinforced the alignment between near-term climate commitments and the long-term strategic direction provided by the LT-LEDS, (Inception Workshop Report, Deliverable 2.2.2.1b). 


Outcome 2.2; Output 2.2.2
· Under Activity 2.2.2.1, , The recruitment of an international consultancy firm and national sectoral consultants to support the LT-LEDS development process has been successfully completed despite the challenges faced due to the contextual complexities and limited availability of specialized national expertise in the country. In the next reporting period, the project will initiate consultations and analytical work to support the LT-LEDS visioning process, (Deliverable 2.2.2.1c).
· For Activity 2.2.2.2, the project advanced preparations for the elaboration of Yemen’s LT-LEDS by recruiting a Local Stakeholder Engagement and Facilitative Dialogue Specialist to support stakeholder identification and engagement, (Deliverable 2.2.2.1d). The specialist conducted a comprehensive stakeholder mapping and analysis across government entities, private sector, civil society, academia, development partners, and youth and vulnerable groups, (Deliverable 2.2.2.1e). Based on this analysis, a Stakeholder Engagement Plan (SEP) was developed, outlining tailored communication and consultation modalities, integrating gender and social inclusion considerations, and strengthening national ownership and institutional coordination. The stakeholder mapping and SEP will inform the development and implementation of Yemen’s LT-LEDS and MRV system under Outputs 2.2.2 and 2.2.4, (Deliverable 2.2.2.1f).
· No progress was reported under Activities 2.2.2.3, 2.2.2.4, and 2.2.2.5 during the reporting period. Planned milestones for the next reporting period include the design and delivery of a capacity-building technical training aligned with the requirements for LT-LEDS implementation, the initiation of stakeholder consultations to inform the development of the LT-LEDS Investment Plan, and the drafting of the Investment Plan to guide resource mobilization and financing pathways for low-emission development priorities.


Outcome 2.2; Output 2.2.4
· Under Activity 2.2.4.1, significant preparatory progress was made during the reporting period. A comprehensive Terms of Reference was developed for an international consultant to lead the development of the MRV system, and the recruitment and onboarding process was successfully finalized, (Deliverable 2.2.4.1a). These preparatory steps provide a solid technical foundation for advancing the development of the MRV roadmap and methodology in the upcoming implementation period.
· No progress was reported under Activity 2.2.4.2 during the reporting period. Planned milestones for the next reporting period include defining the software requirements, system architecture, and functional specifications for the pilot web platform.
· Similarly, no progress was reported under Activity 2.2.4.3 during the reporting period. In the next reporting period, the project intends to develop a capacity-building plan and initiate training activities for relevant government counterparts to support the operationalization of the MRV system.

Outcome 2.2; Output 2.2.6; Activity 2.2.6.1
· No progress was reported during the reporting period. In line with the project’s adaptive implementation approach, activities in 2026 will focus on identifying opportunities to further mainstream and integrate the activity within existing national processes, thereby strengthening efficiency and supporting greater uptake of the LT-LEDS while avoiding the creation of parallel or duplicative documentation burdens for the Government. 
 

Yemen’s protracted crisis, insecurity, and fragile institutional environment have significantly delayed the implementation of the LT-LEDS/MRV project. Conflict-related access constraints, international travel advisories, and mobility restrictions have limited stakeholder engagement, delayed workshops, and prevented international consultants and firms from entering the country. These conditions also necessitated the cancellation and re-launch of key procurement processes, including for the LT-LEDS lead and MRV system developer, extending recruitment timelines by six to nine months and delaying consultations, data collection, and validation activities. Additional mobility constraints and limited national coordination further delayed the project inception workshop, originally planned for November 2024 but held in February 2025. Institutional fragmentation across regions has also slowed coordination with the NDA and line ministries, reducing predictability and requiring closer alignment with the UN Habitat-led NDC 3.0 process. This interdependency has postponed LT-LEDS analytical work and MRV roadmap development into the 2026–2027 period. With the NDC process now nearing completion, implementation of the LT-LEDS is expected to accelerate, and the project continues to actively manage these interlinkages to ensure coherence.	Comment by Benjamin Basmaci: GCF comment: 

1. Please provide further clarity regarding 'the complex implementation context' in the executive summary including specific factors and constraints affecting project delivery.	Comment by Benjamin Basmaci: Ben has rewritten. To be verified by CO. 

The project therefore submitted a no cost extension (NCE) to complete remaining activities that have not yet achieved the expected progress. The project was originally scheduled to conclude on 27 June 2026; however, the remaining implementation period is insufficient to finalize the development of the LT‑LEDS and the MRV system. Following consultations with the National Designated Authority (NDA), a request for a 12‑month no‑cost extension has been initiated to ensure the successful completion of all planned outputs.
Further elaboration and mitigation actions will be elaborated in the extension request):










1.5 Challenges and lessons

Challenges encountered *
	Challenge #1: The country complex context, shaped by the prolonged crisis, imposed significant security and mobility restrictions that further constrained the ability of international consultants and firms to operate in Yemen.
Challenge #2: Limited availability of specialized national consultants and difficulties in mobilizing international expertise to support both the design of the MRV system and the development of the LT‑LEDS strategy. 
Challenge #3: Delays of the inception workshop for more than three months led to delays in starting project activities.



Challenges and lessons learned *
	Response to challenge #1:
· In response to challenge 1, the project revised the Terms of Reference for international consultancies to allow assignments to be delivered remotely, supported by national consultants. This adaptive strategy enables remote technical support and hybrid advisory modalities and reduces the need for in-country travel. Priority was given to mobilizing national and regional expertise, ensuring continuity of project activities despite limited physical access. In a crisis and conflict-affected contexts, project design must anticipate security and mobility constraints from the outset, incorporating flexible implementation modalities and contingency planning for remote engagement. Additionally, procurement timelines should remain flexible.
Response to challenge #2:
· Investing early in national technical capacities is essential, which not only mitigates reliance on international consultants but also enhances long-term sustainability of climate MRV systems.  Adaptive management, flexible timelines, and hybrid delivery models are also essential in maintaining project momentum in a complex operational environment.
Response to challenge #3: 
· Coordination with other implementing partners, such as UN-Habitat, can strengthen synergies, consolidate efforts and improve efficiency of resource utilization when advancing and linking LT-LEDS/LTS with the NDC. Early coordination and establishing clear roles, responsibilities and coordination mechanisms at the outset helps reduce delays and improves efficiency in joint implementation.  

Given these challenges and their cumulative impact on project implementation and its timeframe, the project—together with the NDA—has initiated the process for a no‑cost extension request to ensure the project milestones and outputs can be effectively completed to the required quality.




Describe the challenge faced during the reporting period of implementation and critical risks that may result in a change to the scope and/or timing of the project; please provide a description and how they have impacted the implementation period and could impact other activities and final targets. N.B. Choose the most relevant type if the challenge is related to multiple types.

1.6 Portfolio level reporting


DPs may submit a portfolio level report in this section to supplement the submission of grant-level reports.
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RPSP SECTION 2: REPORTING ON READINESS GRANT LOGICAL FRAMEWORK
Please note that the report will be considered valid only after all the sections and attachments are filled with relevant details.




Check RRMF indicators retrofitted for original proposal's logframe here
/// RRMF indicators retrofit tables ///
Select the grant ID to see the RRMF indicators mapped to original outputs and activities in the proposal.


This section requires an overview of key achievements and deliverables in implementing the Readiness Support activities. Any key deliverables to the agreed outputs should be submitted with the grant progress report.

Select Applicable Objectives *
[image: ] Objective 1: Capacity Building
Objective 2: Strategic FrameworksX

[image: ] Objective 3: National Adaptation Plans and Adaptation Planning Processes [image: ] Objective 4: Pipeline development
[image: ] Objective 5: Knowledge sharing and learning


Is it for a Regional Readiness (multi-country) grant? *
[image: ] Yes [image: ] No


Objective 2: Strategic Frameworks
Select Applicable Outcomes: 2
[image: ] Outcome 2.1: GCF recipient countries have developed initial country programmes to guide GCF investment and programming of GCF Readiness and Preparatory Support resources
X Outcome 2.2: GCF recipient countries have developed or enhanced strategic frameworks to address policy gaps, improve sectoral expertise, and enhance enabling environments for GCF Programming
[image: ] Outcome 2.3: Entity Work Programmes of accredited direct access entities developed, that are aligned with the priorities of the countries, including country programmes and the GCF result areas
Outcome 2.4: Strategies for transforming and attracting private sector investment for low emissions and resilience developed and being used


Summary of Objective 2 *

Please provide summary of the outcomes under this objective


Outcome 2.2: GCF recipient countries have developed or enhanced strategic frameworks to address policy gaps, improve sectoral expertise, and enhance enabling environments for GCF Programming

Select Applicable Outputs: 2.2
[image: ] Output 2.2.1: Readiness needs assessment to develop an action plan with strategies for Readiness support Output 2.2.2: Long-term, Low Emission Development Strategy (LT-LEDs / LTS) developedX


[image: ] Output 2.2.3: NDC updated or revised and/or financing strategy or related policies developed.
Output 2.2.4: MRV systems developed and operational for tracking internal and external climate finance flows [image: ] Output 2.2.5: Studies, action plans, modelling efforts and other research efforts conducted/developedX

Output 2.2.6: Sectorial strategic frameworks or associated plans developedX

[image: ] Output 2.2.7: Appropriate climate technologies/ solutions identified and prioritized



Output 2.2.2: Long-term, Low Emission Development Strategy (LT-LEDS/ LTS) developed
Select Applicable Indicators: 2.2.2
Indicator 2.2.2.1: Has a long-term strategy (LTS) been developed with the support of Readiness grants?X




[bookmark: _Hlk216633816][bookmark: _Hlk192576759]Indicator 2.2.2.1: Has a long-term strategy (LTS) been developed with the support of Readiness grants?
Mid-century long-term low GHG emissions development strategies or long-term strategies (LTS) provide a pathway to a whole-of-society transformation and a vital link between shorter-term NDCs and the long-term objectives of the Paris Agreement.

Progress 2.2.2.1 *
[image: ]Yes [image: ] No 

Narrative description

	
Activity 2.2.2.1:
The recruitment of the international consultancy firm that will support the LT‑LEDS development process has successfully been completed, despite challenges related to contextual complexities and the limited availability of specialized national expertise. In the next reporting period, the project will initiate consultations and analytical work to support the LT‑LEDS visioning process (Deliverable 2.2.2.1c).

Additionally, the Joint Workplan between NDC 3.0 and LT-LEDS was development (deliverable 2.2.2.1a) to further coordinate efforts on the visioning roadmap for LT-LEDS to better coordinate activities. 

Activity 2.2.2.2:

The project advanced preparations for the elaboration of Yemen’s LT‑LEDS through the recruitment of a Local Stakeholder Engagement and Facilitative Dialogue Specialist (Deliverable 2.2.2.1d). The specialist conducted a comprehensive stakeholder mapping and analysis across government entities, the private sector, civil society, academia, development partners, as well as youth and vulnerable groups (Deliverable 2.2.2.1e).

Based on this analysis, a Stakeholder Engagement Plan (SEP) was developed, outlining tailored communication and consultation modalities, integrating gender and social inclusion considerations, and strengthening national ownership and institutional coordination. The stakeholder mapping and SEP will inform the development and implementation of Yemen’s LT‑LEDS and MRV system under Outputs 2.2.2 and 2.2.4 (Deliverable 2.2.2.1f)

No progress on activities 2.2.2.3; 2.2.2.4; 2.2.2.5 

These preparatory activities established the institutional and operational framework necessary to initiate the LT-LEDS development process in the next reporting period.




Description briefly outlining the development process of the LTS and the date the LTS has been approved

Deliverables achieved
	Deliverable 2.2.2.1a: Joint workplan for the LT-LEDS and NDC process (draft) 
Deliverable 2.2.2.1b: Inception Workshop Report 
Deliverable 2.2.2.1c: International firm ToR for LT-LEDS development  
Deliverable 2.2.2.1d: Local Stakeholder Involvement and Facilitative Dialogue Specialist ToR
Deliverable 2.2.2.1e: Stakeholder Analysis and Mapping report (final)

Deliverable 2.2.2.1f: Stakeholder 
Engagement Plan (final)



Please state the actual deliverables achieved from the completed activity and ensure that the deliverables are as per the approved grant. Please underline the deliverables that have changed from the approved grant.

Attachment of Pre and post development evaluation report of LTS-long-term strategy







Output level implementation timelines

Original Start Date *

2024-03-27

As stated in the approved proposal, approved extension plan, or in the latest approved Progress Report.
Variance/delay explanation *
[bookmark: _Hlk188699168]
Actual/Planned Start Date *

2025-02-05


Actual start date of the output, or the planned date if the implementation hasn't started yet.

Original End Date *

2026-06-27

As started in the approved proposal, approved extension plan, or in the latest approved Progress Report.
[bookmark: _Hlk188699205]
Actual/Expected End Date *
2027-04-30


Actual end date of the output if it’s already completed, or the expected end date per updated estimates


Project implementation began later than planned due to delays in initial funding timelines. Activities commenced in 2025 but were further affected by Yemen’s fragile context, including insecurity, mobility constraints, and limited availability of specialized firms. These constraints have delayed the recruitment and mobilization of international firm for the LT-LEDS development and its related activities, resulting in a compressed remaining timeframe for implementation. Accordingly, the project, in coordination with the NDA, has initiated a no-cost extension request to ensure completion of all outputs to the required quality.

Please explain the reasons for any difference between a planned output and the actual output. If there’s no variation, please add "N/A"



Output 2.2.4: MRV systems developed and operational for tracking internal and external climate finance flows	Comment by Benjamin Basmaci: GCF: 

1. Narrative description: Please structure the progress reported under the narrative description by activity in line with the approved logframe.
2. Progress 2.2.4.1: Please indicate 'no' for progress as the output has not been acheived yet.
Select Applicable Indicators: 2.2.4
Indicator 2.2.4.1: Has an MRV system been developed for tracking internal and external climate finance flows with the support of Readiness grants?X




[bookmark: _Hlk192576617]Indicator 2.2.4.1: Has an MRV system been developed for tracking internal and external climate finance flows with the support of Readiness grants?
Monitoring Reporting and Verification (MRV) systems for climate finance are used to track internal and external climate finance flows across a variety of sources.

Progress 2.2.4.1 *
[image: ]  Yes 

· No


	Output 2.2.4
Similar preparatory steps were taken to ensure effective implementation of the activities under this output including:

Activity 2.2.4.1: Significant preparatory progress was achieved during the reporting period. A comprehensive Terms of Reference was developed for the recruitment of an international consultant to lead the MRV system design. The recruitment and onboarding process was successfully finalized (Deliverable 2.2.4.1a). These preparatory steps provide a solid technical foundation for advancing the development of the MRV roadmap and methodology in the upcoming implementation period.

Activity 2.2.4.2: No substantive progress has been made to date. However, the recruitment of a Local Stakeholder Involvement and Facilitative Dialogue Specialist (Deliverable 2.2.4.1b) has been concluded. 

Activity 2.2.4.3: No substantive progress has been made to date. However, the recruitment of a Local Stakeholder Involvement and Facilitative Dialogue Specialist (Deliverable 2.2.4.1b) has been completed to facilitate coordination and consultations with national stakeholders, which will underpin the forthcoming capacity building plan and workshops.





































Outlining what MRV system for climate finance has been developed with readiness support

Deliverables achieved· ToR developed for the International MRV Consultant, who will lead the design of the national MRV system.
· Contracting of the international MRV consultant has been completed.
· Stakeholder analysis and engagement planning for MRV: Comprehensive stakeholder mapping and the Stakeholder Engagement Plan (SEP) identify MRV-relevant actors, clarify roles, and outline structured engagement approaches.


	Deliverable 2.2.4.1a: MRV International Consultant ToR (final) 
Deliverable 2.2.4.1b: Local Stakeholder Involvement and Facilitative Dialogue Specialist ToR (final)



Please state the actual deliverables achieved from the completed activity and ensure that the deliverables are as per the approved grant. Please underline the deliverables that have changed from the approved grant.

Attachment of MRV system outline report and evaluation report



Output level implementation timelines

Original Start Date *

2024-03-27


As stated in the approved proposal, approved extension plan, or in the latest approved Progress Report.
Variance/delay explanation *

Actual/Planned Start Date *


Actual start date of the output, or the planned date if the implementation hasn't started yet.2025-05-01



Original End Date *

2026-06-27

As started in the approved proposal, approved extension plan, or in the latest approved Progress Report.

Actual/Expected End Date *
2027-03-31

Actual end date of the output if it’s already completed, or the expected end date per updated estimates


Project implementation began later than planned due to delays in initial funding timelines. Activities commenced in 2025 but were further affected by Yemen’s fragile context, including insecurity, mobility constraints, and limited availability of specialized firms.. While mitigation measures were introduced, including revised ToRs enabling remote delivery supported by national consultants, the resulting delays significantly compressed the remaining implementation timeframe. Accordingly, the project, in coordination with the NDA, has initiated a no-cost extension request to ensure completion of all outputs to the required quality.


Please explain the reasons for any difference between a planned output and the actual output. If there’s no variation, please add "N/A"


Output 2.2.6: Sectorial strategic frameworks or associated plans developed
Select Applicable Indicators: 2.2.6	Comment by Benjamin Basmaci: GCF: 

1. Narrative description: Please structure the progress reported under the narrative description by activity in line with the approved logframe.




Indicator 2.2.6.1: Number of sectors related strategic framework or action plans developedX


Activity 2.2.6.1: No substantive progress has been reported under this activity to date. However, preparatory steps undertaken under Output 2.2.2, including comprehensive stakeholder mapping and analysis, as well as the contracting of the service provider firm, directly contribute to the achievement of Output 2.2.6. These actions have established the institutional arrangements, technical readiness, and consultative mechanisms required to advance the analytical studies, sectoral assessments, and subsequent implementation processes under this output.


Indicator 2.2.6.1: Number of sectors related strategic framework or action plans developed
This indicator asks about strategy-focused sectorial frameworks or associated action plans. Sectoral strategic frameworks are strategies to make a specific sector climate adaptive and low-emission, for instance by removing market, technology, regulatory and other barriers to scaled-up investment.

Progress 2.2.6.1 *
[image: ]  Yes 

· No

 

Narrative description


Explanation what type of strategy or action plan was developed to implement strategic frameworks and what sector they pertain to

Deliverables achieved
· Deliverable 2.2.2.1C: ToR for an international firm to lead the LT-LEDS strategy exercise (final), as indicated under output: 2.2.2 


Please state the actual deliverables achieved from the completed activity and ensure that the deliverables are as per the approved grant. Please underline the deliverables that have changed from the approved grant.

Output level implementation timelines

Original Start Date *

2024-03-27


As stated in the approved proposal, approved extension plan, or in the latest approved Progress Report.
Variance/delay explanation *

Actual/Planned Start Date *


Actual start date of the output, or the planned date if the implementation hasn't started yet.2025-05-01



Original End Date *

2026-06-27

As started in the approved proposal, approved extension plan, or in the latest approved Progress Report.

Actual/Expected End Date *
2027-04-30

Actual end date of the output if it’s already completed, or the expected end date per updated estimates


Project implementation began later than planned due to delays in initial funding timelines. Activities commenced in 2025 but were further affected by Yemen’s fragile context, including insecurity, mobility constraints, and limited availability of specialized firms. These constraints have delayed the recruitment and mobilization of international firms for the LT-LEDS development and its related activities, resulting in a compressed remaining timeframe for implementation. Accordingly, the project, in coordination with the NDA, has initiated a no-cost extension request to ensure completion of all outputs to the required quality.

Please explain the reasons for any difference between a planned output and the actual output. If there’s no variation, please add "N/A"

Section 3: Budget & Expenditure - v1 (Draft) 2025-01-15 18:45 +09:00	

RPSP SECTION 3: BUDGET AND EXPENDITURE
Please note that the report will be considered valid only after all the sections and attachments are filled with relevant details.


To add expenses: choose "Add row", select from the dropdown menu relevant Outcome, Output and Cost category and provide numeric value for expense. If cost category is missing, add own cost category simply by typing it into the "Cost Category" field.

To see the summary of costs added, after providing numeric values for each Outcome, Output, and Cost Category, click on the "Fill" slide button to see calculated totals. Please make sure that you choose "contingency" and "delivery partner fee" in all columns to return the correct totals.

In the remark column, you can provide justification or a note at each budget line. Please be advised that this is the only column where you can type text.


3.1 Budget and Expenditure reporting

Select currency to report the Budget and Expenditure *
[image: ] USD [image: ] EUR



3.1.1 Resources



a. Fund Received from GCF


Fund Cumulative Prior Period
USD



Fund Received Current Period472,807.5

USD



Total Fund Received


Remarks





b. Interest IncomeUSD
USD





c. Other ResourcesUSD
USD






TOTAL RESOURCES	Sum of fund cumulative prior
period

Sum of fund received current period
 USD472,807.5				


Sum of total fund received

USD472,807.5


Note: Please enter "0 (zero)" without leaving any data fields blank to get the sum.





3.1.2 Budget & Expenditure


Please, select relevant Outcomes, Outputs and Cost categories. If relevant Cost Category was not found, type in the field own name for the cost category.
This component can't be displayed in printable format. Please refer to the online version.



Note: Any reallocation of the approved budget among the cost categories resulting in a variation of more than 20% must seek prior approval from the GCF Secretariat in writing. This method may not be used to increase project management costs.
You may submit a budget change request using the template here: www.greenclimate.fund/document/letter-request-change-approved-readiness-and-preparatory-support- programme-proposal

As an option, please provide the budget and expenditure report template.



Use the template provided here: www.greenclimate.fund/sites/default/files/document/readiness-budget-and-expenditure-report-template-20240202-1.xlsx Accepted formats: MS Excel (.xlsx, .xls)



Please provide any supporting documents as attachment below when requested.



This may include supporting documents to justify the committed amounts when the DP is requested to provide them additionally during the review.


	3.2 Project Total
	

	Budget
	

	Approved budget
	Budget re-allocation
	Budget after re-allocation
	Change in %

	945,615

	0
	0
	

	Expenditure
0
	
	
	

	Cumulative Prior period Expenditure
	Expenditure for this reporting period
	Commitment
	Total Expenditure

	0
	0
	0
	0

	Budget utilisation rate in %
	Available budget
	
	

	0
	945,615

	
	





3.3 Reporting on the disbursement schedule

Please provide the updated disbursement schedule. You may refer to the initial disbursement schedule planned at the proposal approval stage. Add as many rows as needed to list all the tranches planned. Please make sure that the sum of disbursed and scheduled amounts is in line with the total approved amount and the sum of disbursed amount is in line with the total disbursed amount.
USD
USD



REFERENCE ONLY:

Total approved amount  945,615

Total disbursed amount
472,807.5





	
	Tranche No.
	
	Amount
	?
	
	
	Date
	?
	
	Status
	

	
	1

	
	 472,807.5
	
	USD
	
	 2024-07-24
	
	
	Received
	

	
	2
	
	472,807.5
	
	
	
	 2025-06-30
	
	
	Planned for 2025
	

	
	
	
	
	
	
	
	
	
	
	
	






3.4 Reporting on changes in the budget plan

3.4.1 Are there significant changes in the budget plan reported in this section?
[image: ] Yes [image: ] No

Full review history	
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