Umbrella Programme to Support NBSAP Update and the 7th National Reports

Annual Project Review Report

GLOBAL ENVIRONMENT FACILITY

(as applicable for donor specific reporting)

| Implementing Agency: | United Nations Development Programme (UNDP) |
| --- | --- |
| Project ID: Gender Marker: Digitalization Marker: Project Title: | 01002592‬ GEN 2 Umbrella Programme to Support NBSAP Update and the 7th National Reports |
| Project Duration: | 15 May 2024 – 15 November 2027 |
| Country / Region: | Turkmenistan/RBEC |
| Funding Partner/s: | Global Environment Facility (GEF) |
| Responsible Parties: |  |
| Reporting Period: | 01 January 2025 – 31 December 2025 |
| Project Manager: | Rahmanberdi Hanekov, Project Coordinator, Rahmanberdi.hanekov1@undp.org |

Please use font Proxima Nova and font size 10 for all text on narrative sections. You may refer to UNDP branding guidelines through this link.

Table of Contents

I.	Executive Summary	3

II.	Introduction / Background	4

III.	Progress Review: Key Activities and Results, January-December 2025	5

Section 1: Analysis of Theory of Change	5

Section 2:  Overall progress against outcomes	5

Section 3: Monitoring and Evaluation of activities.	5

Section 4: Progress against each output	5

Section 5: Cross-Cutting Integration	6

IV.	Partnerships and Sustainability	8

V.	Update on risks and mitigation measures	8

VI.	Key Challenges, Lessons Learned and Recommendations	9

VII.	Financial Summary	10

VIII.	Annexes	12

Annex I: Progress Review: detailed matrix of activities and results	12

Annex II: Updated Risk Log	15

Annex III: Multi-Year Work Plan for Turkmenistan (2024-2027)	17

Acronyms

| 6NR 7NR BD BIOFIN BPPS CBD CO COP CPD GBF GBF-EAS GEF GPMTSU LPAC NBSAP NBT NDC OFP RBEC UNDP | 6th National Report 7th National Report Biodiversity Biodiversity Finance Initiative Bureau for Programme and Policy Support Convention on Biologic Diversity Country Office Conference of the Parties Country Programme Document Kunming-Montreal Global Biodiversity Framework Global Biodiversity Framework Early Action Support Programme Global Environment Facility Global Project Management and Technical Support Unit Local Project Appraisal Committee National Biodiversity Strategy and Action Plan National Biodiversity Target Nationally Determined Contribution Operational Focal Point Regional Bureau for Europe and the Commonwealth of Independent States United Nations Development Programme |
| --- | --- |

- Executive Summary

# This Annual Project Review Report covers the period from 01 January 2025 to 31 December 2025 for the Turkmenistan component of the Umbrella Programme to Support NBSAP Update and the 7th National Reports. The project's overarching objective is to support Turkmenistan in revising its National Biodiversity Strategy and Action Plan (NBSAP) to align with the Kunming-Montreal Global Biodiversity Framework (GBF) and to prepare and submit its 7th National Report (7NR) to the CBD Secretariat.

# The project was officially planned to start in May 2024, but faced a delayed commencement in the country, which impacted the established implementation timelines for both the NBSAP update and the 7NR development. To mitigate this, significant effort was focused on establishing the core team and launching foundational activities in the latter half of 2025.

# Key achievements during the reporting period (Jan-Dec 2025) include:

# Project Mobilization: A Project Coordinator/Biodiversity Specialist was successfully hired in October 2025 to accelerate implementation and coordinate activities.

# Stakeholder Engagement: A National Introductory Workshop was conducted with broad representation from key national agencies, ministries, research institutes, and civil society, underscoring the "whole of government" and "whole of society" approach necessary for effective GBF implementation.

# NBSAP Foundation: Two national experts were recruited to conduct essential preparatory work for Outcome 1.

# Monitoring and Evaluation: A Project Steering Committee was established with representatives from key national partner agencies, and an informal working group was set up for monitoring and consultations on the NBSAP update and 7NR process.

# Key Challenges, Risks, and Mitigation: The main challenge encountered was the delayed project start, which has subsequently been addressed by the hiring of the Project Coordinator and the ongoing recruitment of national experts to catch up with the planned activities.

- Introduction / Background

The 15th meeting of the Conference of Parties (COP15) to the CBD adopted Decision 15/6 on “Mechanisms for Planning, Monitoring, Reporting, and Review”, which requests Parties to update their NBSAPs in alignment with the goals and targets of the GBF, including those related to means of implementation.

The GEF-8 ‘Umbrella Programme to support NBSAP Update and Seventh National Reports' is a Party-led effort funded by the Global Environment Facility (GEF) to continue the process of updating NBSAPs and undertaking reporting on implementation of the GBF.

The Programme aims to support the achievement of this and related COP decisions through addressing the following proposed actions, which countries can select to undertake as appropriate, based on the progress made under the GEF Early Action Support project and in consideration of national circumstances and priorities:

- Implement comprehensive NBSAP stakeholder engagment to promote whole-of-government and whole-of-society approaches

- Enable gender mainstreaming within consultation processes and within the NBSAP

- Identify and prioritize gaps and inconsistencies be - tween the NBSAP and achieving the KMGBF

- Strengthen policy alignment, coherence, and biodiversity mainstreaming into key sectors

- Strengthen readiness for NBSAP implementation

- Undertake as needed integrated spatial planning for the NBSAP

- Develop, as needed, action plans to support the NBSAP

- Undertake, as needed, planning processes for ca - pacity development, resource mobilization, and monitoring and evaluation

In addition, pursuant to CBD Decision 15/6, countries also committed to submit their 7NR to the CBD by 28 February 2026. Component 2 of this Programme supports the development of these National Reports through undertaking the following proposed actions, which countries can select based on national circumstances and priorities:

- Prepare the national reporting processes, including stakeholder engagement

- Analyze the alignment of the NBSAP with the KMGBF, including the monitoring framework

- Assess progress towards national targets

- Assess progress towards the goals and targets of the KMGBF

- Identify key messages and conclusions

- Support capacities for using the headline and other indicators

- Progress Review: Key Activities and Results, January-December 2025

## Section 1: Analysis of Theory of Change

The objective of this project is to enable Parties to the Convention on Biological Diversity to implement two recent commitments: a) revise their National Biodiversity Strategies and Action Plans (NBSAPs) to align with the newly approved Kunming-Montreal Global Biodiversity Framework; and b) complete National Reports on the status of biodiversity and of achieving the goals and targets of this new framework. The project strategy is very relevant since it helps Parties continue to accelerate progress achieving GBF goals and targets.

## Section 2:  Overall progress against outcomes

The National Biodiversity Strategies and Action Plans (NBSAPs) are the principal instrument for implementing the Convention on Biological Diversity (CBD) and the Kunming-Montreal Global Biodiversity Framework (KMGBF) at the national level. Key outcome of this project is updating NBSAPs to align them with KMGBF to achieve the Convention’s vision of ‘living in harmony with nature by 2050’.

This project

## Section 3: Monitoring and Evaluation of activities.

The Project Steering Committee was established representing members from key national partner agencies which will review performance based on monitoring and evaluation, and implementation issues to ensure quality delivery of results.  Also, informal working group was established for monitoring and consultations on the process of updating NBSAP and development of 7th National Report.

## Section 4: Progress against each output

| Project Outcome 1: GBF-aligned NBSAP is developed |  |  |
| --- | --- | --- |
| indicators | Targets | Progress against targets |
| Number of countries that have updated their NBSAP to align with the KunmingMontreal Global Biodiversity Framework | Baseline: 0 Mid-term target: 30 End of Project Target: 69 (All participating countries) | Reporting period: Jan-Dec 2025 Cumulative total: n/a (this is global project) |
| Project Outcome 2.1: National Reports on Biodiversity (7NR) are completed for each country |  |  |
| Number of national reports completed and submitted to the CBD Secretariat | Baseline: 0 Mid-term target: 20 End of Project Target: 69 (All participating countries) | Reporting period: Jan-Dec 2025 Cumulative total: n/a (this is global project) |

Key Activities:

- Review of the work undertaken by national and international experts in the framework of the Early Action Support Programme (EAS)

- Regular communication with Regional Programme Team regarding project implementation process, online reporting tool and other related matters

- Regular contact/communication with National CBD Focal point and key national stakeholders related to project implementation

- Recruitment of  National expert to develop comprehensive stakeholder engagement plan for the NBSAP development/updating process, based on the results of a stakeholder analysis and international best practices

- Recruitment of  National expert to compile gap analysis for each Global Target of the GBF, to develop a detailed table containing the corresponding NBSAP item (or an indication of its absence) for each Global Target, compiling list of priority gaps and non-compliances ranked by severity and potential impact on achieving the GBF, and developing strategic recommendations for updating the NBSAP

- National Introductory Workshop was conducted with participation of representatives from key national agencies and organizations, including ministries, government committees, research institutes, universities, civil society and public organizations. This broad representation underscores the "whole of government" and "whole of society" approach necessary for the effective implementation of the GBF

Key Results:

## Section 5: Cross-Cutting Integration

Human and Social Context:

- Leave No One Behind

The project will not lead to exclusion of any potentially affected stakeholders, in particular marginalized groups and excluded individuals (including persons with disabilities), from fully participating in decisions that may affect them

- Human Rights

Aligned with this approach, this project mainstreams the human rights-based approach by providing guidance and capacity building to Parties (through technical support by the project) on gender-sensitive and socially inclusive stakeholder engagement (Outputs 1.1.1 and 1.1.2) , integration of social and environmental screening principles and procedures (Output 1.1.5), and establishing a  grievance redress mechanism (GRM) which will be accessible to all stakeholders to voice their concerns about the project. This will help ensure that the process followed by Parties to update NBSAPs is inclusive, free from discrimination and transparent.

- Gender Equality and Women’s Empowerment

Gender mainstreaming is an important aspect of CBD implementation., The global technical support grant component of the project will provide guidance to Parties on how to ensure a gender responsive and socially inclusive approach, including recommendations for inclusion of women and women’s groups in consultations and specific issues related to gender.

The project will promote gender equality and develop capacities contributing to the national gender equality agenda and globally at SDG 5. The project will develop gender analyses and action plans (Output 1.1.2) to ensure gender mainstreaming within consultation processes and integration of gender issues int the NBSAP updates.

- Disability Inclusion

The consultation guidelines require that culturally appropriate consultation mechanisms are deployed, including to consider participation access needs for persons with disabilities, and awareness of sociocultural power dynamics (gender norms, informal hierarchies, unpaid care roles) that may impact full participation.

- Cultural Heritage

Project will not have adverse impacts to sites, structures, or objects with historical, cultural, artistic, traditional or religious values or intangible forms of culture

Interactions between Social and Environmental Factors:

- Sustainability and Resilience

This is a key focus of the project insofar as it aims to help Parties update their NBSAPs to align them with the post-2020 GBF, the mission of which is ‘To take urgent action across society to conserve and sustainably use biodiversity and ensure the fair and equitable sharing of benefits from the use of genetics resources, to put biodiversity on a path to recovery by 2030 for the benefit of planet and people’.  The project will be contributing to the GBF’s long term vision of living in harmony with nature by 2050.

Natural Environment:

- Biodiversity Conservation

Project will not have adverse impacts to habitats (e.g. modified, natural, and critical habitats) and/or ecosystems and ecosystem services. It will not involve risks to endangered species (e.g. reduction, encroachment on habitat)

- Sustainable Natural Resource Management

Project will not involve increases in vulnerability to climate change impacts or disaster risks now or in the future (also known as maladaptive or negative coping practices). It will raise awareness to enhance future application of social and environmental safeguards standards and procedures, especially in the context of potential downstream impacts on Protected Areas or any other regulated areas/territories

- Climate Change

The project will not involve increases in vulnerability to climate change impacts or disaster risks now or in the future (also known as maladaptive or negative coping practices)

- Disaster Risks

The project will not involve outputs and outcomes sensitive or vulnerable to potential impacts of climate change or disasters

- Partnerships and Sustainability

Partnerships

The project employs a whole-of-government and whole-of-society approach and put efforts for implementation of a comprehensive stakeholder engagement to promote this approach.

The project coordinates closely with the Global Biodiversity Framework Early Action Support (GBF-EAS) and the Umbrella Programme to Support Development of Biodiversity Finance Plans (BIOFIN) to ensure that resources are used effectively towards NBSAP revision and 7NR preparation

Sustainability

The successful alignment of NBSAPs and National Biodiversity Targets (NBTs) with the post-2020 GBF will be an important for country to rollout implementation of those targets through targeted actions. And successful implementation of this project will provide a potential pathway for developing plans and scaling up action through projects funded in subsequent GEF cycles, or through funding from other donors.

- Update on risks and mitigation measures

Due to delayed start of the project in the country, the activities are slightly behind the established timelines for NBSAP Update and development of the 7th National Report. In addition, internet connection restrictions and challenging multi-level national bureaucratic procedures for approval of strategies/plans, may cause delays in submission of national Goals and Targets online as it is required by CBD. Project team is putting extra efforts to mitigate these potential risks via working closely with National CBD Focal Point to foster the approval process of NBSAP (updated goals and targets) timely informing high-level decision-makers regarding the process and receiving their feedback/approval. Additionally, project staff will support national stakeholders by providing reliable internet connection (CBD NFP and/or designated body/person) for incorporating data into Online Reporting Tool. See Updated Risk Log in Annex II.

- Key Challenges, Lessons Learned and Recommendations

As it was mentioned above that delayed start of the project has impacted the implementation process. However, successful steps were taken by country to address this challenge. Project Coordinator/Biodiversity Specialist was hired in October to catch up with project activities.  Recruitment of couple of national experts is underway which will foster the project implementation process.

There is a shortage of qualified local experts/consultants in the field of biodiversity conservation and related areas. Project staff is addressing this challenge disseminating the information regarding the project via NFP and key national stakeholders for greater public. The process of recruitment of individual consultants widely disseminated on UNDP Turkmenistan website and social media channels.

Lack of data or bureaucratic challenges of receiving data from sector ministries restricts the scope of activities for collecting qualitative and quantitative information for assessing the implementation of current NBSAP and its revision. The project team is addressing this challenge via regular consultations with key national partners regarding the necessity of quality data for updating the NBSAP and development of the report. In addition, capacity development activities are conducted for wide range of stakeholders by promoting whole-of-government and whole-of-society approach.

Lessons Learned:

As it was mentioned above, project has delayed start due to objective and subjective factors. However, having Project Coordinator and national experts on board, we will catch up with implementation of project activities. The process of hiring couple of experts is already underway and key national stakeholders are regularly advised to foster the process of updating NBSAP.

- Financial Summary

Table 1: Overview of available resources for the project duration

(Total funds received from different donors for the year of the AWP; please follow this format)

| Donor | Opening Balance | Contribution Received | Available Resources |
| --- | --- | --- | --- |
| GEF | 0 | 463,547 | 463,547 |
| Total | 0 | 463,547 | 463,547 |

Table 2: Overview of allocation and utilization per output

| Outcome | Global Environment Facility (GEF) |  | Total Utilization |
| --- | --- | --- | --- |
|  | Total Budget | Utilization |  |
| 1.1. GBF-aligned NBSAP is developed | 343,547 |  |  |
| 2.1 National Reports on Biodiversity are completed for each country | 100,000 |  |  |
| PMC | 20,000 | 2,426.45 |  |
| Total | 463,547 |  |  |

Include the two disclaimers as shown in the below footnotes.

- Annexes

## Annex I: Progress Review: detailed matrix of activities and results

| Outcome 1 | Indicators | Baseline | Mid-term target | Annual progress 2025 | Annual progress 2026 | Annual progress 2027 | Final target 2027 | Final progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1. GBF-aligned NBSAP is developed Budget: 343,547 Expenditure to date: | - Number of countries with NBSAPs that align with KM-GBF | 0 | 30 |  |  |  | 69 (All participating countries) |  |
| Activities |  |  | Results |  |  |  |  |  |
| Activity 1.1.1: Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the NBSAP |  |  | National expert was hired to develop comprehensive stakeholder engagement plan for the NBSAP development/updating process, based on the results of a stakeholder analysis and international best practices National Introductory Workshop was conducted with participation of representatives from key national agencies and organizations, including ministries, government committees, research institutes, universities, civil society and public organizations. This broad representation underscores the "whole of government" and "whole of society" approach necessary for the effective implementation of the GBF |  |  |  |  |  |
| Activity 1.1.2: A national gender analysis and action plan developed to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process. |  |  |  |  |  |  |  |  |
| Activity 1.1.3: Building on the results of the EAS to accelerate early action on NBSAPs, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework |  |  | National expert was hired to compile gap analysis for each Global Target of the GBF, to develop a detailed table containing the corresponding NBSAP item (or an indication of its absence) for each Global Target, compiling list of priority gaps and non-compliances ranked by severity and potential impact on achieving the GBF, and developing strategic recommendations for updating the NBSAP |  |  |  |  |  |
| Activity 1.1.4: Building on the results from policy alignment reviews included in the EAS, develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the NBSAP |  |  |  |  |  |  |  |  |
| Activity 1.1.5: An assessment of the potential environmental and social impacts and potential risks of the implementation of the updated NBSAP |  |  |  |  |  |  |  |  |
| Activity 1.1.6: Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP |  |  |  |  |  |  |  |  |
| Activity 1.1.7: Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP |  |  |  |  |  |  |  |  |
| Activity 1.1.8: An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project, the umbrella program to support development of biodiversity finance plans, and other initiatives such as BIOFIN |  |  |  |  |  |  |  |  |
| Outcome 2 | Indicators | Baseline | Mid-term target | Annual progress 2025 | Annual progress 2026 | Annual progress 2026 | Final target 2027 | Final progress |
| 2.1 National Reports on Biodiversity are completed for each country | - Number of national reports completed and submitted to the CBD Secretariat | 0 | 20 |  |  |  | 69 (All participating countries) |  |
| Activities |  |  | Results |  |  |  |  |  |
| Activity 2.1.1 Brief overview of the process of preparation of the report is completed |  |  |  |  |  |  |  |  |
| Activity 2.1.2 Status of the revised or updated national biodiversity strategy and action plan (NBSAP) in the light of the Kunming-Montreal Global Biodiversity Framework |  |  |  |  |  |  |  |  |
| Activity 2.1.3 Assessment of progress towards national targets are completed |  |  |  |  |  |  |  |  |
| Activity 2.1.4. Assessment of progress related to the goals and targets of the Kunming-Montreal Global Biodiversity Framework is completed |  |  |  |  |  |  |  |  |
| Activity 2.1.5 Conclusions on the implementation of the Convention and the Kunming-Montreal Global Biodiversity Framework are completed |  |  |  |  |  |  |  |  |

## Annex II: Updated Risk Log

| # | Description | Date Identified | Type | Impact & Probability | Counter-measures / Mngt response | Owner | Last Update | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Parties may not have access to the tools, methodologies and approaches required to complete all aspects of this project in time. | 30/09/2025 | Organizational | This will impact the performance of the project and empowerment of national counterparts P = 1 I =3 | This risk is mainly related to Online reporting Tool (ORT) of GBF. Due to internet restrictions in country, there is a potential challenge actually being able to access the online reporting tool (https://ort.cbd.int) by national stakeholders. This risk is treated by project staff via providing reliable internet connection for CBD NFP and/or designated body/person to incorporate data into ORT | Project Coordinator | 27/11/2025 | reducing |
| 2 | The risk of lack of national approval of updated NBSAPs and political will to implement the results of the project. (Theory of Change assumption) There is political will to validate GBF-aligned NBSAPs and NBTs | 31/10/2025 | Strategic | This will impact in the submission of the NBSAP to the Secretariat of CBD P = 2 I =4 | Project team treats this risk via working closely with National CBD Focal Point to foster the approval process of NBSAP (updated goals and targets) by in time informing high-level decision-makers regarding the process and receiving their feedback/approval | Project Coordinator | 27/11/2025 | reducing |

## Annex III: Multi-Year Work Plan for Turkmenistan (2024-2027)

| Quantum Outcome (GEF Component) | Quantum Output (GEF Outcome) | Quantum Activity (GEF Output) | Quantum Responsible Party (UNDP, IP, or Responsible Party) | Quantum Fund ID | Quantum Donor ID | Quantum Budgetary Account Code | Quantum Budget Account Description | Amount Year 2024 (USD) | Amount Year 2025 (USD) | Amount Year 2026 (USD) | Amount Year 2027 (USD) - 8 months | Total (USD) | Budget Note: |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Revision and updating of National Biodiversity Strategies and Action Plans | 1.1 GBF-aligned NBSAP is developed | 1.1.1 Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the NBSAP. | UNDP (insert country name CO) | 62000 | 10003 | 71300 | Local Consultants | 12,500 | 6,250 | 3,125 | 2,318 | 24,193 | 1 |  |
|  |  |  |  |  |  | 71400 | Contractual services - Individuals | 5,000 | 1,875 | 1,250 | 1,250 | 9,375 | 2 |  |
|  |  |  |  |  |  | 71600 | Travel | 2,500 | 2,500 | - | - | 5,000 | 3 |  |
|  |  |  |  |  |  | 75700 | Training, workshop and conference | 2,500 | 1,875 | - | - | 4,375 | 4 |  |
|  |  | Total Output 1.1.1 |  |  |  |  |  | 22,500 | 12,500 | 4,375 | 3,568 | 42,943 |  |  |
|  |  | 1.1.2 A national gender analysis and action plan developed to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process. | UNDP (insert country name CO) | 62000 | 10003 | 71300 | Local Consultants | 12,500 | 6,250 | 3,125 | 2,318 | 24,193 | 5 |  |
|  |  |  |  |  |  | 71400 | Contractual services - Individuals | 5,000 | 1,875 | 1,250 | 1,250 | 9,375 | 6 |  |
|  |  |  |  |  |  | 71600 | Travel | 2,500 | 2,500 | - | - | 5,000 | 7 |  |
|  |  |  |  |  |  | 75700 | Training, workshop and conference | 2,500 | 1,875 | - | - | 4,375 | 8 |  |
|  |  | Total Output 1.1.2 |  |  |  |  |  | 22,500 | 12,500 | 4,375 | 3,568 | 42,943 |  |  |
|  |  | 1.1.3 Building on the results of the EAS to accelerate early action on NBSAPs, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework. | UNDP (insert country name CO) | 62000 | 10003 | 71300 | Local Consultants | 12,500 | 6,250 | 3,125 | 2,318 | 24,193 | 9 |  |
|  |  |  |  |  |  | 71400 | Contractual services - Individuals | 5,000 | 1,875 | 1,250 | 1,250 | 9,375 | 10 |  |
|  |  |  |  |  |  | 71600 | Travel | 2,500 | 2,500 | - | - | 5,000 | 11 |  |
|  |  |  |  |  |  | 75700 | Training, workshop and conference | 2,500 | 1,875 | - | - | 4,375 | 12 |  |
|  |  | Total Output 1.1.3 |  |  |  |  |  | 22,500 | 12,500 | 4,375 | 3,568 | 42,943 |  |  |
|  |  | 1.1.4 Building on the results from policy alignment reviews included in the EAS, develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the NBSAP. | UNDP (insert country name CO) | 62000 | 10003 | 71300 | Local Consultants | 12,500 | 6,250 | 3,125 | 2,318 | 24,193 | 13 |  |
|  |  |  |  |  |  | 71400 | Contractual services - Individuals | 5,000 | 1,875 | 1,250 | 1,250 | 9,375 | 14 |  |
|  |  |  |  |  |  | 71600 | Travel | 2,500 | 2,500 | - | - | 5,000 | 15 |  |
|  |  |  |  |  |  | 75700 | Training, workshop and conference | 2,500 | 1,875 | - | - | 4,375 | 16 |  |
|  |  | Total Output 1.1.4 |  |  |  |  |  | 22,500 | 12,500 | 4,375 | 3,568 | 42,943 |  |  |
|  |  | 1.1.5 An assessment of the potential environmental and social impacts and potential risks of the implementation of the updated NBSAP. | UNDP (insert country name CO) | 62000 | 10003 | 71300 | Local Consultants | 12,500 | 6,250 | 3,125 | 2,318 | 24,193 | 17 |  |
|  |  |  |  |  |  | 71400 | Contractual services - Individuals | 5,000 | 1,875 | 1,250 | 1,250 | 9,375 | 18 |  |
|  |  |  |  |  |  | 71600 | Travel | 2,500 | 2,500 | - | - | 5,000 | 19 |  |
|  |  |  |  |  |  | 75700 | Training, workshop and conference | 2,500 | 1,875 | - | - | 4,375 | 20 |  |
|  |  | Total Output 1.1.5 |  |  |  |  |  | 22,500 | 12,500 | 4,375 | 3,568 | 42,943 |  |  |
|  |  | 1.1.6 Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP. | UNDP (insert country name CO) | 62000 | 10003 | 71300 | Local Consultants | 12,500 | 6,250 | 3,125 | 2,318 | 24,193 | 21 |  |
|  |  |  |  |  |  | 71400 | Contractual services - Individuals | 5,000 | 1,875 | 1,250 | 1,250 | 9,375 | 22 |  |
|  |  |  |  |  |  | 71600 | Travel | 2,500 | 2,500 | - | - | 5,000 | 23 |  |
|  |  |  |  |  |  | 75700 | Training, workshop and conference | 2,500 | 1,875 | - | - | 4,375 | 24 |  |
|  |  | Total Output 1.1.6 |  |  |  |  |  | 22,500 | 12,500 | 4,375 | 3,568 | 42,943 |  |  |
|  |  | 1.1.7 Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP | UNDP (insert country name CO) | 62000 | 10003 | 71300 | Local Consultants | 12,500 | 6,250 | 3,125 | 2,318 | 24,193 | 25 |  |
|  |  |  |  |  |  | 71400 | Contractual services - Individuals | 5,000 | 1,875 | 1,250 | 1,250 | 9,375 | 26 |  |
|  |  |  |  |  |  | 71600 | Travel | 2,500 | 2,500 | - | - | 5,000 | 27 |  |
|  |  |  |  |  |  | 75700 | Training, workshop and conference | 2,500 | 1,875 | - | - | 4,375 | 28 |  |
|  |  | Total Output 1.1.7 |  |  |  |  |  | 22,500 | 12,500 | 4,375 | 3,568 | 42,943 |  |  |
|  |  | 1.1.8 An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project, the umbrella program to support development of biodiversity finance plans, and other initiatives such as BIOFIN. | UNDP (insert country name CO) | 62000 | 10003 | 71300 | Local Consultants | 12,500 | 6,250 | 3,125 | 2,321 | 24,196 | 29 |  |
|  |  |  |  |  |  | 71400 | Contractual services - Individuals | 5,000 | 1,875 | 1,250 | 1,250 | 9,375 | 30 |  |
|  |  |  |  |  |  | 71600 | Travel | 2,500 | 2,500 | - | - | 5,000 | 31 |  |
|  |  |  |  |  |  | 75700 | Training, workshop and conference | 2,500 | 1,875 | - | - | 4,375 | 32 |  |
|  |  | Total Output 1.1.8 |  |  |  |  |  | 22,500 | 12,500 | 4,375 | 3,571 | 42,946 |  |  |
|  | Total Outcome 1.1 |  |  |  |  |  |  | 180,000 | 100,000 | 35,000 | 28,547 | 343,547 |  |  |
| Total Component 1 |  |  |  |  |  |  |  | 180,000 | 100,000 | 35,000 | 28,547 | 343,547 |  |  |
| 2. Complete 7th National Reports on Biodiversity | 2.1 National Reports on Biodiversity are completed for each country | 2.1.1 Brief overview of the process of preparation of the report is completed. | UNDP (insert country name CO) | 62000 | 10003 | 71300 | Local Consultants | 3,000 | 3,000 | 10,000 | 1,000 | 17,000 | 33 |  |
|  |  |  |  |  |  | 71400 | Contractual services - Individuals | - | 1,000 | 1,000 | - | 2,000 | 34 |  |
|  |  |  |  |  |  | 71600 | Travel | 1,000 | - | - | - | 1,000 | 35 |  |
|  |  | Total Output 2.1.1 |  |  |  |  |  | 4,000 | 4,000 | 11,000 | 1,000 | 20,000 |  |  |
|  |  | 2.1.2 Status of the revised or updated national biodiversity strategy and action plan (NBSAP) in the light of the Kunming-Montreal Global Biodiversity Framework. | UNDP (insert country name CO) | 62000 | 10003 | 71300 | Local Consultants | 3,000 | 3,000 | 10,000 | 1,000 | 17,000 | 36 |  |
|  |  |  |  |  |  | 71400 | Contractual services - Individuals | - | 1,000 | 1,000 | - | 2,000 | 37 |  |
|  |  |  |  |  |  | 71600 | Travel | 1,000 | - | - | - | 1,000 | 38 |  |
|  |  | Total Output 2.1.2 |  |  |  |  |  | 4,000 | 4,000 | 11,000 | 1,000 | 20,000 |  |  |
|  |  | 2.1.3 Assessment of progress towards national targets are completed; | UNDP (insert country name CO) | 62000 | 10003 | 71300 | Local Consultants | 3,000 | 3,000 | 10,000 | 1,000 | 17,000 | 39 |  |
|  |  |  |  |  |  | 71400 | Contractual services - Individuals | - | 1,000 | 1,000 | - | 2,000 | 40 |  |
|  |  |  |  |  |  | 71600 | Travel | 1,000 | - | - | - | 1,000 | 41 |  |
|  |  | Total Output 2.1.3 |  |  |  |  |  | 4,000 | 4,000 | 11,000 | 1,000 | 20,000 |  |  |
|  |  | 2.1.4. Assessment of progress related to the goals and targets of the Kunming-Montreal Global Biodiversity Framework is completed; | UNDP (insert country name CO) | 62000 | 10003 | 71300 | Local Consultants | 3,000 | 3,000 | 10,000 | 1,000 | 17,000 | 42 |  |
|  |  |  |  |  |  | 71400 | Contractual services - Individuals | - | 1,000 | 1,000 | - | 2,000 | 43 |  |
|  |  |  |  |  |  | 71600 | Travel | 1,000 | - | - | - | 1,000 | 44 |  |
|  |  | Total Output 2.1.4 |  |  |  |  |  | 4,000 | 4,000 | 11,000 | 1,000 | 20,000 |  |  |
|  |  | 2.1.5 Conclusions on the implementation of the Convention and the Kunming-Montreal Global Biodiversity Framework are completed. | UNDP (insert country name CO) | 62000 | 10003 | 71300 | Local Consultants | 3,000 | 3,000 | 10,000 | 1,000 | 17,000 | 45 |  |
|  |  |  |  |  |  | 71400 | Contractual services - Individuals | - | 1,000 | 1,000 | - | 2,000 | 46 |  |
|  |  |  |  |  |  | 71600 | Travel | 1,000 | - | - | - | 1,000 | 47 |  |
|  |  | Total Output 2.1.5 |  |  |  |  |  | 4,000 | 4,000 | 11,000 | 1,000 | 20,000 |  |  |
|  | Total Outcome 2.1 |  |  |  |  |  |  | 20,000 | 20,000 | 55,000 | 5,000 | 100,000 |  |  |
| Total Component 2 |  |  |  |  |  |  |  | 20,000 | 20,000 | 55,000 | 5,000 | 100,000 |  |  |
| Sub-total Components 1 and 2 |  |  |  |  |  |  |  | 200,000 | 120,000 | 90,000 | 33,547 | 443,547 |  |  |
| PMC |  |  |  |  |  | 74596 | Services to projects - GOE for CO | 5,000 | 5,000 | 5,000 | 5,000 | 20,000 | 48 |  |
| Total Project Management Cost |  |  |  |  |  |  |  | 5,000 | 5,000 | 5,000 | 5,000 | 20,000 |  |  |
| Grand total |  |  |  |  |  |  |  | 205,000 | 125,000 | 95,000 | 38,547 | 463,547 |  |  |

Disclaimer 1: Data contained in this financial report section is an extract of UNDP financial records. All financial provided above is provisional. Certified financial statements will be provided on <indicate date (30 June of the following year)>.

Disclaimer 2: Of the USD xxxxx presented above, USD xxxx corresponds to eligible expenses (as per IPSAS terminology), and USD xxxx corresponds to legal commitments in force between UNDP and third parties for the reporting period.