COUNTRY IMPLEMENTATION STRATEGY

SUBMITTED TO

FOR THE PERIOD 2019-2022

BIOFIN Phase II

# Contents

Contents	2

ACRONYMS	5

1.	Vision	8

2.	Introduction	9

2.1.	Phase 1 of BIOFIN 2015 - 2018	10

2.1.1.	Policy and Institutional Review (PIR)	10

2.1.2.	Biodiversity Expenditure Review (BER)	11

2.1.3.	The Finance Needs Assessment	12

2.1.4.	The Biodiversity Finance Plan	13

2.2.	Initial work on the Implementation of Finance Solutions under BIOFIN Phase I	13

2.2.1.	Making a case for protected areas in the Northern Cape	13

2.2.2.	Wildlife ranching certification	14

2.2.3.	Biodiversity tax incentives	14

2.2.4.	National Biodiversity Offsets Policy	14

3.	BIOFIN Phase 2 Strategy	15

3.1.	Approach	16

3.1.1.	South Africa’s National Biodiversity Economy Strategy	16

3.2.	Protected areas	20

3.2.1.	Growing own revenue in protected areas	20

3.2.2.	Property rates tax reform	21

3.2.3.	Building a grant mechanism to adequately finance the biodiversity stewardship programmes	22

3.2.4.	Institutional support for biodiversity tax incentives	23

3.2.5.	Improved biodiversity offsets modality for protected area expansion	24

3.3.	Sustainable utilization	25

3.3.1.	Implementation of a voluntary market-based certification in the wildlife sector	25

3.3.2.	Development and promotion of an online economy investment portal	26

3.3.3.	Improving the effectiveness of permits	27

4.	Management Arrangements	28

4.1.	BIOFIN Core Team	28

4.2.	High Level Political Commitment	28

4.3.	BIOFIN Governance Mechanism	29

4.3.1	Project Steering Committee (PSC)	29

4.3.2	BIOFIN Project Management Team	29

4.3.3	BIOFIN Project Task Team/s (PTT)	30

5	Institutionalization	30

5.3	Partnerships and other stakeholders	31

5.2 Related initiatives	31

5.3.1	Sustainable financing framework for state managed protected areas	32

5.3.2	Protected Areas Expenditure Review	32

5.3.3	Natural Capital Accounting (NCA) and Valuation of Ecosystem Services (VES) Project – South Africa	32

5.4	Capacity Development	32

5.5	Scaling Financial Solutions	33

5.6	Sustainability / Exit plans	33

6	Communication	33

7	Monitoring and Evaluation	33

8	Knowledge Management	34

9	Annexure 1: Multiyear Work Plan	1

10	Annexure 2: Finance Solutions Proposals	1

11	Annexure 3: Terms of reference for team members	1

12	Annexure 5: Logical/Results Framework	1

13	Annexure 6: Gender Action Plan	1

LIST OF TABLES

Table 1 		PIR issues and recommendations

Table 2		Prioritised Finance Solutions

Table 3		Activities to institutionalise BIOFIN

LIST OF FIGURES

Figure 1		Action pillars and Finance Solutions

Figure 2		Linking Financial Solutions to the biodiversity economy

# ACRONYMS

BER		Biodiversity Expenditure Review

BES		Biodiversity Economy Strategy

BFP		Biodiversity Finance Plan

BIOFIN		Biodiversity Finance Initiative

CBD 		Convention on Biological Diversity

CEO		Chief Executive Officer

CITES		Convention on International Trade in Endangered Species

CO		Country Office

COGTA		Cooperative Governance and Traditional Affairs

DAFF		Department of Agriculture, Forestry and Fisheries

DEFF		Department of Environmental, Forestry and Fisheries

DMR		Department of Mineral Resources

DENC		Department of Environment and Nature Conservation

DPME		Department of Planning, Monitoring and Evaluation

DPW		Department of Public Works

DSBD		Department of Small Business Development

DWS		Department of Water and Sanitation

ECPTA		Eastern Cape Parks and Tourism Agency

EEA		Experimental Ecosystem Accounting

EKZNW		Ezemvelo KZN Wildlife

ENE		Estimate of National Expenditure

EPIP		Environmental Protection & Infrastructure Projects

ESG		Environmental, Social and Governance

FNA		Finance Needs Assessment

FS		Financial Solution

GDP		Gross Domestic Product

GEF		Global Environment Facility

GTAC		Government Technical Advice Centre

IUCN		International Union for the Conservation of Nature

ITA		Income Tax Act

LEDET		Limpopo Economic Development, Environment, and Tourism

MEC		Member of the Executive Council (Provincial)

MINMEC	Minister and MEC Committee

MINTECH	Minister and MEC Technical Committee

M&E		Monitoring and Evaluation

MPRA		Municipal Property Rates Act

MTEF 		Medium Term Expenditure Framework

MTSF		Medium Term Strategic Framework

NBES		National Biodiversity Expansion Strategy

NBSAP		National Biodiversity Strategy and Action Plan

NCA		Natural Capital Accounting

NDP		National Development Plan

NGO		Non-governmental Organisation

NPAES		National Protected Area Expansion Strategy

NT		National Treasury

OECM		Other Effective area-based Conservation Measures

ODA		Overseas Development Assistance

PA		Protected Areas

PAME 		Protected Areas Management Effectiveness

PAMA		Protected Areas Management Authorities

PDI		Previously Disadvantaged Individuals

PIR		Policy Institutional Review

PMT		Project Management Team

PPA		Private Protected Areas

PSC		Project Steering Committee

PTT		Project Task Team

SALGA		South African Local Government Association

SANBI		South African National Biodiversity Institute

SANParks	South African National Parks

SEEA		System of Environmental Economic Accounting

SARS		South African Revenue Services

SDG		Sustainable Development Goals

SME		Small and Medium Enterprise

UNDP		United Nations Development Programme

UNSD		United Nations Statistics Division

USD		United States Dollar

VES		Valuation of Ecosystem Services

WRSA		Wildlife Ranching South Africa

ZAR		South African Rand

The Biodiversity Finance Initiative

Implementation Strategy for BIOFIN Phase II

2019 – 2022

Country				:              South Africa

Budget				:              USD 2,250,000

Submitted by the Project Manager:     	Flora Mokgohloa

Endorsed by the Director General	:   	Nosipho Ngcaba

Steering Committee Chair	:  	Shonisani Munzhedzi

UNDP Country Office Representative	Dr Janice Golding

BIOFIN Technical Adviser	: 	Tracey Cumming

Global BIOFIN Manager		: 	Onno van den Heuvel

-----------------------------------------------------------------------------------------------------------------------------------------------------------

# Vision

South Africa’s development trajectory is articulated in the National Development Plan 2030 (NDP 2030), which emphasizes economic growth and development but recognizes the “need to protect the natural environment in all respects, leaving subsequent generations with an endowment of at least equal value”. By 2030, South Africa should be well on the way to a low carbon resilient economy. The NDP 2030 therefore recognizes the linkages between protection of biodiversity, ecosystem health, water management and creating decent jobs as many vulnerable communities are dependent on biodiversity for livelihoods. Furthermore, biodiversity is identified as one of the sectors to contribute to addressing the triple challenges of poverty, unemployment and inequality.

Recognised as one of the most biodiverse countries, with 9 biomes and approximately 95 000 species, South Africa aims to protect these natural resources, whilst restoring degraded ecosystems and utilising biodiversity resources for benefit of all. In this regard, the vision for the country as outlined in the National Biodiversity Strategy Action Plan 2015-2025 (NBSAP), is ‘to conserve, manage and sustainably use biodiversity to ensure equitable benefits for the people of South Africa now and in the future’. This vision is supported by the following six (6) goals:

- Management of biodiversity assets and their contribution to the economy, rural development, job creation and social well-being is enhanced.

- Investments in ecological infrastructure enhance resilience and ensure benefits to society

- Biodiversity considerations are mainstreamed into policies, strategies and practices of a range of sectors.

- People are mobilized to adopt practices that sustain the long-term benefits of biodiversity

- Conservation and management of biodiversity is improved through the development of an equitable and suitably skilled workforce.

- Effective knowledge foundations, including indigenous knowledge and citizen science, support the management, conservation and sustainable use of biodiversity.

Key in meeting these goals is the adequate resourcing and financing of biodiversity and conservation, protection and management efforts. South Africa, therefore, considers issues relating to biodiversity finance as the practice of raising and managing capital and using financial incentives to support sustainable biodiversity management.

The BIOFIN approach includes private and public financial resources used to conserve biodiversity and investments in commercial activities that produce positive biodiversity outcomes. BIOFIN provides an important opportunity to develop people centred developmental approaches for the sustainable use of biodiversity, ecosystem restoration and resourcing biodiversity and conservation.

The NBSAP 2015-2025, has 6 strategic objectives and related outcomes one of which makes reference to resource mobilisation. Outcome 3.5 states that by 2025, there will be appropriate allocation of resources in key sectors and spheres of government to facilitate effective management of biodiversity, especially in biodiversity priority areas. The related indicator is ‘number of sector policies and/or institutional structures adjusted to facilitate the sustainable flow of resources into the biodiversity sector’. In this regard, in line with global commitments and national consideration as outlined in the NDP and the NBSAP, the vision for BIOFIN is sustainable flow of resources for effective management of biodiversity.

# Introduction

Globally, the BIOFIN project is significant since available evidence indicates that a significant funding gap exists for biodiversity and that large streams of global investment are required to meet the Aichi targets. Target 20 calls for countries to assess the financial resource needs and mobilize financial resources for effectively implementing the Strategic Plan for Biodiversity.  In addition, funding for biodiversity has been identified as a global goal and is specifically included under the Sustainable Development Goals (SDG) Target 15. SDG 15 specifically requires tracking of official development assistance (ODA) and public expenditure on conservation and sustainable use of biodiversity and ecosystems. The BIOFIN Initiative supports initiatives to meet these global obligations and is therefore well placed to provide South Africa with the metrics for reporting on this important aspect.

South Africa has identified the need to systematically prioritize resources and activities articulated in the NBSAP to provide appropriate measures for implementation. The current expenditure on biodiversity is largely driven by the public sector which amounts to just under 1 % of total government expenditure. The total funding required to finance 68% of the NBSAP actions up to 2025 is estimated at ZAR 63 billion, whilst estimates of finance shortfalls range between 34% and 67% of actual spending levels. At the same time, as a developing country, South Africa has identified biodiversity as a sector that can contribute to economic growth through the creation of jobs in biodiversity value chain, creation of new entrants to the biodiversity sector and conserving more land for biodiversity. Through the biodiversity economy, the wildlife economy is projected to have the potential to create an additional 100,000 new jobs and grow at 10% per annum by 2030, whilst the bioprospecting industry could create a sustainable, inclusive and commercially viable sector by adding 10 000 new jobs from the current 6 200 jobs and contributing ZAR1.7 billion to the Gross Domestic Product (GDP) at 10% p.a. till 2030. Furthermore, vast opportunities have been identified in the ecotourism space, where protected areas can be unlocked to create job opportunities for local communities and small and medium enterprises (SME). A paradigm shift is required towards new investment and fiscal policy that better incorporates the economic value and financial benefits of biodiversity and sustainable development.

BIOFIN provides a useful mechanism to prioritize actions to meet the funding gap through:

- Avoiding future expenditures through strategic investment and policy changes;

- Delivering better on conservation through improved effectiveness, efficiency and synergies;

- Generating revenues targeted towards biodiversity; and

- Realigning expenditures to reduce negative impacts and improve positive outcomes.

## Phase 1 of BIOFIN 2015 - 2018

In Phase 1 of BIOFIN, using the BIOFIN methodology, South Africa completed the Policy and Institutional Review, the Biodiversity Expenditure Review and the Finance Needs Assessment based on the National Biodiversity Strategy and Action Plan (NBSAP 2015-2025). These informed the completion of the Biodiversity Finance Plan (BFP) in which finance solutions for implementation in South Africa were identified.

### Policy and Institutional Review (PIR)

The PIR analyzed the integration of biodiversity and ecosystem services in sectoral and development policy, planning and institutions by identifying policy and institutional frameworks driving positive and negative trends in biodiversity loss and protection. The policy review identified policies and policy factors, whilst the Institutional Review identified the key existing and potential future finance actors under the ‘business as usual scenario, and a ‘biodiversity investment’ scenario. The ‘business as usual’ scenario highlighted what pressures will persist on biodiversity into the future without intervention, whilst the ‘biodiversity investment’ scenario highlighted how addressing pressures through the implementation of the NBSAP would lead to the improved status and trends in biodiversity and ecosystems, and associated human wellbeing. The key issues and recommendations from the PIR are presented in Table 1 below.

Table 1: PIR Issues and recommendations

| Key issue | Recommendations |
| --- | --- |
| The ability to motivate for increased funding for the effective implementation of policy towards meeting biodiversity management and conservation target | There is a need in the environmental sector to ensure stronger alignment of departmental budgets in the estimate of National Expenditure (ENE) with broader national priorities in the National Development Plan (NDP) and the Medium Term Strategic Framework (MTSF). |
|  | There is a need to strengthen performance monitoring and reporting systems to better articulate impact and outcomes of biodiversity management functions, including cross-sectoral impacts. |
|  | There is need to enhance financial resources for biodiversity management functions and identify strategic level capacity to identify and leverage areas of alignment between departments. |
| The ability to ring-fence funds for biodiversity management and conservation, particularly in transfers between National Treasury, DEFF, provincial environment departments and municipalities. | There is a need for mechanisms to ensure ring-fenced allocations for the environmental sector to transfer funds to provinces for discrete purposes to do resource management and protection. |
|  | There is an opportunity that exists to align and motivate for such a ring-fencing mechanism with a quantification of the unfunded biodiversity mandate |
| The need to improve capacities to ensure effective enforcement of legislation, including legal recourse for harm to the environment. | Strengthen capacities in the legal system to understand the full impact of environmental transgressions in order to ensure sanctions are a sufficient deterrent. |
|  | Identify and address other institutional factors contributing towards weak enforcement such as lack of capacity and resources |
| The ability to grow the resource base for biodiversity management through better alignment of functions between sectors that deliver mutual benefits. | Identify capacities needed to ensure alignment of biodiversity management functions and the budgets of sectors that these functions serve. |
|  | Identify opportunities and capacities needed to be able to effectively and efficiently direct revenue from revenue-generating activities to the management of biodiversity (the asset base) that generates that revenue. |
| Effectively addressing issues to ensure that sectors that impact biodiversity pay more of true full cost of the impact, and are sufficiently able to minimise or offset the impacts of their activities on biodiversity. | An improved understanding of the costs involved for particular sectors to more fully mitigate (including managing and conserving) impacts on biodiversity, particularly relative to other development costs. |
|  | Ensuring sufficient regulatory clarity around the application of biodiversity offsets as a mechanism to compensate for unavoidable biodiversity loss |
| A range of opportunities exist to grow and strengthen donor investment in biodiversity outcomes. | Explore opportunities through BIOFIN to engage donors on foreign aid policies (in country and multilateral) to better accommodate the finance support needed for biodiversity interventions. |
|  | Enhance investment of development aid in other sectors (e.g. health, climate finance) that benefit from or impact on biodiversity management. |
|  | Ensure donor-funded programmes or initiatives consistently address mechanisms to ensure the longer term sustainability of outcomes of the funding as part of the investment. |

### Biodiversity Expenditure Review (BER)

The Biodiversity Expenditure Review quantified past and current public and private expenditure on biodiversity in a range of sectors.  The BER found that the Government of South Africa, through the National Revenue Fund, is the single biggest funder as well as implementer of biodiversity-related activities. The percentage of total consolidated government expenditure directed towards biodiversity conservation-related activities was approximately 0.93% per year between 2009 and 2015. National government departments and their entities spent ZAR36, 1 billion, or 60%, on biodiversity, compared to provincial government departments and entities (ZAR19, 7 billion, or 33%) and local government (ZAR4, 1 billion, or 7%). The general trend indicates a negative growth in government allocations which implies inability to perform basic biodiversity management functions.

For the non-state sector, the BER identified two sources of private sector expenditure namely; Non-Government Organisation (NGO) expenditure and the expenditure related to the ongoing management of South Africa’s private and communal protected areas. NGOs spending funds on biodiversity in South Africa receive their funds from a range of sources. Of the seven NGOs analysed, the largest source of funds came from international private sector sources (39%). Total biodiversity expenditure by NGOs operating in South Africa from 2009 to 2015 was estimated to be ZAR1.78 billion.

In respect of revenue, only the South African National Parks (SANParks) can raise revenue from a variation of activities and product offerings within the system of national parks. Notwithstanding limitations in constitutional mandate to raise revenue, the provincial agencies of the North West and Kwa-Zulu Natal (Ezemvelo-KZN) provinces were able to increase their revenue by 37% and 29% respectively during the period 2009 to 2015. Other management authorities raised an average of 13% revenue, and this has implications for future budget allocations. The recommendations from the BER are: -

- Setting Public Biodiversity Finance Targets in the medium term to increase the number of biodiversity initiatives and their subsequent impact.

- Improved Reporting on Biodiversity Financial Flows for all government departments and entities to report on their plans to invest in biodiversity-related initiatives and actual biodiversity expenditure to relevant authorities.

- Making the Improved Case for Increased Biodiversity Finance at all levels of government, to ensure increased sustainable funding for management authorities and other government departments, according to their allocated mandate.

- Improved Monitoring of Overseas Development Assistance (ODA) Flows for Biodiversity-related Initiatives to better identify and track allocations outside the official budget system.

- NGO and Government Collaboration for Biodiversity Initiatives to improve the effectiveness of biodiversity finance, allowing for common plans and initiatives to be aligned and implemented.

- Private and communal protected areas should continue to be recognised and supported as they make up 30% of protected land. The private and communal protected areas saves the state the cost of purchasing land for protected area expansion, as well as the cost of managing the land

- Developing a Biodiversity-Focused Budget Tagging System integrated into existing budgeting and accounting systems to ensure accurate apportionment of biodiversity expenditure within planning, budgeting and budget execution in order to progressively achieve the NBSAP targets.

### The Finance Needs Assessment

The Finance Needs Assessment (FNA) provided a costing of the National Biodiversity Strategy and Action Plan (NBSAP) for 2015 – 2025 and estimated a finance gap for biodiversity at a country level. It indicates that ZAR63 billion will be required over 10 years based on 68% of the NBSAP actions only in relation to major funding needs in ecosystem restoration and protected area establishment and management. Additional Actions in the NBSAP were not able to be costed, therefore the total funding need to implement the NBSAP should be considered to be higher than ZAR63 billion.   In order to get a sense of the funding gap for biodiversity conservation in South Africa, five case studies were examined, including studies on two provincial agencies; 11 national parks; a rationalisation study of protected area agencies; and the National Biodiversity Framework 2008. These case studies demonstrated a percentage funding gap from 24% to 67%. This is illustrative of the magnitude of the financial gap faced by biodiversity actors in the sector. Reducing the funding gap for biodiversity can be addressed by increasing funding from existing sources, identifying new and innovative sources of funding, and improving the effectiveness with which resources are allocated and spent. In order to reduce the funding gap, the main recommendation in the FNA was to implement results based costing for projects, programmes and policies in order to integrate financial planning with programmes of work, and motivate more accurately for their funding needs to be met. In addition, new policies, strategies and frameworks developed by the sector should be costed to support their implementation.

### The Biodiversity Finance Plan

Building on the PIR, the BER and the FNA, the Biodiversity Finance Plan was completed to provide Finance Solutions (practical tools) that can unlock biodiversity finance for the sector over the short to medium term. In the Biodiversity Finance Plan, 16 finance solutions were categorised into three action pillars, namely protected areas; ecosystem restoration; and sustainable utilisation, as depicted in Figure 1 below.

Figure 1: Action pillars and related finance solutions

The Biodiversity Economy Financial Solution includes a number of actions to implement the Biodiversity Economy Strategy. Biodiversity stewardship which cuts across the three action pillars was identified as an enabler in implementation, as it is linked to many of the finance solutions. Another finance solution which has subsequently added is the effectiveness of permits and licences that are administered in the biodiversity sector which also links with fines and penalties. The BFP is attached in Annexure 4.

## Initial work on the Implementation of Finance Solutions under BIOFIN Phase I

During the course of Phase I, two finance solutions were already initiated, namely the making a case for protected area funding in the Northern Cape and investigation of the viability of a wildlife ranching certification scheme in the country. In addition to this, the BIOFIN team provided technical input to finance mechanisms that were in the process of being developed while the BIOFIN Phase I studies where underway. These were the development of a national policy on biodiversity offsets, led by DEFF with partners, and the development of biodiversity tax incentives. The finance mechanism on biodiversity tax incentives was being led by BirdLife South Africa, as part of a Global Environment Facility (GEF) funded project implemented through the South African National Biodiversity Institute (SANBI). For effective implementation, there is a need for further work on these finance solutions as part of Phase 2 strategy implementation which is outlined below.

### Making a case for protected areas in the Northern Cape

Under the Protected Area pillar, a study on making a case for protected areas with specific reference to the Northern Cape Province was completed. This was motivated by the fact that expenditure on protected areas in this province has declined dramatically over the years. The outcome of the study provides the province with a mechanism for valuing ecosystem services and practical decision support tools to motivate and lobby for funding with the Provincial Treasury and develop partnerships in the management of biodiversity. Further refinement of this will require developing a Sustainable Finance Plan for Protected Areas which will quantify and identify finance gaps and needs and possible sources. This will be complemented by an effective communication strategy, tools and mechanisms to market the products and services on offer which will be implemented as part of Phase 2 within the finance solutions of growing protected areas own revenue. The overall outcome of this study will be shared with other management authorities.

### Wildlife ranching certification

One of the finance solutions falling within the Sustainable Utilisation pillar was on investigating the feasibility of a certification scheme for wildlife ranching in the country. This was motivated by the fact that there is no scheme to help to identify environmentally sound practices in the wildlife sector, making it difficult for the market to reward ‘greener’ enterprises. The outcome of the study indicates that there is a need for a scheme in order to encourage best practice.

Consultations were limited to wildlife association level participation, further consultations with the land owners and business owners in the sector will be required as part of Phase 2 to present the outcome of the study and depending on the outcome to possibly design a certification scheme for implementation. Once the scheme is implemented, funds collected from participants will be invested back into biodiversity. As wildlife certification is part of sustainable utilisation, further work on this finance solution will be implemented as part of the biodiversity economy finance solution.

### Biodiversity tax incentives

The Fiscal Benefits Project funded by Global Environment Facility undertaken through SANBI by BirdLife South Africa, was launched in 2015 and has successfully tested biodiversity tax incentives as a benefit for landowners and communities who have declared protected areas through the national biodiversity stewardship initiative. The success of the project has led to the introduction of a new tax incentive into the Income Tax Act where Section 37D provides a tax break for conservation commitment. During Phase I, BIOFIN provided technical input to this programme of work. This finance mechanism received a special commendation of the Pathfinder Award at COP 14 held in Egypt.

Continued implementation is required for this finance solution to be fully effective, including further engagement with National Treasury (NT) to identify potential areas for improvement, further amendments to tax legislation, and engagements with the South African Revenue Service (SARS) to create supporting policy and tax appropriation tools that correspond with legislative amendments. In addition to this, more capacity development will be required to build a coalition of experts to guide uptake of the tax incentives on the ground.

### National Biodiversity Offsets Policy

The National Biodiversity Offsets Policy was developed during the course of Phase I of BIOFIN, and BIOFIN provided technical input to relevant workshops and to the actual text of the Policy. This policy has since gone out for public review and awaiting cabinet approval. A finance solution on biodiversity offsets will be implemented as part of Phase II.

# BIOFIN Phase 2 Strategy

The legacy of the past which manifests itself in the structural inequalities characterizing South Africa’s economy exclude Previously Disadvantaged Individuals (PDIs) to participate meaningfully in the protection, restoration and sustainable utilization of biodiversity. South Africa is therefore one of only a few countries in the world where participation in the protection and sustainable use and ownership of biodiversity economy, especially the wildlife, is vested in private landowners, which presents game ranchers with a comparative advantage second to none. Whilst some progress has been made to get new players in the sector with government support, the meaningful participation of PDIs continues to be hindered by high barriers to entry such as ownership and access to land, access to capital costs for acquiring land, associated infrastructure, skills and access to biodiversity resources.

Biodiversity has globally been identified as a cornerstone for economic growth and sustainable development. As one of the mega-biologically diverse countries, this has posed a challenge to the country to establish mechanisms through which its biodiversity can be protected, restored and sustainably used to contribute towards addressing the vicious circle of the three economic ills facing the country i.e. unemployment, poverty and inequality. Conservation receives attention through the system of protected areas and South Africa has identified that for conservation to support biodiversity, conservation and to thrive, there is a need to develop the biodiversity economy.

The biodiversity economy advances the CBD objectives of conservation, sustainable use, and access, fair and equitable sharing of benefits to biological resources to meet legislative requirements in terms of the National Environmental Management: Biodiversity Act. The Department of Environment, Forestry and Fisheries (DEFF) has adopted a transformative agenda which seeks to achieve an inclusive biodiversity economy sector that will immensely contribute to the economy of the country whilst advancing the protection of biodiversity. This economic transformation will allow for opening the sector through the participation of previously disadvantaged individuals, especially women, in these sectors.

The biodiversity economy is therefore anchored on increasing the share of the green economy by enhancing the contribution of the biodiversity economy to the Gross Domestic Product (GDP). The economic activities identified include eco-tourism, wildlife ranching and bioprospecting and are value-adding to the protected area network and broadly the conservation estate which also include protected environments, biodiversity and management areas of national, provincial, local, private and community owned which is representative of South Africa’s mega-diverse ecosystem.

Considering the dire effects of climate change, the biodiversity economy will enhance better utilisation of the available land by reducing bush encroachment, development of non-consumptive products (tourism, wildlife viewing) and consumptive products and services (bioprospecting, hunting and meat) and therefore provides more job opportunities. Wildlife could be combined with tourism and could create much needed job opportunities in the deep rural areas thereby preventing people from moving to urban areas. BIOFIN is therefore one of the tools for South Africa to grow its biodiversity economy to meet its developmental goals and targets as per the National Development Plan in an environmentally sustainable manner whilst fulfilling global commitments in line with the Sustainable Development Goals, global conventions and protocols on biodiversity and the Aichi Targets.

The strategic focus of BIOFIN Phase 2 will therefore be on enabling mechanisms for the biodiversity economy. The Biodiversity Economy therefore forms the core of Phase 2 implementation of BIOFIN around which other financial solutions are linked.

## Approach

### South Africa’s National Biodiversity Economy Strategy

Implementation of BIOFIN Phase 2 in South Africa is being designed to support and complement the National Biodiversity Economy Strategy (NBES). The NBES serves as a suitable strategic tool to achieve the anticipated sustainable advancement for the wildlife and bioprospecting/bio trade sectors of South Africa. It has also demonstrated the importance of the biodiversity sector to the economy of the country, achieving sustainable livelihoods specifically for especially women and youth in rural communities. Through the fast results methodology referred to as Operation Phakisa, a set of 20 complementary initiatives with six recommendations have been identified and detailed plans have been developed for activities to be implemented. The initiatives aim to accelerate rural development, improve social well-being, and ensure equitable access and benefit sharing from biological resource, while maintaining the ecological resource base.

There is a high level political commitment that has been demonstrated for the biodiversity economy which is supported by the relevant political structures. The Delivery Unit in DEFF facilitates implementation of the initiatives with oversight by the Department of Planning, Monitoring and Evaluation (DPME) and reports through national, provincial and intergovernmental mechanisms. Most biodiversity economy activities take place in and around protected areas, expansion areas and stewardship sites and the biodiversity economy nodes have been identified within expansion areas of protected areas and stewardship sites. It is therefore the intention of South Africa as part of BIOFIN Phase 2 to implement those solutions that will unlock the Biodiversity Economy, especially targeting women’s participation in the identified areas and associated activities. The implementation of the financial solution will generate new money through impact investments in the Biodiversity Economy in:

- Promoting access and benefit sharing to biological and genetic resources

- Infrastructure and services investments for protection of biodiversity in eco-tourism

- Sustainable use in beneficiation which involves:

- Wildlife - Donation of game, game farming, meat production; and,

- Bioprospecting - Cultivation and donation saplings for bioprospecting, manufacturing and sale of bio-products.

These biodiversity economy activities will be supported by the following actions:

- Identifying and setting up funding and financial mechanisms and tools to protect biodiversity whilst growing the economy;

- Management agreement on land/ assets and further investments in expansion of protected areas;

- Reinvesting all proceeds from the biodiversity economy in biodiversity protection;

- Identification of beneficiary communities and entrepreneurs with a focus on women business owners;

- Skills development in biodiversity conservation, restoration and business development;

- Business development in structuring of legal entity and articles of incorporation to operate the businesses;

- Support the issuing of permits such as hunting licenses, permits for translocation during game donation, bioprospecting permits, threatened and protected species; and

- Enforcement and compliance of permit conditions and application of appropriate fines and penalties.

The BIOFIN finance solutions to be implemented as part of Phase II will therefore relate to:

- Those related to cost savings for the overburdened state which will lead to better spending of existing resources.

- Those related to new revenue streams for the biodiversity management and

- Those related to avoiding future costs through the use of financial instruments.

Table 2 below indicates the prioritised financial solutions for Phase 2 implementation in line with desired outcomes. These finance solutions are inter-related and inter-linked and will be implemented in a manner to realize greater economies of scale and benefits whilst where possible, cost saving on implementation. In this case where implementation of a finance solutions is likely to realize positive outcomes for the other, terms of reference will be designed such that there may only be a need for one study instead of two where possible.

Table 2.  Prioritised Finance Solutions for Phase 2 in line with desired outcomes

| Desired outcomes |  |  |
| --- | --- | --- |
| Realising savings on expenditure on biodiversity based on BER assessment as baseline | Generate new financial resources or innovative funding sources | Avoid future costs on biodiversity through use of financial instruments |
| Finance Solutions |  |  |
| - Growing protected area own revenue | - Wildlife certification - Impact investment platform | - Permits and licences |
| - Reform property rates |  | - Biodiversity offsets |
|  |  | - Tax incentives |
| - Enabling mechanisms for stewardship |  |  |

The implementation of the Finance Solutions will be complementary to the overall Biodiversity Economy as illustrated in Figure 2 below:

Figure 2: Linking finance solutions to the biodiversity economy

Figure 2 above demonstrates that impact investments in the biodiversity economy will generate new money through investment in the nodes which are mostly in expansion areas and stewardship sites in and around protected areas. Through the realignment of property rates, more appropriate property rates will be charged for PAs. Further to this, landowners will receive a tax incentive for keeping their land for biodiversity, whilst land identified for expansion and stewardship will attract investment in biodiversity economy activities.

In Phase II, BIOFIN South Africa will therefore implement innovative financial solutions beyond increasing public budget, such as public expenditure alignment, deliver better through efficient expenditure, and avoid future costs due to negative impacts on biodiversity.

In the protected area pillar, the focus will be on growing protected area revenue whilst reducing fixed costs such property rates and variable costs like operational costs of managing protected areas. Further to this considering the National Protected Area Expansion Strategy, innovative funding mechanisms will be explored in various models of stewardship.

In the ecosystem restoration pillar, various initiatives are already underway in restoration and rehabilitation of ecosystems and to support biodiversity. The Finance solution in this category is on the implementation of a biodiversity offsets which will explore mechanisms for biodiversity banking to enable offsets.

In respect of sustainable utilisation, it is the intention to unlock the biodiversity economy in the area of wildlife and bioprospecting specifically for women. This includes implementing mechanism to attract investments in the wildlife products and increasing ranching and cultivation opportunities within identified land in and around protected areas. Secondary industries will be developed, and small business and market opportunities will be opened. This will be supported by a harmonised permitting and licensing system and a robust compliance and enforcement mechanism. These activities can generate finance for other related biodiversity actions.

This implementation will be supported through several parallel programmes and activities that will ensure an integrated approach to BIOFIN implementation.

In light of recommendations from the PIR, BER and FNA, the following prioritised activities will be undertaken to support institutionalisation of BIOFIN Phase II.

Table 3: Prioritised activities to institutionalise BIOFIN

| Action Plan and Budget |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome/s (Result/s): BIOFIN is a convening platform for institutionalizing resource mobilisation for biodiversity |  |  |  |  |  | Timeframe |  |  |
| Output/s | Activities | Responsible actor/s | Funding source | Total Costs (USD) | Atlas. Budg. Code (For approved projects) | 2020 | 2021 | 2022 |
| Baseline: Biodiversity is a concurrent function between national, provinces and local government Indicators: Mainstreaming of biodiversity finance in related sectors Targets: By 2022, BIOFIN will be institutionalised within government and all related institutions | Quantify unfunded mandates and identify funding sources | DEFF/NT | BIOFIN | 20000 |  | X | X |  |
|  | Enhance and strengthen mechanisms and capacity for Improved Reporting on Biodiversity Financial Flows | DEFF/NT | BIOFIN | 20000 |  |  | X | X |
|  | Identify donor funding sources and tag for biodiversity | DEFF | BIOFIN | 10000 |  | X | X | X |
|  | Develop a biodiversity funding tagging system integrated into existing budgeting and accounting system | DEFF/NT | BIOFIN | 31275 |  | X | X | X |
| TOTAL |  |  |  | 81275 |  |  |  |  |

The next section provides a summary of each Finance Solution together with desired outcomes and outputs. The Finance Solution proposal for each solution is attached in Annexure 2 with more updated information from the BFP.

## Protected areas

### Growing own revenue in protected areas

Own or commercial revenue from sources such as gate fees, tourism concessions, conferencing facilities and wildlife sales can play an important role in supporting the financial sustainability of protected areas. Success in generating own revenue is, however, highly variable among the different conservation authorities in South Africa.

Across conservation authorities, only South African National Parks can generate in excess of 51% of own revenue. Of the provincial conservation agencies, the North West Tourism Board generated own review making up 37% of total revenue for the period under review, followed by Ezemvelo KZN Wildlife (EKZNW) with 29%. The remaining conservation agencies all generated own revenue was under 13% of total revenue according to the BER. The lack of other agencies’ ability to collect substantial site-based revenue is a concern in terms of managing the risk of future budget cuts in allocations.

This solution will focus on growing own revenue for the various provincial management authorities. The aim of this solution is to increase the rate of own revenue growth for protected areas, a particularly important imperative given significant government budget constraints. The solution builds on the ‘Making a case for protected areas in the Northern Cape’ that was undertaken as part of Phase I.

The financial solution entails gathering key data, undertaking assessments of key income streams, identifying enabling institutional arrangements and responsive management strategies and improving business models for conservation authorities, including partnerships with the private sector. The completion of this finance solution will also build on a study undertaken by National Treasury on Performance and Expenditure Review for provincial nature reserves and another study by DEFF on sustainable financing for protected areas.

| Outcome | Improved management of protected areas due to increase in revenue generation. |  |  |  |
| --- | --- | --- | --- | --- |
| Outputs | Increased revenue generation in state-run protected areas. |  |  |  |
| Primary Indicator | Four percent (above inflation) increase in revenue generation of provincial protected area management authorities by 2022. |  |  |  |
| Indicator | Baseline | Target | Stakeholders | Roadmap |
| Percentage increase in the amount of revenue generated and retained in each (four) provincial protected area management authority | In 2016, conservation management authorities generated R 452 million in own revenue. | By 2022, there will be 4% (above inflation) growth in revenue generated and retained through associated activities in selected provincial Management Authorities. | Provincial management authorities) CEO Forum Researchers and consultants as and when required. | Identify revenue generating opportunities in PAs. Facilitate the implementation of a mix of viable opportunities. Where possible, implement public private partnerships. |
| Sustainable financial strategies developed | No existing strategies for MAs | Strategies developed and implemented. |  |  |

### Property rates tax reform

Municipalities charge different rates for protected areas due to interpretation of the Property Rates Act which leads to financial pressure on management authorities. Certain protected areas face the challenge of being charged substantial property rates and this is putting undue financial pressure on providers of important public goods. As of May 2016, SANParks was facing demands from various local municipalities for rates arrears totalling approximately R212 million. In addition, they estimate that future demands would be in excess of R80 million/yr.

This solution therefore aims to ensure that the application of rates policies by municipalities better reflects the spirit or intention of the Act with respect to the concessions it offers protected areas and botanical gardens. In this regard, DEFF will engage with the Department of Cooperative Governance and Traditional Affairs (CoGTA) and National Treasury which are responsible for the Municipal Property Rates Act, in developing a policy practice/ interpretation note to guide the rating protected areas preferably in the national rates framework published under the Act. For this financial solution, there is a need to provide guidance on the interpretation of Section 17 used in order to allow for the contribution of intangible value of land set aside for biodiversity and conservation. This will provide guidance to municipalities in the review of their rates policy and its application.

| Outcome | A reduced financial burden on protected areas due to a reduction in property rates |  |  |  |
| --- | --- | --- | --- | --- |
| Outputs | Application of the correct interpretation of section 17 (e) and (g) of the Municipal Property Rates Act in relation to protected areas by 2022. |  |  |  |
| Primary indicator | 50% reduction in property rates in protected areas, for all relevant PAs. |  |  |  |
| Indicator | Baseline | Target | Stakeholders | Roadmap |
| Percentage reduction in property rates charged on protected areas, for all relevant PAs* | R240 million per annum spent on property rates by SANParks and 10 management authorities. | 50% reduction in property rates | DEFF Management authorities COGTA National Treasury | Assess Sect 17 of MPRA Propose a guideline document on application Work with municipalities on application in the municipal property rates policies. |
| Development of a national framework | No framework | Framework developed and applied by all Municipalities |  |  |

*Since the application of the Municipal Property Rates Act is being applied differently around the country, some PAs are not currently being charged property rates.

### Building a grant mechanism to adequately finance the biodiversity stewardship programmes

Biodiversity stewardship programmes provide a highly cost-effective mechanism for expanding and managing protected areas. Stewardship can secure government investments in natural resource management on non-state land and can be used as a mechanism to enable sustainable use of biodiversity. It has been clearly demonstrated that the state benefits from substantial cost savings when establishing and managing protected areas through biodiversity stewardship programmes, in comparison to the alternative model where the state purchase and management of the land (SANBI, 2015). Despite the financial and practical arguments for investing in the biodiversity stewardship programmes, these government-led programmes remain substantially under-resourced within all conservation authorities, and the benefits of these innovative programmes are not being fully realized by the state. This solution is focused on enhancing, consolidating and adequately financing the biodiversity stewardship programs, so that the full benefit of the biodiversity stewardship programmes can be felt, contributing to protected area expansion targets, ecosystem restoration, and sustainable use of biodiversity across the country. The activities include enhancing the value proposition for stewardship and setting up an enabling mechanism for tagging biodiversity related grants administered by other departments such as Land Care, Disaster Management Fund or Water Tariff. As the financing of biodiversity stewardship programmes can come from several different sources, this finance solution, in practical terms, will rely on other finance solutions, as well as other programmes of work, in order to be fully realized. It will also play a facilitating role increasing the likelihood that other finance solutions, such as revolving land trusts, will emerge.

| Outcome | Stewardship sites are adequately and appropriately funded through a grant mechanism from national government. |  |  |  |
| --- | --- | --- | --- | --- |
| Outputs | Budget from the fiscus and other sources tagged to fund stewardship programmes. |  |  |  |
| Primary indicator | R80 million (USD6 million) per annum channeled directly from the state to provincial biodiversity stewardship programmes by 2022. |  |  |  |
| Indicator | Baseline | Target | Stakeholders | Roadmap |
| National funds routed directly to provinces for provincial biodiversity stewardship type programs for PA expansion, climate resilience, watershed management. | R0 | R80 million (USD6 million) p.a. grant program by 2022. | SANBI DEFF Management authorities | Identify biodiversity opportunities in stewardship sites Develop a mechanism to tag biodiversity related funds to set aside a portion for stewardship. |
| Provincial treasury allocations to provincial biodiversity stewardship programs | R22 million (2018/9) | R40 million (USD3 million) p.a. mobilized by 2022 |  |  |
| Existence of conditional grant type mechanism in environment sector | None exists | A grant framework structure is in place by 2022 |  |  |
| Number of stewardship sites using innovative funding sources for rehabilitation and management | Zero | Five sites (using water tariff, impact investment, or offset funds) |  |  |

### Institutional support for biodiversity tax incentives

The South African Government, through the National Treasury (NT), has provided fiscal incentives in the form of biodiversity tax incentives in an effort to fulfil national environmental policy to preserve the environment, through the Government led regime of entering into bilateral agreements with private and communal landowners to formally conserve and maintain a particular area of land. These bilateral agreements result in declared protected areas and are established through the national biodiversity stewardship initiative. These agreements result in environmental management expenses incurred by taxpayers as well as loss of economic rights and use. The biodiversity tax incentives present a mechanism to address the mitigation of management costs, address potential loss of production income as a result of land management restrictions, ensure the continued investment of landowners and communities in long term and effective land management, and ultimately assist in the sustainability of compatible commercial operations essential to the persistence of the area and the economy and livelihood growth required in South Africa.

The feasibility of the biodiversity tax incentives has been thoroughly tested through BirdLife South Africa’s Fiscal Benefits Project and shown to provide much needed expense relief as well as long term financial sustainability to privately and communally owned and managed protected areas. The implementation of this finance solution aims to introduce other biodiversity tax incentives into national legislation to further bolster this finance solution. It will also provide mechanisms to build capacity among landowners and communities as well as tax and financial professionals in applying for incentives. Building on the work completed in Phase 1, it is the intention to upscale and mainstream this finance solution and enhance communication systems to produce continuous improvement in the biodiversity tax benefit package.

| Outcome | Reduced financial burden on private and communal protected areas due to improved income tax incentives |  |  |  |
| --- | --- | --- | --- | --- |
| Outputs | Legislative amendment of Section 37 of the Income Tax Act (ITA) |  |  |  |
| Primary indicator | Amendment of Section 37C of the ITA |  |  |  |
| Indicator | Baseline | Target | Stakeholders | Roadmap |
| Amendment of Section 37C of the ITA | Defunct incentive and no financial mobilization for non-state protected area management. Preliminary work conducted by the Fiscal Benefits Project. No Amendment. | By 2022, the ITA will be amended to create a new effective biodiversity tax incentive. | DEFF Wilderness Foundation National Treasury SARS | Engagement with NT Development of tax training materials Amendment to legislation Lobby SARS In implementation |
| Testing of new tax incentive at pilot sites (If target for 2021 successful) | (Amendment secured) No actual or empirical testing of the proposed new biodiversity tax incentive. | By 2022, a minimum of 7 pilot sites are selected to test the new tax incentive. This includes assisting in securing an additional 50 000 ha of protected area. |  |  |
| Appropriating the new tax incentive for management costs in a landowner’s tax return | (Amendment secured) No financial benefit for the management costs incurred on non-state protected areas. | By the end of 2022, a minimum of one tax return is completed for a pilot site to appropriate the new tax incentive and receive the deduction for costs incurred to affect the required management plan. |  |  |

### Improved biodiversity offsets modality for protected area expansion

This finance solution draws on the finalisation of the National Biodiversity Offsets Policy and associated biodiversity offsetting guidelines and aims to design and pilot effective implementation modalities for biodiversity offsets across the country. Biodiversity offsetting is the final option in the mitigation hierarchy but remains one of the least utilised mitigation options for various reasons. The efficient and effective implementation of the Biodiversity Offset Policy should counterbalance biodiversity loss in unprotected landscapes through increased formal protection and management of biodiversity.  Certain types of development (such as renewable energy, and large or cross-province infrastructure) require intricate regulatory and financing approvals – which can be jeopardised if biodiversity impact mitigation measures are not adequately managed. By using a combination of biodiversity offset banking approaches (possibly funded by NGOs and impact investment) and requiring reinvestment of returns in PA expansion and management costs, a pro-active ready-made offset mechanism is provided. This will provide mitigation measure assurance for regulators and financiers.

| Outcome | A net gain in biodiversity protection through an improved modality for implementing biodiversity offsets |  |  |  |
| --- | --- | --- | --- | --- |
| Outputs | An increase in PAs established through biodiversity offset decisions, based on the application of the mitigation hierarchy |  |  |  |
| Primary indicator | An offset bank is in place by 2022 |  |  |  |
| Indicator | Baseline | Target | Stakeholders | Roadmap |
| An offset bank in place where DEFF authorized development is likely to occur | No bank | An offset bank type system in place around 3 protected areas, totaling 50 000 ha by 2022 | DEFF SANBI National Treasury NGOs | DEFF, SANParks will identify candidate projects that can generate offsets through the environmental authorisation process An offset register will be set up and marketed to developers An offset bank will be set up Developers will deposit funds into the offset bank which can then be used for PA expansion |
| Annual funding flow to offset bank | Zero | R15 million per annum flows to offset bank management authorities |  |  |
| Protocol for facilitating development through proactive offsets | None exists | A protocol is in place by 2021 |  |  |
| Offsets register developed and maintained in DEFF for monitoring offset bank performance and verifying compliance with Environmental Authorisations | A preliminary register last updated in 2016 by SANBI. | An up to date (i.e. 30 days lag time from issuance of Environmental Authorisations) offset register exists as part of the IEM tracking systems for development authorisations, in place by 2022. |  |  |

## Sustainable utilization

### Implementation of a voluntary market-based certification in the wildlife sector

Presently, the area of land under private wildlife ranches in South Africa is approximately 17 million hectares, representing a minimum of 14% of the total land area of the country. The wildlife sector has been growing consistently faster than the general economy, contributing R3 billion to GDP in 2014 – almost double the contribution made by the sector in 2008.

The wildlife ranching sector operates along a continuum of management practices, ranging from extensive to intensive. At one end, extensive game ranches are managed to a great extent as protected areas, including ensuring appropriate species population densities, supporting well-balanced community structures and maintaining ecosystem functioning. At the other end of the spectrum, intensive game ranches confine specimens of wild species to small- or medium-sized enclosures, control natural predators, and provide food, water and veterinary support to animals.

While the level of contribution to biodiversity conservation has yet to be adequately quantified, it is likely that these areas contribute significantly, particularly where ranches are extensive in nature. If managed to environmentally sustainable best practices, extensive ranches have the potential to contribute to conservation outcomes such as the Aichi Target 11 through the Convention on Biological Diversity’s (CBD) definition on other effective area-based conservation measures (OECM). A significant number of game ranches could have their contributions to biodiversity conservation recognized under Aichi target 7 along with areas under agriculture, aquaculture and forestry are managed sustainably, ensuring conservation of biodiversity.

Building on the certification feasibility study completed in BIOFIN Phase 1, the implementation of a scheme would encourage sustainable conservation, hunting and may also encourage conglomeration of small farms into joint businesses. Additional benefits of such a scheme could also be significant, including helping to develop better knowledge and management of the industry, and better knowledge of its impacts on biodiversity, as well as having a positive impact on ecosystem health and the supply of ecosystem services and benefits to broader society. A certification scheme would also encourage transformation of the wildlife industry by ensuring that emerging wildlife ranchers are supported and enabled to operative thriving enterprises in this sector.

| Outcome | Area under management of the wildlife ranching industry contributes to conservation outcomes and protected area targets |  |  |  |
| --- | --- | --- | --- | --- |
| Outputs | A certification system for the game ranch industry is developed and implemented which verifies best environmental management practices |  |  |  |
| Primary indicator | Percentage of potential conservation area under game ranch management certified. |  |  |  |
| Indicator | Baseline | Target | Stakeholders | Roadmap |
| Percentage of potential conservation area under game ranch management certified. | 0 % potential conservation area under game ranch management certified. | 1-5% (200 000 – 1 million ha) of privately-owned game ranches certified. | DEFF; Wildlife Ranching South Africa (WRSA); Wildlife Forum; | Undertake baseline studies to understand scope and scale of the ranching industry; Develop certification concept in conjunction with private and public sectors; test mechanism with selected game ranches; Develop a wildlife ranching certification brand. |
| Percentage of potential conservation area (assessed Other Effective Area-Based Conservation) under game ranch management certified. | 0 % potential conservation area under game ranch management certified. | 0,5% (100 000 ha) of privately-owned certified game ranches assessed as OECMs | DEFF Wildlife Ranching South Africa (WRSA) Wildlife Forum |  |
| Number of female owned game ranches supported to become certified | 0 | 10 | DEFF Wildlife Ranching South Africa (WRSA) Wildlife Forum |  |

### Development and promotion of an online economy investment portal

South Africa has developed a Biodiversity Economy Strategy (BES) that serves as a guide for the sustainable growth of the wildlife economy, ecotourism and bioprospecting sectors. The BES provides a basis for addressing constraints for growth, ensuring sustainability, identifying clear stakeholder responsibilities, and monitoring progress of the enabling actions identified in the strategy.

Facilitating financing of and investment into Biodiversity Economy enterprises is an essential part of creating an enabling environment for the sustainable growth of the sector. The Department of Environment, Fisheries and Forestry (DEFF) has developed an investment portal for the Biodiversity Economy called www.thegamechanger.co.za. Investment sites and initiatives are profiled on this platform. A review of the platform has been undertaken and a substantial revision of this portal is recommended to significantly enhance its effectiveness.

The envisaged Biodiversity Economy investment portal which will be redeveloped under BIOFIN phase 2 seeks to link partners and sources of finance (such as individual investors, impact investors, foundations, endowments, fund managers, international cooperating partners, grant making agencies, private and institutional bankers and development finance institutions) with investees that have undergone a rigorous due diligence and project preparation process. This is to ensure that the investment and/or partnership objectives are clearly defined, in order to establish a basis for further engagements between an investee and investor.

The focus of this finance solution is to facilitate the profiling of a key sub-set of enterprises and projects on this revised investment platform that are linked to Biodiversity Stewardship sites and Conservation Areas - also referred to as Other Effective Area-Based Conservation Measures (OECMs). Such sites contribute to South Africa’s Conservation Areas Convention on Biological Diversity (CBD) Aichi Target 11 and have proved to be very cost-effective ways of contributing to the National Protected Areas Expansion Strategy.

| Outcome | Development and promotion of an online investment portal with the aim of facilitating financing of and investment into Biodiversity Economy enterprises |  |  |  |
| --- | --- | --- | --- | --- |
| Outputs | Through the investment portal, investors are able to invest in additional 50 000 ha of biodiversity stewardship sites which contribute to the conservation estate by 2022 |  |  |  |
| Primary indicator | Area (ha) of biodiversity stewardship sites are added to the conservation estate by 2022 |  |  |  |
| Indicator | Baseline | Target | Stakeholders | Roadmap |
| Number of hectares of stewardship area added | 450 000 ha secured under Biodiversity Stewardship agreements | 50 000 ha of additional stewardship sites added to the conservation estate by 2022 | DEFF; SANBI; Private sector | Identify potential investees/land reform beneficiaries; concept development of platform; development of business cases for investees; develop an investor engagement strategy. |
| Number of Biodiversity Stewardship Sites that have a developed Investment Prospectus | 0 | 10 | DEFF; SANBI; Private sector |  |

### Improving the effectiveness of permits

DEFF and Management Authorities administer several different permits in line with the National Environmental Management: Biodiversity Act (NEMBA) legislation in relation to Threatened and protected species (TOPS), Bioprospecting Access and Benefit Sharing (BABS), Convention on International Trade of Endangered Species (CITES), Alien Invasive Species (AIS) regulations. One of the limitations in relation to implementation is standards in permit fee applications and lack of a mechanism to review these fees and capacity at various levels in DEFF and Regulatory Authorities.

Over the years, attempts have been made to harmonize the permit process and to ensure minimum administration and capacity in application. Key issues include the fact that the current permit fees are not aligned with the economics of restricted activities and are not reflective of the cost of processing the application and are therefore considered to be too low. Management authorities that are required to process the applications do not have the required supporting expertise (i.e. social scientist, economist and legal experts) to undertake a comprehensive assessment and to objectively determine the most appropriate increase in fees. Legal limitations include the fact that currently the permit fee is published in the Regulations rather than a separate gazette, making review and amendments to fees an unnecessarily time-consuming process. The aim of this finance solution would be therefore to attempt to understand the feasibility of how fees charged for permits can be cost reflective from a social, environmental and economic perspective.

- Management Arrangements

  - BIOFIN Core Team

BIOFIN will be implemented in partnership between UNDP Country Office (CO) and DEFF. The Country Implementation Strategy together with the Annual Work Plan will outline the description and schedule of activities together with measurable indicators.

The Letter of Agreement/ Memorandum of Agreement to be signed between the two parties will govern the relationship between UNDP CO and DEFF in the implementation.

The BIOFIN Team will be made up of two core team members who will be placed within DEFF and the UNDP CO respectively. The terms of reference (TOR) for the team are attached in Annexure 3. The overall role of the BIOFIN team includes:

- Technical leadership, strategic engagement and coordination in implementation;

- Monitoring and Evaluation;

- Programme management and advocacy

- Secretariat services to the institutional structures that support BIOFIN; and

- Communication and awareness on BIOFIN.

The team will be made of: -

- National Project Manager appointed in DEFF (100% time)

- Programme Management Specialist  appointed by UNDP (100% time)

Support consultants in areas of technical expertise, communication, training and capacity building services will be procured as and when required. There are various processes and institutional mechanism that will support BIOFIN Phase II implementation and these are outlined in the section that follow.

## High Level Political Commitment

Issues of biodiversity receive high level political commitment in South Africa as demonstrated during the Presidential launch of the Biodiversity Economy 26th August 2018 where the then Minister of Environmental Affairs as the host to the President of the Country, was supported by:

- Minister of Land Reform and Rural Development

- Minister of Tourism

- Minister of Small Business Development

- The Premier of Limpopo Province

- The Member of the Executive Council responsible for Economic Development, Environment and Tourism in Limpopo Province

- The Member of the Executive Council responsible for Environment, Agriculture and Rural Development in North West Province

- The Executive Mayor of Vhembe District Municipality

- Traditional leaders of Vha-Vhenda

Further to this, the team will be supported by various institutional mechanisms for smooth operation which are complementary and mutually re-enforcing. The following Institutional Mechanisms as per the approved Governance Framework will support implementation.

## BIOFIN Governance Mechanism

The following Institutional Mechanisms have been identified to support implementation:-

- Project Steering Committee (PSC)

- Programme Management Team (PMT)

- Project Task Teams for implementation (PTT)

These Institutional Mechanisms will be supported by a Secretariat (BIOFIN team) which will be responsible for:-

- Technical leadership in BIOFIN

- Coordinating arrangements for meetings with respective Committee members and provide Secretariat Services

- Preparing the agendas for all meetings

- Maintaining contact with members to ensure that the process is meeting expectations

- Ensuring that summaries of meetings are kept, approved by members and distributed on time

- Working with the members to identify priorities and indicate a focus and timeline for each issue proposed for discussion.

## Project Steering Committee (PSC)

The objective of the steering committee is to guide and support the implementation of BIOFIN to:

  - Approve project annual work plan and major project deliverables, as well as other project planning and implementation instruments.

  - Review and monitor project progress  in order to ensure that the project remains on course to deliver products of the required quality to meet the outcomes defined in the project

  - Consider and adopt Quarterly reports and progress reports on implementation of the prioritized finance solution.

The PSC will be made up of the following:

- UNDP Country Office;

- DEFF DDG Biodiversity or alternate;

- SANBI;

- SANParks;

- Isimangaliso World Heritage Site Authority

- National Treasury;

- Department of Cooperative Governance and Traditional Affairs; and

- Department of Planning, Monitoring and Evaluation.

- Representative from the Private Sector

- Representative from non-governmental and / or community based organisation

## BIOFIN Project Management Team

The Project Management Team will guide the Instutionalisation and alignment in the implementation of the finance solutions.

The objective of the PMT to guide and support institutionalisation of BIOFIN in South Africa through the:

  - Development of the project annual work plan and major project deliverables, as well as other project planning and implementation instruments

  - Identification areas of alignment and institutionalisation

  - Ensuring that the project remains on course to deliver products of the required quality to meet the outcomes defined in the project;

  - Supporting the service providers in securing stakeholder involvement on matters of biodiversity expenditure, costing, and resource mobilisation, and any other biodiversity and finance related matters emerging from the consultation process;

  - Identifying and supporting project evaluations should the need arise; and

The PMT will be made up of

- National Treasury

- United Nations Development Programme country office

- BIOFIN Finance Solution Task Team Leader

## BIOFIN Project Task Team/s (PTT)

Project Task Teams will be set up to support each individual finance solution. The Project Task Teams will be responsible for:

- Developing project implementation plans with project deliverables;

- Developing/endorsing terms of reference for sourcing of professional services;

- Supporting the service providers in securing stakeholder involvement on matters of biodiversity expenditure, costing, and resource mobilisation, and any other biodiversity and finance related matters emerging from the consultation process;

- Consulting with subject experts to advice on implementation as and when necessary; and

- Reporting on project implementation.

The composition of each PTT will be comprised of the BIOFIN Core Team and the responsible parties for each of the financial solution.

# Institutionalization

Government planning is guided by the National Development Plan 2030, which outlines a growth and development trajectory of South Africa by 2030. The National Development Plan 2030 outlines fourteen (14) outcomes which are aligned to the seventeen (10) Sustainable Development Goals (SDGs). Outcome 10 of the NDP envisions a ‘transition to an environmentally sustainable, climate-change resilient, low-carbon economy and just society’. The NDP advances ecosystem protection as one of its principle which acknowledges that human well-being is dependent on the health of the planet. Whilst NDP places emphasis on growth and development, it however that affirms that South Africa “needs to protect the natural environment in all respects, leaving subsequent generations with an endowment of at least equal value”. It therefore recognizes the need to mainstream and integrate biodiversity consideration in planning and decision-making.

The Policy and Review

Part of institutionalisation will be:-

- Work with the Northern Cape provincial government to further enhance the socio-economic and environmental potential of protected areas using the Ecosystem Evaluation methods. The Tourism Agency and Development Agency have expressed interest in integrating outcomes of ‘making a case’ in the overall tourism strategy of the province

- Work with the wildlife sector on the development of certification scheme and establish and institution (using existing mechanism) to set up the certification scheme

- Improve financial governance of biodiversity working with National Treasury to establish a ‘10 by 10’ budget committee where DEFF with other national departments and provinces discuss budget and expenditure on biodiversity.

- Enhance skills and understanding of biodiversity finance in the public sector to improve financial governance and better regulation of industry. This forms part of the awareness, training and capacity building.

Planning and Implementation of BIOFIN will be supported and guided by existing internal and environment sector institutional processes and mechanisms. This includes mainstreaming BIOIFN into government-wide medium-term strategic planning and annual planning cycle. These processes are coordinated through the Presidency, Department of Planning, Monitoring and Evaluation (DPME) and the respective Offices of the Premier in the nine provinces and include local government through SALGA. Phase 2 of BIOFIN (2018-2022) fits into the 2nd cycle of MTSF which is 2019-2024 and related Annual Performance Plans of the Environmental sector. Monitoring and reporting is undertaken on a quarterly basis, whilst evaluation is demand driven at intervals. Monitoring reports are considered by Cabinet to track government wide performance.

There are existing consultative and decision-making governance mechanisms to support institutionalisation and implementation of BIOFIN. These include but are not limited to:

- Director General Economy Cluster which coordinates all economic related functional government departments;

- Working Group 1 where DEFF meets with protected area Management Authorities and provincial representatives;

- MINTECH - Ministers Technical Group where the Director General meets with Heads of Departments in provinces and Director Generals of relevant national departments such as Water and Sanitation, Agriculture, Forestry and Fisheries, Mineral Resources and Tourism and the South African Local Government Local Association (SALGA);

- MINMEC – Minister, other national Ministers, Members of the Provincial Executive Councils, the South African Local Government Association; and,

- CEO’s Forum - Forum of Chief Executive Officers of South African National Parks, provincial tourism and conservation agencies and heads of management authorities.

As part of implementation of each financial solution, relevant project managers will be responsible for implementation within the respective institution. Implementation will action such as improving biodiversity governance and implementing recommendations from each financial solution.

## Partnerships and other stakeholders

Outside of the public sector, the biodiversity sector in South Africa is diverse and driven by different interest groups from business, non-government organisations, professional organisations and community-based organisations. There are existing forums with each stakeholder interest group in biodiversity sector and where relevant, meetings are held on a quarterly basis to discuss areas of common interest including legal and regulatory developments, capacity development and implementation of BIOFIN solutions. The partners that will be engaged in implementation include:

- Protected area Management Authorities in relation to conservation and protected areas;

- Other relevant government departments responsible for Treasury, Water and Sanitation, Agriculture, Public Works and Defence;

- Relevant scientific authorities and academic institutions;

- Sector organisations and associations that are non-profit;

- Donor organisations and agencies; and

- Private sector.

## 5.2 Related initiatives

The DEFF and its entities SANParks, Isimingaliso and SANBI as well as provincial authorities have several initiatives that complement and align to BIOFIN implementation. From a global perspective, BIOFIN is integrated into South Africa’s country report for CBD as part of reporting on progressing on the NBSAP. BIOFIN supports the implementation of recommendations of the Sustainable financing framework for protected areas undertaken by the DEFF and the Protected Area Expenditure Review undertaken by National Treasury. Further to this, BIOFIN will complement work undertaken on natural capital accounting (NCA) and valuation of ecosystem services (VES) funded by the European Union and jointly work on utilising emerging data for national policy and fiscal processes. The NCA process is being undertaken by Statistics South Africa in collaboration with DEFF, SANBI, National Treasury and DPME.

### Sustainable financing framework for state managed protected areas

The aim of the study was to strengthen the business case for protected areas in sustainable development and identify sustainable financing instruments and strategies for protected areas within the public sector management authorities. Recommended strategies that link to BIOFIN include growing protected area own revenue, strengthening biodiversity stewardship programmes and implementing biodiversity economy activities such as eco-tourism, hunting and bioprospecting. Partnerships with communities and the private sector are also key to realising funding streams through co-management agreements, offsets and setting up financial mechanisms for protected areas.

### Protected Areas Expenditure Review

The review, undertaken by National Treasury, focused on the management arrangements of state managed protected areas and determining how protected areas are funded from the public purse, including expenditure and cost drivers in management.  The outcome of the study strengthens the value of gathering data in a systematic way and using the data available and data required for a comprehensive picture of expenditure and cost drivers for state managed protected areas. Data gathering was a challenge due to different codes of budget items applied.

### Natural Capital Accounting (NCA) and Valuation of Ecosystem Services (VES) Project – South Africa

The NCA&VES project was launched in 2017 by the United Nations Statistics Division (UNSD) and United Nations Environment (UNE). The NCA&VES project aims to assist five participating partner countries (South Africa, Brazil, China, India and Mexico) to advance the knowledge agenda on environmental and ecosystem accounting and initiate pilot testing of System of Environmental-Economic Accounting (SEEA) Experimental Ecosystem Accounting (EEA), with a view to improving the management of natural biotic resources, ecosystems and their services at the national level as well as mainstreaming biodiversity and ecosystems in national level policy, planning and implementation. The NCA&VES Project is one of several global projects over the past 10 years focusing on advancing the SEEA-EEA.

## Capacity Development

The PIR has identified specific capacity gaps specifically within the public sector in order to address policy drivers in biodiversity. Capacity development will therefore be prioritised in the public sector through focused capacity development initiatives initially with management authorities in the implementation of the finance solutions and also as part of institutionalisation. Through existing institutional mechanisms, such as Working Group 1 and the CEO’s forum which consists of related national departments and entities, management authorities and provincial authorities respectively, BIOFIN is an agenda item when appropriate, where progress is reported on an ongoing basis. Other intergovernmental workshops and conferences organised by DEFF and other partners are also used for capacity development. Further to this, focused capacity development initiatives will be integrated in the implementation of financial solutions.

## Scaling Financial Solutions

The seven finance solutions proposed in the Phase II implementation strategy are inter-related and integrated. There are initiatives internally and in the sector that aim to raise funding for biodiversity by using the public resources to deliver better. The implementation of some of the finance solutions such as tax incentives and property rates, may lead to policy or legislative changes or interpretations to effect resource mobilisation for biodiversity. Part of the implementation will link into partner specific initiatives where possible, such as Global Environment Facility (GEF) funded programmes. The financial return for each solution would where possible be quantified to demonstrate possible multiplier effect of the financial solution and economic returns.

## Sustainability / Exit plans

BIOFIN will be mainstreamed within the biodiversity sector as an enabling mechanism for resource mobilisation. In this regard, implementation is shared within partners and integrated with other existing programs. In the implementation of BIOFN, South Africa has opted for a shared implementation model between DEFF and UNDP. UNDP will ensure that BIOFIN is integrated into UN operational processes and systems for better oversight on governance of BIOFIN and ensuring that outputs align with global objectives. DEFF will ensure and promote BIOFIN policy integration and interface with management authorities and other stakeholders and will use established strengthened institutional mechanisms and processes to mainstream BIOFIN across government and the sector.

Finance solutions are aligned to the country’s strategic imperatives in terms of the National Development Plan and the NBSAP. In this regard, BIOFIN is an enabling mechanism to explore additional funding for biodiversity and enable the biodiversity economy as it relates to the conservation and sustainable management biodiversity.  The Project Manager operates within the DEFF and can interact and align BIOFIN with other processes and programmes broadly in the sector. For each finance solution, a relevant staff member in the department or relevant public entity acts as a Project Manager for the implementation of that finance solution in order to ensure policy alignment and integrate BIOFIN with existing and ongoing programmes. The implementation of financial solutions will therefore be sustained by permanent staff in DEFF and its entities (SANParks and SANBI), other national departments such as DWS, DAFF and their related entities, DPW and DEFENCE. Further to this, strengthened partnership mechanisms such as People and Parks which works directly with communities, the industry interest groups in wildlife, bioprospecting and with the business sector will ensure sustainability outside the government sector.

# Communication

BIOFIN is communicated through existing communication channels within the sector; partners; and governmental and non-governmental processes through formal and informal consultative mechanisms such as workshops and conferences. These mechanisms attract a range of stakeholder interest groups in the biodiversity sector. A comprehensive communication strategy will be developed as part of Phase 2 by the end of 2019 to practically demonstrate the benefits of biodiversity finance and implementing BIOFIN. Appropriate communication platforms will be identified, media products such as collateral material will be developed to support the communication and enhance advocacy. As part of awareness and advocacy, presentation slots will be secured in appropriate workshops, conferences and seminars where the work will be presented.

# Monitoring and Evaluation

The need for quantifiable indicators has been stressed for sustainability and relevance of BIOFIN. In this regard, a set of financial and biodiversity targets and measures will be developed and quantified throughout the implementation. BIOFIN is integrated in the strategic plan and annual performance plan of DEFF where high level indicators on biodiversity finance are included in order to facilitate NBSAP implementation. The entities and other departments implementing BIOFIN will be mandated to include indicators in their strategic plans. Quarterly and annual performance review take place at scheduled intervals in line with government wide performance management reporting. DEFF will engage with the Department of Planning, Monitoring and Evaluation to identify specific areas that will require evaluation. The BIOFIN Global M & E framework will be adapted to local conditions.

Reporting to the global BIOFIN team will be done on a bi-annual basis, and the BIOFIN Annual Work Plan will be reviewed twice a year in order to make adjustment to new and ongoing requirements, in consultation with the global BIOFIN team.

# Knowledge Management

Knowledge management will contribute to creating institutional memory at the national, regional and global level. By creating a repository of knowledge products such as reports, documents and memoranda, it will be possible to transfer knowledge in order to support scalability of lessons learnt, contribute to continuous improvement and support decision making and communication.

Existing knowledge platforms will be used such as Global and Regional Workshops, Regional Calls with counterparts on the continent, updating country information on the BIOFIN website and project reports such as quarterly reports, on the Annual Work plan, webinars and training materials and inception reports.

The DEFF has a learning and knowledge management exchange platform which provides a mechanism for sharing lessons on BIOFIN implementation. Mechanisms that exist within sector and partner institutions such as SANBI and SANParks will also be used. This also includes mechanism for the policy; science and practice interface, which allows for integration of the practical implementation of policy to provide feedback into policy and science and research through government, the scientific authorities and the research institutions.

# Annexure 1: Multiyear Work Plan

(Sent as a separate attachment)

# Annexure 2: Finance Solutions Proposals

BIOFIN Proposal Template

Design and Implementation of Finance Solutions -

Country: South Africa 				Submission date: …30/04/2019…..…….………….

Contact person: Kalie Naude			Email Address: knaude@environment.gov.za

SECTION 1 – FOR PROPOSED FINANCE SOLUTIONS

☐ Feasibility stage (If the solution is in the preparatory stage less details will be expected. Only the white sections in the table must be filled, the grey sections will be filled at the next stage).

☒ Full implementation stage (If the solution enters in the full implementation stage, more details are expected. The white and the grey sections must be filled with as many details as possible)

| Proposal Summary |  |
| --- | --- |
| Title of the Finance Solution | Growing protected area own revenue |
| Concise Description (abstract) | Own or commercial revenue from sources such as gate fees, tourism concessions, conferencing facilities and wildlife sales can play an important role in supporting the financial sustainability of protected areas. Success in generating own revenue is, however, highly variable among the different conservation authorities in South Africa. Across conservation authorities, only South African National Parks can generate in excess of 51% of own revenue. Of the provincial conservation agencies, the North West Tourism Board generated own review making up 37% of total revenue for the period under review, followed by Ezemvelo KZNWildlife (EKZNW) with 29%. The remaining conservation agencies own revenue was under 13% of total revenue for this period. The lack of other agencies’ ability to collect substantial site-based revenue is a concern in terms of managing the risk of future budget cuts in allocations. In the BIOFIN funded study on ‘making a case for protected areas in the Northern Cape’, based on ecosystem evaluation, protected areas have a potential to generate revenue. Institutional weaknesses and lack of integration limits the potential for revenue generation. Part of this solution will facilitate the implementation of the study in the Northern Cape. According to Protected Areas Management Effectiveness (PAME) annual report of 2017/18, EKZNW has experienced a major budget gap as a result of the budget cuts 3 years ago and the additional budget cuts of 5%, 6% and 7% over the Medium Term Expenditure Framework (MTEF). The entity is in a very difficult financial position. This will affect the conservation activities and tourism competitive position. A decreased tourism occupancy will affect provincial economic growth employment. The aim of this solution is to increase the rate of own revenue growth for protected management authorities which is particularly important given the significant government budget constraints. The solution entails gathering key data on own revenue stream activities, undertaking assessments of key income streams, identifying enabling institutional arrangements and responsive management strategies and improving business models for conservation authorities, including partnerships with the communities and the private sector. |
| Contribution to SDGs | Goal 8 Decent work and economic growth Goal 12 Responsible production and consumption Goal 13 Climate change Goal 14 Life below water Goal 15 Life on land resources, as internationally agreed Goal 17 Partnerships for the goals |
| Contribution to Aichi Targets / National Targets / Biodiversity Finance Plan | AICHI 11: Well-governed and effectively managed protected areas are a proven method for safeguarding both habitats and populations of species and for delivering important ecosystem services. NBSAP 1. Management of biodiversity assets and their contribution to the economy, rural development, job creation and social well-being is enhanced. |
| Implementing / Strategic partners (if other than UNDP) | Provincial conservation authorities and agencies: e.g. ECPTA, LEDET and DENC and EKZNW; and national institutions DEFF and SANParks. |
| Start and End Date | 2020-2022 |

Categorization

| Solution Category/ies from the BIOFIN Catalogue | Protected Areas/ Sustainable utilization |
| --- | --- |
| Relevant Finance Result(s) | Mobilizing resources Delivering Better |
| Estimated Finance Result | Based on assumptions of the 2015 revenue figures given in the BER, it is estimated that a 4% above inflation increase in revenue generation for the provincial management authorities would result in revenue of approximately R720 million by 2023. |
| Finance Source | Public |
| Sector | Government |
| Instrument Type | (Mixed) Regulatory and Economic |

Note: if Private sector please check due diligence requirements / guidelines at this LINK

| Budget (USD) |  |  |
| --- | --- | --- |
| Total resources required: | USD 290 000 |  |
| Total resources allocated: |  |  |
|  | BIOFIN | USD 180 000 |
|  | Donor (UNDP-GEF 5): | USD 60 000 |
|  | Government: DEFF | USD 50 000 |
|  | Government of South Africa In-kind |  |
|  | In-Kind | Staff time |
| Unfunded: |  | 0 |

| Main Proposal and approach |  |
| --- | --- |
| - Background | The Biodiversity Expenditure Review (BER) conducted by BIOFIN provides data on government funding allocations and own or commercial revenues generated for most of the conservation authorities. Data based on 2015 indicates that SANParks performed best, funding 52% of their expenditure through own revenue in 2015, followed by Northwest Parks (37% own revenue) and Ezemvelo KZN Wildlife (27% own revenue). The Northern Cape, Mpumalanga and Limpopo conservation authorities generated the lowest level of own revenues at 5% and 6% respectively. Average own revenues were approximately 20% of total income for the conservation authorities considered, if each management authority is given an equal weighting. It increases to 37% if a gross average is measured due to the dominance of SANParks. With respect to recent growth, between 2009 and 2015, SANParks and iSimangaliso were able to grow own revenues strongly at annual rates of 4% to 6% above inflation, own revenue for Cape Nature and the Eastern Cape Parks and Tourism Board approximately matched inflation while own revenues decreased by more than 10% per annum in real terms in Mpumalanga and Limpopo. One of the mechanisms used by National Treasury to allocate more public funds, is the ability to generate revenue. In the ‘making a case study for the Northern Cape’, there were low levels of publicity on, and utilisation of, protected areas, limiting revenue generating opportunities. The economic valuation of ecosystem services in this study estimated that the value of services from the protected areas in the Northern Cape was around R1, 2 billion per annum. This needs to be supported by annual investment in public funds of approximately R25m per annum. The study also found that the Northern Cape province has large potential for biodiversity offsets which can offset the cost to damage to the environment in the region. Data in the BER shows that success in generating own revenue, and its individual components or sources, is highly variable. SANParks is the conservation authority that continues to have the greatest success with commercial revenue generation. For other protected areas governed by other Management Authorities, there is a decline in revenue generated. The need for Management Authorities to increase own revenue generation is well recognised along with the understanding that each management authority faces sometimes very different circumstances. This solution will investigate additional activities that can be further developed and packaged for additional revenue sources to contribute to sustaining protected areas and supporting making a case for biodiversity. |
| - Objective(s) and Results expected: | - To improve the financial sustainability of the network of protected areas in provinces by optimizing and diversifying revenue streams and by improving cost efficiencies. - To support Protected Areas Management Authorities (PAMAs) in optimising the management of revenue and identifying new mechanisms for sourcing revenue in order to fulfil their conservation management objectives in a manner that ensures the social and economic benefits derived from PAs are fully realised. |
| - Business case (Approx 150 words) | - The urgency associated with having to show gains in own revenue generation by protected areas has been on the increase and is likely to intensify in the prevailing fiscal environment. - The need to demonstrate revenue generation to enhance motivation for increase in funding for protected areas. The experience gained in making a case for protected areas in the Northern Cape motivates for mechanisms to grow protected areas own revenue. - The experience of SANParks and select other conservation authorities demonstrates the potential to grow own revenues at rates that comfortably exceed inflation. - Tourism contributes roughly 3.1% to the national GDP and 4.5% of all jobs in the country. It continues to grow strongly, particularly in the nature-based tourism sub-sector which relies on protected areas as attractions. Conservation authorities such as Limpopo and Eastern Cape have the potential to grow their share of tourism within protected areas. |
| - Structure of the Finance Solution (100 words approx.) | This finance solution will be a mix of regulatory interventions that conservation authorities can implement to enhance revenue collection and development of a tourism product offering that can be developed for commercialisation. It will also include motivation for valuing ecosystem services that protected areas provide to motivate for more public expenditure allocation. Conservation authorities will be able to generate more revenue through improved regulatory governance and implementing of revenue raising activities. |
| - Description of Activities | Year 1: Set up task team and assess governance and infrastructure - BIOFIN will support DEFF to establish task teams in Provincial Management Authorities to facilitate the standardised information gathering and to act as forums to discuss and develop ideas. - BIOFN and GEF 5 will facilitate completion of financial scorecards using (FSC) indicators for the Management Authorities - BIOFIN and DEFF will unpacking of sustainable financing options for each Provincial Management Authorities. - DEFF with support of BIOFIN will establish the PA financing forum which will include all management authorities and regularly or through existing mechanisms as a peer-to-peer learning network to share lessons learnt. Year 1 & 2 Develop income streams and identify revenue sources - DEFF with support of will establish a broader forum which will include public and private sector on financing PA’s. - National Treasury supported by BIOFIN will develop and implement a consistent accounting and financial reporting framework for MAs that are better aligned with business principles and address the need to ring-fence financial reporting of MAs within provincial departments. - DEFF and MAs supported by BIOFIN will finalise the sustainable financing strategy for each management authority Year 3 Work on improving revenue generation and retention mechanisms - Management authorities will implementation of the actions and activities identified in the financial sustainable strategy. DEFF will monitor and evaluate of progress of the implementation of the sustainable financing strategy. - BIOFIN and DEFF will engage and work with Provincial and National Treasury on mechanisms for revenue retention. - BIOFIN and DEFF, working with National Treasury will develop strategies for revenue retention such as trading/cost recovery accounts as well as strategies for the retention of unspent allocated funds from the annual budget. |
| - Institutional Arrangements | - BIOFIN Project Team supports the coordination and implementation of the project - BIOFIN and National Treasury supports development of financial reporting frameworks and revenue retention mechanisms together with Provincial Treasuries - DEFF as the project owner, overseer and facilitator on the implementation of the project and beyond. - Provincial protected area Management Authorities as project custodians and implementers through their Task Teams. - Provincial Task Teams for each province to gather information and develop ideas on development of Sustainable financing strategy as the guiding tool and support implementation thereof. - Project Steering Committee to oversee and monitor the implementation of the project on the quarterly basis until the end of the project. and present in various intergovernmental forums such as PA-CEO Forum, UNDP-GEF, Working Group 1 |
| - Main risks and management response for solution implementation | - Significant capacity constraints in terms of protected area management capacity to implement own revenue options successfully. This will be mitigated by establishing a task team which meets regularly and provides feedback. - Ability to implement new and innovative options to diversify incomes. This will be mitigated by sharing lessons from other province with more tourism experience. Opportunities for public-private partnerships will be explored to support tourism development over the longer term. - Dwindling protected area budgets may create difficulties for undertaking new initiatives that require staff time and often capital investment. This will be mitigated by involving National and Provincial Treasury so that they can provide input and understand that sufficient PA budget will provide higher returns on investment if the PA system is geared up to generate revenue. - Lower than expected tourism growth due to external factors. This will be mitigated by encouraging tourism agency to build partnerships in marketing and publicity. |
| - Sustainability (100 words max) | The development of sustainable financing strategies for each of the four management authorities will provide a long-term framework on which to develop revenue generation activities which will provide a level of financial sustainability for management authorities into the foreseeable future. Additionally, the revenue generation activities will reduce reliance on government transfers. The establishment of the task teams and the Protected Area Financing Forum will provide a forum for peer to peer learning network and build capacity within the management authorities. |
| - M&E (100 words approx.) | The impact of this finance solution will be assessed by the increase in own revenue generated. Key performance indicators developed at the start of the project will be used for monitoring the implementation of the financial solution. Provincial and national treasury will provide support in financial governance and provide guidance on mechanisms for revenue retention. |

| Indicator | Baseline | Target |
| --- | --- | --- |
| Increase in revenue generated and retained by protected areas in four provinces | In 2016, provincial conservation management authorities generated R 452 million in own revenue. | 4% above inflation increase in own revenue for each MA by 2022. |
| Sustainable financial strategies developed | No existing strategies for MAs | Strategies developed and implemented |

SECTION 2 – FOR APPROVED FINANCE SOLUTIONS ONLY

Please provide the following information which will be included in next Work plan/Budget revision (or use actual Work plan document):

| Action Plan and Budget |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome/s (Result/s): Improved management of protected areas due to increase in revenue generation. |  |  |  |  |  | Timeframe |  |  |
| Output/s | Activities (example below) | Responsible actor/s | Funding source | Total Costs (USD) (detail by year in the AWP if FS approved) | Atlas. Budg. Code (For approved projects) | 2020 | 2021 | 2022 |
| Baseline: For 2016 Indicators: Increase in revenue Targets: By 2022, there will be 4% (above inflation) increase in revenue generated | Preparatory activities: |  |  |  |  |  |  |  |
|  | Convene task teams for each MA | DEFF | DEFF | 25 000 |  | X |  |  |
|  | Complete Financial Score Card (FSC) | DEFF/Provincial Management Authorities | BIOFIN GEF 5 | 60 000 |  | X |  |  |
|  | Implementation |  |  |  |  |  |  |  |
|  | Unpack and develop a suite of income generating activities and apply to each conservation management authorities. | BIOFIN | BIOFIN | 100 000 |  | X |  |  |
|  | Establish the PA financing forum which will include all MA’s | DEFF | DEFF | 25 000 |  |  | X |  |
|  | Implementation of the actions and activities identified in the financial sustainable strategy. | DEFF/BIOFIN | BIOFIN | 80 000 | Capacity training/ |  | X | X |
| TOTAL |  |  |  | 290 000 |  |  |  |  |

Annex 1: BIOFIN Prioritization Scoring and Screening Questions

| Questions | Indicative marks for scoring (1-5) | Score |
| --- | --- | --- |
| Is there a positive record of implementation? | 1= no, or limited records of success 3= successful pilots 5= yes, high potential of scalability | 5 |
| Will it generate, leverage, save, or realign a large volume of financial resources? | 1= minimal scale 2= <5 per cent of current expenditures / needs 3= 5-15 per cent of current expenditures / needs 4= >20 per cent of current expenditures / needs 5= game changer | 3 |
| Will financing sources be mobilized in a compatible timeline with needs? | 1 = no, the mobilization is not aligned with needs 3 = likelihood of being mobilized in alignment with needs 5 = yes, forthcoming and compatible schedules | 3 |
| Will financing sources be stable and predictable? | 1 = no, the source of revenue may be highly unstable and vulnerable to external factors 3 = likelihood of being reasonably stable and predictable source 5 = yes, very stable and predictable | 3 |
| Do the persons or entities paying have a willingness and ability to pay or invest? | 1 = no 3 = possibly 5 = yes | 3 |
| Are the financial risks adequately managed (e.g. exchange rate, lack of investors, etc.)? | 1 = no, high risks remain 3 = moderate risks 5 = yes, low residual risks | 3 |
| Are start-up costs onerous in comparison to the expected financial returns? | 1 = very costly (compared to returns) 3 = moderate (compared to returns) 5 = very low/minimal (compared to returns) | 3 |
| Does the solution improve incentives to manage biodiversity and ecosystems sustainably? (See Chapter 1). | 1 = not clear 3 = likely 5 = most certainly | 5 |
| Will the financial resources remain targeted to biodiversity over time? | 1 = not clear, high risk of misallocation 3 = likely, administrative provisions 5 = yes, strong legal provisions | 5 |
| Are risks to biodiversity (e.g. disrespect of mitigation hierarchy) low or easily mitigated? How challenging would it be to develop safeguards? | 1 = high risks, no easy mitigation 3 = reasonable risks, mitigation possible 5 = low risks, easy safeguards | 5 |
| Will there be a positive social and economic impact (e.g. jobs, poverty reduction and cultural)? | 1 = no 3 = moderate 5 = strong positive impact | 5 |
| Would there be a positive impact on gender equality, especially regarding participation in design and implementation or access to opportunities and benefits? | 1 = no 3 = moderate 5 = strong positive impact | 5 |
| Have risks of significant unintended negative social consequences been anticipated and managed? | 1 = no, high risks remain 3 = moderate and manageable 5 = yes, minimal residual risks | 5 |
| Will it be viewed as equitable and will there be fair access to the financial and biodiversity/ecosystem resources? | 1 = no, risk of inequitable outcome 3 = maybe 5 = yes | 5 |
| Is it backed by political will? | 1 = no, resistance from key stakeholders 3 = maybe 5 = yes, with public statements in support | 5 |
| Have political risks been anticipated and managed? | 1 = no, high risks remain 3 = moderate and manageable 5 = yes, minimal residual risks | 5 |
| Is buy-in among stakeholders (i.e. potential investors/ decision makers, implementers, and beneficiaries) sufficiently strong to counter potential opposition? | 1 = no 3 = partial buy-in 5 = yes, strong buy-in | 5 |
| Do the managing actor(s) have sufficient capacity? Can they rapidly acquire it? | 1 = no, severe capacity gap 3 = moderate capacity gap 5 = yes, strong capacity | 2 |
| Is it legally feasible? How challenging will any legal requirements be? | 1 = no, new law is required 3 = new regulations required 5 = yes, new regulations are not needed | 5 |
| Is it coherent with the institutional architecture, can synergies be achieved? | 1 = no, limited or no synergies / coherence 3 = potential synergies 5 = yes, fully coherent / large synergies | 5 |

BIOFIN Proposal Template

Design and Implementation of Finance Solutions - Output 5

Country: South Africa			Submission date: 06/03/2020……..…….………….

Contact person: Karl Naude		Email Address: knaude@environment.gov.za

SECTION 1 – FOR PROPOSED FINANCE SOLUTIONS

☐ Feasibility stage (If the solution is in the preparatory stage less details will be expected. Only the white sections in the table must be filled, the grey sections will be filled at the next stage).

☒ Full implementation stage (If the solution enters in the full implementation stage, more details are expected. The white and the grey sections must be filled with as many details as possible)

| Proposal Summary |  |
| --- | --- |
| Title of the Finance Solution | Reform of property rates legislation, interpretation and application to protected areas |
| Concise Description (abstract) | Certain categories of protected areas face the challenge of being charged substantial property rates bills due to ambiguity regarding the interpretation and application in the Municipal Property Rates Act No.6 of 2004 (MPRA). This is placing considerable undue financial pressure on state entities and private citizens providing a public benefit through the management and protection of South Africa’s protected areas. As an example, as of May 2016, South African National Parks (SANParks) was facing demands from various local municipalities for rates arrears totalling approximately R212 million. In addition, they estimate that future demands would be in excess of R80 million/yr. This solution aims to ensure that the application of national legislation defining property rates exclusions, exemptions and rebates and the associated policies and application procedures by municipalities better reflects the spirit and intention of the MPRA with respect to the concessions it offers protected areas national botanical gardens. In implementing this solution, further intergovernmental collaboration will be undertaken between Department of Environment, Forestry and Fisheries (DEFF), Cooperative Governance and Traditional Affairs (CoGTA), South African Local Government Association (SALGA) and National Treasury (NT) to look at an interim solution in resolving current municipal rates bills received by management authorities. Parallel to this, technical assessment will be undertaken to inform the development of a national framework which will serve as a guide to municipalities to amend their rates policies. There is a task team recommended by the Department through Working Group1 to look at Property Rates countrywide and recommend a way forward to address the application of property rates within the definition of the Local Government Municipal Property Rates Act, 2004, especially with regards to impermissible rates under section 17 (1)(e). |
| Contribution to SDGs | SDG 8: Decent work and economic growth SDG 11: Sustainable Cities SDG 15: Life on land SDG 17: Partnerships for goals |
| Contribution to Aichi Targets / National Targets / Biodiversity Finance Plan | Aichi Target 11: The clear interpretation and application of municipal property rates exclusions has the potential to promote and support the declaration and expansion of the protected area estate for improved management, effectively assisting South Africa to achieve Target 11. Aichi Target 20: The clear interpretation and application of municipal property rates exclusions has the potential to promote another form of fiscally based incentive and create another finance solution tailor made for biodiversity protection and management and aid South Africa to achieve Target 20. NBSAP: 1. Management of biodiversity assets and their contribution to the economy, rural development, job creation and social well-being is enhanced. National Targets for protected areas: The clear interpretation and application of municipal property rates exclusions has the potential to promote and support the declaration and expansion of the protected area estate for improved management of protected areas on state effectively assisting South Africa to reach its national protected area expansion targets encased in the National Protected Area Expansion Strategy. National Targets for the creation of environmental incentives: The clear interpretation and application of municipal property rates exclusions has the potential to promote the effective use of another form of fiscal incentive dedicated to protecting and managing biodiversity and ecological infrastructure, effectively assisting South Africa to achieve the creation of legitimate environmental incentives. |
| Implementing / Strategic partners (if other than UNDP) | DEFF, South African National Biodiversity Institute, Protected Area Management Authorities, Cooperative Governance and Traditional Affairs, National Treasury and BirdLife SA |
| Start and End Date | 2020 – 2022 |

Categorization

| Solution Category/ies from the BIOFIN Catalogue | Protected areas/ Fiscal Incentives |
| --- | --- |
| Relevant Finance Result(s) | Re-aligning existing resources Preventing future costs |
| Estimated Finance Result | The key results would be realized through savings on property rates that protected area authorities could rather be using for conservation. These would include arrears amounts which may exceed the R212 million being demanded from SANParks alone (the nine provincial Protected Area Management Authorities are subject to the same challenge). Future avoided costs for all protected area authorities (i.e. the ten state authorities, privately or communally owned protected areas, and national botanical gardens) were assumed to be approximately twice the R80 million per year rates liability estimated for SANParks after three years, reflecting the area under their management relative to the national protected areas estate. The potential maximum additional cost to DEFF and its partners of achieving the necessary reforms was assumed to be R3 million in potential legal fees and other specialist input. |
| Finance Source | Public |
| Sector | Protected Areas |
| Instrument Type | Fiscal Incentive: Municipal Rates Exclusions, Exemptions and Rebates |

Note: if Private sector please check due diligence requirements / guidelines at this LINK

Note: if Private sector please check due diligence requirements / guidelines at this LINK

| Budget (USD) |  |  |
| --- | --- | --- |
| Total resources required: | USD 150 000 |  |
| Total resources allocated: |  |  |
|  | BIOFIN | USD 150 000 |
|  | Donor 1: |  |
|  | Donor 2: | - |
|  | Government of … | - |
|  | In-Kind | Staff time |
| Unfunded: |  | 0 |

| Main Proposal and approach |  |
| --- | --- |
| - Background (100 words max) | Municipal property rates legislation and policies are governed by the Municipal Property Rates Act (MPRA). The MPRA equates to national legislation and provides for three forms of property rates fiscal concessions both through prescription as well as through discretionary powers placed on municipalities, namely: rates exclusions, rates exemptions and rates rebates. Property rates are a substantial source of revenue for municipalities and can be used to relieve the financial pressure experienced by many municipalities as a result of reductions or misappropriations of fiscal allocations. These areas of interpretive debate, alongside the discretionary powers afforded municipalities, have consequences for different categories of protected areas and botanical gardens. There are positive biodiversity outcomes when applied for the benefit of environmental management and protection, in line with the spirit and purport of the legislation. However, there are negative consequences which are particularly significant in the case of protected areas, and which fail to provide financial sustainability to protected areas and botanical gardens, but rather place undue financial strain. Section 17(1) (e) of the MPRA excludes a municipality’s rating power over a property, whereby the municipality may not levy a rate on those parts of a property declared as a special nature reserve, national park or nature reserve within the meaning of the Protected Areas Act, or of a national botanical garden within the meaning of the Biodiversity Act, which are not developed or used for commercial, business, agricultural or residential purposes. The intention of this condition, which came into effect in 2009, was to exclude the rating of the bulk of a property that is used for conservation purposes, but to still rate those portions of the property that are clearly not used for conservation purposes and are used for commercial, industrial, residential or other non-conservation related purposes or where there is essentially exists a ‘right of use’ on a portion of the property (for example, a game lodge or a restaurant). However, there are instances where in the implementation of the MPRA, conservation authorities and private citizens responsible are charged exorbitant and unrealistically high property rates for entire properties declared as protected areas or designated as botanical gardens. This leads to significant additional costs now or in the future in that rates there is no incentive for the declaration of future protected areas and botanical gardens which limits the ability to effectively manage these areas sustainably. In addition, in the application of the tax legislation, a precedent exists regarding the determination and valuation of any ‘right of use’ regarding the valuation of a property. |
| - Objective(s) and Results expected: (100 words max) | The objective of this finance solution is to ensure that there is correct interpretation of the legislation in order to provide a standardised mechanism to rate protected areas correctly. This will allow management authorities to apply for a reduction or for exemption for property rates for protected areas and botanic gardens. The key results would be realised through savings on property rates that protected area authorities could use for biodiversity instead. |
| - Business case (Approx 150 words) | - Protected areas and national botanical gardens are a public good providing significant biodiversity and socio-economic benefits to society. - Their contribution is reflected in the concessions offered to them in the Municipal Property Rates Act, but not consistently in the application of the Act at municipal level, resulting in unwarranted financial strain on protected areas and botanical gardens. - Alleviating this financial strain would make an important contribution to the financial sustainability of protected areas and botanical gardens at a time when they are under significant budgetary pressure. |
| - Structure of the Finance Solution (100 words approx.) | The finance solution is a fiscal mechanism where special nature reserves, national parks or nature reserves within the meaning of the Protected Areas Act and botanical gardens will qualify for an exemption or reduction in property rates that are charged. Currently there is no standardized mechanism to determine property rates for the specific areas indicated in the Local Government Municipal Property Rates Act, 2004, section 17 (1)(e), included the value of the area and the level of the rates to be levied. |
| - Description of Activities and Milestones (150 words approx.) | Year 1 – 2020 DEFF supported by BIOFIN will engage South African Local Government, Cooperative Governance and Traditional Affairs, National Treasury and possibly others in order to explore options in principle. - Development of standardised interpretation and approach to section 17 of the MPRA; - Reach agreement on interim solution to immediate financial challenges faced by protected areas. - Development of qualifying criteria for protected areas to be excluded for property rates in terms of Section 17 of MPRA Year 2 – 2021 - BIOFIN will support DEFF to undertake technical assessment and associated work on long-term solution likely to be within national framework for property rates published under the MPRA - BIOFIN will support NT and DCOGTA on widespread consultation on the national guidance and agreement. Year 3-2022 - Finalization and approval of national framework by National Treasury and DCOGTA - BIOFIN will support NT and DCOGTA to communicate key aspects of the framework to stakeholders - BIOFIN supports a test case in Municipalities on the application of rates policies |
| - Institutional Arrangements (100 words max) | - BIOFIN will support DEFF, Cooperative Governance and Traditional Affairs, and National Treasury engagement - Management authorities, relevant provincial departments and municipalities |
| - Main risks and management response for solution implementation (100 words max) | - Inability to reach a workable agreement with Cooperative Governance and Traditional Affairs and National Treasury regarding proposed solutions. This will be mitigated by establishing a high-level political engagement between DEFF, Cooperative Governance and Traditional Affairs and National Treasury. - Inability to carry out additional technical and legal work due to limited resources. This will be mitigated by exploring other resources from other sources. - Resistance from local municipalities regarding the implementation of solutions that would have a negative impact on their finances. National Treasury could look at the possibility of indirectly compensating municipalities with a high number of PAs vs rates base, through intergovernmental transfers that acknowledge the loss of revenue when PAs pay less/no property rates. |
| - Sustainability and institutionalization (100 words approx..) | This finance solution will result in correct application and interpretation of legislative which will be through policy practice notes that will effect changes to municipal property policies. Municipalities will be able to apply a uniform policy that recognizes the intrinsic biodiversity value of protected areas. |
| - M&E (100 words approx.) | Impact of the solution will be assessed through the increase of protected areas excluded from property rates in line with the national framework |

| Indicator | Baseline | Target |
| --- | --- | --- |
| Reduction property rates charged on protected areas | R240 million per annum spent on property rates by SANParks and 10 management authorities. | 50% reduction in property rates by 2022 |
| Development of a national framework | No Framework | Framework developed and applied by all Municipalities |

SECTION 2 – FOR APPROVED FINANCE SOLUTIONS ONLY

Please provide the following information which will be included in next Work plan/Budget revision (or use actual Work plan document):

| Action Plan and Budget |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome/s (Result/s): A reduced financial burden on protected areas due to a reduction in property rates |  |  |  |  |  | Timeframe |  |  |  |
| Output/s | Activities (example below) | Responsible actor/s | Funding source | Total Costs (USD) (detail by year in the AWP if FS approved) | Atlas. Budg. Code (For approved projects) | 2020 | 2021 | 2022 | … |
| Baseline: R212 million per annum spent on property rates by SANParks Target: 50% reduction in property rates Indicators: Reduction property rates charged on protected areas Exemption in property rates | Preparatory activities: |  |  |  |  |  |  |  |  |
|  | Finalize discussion document | DEFF and management authorities | DEFF | Staff time |  | X |  |  |  |
|  | Present concept to National Treasury and CoGTA and agree on interim approach | DEFF Task Team | DEFF | Staff time |  | X |  |  |  |
|  | Implementation |  |  |  |  |  |  |  |  |
|  | Technical assessment | BIOFIN PMU and DEFF | BIOFIN | 50 000 |  | X |  |  |  |
|  | Development of a budget memo for National Treasury | BIOFIN PMU and DEFF | BIOFIN | 20 000 |  |  | X |  |  |
|  | Develop a national framework for municipal property rates policies | BIOFIN PMU and DEFF | BIOFIN | 30 000 |  |  | X |  |  |
|  | Validation | BIOFIN PMU and DEFF |  |  |  |  |  |  |  |
|  | Consultation with municipalities | BIOFIN PMU and DEFF | BIOFIN | 30 000 |  |  |  | X |  |
|  | Test case in municipal property rates policies | BIOFIN PMU and DEFF | BIOFIN | 20 000 |  |  |  | X |  |
|  | Alignment to property rates policies in municipalities | Municipalities |  |  |  |  |  |  |  |
|  | Implementation | Municipalities |  |  |  |  |  |  |  |
| TOTAL |  |  |  | 150 000 |  |  |  |  |  |

Annex 1: BIOFIN Prioritization Scoring and Screening Questions

| Questions | Indicative marks for scoring (1-5) | Score |
| --- | --- | --- |
| Is there a positive record of implementation? | 1= no, or limited records of success 3= successful pilots 5= yes, high potential of scalability | 3 |
| Will it generate, leverage, save, or realign a large volume of financial resources? | 1= minimal scale 2= <5 per cent of current expenditures / needs 3= 5-15 per cent of current expenditures / needs 4= >20 per cent of current expenditures / needs 5= game changer | 4 |
| Will financing sources be mobilized in a compatible timeline with needs? | 1 = no, the mobilization is not aligned with needs 3 = likelihood of being mobilized in alignment with needs 5 = yes, forthcoming and compatible schedules | 3 |
| Will financing sources be stable and predictable? | 1 = no, the source of revenue may be highly unstable and vulnerable to external factors 3 = likelihood of being reasonably stable and predictable source 5 = yes, very stable and predictable | 3 |
| Do the persons or entities paying have a willingness and ability to pay or invest? | 1 = no 3 = possibly 5 = yes | 3 |
| Are the financial risks adequately managed (e.g. exchange rate, lack of investors, etc.)? | 1 = no, high risks remain 3 = moderate risks 5 = yes, low residual risks | 3 |
| Are start-up costs onerous in comparison to the expected financial returns? | 1 = very costly (compared to returns) 3 = moderate (compared to returns) 5 = very low/minimal (compared to returns) | 3 |
| Does the solution improve incentives to manage biodiversity and ecosystems sustainably? (see Chapter 1). | 1 = not clear 3 = likely 5 = most certainly | 5 |
| Will the financial resources remain targeted to biodiversity over time? | 1 = not clear, high risk of misallocation 3 = likely, administrative provisions 5 = yes, strong legal provisions | 5 |
| Are risks to biodiversity (e.g. disrespect of mitigation hierarchy) low or easily mitigated? How challenging would it be to develop safeguards? | 1 = high risks, no easy mitigation 3 = reasonable risks, mitigation possible 5 = low risks, easy safeguards | 3 |
| Will there be a positive social and economic impact (e.g. jobs, poverty reduction and cultural)? | 1 = no 3 = moderate 5 = strong positive impact | 3 |
| Would there be a positive impact on gender equality, especially regarding participation in design and implementation or access to opportunities and benefits? | 1 = no 3 = moderate 5 = strong positive impact | 3 |
| Have risks of significant unintended negative social consequences been anticipated and managed? | 1 = no, high risks remain 3 = moderate and manageable 5 = yes, minimal residual risks | 3 |
| Will it be viewed as equitable and will there be fair access to the financial and biodiversity/ecosystem resources? | 1 = no, risk of inequitable outcome 3 = maybe 5 = yes | 3 |
| Is it backed by political will? | 1 = no, resistance from key stakeholders 3 = maybe 5 = yes, with public statements in support | 3 |
| Have political risks been anticipated and managed? | 1 = no, high risks remain 3 = moderate and manageable 5 = yes, minimal residual risks | 3 |
| Is buy-in among stakeholders (i.e. potential investors/ decision makers, implementers, and beneficiaries) sufficiently strong to counter potential opposition? | 1 = no 3 = partial buy-in 5 = yes, strong buy-in | 5 |
| Do the managing actor(s) have sufficient capacity? Can they rapidly acquire it? | 1 = no, severe capacity gap 3 = moderate capacity gap 5 = yes, strong capacity | 3 |
| Is it legally feasible? How challenging will any legal requirements be? | 1 = no, new law is required 3 = new regulations required 5 = yes, new regulations are not needed | 3 |
| Is it coherent with the institutional architecture, can synergies be achieved? | 1 = no, limited or no synergies / coherence 3 = potential synergies 5 = yes, fully coherent / large synergies | 3 |

BIOFIN Proposal Template

Design and Implementation of Finance Solutions - Output 5

Country: South Africa				Submission date: 06/03/2020

Contact person: Pamela Kershaw      		Email Address: pkershaw@environment.gov.za

SECTION 1 – FOR PROPOSED FINANCE SOLUTIONS

☐ Feasibility stage (If the solution is in the preparatory stage less details will be expected. Only the white sections in the table must be filled, the grey sections will be filled at the next stage).

☒ Full implementation stage (If the solution enters in the full implementation stage, more details are expected. The white and the grey sections must be filled with as many details as possible)

| Proposal Summary |  |
| --- | --- |
| Title of the Finance Solution | Building a grant mechanism to adequately finance the biodiversity stewardship programmes |
| Concise Description (abstract) | The PIR recognised a need for mechanisms to ensure ring-fenced allocations for the environmental sector to transfer funds to provinces for discrete purposes to do resource management and protection. Biodiversity stewardship programmes provide a highly cost-effective mechanism for expanding protected areas in South Africa and can secure investments in climate resilience and natural resource management contributing to national development goals. Despite the financial, economic and environmental benefits of biodiversity stewardship, these government-led programmes remain substantially under-resourced within all conservation authorities. This solution, a grant mechanism for adequately financing biodiversity stewardship capacity in state agencies, aims to build the first conditional grant-type appropriation program in the National Environment budget vote for disbursement to provinces for stewardship staff and operational capacity. This capacity will directly enable pursuing protected area expansion targets; securing strategic water source areas through good land management; as well as securing investments in the wildlife economy; and ecosystem restoration for climate resilience. As the direct financing of biodiversity stewardship implementation can come from a number of different sources (including tax and rates incentives, water tariffs and existing government funds and private investments), this finance solution will also seek to remove obstacles to using other innovative finance sources to complement direct state funding. In practical terms, this will enable other finance solutions and programmes of work. It will also play a facilitating role increasing the likelihood that other finance solutions, such as unlocking returns from the wildlife economy and revolving land trusts, will succeed. |
| Contribution to SDGs | This solution directly contributes to SDGs 12, 13, 14, 15 & 17, and indirectly to 1, 5, and 8. Goal 1 No poverty Goal 5 Gender equality Goal 8 Decent work and economic growth Goal 12 Responsible production and consumption Goal 13 Climate change Goal 14 Life below water Goal 15 Life on land Goal 17 Partnerships for the goals |
| Contribution to Aichi Targets / National Targets / Biodiversity Finance Plan | Aichi target 11: “By 2020, at least 17 per cent of terrestrial and inland water areas and 10 per cent of coastal and marine areas, especially areas of particular importance for biodiversity and ecosystem services, are conserved through effectively and equitably managed, ecologically representative and well-connected systems of protected areas and other effective area-based conservation measures, and integrated into the wider landscape and seascape.” NBSAP Goal 1: People are mobilized to adopt practices that sustain the long-term benefits of biodiversity. Goal 3: Biodiversity considerations are mainstreamed into policies, strategies and practices of a range of sectors. Realizing the National Development Plan vision will require improving mechanisms to secure priority sites and ecosystem services (including ecological infrastructure). Biodiversity stewardship has been shown to be the most cost-effective tool we currently have to improve protection and management of non-state land and underpin rehabilitation. This finance solution was included in the Biodiversity Finance plan and is seen as crucial for the success of other finance solutions in the Plan. |
| Implementing / Strategic partners (if other than UNDP) | DEFF (principal), South African National Parks (SANParks), Provincial conservation authorities and local government (implementation of stewardship programs), National Treasury (support and technical assistance) SANBI (support). |
| Start and End Date | 2020 to 2022 |

Categorization

| Solution Category/ies from the BIOFIN Catalogue | Cross cutting Enhance public budget execution: Remove barriers for public budget execution and internal; : Influence the recurrent budget formulation; and Enhanced land or marine stewardship Non-state Protected Areas |
| --- | --- |
| Relevant Finance Result(s) | - Mobilizing Resources - Delivering Better - Re-aligning existing resources - Preventing future costs |
| Estimated Finance Result | R80 million (USD6 million) per annum channeled directly from the state to provincial biodiversity stewardship programmes by 2022. This investment from the state will result in substantial costs savings, as it will leverage private sector investment in PA establishment and management. |
| Finance Source | Public/Private & national/international |
| Sector | Conservation and Biodiversity |
| Instrument Type | Mixed (private and public) |

Note: if Private sector please check due diligence requirements / guidelines at this LINK

| Budget (USD) |  |  |
| --- | --- | --- |
| Total resources required: | USD 262 000 |  |
| Total resources allocated: |  |  |
|  | BIOFIN | USD 190 000 |
|  | Donor 1: SANBI | USD 72 000 |
|  | Donor 2: |  |
|  | Government of South Africa |  |
|  | In-Kind | - |
| Unfunded: |  | - |

| Main Proposal and approach |  |
| --- | --- |
| - Background | South Africa’s biodiversity stewardship programmes provide trained staff to encourage communal and private landowners to better conserve biodiversity. A suite of options of are available, with applicable incentives and support scaled according to protection levels adopted. Eligible sites are secured through agreements (including protected area designation) and appropriate management plans. Current (2018/9) government (R22,5m) and donor (R14,5m) budgets for stewardship programmes fall short of the minimum required for meeting PA expansion targets (R74m), let alone for a concerted effort to secure water source areas, protect and rehabilitate undeclared state land with important biodiversity and serve the emerging biodiversity economy. Fully fledged programs in all 9 provinces are estimated to cost R120m p.a. Provincial government budgets are constrained, and biodiversity is seldom prioritised. The Environment sector is the only concurrent competency (i.e. a function shared between national and provincial government) that does not to have a mechanism for conditional grants to provinces for implementing national priorities. Without vibrant biodiversity stewardship programmes, it is difficult to deliver on other biodiversity finance solutions (including tax incentives, property rates incentives, and private sector wildlife economy investments) or deploy other revenue (e.g. from water tariffs) for ecosystem rehabilitation or protection. Given the multifaceted nature of the biodiversity stewardship programmes, there is strong case to be made for innovative funding mechanisms to be developed to complement direct state investment. Viable opportunities for this have been set out in the BFP. These include water tariffs, biodiversity offsets; climate change funding. This finance solution seeks to pilot at least one of these mechanisms as part of the integrated work on resilient funding for biodiversity stewardship programmes |
| - Objective(s) and Results expected: | Objective: Ensure adequate resourcing of biodiversity stewardship capacity and operational costs in provinces. Results: - A grant framework for biodiversity stewardship is developed with National Treasury for financial allocation to provincial biodiversity stewardship programs - Three to five-year resource allocation plan setting out national and provincial funds required and the resulting Medium-Term Expenditure Framework (MTEF) submission on biodiversity stewardship programmatic funding - A successful pilot of deployment of water tariffs, offset funds or other (impact) investments in priority areas through stewardship. |
| - Business case | A detailed business case for investing in biodiversity stewardship has been developed by SANBI (2017). Establishing a protected area through biodiversity stewardship is between 70 and 400 times less costly to the state than land acquisition, ongoing management of a contract protected area is between 4 and 17 times less costly than managing a state-owned protected area. This conditional grant mechanism is feasible as it is commonly used by other government departments in South Africa with concurrent competencies. For instance, the National LandCare program in Department of Agriculture allocates around R80 million annually (in quarterly tranches) to provincial departments to implement natural resource protection programs. |
| - Structure of the Finance Solution | - Develop a conditional grant framework that allocates national fiscal resources to provinces, and ring-fences them for implementation for discrete purposes to undertake resource management and protection. - Pilot the use of an alternative finance source in priority areas using the established stewardship program capacity. |
| - Description of Activities | - Review existing national budget appropriations for provincial implementation in other jurisdictions (such as the LandCare in Agriculture) to elicit key success factors for an environmental sector mechanism. Determine options to transfer to provincial department or statutory conservation agencies. Scope out matching grant requirements (to prevent provincial budget substitution). - Clarify a stewardship value proposition in supporting key government policies, including the National Biodiversity Economy Strategy; Securing Strategic Water Source Areas; The Ecosystem-based Adaptation Strategy for Climate Resilience, and specifically the National Development Plan. Determine most appropriate mechanism to promote for synergy with contractual stewardship implementation. - Building on the costing needs analysis (SANBI), scope out appropriate cost-sharing between national and provincial budgets. Draw up a 3-5-year nominal budget for each provincial implementation entity, and associated targets. - Develop a policy proposal for MTEF submission in DEFF’s priorities for an appropriation for a national stewardship program implemented by grants to provinces. - Draw up an implementation checklist for provincial biodiversity stewardship implementers to ease the burden of monitoring effectiveness and reporting on condition grants to the National Treasury. Workshop program implementation with 9 provinces, DEFF, SANParks, SANBI and Treasury/ GTAC support. 6. Pilot the deployment of at least 1 innovative funding source (e.g. water tariff funding, climate finance, and biodiversity offset funds) through the stewardship mechanisms in priority areas in two provinces. |
| - Institutional Arrangements | This is a cross-cutting financial solution and will require institutional support from National Treasury, DEFF, SANBI, SANParks and provinces. SANBI is leading work on a cost analysis for biodiversity stewardship, with support from NGOs, conservation authorities and DEFF. National Treasury and possibly the Government Technical Advice Centre (GTAC) will need to advise on the appropriate grant framework. It is likely that a Task Team comprising of multiple institutions will be convened to manage the work programs under this financial solution. There already exists a national Biodiversity Stewardship Task Team, convened by SANBI with representation from all nine provinces, DEFF, SANParks and some NGOs, which can support this work. |
| - Main risks and management response for solution implementation) | - There is historic resistance to using conditional grant frameworks in the Environment sector. This solution needs to determine why, and purpose-build a response to address any residual concerns. - It is possible that some provinces may substitute national program funds for their budget commitments to various conservation agencies’ stewardship efforts. This will be managed through building a matching requirement into the grant program structure and tracking provincial allocations through the annual expenditure review. - Pressure on the fiscal framework or existing commitments prevents DEFF budget including a conditional grant component. The solution will have to make the case to DEFF senior management and their political principals in the Minister’s and MEC’s forum to support the flexible, systematic and low-cost stewardship approach to achieve national environmental and development priorities. - Reduced financial opportunities within the private sector to support public sector funding. This will be mitigated by capitalizing on other sources such as offsets or social responsibility programmes. |
| - Sustainability and institutionalization | The hope is that the grant framework becomes a durable part of the public sector financing approach to policy priorities in the environment sector, complemented by private sector financing mechanisms. The deeper understanding of the grant framework administration and reporting requirements within DEFF and the provinces should achieve the institutionalization. The provinces will be expected to accommodate the existing or nascent stewardship program staff within their staff structures (as a useful way to organize most work involving PA expansion and non-state land protected areas). |
| - M&E | The main indicators will be verified by the National Budget /medium term fiscal framework of 2020/21 (or beyond) containing the grant or an equivalent program. Even if the R80m target is not reached, the existence of the grant framework will be a satisfactory outcome. The nine provincial budgets (or those of the 6 statutory agencies in those provinces where this function resides in them) provide the means of verification for the continued support of provincial stewardship programs. Case studies written up on the use of an alternative/ innovative finance mechanism in a priority site through stewardship will be used to monitor outcomes. |

| Indicator | Baseline | Target |
| --- | --- | --- |
| National funds routed directly to provinces for provincial biodiversity stewardship type programs for PA expansion, climate resilience, watershed management. | R0 | R80 million (USD6 million) p.a. grant program by 2022. |
| Provincial treasury allocations to provincial biodiversity stewardship programs | R22 million (2018/9) | R40 million (USD3 million) p.a. mobilized by 2022 |
| Existence of conditional grant type mechanism in environment sector | None exists | A grant framework structure is in place by 2022 |
| Number of stewardship sites using innovative funding sources for rehabilitation and management | Zero | Five sites (using water tariff, impact investment, or offset funds) |

SECTION 2 – FOR APPROVED FINANCE SOLUTIONS ONLY

Please provide the following information which will be included in next Work plan/Budget revision (or use actual Work plan document):

| Action Plan and Budget |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome/s (Result/s): Stewardship sites are adequately and appropriately funded through a grant mechanism from national government. |  |  |  |  |  | Timeframe |  |  |  |
| Output/s | Activities (example below) | Responsible actor/s | Funding source | Total Costs (USD) (detail by year in the AWP if FS approved) | Atlas. Budg. Code (For approved projects) | 2020 | 2021 | 2022 | … |
| Baseline: RO funds allocated to stewardship Indicators: establishment of a national grant framework Targets: By 2022, a grant framework will be in place that can generate up to R80m | Preparatory activities: | DEFF and SANBI | SANBI/ DEFF |  |  |  |  |  |  |
|  | Consultation with National Treasury | BIOFIN DEFF and SANBI |  |  |  | X |  |  |  |
|  | Review of existing grants to identify stewardship funding opportunities | BIOFIN DEFF and SANBI | BIOFIN / SANBI | 50 000 10 000 |  | X |  |  |  |
|  | Implementation |  |  |  |  |  |  |  |  |
|  | Develop a value proposition for stewardship for consultation with other departments | BIOFIN DEFF SANBI | BIOFIN / SANBI | 50 000 20 000 |  | X |  |  |  |
|  | Develop a costing and grant framework for stewardship | BIOFIN DEFF SANBI | BIOFIN / SANBI | 70 000 40 000 |  |  | X |  |  |
|  | MTEF Submissions |  |  |  |  |  |  |  |  |
|  | Validation |  |  |  |  |  |  |  |  |
|  | Stakeholder consultation | SANBI | BIOFIN/ SANBI | 20 000 2 000 |  |  |  | X |  |
| TOTAL |  |  |  | 262 000 |  |  |  |  |  |

Annex 1: BIOFIN Prioritization Scoring and Screening Questions

| Questions | Indicative marks for scoring (1-5) | Score |
| --- | --- | --- |
| Is there a positive record of implementation? | 1= no, or limited records of success 3= successful pilots 5= yes, high potential of scalability | 3 |
| Will it generate, leverage, save, or realign a large volume of financial resources? | 1= minimal scale 2= <5 per cent of current expenditures / needs 3= 5-15 per cent of current expenditures / needs 4= >20 per cent of current expenditures / needs 5= game changer | 3 |
| Will financing sources be mobilized in a compatible timeline with needs? | 1 = no, the mobilization is not aligned with needs 3 = likelihood of being mobilized in alignment with needs 5 = yes, forthcoming and compatible schedules | 3 |
| Will financing sources be stable and predictable? | 1 = no, the source of revenue may be highly unstable and vulnerable to external factors 3 = likelihood of being reasonably stable and predictable source 5 = yes, very stable and predictable | 3 |
| Do the persons or entities paying have a willingness and ability to pay or invest? | 1 = no 3 = possibly 5 = yes | 3 |
| Are the financial risks adequately managed (e.g. exchange rate, lack of investors, etc.)? | 1 = no, high risks remain 3 = moderate risks 5 = yes, low residual risks | 5 |
| Are start-up costs onerous in comparison to the expected financial returns? | 1 = very costly (compared to returns) 3 = moderate (compared to returns) 5 = very low/minimal (compared to returns) | 5 |
| Does the solution improve incentives to manage biodiversity and ecosystems sustainably? (see Chapter 1). | 1 = not clear 3 = likely 5 = most certainly | 5 |
| Will the financial resources remain targeted to biodiversity over time? | 1 = not clear, high risk of misallocation 3 = likely, administrative provisions 5 = yes, strong legal provisions | 5 |
| Are risks to biodiversity (e.g. disrespect of mitigation hierarchy) low or easily mitigated? How challenging would it be to develop safeguards? | 1 = high risks, no easy mitigation 3 = reasonable risks, mitigation possible 5 = low risks, easy safeguards | 5 |
| Will there be a positive social and economic impact (e.g. jobs, poverty reduction and cultural)? | 1 = no 3 = moderate 5 = strong positive impact | 5 |
| Would there be a positive impact on gender equality, especially regarding participation in design and implementation or access to opportunities and benefits? | 1 = no 3 = moderate 5 = strong positive impact | 4 |
| Have risks of significant unintended negative social consequences been anticipated and managed? | 1 = no, high risks remain 3 = moderate and manageable 5 = yes, minimal residual risks | 3 |
| Will it be viewed as equitable and will there be fair access to the financial and biodiversity/ecosystem resources? | 1 = no, risk of inequitable outcome 3 = maybe 5 = yes | 4 |
| Is it backed by political will? | 1 = no, resistance from key stakeholders 3 = maybe 5 = yes, with public statements in support | 3 |
| Have political risks been anticipated and managed? | 1 = no, high risks remain 3 = moderate and manageable 5 = yes, minimal residual risks | 3 |
| Is buy-in among stakeholders (i.e. potential investors/ decision makers, implementers, and beneficiaries) sufficiently strong to counter potential opposition? | 1 = no 3 = partial buy-in 5 = yes, strong buy-in | 3 |
| Do the managing actor(s) have sufficient capacity? Can they rapidly acquire it? | 1 = no, severe capacity gap 3 = moderate capacity gap 5 = yes, strong capacity | 3 |
| Is it legally feasible? How challenging will any legal requirements be? | 1 = no, new law is required 3 = new regulations required 5 = yes, new regulations are not needed | 3 |
| Is it coherent with the institutional architecture, can synergies be achieved? | 1 = no, limited or no synergies / coherence 3 = potential synergies 5 = yes, fully coherent / large synergies | 5 |

BIOFIN Proposal Template

Design and Implementation of Finance Solutions - Output 5

Country: South Africa			Submission date: 06/03/2020

Contact person: Pamela Kershaw	Email Address: pkershaw@environment.gov.za

SECTION 1 – FOR PROPOSED FINANCE SOLUTIONS

☐ Feasibility stage (If the solution is in the preparatory stage less details will be expected. Only the white sections in the table must be filled, the grey sections will be filled at the next stage).

☒ Full implementation stage (If the solution enters in the full implementation stage, more details are expected. The white and the grey sections must be filled with as many details as possible)

| Proposal Summary |  |
| --- | --- |
| Title of the Finance Solution | Institutional support for biodiversity tax incentives |
| Concise Description (abstract) | The South African Government, through the National Treasury, has provided fiscal incentives in the form of biodiversity tax incentives to South Africa’s protected areas. The original biodiversity tax incentive is section 37C and was lodged in the Income Tax Act (ITA) in 2009. Section 37C has not been utilised by taxpayers in 10 years and is functionally defunct. A second tax incentive, section 37D, was lodged in the ITA in 2015. Section 37D is fully functional and is being utilised across the country, with approximately 60 tax sites recorded in 2019, and more planned for 2020.This finance solution seeks to address the current dysfunction of section 37C by amending the ITA, ensuring additional financial sustainability and mobilization for South Africa’s protected areas. The biodiversity tax incentives were created to address environmental management expenses incurred by taxpayers as well as loss of economic rights and use when declaring protected areas. Section 37D allows for a landowner or community who declares their land as a Nature Reserve or National Park to deduct the full value of that declared land from their taxable income each year for 25 years at 4 per cent per annum. The value of section 37D is currently addressing South Africa’s BIOFIN gap by approximately 8.8 per cent and is estimated to contribute R1.4 billion by 2026. These estimates have already been exceeded, e.g.: 2019 estimated contribution of R75 million is over R100 million. The values of individual tax incentives vary across landscapes depending on the size and activities of the protected area but can be numerically quantified with ease. The resultant biodiversity and economic outcomes can also be tracked over time but take slightly more effort to quantify. The feasibility of the biodiversity tax incentives has been thoroughly tested through the work conducted by niche tax expert, Candice Stevens (refer to the Fiscal Benefits Project). This work resulted in the implementation of the new and effective tax benefit, section 37D. This work also showed why the original tax incentive, section 37C, failed and what would need to be corrected for it to achieve its original policy mandate and provide financial benefits. Within this scope of work, preliminary investigations regarding possible tax structuring to address legislative amendments to section 37C and discussions with National Treasury were concluded in 2018, resulting in an official Annexure C Submission. The biodiversity tax incentives now require advanced technical structuring, technical amendments, institutional support and practical enabling at pilot sites to upscale their impact through the creation of a second effective biodiversity tax incentive to manage biodiversity and ecosystems sustainably. It should be noted that tax incentives increase leveraging opportunities with other financial solutions and assist in attracting further investment. The implementation of this finance solution therefore requires the following key focal areas and corresponding actions: - Technical Amendment of section 37C: this is vital if the failure of the original biodiversity tax incentive is to be addressed. If the ITA is not amended in a technically accurate manner that translates into the appropriate contexts, then the potential financial mobilisation and sustainability for biodiversity and ecosystem services it could provide will not be realised. This was achieved previously with section 37D and it is believed that the process can be repeated and thereby provide a financial solution for the environmental management costs incurred within protected areas. - Negotiations with National Treasury; - Following fiscal policy and legislative amendment procedures determined by National Treasury; - Technical structuring of an alternative/s tax incentive; - Technical analysis of the proposed technical structuring and its anticipated uptake and impact within the appropriate contexts; - Amendment of tax legislation; - Testing at pilot sites. - Investigation into other potential tax incentives for area-based conservation and management. |
| Contribution to SDGs | SDG 15: The South African biodiversity tax incentives promote, support and create financial sustainability for South Africa’s protected areas on private and communal land through the national biodiversity stewardship initiative. SDG 8: The South African biodiversity tax incentives promote, support and create financial sustainability for commercial activities compatible with protected areas and sustainable practices within various sectors. Supporting and creating financial sustainability for South Africa’s burgeoning Wildlife Economy is critical to boosting the creation of sustainable livelihoods and growing the economy as encompassed in SDG 8. SDG 17: The South African biodiversity tax incentives promote, support and foster strong collaborative partnerships between government, civil society and the private sector. The achievement of the introduction of South Africa’s first effective biodiversity tax incentive through the Fiscal Benefits Project was the cumulative effort of civil society technical expertise and institutional support from government and is a clear reflection of the partnerships required to achieve the SDGs. |
| Contribution to Aichi Targets / National Targets / Biodiversity Finance Plan | Aichi Target 11: The South African biodiversity tax incentives promote and support the declaration of protected areas on private and communal land through the national biodiversity stewardship initiative, effectively assisting South Africa to achieve Target 11. Aichi Target 20: The South African biodiversity tax incentives are a globally unique finance solution and are tailor made incentive for biodiversity protection and management and aid South Africa to achieve Target 20. National Targets for protected areas: The South African biodiversity tax incentives promote and support the declaration of protected areas on private and communal land through the national biodiversity stewardship initiative, effectively assisting South Africa to reach its national protected area expansion targets encased in the National Protected Area Expansion Strategy which references biodiversity tax incentives as part of this strategy. National Targets for the creation of environmental incentives: The South African biodiversity tax incentives are one of the country’s most innovative and effective environmental incentives that are dedicated to protecting and managing biodiversity and ecological infrastructure, effectively assisting South Africa to achieve the creation of legitimate environmental incentives. (For national targets refer to the NDP, NBF, NBSAP, NPAES, and Biodiversity Finance Plan). |
| Implementing / Strategic partners (if other than UNDP) | Wilderness Foundation Africa’s Innovative Finance Division (hosts the institutional knowledge to the biodiversity tax incentives), Department of Environment, Forestry and Fisheries, South African National Biodiversity Institute, National Treasury and SARS. |
| Start and End Date | 2020-2022 |

Categorization

| Solution Category/ies from the BIOFIN Catalogue | Protected Areas/ Fiscal Incentives |
| --- | --- |
| Relevant Finance Result(s) | 1) Mobilizing Resources 2) Financial Sustainability 4) Preventing future costs |
| Estimated Finance Result | The value of section 37D is currently addressing South Africa’s BIOFIN gap by approximately 8.8 per cent and is estimated to contribute R1.4 billion by 2026. These estimates have already been exceeded, e.g.: 2019 estimated contribution of R75 million is over R100 million. The values of individual tax incentives vary across landscapes depending on the size and activities of the protected area but can be numerically quantified with ease and are recorded by SARS. The resultant biodiversity and economic outcomes can also be tracked over time but take slightly more effort to quantify. It is anticipated that amending section 37C to create a new effective incentive will increase the overall contribution to the BIOFIN gap through fiscal incentives to approximately 22 per cent (as based on the technical structuring investigations detailed above). |
| Finance Source | Public/Private national |
| Sector | Public and private |
| Instrument Type | Tax |

Note: if Private sector please check due diligence requirements / guidelines at this LINK

| Budget (USD) |  |  |
| --- | --- | --- |
| Total resources required: | USD 140 000 |  |
| Total resources allocated: |  |  |
|  | BIOFIN | USD 140 000 |
|  | Donor 1: | - |
|  | Donor 2: | - |
|  | Government of South Africa | Staff time |
|  | In-Kind |  |
| Unfunded: |  | 0 |

| Main Proposal and approach |  |
| --- | --- |
| - Background (100 words max) | The South African Government, through the National Treasury, has provided fiscal incentives in the form of biodiversity tax incentives (section 37D and C of the ITA) for taxpayers declaring protected areas on private and communal land. These agreements, made voluntarily, result in management expenses as well as loss of economic rights and use. Section 37C represents the original incentive introduced into legislation as of 8 January 2009. It remains defunct due to its poor technical tax structuring, misinterpretation by local branches of the South African Revenue Services (SARS), and inability to provide a tangible benefit to taxpayers. Section 37D is a new tax incentive available as of 1 March 2015. It is being accessed by taxpayers and answering a deliberate financial need for protected areas. It represents the successful process of amending the legislation, addressing tax appropriation with SARS, testing at pilot sites, and eventual mainstreaming. The feasibility of the biodiversity tax incentives has been thoroughly tested through the work conducted by niche tax expert, Candice Stevens (refer to the Fiscal Benefits Project). This work resulted in the implementation of the new and effective tax benefit, section 37D. This work also showed why the original tax incentive, section 37C, failed and what would need to be corrected for it to achieve its original policy mandate and provide financial benefits. Within this scope of work, preliminary investigations regarding possible tax structuring to address legislative amendments to section 37C and discussions with National Treasury were concluded in 2018, resulting in an official Annexure C Submission. The biodiversity tax incentives effectively enhance the financial effectiveness of South Africa’s protected areas and their compatible commercial activities and aid in sustainable biodiversity and ecosystem management. This is essential to the longevity of these areas and the creation of broader Biodiversity Economy livelihoods, the effective growth of small, medium and micro enterprises (SMMEs) and commercial operations linked to the Wildlife Economy. They also increase the protected area estate and area under responsible land management. Non-state investment in establishing and managing protected areas requires a suite of sustainable finance tools to mitigate management costs, offset loss of production income, increase land under protection, and ensure effective growth of enterprises engaged in the biodiversity economy. |
| - Objective(s) and Results expected: (100 words max) | The implementation of this finance solution aims to create a new tax incentive for the deduction of expenses related to the management of protected areas where the costs are born by private and communal landowners. It should be noted that South African protected area legislation (NEMPAA) requires a management plan to be complied and signed off by the MEC of the relevant province for each protected area that is declared. These management plans detail the management activities required to be undertaken by the owner of the protected area and create the burden of cost for the management of protected areas. This finance solution proposes to amend the current and defunct section 37C with the creation a new tax incentive to address the management costs incurred for protected areas. By doing so, the cost burden to citizens is reduced, the protected area management costs become financially sustainable, and the protected area status and quality of biodiversity and ecological infrastructure are improved. The financial benefits of these biodiversity tax incentives include: (1) ability of the landowners to offset land costs, through the effective use of section 37D as described above ,and to also allow for landowners to deduct all expenses relating to the management of non-state protected areas per NEMPAA required management plans. Landowners declaring protected areas bear the burden of cost to implement all management activities specific to the protected area they elected to declare. These costs can be substantial in nature and are currently unsupported. If section 37C were amended successfully, landowners may recover these costs and more effectively manage the protected areas they steward and not be placed under unnecessary financial strain in doing so, (2) reduced total costs of acquisition and management of new protected areas for government, (3) low cost incentive scheme with minimal transaction costs for government, (4) increased economic viability of landowner entities. This, in turn, will support the establishment and long-term management of non-state protected areas, an important component of South Africa’s protected area expansion strategy. It also addresses the policy imperative of creating positive incentives for environmental efforts. |
| - Business case (Approx 150 words) | The uptake and application of the income tax-based incentives has historically failed to be achieved even though provisions exist in the ITA. The original legislation was amended in 2015 in a bid to make the incentives more favourable and accessible. This included allowing landowners to claim the purchase value of a qualifying protected area as a straight-line deduction against income over 25 years (i.e. 4% of the value can be claimed as a deduction each year). It is envisaged that this process can be replicated to create an additional biodiversity tax incentive by amending the last component of the defunct historical tax incentive. The effect of this specific amendment would be to remove the cost burden currently placed on private and communal landowners to manage protected areas and effect legally required management plans. The amendment would create a dedicated deduction for protected area management costs which would allow protected areas to be managed more sustainably and effectively in the long term. This has benefits for reducing the financial strain on landowners as well as improving the status and quality of biodiversity conservation and ecological infrastructure management. Additional benefits include: - A beneficial tax system provides a unique finance model able to leverage public funding as well as critical private investment, by stimulating landowner input into PAs and ensuring that their input endures over the medium to long term. - National Treasury and SARS have demonstrated a willingness to continue to engage in improving and implementing an effective tax benefit system. |
| - Structure of the Finance Solution (100 words approx.) | This finance solution will involve the application of tax incentives for land set aside for conservation. As the provision has not been applied previously, there is a need to enhance the legislation and build awareness to apply the provision. In implementing this finance solution, National Treasury and SARS will be involved. The following steps are outlined: 1) introduce other biodiversity tax incentives into national legislation, with the primary aim of amending existing legislation to allow for a technical tax structure that will provide an income tax deduction related to the conservation management expenses incurred by private and communal landowners for the effective and long term management of protected areas; 2) test the proposed new incentive at selected pilot sites to ensure that the restructured tax amendment provides privately and communally owned protected areas with a legitimate financial benefit that addresses the costs they are incurring to fulfil their management plans; 3) further increase the national and international up-scaling and mainstreaming of this finance solution, and 4) enhance communication systems to produce continuous improvement in the biodiversity tax benefit package. |
| - Description of Activities (150 words max) | Amendment of section 37C: 2020 - Engage with and collaborate with National Treasury for potential enhancements and further amendments to legislation; - Maintain regular communication with National Treasury; - Annexure C Submission re-instigated or repeated if necessary; - Advance and finalise the development of technical tax structures; - Convene high level technical workshop with key experts to discuss technical structuring and implications on the ground; - Negotiate technical structuring of newly proposed tax incentive; - Engage in legislative amendment process; - Communicate implications to broader community of practice. 2021 - Repeat steps 1 through 7 should National Treasury not agree to amend the ITA in 2020; - Should steps 1 through 8 prove successful in 2020 then the following activities are outlined: - Identify pilot sites to begin testing new incentive; - Begin engagement with SARS to ensure corresponding appropriation processes for new policy and legislation; - Aim to process taxpayer returns with new incentive. 2022 - Repeat steps 1 through 8 (2019) should National Treasury not agree to amend the Income Tax Act in 2020; - Repeat steps 2 through 5 (2020) if necessary. Investigation into other potential tax incentives for area-based conservation and management: Jan 2020 – June 2021 - Maintain investigations and research into possible new tax incentives throughout the project period; - Determine National Treasury’s willingness to explore further tax benefits over and above section 37C and D; Develop possible technical incentives structures should an opportunity arise. |
| - Institutional Arrangements (100 words max) | Implementation of the solution should be led by a niche technical tax specialist with expertise in this area of work, noting the critical integration of tax incentives and protected areas. It should be noted that the availability of this niche skill set, and experience is limited. DEFF – Institutional support regarding intergovernmental processes; policy advice and support. National Treasury and SARS to provide enabling mechanisms. SANBI - Institutional support regarding intergovernmental processes; engagement with the broader biodiversity stewardship community of practice. National Biodiversity Stewardship Technical Working Group – engagement with broader community of practice. |
| - Main risks and management response for solution implementation (100 words max) | The main risks are listed in point form below with the corresponding management response detailed under each point: - Lack of correct institutional support from DEFF; - Allocation of dedicated DEFF representative with sufficient institutional knowledge to support the finance solution with legitimate institutional support; - Dedicated representative to engage with implementing/ strategic partners to ensure avoidance of duplication of effort or any miscommunication of information and incorrect technical tax information given to National Treasury. - Incorrect technical structuring and technical analysis; - Technical tax expert appointed to undertake the technical structuring and analysis of the finance solution, noting the unique and niche nature of the tax work required to create a legitimate finance solution for the management expenses related to non-state protected areas; - Niche tax skills in incentives is required as well as a firm understanding of the appropriate environmental legislation and biodiversity stewardship processes and community of practice as the technical aspects overlap. - Lack of buy-in or agreement by National Treasury regarding policy and legislative structuring and amendments (noting that estimated loss to the fiscus is negligible due to the limited number of qualifying protected areas); or - Preparation of preliminary calculations of negligible loss to the fiscus to allay any concerns noted by National Treasury regarding the fiscus; - Preparation of preliminary calculations regarding the potential return on investment for National Treasury; - Preparation of technical tax amendments and possible incentive structures to be presented to National Treasury; - Build a case regarding the amendment and its benefits for presentation to National Treasury; - Technical expert and DEFF representative for institutional support align approach and attend meetings with National Treasury regularly to discuss all elements of the proposed amendment to the ITA. - By SARS regarding legal and tax interpretation and appropriation of tax incentives by taxpayers at local SARS branches; - Pilot amendments at selected sites to determine the practical approach to the incentive with taxpayers and communicate all practical implementation approaches, errors, areas of interpretation, etc. to SARS; - Assist with the development of tax learning. - Both tax policy and legislation and tax appropriation need to align; and - Ensure that the working context of the proposed amendment aligns with the proposed legal amendments by ensuring that technical information given on the tax structure and on the biodiversity stewardship process and protected area declarations by the technical expert are taken cognizance of; - Address the use of pilot sites. - If this framework is challenged, eroded or under resourced it will create a risk to the tax incentives. - See above for DEFF institutional support. |
| - Sustainability and institutionalization (100 words approx.) | The following exhibits the institutionalization and sustainability of the biodiversity tax incentives finance solution, they exist independently of the BIOFIN Project and beyond the life of the BIOFIN Project: - Legislative amendments, see section 37D of the ITA; - SARS Draft Interpretation Note on section 37D and C; - Official Annexure C Submissions submitted to National Treasury regarding the proposed amendments to section 37C; - Improved capacity within the broader area-based conservation community of practice including national and provincial government, NGOs and the private sector through workshops, training and information sessions; - Improved capacity to policy makers including national and provincial government through workshops, training and information sessions; - Improved capacity for tax practitioners, accountants and legal professionals through workshops, training and information sessions and the provision of tax materials and legal updates; - Tax materials have been extensively developed for both tax and legal professionals as well biodiversity stewardship implementers and landowners; - The tax incentives information, legal requirements and best practice approach has been documented and entrenched into national guidelines, including the National Biodiversity Stewardship Guidelines; - Incorporation of standard tax requirements and legal wording into biodiversity stewardship and protected area declaration documentation across the various provinces; - A National Biodiversity Tax Advisory Committee which was established to provide expert input and oversight regarding technical tax matters and biodiversity stewardship concerns; - The tax incentive finance solution also forms part of the National Legal Reference Group held by SANBI to ensure that the tax requirements and legal interpretation are encased in corresponding protected area legal processes. |
| - M&E (100 words approx.) | This Finance Solution will be monitored and evaluated by development of practice notes and tax training materials for biodiversity tax practitioners. Further to this by end of implementation it is the intention that Section 37 will be amended. |

| Indicator | Baseline | Target |
| --- | --- | --- |
| Amendment of section 37C | Defunct incentive and no financial mobilization for non-state protected area management. Preliminary work conducted by the Fiscal Benefits Project. No Amendment. | By 2021, the ITA will be amended to create a new effective biodiversity tax incentive. |
| Testing of new tax incentive at pilot sites (If target for 2021 successful) | (Amendment secured) No actual or empirical testing of the proposed new biodiversity tax incentive. | By 2022, a minimum of 7 pilot sites are selected to test the new tax incentive. This includes assisting in securing an additional 50 000 ha of protected area for the national protected area estate affording key priority areas for biodiversity with long term protection and management. |
| Appropriating the new tax incentive for management costs in a landowner’s tax return ((If target for 2021 successful and if all the required legal processes for the protected area declaration and management plan are completed accurately) | (Amendment secured) No financial benefit for the management costs incurred on non-state protected areas. | By the end of 2022, a minimum of one tax return is completed for a pilot site to appropriate the new tax incentive and receive the deduction for costs incurred to affect the required management plan. If this is successful it will allow for estimates to be determined regarding the contribution that this new incentive would make to plugging South Africa’s biodiversity finance gap. |

SECTION 2 – FOR APPROVED FINANCE SOLUTIONS ONLY

Please provide the following information which will be included in next Work plan/Budget revision (or use actual Work plan document):

| Action Plan and Budget |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome/s (Result/s): Reduced financial burden on private and communal protected areas due to improved income tax incentives |  |  |  |  |  | Timeframe |  |  |  |
| Output/s | Activities (example below) | Responsible actor/s | Funding source | Total Costs (USD) (detail by year in the AWP if FS approved) | Atlas. Budg. Code (For approved projects) | 2020 | 2021 | 2022 | … |
| Baseline: Defunct incentive and no financial mobilization for non-state protected area management. Preliminary work conducted by the Fiscal Benefits Project. Indicators: Amendment of section 37C Targets: By 2021, the ITA will be amended to create a new effective biodiversity tax incentive. | Preparatory activities |  |  |  |  |  |  |  |  |
|  | Technical investigations and technical structuring finalised. | BIOFIN PMU & DEFF | BIOFIN | 40 000 |  | X |  |  |  |
|  | Implementation |  |  |  |  |  |  |  |  |
|  | National Treasury’s agreement to amend the Income Tax Act regarding section 37C; Independent M&E | BIOFIN PMU & DEFF | BIOFIN | 20 000 |  | X |  |  |  |
|  | Annexure C Submission re-invigorated or repeated and Official comments and submissions regarding legislative changes; | BIOFIN PMU & DEFF | BIOFIN | 20 000 |  |  | X |  |  |
|  | Amendment placed into legislation: Draft Taxation Laws Amendment Bill and Taxation Laws Amendment Act. | BIOFIN PMU & DEFF | BIOFIN | 30 000 |  |  | X |  |  |
|  | National Biodiversity Tax Advisory Committee review and assistance of technical structuring, legislative amendments and contextual implications; | BIOFIN PMU & DEFF | BIOFIN | 10 000 |  |  |  | X |  |
|  | Validation |  |  |  |  |  |  |  |  |
|  | SARS tax return validation processes | BIOFIN PMU & DEFF | BIOFIN | 20 000 |  |  |  | X |  |
| TOTAL |  |  |  | 140 000 |  |  |  |  |  |

Annex 1: BIOFIN Prioritization Scoring and Screening Questions

| Questions | Indicative marks for scoring (1-5) | Score |
| --- | --- | --- |
| Is there a positive record of implementation? | 1= no, or limited records of success 3= successful pilots 5= yes, high potential of scalability | 5 |
| Will it generate, leverage, save, or realign a large volume of financial resources? | 1= minimal scale 2= <5 per cent of current expenditures / needs 3= 5-15 per cent of current expenditures / needs 4= >20 per cent of current expenditures / needs 5= game changer | 4 |
| Will financing sources be mobilized in a compatible timeline with needs? | 1 = no, the mobilization is not aligned with needs 3 = likelihood of being mobilized in alignment with needs 5 = yes, forthcoming and compatible schedules | 3 |
| Will financing sources be stable and predictable? | 1 = no, the source of revenue may be highly unstable and vulnerable to external factors 3 = likelihood of being reasonably stable and predictable source 5 = yes, very stable and predictable | 5 |
| Do the persons or entities paying have a willingness and ability to pay or invest? | 1 = no 3 = possibly 5 = yes | 3 |
| Are the financial risks adequately managed (e.g. exchange rate, lack of investors, etc.)? | 1 = no, high risks remain 3 = moderate risks 5 = yes, low residual risks | 3 |
| Are start-up costs onerous in comparison to the expected financial returns? | 1 = very costly (compared to returns) 3 = moderate (compared to returns) 5 = very low/minimal (compared to returns) | 5 |
| Does the solution improve incentives to manage biodiversity and ecosystems sustainably? (see Chapter 1). | 1 = not clear 3 = likely 5 = most certainly | 5 |
| Will the financial resources remain targeted to biodiversity over time? | 1 = not clear, high risk of misallocation 3 = likely, administrative provisions 5 = yes, strong legal provisions | 5 |
| Are risks to biodiversity (e.g. disrespect of mitigation hierarchy) low or easily mitigated? How challenging would it be to develop safeguards? | 1 = high risks, no easy mitigation 3 = reasonable risks, mitigation possible 5 = low risks, easy safeguards | 5 |
| Will there be a positive social and economic impact (e.g. jobs, poverty reduction and cultural)? | 1 = no 3 = moderate 5 = strong positive impact | 3 |
| Would there be a positive impact on gender equality, especially regarding participation in design and implementation or access to opportunities and benefits? | 1 = no 3 = moderate 5 = strong positive impact | 3 |
| Have risks of significant unintended negative social consequences been anticipated and managed? | 1 = no, high risks remain 3 = moderate and manageable 5 = yes, minimal residual risks | 3 |
| Will it be viewed as equitable and will there be fair access to the financial and biodiversity/ecosystem resources? | 1 = no, risk of inequitable outcome 3 = maybe 5 = yes | 3 |
| Is it backed by political will? | 1 = no, resistance from key stakeholders 3 = maybe 5 = yes, with public statements in support | 5 |
| Have political risks been anticipated and managed? | 1 = no, high risks remain 3 = moderate and manageable 5 = yes, minimal residual risks | 3 |
| Is buy-in among stakeholders (i.e. potential investors/ decision makers, implementers, and beneficiaries) sufficiently strong to counter potential opposition? | 1 = no 3 = partial buy-in 5 = yes, strong buy-in | 5 |
| Do the managing actor(s) have sufficient capacity? Can they rapidly acquire it? | 1 = no, severe capacity gap 3 = moderate capacity gap 5 = yes, strong capacity | 5 |
| Is it legally feasible? How challenging will any legal requirements be? | 1 = no, new law is required 3 = new regulations required 5 = yes, new regulations are not needed | 3 |
| Is it coherent with the institutional architecture, can synergies be achieved? | 1 = no, limited or no synergies / coherence 3 = potential synergies 5 = yes, fully coherent / large synergies | 4 or 5 |

BIOFIN Proposal Template

Design and Implementation of Finance Solutions - Output 5

Country: South Africa 				 Submission date: 06/03/2020

Contact person: Pamela Kershaw   		Email Address: pkershaw@environment.gov.za

SECTION 1 – FOR PROPOSED FINANCE SOLUTIONS

☐ Feasibility stage (If the solution is in the preparatory stage less details will be expected. Only the white sections in the table must be filled, the grey sections will be filled at the next stage).

☒ Full implementation stage (If the solution enters in the full implementation stage, more details are expected. The white and the grey sections must be filled with as many details as possible)

| Proposal Summary |  |
| --- | --- |
| Title of the Finance Solution | Improved biodiversity offsets modality for protected area expansion |
| Concise Description (abstract) | Biodiversity offsetting is the final option in the mitigation hierarchy but remains one of the least utilised mitigation options for various reasons. Weak guidance and implementation experience result in high transaction costs and politically unpalatable delays to key infrastructure developments. As a result, biodiversity offsetting has been implemented in a relatively ad-hoc manner, reducing the opportunities for effective PA expansion and cost shifting to infrastructure developers. An effective enabling environment for implementing biodiversity offsets required from DEFF-authorised infrastructure developments will leverage funding for additional biodiversity conservation and management interventions. Proactive identification and setting aside of “offset-receiving areas” (also called ‘banks’) through careful deployment of NGO and private impact investment will be calibrated to the anticipated offset requirements for renewable energy development and large infrastructure projects. The set asides can be achieved through outright acquisition of land, ‘revolving property purchases’ or payments for biodiversity stewardship by contractual agreement. This finance solution builds on the finalisation of the National Biodiversity Offsets Policy and associated biodiversity offsetting guidelines and aims to design and pilot effective implementation modalities for biodiversity offsets across the country. |
| Contribution to SDGs | The primary contributions will be to SDGs 6, 13, 15 and 17. Biodiversity offsets can secure key water source areas from inappropriate development and improve their management and ecological functioning (SDG 6). By focusing explicitly on securing ecological corridors and ecosystem services, effective biodiversity offsets would underpin climate adaptation (SDG13). Through biodiversity stewardship (as the principal tool through which protected area expansion has occurred in South Africa) and engagement of NGO partners and investors in offset banks, biodiversity offsets contribute to towards achieving SDGs 15 and 17. |
| Contribution to Aichi Targets / National Targets / Biodiversity Finance Plan | Biodiversity offsets would contribute to Aichi Target 11 of at least 17 per cent of terrestrial and inland water areas and 10 per cent of coastal areas. Numerous cases in which biodiversity offsets have been written into conditions of a proposed development project’s Environmental Authorization, have been secured as a Protected Area in terms of the National Protected Areas Act (NEMPAA). It is estimated that offsets have secured around 100 000ha for protection in SA towards national targets set for national Protected Area expansion. The National Development Plan calls for a streamlined biodiversity offsets regime to mitigate biodiversity loss and the ecological deficit being potentially exacerbated by infrastructure development. The opportunities around biodiversity offsets (in ha and finance contributions) were set out in the BFP. |
| Implementing / Strategic partners (if other than UNDP) | DEFF (regulatory and administrative functions), SANParks (pilot implementation, GIS), WWF-SA (Pilot implementation, Conservation Outcomes (pilot implementation); Wilderness Foundation Africa (Pilot implementation); SANBI (Program management, GIS and support). |
| Start and End Date | 2020 –2022 |

Categorization

| Solution Category/ies from the BIOFIN Catalogue | Protected areas; Biobanking; Conservation Easements; Impact investment |
| --- | --- |
| Relevant Finance Result(s) | Delivering Better and Generate Resources |
| Estimated Finance Result | R15 million (US$1 million) per annum |
| Finance Source | Public/ private |
| Sector | Protected Areas, Conservation and Biodiversity, Energy, Transport |
| Instrument Type | Regulatory and Market |

Note: if Private sector please check due diligence requirements / guidelines at this LINK

| Budget (USD) |  |  |
| --- | --- | --- |
| Total resources required: | USD 190 000 |  |
| Total resources allocated: |  |  |
|  | BIOFIN | USD 190 000 |
|  | Donor 1: SANBI & SANParks | USD 10 000 & USD20 000 |
|  | Donor 2: DEFF | USD 20 000 |
|  | Government of South Africa | USD |
|  | In-Kind | Staff time |
| Unfunded: |  | - |

| Main Proposal and approach |  |
| --- | --- |
| - Background | In South Africa, biodiversity offsets may be a means of financing a net increase in the protected area estate and a net gain in ecosystem functioning. The efficient and effective implementation of the Biodiversity Offset Policy should counterbalance biodiversity loss in unprotected landscapes through increased formal protection and effective management of biodiversity. Certain types of development (such as renewable energy, and large or cross-province infrastructure) require intricate regulatory and financing approvals – which can be jeopardised if biodiversity impact mitigation measures are not adequately managed. By using a combination of biodiversity offset banking approaches (possibly funded by NGOs and impact investment) and requiring reinvestment of returns in PA expansion and management costs, a pro-active ready-made offset mechanism is provided. This will provide mitigation measure assurance for regulators and financiers. |
| - Objective(s) and Results expected: | - Establish offset receiving areas or “banks” for expected developments (such as the Renewable Energy Development Zones and key infrastructure corridors) – target of 50 000ha. - Establish the DEFF regulatory protocols in the Integrated Environmental Management (IEM) branch for crafting appropriate offset conditions of authorisation and streamlining implementation opportunities. - Assist NGOs to pursue a proactive offset approach or formal bank around targeted PAs. (WWF-SA, Wilderness Foundation have indicated interest in establishing and managing banks, sourcing impact investments and revolving funds if required). - Secure investments in the offset banks from liability holders, including the costs of ongoing management for 30 years post commencement. - At the end of three years have three offset banks established around various protected areas totalling 50 000ha. |
| Business case | Experience with offsets for large infrastructure and renewable energy projects indicates that post-EIA and offset study, implementation arrangements can take over 5 years to be resolved (e.g. SANRAL for the N2 Wild Coast Highway, TCTA for the Springgrove dam) incurring significant transaction costs and risks for biodiversity outcomes and often under-estimate costs of offset establishment and/or management. Cases where proactive offsets have been pursued are rare in SA, but some examples in the Northern Cape (Kangnas and Khoeris WEFs) point to offsets being expedited within months of final regulatory approval if proactively secured, with benefits to both developers and biodiversity outcomes. In some areas, existing NGO land acquisition budgets could be used to secure (through stewardship type contractual agreement or outright acquisition) land for offsets, and the funds then recovered from offset liability holders and reinvested in the bank or other under-protected ecosystem. |
| Structure of the Finance Solution | The state regulator sets up a streamlined mechanism for meeting offset liability. NGOs and potentially private investors establish offset banks around key PAs in ecosystems where DEFF authorized development is likely to happen. The offset banks would usually be in PA expansion zones and be contracted in or purchased. Once the EIA process for a development is underway, estimation of impacts and required offsets for biodiversity components would be matched with appropriate offset banks. An offset agreement would be concluded with an offset bank to match specific requirements and set out funding flows. The offset parameters are captured in the register and those portions would be retired from the offset bank. |
| - Description of Activities (150 words max) | - Capture lessons from previous biodiversity offsets consolidated in PAs to inform good implementation and financial practice. - Train DEFF staff in effective biodiversity offset condition-setting as part of the environmental authorisation process, to streamline implementation and promote the use of offset banks where appropriate. - Extend the offsets register and make it interoperable with Environmental Authorisation tracking systems. - Interrogate appropriate financial mechanisms to guarantee offset payment - Identify key offset receiving areas for potential offset banks, using infrastructure location as well as biodiversity exchange rules for guidance. (Build on the Northern Cape pilot work by Wilderness Foundation for DENC) - Assess specific properties to determine whether they could be contractually incorporated or bought for the offset banks. NGOs secure acceptable candidate sites. Undertake basic required rehabilitation and protection. - Market offset sites to various developers likely to have offset requirements emerge during EIA processes. - Conclude agreements between offset banks and liability holders to “retire” the relevant offset credits, and facilitate finance to the banks (to reimburse establishment costs) and PA management authorities (for long term management responsibility) - Reinvest a portion of the reimbursed establishment costs to extend the offset bank or initiate a new one. |
| - Institutional Arrangements | The South African National Biodiversity Institute (SANBI) is well placed to manage this FS given their impartiality, interest and history with Biodiversity Offset policy development. DEFF, participating NGOs, SANBI, SANParks and other participating Protected Area management authorities would form a project committee. DEFF would manage the process of finalizing outstanding policy requirements (if any) and establishing the protocols for offset implementation as part of the environmental authorization process. SANBI and SANParks would finalize the technical and spatial component of the offset banks, in conjunction with participating NGOs. The latter would secure key parts of the bank through stewardship, contractual park agreements or outright acquisition. NGOs would also play an interim role in managing the offset banks and marketing the biodiversity values that are available to any developers with current or potential future offset liabilities. SANParks and other PA management authorities would take over long term management of the offset areas, using funds from the developers dedicated for that purpose. The NGOs would be required to reinvest a portion of any land protection costs reimbursed by developers into further offset banks or PA expansion. |
| - Main risks and management response for solution implementation | - Banking may be facilitating inappropriate developments which would otherwise not be permitted. Response – DEFF must maintain the criteria around impacts which are not offsetable or otherwise unacceptable. All actors, especially NGOs, must be free to object to or appeal development approvals they feel inappropriate regardless of their role in offset banking. - Reluctance and institutional inertia among state PA management authorities to take on additional land for PAs. Response – Implementation policies will be developed with SANParks and provincial conservation agencies with appropriate risk management. - Land holding costs of land for PAs in SA can sometimes be considerable. In some cases, the marginal costs of expanding a PA can be managed, but in cases where NGOs are managing offset banks this can be a threat to financial viability. Response - the Property Rates FS incorporated in this BIOFIN Strategy will enable offset banks to operate free from Property Rates. Much of the initial rehabilitation and protection funds could be sourced from the Environmental Programmes branch in DEFF or from Impact Investment, to be reimbursed by offset holders. The Tax incentives FS incorporated in this BIOFIN Strategy should make all the costs associated with purchase and management tax deductible. - Lack of uptake of offset banks by regulators and/or development applicants. Response – initially this will be piloted for the developments authorised by DEFF, which manages this risk. - Stewardship type approaches have not been properly tested for offset banks. Response – Where stewardship agreements are not likely to be durable, acquisition and revolving land trust options can be deployed instead. - Department of Mineral Resources may impede the establishment of offset banks or frustrate declaration of new protected areas. Response - Appropriate engagement at the various cooperative governance forums by DEFF and SANParks will assist with this, as will an indication that this process may reduce environmental resistance to mineral developments provided pre-emptive mitigation is in place. |
| - Sustainability and institutionalization | If the offset banks prove workable, the revolving nature of the funds would suggest that additional offset banks would be established in areas of demand and under-protected ecosystems. The protocols or approaches developed by DEFF IEM could easily be replicated or built on by the nine provincial Competent Environmental Authorities and the Dept. Mineral Resources (which issues authorisations for mineral related developments). This finance solution also includes training of DEFF staff in effective biodiversity offset condition-setting. |
| - M&E (100 words max) | The existence of the Offset Register in DEFF would be a key mechanism to monitor effectiveness of the Finance Solution. The number of ha “retired’” from offset banks to discharge developer’s liabilities is the primary monitoring outcome. Evaluation can be gauged by the contribution of these ha towards the country’s PA expansion targets. The quantum of annual (re) investment in offset banks would indicate the effectiveness of this solution. A Key Performance Indicator for this solution would be that a developer’s mitigation/offset liability is effectively concluded within 12 months of final regulatory approval being issued. |

| Indicator | Baseline | Target |
| --- | --- | --- |
| An offset bank in place where DEFF authorized development is likely to occur | No bank | An offset bank type system in place around 3 protected areas, totaling 50 000 ha by end 2022 |
| Annual funding flow to offset bank | Zero | R15 million per annum flows to offset bank management authorities by end 2023 |
| Protocol for facilitating development through proactive offsets | None exists | A protocol is in place by 2020 |
| Offsets register developed and maintained in DEFF for monitoring offset bank performance and verifying compliance with Environmental Authorisations | A preliminary register last updated in 2016 by SANBI. | An up to date (i.e. 30 days lag time from issuance of Environmental Authorisations) offset register exists as part of the IEM tracking systems for development authorisations, in place by 2021. |

SECTION 2 – FOR APPROVED FINANCE SOLUTIONS ONLY

Please provide the following information which will be included in next Work plan/Budget revision (or use actual Work plan document):

| Action Plan and Budget |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome/s (Result/s): A net gain in biodiversity protection through an improved modality for implementing biodiversity offsets |  |  |  |  |  | Timeframe |  |  |
| Output/s | Activities (example below) | Responsible actor/s | Funding source | Total Costs (USD) (detail by year in the AWP if FS approved) | Atlas. Budg. Code (For approved projects) | 2020 | 2021 | 2022 |
| Baseline: No offset bank in place Indicators: An offset bank in place where DEFF authorized development is likely to occur Targets: An offset bank type system in place around 3 protected areas, totaling 50 000 ha by 2022 | Preparatory activities: |  |  |  |  |  |  |  |
|  | Capture lessons from previous biodiversity offsets consolidated in PAs to inform good implementation and financial practice. | BIOFIN PMU with SANBI | BIOFIN | 15 000 |  | X |  |  |
|  | Develop guideline for setting conditions of Authorisation for offsets. | BIOFIN PMU with SANBI | BIOFIN | 10 000 |  | X |  |  |
|  | Train DEFF, Provincial conservation management agencies & SANParks staff in effective biodiversity offset condition-setting as part of the environmental authorisations process, to streamline implementation and promote the use of offset banks where appropriate. | BIOFIN PMU with SANBI | BIOFIN | 10 000 |  | X | X |  |
|  | Ensure effective offset triggers and guidance in relevant IEM tools, EMPrs, standards & Screening | BIOFIN PMU with SANBI | BIOFIN | 10 000 |  | X |  |  |
|  | Extend the offsets register and make it interoperable with Environmental Authorisation tracking systems. | BIOFIN PMU with SANBI | BIOFIN | 10 000 |  |  | X |  |
|  | Interrogate appropriate financial mechanisms to guarantee offset payment to management authorities or offset banks over life of liability (min 30 years). | BIOFIN PMU with SANBI | BIOFIN | 30 000 |  |  | X | X |
|  | Identify key offset receiving areas for potential offset banks, using infrastructure location as well as biodiversity exchange rules for guidance. | BIOFIN PMU with SANBI | BIOFIN | 15 000 | X | X |  |  |
|  | Assess specific properties to determine whether they could be contractually incorporated or bought for the offset banks. NGOs secure acceptable candidate sites. Undertake basic required rehabilitation and protection. | BIOFIN PMU with SANBI | BIOFIN | 30 000 | X | X |  |  |
|  | Undertake preliminary work to prepare for declaration & management plan development. | BIOFIN PMU with SANBI | BIOFIN | 24 000 |  | X | X |  |
|  | Market offset sites to various developers likely to have offset requirements emerge during EIA processes. | BIOFIN PMU with SANBI | BIOFIN | 6 000 |  |  | X | X |
|  | Conclude agreements between offset banks and liability holders to “retire” the relevant offset credits and facilitate finance to the banks (to reimburse establishment costs) and PA management authorities (for long term management responsibility). | BIOFIN PMU with SANBI | BIOFIN | 30 000 |  |  |  | X |
| TOTAL |  |  |  | 190 000 |  |  |  |  |

Annex 1: BIOFIN Prioritization Scoring and Screening Questions

| Questions | Indicative marks for scoring (1-5) | Score |
| --- | --- | --- |
| Is there a positive record of implementation? | 1= no, or limited records of success 3= successful pilots 5= yes, high potential of scalability | 3 |
| Will it generate, leverage, save, or realign a large volume of financial resources? | 1= minimal scale 2= <5 per cent of current expenditures / needs 3= 5-15 per cent of current expenditures / needs 4= >20 per cent of current expenditures / needs 5= game changer | 3-4 |
| Will financing sources be mobilized in a compatible timeline with needs? | 1 = no, the mobilization is not aligned with needs 3 = likelihood of being mobilized in alignment with needs 5 = yes, forthcoming and compatible schedules | 5 |
| Will financing sources be stable and predictable? | 1 = no, the source of revenue may be highly unstable and vulnerable to external factors 3 = likelihood of being reasonably stable and predictable source 5 = yes, very stable and predictable | 2 |
| Do the persons or entities paying have a willingness and ability to pay or invest? | 1 = no 3 = possibly 5 = yes | 5 |
| Are the financial risks adequately managed (e.g. exchange rate, lack of investors, etc.)? | 1 = no, high risks remain 3 = moderate risks 5 = yes, low residual risks | 3 |
| Are start-up costs onerous in comparison to the expected financial returns? | 1 = very costly (compared to returns) 3 = moderate (compared to returns) 5 = very low/minimal (compared to returns) | 2 |
| Does the solution improve incentives to manage biodiversity and ecosystems sustainably? (see Chapter 1). | 1 = not clear 3 = likely 5 = most certainly | 5 |
| Will the financial resources remain targeted to biodiversity over time? | 1 = not clear, high risk of misallocation 3 = likely, administrative provisions 5 = yes, strong legal provisions | 5 |
| Are risks to biodiversity (e.g. disrespect of mitigation hierarchy) low or easily mitigated? How challenging would it be to develop safeguards? | 1 = high risks, no easy mitigation 3 = reasonable risks, mitigation possible 5 = low risks, easy safeguards | 5 |
| Will there be a positive social and economic impact (e.g. jobs, poverty reduction and cultural)? | 1 = no 3 = moderate 5 = strong positive impact | 3 |
| Would there be a positive impact on gender equality, especially regarding participation in design and implementation or access to opportunities and benefits? | 1 = no 3 = moderate 5 = strong positive impact | 2 |
| Have risks of significant unintended negative social consequences been anticipated and managed? | 1 = no, high risks remain 3 = moderate and manageable 5 = yes, minimal residual risks | 5 |
| Will it be viewed as equitable and will there be fair access to the financial and biodiversity/ecosystem resources? | 1 = no, risk of inequitable outcome 3 = maybe 5 = yes | 4 |
| Is it backed by political will? | 1 = no, resistance from key stakeholders 3 = maybe 5 = yes, with public statements in support | 3 |
| Have political risks been anticipated and managed? | 1 = no, high risks remain 3 = moderate and manageable 5 = yes, minimal residual risks | 3 |
| Is buy-in among stakeholders (i.e. potential investors/ decision makers, implementers, and beneficiaries) sufficiently strong to counter potential opposition? | 1 = no 3 = partial buy-in 5 = yes, strong buy-in | 4 |
| Do the managing actor(s) have sufficient capacity? Can they rapidly acquire it? | 1 = no, severe capacity gap 3 = moderate capacity gap 5 = yes, strong capacity | 3 |
| Is it legally feasible? How challenging will any legal requirements be? | 1 = no, new law is required 3 = new regulations required 5 = yes, new regulations are not needed | 4 |
| Is it coherent with the institutional architecture, can synergies be achieved? | 1 = no, limited or no synergies / coherence 3 = potential synergies 5 = yes, fully coherent / large synergies | 3 |

late

Design and Implementation of Finance Solutions - Output 5

BIOFIN Proposal Template

Design and Implementation of Finance Solutions

Country: South Africa 			 	Submission date: 06/03/2020

Contact person: Roland Vorwerk	     		Email Address: rvorwerk@environment.gov.za

SECTION 1 – FOR PROPOSED FINANCE SOLUTIONS

| Proposal Summary |  |
| --- | --- |
| Title of the Finance Solution | Development and implementation of a voluntary market-based certification scheme in the wildlife sector |
| Concise Description (abstract) | The exceptional biodiversity of South Africa provides a wide range of benefits to the country’s economy, society and human wellbeing. The sustained benefit flows that nature provides is dependent on functioning ecosystems, healthy species populations and genetic diversity. The South African Constitution enshrines the right to secure ecologically sustainable development and the use of natural resources while promoting economic and social development. Sustainable use of biodiversity resources is further articulated in the Biodiversity Economy Strategy and in key Multilateral Environmental Agreements such as the Convention on Biological Diversity (CBD), the International Union for the Conservation of Nature’s (IUCN) World Conservation Strategy and the Convention on International Trade in Endangered Species (CITES). Increased investment in effectively managing, conserving and sustainably utilizing biodiversity by the public and private sector in South Africa has led to 13,2% (14,9m hectares) of South Africa being under conservation (including formally protected areas) and approximately 9,000 privately owned game ranches accounting for a further 17,7% (20m hectares) of the country. Significant tracts of pristine land under the custodianship of communities, land reform beneficiaries and new entrants to the sector could make a further substantial contribution to these amounts. There is a significant opportunity for the sector to yield inclusive rural economic growth and the creation of new biodiversity-related jobs and enterprises. The wildlife economy is a complex and multi-faceted commercial sector that includes a combination of agriculture, ecotourism and conservation activities. The primary objective of the wildlife ranching sector is to run profitable enterprises that encompass four broad types of activities, these being the animal husbandry of game animals (breeding and live sales), hunting, game products (including game meat production) and ecotourism. Wildlife ranches are managed along a continuum from intensive to extensive systems, providing different environmental benefits depending on their management objectives. The proposed voluntary market-based certification scheme for the wildlife industry will provide a verifiable mechanism to accurately quantify and evaluate the sector’s contribution to biodiversity conservation and sustainable development. The scheme is envisaged to be based on sustainability standards that are developed jointly through extensive consultation between government departments with different mandates, the established private sector, new entrants such as communities and emerging game ranchers, research institutions and civil society. The scheme will seek to ensure that the objectives of economic growth, transformation and sustainability are met and thereby create an evidence-based framework to evaluate the sector’s performance across the triple bottom line of environment (with a primary focus on contribution to biodiversity conservation), financial and social measures to create greater business value. A literature review and feasibility study on the development of a market-based certification scheme in the South African wildlife sector was commissioned under Phase 1 implementation of BIOFIN. This study was guided by a multi-sector working group comprising representation from the wildlife ranching industry, the public sector and civil society. The findings and recommended steps outlined in this study (outlined further under the Project Background below) and a number of further engagements with various stakeholders and access to additional information and literature sources have informed the development of this Finance Solution. |
| Contribution to SDGs | SDG 3 – Good Health and Well-being SDG 8 – Decent Work and Economic Growth SDG 12 – Responsible Consumption and Production SDG 15 – Life on Land: Protect, restore and promote sustainable use of terrestrial ecosystems, sustainably manage forests, combat desertification and halt and reverse land degradation and halt biodiversity loss |
| Contribution to Aichi Targets / National Targets / Biodiversity Finance Plan | AICHI 7: By 2020 areas under agriculture, aquaculture and forestry are managed sustainably, ensuring conservation of biodiversity AICHI 11: Well-governed and effectively managed protected areas are a proven method for safeguarding both habitats and populations of species and for delivering important ecosystem services. NBSAP 1: Management of biodiversity assets and their contribution to the economy, rural development, job creation and social well-being is enhanced. |
| Implementing / Strategic partners (if other than UNDP) | Department of Environment, Forestry and Fisheries (DEFF), provincial protected area agencies and industry associations that are members of the Wildlife Forum. |
| Start and End Date | 2019-2022 |

Categorization

| Solution Category/ies from the BIOFIN Catalogue | Sustainability Standards and Certification |
| --- | --- |
| Relevant Finance Result(s) | 1) Mobilizing Resources 2) Delivering Better 3) Re-aligning existing resources 4) Preventing future costs. |
| Estimated Finance Result | Increased investment in effectively managing, conserving and sustainably utilizing biodiversity by the public and private sector in South Africa has led to 13,2% (14,9m hectares) of South Africa being under conservation (including formally protected areas) and approximately 9,000 privately owned game ranches accounting for a further 17,7% (20m hectares) of the country. Significant tracts of pristine land under the custodianship of communities, land reform beneficiaries and new entrants to the sector could make a further substantial contribution to these amounts. It is estimated that game ranchers owning 2 million hectares of land will be certified under the proposed sustainability scheme by December 2022. It is further estimated that 10% of this total would be assessed as OECMs, thereby contributing 200,000 hectares of privately or communally held land to the conservation estate. At the National Biodiversity Stewardship conference held in 2017, a presentation by Angus Burns from WWF indicated that the cost to purchase land (for Biodiversity Stewardship) was estimated at R9000 per hector, hence the 200,000 hectares indicated above equates to a total cost to purchase equaling R1, 8 billion. This does not include annual management costs of this estate. There is a significant opportunity for the sector to yield inclusive rural economic growth and the creation of new biodiversity-related jobs and enterprises, whilst effectively monitoring the biodiversity conservation contribution of the sector. |
| Finance Source | Public |
| Sector | Wildlife |
| Instrument Type | Market and regulatory. |

Note: if Private sector please check due diligence requirements / guidelines at this LINK

| Budget (USD) |  |  |
| --- | --- | --- |
| Total resources required: | USD 240 000 |  |
| Total resources allocated: |  |  |
|  | BIOFIN | USD 240,000 |
|  | Government of South Africa (DEFF, SANBI, DALRRD) In-kind | USD 165,000 |
|  | Wildlife Industry In-kind: (WRSA and other associations) | USD 50,000 |
|  | Civil Society In-kind: (EWT and other NGOs) | USD 40,000 |
| Unfunded: |  |  |

| Main Proposal and approach |  |
| --- | --- |
| - Background | South Africa has developed a Biodiversity Economy Strategy (BES) that serves as a guide for the sustainable growth of the wildlife economy, ecotourism and bioprospecting sectors. The BES provides a basis for addressing constraints for growth, ensuring sustainability, identifying clear stakeholder responsibilities, and monitoring progress of the enabling actions identified in the strategy. A key focus of the BES is on providing an enabling environment for communities and entrepreneurs to participate in the biodiversity economy, while contributing to poverty alleviation, sustainable development and conservation of the country’s biodiversity. South Africa’s wildlife sector has been growing consistently faster than the general economy for several years, contributing R3 billion to GDP in 2014 – almost double the contribution made by the sector in 2008. The Biodiversity Economy Strategy estimates that the sector’s GDP contribution could be R14 billion by 2030. The NBA 2018 estimates that the total biodiversity-related employment was 388,000 jobs, of which 70,000 were in the ‘conserving biodiversity’ category, and 318,000 from the ‘using biodiversity’ sector which is further broken down into 86,000 in non-consumptive use of biodiversity activities such as photographic tourism and 232,000 in the extractive use of biodiversity activities such as the game ranching and hunting (65,000), fisheries, trade in traditional medicines and indigenous tea production. The Wildlife Economy aspiration articulated under the Biodiversity Economy Phakisa in 2016 aims to create an inclusive, sustainable and responsive wildlife economy that grows at 10% p.a. until at least 2030, while providing a foundation for social well-being and maintaining the ecological resource base. The Biodiversity Economy Strategy, which unambiguously adopts a sustainable use of biodiversity principle, estimates that the sector’s GDP contribution could be R14 billion by 2030. As part of developing a national implementation plan for the BES, the Department of Environmental Affairs hosted the Biodiversity Economy Phakisa (a fast results delivery programme) in May 2016 to engage the wildlife sector in identifying the challenges and opportunities for sustainably growing the biodiversity economy of the country. The vision of a thriving, inclusive and sustainable wildlife economy for the well-being of all South Africans was formulated. Subsequently, several initiatives have been implemented to support the aspiration of an inclusive, sustainable and responsive wildlife economy that grows at 10% per annum until at least 2030, while providing a foundation for social well-being and maintaining the ecological resource base. Three broad objectives relating to facilitating transformation, driving economic growth and creating an enabling environment for the wildlife sector were identified. The development of a voluntary, market-driven certification scheme for the wildlife industry was identified as a viable intervention to recognize and harness the contribution of the wildlife ranching sector to the biodiversity economy as a primary objective and biodiversity conservation as a possible secondary outcome, while at the same time adequately mitigating reputational and ecological risks and reducing negative impacts on ecosystem services, thereby improving the industry’s image in a competitive international market. The sector contributes to biodiversity conservation in South Africa, but there is currently no objective mechanism to quantify this contribution. Wildlife ranches are managed along a continuum from intensive to extensive systems, providing different environmental benefits depending on their management objectives. Certification is a mechanism which indicates that certain standards have been met in a production system. It is a non-government, market-driven approach to incentivize environmentally sustainable practices, adequately mitigate risk or environmental impacts of production and optimize business operations and practices. Benefits could include aspects relating to easing the regulatory burden at the provincial and national levels with potential cost savings or operational efficiencies made possible through a fundamentally more cooperative approach between key parties. Given the reputational risk of trophy hunting and intensive breeding practices, certification may help to ‘re-brand’ sustainable use in South Africa and gain greater access to international markets. The certification scheme is envisaged to help improve the resilience of the sector while at the same time helping to secure biodiversity and ecosystem services as a global public good. Tailored extension services and mentorship programs could be designed to ensure emerging wildlife ranchers are supported to access the opportunities in the sector. Harnessing adaptive management, and continual improvement practices and industry-wide advocacy could lead to significantly increased biodiversity conservation outcomes on privately held land. Investment in restoring and maintaining ecological infrastructure should be approached as a long-term endeavor and should be an opportunity to create long-term employment and labor-intensive activities, many of which would be located outside major urban centers. A stakeholder workshop was held in November 2017 to provide an overview on current and relevant certification schemes and to establish a multi-sector working group to drive the development of the voluntary market-based certification scheme. There was broad consensus that the certification scheme should be informed by a base sustainability standard comprising environmental, social and economic indicators in addition to specific activity standards. Environmental standards are minimum requirements that ensure the sustainable use of resources and/or minimize negative impacts on the environment. Social/welfare standards ensure that treatment of people and/or animals is fair and humane. Economic standards ensure that the operational aspects of the enterprise are financially optimal. The following vision was developed by the working group: “To promote and demonstrate voluntary stakeholder contributions to the biodiversity economy through responsible and sustainable natural resource management for the benefit of the people of South Africa and the environment”. A literature review and feasibility study on the development of a market-based certification scheme in the South African wildlife sector was commissioned under Phase 1 implementation of BIOFIN. This study was guided by a multi-sector working group comprising representation from the wildlife ranching industry, the public sector and civil society. The literature review synthesized wildlife industry legislation, standards and best practice guidelines that have been developed pertaining to the industry. A broad overview of conservation and welfare issues in the wildlife industry was also provided. The regulatory role of provincial protected area agencies was outlined, and potential efficiencies and related aspects could be reimagined within a more cooperative approach to supporting and growing the industry, whilst still providing the necessary biodiversity conservation oversight as outlined in their mandate. A total of 13 sustainability standards and certifications (such as the Forest Stewardship Council, Marine Stewardship Council, Fair Trade Tourism and WWF Conservation Champions – formerly the Biodiversity Wine Initiative) in the broader agricultural and tourism sectors were reviewed with an elaboration on market response, producer benefits, environmental impacts, costs of certification and challenges associated with certification. Voluntary standard-based certification was shown to be an effective strategy to combine efficient and productive agricultural systems with biodiversity conservation. Furthermore, sustainability standards are considered effective if they result in improvements in social, environmental and economic practices. The cost of certification was shown to be largely dependent on the size of the enterprise, the level of stakeholder involvement and the auditing process attached to the certification scheme. Key conclusions of the literature review included the following: 1) for certification to be effective, standard criteria should be meaningful and measurable; 2) standards need to be rigorous enough to result in environmental change; 3) verification of changes in producer practices must be independently evaluated; 4) cost-effectiveness is important for widespread adoption; and 5) continuous improvement can be more effective than just setting a minimum standard. To determine the feasibility of a voluntary market-based certification scheme a choice experiment was conducted to determine respondents’ relative preferences for various attributes of voluntary certification. A total of 243 wildlife ranchers participated in the survey. The overall model indicated that under the most marketable scenario, potentially interested ranchers would require a 9% increase in income on average in order to participate in the scheme. Respondents who supported a certification scheme indicated that the principles of sustainable rangeland management and ensuring ethical hunting practices were overwhelmingly supported with substantially less support for principles relating to fencing, intensive breeding practices and predator control. Mistrust, the association of certification with industry regulation and insufficient reward were given as the main reasons among respondents who did not support certification. Another outcome of the Biodiversity Economy Phakisa in 2016 was to re-position the Wildlife Forum as an efficient interdepartmental/industry collaboration and coordination platform to unlock the sustainable use opportunities of the Wildlife Economy. Throughout 2018 and 2019 feedback on the progress of the literature review and feasibility study was provided to this forum. At the September 2019 Wildlife Forum meeting several principles were agreed to frame the next phase of engagement in the development of a voluntary market-driven wildlife industry certification scheme. These principles include: 1) the phase 1 literature review and feasibility report is a starting point for further engagements; 2) the ownership of the certification scheme will need to be determined in the next phase of its development; 3) the certification scheme should aim to support and enhance the sustainability of wildlife ranching operations and not be a barrier to entry for new entrants into the sector; 4) the base standard of the certification scheme should be based at the level of the game ranch, with a focus on custodianship practices of both land and species; 5) the scheme should focus on providing positive incentives to encourage increased uptake of sustainable practices; 6) the scheme should be voluntary, market-driven and not be used as a fund-raising mechanism by the public sector; 7) the wildlife ranching industry is primarily run on a similar basis to commercial agricultural enterprises and should not be expected to contribute to Aichi Target 11; and 8) the views of consumer groups should also be taken into account in the further development of the scheme. The base standard indicated under 4) above would be further complemented by separate activity standards, such as for hunting, game meat harvesting and other value chain activities in the wildlife industry. The development of the scheme would encourage more sustainable ecosystem management. Several initiatives related to the development of this certification scheme are underway. Conservation Outcomes, through an initiative funded by the Green Trust, has started work on developing a game meat harvesting protocol linked to the development of a brand for game meat that has been harvested from Protected Areas. WRSA has developed a suite of best practice guidelines that their members are required to comply with. Similarly, other associations have developed standards or guidelines for their respective activities within the broader wildlife economy. A project is being developed to establish what kind of game ranches, or portions thereof, could be considered candidate Conservation Areas (Other effective area-based Conservation Measures). It will be important to take these initiatives into account in the next development phase of the scheme. |
| - Objective(s) and Results expected: | Objective: To design and implement a sector-wide voluntary market-based certification scheme that is supported by key sector stakeholders and that incentivizes environmentally and socially sustainable practices and contributes to biodiversity conservation. The intention is for this system to be cost effective while maintaining a high standard, rewarding exemplary practices. It should be recognized by national and international markets, and ideally be an international benchmark for the sector. The key objectives of the proposed certification scheme would be to: - Increase the amount of land used in the wildlife sector; - Encourage sustainable practices in the wildlife sector, and increasing private wildlife ranchers’ contribution to biodiversity conservation (species and landscape level); - Provide a systematic means of improving industry reputation; and - Stimulate inclusive growth in the industry. Results expected: - Improved financial returns for wildlife ranchers through improved sustainable practices and greater access to benefits and markets. - Verifiable contribution to biodiversity conservation and harnessing of adaptive management principles at the enterprise level - Develop a finance mechanism for support of sustainable wildlife ranching and harnessing the private sector to support the recovery of threatened species or landscapes - Greater collaboration amongst all stakeholders at a local, regional and national level - Extension services institutionalized to mainstream sustainable wildlife ranching practices, especially for new entrants - Increased profile of the industry as an internationally recognised sustainable use advocate |
| - Business case (Approx 150 words) | Certification is carried out to provide assurance that standards in a system have been met and is usually accompanied by the right to mark products with an associated label. Through certification there is potential for producers to gain benefits in the form of increased income from higher prices, access to new markets and decreased administrative burdens. It is envisaged that the development of a certification scheme for the wildlife ranching sector in South Africa is guided by the Codes of Good Practice of ISEAL, which is a global membership organisation for credible sustainability standards. These codes include standard-setting, impact evaluation and assurance (certification and accreditation). A consumer demand study will be undertaken so that participating game ranches can better position themselves to take advantage of opportunities that emerge from such a study, and to refine strategies to consider further insights. In order to further incentivize good practices and reward these through economic gain, a coordinated branding and advocacy strategy would be developed to counter the prevailing negative perceptions and narratives around sustainable use of wildlife (including hunting). This would include a consumer awareness campaign about the environmental and conservation benefits of eating certified wildlife ranch products. New and innovative funds and initiatives such as the IUCN Green List of Species could provide ways in which the private wildlife ranching sector could be further be incentivized to support initiatives aimed as threatened species that comply with international guidelines on the wildness scale. |
| - Structure of the Finance Solution (100 words approx.) | A market-based certification scheme, voluntarily applied on communal and private game ranches, with supporting extension services, will improve ecosystem and species management outcomes of the game ranches. The certification scheme will be based on collaboratively developed standards relating to environmental, social, ethical and financial issues and will allow certified game ranches to demonstrate their contribution to biodiversity conservation and other socio-economic indicators. |
| - Description of Activities | - DEFF will develop of a spatial database for the mapping game ranches in South Africa in partnership with Wildlife Ranching South Africa (WRSA). - DEFF supported by BIOFIN will conduct assessments of candidate sites to determine eligibility in various existing frameworks such as OECMs and Verifiable Conservation Areas. - DEFF and BIOFIN will engage with provinces on the development case and the business case for the certification scheme in preparation for national roadshow. Discussion to also include assessment of extent and capacity of support to the wildlife ranching sector, Biodiversity Economy support opportunities within the context of the District Delivery model and an exploration of what kind of extension support could be made available to new sector entrants. - BIOFIN will support DEFF to conduct a demand study to determine what factors would drive a certification study from a user perspective. - DEFF and BIOFIN will undertake field visit with industry representatives to investigate practical and operational aspects of certification systems in primary sectors such as forestry and fishing industries. - BIOFIN will support DEFF in stakeholder engagement across the country to present and discuss the development case and the business case for the certification scheme, and to get an idea of what kind of transformation support through formal and/or informal mentorships and partnerships are being undertaken - BIOFIN will support the development of sustainability standards for the landscape level, species wildness continuum and individual sector activities. - Develop a game ranch management plan template that addresses the criteria defined in the sustainability standards including template for a periodic conservation performance report that includes conservation outcomes (measured results of conservation actions), lessons learned (shared experiences on addressing threats and realizing opportunities, adaptive management (revisions of the conservation programmes). - Pilot the assessment of several game ranches based on the standards developed, refine standards where necessary - Refine the detail on the proposed certification scheme design and start up processes with the help of input from a certification specialist with experience in developing schemes in South Africa. The scheme to include clear outline of the third-party auditing process to provide additional assurance to stakeholders - DEFF will outline a range of benefits linked to participation in the scheme - Development of a Biodiversity Economy brand that would be linked to this certification scheme and develop a PR campaign - BIOFIN will support DEFF to conduct national road show of the proposed certification scheme |
| - Institutional Arrangements | Convene a Task Team from government, private and non-profit organization stakeholders to report to the South African BIOFIN Unit and the Wildlife Forum Task Team to determine scope of specialist studies as described in the activities above. |
| - Main risks and management response for solution implementation | The main risks associated with this solution is limited uptake of the proposed scheme by the ranching sector and potential consumers. This will be mitigated through stakeholder engagement with the sector where the certification scheme is introduced and tested. It can also be determined through evidence of increased market share (especially internally) with an eco-label. Environmental: There is a risk of green washing where the scheme is seen as a as a marketing tool to demonstrate Environmental, Social and Governance (ESG) responsibility. The mitigation will be creating sound standards, and building in a good independent auditing processes. Social Risks: Negative perception on the wildlife economy activities such as trophy hunting and captive breeding of wildlife. This will be mitigated through communication on the value of sustainable use as a conservation strategy. Economic: Loss of business for unsustainable practices being forced out of the market which could also result in job losses. This will be mitigated though demonstrating the value of certification and assisting non-certified business to be certified. |
| - Sustainability | The process of engagement and collaboration with the wildlife industry on the development of the certification scheme and the standards will ensure that broad consensus is reached on the development and business case for the scheme. It is envisaged that an independent entity will be set up to ensure third-party audits of individual game ranch assessments against the standards that have been developed. The suite of benefits built into the business case for the scheme would ensure that the benefits of participating in the scheme outweigh the administrative and financial costs of compliance. |
| - M&E (100 words approx.) | The primary tool of the certification scheme is envisaged to be the game ranch management plan, with a periodic report speaking to required indicators across the triple bottom line. An independent verification process would provide an added measure of monitoring of compliance. |

| Indicator | Baseline | Target |
| --- | --- | --- |
| Percentage of game ranches certified. | 0 % potential conservation area under game ranch management certified. | 1-5% (200 000 – 1 million ha) of privately-owned game ranches certified by 2022. |
| Percentage of potential conservation area (assessed Other Effective Area-Based Conservation) under game ranch management certified. | 0 % potential conservation area under game ranch management certified. | 0,5% (100 000 ha) of privately-owned certified game ranches assessed as OECMs by 2022 |
| Number of female owned game ranches supported to become certified | 0 | 10 by 2024 |

SECTION 2 – FOR APPROVED FINANCE SOLUTIONS ONLY

Please provide the following information which will be included in next Work plan/Budget revision (or use actual Work plan document):

| Action Plan and Budget |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome/s (Result/s): Area under management of the wildlife ranching industry contributes to conservation outcomes and protected area targets |  |  |  |  |  | Timeframe |  |  |  |
| Output/s | Activities (example below) | Responsible actor/s | Funding source | Total Costs (USD) (detail by year in the AWP if FS approved) | Atlas. Budg. Code (For approved projects) | 2020 | 2021 | 2022 | … |
| Baseline: No game ranches audited/certified Indicators: Percentage of potential conservation area under game ranch management certified. Targets: 1-5% (200 000 – 1 million ha) of privately-owned game ranches certified. | Preparatory activities |  |  |  |  |  |  |  |  |
|  | Undertake assessment of the biodiversity contributions of the ranching sector on a suitable number (to be determined) of sample ranches. | DEFF BIOFIN | BIOFIN | 50 000 |  | X |  |  |  |
|  | Develop a business case for the benefits associated with certification for the wildlife ranching sector and wider economy. | DEFF BIOFIN | BIOFIN | 40 000 |  |  | X |  |  |
|  | Develop a demand study to determine what factors would drive a certification study from a user perspective. | DEFF BIOFIN | BIOFIN | 40 000 |  |  | X |  |  |
|  | Design of certification system | DEFF BIOFIN | BIOFIN | 40 000 |  |  | X |  |  |
|  | Undertake stakeholder consultation with ranching stakeholders to test whether the certification mechanism is acceptable. | DEFF BIOFIN | BIOFIN | 10 000 |  |  | X | X |  |
|  | Implementation |  |  |  |  |  |  |  |  |
|  | Pilot certification system | DEFF BIOFIN | BIOFIN | 20 000 |  |  |  | X |  |
|  | Development of a Biodiversity Economy brand that would be linked to this certification scheme and develop a PR campaign | DEFF | BIOFIN | 40 000 |  |  |  | X |  |
| TOTAL |  |  |  | 240 000 |  |  |  |  |  |

Annex 1: BIOFIN Prioritization Scoring and Screening Questions

| Questions | Indicative marks for scoring (1-5) | Score |
| --- | --- | --- |
| Is there a positive record of implementation? | 1= no, or limited records of success 3= successful pilots 5= yes, high potential of scalability | 3 |
| Will it generate, leverage, save, or realign a large volume of financial resources? | 1= minimal scale 2= <5 per cent of current expenditures / needs 3= 5-15 per cent of current expenditures / needs 4= >20 per cent of current expenditures / needs 5= game changer | 3 |
| Will financing sources be mobilized in a compatible timeline with needs? | 1 = no, the mobilization is not aligned with needs 3 = likelihood of being mobilized in alignment with needs 5 = yes, forthcoming and compatible schedules | 5 |
| Will financing sources be stable and predictable? | 1 = no, the source of revenue may be highly unstable and vulnerable to external factors 3 = likelihood of being reasonably stable and predictable source 5 = yes, very stable and predictable | 5 |
| Do the persons or entities paying have a willingness and ability to pay or invest? | 1 = no 3 = possibly 5 = yes | 3 |
| Are the financial risks adequately managed (e.g. exchange rate, lack of investors, etc.)? | 1 = no, high risks remain 3 = moderate risks 5 = yes, low residual risks | 3 |
| Are start-up costs onerous in comparison to the expected financial returns? | 1 = very costly (compared to returns) 3 = moderate (compared to returns) 5 = very low/minimal (compared to returns) | 5 |
| Does the solution improve incentives to manage biodiversity and ecosystems sustainably? (see Chapter 1). | 1 = not clear 3 = likely 5 = most certainly | 5 |
| Will the financial resources remain targeted to biodiversity over time? | 1 = not clear, high risk of misallocation 3 = likely, administrative provisions 5 = yes, strong legal provisions | 4 |
| Are risks to biodiversity (e.g. disrespect of mitigation hierarchy) low or easily mitigated? How challenging would it be to develop safeguards? | 1 = high risks, no easy mitigation 3 = reasonable risks, mitigation possible 5 = low risks, easy safeguards | 5 |
| Will there be a positive social and economic impact (e.g. jobs, poverty reduction and cultural)? | 1 = no 3 = moderate 5 = strong positive impact | 5 |
| Would there be a positive impact on gender equality, especially regarding participation in design and implementation or access to opportunities and benefits? | 1 = no 3 = moderate 5 = strong positive impact | 5 |
| Have risks of significant unintended negative social consequences been anticipated and managed? | 1 = no, high risks remain 3 = moderate and manageable 5 = yes, minimal residual risks | 3 |
| Will it be viewed as equitable and will there be fair access to the financial and biodiversity/ecosystem resources? | 1 = no, risk of inequitable outcome 3 = maybe 5 = yes | 5 |
| Is it backed by political will? | 1 = no, resistance from key stakeholders 3 = maybe 5 = yes, with public statements in support | 5 |
| Have political risks been anticipated and managed? | 1 = no, high risks remain 3 = moderate and manageable 5 = yes, minimal residual risks | 5 |
| Is buy-in among stakeholders (i.e. potential investors/ decision makers, implementers, and beneficiaries) sufficiently strong to counter potential opposition? | 1 = no 3 = partial buy-in 5 = yes, strong buy-in | 4 |
| Do the managing actor(s) have sufficient capacity? Can they rapidly acquire it? | 1 = no, severe capacity gap 3 = moderate capacity gap 5 = yes, strong capacity | 3 |
| Is it legally feasible? How challenging will any legal requirements be? | 1 = no, new law is required 3 = new regulations required 5 = yes, new regulations are not needed | 5 |
| Is it coherent with the institutional architecture, can synergies be achieved? | 1 = no, limited or no synergies / coherence 3 = potential synergies 5 = yes, fully coherent / large synergies | 5 |

BIOFIN Proposal Template

Country: South Africa		            			Submission date: 06/03/2020

Contact person: Yuval Tchetchik 		          	Email Address: ytchetchik@environment.gov.za

SECTION 1 – FOR PROPOSED FINANCE SOLUTIONS

| Proposal Summary |  |
| --- | --- |
| Title of the Finance Solution | Developing and promoting an online Biodiversity Economy Investment Portal |
| Concise Description (abstract) | South Africa has developed a Biodiversity Economy Strategy (BES) that serves as a guide for the sustainable growth of the wildlife economy, ecotourism and bioprospecting sectors. The BES provides a basis for addressing constraints for growth, ensuring sustainability, identifying clear stakeholder responsibilities, and monitoring progress of the enabling actions identified in the strategy. Facilitating financing of and investment into Biodiversity Economy enterprises is an essential part of creating an enabling environment for the sustainable growth of the sector. The Department of Environment, Fisheries and Forestry has developed an online investment portal (www.thegamechanger.co.za) that profiles a number of Biodiversity Economy investment opportunities. A review of this existing platform has been undertaken and a substantial revision of this portal will significantly enhance its effectiveness. The redeveloped Biodiversity Economy investment portal will profile investor-ready opportunities and link these to potential partners and/or sources of finance. These could be individual investors, impact investors, crowd-funding initiatives, enterprise challenge funds, foundations, endowments, fund managers, international cooperating partners, grant making agencies, private and institutional bankers and development finance institutions. A specific focus of this finance solution is to facilitate the development of business cases of a key sub-set of enterprises that form part of the Land Reform and Biodiversity Stewardship Initiative (LRBSI). This will ensure a clear articulation of the investment and/or partnership objectives of the investee in order to establish a basis for further engagements with a potential investor/funder. The GEF5 Biodiversity and Land Use Project supports the LRBSI. Biodiversity Stewardship sites contribute towards the Convention on Biological Diversity (CBD) Aichi Target 11 of an expanded Protected Area Estate. These sites have proved to be very cost effective ways of contributing to the National Protected Areas Expansion Strategy. Although this finance solution is focusing on the redevelopment of the investment platform and profiling of sites that have (or are working towards) Biodiversity Stewardship status, other Biodiversity Economy projects or enterprises that meet the required project preparation threshold will have access to the platform to facilitate linkages with investors and/or funders. A system of support for the project preparation phases of the full range of potential investees is not within the scope of this Finance Solution, and other funding sources from the Department or other National Departments, the Small Enterprises Development Agency (SEDA) and the UNDP small grants programme, amongst others, could be accessed. |
| Contribution to SDGs | SDG 8 – Decent Work and Economic Growth SDG 11- Sustainable Communities and Cities SDG 15 – Life on Land. |
| Contribution to Aichi Targets / National Targets / Biodiversity Finance Plan | AICHI 11: Well-governed and effectively managed protected areas are a proven method for safeguarding both habitats and populations of species and for delivering important ecosystem services. AICHI 20: By 2020 the mobilization of financial resources for effectively implementing the Strategic Plan for Biodiversity 2011-2020 from all sources is facilitated. NBSAP 1: Management of biodiversity assets and their contribution to the economy, rural development, job creation and social well-being is enhanced. NPAES: The NPAES highlights ways in which we can become more efficient and effective in allocating the scarce human and financial resources available for protected area expansion. The goal of the NPAES is to achieve cost-effective protected area expansion for ecological sustainability and increased resilience to climate change. EPIP: Potential to leverage additional private sector and other funding from the Department’s Environmental Protection & Infrastructure Projects (EPIP) amounts allocated to Biodiversity Economy projects owned by communities and emerging game ranchers. |
| Implementing/ Strategic partners (if other than UNDP) | Department of Environment, Forestry and Fisheries (DEFF), South African Biodiversity Institute (SANBI), South African National Parks (SANParks) and provincial protected area agencies |
| Start and End Date | 2020-2022 |

Categorization

| Solution Category/ies from the BIOFIN Catalogue | Impact investment, Crowd-funding, Enterprise Challenge and Innovation Funds, Financial guarantees (public or private guarantees) |
| --- | --- |
| Relevant Finance Result(s) | 1) Mobilizing Resources 2) Delivering Better 3) Re-aligning existing resources |
| Estimated Finance Result | The estimated finance result envisaged under this solution is securing investment into Biodiversity Economy initiatives to support the viability and therefore the declaration of 10 Biodiversity Stewardship sites covering a total of 50,000 hectares. According to an estimate presented at the 2017 Biodiversity Stewardship Conference, the cost to purchase such land for conservation would be approximately R9000 per hectare. The investment portal will be available to the full spectrum of eligible Biodiversity Economy enterprises, including projects co-funded by EPIP (thereby leveraging further funding from this public investment). All the additional projects and efforts within the biodiversity economy will be eventually channeled through the digital platform for show-casing and hence the platform becomes an integrator and enabler of growth in the biodiversity economy at large. |
| Finance Source | Public and private finance from national and international sources. |
| Sector | Biodiversity |
| Instrument Type | Market based |

Note: if Private sector please check due diligence requirements / guidelines at this LINK

| Budget (USD) |  |  |
| --- | --- | --- |
| Total resources required: | USD 240 000 |  |
| Total resources allocated: |  |  |
|  | BIOFIN | USD 240 000 |
|  | Donor 1: |  |
|  | Donor 2: |  |
|  | Government of South Africa (DEFF) In-kind | USD 160 000 |
|  | South African National Biodiversity Institute: (SANBI) | USD 80 000 |
| Unfunded: |  |  |

| Main Proposal and approach |  |
| --- | --- |
| - Background | South Africa’s Biodiversity Economy has been growing consistently faster than the general economy for a number of years, contributing R3 billion to GDP in 2013 – almost double the contribution made by the sector in 2008. The Biodiversity Economy Strategy estimates that the sector’s GDP contribution could be R14 billion by 2030. The Biodiversity Economy can play an important role in driving the transition to a low carbon economy. Significant, sustained and targeted investment will be required in the Biodiversity Economy in order for the sector to make the envisaged GDP contribution by 2030, while simultaneously enhancing economic, social and environmental outcomes. A clear outline of finance needs and suitable finance opportunities is to be determined, in order to identify the current investment gap in the Biodiversity Economy. Policy makers can play an important role of closing this gap by using instruments to attract the participation of a wide range of financing and investment agencies, entities and initiatives. In order to achieve the envisaged growth, investment needs to take place on a far greater scale than has been the case. At a global level ambitious targets to reduce poverty and combat climate change are set out in Agenda 2030 and the Paris Agreement. The Paris Agreement established the goal of ‘making financial flows consistent with a pathway towards low greenhouse gas emissions and climate-resilient development’. There are significant opportunities for financing the Biodiversity Economy under this goal articulation, as the sector could benefit from this significant structural adjustment towards low-carbon and renewable natural asset sectors in the international finance industry. The sustainable finance community has developed knowledge and expertise on integrating environmental, social and governance (EGS) issues for the wider financial sector to build on. There is a growing stakeholder expectation of increased accountability and resilience in investment decisions. Increasing commitment to decarbonize portfolios and to pay attention to long-term investment value drivers including ESG issues are being integrated into investment decision processes. The need and value of conserving natural, social and cultural assets and an increasing awareness of sustainability considerations integrated into investment decisions. This is giving rise to a significant new type of finance such as impact investment, crowdfunding, and Enterprise Challenge Funds. A strengthened investment environment will enable the mobilization of public and private resources to support resilient, sustainable and inclusive growth. The investment of public funds should be catalytic and lead to further coordinated investments from the public and private sectors. This will require more innovative and sophisticated financing strategies that facilitate significant and sustainable flows of finance to support sustainable and thriving Biodiversity Economy enterprises and programmes. In order to achieve the envisaged growth and to ensure transformation of the sector, it is important to create an enabling environment for communities and entrepreneurs to participate in the biodiversity economy. This will contribute to poverty alleviation, sustainable development and conservation of the country’s biodiversity, requiring an integrated approach across a wide range of departments, all levels of government and input and support from industry and civil society. A key focus of this envisaged work will be to devise appropriate mechanisms to leverage new investment into the Biodiversity Economy sector. Investment and financing for the sector does not necessarily require the creation of new instruments, but rather better showcasing existing investment opportunities (Biodiversity Economy projects) and connecting those opportunities/enterprises with available traditional and more innovative financing instruments and partners This Finance Solution will provide inputs and clarity on key policy considerations to further promote and mainstream investment and financing for sustainable Biodiversity Economy development such as: - Promotion of finance for investment projects of all sizes and at various stages of development (such as start-up and early stages). Development of Risk-sharing mechanisms to foster private sector participation should be undertaken. - Make a clearer case which Biodiversity Economy investments support the transition towards low carbon, climate resilient investments. - Develop a coherent and consistent policy framework to support the shift to more sustainable Biodiversity Economy investment and financing practices. - Improve data and analysis on finance and investment in Biodiversity Economy enterprises. Existing Digital platform (www.thegamechanger.co.za) In 2016, the Department of Environmental Affairs (DEA) appointed a service provider to develop an easy to read digital friendly Investment Catalogue profiling the biodiversity based economic opportunities in South Africa, especially those associated with land reform and emerging wildlife farmers and ranchers. The online catalogue, known as ‘The Game Changer’, was designed as an online multimedia platform, allowing for ongoing updates. The primary goals of the project where: - To create awareness and sensitize communities and incumbent farmers (and related - stakeholders) about biodiversity and ecosystems - Highlight opportunities in the 2 pillars of the Biodiversity Economy namely: Bioprospecting and the Wildlife Economy - Sensitizing and educating communities and beneficiaries of Environmental Protection and Infrastructure Programmes (EPIP) about the economy, natural resources management as well as access to market for beneficiaries - Showcase pilot projects and demonstrate where investment opportunities are, and - To start match making through awareness campaigns to the private sector. A review of this existing platform has been undertaken and a substantial revision of this portal will significantly enhance its effectiveness. The redeveloped Biodiversity Economy investment portal will profile investor-ready opportunities and link these to potential partners and/or sources of finance. |
| - Objective(s) and Results expected: (100 words max) | Objectives: - To create a template of what a Biodiversity Stewardship site investee prospectus should contain in order to engage an investor or partner (this template can form the basis for the full range of investee types) - To create an online investment portal that facilitates financing and partnership transactions between investees and investors in the Biodiversity Economy sector - To understand the investor landscape that could be accessed by the full range of Biodiversity Economy enterprises - To create awareness about investment and partnership opportunities in the Biodiversity Economy sector - To create a repository of usable and current information on the legislative and compliance landscape for investment in the Biodiversity Economy Results expected: - Biodiversity Economy enterprises are able to find project partners or financers more efficiently, thereby potentially reducing cost of capital and the time taken to finalise transactions - The profile of the Biodiversity Economy sector is substantially increased amongst the investor community, with an increasing investment portfolio held in this sector - Significant leveraging of additional funds into the sector from investment of public funds such as those under the EPIP programme - Additional financing options for Biodiversity Stewardship sites leads to an increasing number of sites being declared with shorter lead times, due to better profiling of sustainable and conservation compatible Biodiversity Economy opportunities on these sites |
| - Business case | The redevelopment of the Biodiversity Economy Investment Portal provides an opportunity to profile investment opportunities identified in priority Biodiversity Stewardship sites and Conservation Areas to a range of potential investors. These sites are well placed to secure investment from Impact investment sources, Crowd-funding initiatives and Enterprise Challenge Funds. The National Biodiversity Assessment 2018 (NBA 2018) indicates that strategic gains are possible by focusing on areas that are still in good ecological condition and where there are relatively easy opportunities for protection or other effective area-based conservation measures. Maintaining intact ecosystems and species populations and ensuring connectivity across landscapes are vital for preserving adaptive capacity of nature to climate change. This will enhance human adaptive capacity and resilience. Biodiversity stewardship (BDS) is an approach to securing land in biodiversity priority areas through entering into agreements with private landowners, communal property associations (CPAs) and the custodians of communal land. Conservation authorities, supported by conservation non-government organizations (NGOs), lead this work. The objective of biodiversity stewardship is to conserve and manage biodiversity priority areas through voluntary agreements with landowners and communities. There are three categories of biodiversity stewardship, - protected areas (national parks, nature reserves and protected environments), - conservation areas (contractually binding biodiversity agreements and conservation agreements), and - conservation partnership areas, including conservancies (not legally binding) The Land Reform and Biodiversity Stewardship Initiative (LRBSI) aims to address the critical developmental and environmental challenges faced by South Africa. This initiative caters for land reform beneficiaries in areas of critical biodiversity importance, to ensure the conservation of biodiversity and provision of ecosystem services while promoting sustainable rural development. A major component of the LRBSI is capacity building and facilitation of partnerships, so that communities can benefit from participation in both the Biodiversity Stewardship programmes and Biodiversity Economy opportunities. Technical support that integrates Biodiversity Economy development opportunities at the same time as the biodiversity assessment should take place in the pre-declaration phase. A geospatial mapping of existing and potential BDS sites, and an indication of where each site is at in terms of The Journey to Thriving Biodiversity Economy Enterprises that is being developed by the Department, will provide a clear indication of what support is required per site. The provincial protected area expansion plans could provide the potential sites and the conservation agencies can provide the existing sites. The GEF 5 (Biodiversity and Land Use Project) has a financial mechanism deliverable linked to biodiversity stewardship. This can be a fiscal financial incentive (separate Finance Solution under BIOFIN Phase 2) or a sector related funding opportunity that enables additional funding to flows (such as biodiversity economy resources, land reform resources or Natural Resource Management resources) towards stewardship landowners. SANBI will support further scoping work for this Finance Solution through this project. |
| - Structure of the Finance Solution | Biodiversity stewardship is an approach to entering into agreements with private and communal landowners to protect and manage land in biodiversity priority areas, led by conservation authorities in South Africa. It recognizes landowners as the custodians of biodiversity on their land. Biodiversity stewardship is a highly cost-effective mechanism for expanding protected areas. Both the processes to negotiate and declare a protected area through the biodiversity stewardship model, as well as the ongoing cost of supporting the landowners to manage the biodiversity stewardship sites once they are declared, are many times less costly to the conservation authority than the cost to purchase land and manage protected areas themselves. Providing targeted support to develop the Biodiversity Economy business case for a Biodiversity Stewardship site and facilitating financing or a partnership to ensure a thriving enterprise, will ensure that an increasing number of economically viable privately-owned sites are secured under formal protection with significant biodiversity conservation dividends. |
| - Description of Activities (150 words max) | - DEFF and SANBI will integrate use of Biodiversity Economy tools into activities of the Land Reform and Biodiversity Stewardship Initiative, including a learning exchange and capacity building for identified beneficiaries. - BIOFIN will support the development of a guideline for project preparation and investment prospectus template required by each enterprise to be investor ready. - DEFF and SANBI will identify 10 priority Biodiversity Stewardship sites that have been identified through the GEF 5 Biodiversity and Land Use Project and develop Business Plans for each of these with an investment prospectus for profiling on the Investment Portal - DEFF and BIOFIN will undertake an investor landscape profiling study to identify existing and potential partners, donors and funders in the Biodiversity Economy sector - DEFF will redevelop the digital platform to include best practice features including search engine optimization, analytics and user centric design thinking - Create a feature on the platform that outlines the legal, regulatory and compliance processes that relate to the Biodiversity Economy - BIOFIN and DEFF will develop a broad integrated engagement plan to raise the profile of the investment portal and investment opportunities in the Biodiversity Economy Sector |
| - Institutional Arrangements (100 words max) | Ownership and overall responsibility to manage the project and ongoing execution and implementation of all aspects is with (DEFF). The Biodiversity Stewardship community of practice facilitated by SANBI has been focusing on enhancing the capacity and capabilities of biodiversity stewardship practitioners in support of expanding South Africa’s network of protected areas, whilst effectively securing conservation, land reform and rural development returns. BIOFIN will support the biodiversity value proposition for each identified site. A service provider will be appointed to provide all support needed in the scoping, development and ongoing support (and regular updating) of the platform. As a starting point a Terms of Reference scoping document will be clearly defined outlining all deliverables. As part of the broader engagement program, there will be a strong drive to identify partners in the private sector. An advocacy strategy, including a series of stakeholder consultation workshops, will raise awareness of investment opportunities in the Biodiversity Economy. |
| - Main risks and management response for solution implementation (100 words max) | Social - The investment catalogue must outline the need for investment that is sustainable in the long term. Financial stability is important to ensure that rural communities can depend on financial flows for the duration of the transaction period. Environmental risks - Projects that are profiled on the investment platform must minimum acceptable environmental standards that are conservation-compatible. Private sector - The project team will ensure that investors do not engage in any of the exclusionary criteria as outlined in the private sector partner tool of UNDP. Project execution – Dedicated project manager within DEFF will ensure alignment to work within the mandate of the Chief Directorate: BESU. |
| - Sustainability (100 words max) | The project preparation guideline and investment prospectus template will serve as an important tool to support all Biodiversity Economy enterprises being profiled on the Investment Portal. This will ensure that only investor-ready enterprises and projects will be profiled, thereby increasing the credibility of the investment portal. A number of priority interventions are being directed at supporting enterprises and communities in developing their respective Biodiversity Economy business cases, thereby ensuring a strong pipeline of investees in the project preparation phase. Similarly, ongoing initiatives to expand the understanding of the investor landscaping through mainstreaming the Biodiversity Economy sector will increase the overall awareness of investment opportunities in the sector. There is a cross-cutting integration drive across all public sector activities within the Biodiversity Economy Strategy implementation that will coordinate resource and projects with the digital platform at its center and being the public face of these activities. |
| - M&E | In order to measure progress of the project, it will be the responsibility of the project manager to put in place measuring all necessary processes. This requirement will be scoped with the development service provider such that reporting can be done on the platform itself and accessible for designated users. A basic dashboard and corresponding report will be available. Identified metrics to measure as follows - Number of investees who are profiled on the platform - Investee by sub-sector such as a Biodiversity Stewardship site profiled - Website analytics including number of new investors who are registered on the online investor platform; - Number of transactions facilitated - Value of transactions facilitated - Indicator relating to biodiversity conservation contribution of enterprise - Number of jobs created - Number of promotion activities to profile the platform to investors |

| Indicator | Baseline | Target |
| --- | --- | --- |
| Number of hectares of stewardship area added | 450,000 hectares secured under Biodiversity Stewardship agreements (2014) | 50 000h of additional stewardship sites added to the conservation estate by 2023 |
| Number of Biodiversity Stewardship Sites that have a developed Investment Prospectus | 0 | 10 by 2023 |

SECTION 2 – FOR APPROVED FINANCE SOLUTIONS ONLY

Please provide the following information which will be included in next Work plan/Budget revision (or use actual Work plan document):

| Action Plan and Budget |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome/s (Result/s): |  |  |  |  |  | Timeframe |  |  |  |
| Output/s | Activities (example below) | Responsible actor/s | Funding source | Total Costs (USD) (detail by year in the AWP if FS approved) | Atlas. Budg. Code (For approved projects) | 2020 | 2021 | 2022 | … |
| Baseline: 450,000 hectares secured under Biodiversity Stewardship agreements (2014) Indicators: Number of hectares of stewardship area added Targets: 50 000h of additional stewardship sites added to the conservation estate by 2023 | Preparatory activities |  |  |  |  |  |  |  |  |
|  | Investees: Host a Land Reform and Biodiversity Stewardship learning exchange with 60 potential investees/land reform beneficiaries | SANBI | SANBI | 50 000 |  | x |  |  |  |
|  | Digital Platform: Hold concept workshops to finalize content and look and feel/functionality requirements for platforms | DEFF | DEFF | 10 000 |  |  |  |  |  |
|  | Investees: Finalize list of priority sites through internal screening for business plan development and hold consultation workshops with each pilot project | DEFF, SANBI | DEFF | 20 000 |  | x |  |  |  |
|  | Investors: Prepare an initial scan of the investor landscape including survey of potential to include Biodiversity Economy projects in investment portfolios | DEFF | DEFF | 20 000 |  | x |  |  |  |
|  | Implementation |  |  |  |  |  |  |  |  |
|  | Investees: Appoint consultant to develop business plans (including investment prospectus) for 10 selected sites. | DEFF | BIOFIN | 70 000 |  | x | x | x |  |
|  | Investees: Ongoing capacity building of potential investees to ensure growing project pipeline | DEFF, SANBI | DEFF, SANBI | 50 000 30 000 |  | x | x | x |  |
|  | Digital Platform: Appoint service provider to 1) Hold customer needs / design workshop 2) Build platform, iterate and test 3) support a fully functional platform | DEFF | BIOFIN | 70 000 |  | x | x | x |  |
|  | Investors: Appoint service provider to developed detailed investor landscape analysis. | DEFF | BIOFIN | 40 000 |  | x |  |  |  |
|  | Advocacy: Develop and implement investor engagement strategy to raise awareness of the platform. | DEFF | DEFF, BIOFIN | 40 000 40 000 |  | x | x | x |  |
|  | Validation |  |  |  |  |  |  |  |  |
|  | Monitoring and Evaluation of Investment Portal | DEFF | DEFF | 20 000 |  | x | x | x |  |
| TOTAL |  |  |  | 240 000 |  |  |  |  |  |

Annex 1: BIOFIN Prioritization Scoring and Screening Questions

| Questions | Indicative marks for scoring (1-5) | Score |
| --- | --- | --- |
| Is there a positive record of implementation? | 1= no, or limited records of success 3= successful pilots 5= yes, high potential of scalability | 3 |
| Will it generate, leverage, save, or realign a large volume of financial resources? | 1= minimal scale 2= <5 per cent of current expenditures / needs 3= 5-15 per cent of current expenditures / needs 4= >20 per cent of current expenditures / needs 5= game changer | 5 |
| Will financing sources be mobilized in a compatible timeline with needs? | 1 = no, the mobilization is not aligned with needs 3 = likelihood of being mobilized in alignment with needs 5 = yes, forthcoming and compatible schedules | 5 |
| Will financing sources be stable and predictable? | 1 = no, the source of revenue may be highly unstable and vulnerable to external factors 3 = likelihood of being reasonably stable and predictable source 5 = yes, very stable and predictable | 3 |
| Do the persons or entities paying have a willingness and ability to pay or invest? | 1 = no 3 = possibly 5 = yes | 5 |
| Are the financial risks adequately managed (e.g. exchange rate, lack of investors, etc.)? | 1 = no, high risks remain 3 = moderate risks 5 = yes, low residual risks | 3 |
| Are start-up costs onerous in comparison to the expected financial returns? | 1 = very costly (compared to returns) 3 = moderate (compared to returns) 5 = very low/minimal (compared to returns) | 3 |
| Does the solution improve incentives to manage biodiversity and ecosystems sustainably? (see Chapter 1). | 1 = not clear 3 = likely 5 = most certainly | 5 |
| Will the financial resources remain targeted to biodiversity over time? | 1 = not clear, high risk of misallocation 3 = likely, administrative provisions 5 = yes, strong legal provisions | 5 |
| Are risks to biodiversity (e.g. disrespect of mitigation hierarchy) low or easily mitigated? How challenging would it be to develop safeguards? | 1 = high risks, no easy mitigation 3 = reasonable risks, mitigation possible 5 = low risks, easy safeguards | 3 |
| Will there be a positive social and economic impact (e.g. jobs, poverty reduction and cultural)? | 1 = no 3 = moderate 5 = strong positive impact | 5 |
| Would there be a positive impact on gender equality, especially regarding participation in design and implementation or access to opportunities and benefits? | 1 = no 3 = moderate 5 = strong positive impact | 5 |
| Have risks of significant unintended negative social consequences been anticipated and managed? | 1 = no, high risks remain 3 = moderate and manageable 5 = yes, minimal residual risks | 3 |
| Will it be viewed as equitable and will there be fair access to the financial and biodiversity/ecosystem resources? | 1 = no, risk of inequitable outcome 3 = maybe 5 = yes | 5 |
| Is it backed by political will? | 1 = no, resistance from key stakeholders 3 = maybe 5 = yes, with public statements in support | 5 |
| Have political risks been anticipated and managed? | 1 = no, high risks remain 3 = moderate and manageable 5 = yes, minimal residual risks | 3 |
| Is buy-in among stakeholders (i.e. potential investors/ decision makers, implementers, and beneficiaries) sufficiently strong to counter potential opposition? | 1 = no 3 = partial buy-in 5 = yes, strong buy-in | 5 |
| Do the managing actor(s) have sufficient capacity? Can they rapidly acquire it? | 1 = no, severe capacity gap 3 = moderate capacity gap 5 = yes, strong capacity | 3 |
| Is it legally feasible? How challenging will any legal requirements be? | 1 = no, new law is required 3 = new regulations required 5 = yes, new regulations are not needed | 1 |
| Is it coherent with the institutional architecture, can synergies be achieved? | 1 = no, limited or no synergies / coherence 3 = potential synergies 5 = yes, fully coherent / large synergies | 5 |

FINANCE SOLUTION Proposal Template

Country: South Africa…….…………                Submission date: …06/03/2020..…….………….

Contact person: Olga Kumalo.…….                Email Address:  okumalo@environment.gov.za

SECTION 1 – FOR PROPOSED FINANCE SOLUTIONS

☒ Feasibility stage (If the solution is in the preparatory stage less details will be expected. Only the white sections in the table must be filled, the grey sections will be filled at the next stage).

☐ Full implementation stage (If the solution enters in the full implementation stage, more details are expected. The white and the grey sections must be filled with as many details as possible)

| Proposal Summary |  |
| --- | --- |
| Title of the Finance Solution | Improve effectiveness of permits |
| Concise Description (Approx 150 words) | In terms of National Environmental Management Biodiversity Act (NEMBA) and National Environmental Management Protected Areas (NEMBA) Act, global conventions and protocols, DEFF and regulatory authorities administer different types of permits and enforce compliance through fines and penalties. This includes permits and licenses for Threatened or Protected Species (TOPS) including marine, Bioprospecting Access and Benefits Sharing (ABS), Alien and Invasive Species (AIS) and Convention on International Trade on Endangered and Threatened Species (CITES). Reporting on volumes on applications handled varies. The challenges lie in reporting on TOPS applications. The department is working on a consolidated electronic application system. The fee structure for permits should, whilst it is an administrative cost to the state (staff time), needs to be environmentally, socially and economically responsive so that it does not have a negative effect on State finances or the achievement of national policy goals. This finance solution will look at a mechanism or criteria to determine how fees can be determined and increased when the need arises. The fees are currently determined in different regulations and has no mechanism to review the amount as and when determined. In this regard, the finance solution will provide a guideline for determining fees and enable the gazetting of such fees in one regulation or in different regulations. Based on the possible increase in income, recommendations will be made to National and provincial treasuries for regulatory authorities to retain revenue in order to support administration operations. |
| Contribution to SDGs | Goal 8 Decent work and economic growth Goal 12 Responsible production and consumption Goal 14 Life below water Goal 15 Life on land |
| Contribution to Aichi Targets / National Targets / Biodiversity Finance Plan | AICHI 11 By 2020, at the latest, Governments, business and stakeholders at all levels have taken steps to achieve or have implemented plans for sustainable production and consumption and have kept the impacts of use of natural resources well within safe ecological limits NBSAP 1 Management of biodiversity assets and their contribution to the economy, rural development, job creation and social well-being is enhanced. |
| Implementing / Strategic partners (if other than UNDP) | DEFF, Regulatory Authorities |
| Start and End Date | 2020 – 2022 |

Finance Results

| Solution Category/ies from the BIOFIN Catalogue | Public and regulatory |
| --- | --- |
| Relevant Finance Result(s) | Delivering Better |
| Estimated Finance Result |  |
| Finance Source | Public/Private national/international |
| Sector | Multiple Sectors |
| Instrument Type | Regulatory |

Note: if Private sector please check due diligence requirements / guidelines at this LINK

| Budget (USD) |  |  |
| --- | --- | --- |
| Total resources required: | USD 100 000 |  |
| Total resources allocated: |  |  |
|  | BIOFIN | USD 100 000 |
|  | Donor: | - |
|  | Donor 2: | - |
|  | Government of South Africa | DEFF and provincial staff time |
|  | In-Kind | Staff time |
| Unfunded: |  |  |

| Main Proposal and approach |  |  |
| --- | --- | --- |
| - Background information (150 words approx.) | DEFF and Regulatory Authorities administer a number of different permits in line with the National Environmental Management: Biodiversity Act (NEMBA) legislation in relation to: - Threatened and protected species (TOPS) - Bioprospecting, Access and Benefit Sharing (BABS) - Convention on International Trade of Endangered Species (CITES) - Alien Invasive Species (AIS) regulations. Over the years, attempts have been made to harmonize the permit process and to ensure minimum administration and capacity demands in application. The current permit fees are not cost reflective against the cost of processing the permit applications, or the value of the relevant species. The implementation of an effective and efficient fee structure also has to meet socio-economic considerations to allow previously disadvantaged individuals to apply for permits and licenses. From a legal perspective, permit fees are published in the Regulations rather than a separate gazette. This makes any adjustments to the fees a time and resource consuming exercise. Shifting the fee structure to a separate gazette would make periodic adjustments easier. Regulatory authorities that are required to process the applications do not have the required supporting expertise (i.e. social scientist, economist and legal experts) to undertake a comprehensive assessment of the fees to objectively determine the level of increment of permit processing fees (although a Task Team has been has been established to propose implementation mechanisms for TOPS regulations), and there is no standard mechanism to review these fees. An increment of permit processing fee may be met with challenges and opposition if the above information is not appropriately determined and made available. Finally, the ability of regulatory authorities to ring-fence or retain funds related to permits and licenses varies across legislation, and therefore an attempt should be made to improve the retention of these fees to reduce the burden on the fiscus. |  |
| - Objective(s) and Results expected (100 words approx.) | - To comprehensively assess and review the administrative system and charges for permits for biodiversity related all regulations and develop an appropriate framework for determining adjustments to these. - To recommend a robust regulatory system for implementation for an appropriate framework for determining cost-reflective fees and for increase of such fees. |  |
| - Business case (Approx 150 words) | The process was motivated by the lack of an environmental, socially and economically responsive mechanism to determine fees for biodiversity related permits and licences to implement TOPS regulations. Further to this there is no mechanism to increase the fees. There is need for a mechanism to determine the setting and increase of fees in line with administrative requirements, operational costs, cost to the environment and social and economic considerations. Currently some provinces charge some of the permits based on quotas whilst others charge based on species value which implies there is no uniformity. |  |
| - Structure of the Finance Solution (100 words approx.) | This finance solution will investigate a mechanism to ensure that fees and fines are environmentally, socially and economically responsive and cost-reflective. It will result in the development of a new regulatory mechanism to determine fees. It is believed that once an appropriate model/ guideline for determining fees is developed, this will lead to an increase in the charges and result in a direct financial result. Further to this, the model will enable a new legal mechanism (gazette) which will allow fees to be published and adjusted as and when determined. |  |
| - Description of Activities and Milestones (150 words approx.) | - Baseline assessment of provincial income from fees for different types permits and licences. - Review fees model for permits and licenses that different competent authorities use and make recommendations on how to determine a fee structure based on social, environmental and considerations - Develop a guideline for determining and amending fees for permits and licenses to be used in an appropriate regulatory mechanism (gazette) for implementation of new fees. |  |
| - Institutional Arrangements (100 words approx.) | DEFF will work with regulatory authorities to determine current income from fees for the different types permits and licenses. Further work will be undertaken with National Treasury to determine the framework/ mechanism for the determination of the fees. Once this is agreed to, the guideline will go through public participation and promulgated in the government gazette to give effect to the finance solution. The provincial issuing authorities will, through work with their respective Provincial Treasuries, to ring-fence the funds generated through the permit processing fees. These ring-fenced funds would then be directed back to relevant functions within the provincial issuing authorities. |  |
| - Main risks and management response for solution implementation | Main Risks: - Public acceptability, which may lead to implementation challenges and low revenue - National Treasury does not agree to ring-fence fees generated - Increased permit processing fee may have negative impact on the already disadvantaged individuals. - Lack of capacity to implement Management response: - Encourage regulated community to apply for necessary permits prior to undertaking restricted activities for which a permit is required through advocacy - Lobby regulated community to understand the rationale for a new mechanism and for increasing permit processing fees through consultation. - Engage with National Treasury to lower the minimum threshold for ring-fencing permit processing fees - Reduce capacity requirements through enabling exemption for certain categories of persons from paying permit processing fees. - Capacity building for management authorities. |  |
| - Sustainability and institutionalization (100 words approx.) | The results of this finance solution will be institutionalized through an enabling mechanism in the form of a guideline to determine cost reflective fees and also allow for review as and when necessary. The results will also assist in ensuring that determination of fees is applied uniformly across the regulatory authorities. Further to this the result of the finance solution will be effected in a legislative tool which is a government gazette. |  |
| - M&E (100 words approx.) | The implementation of this finance solution will be monitored through regular quarterly reports on permits and licenses issued by the regulatory authorities. The quarterly reports form part of institutional reporting by the regulatory authorities to the Working Group. Further monitoring will be done through management account reports that regulatory authorities submit to respective treasuries. |  |
| Indicator | Baseline | Target |
| Complete baseline assessment on income report from fees charged for different permits and licenses | X Rand for different TOPS/ CITES and Bioprospecting permits and licenses | By 2022, the income for fees/ charges for different permits and licenses will be completed. |
| Complete a framework and formula for setting fees and determining increases | No framework for setting fees and determining increases | By 2022, there will be a framework for setting fees and determining increases |
| Complete guideline for setting fees and determining increases | Regulations on issuing of permits and licenses | By 2022, there will be a guideline for setting fees and determining increases |
|  | … | … |

SECTION 2 – FOR APPROVED FINANCE SOLUTIONS BY TECHNICAL ADVISOR ONLY

Please provide the following information which will be included in next Work plan/Budget revision (or use actual Work plan document):

| Action Plan and Budget |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome/s (Result/s): Revision of the pricing structure of permits and licenses and the implementation of a single, national cost regulation |  |  |  |  |  | Timeframe |  |  |  |
| Output/s | Activities (example below) | Responsible actor/s | Funding source | Total Costs (USD) (detail by year in the AWP if FS approved) | Atlas. Budg. Code (For approved projects) | 2020 | 2021 | 2022 | … |
|  | Preparatory activities |  |  |  |  |  |  |  |  |
|  | Baseline assessment of national and provincial income from fees | DEFF | BIOFIN | 30 000 |  | X |  |  |  |
|  | Review fees model for permits and licenses that different competent authorities use and make recommendations on how to determine a fee structure based on social, environmental and considerations |  | BIOFIN? | 30000 |  |  | X |  |  |
|  | Develop a guideline for determining and amending fees for permits and licenses to be used in an appropriate regulatory mechanism (gazette) for implementation |  | BIOFIN? | 40000 |  |  |  | X |  |
| TOTAL |  |  |  | 100 000 |  |  |  |  |  |

Annex 1: BIOFIN Scoring and Screening Questions

| No | Questions | Indicative marks for scoring (1-5) | Score |
| --- | --- | --- | --- |
| 1 | Is there a positive record of implementation? | 1= no, or limited records of success 3= successful pilots 5= yes, high potential of scalability | 3 |
| 2 | Will it generate, leverage, save, or realign a large volume of financial resources? | 1= minimal scale 2= <5 per cent of current expenditures / needs 3= 5-15 per cent of current expenditures / needs 4= >20 per cent of current expenditures / needs 5= game changer | 4 |
| 3 | Will financing sources be mobilized in a compatible timeline with needs? | 1 = no, the mobilization is not aligned with needs 3 = likelihood of being mobilized in alignment with needs 5 = yes, forthcoming and compatible schedules | 3 |
| 4 | Will financing sources be stable and predictable? | 1 = no, the source of revenue may be highly unstable and vulnerable to external factors 3 = likelihood of being reasonably stable and predictable source 5 = yes, very stable and predictable | 5 |
| 5 | Do the persons or entities paying have a willingness and ability to pay or invest? | 1 = no 3 = possibly 5 = yes | 3 |
| 6 | Are the financial risks adequately managed (e.g. exchange rate, lack of investors, etc.)? | 1 = no, high risks remain 3 = moderate risks 5 = yes, low residual risks | 5 |
| 7 | Are start-up costs onerous in comparison to the expected financial returns? | 1 = very costly (compared to returns) 3 = moderate (compared to returns) 5 = very low/minimal (compared to returns) | 5 |
| 8 | Does the solution improve incentives to manage biodiversity and ecosystems sustainably? (see Chapter 1). | 1 = not clear 3 = likely 5 = most certainly | 5 |
| 9 | Will the financial resources remain targeted to biodiversity over time? | 1 = not clear, high risk of misallocation 3 = likely, administrative provisions 5 = yes, strong legal provisions | 5 |
| 10 | Are risks to biodiversity (e.g. disrespect of mitigation hierarchy) low or easily mitigated? How challenging would it be to develop safeguards? | 1 = high risks, no easy mitigation 3 = reasonable risks, mitigation possible 5 = low risks, easy safeguards | 3 |
| 11 | Will there be a positive social and economic impact (e.g. jobs, poverty reduction and cultural)? | 1 = no 3 = moderate 5 = strong positive impact | 3 |
| 12 | Would there be a positive impact on gender equality, especially regarding participation in design and implementation or access to opportunities and benefits? | 1 = no 3 = moderate 5 = strong positive impact | 3 |
| 13 | Have risks of significant unintended negative social consequences been anticipated and managed? | 1 = no, high risks remain 3 = moderate and manageable 5 = yes, minimal residual risks | 5 |
| 14 | Will it be viewed as equitable and will there be fair access to the financial and biodiversity/ecosystem resources? | 1 = no, risk of inequitable outcome 3 = maybe 5 = yes | 5 |
| 15 | Is it backed by political will? | 1 = no, resistance from key stakeholders 3 = maybe 5 = yes, with public statements in support | 5 |
| 16 | Have political risks been anticipated and managed? | 1 = no, high risks remain 3 = moderate and manageable 5 = yes, minimal residual risks | 5 |
| 17 | Is buy-in among stakeholders (i.e. potential investors/ decision makers, implementers, and beneficiaries) sufficiently strong to counter potential opposition? | 1 = no 3 = partial buy-in 5 = yes, strong buy-in | 5 |
| 18 | Do the managing actor(s) have sufficient capacity? Can they rapidly acquire it? | 1 = no, severe capacity gap 3 = moderate capacity gap 5 = yes, strong capacity | 3 |
| 19 | Is it legally feasible? How challenging will any legal requirements be? | 1 = no, new law is required 3 = new regulations required 5 = yes, new regulations are not needed | 3 |
| 20 | Is it coherent with the institutional architecture, can synergies be achieved? | 1 = no, limited or no synergies / coherence 3 = potential synergies 5 = yes, fully coherent / large synergies | 5 |

# Annexure 3: Terms of reference for team members

For effective implementation of Phase 2, the BIOFIN Unit will be set up and the following have been identified as an optimal capacitation requirement.

1. NATIONAL PROJECT MANAGER

Location: DEFF

Starting Date: 22 July 2019

Supervisor: Deputy Director General Biodiversity and Conservation / UNDP Environment, Energy and Climate Change Lead

Duration of contract: 3 years at 100%

1.1	JOB PURPOSE:

To coordinate and manage Biodiversity Finance (BIOFIN) implementation at national level, ensuring activities are carried out on time and within planned budget.

  - MAIN OBJECTIVES / KEY PERFORMANCE AREAS:

    - Ensure management of the BIOFIN project

- Coordinate and manage implementation of the BIOFIN project at national level and ensure activities are carried out on time and within planned budget.

- Consult with the United Nations Development Program (UNDP) Country Office and BIOFIN Unit and BIOFIN Global Team to elaborate/revise work plan, report on the schedule and budget.

- Assist with the identification and selection of national consultants and experts, in close collaboration with the UNDP Country Office and the BIOFIN Unit.

- Oversee the work of national experts and institutions to ensure that outputs are delivered on time, on budget, and to high quality standards (with support from Environmental Finance Expert).

- Ensure administrative requirements are managed and executed in a timely and appropriate manner.

- Provide support to the formulation and management of the National BIOFIN Governance mechanisms.

- Establish and maintain links with other national and international programmes National Biodiversity Strategies and Action Plans (NBSAP) and projects.

- Lead project monitoring, reporting and evaluation at national level.

- Lead capturing and documenting of lessons from project implementation and make recommendations to the relevant BIOFIN Committees for more effective implementation of activities.

- Compile BIOFIN progress reports (substantive and financial) regularly for UNDP and project partners.

    - Provide technical leadership and support to the BIOFIN project

- Provide key technical leadership on Public Finance and technical expertise in assuring horizontal integration and consistency of work streams/studies with support from the Environmental Economics and Finance Expert.

- Provide technical support and overall coordination to the national BIOFIN team to complete BIOFIN deliverables in a consistent manner and provide quality assurance of national products with support from the Environmental Economics and Finance Expert

- Engage with the BIOFIN Global team regularly on project implementation.

- Facilitate coordination of national BIOFIN and NBSAP processes for mutual reinforcement.

- Provide technical support, policy inputs and oversight for the finalisation and implementation of the Biodiversity Finance Plan and specific finance solutions with support from the Environmental Economics and Finance Expert.

    - Provide communication support on project outreach to the stakeholders

- Consult with national stakeholders and position BIOFIN objectives and processes towards relevant government departments and partner institutions, to catalyse transformational outcomes.

- Oversee the development of a communication strategy for BIOFIN within the first year of implementation

- Oversee the implementation of the BIOFIN communications strategy

- Ensure collaboration of counterparts on data and information provision, expert review and verification.

- Ensure effective coordination and communication of BIOFIN project objectives and activities by liaising with national and international counterparts, NGOs and other groups

- Organize national workshops as required.

- Edit, print and publish final Summary for Policy Makers.

- Publicise and promote the results and impacts of BIOFIN at national level.

- Support advocacy work for biodiversity finance solutions.

- Prepare detailed reports and analysis of national BIOFIN project results and impacts including in preparation for the CBD COP, the global BIOFIN Workshop and for project end.

    - Provide knowledge management and reporting support

- Document decisions and assumptions made while completing the BIOFIN outputs

- Compile reports and prepare policy documents and information notes to communicate BIOFIN objectives and results to key stakeholders.

- Participate in BIOFIN Regional calls and workshops, and BIOFIN global workshops

- Document lessons learned from conducting the BIOFIN project ranging from institutional considerations to technical issues.

- Prepare reports, presentations and case studies, as required, for submission to regional and global meetings.

    - Deliverables

- Detailed BIOFIN Work Plan and budget agreed by all major partners and approved by the Global BIOFIN team, to be revised and approved every six months

- Finance Solution Implementation: (I) Project proposal (s) for suggested activities, (II) ToR for additional consultants / service contracts, (III) Mid-term and Final Report on the results of implementation.

- All consultants and team members recruited and delivering to schedule and working relations between team members clarified and effective.

- National Steering/Advisory Committee formed and operational.

- Lines of communication and working methods agreed and functional.

- Reporting and updates provided to UNDP, government, etc.

- Planned activities are carried out in line with timelines and required quality standards.

- Project Synthesis Report and Policy Briefs (with recommendations to government)

- Policy Development: Specific policy recommendations/papers for relevant national/sectoral policy processes.

- Overall transformational process (outreach to government, steering committee, etc.)

- All workshops organised in line with work plan and well documented.

    - Education:

- Degree in management, administration, economics, environment or a closely related field, or equivalent relevant work experience.

- 5 years’ experience in management support, strategic management and coordination

- Experience working with multiple partners and UN will be an added advantage

    - Competencies:

- Ability to maintain overview in complex work situations, self-starter in supporting the coordinator in communicating and keeping timelines.

- Able to gather and process data and information.

- Excellent interpersonal skills to network among the national team and beyond to other national institutions.

- Writes clearly professional correspondence adequately.

- Highly organized person, sets priorities, produces quality outputs, meets deadlines and manages time efficiently.

- Shares knowledge and is willing to provide support to others who request advice or help.

- Works toward creative solutions by analysing problems carefully and logically.

- Maintains professional relationships with supervisors, co-workers and clients.

    - Experience:

- At least 10 years of experience, preferably in the programme management and implementation of projects

- At least 5 years of experience in the management or review of public finance, conservation finance or environmental finance

- Experience in dealing with international and national experts and institutions.

- Exposure to environmental, finance, economic and biodiversity issues is required.

- Sound understanding of key software packages (MS Office)

2. PROJECT ADMINISTRATOR

Location: UNDP

Starting Date: 01 April 2020

Supervisor: UNDP Environment, Energy and Climate Change Lead / National Project Manager

Duration of contract: 3 years at 100% (recommended)

2.1 Job purpose

To coordinate and provide back-office management support to the BIOFIN project, including the planning and implementation of work streams and budgets; managing the meeting of project timelines and milestones.

2.2 Main purpose / Key performance areas

2.2.1 Management support

- Providing support on the general administrative requirements of the project, including those related to project management and funding.

- Assist in ensuring that project is executed in a timely and appropriate manner.

- Facilitate, guide and monitor the work of the national BIOFIN team; manage payment schedules.

- Assist in project related activities, where required. These may include planning for meetings, local and national consultations, trips and other project related activities.

- Maintain linkages with national and international organizations and persons.

- Maintain records of meetings, decisions, actions, etc.

- Any other duties assigned by the National BIOFIN Project Manager that have direct relevance to the project.

- Monitor and report on project implementation against targets and indicators

- Prepare monitoring reports

- Coordinate the evaluation of BIOFIN

    - Financial Oversight

- Manage the project budget, oversee overall resource allocation, with the National Project Leader.

- Ensure financial resources are disbursed on time to implementing partners.

- Maintain records of expenditures and collaborate in financial reporting.

- Prepare expenditure reports

- Ensure the atlas approval system is set up at the Country Office for BIOFIN

2.2.3 Deliverables

- High level administrative and logistical support to the BIOFIN Team

- Administration records; agendas, minutes of meetings, follow up on actions

- Procurement plan and payment of invoices

- Reconciliation of statement of accounts including expenditure reports

- Atlas approval system

- Monitoring and evaluation reports

2.2.4 Education:

- Degree in management, administration, economics, environment or a closely related field, or equivalent relevant work experience.

2.2.5 Competencies:

- Ability to maintain overview in complex work situations, self-starter in supporting the Project Manager in communicating and keeping timelines.

- Able to gather and process data and information.

- Excellent interpersonal skills to network among the national team and beyond to other national institutions.

- Writes clearly professional correspondence adequately.

- Highly organized person, sets priorities, produces quality outputs, meets deadlines and manages time efficiently.

- Shares knowledge and is willing to provide support to others who request advice or help.

- Works toward creative solutions by analysing problems carefully and logically.

- Maintains professional relationships with supervisors, co-workers and clients.

2.2.6 Experience:

- At least 5 years of experience, preferably in programme management and implementation support, monitoring and evaluation

- Experience in dealing with international and national experts and institutions.

- Exposure to environmental issues or biodiversity desirable, but not required.

- Sound understanding of key software packages (MS Office)

. 3. PROJECT MANAGEMENT SPECIALIST

Job Description

- 1. Technical guidance and leadership (60%):

- -Work with the finance solution working groups/task teams and key experts, as well as the National Project Manager, to update the finance solution implementation plans for each of the finance solutions;

- -Develop the Terms of Reference for the appointment of consultants/experts for the implementation of specific finance solutions in consultation with the National Project Manager and in line with the approved Annual Work Plan;

- -Provide technical leadership and support to the working groups, task teams and experts implementing the BIOFIN South Africa finance solutions, including reviewing reports, conducting necessary meetings, workshops and field visits to support progress and guarantee the quality of work;

- -Together with the BIOFIN National Project Manager, work to ensure technical coordination and backstopping of the project work streams;

- -Lead the provision of capacity development as the annual work plan allows;

- -Contribute to the national dialogue on policies and measures that can improve the sustainable management and protection of South Africa’s natural resources;

- -Identify good practices and lessons learned that could contribute to improving the management of UNDP initiatives, projects and programs.

- 2. Programme Management support (30%):

- -Work closely with the National Project Manager, ensuring effective management and implementation of the BIOFIN project as per the BIOFIN Phase 2 Work Plan;

- -Provide input to the National Project Manager and Project Administrator to support the preparation of annual work plans, biannual workplan revisions, and the quarterly procurement plans;

- -Assist the National Project Manager in supervising and coordinating the work of all project personnel, consultants and subcontractors (quality assurance and contract management);

- -Working with the National Project Manager, Project Administrator and Programme Finance Associate, contribute to the proper management of funds according to UNDP requirements, and budget planning and control;

- -Support the National Project Manager in the preparation of timely project reports to the global UNDP BIOFIN team, including biannual progress reports, quarterly consolidated financial reports, final project report, and other reports required by UNDP;

- -Provide input to the National Project Manager in the development of project reports, including progress reports and the final project report, to the Project Steering Committee;

- -With support from the Project Administrator, ensure compliance of the project by providing regular information to the UNDP corporate systems (ATLAS, Transparency Dashboard, Sharepoint, ATLAS Risk Log, Results Orientated Annual Reporting (ROAR) processes, PIMS+ etc

- -Work in close collaboration with the UNDP South Africa Climate and Environment Programme Manager, the BIOFIN Technical Adviser (global) and the BIOFIN National Project Manager/ Team Leader (DEFF) to ensure the exchange and sharing of experiences and lessons learned from relevant cross-cutting capacity development and environmental projects, both nationally and internationally.

- 3. Strategic partnerships, promotion and awareness (10%):

- -Work with the National Project Manager to create strategic alliances with other partners on biodiversity finance;

- -Facilitate collaboration between partners and key stakeholders in the development of finance solutions, including but not limited to National Treasury, SANBI, DEFF, and key NGOs;

- -Provide input to relevant UNDP and DEFF communication initiatives associated with the BIOFIN project (e.g. social platforms, documentaries, radio programming, television spots and awareness campaigns, case studies, etc.), increasing the awareness of the project within South Africa, regionally and globally.

- 4.  Deliverables:

- -Finalisation of implementation plans for all finance solutions;

- -Finalised terms of reference for the appointment of consultants in line with the Annual Work Plan;

- -Delivery of biodiversity finance solutions as set out in the implementation plans and Annual Work Plan

- -Contributions to Annual Work Plan revisions, quarterly and annual reports and all other project reports available on time;

- -Thematic notes and briefing notes on the BIOFIN topics produced and shared;

- -Contributions to project reports, including biannual reports and final project report;

- -Project evaluations and BIOFIN global team missions carried out and recommendations followed.

- -Preparation and organization of secure information on the execution of the project, contributions for the monitoring and evaluation of UNDP Country Programme Document (CPD), the UN Strategic Development Cooperation Framework (UNSCDF) in South Africa;

- -Final review of the budget and financial closure of the project 12 months after the project's operational term

- Competencies

- Core

- Innovation

- -Ability to make new and useful ideas work

- Leadership

- -Ability to persuade others to follow

- People Management

- -Ability to improve performance and satisfaction

- Communication

- -Ability to listen, adapt, persuade and transform

- Delivery

- -Ability to get things done while exercising good judgement

- Technical/Functional

- Results-Based Programme Development and Management

- -Provides information and documentation on specific stages of projects/programme implementation

- Building Strategic Partnerships

- -Ability to develop, maintain, and strengthen partnerships with others inside (Programmes/Projects) or outside the organization who can provide information, assistance, and support.

- -Sets overall direction for the formation and management of strategic relationships contributing to the overall positioning of UNDP.

- Sustainable Development Goals

- -Knowledge of the Sustainable Development Goals and the ability to apply to strategic and/or practical situations

- Innovation and Marketing New Approaches

- -Documents and tracks innovative strategies/best practices/new approaches

- Team Building

- -Ability to work effectively with diverse groups of professionals towards common goals.

- Resource Mobilization

- -Maintains information/databases on potential and actual donors

- -Maintains database of project files

- -Provides data and information needed for preparation of project documents

- Job Knowledge/Technical Expertise

- -Understands the main processes and methods of work regarding to the position

- -Possesses basic knowledge of organizational policies and procedures relating to the position and applies them consistently in work tasks

- -Demonstrates good knowledge of information technology and applies it in work assignments

- Required Skills and Experience

- Education:

- -University degree (Master's or doctoral degree) in environmental economics, economics, biodiversity conservation or public policy with a strong focus on biodiversity finance or environmental economics, or closely related area.

- Experience:

- -At least 8 years’ experience in biodiversity finance, environmental economics, or closely related field;

- -At least 5 years of experience in programme management, or consultancy and advisory services which include implementation, monitoring and evaluation;

- -Experience in dealing with international and national experts across government and institutions related to research and/or advocacy institutions;

- -Knowledge of UNDP project implementation procedures, including procurement, disbursements and reporting and monitoring will be an added advantage;

- -Experience of strong professional relationship building;

- -High competence in MS Office

# Annexure 5: Logical/Results Framework

Table 1 below shows the logical framework for the three-year project. Monitoring and evaluation will be undertaken at two levels; namely at BIOFIN programme level to monitor if the overall objectives are being met and at project level for each of the financial solution.

The monitoring and evaluation framework will seek to answer two questions:

1. What is the status of BIOFIN activities and results?

2. What is the impact of BIOFIN finance solutions in South Africa?

Table 1. Logical Framework of high level outcomes and finance solutions outcomes

| Expected outputs | Indicators | Baseline |  |  |  | Risks | Mitigation |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2020 | 2021 | 2022 |  |  |
| HIGH LEVEL OUTCOMES : BIOFIN |  |  |  |  |  |  |  |
| Effective communication strategy in place® | Complete communication strategy | No strategy in place | 100% complete |  |  | Inability to complete strategy Lack of participation | Include stakeholders in Task Teams on FS implementation and provide regular feedback |
|  | Number of policy information briefs on BIOFIN produced | 0 | 3 | 4 | 7 |  |  |
|  | Number of stakeholders with increased practitioner knowledge on the specific finance solution through direct participation in the implementation of the finance solution | NA | 10 | 15 | 30 |  |  |
| ®Communication strategy will be completed and BIOFIN communicated via different platforms |  |  |  |  |  |  |  |
| Capacity building in biodiversity finance management® | Number of workshops on expenditure reporting | NA (new) | 3 | 5 | 7 | Staff rotation | Written request for representation and commitment to attend capacity building sessions |
|  | Number of stakeholders trained in results based budgeting | NA (new) | 10 | 20 | 20 |  |  |
| ®This is part of institutionalization and BIOFIN will work with National and provincial treasury on implementation |  |  |  |  |  |  |  |
| Knowledge management to share and exchange information on finance solution® | Number of public awareness events on BIOFIN | 4 | 8 | 8 | 8 | No awareness events to share BIOFIN information | Identify and include BIOFIN as an agenda item in opportune platforms |
|  | Number of BIOFIN awareness materials produced | 100 (pop-ups, brochures and T-shirts) | 100 | 150 | 150 |  |  |
| ®It is the intention to use available and new platforms that are relevant where knowledge can be shared |  |  |  |  |  |  |  |

| Financial Solution | Expected Outputs | Indicators | Baseline | Targets |  |  | Risks | Measures |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2019 | 2020 | 2021 | 2022 |  |  |
| Growing protected area own revenue in four provinces | Increased revenue in state-run protected areas | Percentage increase in the amount of revenue generated in provincial protected area management authority | In 2016, provincial conservation management authorities generated R 452 million in own revenue. |  |  | 4% (above inflation) growth in revenue generated and retained through associated activities in selected Management Authorities. | - Insufficient capacity and technical expertise to implement outcomes of the sustainable financing strategies - Inability to develop a suitable model for revenue retention in MAs. | - Additional capacity supplied by members of the PMU. - Additional capacity supplied by members of the PMU |
|  |  | Sustainable financial strategies developed | No existing strategies for selected MAs. | Convene task teams and establish accounting framework for reporting | Strategies developed and implemented. |  |  |  |
| Reform of property rates legislation, interpretation and application to protected areas | Application of the correct interpretation of section 17 (e) and (g) of the Municipal Property Rates Act in relation to protected areas. | Percentage reduction in property rates charged on protected areas, for all relevant PAs | R240 million per annum spent on property rates by SANParks and 10 management authorities. |  |  | 50% reduction in property rates | - Inability to carry out additional technical and legal work due to limited resources/capacity. - Inability to reach a workable agreement with Cooperative Governance and Traditional Affairs and National Treasury. | - Additional capacity supplied by members of the PMU. - Establish a high-level political engagement and cooperation between DEFF, Cooperative Governance & Traditional Affairs and National Treasury. |
|  |  | Development of a national framework. | No national framework in place. |  |  | National framework developed and applied by all Municipalities |  |  |
| Building a grant mechanism to adequately finance the biodiversity stewardship programmes | Budget from the fiscus and other sources tagged to fund stewardship programmes | National funds routed directly to provinces for provincial biodiversity stewardship type programs for PA expansion, climate resilience, watershed management | R0 |  |  | R80 million (USD6 million) p.a. grant program | - Pressure on the fiscal framework or existing commitments prevents DEFF budget including a conditional grant component. - Some provinces may substitute national program funds for their budget commitments to various conservation agencies’ stewardship efforts. | - Development of a value proposition to the Minister’s and MEC’s forum to support the flexible, systematic and low-cost stewardship approach. - Managed through building a matching requirement into the grant program structure and tracking provincial allocations through the annual expenditure review. |
|  |  | Provincial treasury allocations to provincial biodiversity stewardship programs | R22 million (2018/9) |  |  | R40 million (USD3 million) p.a. mobilized |  |  |
|  |  | Existence of conditional grant type mechanism in environment sector | None exists |  |  | A grant framework structure is in place. |  |  |
|  |  | Number of stewardship sites using innovative funding sources for rehabilitation and management. | Zero |  |  | Five sites (using water tariff, impact investment, or offset funds). |  |  |
| Institutional support for biodiversity tax incentives | Legislative amendment of Section 37 of the Income Tax Act (ITA). | Amendment of Section 37C of the ITA. | Defunct incentive and no financial mobilization for non-state protected area management. |  |  | The ITA will be amended to create a new effective biodiversity tax incentive. | - Lack of technical capacity within DEFF and the PMU to structure and sufficiently analyse the FS. - Lack of buy-in or agreement by National Treasury regarding policy and legislative structuring and amendments. - Lack of buy-in by the South African Revenue Service regarding legal and tax interpretation and appropriation of tax incentives. | - Local consultant with niche technical capacity regarding tax matters, environmental legislation & biodiversity stewardship to be contracted. - Preparation of material to make the case for FS and high-level cooperation between local consultant, DEFF representative and National Treasury officials. - Pilot amendments at selected sites to determine the practical approach to the incentive with taxpayers and communicate all practical implementation approaches, errors, areas of interpretation, etc. to SARS |
|  |  | Testing of new tax incentive at pilot sites. | No actual or empirical testing of the proposed new biodiversity tax incentive. |  |  | A minimum of 7 pilot sites are selected to test the new tax incentive. This includes assisting in securing an additional 50 000 ha of protected area. |  |  |
|  |  | Appropriating the new tax incentive for management costs in a landowner’s tax return. | No financial benefit for the management costs incurred on non-state protected areas. |  |  | A minimum of one tax return is completed for a pilot site to appropriate the new tax incentive and receive the deduction for costs incurred to affect the required management plan. |  |  |
| Improved biodiversity offset modality for protected area expansion | An increase in PAs established through biodiversity offset decisions, based on the application of the mitigation hierarchy | An offset bank in place where DEFF authorized development is likely to occur | No bank in place |  |  | An offset bank type system in place around 3 protected areas, totaling 50 000 ha | - Offset banking may facilitate inappropriate developments which would otherwise not be permitted. - Reluctance and institutional inertia among state PA management authorities to take on additional land for PAs. - Lack of uptake of offset banks by regulators and/or development applicants - Department of Mineral Resources may impede the establishment of offset banks or frustrate declaration of new protected areas | - DEFF must maintain the criteria around impacts which are not offsetable or otherwise unacceptable. - Implementation policies will be developed with SANParks and provincial conservation agencies with appropriate risk management. - This will be piloted for the developments authorised by DEFF, which manages this risk. - Appropriate engagement at the various cooperative governance forums by DEFF and SANParks will assist with this, as will an indication that this process may reduce environmental resistance to mineral developments provided pre-emptive mitigation is in place. |
|  |  | Annual funding flow to offset bank | Zero |  |  | R15 million per annum flows to offset bank management authorities |  |  |
|  |  | Protocol for facilitating development through proactive offsets | No protocol exists | Protocol in place |  |  |  |  |
|  |  | Offsets register developed and maintained in DEFF for monitoring offset bank performance and verifying compliance with Environmental Authorisations | A preliminary register last updated in 2016 by SANBI |  |  | An up to date (i.e. 30 days lag time from issuance of Environmental Authorisations) offset register exists as part of the IEM tracking systems for development authorisations |  |  |
| Development and implementation of a voluntary market-based certification scheme in the wildlife sector | A certification system for the game ranch industry is developed and implemented which verifies best environmental management practices | Percentage of potential conservation area under game ranch management certified | 0 % potential conservation area under game ranch management certified. |  |  | 1-5% (200 000 – 1 million ha) of privately-owned game ranches certified. | - Limited uptake of the proposed scheme by the ranching sector and potential consumers. - There is a risk of greenwashing i.e. conveying a false impression on how sustainable the sector’s environmental sector are. - A Wildlife ranching certification scheme could result in businesses with unsustainable practices being forced out of the market. This could lead to job losses. | - This is mitigated through the provision of two activities involving considerable stakeholder engagement with the sector where the certification scheme is introduced and tested. - A management response to this would be the building in a good independent auditing processes to avoid green washing. - The feasibility study will assess how job creation will be enhanced to supersede job losses from non-compliant businesses. |
|  |  | Percentage of potential conservation area (assessed Other Effective Area-Based Conservation) under game ranch management certified. | 0 % potential conservation area under game ranch management certified. |  |  | 0, 5% (100 000 ha) of privately-owned certified game ranches assessed as OECMs. |  |  |
|  |  | Number of female owned game ranches supported to become certified. | 0 % female owned game ranches supported and certified. |  |  | 10 female owned game ranches supported and certified. |  |  |
| Developing and promoting an online biodiversity economy investment portal | Through the investment portal, investors are able to invest in additional 50 000 ha of biodiversity stewardship sites which contribute to the conservation estate | Number of hectares of stewardship area added. | 450 000 ha secured under Biodiversity Stewardship agreements. |  |  | 50 000 ha of additional stewardship sites added to the conservation estate. | - There is a risk that projects profiled on the investment platform may not be environmentally sustainable. - There is a risk that identified projects may not be financially sustainable and rural communities | - Through the investment prospectus, all projects profiled on the platform will adhere to acceptable environmental standards. In addition, the PMU will ensure that investors do not engage in any of the exclusionary criteria as outlined in the private sector partner tool of UNDP. - Through the investment prospectus, all projects profiled on the platform will adhere to acceptable social and financial standards. |
|  |  | Number of Biodiversity Stewardship Sites that have a developed Investment Prospectus. | 0 Biodiversity Stewardship sites with a developed Investment Prospectus. |  |  | 10 Biodiversity Stewardship sites with a developed Investment Prospectus. |  |  |

# Annexure 6: Gender Action Plan

The UNDP GEF Gender Guidelines are used as reference in developing a gender action plan for Phase 2 of BIOFIN. In this regard, gender will be mainstreamed at various levels of implementation where appropriate and include actions in meeting the following requirements as shown in Table 1

Table 1 Requirements, measures and actions

| REQUIREMENT | MEASURES | ACTIONS |
| --- | --- | --- |
| Institutional capacity for gender mainstreaming | Within DEFF, SANBI and UNDP as partners in overall implementation, there is institutional capacity to mainstream gender The BIOFIN Project Reference Group will be chaired by the COO who is DEFF focal point on gender | - Involve respective gender experts in project design |
| Consideration of gender elements in project design implementation and review | In the design of the strategy, gender issues are key to implementation | - For each financial solution, gender issues will be mainstreamed in terms of participation of women and youth |
| Undertaking project gender analysis | An analysis of number of women, skills and expertise available and gaps in skills will be determined | - Determine the number of women involved in the whole project lifecycle - Undertake a gender analysis and make recommendations on mainstreaming |
| Measures to minimise and mitigate adverse gender impacts | Projects will demonstrate impacts on gender and capitalize on positive impacts | - Gender impact analysis will be undertaken for each project to be implemented |
| Integration of gender sensitive activities | Finance solutions will include gender related activities | - Include women as participants and beneficiaries of finance solutions |
| Monitoring and evaluation of gender mainstreaming progress | Indicators will include gender mainstreaming | - The M & E framework for each finance solutions include gender indicators - Gender experts will be engaged in M & E |
| Inclusion of gender experts in the projects | Where appropriate in the implementation, gender experts will be involved | - BIOFIN governance and implementation of Finance Solutions include gender experts. |

Table 2: High level Action Plan at Project Implementation level

| Gender Action Plan Template with Examples |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Project-level outcome: Women participating in biodiversity financial solutions and benefitting from returns |  |  |  |  |  |  |
| Gender-related activity | Indicator | Target | Baseline | Budget | Timeline | Responsibility |
| Women participating in design of financial solution | % increase on women participation | 50% gender parity | TBD | TBD | 2-3 years | PSC |
| Women benefitting from financial solution | % increase in benefits | 50% gender parity | TBD | TBD | 2- 3 years | PSC and PMT |

Please add budget years if needed.

This document refers to ten conservation authorities: SANParks, the national conservation authority, which manages National Parks, and the nine provincial conservation authorities, operational in the nine provinces of South Africa

Please add budget years if needed.

The Municipal Property Rates Act refers specifically to areas as specified in the National Environmental Management: Protected Areas Act, 2003 (Act No. 57 of 2003), or of a national botanical garden within the meaning of the National Environmental Management: Biodiversity Act, 2004 (Act No. 10 of 2004).

Please add budget years if needed.

Please add budget years if needed.

The value is an election between either the acquisition or improvement cost of the land or the value determined by a valuation formula incorporating municipal or market value and capital gains tax.

Please add budget years if needed.

Please add budget years if needed.

Please add budget years if needed.

Please add budget years if needed.

Please add budget years if needed.