# Annual Progress Report 2025:

# Joint Programme in the High Impact Track

Reporting period: From the start date of the joint programme (JP) until 31 December 2025.

- Please be succinct and to the point, focusing on the most important accomplishments and issues that you want to bring to the attention of the Joint SDG Fund at the global level.

- Please do not exceed the word limit for each narrative question.

- Please feel free to contact your main focal point in the Joint SDG Fund Secretariat for questions and support:

  - Food systems: Vittoria.Gemelli@un.org

  - Digital and Global Accelerator: Maya.Marquez@un.org

  - SDG Localization and SDG Investments (C2): Maria.Berenguer@un.org

Submission deadline from RCOs on behalf of RCs and the JP team: 31 January 2026. Please submit this document through this link:  https://forms.cloud.microsoft/e/ZQ8AFTeUr1

https://forms.office.com/e/ZQ8AFTeUr1

# COVER PAGE

| JOINT PROGRAMME (JP) PROFILE: |  |
| --- | --- |
| Country | Sri Lanka |
| JP title | Transforming Local Administrative Data Collection for SDG Acceleration in Sri Lanka |
| Funding Round | Digital Transformation |
| JP TEAM: |  |
| Resident Coordinator | Name: Marc-André Franche Email: franche@un.org |
| JP’s RCO focal point | Name: Azam Bakeer Markar Title: Development Coordination Officer, Partnerships & Development Finance Email: azam.bakeermarkar@un.org |
| Lead PUNO focal point | Name: Yasas Thalagala Title/Organisation: Team Lead – Strategic Engagement, Digital and Innovation Team, UNDP in Sri Lanka Email: yasas.thalagala@undp.org |
| PUNOs focal points | Name: Dr Chatura Wijesundara Title/Organisation: National Professional Officer – Health Economics and Systems Analysis Email: wijesundarac@who.int |
| JP’s designated communications focal point | Name: Title: Organisation: Email: |

​

Rate the overall performance of the JP:

Did the JP deliver its key results as planned in the ProDoc?

☐  Unsatisfactory, Marginal Achievement: Less than 50% of expected results delivered.

☒  Satisfactory Achievement: 50-75% of expected results delivered.

☐  Very Good, Solid Achievement: 100% of expected results delivered; implementation completed on schedule.

☐  Exceptional, Outstanding Achievement: 100% of expected results delivered ahead of schedule, with additional results or improvements delivered.

## Results Narrative

The narrative section provides a succinct description of the progress and results achieved during this reporting period, as per the JP document, including the theory of change and results framework. Please be specific and focus on results, not process or activities, and use bullet points whenever possible.

1. Systems-level Transformation:

What overarching systems-level changes under your key transition area is the JP catalyzing? Please show the relationship between your JP’s interventions and its longer-term strategic intent. Provide descriptions of emerging change in relevant areas of behavior, relationships, power dynamics and institutions, resources and mindsets as described below:

Anchored in the SDG transition area of Digital Transformation, the Joint Programme (JP), “OneRegistry” is catalyzing systems-level change by strengthening Sri Lanka’s Civil Registration and Vital Statistics (CRVS) system as foundational element of the country’s digital public infrastructure. Aligned with national digital priorities, the JP’s interventions support a long-term shift toward integrated, interoperable, and citizen-centred identity and data systems, directly advancing SDG Targets 16.9, 16.10, and 17.18.

During this reporting period, early but tangible changes indicate that systems-level transformation is underway, while establishing the foundation for planned project outcomes.

- Behaviors - How are key stakeholders (government, private sector, civil society, communities) acting differently to accelerate the progress on SDGs and produce transformative impact?

- A  notable shift in executive leadership has catalyzed and scaled systemic behavioral change. A high-level coalition of Ministry of Public Administration (PubAd), Ministry of Digital Economy (MoDE), is now applying sustained,  high level political leadership for integrated digital systems (Annex 01).

- This strategic elevation of the level of leadership ensures whole-of-government alignment and accelerates systemic adoption across ministries and departments, as demonstrated by the joint finalization of a foundational Cabinet Memorandum and cross-agency technical specifications within an eight-month inception phase.

- At the societal level, demand for digital resilience has intensified, particularly among communities affected by Cyclone Ditwah, marked a shift from accepting "repeated visits and high transaction costs" (ToC Gap). The failure of manual processes during the crisis has catalyzed bottom-up advocacy for accessible, equitable, and crisis-resilient digital services, reshaping citizen expectations and strengthening progress toward SDG 16.7.

- The shift from manual to digital processes in Sri Lanka's private sector is being driven by a focus on "Facilitating Conditions", which the JP is leveraging.

- Relationships - New forms of collaboration and coordination or engagement have emerged among actors who previously worked in silos, with evidence that it has catalytic effect on the domain of change the JP is involved in?

The JP has catalysed a shift from project-led coordination, towards a more government-led frequent, collaboration among institutions previously working in silos.

- The JP is facilitating a transition from "fragmented workflows" (ToC Gap) wherein collaboration has evolved from JP-facilitated to Stakeholder-led engagement mechanisms of increasing frequency and effectiveness verified through Technical Review Committee minutes.

- Evidenced by the collaborative development of Cabinet Memorandum and coordinated approvals from the National Planning Department (NPD), the Registrar General’s Department (RGD), PubAd, MoDE, demonstrating increased commitment to policy reform and JP outcomes (Annex 02.B).

- Strategic partnerships, including JP support to Digital Economy Expert Support Unit (DEESU) by JP, are strengthening the foundation for digital transformation ecosystem for OneRegistry.

- These actions reflect stronger institutional alignment, collective ownership, and coordination for the JP outcomes, and government’s digital transformation agenda

- Grievance Redress Mechanism (GRM) is being assessed for inclusion as a ToC Output, to strengthen trust, accountability, and state–citizen relationships (Intermediary Outcome of 'improved trust’) contributing to modernization of the social contract. (Annex 03)

- Power Dynamics - How has decision-making authority or influence shifted towards more systemic impact across individual sectors, industries and policy issues? Who has gained voice or agency in processes that affect them?

- The JP has structured a new governance model that clarifies authority to accelerate systemic change, with the MoDE providing technical leadership, the Ministry of Public Administration driving implementation, and the Registra General’s Department acting as the institutional custodian. This structured mandate is further supported by high-level policy engagement from the Presidential Secretariat and technical expertise of the Ministry of Health, ensuring alignment from policy to execution.

- Furthermore, by embedding a Leaving No One Behind (LNOB) pathway into its design, the JP ensures that evidence from completed baseline and advocacy studies directly informs system recalibration. This shifts power by giving marginalized communities (e.g estate sector populations), a formal voice in shaping the services that affect them.

- The JP is redefining legal identity from a transactional output into the foundational prerequisite for social protection and civic inclusion. (ToC Outcome – Band 4)

- Mindsets -What shifts in understanding, framing, or values are emerging about the challenges and solutions your JP addresses?

A significant mindset shift among key stakeholder leadership has directly transformed operational methodologies. This is evidenced by the Registrar General’s Department proactively leveraging the new Cabinet Memorandum to diagnose and address critical systemic gaps in technical infrastructure and legal frameworks of the existing system.

At the community level, a clear paradigm shift toward digital transformation is underway. This evolution in public perception is quantitatively demonstrated by a baseline survey, in which 65% of respondents now explicitly value digital-first approaches as essential tools for building personal and communal resilience against future shocks, such as climatic disasters like Cyclone Ditwah.

(max 600 words)

2. Policy, regulatory, and capacity shifts:

What policy, regulatory, and capacity shifts has the JP contributed to achieving? Provide a narrative that includes:

The JP has been instrumental in driving high-impact shifts in policy, regulation, and institutional capacity, establishing a robust enabling environment for sustainable digital transformation.

2.1 New or revised policies, regulations, or institutional frameworks developed and adopted at national or sub-national levels as result of the JP;

- The JP has directly influenced and accelerated the adoption of critical national frameworks. Its outcomes are now formally institutionalized within the Cabinet-approved National Digital Economy Blueprint (NDEB), which positions interoperable civil registration as a core component of Sri Lanka’s Digital Public Infrastructure (DPI). This strategic integration was secured through JP-facilitated technical expertise and policy guidance to the Digital Economy Experts Support Unit (DEESU), of the Ministry of Digital Economy, ensuring the CRVS agenda was anchored at the highest level of national planning, accelerating SDGs.

- This strategic elevation transforms the JP from a standalone initiative into a national digital infrastructure asset essential for broader economic and governance reform.

- Concurrently, the pursuit of a dedicated Cabinet Memorandum for the JP seeks to mandate whole-of-government authorization, resolving historical stakeholder fragmentation and creating legally grounded obligations for integrated system development. This is further reinforced by an independent diagnostic study commissioned to provide an objective, evidence-based pathway forward, mitigating a key barrier to consensus and execution.

2.2 Evidence of the broader impact of capacity-building initiatives introduced at scale (including new methodologies, training modules, or standard operating procedures);

The JP has initiated comprehensive capacity-building initiatives designed to build the human capital foundation required for a sustainable digital transition. This systemic approach ensures both the technical competency of operational staff and the strategic leadership necessary to institutionalize reforms.

The JP through the, Capacity Strengthening and Development Programme for the RGD, has mapped specific competencies, needs and targets for 3,000 staff required to operate a digitalized, interoperable CRVS system (Annex 04). This evidence-based blueprint directly informs the development of standardized training modules, a Trainer-of-Trainers (ToT) program, and modules for a scalable Learning Management System (LMS) for long-term, consistent, large-scale upskilling that addresses technical gaps while embedding SDG principles into service delivery. (Annex 05). Parallelly, RGD to Digital Excellence (RGD2DE) Programme (Annex 06 is strengthening the senior management cadre’s capacity for strategic leadership, change management, and data-driven decision-making required to champion the reform agenda, guide complex implementation, and translate new policies into tangible institutional outcomes, thereby ensuring reforms are owned and sustained from within.

2.3 Describe how these changes align with national priorities;

These changes are directly aligned with Sri Lanka’s national priorities on digital transformation and public sector modernisation, as articulated through Cabinet-level policy instruments. The Cabinet Memorandum on the National Digital Economy Blueprint (NDEB) positions foundational registries, verifiable credentials, and interoperable core government systems as critical components of national Digital Public Infrastructure (DPI). Within this framework, JP outcomes particularly the digitalisation of the CRVS system is recognized as an a national digital priority.

By situating CRVS digitalization as a foundational population registry, the JP aligns with national economic and governance reform objectives rather than operating as a standalone project intervention. This framing elevates the JP (outcomes) to a national digital infrastructure asset, reinforcing coherence across digital government initiatives.

In parallel, the Cabinet Memorandum on the JP and OneRegistry reflects a strategic shift toward state-mandated, system-wide reform, reducing fragmentation and discretionary adoption across institutions. This approach strengthens policy coherence and ensures alignment of multiple actors with a unified national digital transformation agenda. Capacity development programmes (CSDP, RGD2DE) further reinforce national priorities by enabling stakeholders to operationalize these policy commitments through JP strengthened systems, institutional readiness, and leadership capacity.

Collectively, these changes ensure that JP-supported reforms are embedded within national frameworks, enhancing policy uptake, implementation effectiveness, and long-term sustainability.

2.4 Describe how these changes support Cooperation Framework results, the Leaving No One Behind principle, and their catalytic effect for JP outcomes and for sustainability prospects.

These systemic changes constitute a direct contribution to the UN Sri Lanka Sustainable Development Cooperation Framework Results Group 4: Inclusive Governance, Justice and Rule of Law.

By transforming civil registration into a reliable source of timely and disaggregated data, the initiative strengthens accessibility, production, and usability for evidence-based policymaking and enhances national reporting against SDG indicator 17.18.1 (UNSDG Output Indicator Framework, Outcome 4.4). The initiative also actively institutionalizes the Leaving No One Behind (LNOB) principle, through targeted streamlining of registration processes in selected high-vulnerability divisions, including estate communities. This would help eliminate critical administrative bottlenecks and reduce processing delays (JP ProDoc – Expected Results 1 and 3), ensuring equitable access to foundational legal identity.

Collectively, these policy, regulatory, and capacity shifts generate a powerful catalytic effect. They create the enabling environment necessary to accelerate JP outcomes while simultaneously engineering the institutional ownership and operational readiness that guarantee long-term sustainability of governance reforms, thereby securing the legacy of the Cooperation Framework’s strategic investment.

(max 500 words)

3. Financing solutions and resource flows:

3.1. Complete the table below providing only actual US$ amount mobilized. Do not list potential resources expected to be mobilized in the future.

| Source of Financing | Type of Source (e.g. PUNO, PPP, DFI, donors, private sector, etc.) | Planned amount in the ProDoc | Actual amount mobilized as of reporting date |
| --- | --- | --- | --- |
| UNDP Sri Lanka | PUNO - UNDP | $ | $69,280.00 |
| UNDP Regional Bureau – Asia Pacific | PUNO - UNDP | $ | $ 22,560.00 |
| UNDP Chief Digital Office | PUNO - UNDP | $ | $ 42,500.00 |
| Huawei | Private Sector | $ | $ 11,343.50 |
| Vital Strategies | Non-Profit | $ | $ 10,000.00 |
| ADB | DFI | $ | $ 18,700.00 |
| TOTAL |  | $ | $ 174,383.50 |

3.2. What financing channels and pathways has the JP developed or influenced? Provide a narrative describing: the "deal room" or financing mix created; how the JP has influenced government budgets and/or broader financing flows; financial instruments, solutions, or processes developed; and any pipeline of investment-ready projects or initiatives established with public and private partners. Detail the financial leverage achieved and explain how these financing mechanisms and partnerships align with national and JP priorities.

The JP has successfully secured and deployed an additional USD 134,340 through strategic internal UNDP financing channels, including UNDP Sri Lanka Country Office, the Regional Bureau for Asia and the Pacific (RBAP), and the Chief Digital Office (CDO). This catalytic funding has been intentionally allocated to high-leverage activities: RBAP resources financed critical technical advisory support and high-level ecosystem mobilization, culminating in the landmark DPI Summit and official project launch. Concurrently, resources from the CDO and Country Office have provided direct, sustained support to the Ministry of Digital Economy’s expert unit (DEESU), directly strengthening the government’s core capacity to lead the DPI and public sector digitalization agenda.

Beyond direct mobilization, the JP’s primary financial impact lies in strategically influencing and aligning public sector investment. By embedding CRVS digitalization within the national Digital Economy Blueprint and creating explicit linkages to national initiatives like the e-NIC and Sri Lanka Unique Digital Identity (SLUDI), the JP has successfully positioned CRVS as a foundational investment within the government’s own digital transformation priorities. This reframing shifts the business case from a standalone project to an essential component of a coordinated, government-led financing strategy for scale-up, thereby directly influencing future budget cycles and reducing fragmentation in public digital spending

(max 500 words)

4. Strategic Partnerships and Stakeholder Engagement

4.1. What type of partnerships has your JP established or is in the process of establishing? (Select all that apply)

☒   National Government Institutions (Please specify): Ministry of Public Administration, Provincial Councils and Local Government, Ministry of Digital Economy, Ministry of Health and Mass Media, Department of Census and Statistics, Registrar General’s Department, National Planning Department, GovTech, SLCERT

☒  Sub-national Government Institutions (Please specify): Divisional Secretariats

☒  International Financial Institutions & Development Finance Institutions (Please specify): Asian Development Bank

☒  Private Sector Companies or Industry Associations (Please specify): OpenCRVS, Vital Strategies, Huawei, Deloitte

☒  Civil Society Organizations, Philanthropic Organizations and Foundations (Please specify): Federation of Information Technology Industry Sri Lanka

☒  Academic/Research Institutions (Please specify): University of Moratuwa

☐  Bilateral Development Partners (Please specify):

☐  European Union (Please specify):

☐  Labour Unions or Organizations (Please specify):

☒  Others (Please specify): UN Office for Digital and Emerging Technologies

4.2. Describe the strategic partnerships you have established focusing on the impact regarding financing and/or policy and systems change. Provide a narrative that: identifies the key partners selected above and explains the nature of engagement with each; and notes any formal partnership arrangements established (such as MOU or similar agreements). Explain how these partnerships have expanded the JP's reach, leveraged additional resources or expertise, and contributed to achieving results at scale.

The Joint Programme has forged and leveraged a strategic multi-stakeholder coalitions to accelerate policy reform, de-risk implementation, and mobilize high-level resources for sustainable scale.

- National and sub-national institutions:

The JP’s core strategy has been to transform institutional fragmentation into a unified, government-led execution framework. By convening and facilitating a high - level stakeholders specifically MoDE, PubAd, RGD, the JP facilitated the establishment of joint committees define clear mandates and institutional roles. This foundational partnership model has directly generated increased institutional ownership and created the operational conditions necessary for future scale, turning disparate stakeholders into a coordinated delivery mechanism for national DPI.

- Private sector partners:

Mobilizing expertise and accelerating readiness through strategic engagements with the private sector have provided critical leverage. Deloitte and Huawei served as catalytic stratergic partners, significantly amplifying the reach and impact of the landmark DPI Summit and project launch, thereby elevating national policy dialogue. Concurrently, the pro bono technical partnership with OpenCRVS, the government mandated software provider, is directly covering certain foundational system development costs, a contribution that dramatically accelerates technical readiness and de-risks the implementation timeline.

- Academic and research institutions (University of Moratuwa):

Ensuring evidence-based to ground the transformation in objective analysis and global standards, the JP has partnered for an independent Institutional Diagnostic Study with University of Moratuwa to provide evidentiary foundation for the Cabinet Memorandum, ensuring the technical pathway is objectively validated.

- UN system partners (UN Office for Digital and Emerging Technologies):

Collaboration with the UN Office for Digital and Emerging Technologies guarantees that system design maintains policy coherence with global DPI standards, safeguarding interoperability and future-proofing the national investment.

4.3. Describe the nature and outcomes of your joint programme’s engagement with the EU to date. What specific actions are planned to strengthen EU involvement in 2026? Please highlight concrete opportunities to expand or diversify EU partnerships and investments in support of the JP’s objectives, including any new areas for collaboration or co-financing.

Notes – RCO/RR engagements with EUAMB, possible EUAMB field visit in 2026.

(max 300 words)

5. Constraints, Adjustments and Lessons Learned:

What key constraints or risks has the JP encountered during the reporting period, and how has the JP team responded? Provide a narrative describing: significant contextual, strategic, operational, or technical challenges faced; adjustments made or mitigation actions taken to strengthen the JP's relevance, effectiveness, and coordination; any measures introduced to enhance JP efficiency and reduce transaction costs (such as joint procurement, management arrangements, or monitoring mechanisms); and lessons learned—both positive and negative—about what worked well and what could have been done differently.

During the reporting period, the Joint Programme navigated a complex implementation landscape shaped by two interconnected constraints: stakeholder readiness for digital transformation and delays in securing formal Cabinet approval. The response to these challenges involved strategic adjustments, proactive engagement, and embedded mitigation measures to safeguard the project’s relevance and long-term sustainability.

Initial stages revealed a significant gap in technical and human capacity across the civil registration ecosystem. Resistance stemmed not from opposition, but from unfamiliarity with digital systems, alongside divergent institutional priorities. Concurrently, uncertainty around formal Cabinet endorsement created an early bottleneck, delaying the cross-ministerial authorizations needed to advance full-scale system development.

The programme proactively managed several compounding risks through targeted actions. A multi-stakeholder engagement strategy, including 19 formal and 30 informal sessions since January 2025, maintained momentum amid institutional changes and prevented over-reliance on any single ministry. Identified infrastructure and skill gaps now directly inform capacity development initiatives, ensuring solutions are co-designed and nationally owned.

Persistent reliance on paper-based systems continues to limit the production of disaggregated, quality data, challenging the Leave No One Behind mandate. This risk will remain until digital transformation reaches critical mass. In contrast, the risk of perpetuating gender bias through legacy data systems was closed by embedding gender-sensitivity as a mandatory technical requirement in all new tools, informed by dedicated consultations.

In response to core constraints, implementation shifted from a linear to a strategically re-sequenced approach. Ecosystem preparation was prioritized, with comprehensive systems mapping, business process re-engineering, and training for 611 officials completed before major technical deployment. Cabinet approval was treated as a critical milestone, with parallel preparatory work avoiding idle time. A high-level meeting convened by the Resident Coordinator bringing together key Ministers and Ministry Secretaries helped fast-track this process Furthermore, a “Technical Sovereignty” approach was adopted, evidenced by the co-design of a Training Needs Assessment with key national agencies, ensuring local ownership from the outset.

Efficiency was enhanced through several measures: joint and bulk procurement for operational activities; pro bono technical collaboration reducing development costs; and streamlined management via the JP Steering Committee co-chairs.

Key lessons emerged from this period. Human and institutional readiness is a prerequisite for technical success. Formal Cabinet authorization, though slowing initial pace, ensured sustainability and high-level anchoring. Conducting diagnostic mapping and needs assessments before procurement allowed for precisely targeted resources, minimizing waste.

These insights directly shape the forward path. Future strategy will adopt a more proactive posture in managing governmental dependencies, flagging decision points early to align expectations. The focus for the coming year will shift to system development and scaling, advancing within a now-prepared and formally authorized ecosystem.

.

(max 500 words)

6. 2026 Plans and Exit Strategy:

What are the JP's priorities for 2026 and beyond, to ensure sustained impact? Provide a narrative describing: 1) key priorities for 2026 focused on financing and financial leverage, strategic partnerships, and transformative impact; 2) the exit strategy developed and how it is being mainstreamed throughout implementation to sustain transformative impact in the mid-to long-term, including mechanisms for resource mobilization, capacity strengthening, transfer of assets when applicable, phase-over of activities/services to local stakeholders and pathways for government and partner-led scaling after JP completion.

A. 2026 Plans – Key Priorities for Sustained and Transformative Impact

In 2026, the Joint Programme will pivot from strategic design to scaled implementation, to ensure a self-sustaining digital transformation of the CRVS system. This transition will align four critical success factors including policy authorization, institutional readiness, technical deployment, and sustainable financing to institutionalize systemic change and ensure durable impact beyond the project lifecycle.

A central priority will be system development readiness, including finalisation of the Functional Requirements Specification (FRS) and related technical, interoperability, and security documentation. Based on this, the systems development/integration service provider will be onboarded to initiate system build, configuration, and testing in line with national digital standards. System development will be deliberately sequenced to ensure institutional and user readiness, reducing risks of low uptake, fragmented interoperability, or rework.

Obtaining Cabinet approval for the OneRegistry initiative is the paramount political priority This  endorsement will institutionalise the reform, authorise system development and deployment, mandate cross-ministerial cooperation, and embed the OneRegistry system within national digital governance and Digital Public Infrastructure frameworks. In parallel, building on the legal landscape review  governing the total operation of Registrar General’s Department (RGD) has been started in 2025. Building on this groundwork, the required inputs needed for new policies and  policy amendments will be developed in year 2026.

Ensuring CRVS ecosystem readiness will be a parallel priority. This includes preparing institutions, policies, workflows, technical standards, and users to absorb and sustain the new system. Updated SOPs, change management interventions, and targeted advocacy will be rolled out to support transition from manual to digital processes.

Capacity development at scale will be implemented based on the completed Training Needs Assessment, strengthening RGD, Divisional Secretariats, health institutions, and related agencies to operate and sustain digital CRVS services.

Finally, strategic partnerships and financing will be deepened by leveraging national budget allocations, co-financing, and partnerships to support system development, operations, and long-term scale-up, positioning 2026 as a transition to government-led implementation.

Rooted in a commitment to transparency and continuous learning, the JP is scheduling two 'Pause and Reflect' sessions for mid- and late 2026. These sessions will involve key stakeholders from the RGD, the Ministry of Public Administration, and the Ministry of Digital Economy to evaluate progress, take corrective measures, enhance ownership, and ensure accountability.

B. Exit Strategy and Sustainability Pathways

The JP’s exit strategy is embedded across implementation and is designed to ensure that CRVS digital transformation is institutionalized, operationally sustained, and government-led beyond the JP lifecycle.

At the institutional and policy level, sustainability is anchored through Cabinet approval of the OneRegistry and CRVS digitalization initiative. Cabinet endorsement will formalize mandates, authorize cross-ministerial cooperation, and embed OneRegistry within national digital governance structures. Following approval, sustainability will be reinforced through the adoption of standards, guidelines, SOPs, and operational manuals, ensuring continuity of implementation, independent of project support. National budget allocations will support ongoing operations and system upkeep. From a transformative impact perspective, OneRegistry is positioned as a foundational enabler and prerequisite for national priorities such as SLUDI and e-NIC, ensuring its relevance and continued investment beyond the JP.

Sustainability will be further reinforced through formal partnerships, including an agreement with GovTech to play a supervisory role over the system. Long-term continuity will be supported through multi-year service level agreements, including a proposed five-year maintenance and support arrangement for the CRVS system with the system developer, and arrangements covering equipment warranties and lifecycle maintenance. Furthermore, the JP aims to onboard the RGD into major digital decision-making platforms, as they currently lack a seat at these tables

At the system and operational level, sustainability is addressed through completion of system development, strengthening of digital and physical infrastructure, and institutional capacity development. A Learning Management System (LMS) and Training of Trainer (TOT) mechanisms will enable continuous skills development and institutional memory.

Together, these measures ensure a planned phase-over to government and partner-led ownership, with clear pathways for post-JP scale and continuity.

(max 500 words)

## Indicator-based Performance Assessment

B.1. The JP results framework and workplan (Excel)

Please assess the JP performance against the indicators identified in you JP's Prodoc annex: Integrated results framework and workplan, including 1) JP outcomes and outputs, and 2) JP workplan.

Please upload the completed excel file via the Microsoft online form (question 8).

Annex A

B.2. Leaving No One Behind

Please indicate the number of direct beneficiaries from your JP to date. Direct beneficiaries are individuals, groups or organizations who actively participate in JP activities and directly benefit from its interventions, such as civil servants attending workshops, small business owners receiving training, or households accessing services provided by the JP.

| Type of engagement | Total Number of People | Number of Women and Girls* | Number of Children (0-14)* | Number of youth (ages 15-24)* |
| --- | --- | --- | --- | --- |
| Training/workshops for targeted groups | 818 |  |  |  |
| Awareness raising campaign for broad audience | 916 |  |  |  |
| Dialogues/consultations with relevant stakeholders | 1657 | 461 | None | 283 |
| Coordination meetings with key partners | 36 | 19 | None |  |
| Access to expanded services | 3634 |  |  |  |
| Others (Please specify): ____ |  |  |  |  |

* Note that it is allowed to have overlaps in the reporting of women/girls and children/youth columns.

B.2.a. Has the JP demonstrated positive results and influence for youth (age 15-24 years) in accordance with the principles in Youth2030 Strategy. If yes, please describe your contributions to the Youth2030 Strategy.

Yes. While the Joint Programme (JP) does not implement youth-targeted interventions, it demonstrates positive, indirect, and systems-level contributions aligned with the UN Youth2030 Strategy, by addressing structural barriers that affect youth access to rights, services, and participation, the JP aims to contribute directly to SDGs 16.9, 17.18, and indirectly to SDG 1 and SDG 5.

The JP is designed using an inclusive and LNOB approach across all activities. This includes systems mapping, capacity development initiatives, and baseline assessments that explicitly capture age-disaggregated data and examine barriers faced by population groups, including youth (15–24), in accessing civil registration and related public services.

Youth2030 identifies key systemic challenges affecting youth, including lack of legal identity and documentation, insufficient age-disaggregated data for policymaking, and digital exclusion from public services (UN Youth2030 Strategy, 2018).

These challenges are directly linked to weaknesses in civil registration and administrative data systems.

The JP is expected to address these gaps through its core outcomes by:

- Strengthening access to timely and reliable legal documentation through digitised and streamlined CRVS processes (contributing to SDG 16.9);

- Improving the availability and use of high-quality, age-disaggregated population and vital statistics for planning and resource allocation (SDG 17.18);

- Reducing digital and administrative exclusion by transforming CRVS into an interoperable digital public service, enabling youth to access education, employment, social protection, and civic services more effectively.

- By reforming foundational governance and data systems, the JP contributes to Youth2030 objectives indirectly but structurally, creating enabling conditions for youth empowerment, inclusion, and participation over the medium to long term.

(max 200 words)

B.2.b. In bullet points, please provide a summary of how the JP is benefiting the marginalized and vulnerable groups identified in the ProDoc. Include results to which you have contributed at both institutional/policy and local/human levels. Please find the 20 standard LNOB groups in footnote 28 on page 17 of the UNSDG Output Indicator Framework's Implementation Guide. You can also consult the human rights checklists on digital transformation, food systems transformation, and social protection and jobs to inform your responses. (NB: PUNOs may need to request access first).

The "OneRegistry" Joint Programme is designed to operationalize the principle of "Leaving No One Behind" . The initiative directly benefits key vulnerable groups, including the urban and rural poor, estate sector communities, persons with disabilities, women and girls, older persons, and those facing geographic or administrative barriers.

Institutional / policy-level results

- sEstablishes an inclusive digital foundation by transforming the Civil Registration and Vital Statistics system into accessible digital public infrastructure, directly increasing access to legal identity for populations previously excluded by paper-based, manual processes.

- Improves the availability of administrative data generated through the CRVS system, including disaggregation by sex, age, disability, and geographic location, enabling government institutions to better identify population groups and geographic areas requiring targeted attention.

- Supports policy, procedural, and system-level reforms that enable the use of digitally generated and verifiable civil registration records, reducing reliance on manual processes.

- Facilitates coordination among government institutions involved in civil registration, population data, and service delivery, supporting more consistent use of CRVS data across sectors relevant to vulnerable populations.

Local / human-level results

- Digitised and streamlined registration processes reduce processing time and administrative steps for birth and death registration in selected divisions, which particularly benefits individuals with limited time, mobility, or financial resources.

- Targeted implementation in high-volume and high-vulnerability divisions improves the timeliness of birth and death registration for residents in urban, rural, and estate sector contexts.

- Awareness-raising, capacity-building, and digital literacy activities support residents’ ability to access and use digital civil registration services, particularly for groups with lower familiarity with digital systems.

- Improved access to civil registration records supports residents’ ability to use official documentation when accessing public services.

(max 200 words)

B.3. Reporting against JSDGF global indicators

Kindly provide progress made against the following Fund-level indicators.

Enabling Action areas:

| Indicators | Progress in 2025 |
| --- | --- |
| Number of integrated policies/regulatory frameworks that have been both adopted and show early evidence of systems change (e.g., increased cross-sector coordination, enhanced resource allocation, improved service delivery integration) with Joint SDG Fund support | A critical Cabinet Memorandum to strengthen the digital transformation regulatory framework is in its final approval phase. |
| Number of policy innovations or regulatory reforms that have been replicated or scaled beyond initial target areas/sectors with Joint SDG Fund support | A comprehensive mapping exercise of all relevant policies and regulatory tools was launched in Q4 2025. This diagnostic is a necessary first step to inform strategic replication and scaling, with completion expected in Q1 2026. |
| Number of new or strengthened institutional mechanisms (e.g., coordination bodies, implementation units, multi-stakeholder platforms) that demonstrate improved cross-sector integration in SDG implementation | 3 (Joint Programme Steering Committee, DEESU, Technical Committees) |
| Number of government entities, both at the central and sub-national levels, that have restructured their planning, budgeting or implementation processes to enable integrated SDG acceleration, with evidence of sustained organizational change | Essential capacity development and infrastructure initiatives for institutional restructuring were deferred due to the national emergency caused by recent heavy flooding and displacements, which required a reallocation of government resources and focus. |

Key Transition and Thematic Indicators (respond to all relevant indicators, especially those in the JP’s primary and secondary transition areas)

| Transition area | Indictors | Progress in 2025 |
| --- | --- | --- |
| Digital | Number of individuals, including those who are marginalised, vulnerable and left behind, benefiting from enhanced digital public services and solutions, including sex-disaggregation | 3634 |
|  | Number of digital applications and engagement platforms, created with UN support, linked to SDGs | System development is sequenced for post-Cabinet authorization; no standalone applications were developed during the foundational phase. |
|  | Number of institutions and private sector partners with enhanced skills and capacities based on support provided | None |
| Food systems | Number of new and improved evidence-based food systems policies/strategies developed and implemented, in line with international human rights and other relevant standards | N/A |
|  | Number of small-holder farmers and producers adopting innovative and sustainable food production practices, including sex-disaggregation |  |
|  | Number of targeted populations, including those who are marginalised, vulnerable and left behind, with improved food security and nutrition outcomes, including sex-disaggregation |  |
| Social Protection & Jobs | Number of reforms, policies and programmes that have been adopted (Decree, Law, governmental policy) and/or implemented, by a national authority (such as the parliament or national assembly, government institution or body relating to decent jobs or social protection and originating in the GA Roadmap) | N/A |
|  | Number of people, including those who are marginalised, vulnerable and left behind, benefiting from the introduction, extension and strengthening of social protection and decent work policies, including sex-disaggregation |  |
| Energy transition | Number of new or enhanced integrated policy and regulatory frameworks developed and/or adopted to accelerate energy transition, in line with international human rights and other relevant standards | N/A |
|  | Number of people/households, including those who are marginalised, vulnerable and left behind, benefiting from improved access to clean and affordable energy, including sex-disaggregation |  |
| Climate, biodiversity, pollution | Number of NDC 3.0 components strengthened with integrated just transition and inclusivity considerations |  |
|  | Reduction of CO2eq emissions, through JSDGF support |  |
|  | Area of terrestrial and marine protected areas created or under improved management practices (hectares), supported by the JSDGF |  |
| Education | Number of children, youth, and adults, including those who are marginalised, vulnerable and left behind, benefiting from improved access to inclusive, quality education, including sex-disaggregation | N/A |
|  | Number of teachers and school staff trained demonstrating gender-sensitive and inclusive teaching practices aligned with national education, including sex-disaggregation |  |
|  | Number of education sector policies/regulatory frameworks adopted or strengthened, in line with international human rights and other relevant standards |  |

## Strategic Communications and Partnership Update

Please provide the links to written communications products published by the JP team PUNOs, RCOs or implementing partners, or the draft outline of a written article to be finalized in the coming weeks. Examples of human-interest stories, practical guidance on storytelling, other useful tools to produce impactful written articles can be found on UNSDG Knowledge Portal (NB: PUNOs may need to request access first).

List of links to written articles, case studies, factsheets, videos (do not include social media posts): - OneRegistry, Endless potential: How Sri Lanka is Modernizing Civil Registration - https://jointsdgfund.org/article/one-registry-endless-potential-how-sri-lanka-modernizing-civil-registration - Project Launch at the DPI Summit - https://bizenglish.adaderana.lk/sri-lankas-dpi-summit-2025-advances-action-on-building-an-inclusive-digital-economy/ - Project Launch at the DPI Summit https://www.dailymirror.lk/breaking-news/SL-upgrades-CRVS-system/108-301755

Draft outline of a written article of a human-interest story (500 words / 1 page max) Restoring Identities after “Cyclone Ditwah” In the bustling office of the Arachchikattuwa Divisional Secretariat, H.R. Priyadarshani has become a lifeline for a community impacted by the devastating floods. As a Development Officer in the Registrar’s department, she works on the front lines of a silent crisis, helping flood affected families restore their vital civil documents. As floodwaters receded, more than 1,500 displaced individuals in the area were left with almost nothing. “The clothes they were wearing were all they had left,” Priyadarshani recalls. Along with homes and livelihoods, vital civil documents, including birth certificates, death records, marriage registrations were washed away, cutting families off from essential state services, humanitarian assistance, and recovery support. Her critical work forms part of the OneRegistry Joint Programme, a critical effort to transform Sri Lanka’s civil registration and vital statistics system into a fully digital, interoperable public service. The initiative aims to streamline registration processes across urban, rural, and estate sectors, ultimately reducing registration times by half and benefiting more than 1.27 million people nationwide. Priyadarshani is witnessing the early stages of this transformation. The shift away from paper-based, time-intensive procedures toward digital access is already changing how services are delivered. “The goal is to allow everything to be completed through a mobile phone,” she explains, reducing the need for citizens to travel long distances simply to submit forms. While the transition is being implemented gradually, alongside infrastructure upgrades and staff capacity development, it is laying the foundation for a more accessible and resilient system. The urgency of this reform became unmistakable during the floods. With records destroyed and offices under strain, maintaining civil registration services was only possible through targeted emergency support. The Joint Programme provided essential equipment, including a laptop, printer, and satellite connectivity, enabling uninterrupted service delivery even under crisis conditions. “These tools have been incredibly valuable,” Priyadarshani notes, allowing her office to issue replacement documents free of charge to the most vulnerable, at a moment when proof of identity meant access to aid, shelter, and recovery assistance. For Priyadarshani, the move toward full digitalization is not just a technical upgrade, it is a safeguard for the future. By integrating modern technology with streamlined registration processes, OneRegistry strengthens the resilience of public institutions and protects citizens from losing their legal identity in times of disaster. In restoring documents, Priyadarshani is restoring dignity, rights, and access. For more than 1,500 flood-affected individuals, this work has ensured that even after “Cyclone Ditwah,” no one is left invisible, and no one is left behind. Case Story: Community mindsets towards digitalization Arna Silva’s life was upended by unprecedented floods that destroyed not only her home but also her family’s critical legal documents, birth and marriage certificates, along with her son’s educational materials. While initial relief was provided, the arduous process of physically replacing these vital records highlighted a systemic vulnerability. Her recovery journey involved a lengthy visit to the local government office, where hours of waiting contrasted with minutes of efficient service once her physical records were located. This experience fundamentally shifted Arna’s perspective on digital solutions. Despite having only basic phone literacy, Arna now sees digitalization as an essential safeguard. She recognizes that secure, digitized civil records would have transformed her recovery from a logistically burdensome ordeal into a swift, accessible process. For her, technology is no longer abstract; it is a practical means of resilience, protecting her family’s identity and future against disaster. She represents a growing community mindset that trusts digital systems not for their complexity, but for their ability to preserve what matters most with certainty and convenience.

List of Annexure

Annex 01 – Meeting Minutes, High Level Stock Taking meeting

Annex 02 – Cabinet paper process documentation

Annex 03 - Theory of Change

Annex 04 – TNA & Summary Schedule

Annex 05 – TOR for CSDP content development and delivery

Annex 06 – TOR for REGD2DE

Annex 07 – Session Plans and Workplan for the training