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	I. Executive Summary (Highlights) HIGHLIGHTS
1. The revised National Biodiversity Strategy and Action Plan (NBSAP) was consolidated into a coherent draft aligned with the Kunming–Montreal Global Biodiversity Framework and ready for validation.
2. A comprehensive capacity and financing assessment identified key governance gaps and proposed actionable reforms to strengthen biodiversity institutions, data systems, and resource mobilization.
3. Somalia’s first national spatial prioritization framework was produced, identifying priority ecosystems, restoration areas, corridors, and candidate protected areas with supporting biodiversity and pressure maps.
4. The Seventh National Report to the Convention on Biological Diversity confirmed Somalia’s foundational biodiversity governance is largely in place, while emphasizing the urgent need for effective execution and resourcing.
5. The thematic review and stakeholder consultations generated actionable recommendations to update national targets and improve integration of biodiversity into development planning and governance.

	
II. Progress Review per Project Output: 
[bookmark: _Toc424189498]OUTCOME 1: 
a. Activities undertaken during the reporting period (2025)
· Developed and initiated implementation of a comprehensive stakeholder engagement plan to support an all-of-society approach to the NBSAP update, engaging government, civil society, academia, the private sector, and local communities.
· Conducted a national gender analysis and prepared a draft gender action plan to support gender mainstreaming in consultations and in actions informing the NBSAP revision.
· Identified and prioritized key gaps and inconsistencies in the existing NBSAP based on Early Action Support (EAS) results, to inform alignment of the updated NBSAP with the Kunming–Montreal Global Biodiversity Framework.
· Undertook policy alignment reviews and drafted an NBSAP section addressing policy coherence and biodiversity mainstreaming across key sectors.
· Carried out an environmental and social impact assessment to identify potential risks associated with implementation of the updated NBSAP, with findings documented in draft form.
· Developed a first draft spatial prioritization for GBF Target 1 using national and global data, and prepared a draft spatialized action plan for area-based targets including Targets 2, 3, 8, 9, 11, and 12.
· Drafted an action plan to eliminate or phase out harmful subsidies and incentives in line with GBF Target 18.
· Assessed gaps in institutional capacity and available resources and drafted capacity development and resource mobilization strategies, building on EAS findings and biodiversity finance initiatives.
b. Achievements by sectors/outputs 
During 2025, Outcome 1 recorded steady progress toward updating Somalia’s NBSAP in line with the Kunming–Montreal Global Biodiversity Framework. Stakeholder engagement structures were established and used to support inclusive consultations, and a national gender analysis with a draft gender action plan was completed to inform gender-responsive NBSAP actions. Key gaps in the existing NBSAP were identified, and draft sections on policy alignment, biodiversity mainstreaming, and environmental and social safeguards were prepared. Initial spatial priorities and draft spatialized action plans for GBF Target 1 and other area-based targets were developed, alongside a draft action plan to phase out harmful subsidies. Capacity and resource gaps were assessed, and draft strategies for capacity development and resource mobilization were prepared, strengthening the foundation for effective NBSAP implementation.
OUTCOME 2: 
a. Activities undertaken during the reporting period 
· Prepared a draft overview of the process for developing Somalia’s Seventh National Report to the Convention on Biological Diversity, including initial data compilation and technical inputs.
· Conducted a draft assessment of the status of the revised National Biodiversity Strategy and Action Plan (NBSAP) in light of the Kunming–Montreal Global Biodiversity Framework.
· Developed a draft assessment of progress towards national biodiversity targets based on available national information and evidence.
· Prepared a draft assessment of progress related to the goals and targets of the Kunming–Montreal Global Biodiversity Framework.
· Drafted preliminary conclusions on Somalia’s implementation of the Convention on Biological Diversity and the Kunming–Montreal Global Biodiversity Framework, including initial identification of gaps and priority actions.
b. Achievements by sectors/outputs
During 2025, Somalia advanced its Seventh National Report to the CBD, producing a more evidence-based assessment of biodiversity progress and readiness to implement the Kunming–Montreal GBF. The report confirms that foundational governance steps are largely in place, identifies gaps in capacity, data, monitoring, and financing, and highlights that the main challenge is translating existing policies and pilot initiatives into fully resourced and enforceable systems that deliver measurable biodiversity and livelihood outcomes.

	OUTCOME 1


	Indicator

	Baseline
	Cumulative target
	Progress for reporting period (disaggregated data to be used)
	Cumulative progress
(disaggregated data to be used)
	Comments

	1.1.1: Number of stakeholders engaged and level of diversity in representation within the NBSAP process.
	1.1.1: No comprehensive stakeholder engagement plan exists; limited stakeholder involvement.
	1 engagement plan developed; ≥80% of identified stakeholder groups engaged
	Draft stakeholder engagement plan developed and applied in consultations; participation included government, CSOs, academia, private sector, women’s groups, and FMS representatives
	Engagement plan in draft; stakeholder participation expanded significantly from baseline, with improved diversity including women and sub-national actors
	

	1.1.2: Existence of a gender analysis report and a corresponding action plan. Indicator 
	1.1.2: No national gender analysis or action plan in place.
	1 gender analysis and 1 gender action plan developed
	National gender analysis drafted; draft gender action plan prepared; women’s participation documented qualitatively
	Gender analysis drafted; draft action plan available but not yet finalized or adopted
	

	1.1.3: Number of identified gaps and prioritized action areas documented
	1.1.3: No detailed gap analysis available.
	1 comprehensive gap analysis and prioritized action list
	Draft gap analysis prepared identifying priority alignment gaps with GBF
	Gap analysis exists in draft form; priorities identified but pending validation
	

	1.1.4: Number of sectors integrating biodiversity considerations into their policy frameworks.
	1.1.4: Limited or no sectoral integration of biodiversity considerations.
	At least 3 key sectors integrate biodiversity
	Policy alignment review conducted; draft NBSAP sections prepared referencing multiple sectors
	Sectoral integration initiated conceptually; 
	

	1.1.5: Number of environmental and social impact assessments (ESIAs) conducted.
	1.1.5: No ESIAs for the updated NBSAP.
	1 ESIA conducted with mitigation measures
	Draft ESIA completed identifying potential environmental and social risks
	ESIA completed in draft form; mitigation measures outlined 
	

	1.1.6: Number of spatial priorities identified and mapped; Spatialized action plans for area-based targets finalized and integrated.
	1.1.6: No spatial priorities or spatialized action plans integrated into the NBSAP.
	100% of spatial priorities mapped and action plans finalized
	Draft spatial prioritization prepared using national and global datasets; area-based targets spatialized in draft
	Initial spatial priorities and maps produced; action plans remain draft and unvalidated
	

	1.1.7: Action plan for phasing out harmful subsidies developed and adopted.
	1.1.7: No actionable plans or mechanisms in place.
	Action plan developed and endorsed
	Draft action plan prepared identifying key harmful subsidies
	Draft plan produced; 
	

	1.1.8: Capacity and resource gap assessment report finalized; Number of strategies or plans developed and approved.
	1.1.8: No comprehensive assessments or strategies available.
	Assessment completed; strategies developed and approved
	Capacity and resource gap assessment drafted; draft capacity development and resource mobilization strategies prepared
	Assessment and strategies available in draft form; 
	

	OUTCOME 2

	 2.1.1:	 Scope, parameters, and categories defined and validated.
	2.1.1: No established parameters or scope for assessments.
	2.1.1:	 Framework and parameters developed and validated.
	Draft scope and assessment framework prepared for the 7th National Report
	Parameters defined in draft; validation pending
	

	2.1.2: Percentage of alignment between updated NBSAP and Kunming-Montreal Framework.
	2.1.2: Current NBSAP does not reflect the Kunming-Montreal Framework.
	2.1.2: Full alignment and updated NBSAP approved.
	Initial alignment analysis conducted between draft NBSAP and GBF goals and targets
	Partial alignment assessed in draft; full alignment pending NBSAP finalization
	

	2.1.3: Number of progress assessment reports finalized and shared.
	2.1.3: No assessment available.
	2.1.3: Complete and share progress reports.
	Draft progress assessment prepared using available national data
	Draft assessment exists; dissemination pending
	

	2.1.4: Assessment of progress related to the goals and targets of the Kunming-Montreal Global Biodiversity Framework is completed.
	2.1.4: No assessment aligned with Kunming-Montreal Framework.
	2.1.4: Comprehensive assessment report finalized and disseminated.
	Draft assessment completed covering GBF goals and targets
	Assessment completed in draft form; not finalized
	

	2.1.5: Conclusions on the implementation of the Convention and the Kunming-Montreal Global Biodiversity Framework are completed.            
	2.1.5: Conclusion on the Implementation of the Convention and the Kunming-Montreal Global Biodiversity Framework not reviewed.   
	2.1.5: Implementation report finalized.   

	Draft conclusions prepared identifying readiness, gaps, and priorities
	Conclusions documented in draft; final review pending
	

	
Project monitoring reports
Government and/or programme monitoring
Reports with photographs and attendance lists. 




Progress toward Outcome 1 shows a clear transition from a zero baseline to draft GBF-aligned planning outputs that strengthen the foundation for an updated NBSAP. A draft stakeholder engagement plan expanded participation and diversity compared to the baseline of limited involvement (Indicator 1.1.1), while a national gender analysis and draft action plan addressed a major gap and improved consideration of women’s roles and impacts (Indicator 1.1.2). Draft gap analysis, policy alignment, ESIA, spatial prioritization, harmful subsidy reform, and capacity and resource assessments demonstrate partial achievement of annual targets that were absent at baseline (Indicators 1.1.3–1.1.8). While most outputs remain in draft form and sectoral integration is still evolving, they collectively contribute to the outcome by improving coherence, safeguards, and evidence-based planning
Progress under Outcome 2 reflects steady advancement toward improved national reporting under the CBD and the Kunming–Montreal Global Biodiversity Framework, starting from a baseline of no defined scope or assessments. Draft parameters and scope for national reporting have been developed (Indicator 2.1.1), alongside initial analysis of NBSAP alignment with the GBF, though full alignment and approval are pending (Indicator 2.1.2). Draft assessments of progress toward national targets and GBF goals and targets, as well as preliminary conclusions on CBD and GBF implementation, indicate partial achievement of annual targets (Indicators 2.1.3–2.1.5). These outputs strengthen the national evidence base and clarify gaps in capacity, data, financing, and gender-disaggregated information

	III. Challenges and Remedial Actions

	 Challenges
	Remedial Actions 

	Delay in procurement and onboarding of the technical team at the ministry.
	Revised workplan and amended the LOA to align timelines and deliverables

	Limited availability of biodiversity data for assessment and reporting.
	Hired an international consultant to develop a standardized methodology for primary data collection, and national researchers to collect data; produced a national biodiversity assessment report.

	Delayed  stakeholder workshops to ensure full representation from all states and sectors, causing delayed liquidation and pushing remaining workshops into 2026.
	Remaining workshops carried forward to 2026.

	IV. Recommendations: (Recommendations to improve future programming). Maximum one page
· Ensure early agreement and timely signing of the Letter of Agreement (LoA) and any necessary amendments before work begins to prevent delays.
· Strengthen risk management by integrating adaptive planning and a risk register to respond quickly to delays, security challenges, or shifts in political priorities.
· Mainstream biodiversity early into national development plans, climate strategies, and sector policies to ensure long-term integration rather than stand-alone interventions.
· Adopt flexible delivery modalities for workshops, using hybrid or decentralized models to ensure participation while minimizing logistical delays and costs.

	V. Lessons Learned: 
· Early procurement planning matters more than expected. Delays in recruiting the technical team showed that procurement timelines can shape the entire delivery schedule.
· Ensure early agreement and timely signing of the Letter of Agreement (LoA) and any necessary amendments before work begins to prevent procurement delays and enable faster onboarding of consultants.
· Strengthen risk management by integrating adaptive planning and a risk register to respond quickly to delays, security challenges, or shifts in political priorities.
· Reinforce monitoring, evaluation, and learning through regular progress reviews and learning loops that allow implementation to be adjusted based on evidence.

	VI.  List of in complete activities to be carried over to the next period
· Workshops for the assessment of gaps in capacities and resources available undertaken, and on that basis, develop plans or strategies for capacity development and resource mobilization.
· Workshops for development of a first approximation of spatial priorities for Target 1.9 and develop a spatialized action plan for other area-based targets.
· Workshops for the identification of an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP.
· Workshops for the assessment of gaps in capacities and resources available undertaken, and on that basis, develop plans or strategies for capacity development and resource mobilization.

	VII. Annexe1: List of trainings: 
	Course/Training name
	Date
	M
	F
	Total
	Facilitated by

	Stakeholder engagement session to ensure whole government and whole of society approach.
	1-2/09/2025
	53
	19
	72
	

	Workshop to identify and prioritize key gaps and inconsistencies between the existing NBSAP and the updates needed to align with the Global Biodiversity Framework
	5-6/10/2025
	42
	30
	72
	

	 Workshop for developing National Gender Analysis and Action Plans
	7-8/10/2025
	40
	28
	68
	

	Consultations to address policy alignment and coherence and biodiversity
mainstreaming into key sectors within
the NBSAP
	 3-4/09/2025
	 55
	 18
	 73
	

	Workshop for the assessment of the  potential environmental and social impacts and potential risks of the implementation of the updated NBSAP.
	23/10/2025
	51
	23
	74
	

	Workshop for the identification of an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP.
	15-16/11/2025
	39
	26
	65
	

	Workshop for the assessment of gaps in capacities and resources available undertaken, and on that basis, develop plans or strategies for capacity development and resource mobilization 
	26/11/2025
	37
	23
	60
	


1. 

	VIII. Annex 2: Expenditure Report
IX. Annex 3: Photos and social media coverage
X. Update Project risks in Quantum
XI. List of evidence and links


 
Annex 2: Expenditure Report


Annex 3: Photos and Social Media Links:
i. https://www.facebook.com/share/p/1C7FeNfK33/?mibextid=wwXIfr
ii. https://www.facebook.com/share/p/1DZRPLFe8Q/?mibextid=wwXIfr
iii. https://www.facebook.com/share/v/1GC4poWHhz/?mibextid=wwXIfr
iv. https://www.facebook.com/share/p/17YJNJFZXD/?mibextid=wwXIfr
v. https://www.facebook.com/share/p/1FbnijxxUL/?mibextid=wwXIfr
vi. https://www.facebook.com/share/p/1APhfeK8pv/?mibextid=wwXIfr
vii. https://www.facebook.com/share/p/17zPLZiby3/?mibextid=wwXIfr
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10079_budget_revision_sheet_2026-01-22-11-06-14.xlsx
Sheet1

						Values

		Component Level 3 (Quantum Task Number)		Account Code		Sum of 2025 Proposed Budget		Sum of S = GL Expenses (2025)

		Activity 1.1.1		71300		- 0		- 0

				71400		6,492.87		6,492.87

				71600		- 0		- 0

				75700		- 0		- 0

				Total		6,492.87		6,492.87

		Activity 1.1.1 MOECC		71600		- 0		- 0

				71800		16,563.00		16,563.00

				74500		277.50		277.50

				75700		- 0		- 0

				Total		16,840.50		16,840.50

		Activity 1.1.2		71300		- 0		- 0

				71400		5,312.34		5,312.34

				71600		- 0		- 0

				75700		- 0		- 0

				Total		5,312.34		5,312.34

		Activity 1.1.2 MOECC		71600		- 0		- 0

				71800		14,437.00		14,437.00

				74500		75.00		75.00

				75700		- 0		- 0

				Total		14,512.00		14,512.00

		Activity 1.1.3		71300		- 0		- 0

				71400		6,460.74		6,460.74

				71600		- 0		- 0

				75700		- 0		- 0

				Total		6,460.74		6,460.74

		Activity 1.1.3 MOECC		71600		5,000.00		5,000.00

				71800		15,500.00		15,500.00

				74500		307.50		307.50

				75700		10,750.00		10,750.00

				Total		31,557.50		31,557.50

		Activity 1.1.4		71300		- 0		- 0

				71400		6,460.74		6,460.74

				71600		- 0		- 0

				75700		- 0		- 0

				Total		6,460.74		6,460.74

		Activity 1.1.4 MOECC		71600		5,000.00		5,000.00

				71800		12,000.00		12,000.00

				74500		180.00		180.00

				75700		11,000.00		11,000.00

				Total		28,180.00		28,180.00

		Activity 1.1.5		71300		- 0		- 0

				71400		6,460.74		6,460.74

				71600		- 0		- 0

				71800		- 0		- 0

				75700		- 0		- 0

				Total		6,460.74		6,460.74

		Activity 1.1.5 MOECC		71600		5,000.00		5,000.00

				71800		16,537.50		16,537.50

				74500		2,747.50		2,747.50

				75700		10,500.00		10,500.00

				Total		34,785.00		34,785.00

		Activity 1.1.6		71300		- 0		- 0

				71400		- 0		- 0

				71600		- 0		- 0

				75700		- 0		- 0

				Total		- 0		- 0

		Activity 1.1.6 MOECC		71600		5,000.00		5,000.00

				71800		13,500.00		13,500.00

				74500		202.50		202.50

				75700		10,000.00		10,000.00

				Total		28,702.50		28,702.50

		Activity 1.1.7		71300		- 0		- 0

				71400		- 0		- 0

				71600		- 0		- 0

				75700		- 0		- 0

				Total		- 0		- 0

		Activity 1.1.7 MOECC		71600		10,000.00		10,000.00

				71800		5,000.00		5,000.00

				74500		75.00		75.00

				75700		10,000.00		10,000.00

				Total		25,075.00		25,075.00

		Activity 1.1.8		71300		- 0		- 0

				71400		2,896.20		2,896.20

				71600		- 0		- 0

				75700		- 0		- 0

				Total		2,896.20		2,896.20

		Activity 1.1.8 MOECC		71600		- 0		- 0

				71800		7,500.00		7,500.00

				74500		7,725.00		7,725.00

				75700		10,000.00		10,000.00

				Total		25,225.00		25,225.00

		Activity 2.1.2		71300		- 0		- 0

				71400		- 0		- 0

				71600		- 0		- 0

				Total		- 0		- 0

		Activity 2.1.2 MOECC		71800		- 0		- 0

				Total		- 0		- 0

		Activity 2.1.3		71300		- 0		- 0

				71400		- 0		- 0

				71600		- 0		- 0

				Total		- 0		- 0

		Activity 2.1.3 MOECC		71800		2,500.00		2,500.00

				74500		37.50		37.50

				Total		2,537.50		2,537.50

		Activity 2.1.4		71300		- 0		- 0

				71400		- 0		- 0

				71600		- 0		- 0

				Total		- 0		- 0

		Activity 2.1.4 MOECC		71800		3,500.00		3,500.00

				74500		52.50		52.50

				Total		3,552.50		3,552.50

		Activity 2.1.5		71300		- 0		- 0

				71400		- 0		- 0

				71600		- 0		- 0

				Total		- 0		- 0

		Activity 2.1.5 MOECC		71800		- 0		- 0

				Total		- 0		- 0

		Activiy 2.1.1		71300		- 0		- 0

				71400		- 0		- 0

				71600		- 0		- 0

				Total		- 0		- 0

		Activiy 2.1.1 MOECC		71800		2,500.00		2,500.00

				74500		37.50		37.50

				Total		2,537.50		2,537.50

		PMC		74500		- 0		- 0

				74596		10,000.00		10,000.00

				Total		10,000.00		10,000.00

		Total		(blank)		257,588.63		257,588.63





Worksheet

		Quantum Award		Quantum Project (Atlas Output)		Source of Funds		Fund Code		Donor Code		Component Level 1		Component Level 2 (Atlas Activity Code)		Component Level 2 (Atlas Activity Name)		Component Level 3 (Quantum Task Number)		Component Level 3 (Quantum Task Name)		Responsible Party Code		Responsible Party Name		Account Code		Account Description		O = Approved Budget (as per ProDoc)		P = GL Expenses (as per CDR at the end of 2024)		Q = Obligations (as per BC at the end of 2024)		R = O-P - Q = Opening Resource Balance		S = GL Expenses (2025)		T = PPM Expenses (2025)		U = BC Obligations (2025)		V = P + S = Total GL Expenses		W = All Years Obligations (as per BC)		X = V + W = Total Consumption		2025 Quantum Budget		2025 Proposed Budget		2025 Budget Difference		2026 Quantum Budget		2026 Proposed Budget		2026 Budget Difference		2027 Quantum Budget		2027 Proposed Budget		2027 Budget Difference		2028 Quantum Budget		2028 Proposed Budget		2028 Budget Difference		2029 Quantum Budget		2029 Proposed Budget		2029 Budget Difference		AN = R - Proposed Budget = Project Budget Balance (based on Proposed Budget)		AO = R - Quantum Budget for current and future years = Project Budget Balance (based on Quantum Budget)		AP = O - V = Project Balance (based on GL Expenses)		AQ = O - V - W = Resource Balance (based on GL Expenses including Obligations)

		1259824		01003136		GEF		62000		10003		Total																		463,547.00		0.00		0.00		463,547.00		257,588.63		257,551.13		0.00		257,588.63		0.00		257,588.63		330,000.00		257,588.63		72,411.37		95,000.00		101,318.79		-6,318.79		38,547.00		37,297.00		1,250.00		0.00		0.00		0.00		0.00		0.00		0.00		67,342.58		0.00		205,958.37		205,958.37

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		Total																343,547.00		0.00		0.00		343,547.00		238,961.13		238,923.63		0.00		238,961.13		0.00		238,961.13		289,376.00		238,961.13		50,414.87		35,000.00		35,694.79		-694.79		28,547.00		27,297.00		1,250.00		0.00		0.00		0.00		0.00		0.00		0.00		41,594.08		-9,376.00		104,585.87		104,585.87

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.1 Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the NBSAP.		1.1.1 Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the NBSAP.		Total												42,943.00		0.00		0.00		42,943.00		23,333.37		23,333.37		0.00		23,333.37		0.00		23,333.37		38,437.00		23,333.37		15,103.63		4,375.00		4,757.13		-382.13		3,568.00		3,568.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		11,284.50		-3,437.00		19,609.63		19,609.63

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.1 Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the NBSAP.		1.1.1 Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the NBSAP.		Activity 1.1.1		Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the National Biodiversity Strategy and Action Plan		001981		UNDP		Total				42,943.00		0.00		0.00		42,943.00		6,492.87		6,492.87		0.00		6,492.87		0.00		6,492.87		6,875.00		6,492.87		382.13		4,375.00		4,757.13		-382.13		3,568.00		3,568.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		28,125.00		28,125.00		36,450.13		36,450.13

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.1 Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the NBSAP.		1.1.1 Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the NBSAP.		Activity 1.1.1		Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the National Biodiversity Strategy and Action Plan		001981		UNDP		71300		Local Consultants		24,193.00		0.00				24,193.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		3,125.00		3,125.00		0.00		2,318.00		2,318.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		18,750.00		18,750.00		24,193.00		24,193.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.1 Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the NBSAP.		1.1.1 Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the NBSAP.		Activity 1.1.1		Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the National Biodiversity Strategy and Action Plan		001981		UNDP		71400		Contractual Services - Individ		9,375.00		0.00				9,375.00		6,492.87		6,492.87		0.00		6,492.87		0.00		6,492.87		6,875.00		6,492.87		382.13		1,250.00		1,632.13		-382.13		1,250.00		1,250.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		2,882.13		2,882.13

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.1 Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the NBSAP.		1.1.1 Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the NBSAP.		Activity 1.1.1		Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the National Biodiversity Strategy and Action Plan		001981		UNDP		71600		Travel		5,000.00		0.00				5,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		5,000.00		5,000.00		5,000.00		5,000.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.1 Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the NBSAP.		1.1.1 Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the NBSAP.		Activity 1.1.1		Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the National Biodiversity Strategy and Action Plan		001981		UNDP		75700		Training, Workshops and Confer		4,375.00		0.00				4,375.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		4,375.00		4,375.00		4,375.00		4,375.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.1 Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the NBSAP.		1.1.1 Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the NBSAP.						009562		SOM-Min. Environ. & Climate Ch		Total				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.1 Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the NBSAP.		1.1.1 Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the NBSAP.						009562		SOM-Min. Environ. & Climate Ch		71800		Contractual Services-Imp Partn		0.00		0.00				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.1 Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the NBSAP.		1.1.1 Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the NBSAP.						009562		SOM-Min. Environ. & Climate Ch		71600		Travel		0.00		0.00				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.1 Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the NBSAP.		1.1.1 Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the NBSAP.						009562		SOM-Min. Environ. & Climate Ch		75700		Training, Workshops and Confer		0.00		0.00				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.1 Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the NBSAP.		1.1.1 Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the NBSAP.		Activity 1.1.1 MOECC		Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the National Biodiversity Strategy and Action Plan		009562		SOM-Min. Environ. & Climate Ch		Total				0.00		0.00		0.00		0.00		16,840.50		16,840.50		0.00		16,840.50		0.00		16,840.50		31,562.00		16,840.50		14,721.50		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-16,840.50		-31,562.00		-16,840.50		-16,840.50

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.1 Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the NBSAP.		1.1.1 Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the NBSAP.		Activity 1.1.1 MOECC		Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the National Biodiversity Strategy and Action Plan		009562		SOM-Min. Environ. & Climate Ch		71600		Travel				0.00				0.00		0.00		0.00		0.00		0.00		0.00		0.00		5,000.00		0.00		5,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-5,000.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.1 Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the NBSAP.		1.1.1 Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the NBSAP.		Activity 1.1.1 MOECC		Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the National Biodiversity Strategy and Action Plan		009562		SOM-Min. Environ. & Climate Ch		71800		Contractual Services-Imp Partn		0.00		0.00				0.00		16,563.00		16,563.00		0.00		16,563.00		0.00		16,563.00		16,563.00		16,563.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-16,563.00		-16,563.00		-16,563.00		-16,563.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.1 Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the NBSAP.		1.1.1 Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the NBSAP.		Activity 1.1.1 MOECC		Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the National Biodiversity Strategy and Action Plan		009562		SOM-Min. Environ. & Climate Ch		74500		Miscellaneous Expenses		0.00		0.00				0.00		277.50		277.50		0.00		277.50		0.00		277.50		0.00		277.50		-277.50		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-277.50		0.00		-277.50		-277.50

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.1 Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the NBSAP.		1.1.1 Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the NBSAP.		Activity 1.1.1 MOECC		Development and implementation of a comprehensive stakeholder engagement plan, to promote an all-of-society approach to the National Biodiversity Strategy and Action Plan		009562		SOM-Min. Environ. & Climate Ch		75700		Training, Workshops and Confer				0.00				0.00		0.00		0.00		0.00		0.00		0.00		0.00		9,999.00		0.00		9,999.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-9,999.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.2 A national gender analysis and action plan developed to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.		1.1.2 A national gender analysis and action plan developed to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.		Total												42,943.00		0.00		0.00		42,943.00		19,824.34		19,824.34		0.00		19,824.34		0.00		19,824.34		38,437.00		19,824.34		18,612.66		4,375.00		5,937.66		-1,562.66		3,568.00		3,568.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		13,613.00		-3,437.00		23,118.66		23,118.66

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.2 A national gender analysis and action plan developed to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.		1.1.2 A national gender analysis and action plan developed to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.		Activity 1.1.2		Develop a national gender analysis and action plan to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.		001981		UNDP		Total				42,943.00		0.00		0.00		42,943.00		5,312.34		5,312.34		0.00		5,312.34		0.00		5,312.34		6,875.00		5,312.34		1,562.66		4,375.00		5,937.66		-1,562.66		3,568.00		3,568.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		28,125.00		28,125.00		37,630.66		37,630.66

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.2 A national gender analysis and action plan developed to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.		1.1.2 A national gender analysis and action plan developed to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.		Activity 1.1.2		Develop a national gender analysis and action plan to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.		001981		UNDP		71300		Local Consultants		24,193.00		0.00				24,193.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		3,125.00		3,125.00		0.00		2,318.00		2,318.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		18,750.00		18,750.00		24,193.00		24,193.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.2 A national gender analysis and action plan developed to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.		1.1.2 A national gender analysis and action plan developed to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.		Activity 1.1.2		Develop a national gender analysis and action plan to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.		001981		UNDP		71400		Contractual Services - Individ		9,375.00		0.00				9,375.00		5,312.34		5,312.34		0.00		5,312.34		0.00		5,312.34		6,875.00		5,312.34		1,562.66		1,250.00		2,812.66		-1,562.66		1,250.00		1,250.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		4,062.66		4,062.66

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.2 A national gender analysis and action plan developed to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.		1.1.2 A national gender analysis and action plan developed to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.		Activity 1.1.2		Develop a national gender analysis and action plan to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.		001981		UNDP		71600		Travel		5,000.00		0.00				5,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		5,000.00		5,000.00		5,000.00		5,000.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.2 A national gender analysis and action plan developed to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.		1.1.2 A national gender analysis and action plan developed to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.		Activity 1.1.2		Develop a national gender analysis and action plan to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.		001981		UNDP		75700		Training, Workshops and Confer		4,375.00		0.00				4,375.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		4,375.00		4,375.00		4,375.00		4,375.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.2 A national gender analysis and action plan developed to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.		1.1.2 A national gender analysis and action plan developed to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.						009562		SOM-Min. Environ. & Climate Ch		Total				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.2 A national gender analysis and action plan developed to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.		1.1.2 A national gender analysis and action plan developed to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.						009562		SOM-Min. Environ. & Climate Ch		71800		Contractual Services-Imp Partn		0.00		0.00				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.2 A national gender analysis and action plan developed to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.		1.1.2 A national gender analysis and action plan developed to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.						009562		SOM-Min. Environ. & Climate Ch		71600		Travel		0.00		0.00				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.2 A national gender analysis and action plan developed to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.		1.1.2 A national gender analysis and action plan developed to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.						009562		SOM-Min. Environ. & Climate Ch		75700		Training, Workshops and Confer		0.00		0.00				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.2 A national gender analysis and action plan developed to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.		1.1.2 A national gender analysis and action plan developed to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.		Activity 1.1.2 MOECC		Develop a national gender analysis and action plan to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.		009562		SOM-Min. Environ. & Climate Ch		Total				0.00		0.00		0.00		0.00		14,512.00		14,512.00		0.00		14,512.00		0.00		14,512.00		31,562.00		14,512.00		17,050.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-14,512.00		-31,562.00		-14,512.00		-14,512.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.2 A national gender analysis and action plan developed to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.		1.1.2 A national gender analysis and action plan developed to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.		Activity 1.1.2 MOECC		Develop a national gender analysis and action plan to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.		009562		SOM-Min. Environ. & Climate Ch		71600		Travel				0.00				0.00		0.00		0.00		0.00		0.00		0.00		0.00		5,000.00		0.00		5,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-5,000.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.2 A national gender analysis and action plan developed to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.		1.1.2 A national gender analysis and action plan developed to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.		Activity 1.1.2 MOECC		Develop a national gender analysis and action plan to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.		009562		SOM-Min. Environ. & Climate Ch		71800		Contractual Services-Imp Partn		0.00		0.00				0.00		14,437.00		14,437.00		0.00		14,437.00		0.00		14,437.00		16,563.00		14,437.00		2,126.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-14,437.00		-16,563.00		-14,437.00		-14,437.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.2 A national gender analysis and action plan developed to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.		1.1.2 A national gender analysis and action plan developed to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.		Activity 1.1.2 MOECC		Develop a national gender analysis and action plan to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.		009562		SOM-Min. Environ. & Climate Ch		74500		Miscellaneous Expenses		0.00		0.00				0.00		75.00		75.00		0.00		75.00		0.00		75.00		0.00		75.00		-75.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-75.00		0.00		-75.00		-75.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.2 A national gender analysis and action plan developed to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.		1.1.2 A national gender analysis and action plan developed to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.		Activity 1.1.2 MOECC		Develop a national gender analysis and action plan to ensure gender mainstreaming within consultation processes and within actions to advise the NBSAP updating and revision process.		009562		SOM-Min. Environ. & Climate Ch		75700		Training, Workshops and Confer				0.00				0.00		0.00		0.00		0.00		0.00		0.00		0.00		9,999.00		0.00		9,999.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-9,999.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.3 Building on the results of the EAS to accelerate early action on NBSAPs, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.		1.1.3 Building on the results of the EAS to accelerate early action on NBSAPs, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.		Total												42,943.00		0.00		0.00		42,943.00		38,018.24		38,018.24		0.00		38,018.24		0.00		38,018.24		39,437.00		38,018.24		1,418.76		4,375.00		4,375.00		0.00		3,568.00		3,568.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-3,018.24		-4,437.00		4,924.76		4,924.76

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.3 Building on the results of the EAS to accelerate early action on NBSAPs, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.		1.1.3 Building on the results of the EAS to accelerate early action on NBSAPs, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.		Activity 1.1.3		Acceleration of early action on National Biodiversity Strategy and Action Plan, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.		001981		UNDP		Total				42,943.00		0.00		0.00		42,943.00		6,460.74		6,460.74		0.00		6,460.74		0.00		6,460.74		6,875.00		6,460.74		414.26		4,375.00		4,375.00		0.00		3,568.00		3,568.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		28,539.26		28,125.00		36,482.26		36,482.26

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.3 Building on the results of the EAS to accelerate early action on NBSAPs, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.		1.1.3 Building on the results of the EAS to accelerate early action on NBSAPs, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.		Activity 1.1.3		Acceleration of early action on National Biodiversity Strategy and Action Plan, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.		001981		UNDP		71300		Local Consultants		24,193.00		0.00				24,193.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		3,125.00		3,125.00		0.00		2,318.00		2,318.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		18,750.00		18,750.00		24,193.00		24,193.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.3 Building on the results of the EAS to accelerate early action on NBSAPs, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.		1.1.3 Building on the results of the EAS to accelerate early action on NBSAPs, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.		Activity 1.1.3		Acceleration of early action on National Biodiversity Strategy and Action Plan, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.		001981		UNDP		71400		Contractual Services - Individ		9,375.00		0.00				9,375.00		6,460.74		6,460.74		0.00		6,460.74		0.00		6,460.74		6,875.00		6,460.74		414.26		1,250.00		1,250.00		0.00		1,250.00		1,250.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		414.26		0.00		2,914.26		2,914.26

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.3 Building on the results of the EAS to accelerate early action on NBSAPs, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.		1.1.3 Building on the results of the EAS to accelerate early action on NBSAPs, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.		Activity 1.1.3		Acceleration of early action on National Biodiversity Strategy and Action Plan, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.		001981		UNDP		71600		Travel		5,000.00		0.00				5,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		5,000.00		5,000.00		5,000.00		5,000.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.3 Building on the results of the EAS to accelerate early action on NBSAPs, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.		1.1.3 Building on the results of the EAS to accelerate early action on NBSAPs, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.		Activity 1.1.3		Acceleration of early action on National Biodiversity Strategy and Action Plan, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.		001981		UNDP		75700		Training, Workshops and Confer		4,375.00		0.00				4,375.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		4,375.00		4,375.00		4,375.00		4,375.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.3 Building on the results of the EAS to accelerate early action on NBSAPs, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.		1.1.3 Building on the results of the EAS to accelerate early action on NBSAPs, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.						009562		SOM-Min. Environ. & Climate Ch		Total				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.3 Building on the results of the EAS to accelerate early action on NBSAPs, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.		1.1.3 Building on the results of the EAS to accelerate early action on NBSAPs, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.						009562		SOM-Min. Environ. & Climate Ch		71800		Contractual Services-Imp Partn		0.00		0.00				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.3 Building on the results of the EAS to accelerate early action on NBSAPs, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.		1.1.3 Building on the results of the EAS to accelerate early action on NBSAPs, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.						009562		SOM-Min. Environ. & Climate Ch		75700		Training, Workshops and Confer		0.00		0.00				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.3 Building on the results of the EAS to accelerate early action on NBSAPs, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.		1.1.3 Building on the results of the EAS to accelerate early action on NBSAPs, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.						009562		SOM-Min. Environ. & Climate Ch		71600		Travel		0.00		0.00				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.3 Building on the results of the EAS to accelerate early action on NBSAPs, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.		1.1.3 Building on the results of the EAS to accelerate early action on NBSAPs, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.		Activity 1.1.3 MOECC		Acceleration of early action on National Biodiversity Strategy and Action Plan, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.		009562		SOM-Min. Environ. & Climate Ch		Total				0.00		0.00		0.00		0.00		31,557.50		31,557.50		0.00		31,557.50		0.00		31,557.50		32,562.00		31,557.50		1,004.50		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-31,557.50		-32,562.00		-31,557.50		-31,557.50

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.3 Building on the results of the EAS to accelerate early action on NBSAPs, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.		1.1.3 Building on the results of the EAS to accelerate early action on NBSAPs, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.		Activity 1.1.3 MOECC		Acceleration of early action on National Biodiversity Strategy and Action Plan, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.		009562		SOM-Min. Environ. & Climate Ch		71600		Travel		0.00		0.00				0.00		5,000.00		5,000.00		0.00		5,000.00		0.00		5,000.00		5,000.00		5,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-5,000.00		-5,000.00		-5,000.00		-5,000.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.3 Building on the results of the EAS to accelerate early action on NBSAPs, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.		1.1.3 Building on the results of the EAS to accelerate early action on NBSAPs, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.		Activity 1.1.3 MOECC		Acceleration of early action on National Biodiversity Strategy and Action Plan, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.		009562		SOM-Min. Environ. & Climate Ch		71800		Contractual Services-Imp Partn		0.00		0.00				0.00		15,500.00		15,567.50		0.00		15,500.00		0.00		15,500.00		16,563.00		15,500.00		1,063.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-15,500.00		-16,563.00		-15,500.00		-15,500.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.3 Building on the results of the EAS to accelerate early action on NBSAPs, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.		1.1.3 Building on the results of the EAS to accelerate early action on NBSAPs, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.		Activity 1.1.3 MOECC		Acceleration of early action on National Biodiversity Strategy and Action Plan, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.		009562		SOM-Min. Environ. & Climate Ch		74500		Miscellaneous Expenses		0.00		0.00				0.00		307.50		240.00		0.00		307.50		0.00		307.50		0.00		307.50		-307.50		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-307.50		0.00		-307.50		-307.50

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.3 Building on the results of the EAS to accelerate early action on NBSAPs, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.		1.1.3 Building on the results of the EAS to accelerate early action on NBSAPs, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.		Activity 1.1.3 MOECC		Acceleration of early action on National Biodiversity Strategy and Action Plan, identify and prioritize essential gaps and inconsistencies between the existing NBSAP and changes needed to achieve the Global Biodiversity Framework.		009562		SOM-Min. Environ. & Climate Ch		75700		Training, Workshops and Confer		0.00		0.00				0.00		10,750.00		10,750.00		0.00		10,750.00		0.00		10,750.00		10,999.00		10,750.00		249.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-10,750.00		-10,999.00		-10,750.00		-10,750.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.4 Building on the results from policy alignment reviews included in the EAS, develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the NBSAP.		1.1.4 Building on the results from policy alignment reviews included in the EAS, develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the NBSAP.		Total												42,943.00		0.00		0.00		42,943.00		34,640.74		34,640.74		0.00		34,640.74		0.00		34,640.74		39,438.00		34,640.74		4,797.26		4,375.00		4,375.00		0.00		3,568.00		3,568.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		359.26		-4,438.00		8,302.26		8,302.26

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.4 Building on the results from policy alignment reviews included in the EAS, develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the NBSAP.		1.1.4 Building on the results from policy alignment reviews included in the EAS, develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the NBSAP.		Activity 1.1.4		Develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the National Biodiversity Strategy and Action Plan		001981		UNDP		Total				42,943.00		0.00		0.00		42,943.00		6,460.74		6,460.74		0.00		6,460.74		0.00		6,460.74		6,875.00		6,460.74		414.26		4,375.00		4,375.00		0.00		3,568.00		3,568.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		28,539.26		28,125.00		36,482.26		36,482.26

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.4 Building on the results from policy alignment reviews included in the EAS, develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the NBSAP.		1.1.4 Building on the results from policy alignment reviews included in the EAS, develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the NBSAP.		Activity 1.1.4		Develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the National Biodiversity Strategy and Action Plan		001981		UNDP		71300		Local Consultants		24,193.00		0.00				24,193.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		3,125.00		3,125.00		0.00		2,318.00		2,318.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		18,750.00		18,750.00		24,193.00		24,193.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.4 Building on the results from policy alignment reviews included in the EAS, develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the NBSAP.		1.1.4 Building on the results from policy alignment reviews included in the EAS, develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the NBSAP.		Activity 1.1.4		Develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the National Biodiversity Strategy and Action Plan		001981		UNDP		71400		Contractual Services - Individ		9,375.00		0.00				9,375.00		6,460.74		6,460.74		0.00		6,460.74		0.00		6,460.74		6,875.00		6,460.74		414.26		1,250.00		1,250.00		0.00		1,250.00		1,250.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		414.26		0.00		2,914.26		2,914.26

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.4 Building on the results from policy alignment reviews included in the EAS, develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the NBSAP.		1.1.4 Building on the results from policy alignment reviews included in the EAS, develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the NBSAP.		Activity 1.1.4		Develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the National Biodiversity Strategy and Action Plan		001981		UNDP		71600		Travel		5,000.00		0.00				5,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		5,000.00		5,000.00		5,000.00		5,000.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.4 Building on the results from policy alignment reviews included in the EAS, develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the NBSAP.		1.1.4 Building on the results from policy alignment reviews included in the EAS, develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the NBSAP.		Activity 1.1.4		Develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the National Biodiversity Strategy and Action Plan		001981		UNDP		75700		Training, Workshops and Confer		4,375.00		0.00				4,375.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		4,375.00		4,375.00		4,375.00		4,375.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.4 Building on the results from policy alignment reviews included in the EAS, develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the NBSAP.		1.1.4 Building on the results from policy alignment reviews included in the EAS, develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the NBSAP.						009562		SOM-Min. Environ. & Climate Ch		Total				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.4 Building on the results from policy alignment reviews included in the EAS, develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the NBSAP.		1.1.4 Building on the results from policy alignment reviews included in the EAS, develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the NBSAP.						009562		SOM-Min. Environ. & Climate Ch		71800		Contractual Services-Imp Partn		0.00		0.00				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.4 Building on the results from policy alignment reviews included in the EAS, develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the NBSAP.		1.1.4 Building on the results from policy alignment reviews included in the EAS, develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the NBSAP.						009562		SOM-Min. Environ. & Climate Ch		71600		Travel		0.00		0.00				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.4 Building on the results from policy alignment reviews included in the EAS, develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the NBSAP.		1.1.4 Building on the results from policy alignment reviews included in the EAS, develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the NBSAP.						009562		SOM-Min. Environ. & Climate Ch		75700		Training, Workshops and Confer		0.00		0.00				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.4 Building on the results from policy alignment reviews included in the EAS, develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the NBSAP.		1.1.4 Building on the results from policy alignment reviews included in the EAS, develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the NBSAP.		Activity 1.1.4 MOECC		Develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the National Biodiversity Strategy and Action Plan		009562		SOM-Min. Environ. & Climate Ch		Total				0.00		0.00		0.00		0.00		28,180.00		28,180.00		0.00		28,180.00		0.00		28,180.00		32,563.00		28,180.00		4,383.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-28,180.00		-32,563.00		-28,180.00		-28,180.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.4 Building on the results from policy alignment reviews included in the EAS, develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the NBSAP.		1.1.4 Building on the results from policy alignment reviews included in the EAS, develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the NBSAP.		Activity 1.1.4 MOECC		Develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the National Biodiversity Strategy and Action Plan		009562		SOM-Min. Environ. & Climate Ch		71600		Travel		0.00		0.00				0.00		5,000.00		5,000.00		0.00		5,000.00		0.00		5,000.00		5,000.00		5,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-5,000.00		-5,000.00		-5,000.00		-5,000.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.4 Building on the results from policy alignment reviews included in the EAS, develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the NBSAP.		1.1.4 Building on the results from policy alignment reviews included in the EAS, develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the NBSAP.		Activity 1.1.4 MOECC		Develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the National Biodiversity Strategy and Action Plan		009562		SOM-Min. Environ. & Climate Ch		71800		Contractual Services-Imp Partn		0.00		0.00				0.00		12,000.00		12,000.00		0.00		12,000.00		0.00		12,000.00		16,563.00		12,000.00		4,563.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-12,000.00		-16,563.00		-12,000.00		-12,000.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.4 Building on the results from policy alignment reviews included in the EAS, develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the NBSAP.		1.1.4 Building on the results from policy alignment reviews included in the EAS, develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the NBSAP.		Activity 1.1.4 MOECC		Develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the National Biodiversity Strategy and Action Plan		009562		SOM-Min. Environ. & Climate Ch		74500		Miscellaneous Expenses		0.00		0.00				0.00		180.00		180.00		0.00		180.00		0.00		180.00		0.00		180.00		-180.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-180.00		0.00		-180.00		-180.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.4 Building on the results from policy alignment reviews included in the EAS, develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the NBSAP.		1.1.4 Building on the results from policy alignment reviews included in the EAS, develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the NBSAP.		Activity 1.1.4 MOECC		Develop an NBSAP section that addresses policy alignment and coherence, and biodiversity mainstreaming into key sectors within the National Biodiversity Strategy and Action Plan		009562		SOM-Min. Environ. & Climate Ch		75700		Training, Workshops and Confer		0.00		0.00				0.00		11,000.00		11,000.00		0.00		11,000.00		0.00		11,000.00		11,000.00		11,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-11,000.00		-11,000.00		-11,000.00		-11,000.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.5 An assessment of the potential environmental and social impacts and potential risks of the implementation of the updated NBSAP.		1.1.5 An assessment of the potential environmental and social impacts and potential risks of the implementation of the updated NBSAP.		Total												42,943.00		0.00		0.00		42,943.00		41,245.74		41,208.24		0.00		41,245.74		0.00		41,245.74		38,938.00		41,245.74		-2,307.74		4,375.00		4,375.00		0.00		3,568.00		3,568.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-6,245.74		-3,938.00		1,697.26		1,697.26

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.5 An assessment of the potential environmental and social impacts and potential risks of the implementation of the updated NBSAP.		1.1.5 An assessment of the potential environmental and social impacts and potential risks of the implementation of the updated NBSAP.		Activity 1.1.5		An assessment of potential socio-economic tradeoffs, including environmental/social impacts derived from the National Biodiversity Strategic Action Plan updated		001981		UNDP		Total				42,943.00		0.00		0.00		42,943.00		6,460.74		6,460.74		0.00		6,460.74		0.00		6,460.74		6,875.00		6,460.74		414.26		4,375.00		4,375.00		0.00		3,568.00		3,568.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		28,539.26		28,125.00		36,482.26		36,482.26

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.5 An assessment of the potential environmental and social impacts and potential risks of the implementation of the updated NBSAP.		1.1.5 An assessment of the potential environmental and social impacts and potential risks of the implementation of the updated NBSAP.		Activity 1.1.5		An assessment of potential socio-economic tradeoffs, including environmental/social impacts derived from the National Biodiversity Strategic Action Plan updated		001981		UNDP		71300		Local Consultants		24,193.00		0.00				24,193.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		3,125.00		3,125.00		0.00		2,318.00		2,318.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		18,750.00		18,750.00		24,193.00		24,193.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.5 An assessment of the potential environmental and social impacts and potential risks of the implementation of the updated NBSAP.		1.1.5 An assessment of the potential environmental and social impacts and potential risks of the implementation of the updated NBSAP.		Activity 1.1.5		An assessment of potential socio-economic tradeoffs, including environmental/social impacts derived from the National Biodiversity Strategic Action Plan updated		001981		UNDP		71400		Contractual Services - Individ		9,375.00		0.00				9,375.00		6,460.74		6,460.74		0.00		6,460.74		0.00		6,460.74		6,875.00		6,460.74		414.26		1,250.00		1,250.00		0.00		1,250.00		1,250.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		414.26		0.00		2,914.26		2,914.26

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.5 An assessment of the potential environmental and social impacts and potential risks of the implementation of the updated NBSAP.		1.1.5 An assessment of the potential environmental and social impacts and potential risks of the implementation of the updated NBSAP.		Activity 1.1.5		An assessment of potential socio-economic tradeoffs, including environmental/social impacts derived from the National Biodiversity Strategic Action Plan updated		001981		UNDP		71600		Travel		5,000.00		0.00				5,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		5,000.00		5,000.00		5,000.00		5,000.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.5 An assessment of the potential environmental and social impacts and potential risks of the implementation of the updated NBSAP.		1.1.5 An assessment of the potential environmental and social impacts and potential risks of the implementation of the updated NBSAP.		Activity 1.1.5		An assessment of potential socio-economic tradeoffs, including environmental/social impacts derived from the National Biodiversity Strategic Action Plan updated		001981		UNDP		75700		Training, Workshops and Confer		4,375.00		0.00				4,375.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		4,375.00		4,375.00		4,375.00		4,375.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.5 An assessment of the potential environmental and social impacts and potential risks of the implementation of the updated NBSAP.		1.1.5 An assessment of the potential environmental and social impacts and potential risks of the implementation of the updated NBSAP.		Activity 1.1.5		An assessment of potential socio-economic tradeoffs, including environmental/social impacts derived from the National Biodiversity Strategic Action Plan updated		001981		UNDP		71800		Contractual Services-Imp Partn		0.00		0.00				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.5 An assessment of the potential environmental and social impacts and potential risks of the implementation of the updated NBSAP.		1.1.5 An assessment of the potential environmental and social impacts and potential risks of the implementation of the updated NBSAP.						009562		SOM-Min. Environ. & Climate Ch		Total				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.5 An assessment of the potential environmental and social impacts and potential risks of the implementation of the updated NBSAP.		1.1.5 An assessment of the potential environmental and social impacts and potential risks of the implementation of the updated NBSAP.						009562		SOM-Min. Environ. & Climate Ch		75700		Training, Workshops and Confer		0.00		0.00				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.5 An assessment of the potential environmental and social impacts and potential risks of the implementation of the updated NBSAP.		1.1.5 An assessment of the potential environmental and social impacts and potential risks of the implementation of the updated NBSAP.						009562		SOM-Min. Environ. & Climate Ch		71600		Travel		0.00		0.00				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.5 An assessment of the potential environmental and social impacts and potential risks of the implementation of the updated NBSAP.		1.1.5 An assessment of the potential environmental and social impacts and potential risks of the implementation of the updated NBSAP.		Activity 1.1.5 MOECC		An assessment of potential socio-economic tradeoffs, including environmental/social impacts derived from the National Biodiversity Strategic Action Plan updated		009562		SOM-Min. Environ. & Climate Ch		Total				0.00		0.00		0.00		0.00		34,785.00		34,747.50		0.00		34,785.00		0.00		34,785.00		32,063.00		34,785.00		-2,722.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-34,785.00		-32,063.00		-34,785.00		-34,785.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.5 An assessment of the potential environmental and social impacts and potential risks of the implementation of the updated NBSAP.		1.1.5 An assessment of the potential environmental and social impacts and potential risks of the implementation of the updated NBSAP.		Activity 1.1.5 MOECC		An assessment of potential socio-economic tradeoffs, including environmental/social impacts derived from the National Biodiversity Strategic Action Plan updated		009562		SOM-Min. Environ. & Climate Ch		71600		Travel		0.00		0.00				0.00		5,000.00		5,000.00		0.00		5,000.00		0.00		5,000.00		5,000.00		5,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-5,000.00		-5,000.00		-5,000.00		-5,000.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.5 An assessment of the potential environmental and social impacts and potential risks of the implementation of the updated NBSAP.		1.1.5 An assessment of the potential environmental and social impacts and potential risks of the implementation of the updated NBSAP.		Activity 1.1.5 MOECC		An assessment of potential socio-economic tradeoffs, including environmental/social impacts derived from the National Biodiversity Strategic Action Plan updated		009562		SOM-Min. Environ. & Climate Ch		71800		Contractual Services-Imp Partn		0.00		0.00				0.00		16,537.50		16,537.50		0.00		16,537.50		0.00		16,537.50		16,563.00		16,537.50		25.50		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-16,537.50		-16,563.00		-16,537.50		-16,537.50

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.5 An assessment of the potential environmental and social impacts and potential risks of the implementation of the updated NBSAP.		1.1.5 An assessment of the potential environmental and social impacts and potential risks of the implementation of the updated NBSAP.		Activity 1.1.5 MOECC		An assessment of potential socio-economic tradeoffs, including environmental/social impacts derived from the National Biodiversity Strategic Action Plan updated		009562		SOM-Min. Environ. & Climate Ch		74500		Miscellaneous Expenses		0.00		0.00				0.00		2,747.50		2,710.00		0.00		2,747.50		0.00		2,747.50		0.00		2,747.50		-2,747.50		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-2,747.50		0.00		-2,747.50		-2,747.50

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.5 An assessment of the potential environmental and social impacts and potential risks of the implementation of the updated NBSAP.		1.1.5 An assessment of the potential environmental and social impacts and potential risks of the implementation of the updated NBSAP.		Activity 1.1.5 MOECC		An assessment of potential socio-economic tradeoffs, including environmental/social impacts derived from the National Biodiversity Strategic Action Plan updated		009562		SOM-Min. Environ. & Climate Ch		75700		Training, Workshops and Confer		0.00		0.00				0.00		10,500.00		10,500.00		0.00		10,500.00		0.00		10,500.00		10,500.00		10,500.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-10,500.00		-10,500.00		-10,500.00		-10,500.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.6 Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.		1.1.6 Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.		Total												42,943.00		0.00		0.00		42,943.00		28,702.50		28,702.50		0.00		28,702.50		0.00		28,702.50		31,563.00		28,702.50		2,860.50		4,375.00		4,375.00		0.00		3,568.00		3,568.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		6,297.50		3,437.00		14,240.50		14,240.50

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.6 Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.		1.1.6 Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.		Activity 1.1.6		Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.		001981		UNDP		Total				42,943.00		0.00		0.00		42,943.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		4,375.00		4,375.00		0.00		3,568.00		3,568.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		35,000.00		35,000.00		42,943.00		42,943.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.6 Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.		1.1.6 Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.		Activity 1.1.6		Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.		001981		UNDP		71300		Local Consultants		24,193.00		0.00				24,193.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		3,125.00		3,125.00		0.00		2,318.00		2,318.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		18,750.00		18,750.00		24,193.00		24,193.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.6 Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.		1.1.6 Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.		Activity 1.1.6		Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.		001981		UNDP		71400		Contractual Services - Individ		9,375.00		0.00				9,375.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		1,250.00		1,250.00		0.00		1,250.00		1,250.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		6,875.00		6,875.00		9,375.00		9,375.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.6 Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.		1.1.6 Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.		Activity 1.1.6		Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.		001981		UNDP		71600		Travel		5,000.00		0.00				5,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		5,000.00		5,000.00		5,000.00		5,000.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.6 Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.		1.1.6 Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.		Activity 1.1.6		Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.		001981		UNDP		75700		Training, Workshops and Confer		4,375.00		0.00				4,375.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		4,375.00		4,375.00		4,375.00		4,375.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.6 Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.		1.1.6 Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.						009562		SOM-Min. Environ. & Climate Ch		Total				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.6 Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.		1.1.6 Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.						009562		SOM-Min. Environ. & Climate Ch		71600		Travel		0.00		0.00				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.6 Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.		1.1.6 Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.						009562		SOM-Min. Environ. & Climate Ch		71800		Contractual Services-Imp Partn		0.00		0.00				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.6 Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.		1.1.6 Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.						009562		SOM-Min. Environ. & Climate Ch		75700		Training, Workshops and Confer		0.00		0.00				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.6 Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.		1.1.6 Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.		Activity 1.1.6 MOECC		Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.		009562		SOM-Min. Environ. & Climate Ch		Total				0.00		0.00		0.00		0.00		28,702.50		28,702.50		0.00		28,702.50		0.00		28,702.50		31,563.00		28,702.50		2,860.50		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-28,702.50		-31,563.00		-28,702.50		-28,702.50

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.6 Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.		1.1.6 Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.		Activity 1.1.6 MOECC		Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.		009562		SOM-Min. Environ. & Climate Ch		71600		Travel		0.00		0.00				0.00		5,000.00		5,000.00		0.00		5,000.00		0.00		5,000.00		5,000.00		5,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-5,000.00		-5,000.00		-5,000.00		-5,000.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.6 Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.		1.1.6 Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.		Activity 1.1.6 MOECC		Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.		009562		SOM-Min. Environ. & Climate Ch		71800		Contractual Services-Imp Partn		0.00		0.00				0.00		13,500.00		13,500.00		0.00		13,500.00		0.00		13,500.00		16,563.00		13,500.00		3,063.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-13,500.00		-16,563.00		-13,500.00		-13,500.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.6 Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.		1.1.6 Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.		Activity 1.1.6 MOECC		Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.		009562		SOM-Min. Environ. & Climate Ch		74500		Miscellaneous Expenses		0.00		0.00				0.00		202.50		202.50		0.00		202.50		0.00		202.50		0.00		202.50		-202.50		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-202.50		0.00		-202.50		-202.50

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.6 Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.		1.1.6 Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.		Activity 1.1.6 MOECC		Building on nationally and globally available data, develop a first approximation of spatial priorities for Target 1, and develop a spatialized action plan for other area-based targets, including Targets 2, 3, 8, 9, 11 and 12, within the NBSAP.		009562		SOM-Min. Environ. & Climate Ch		75700		Training, Workshops and Confer		0.00		0.00				0.00		10,000.00		10,000.00		0.00		10,000.00		0.00		10,000.00		10,000.00		10,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-10,000.00		-10,000.00		-10,000.00		-10,000.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.7 Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP		1.1.7 Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP		Total												42,943.00		0.00		0.00		42,943.00		25,075.00		25,075.00		0.00		25,075.00		0.00		25,075.00		31,563.00		25,075.00		6,488.00		4,375.00		4,375.00		0.00		3,568.00		3,568.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		9,925.00		3,437.00		17,868.00		17,868.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.7 Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP		1.1.7 Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP		Activity 1.1.7		Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP.		001981		UNDP		Total				42,943.00		0.00		0.00		42,943.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		4,375.00		4,375.00		0.00		3,568.00		3,568.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		35,000.00		35,000.00		42,943.00		42,943.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.7 Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP		1.1.7 Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP		Activity 1.1.7		Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP.		001981		UNDP		71300		Local Consultants		24,193.00		0.00				24,193.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		3,125.00		3,125.00		0.00		2,318.00		2,318.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		18,750.00		18,750.00		24,193.00		24,193.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.7 Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP		1.1.7 Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP		Activity 1.1.7		Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP.		001981		UNDP		71400		Contractual Services - Individ		9,375.00		0.00				9,375.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		1,250.00		1,250.00		0.00		1,250.00		1,250.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		6,875.00		6,875.00		9,375.00		9,375.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.7 Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP		1.1.7 Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP		Activity 1.1.7		Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP.		001981		UNDP		71600		Travel		5,000.00		0.00				5,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		5,000.00		5,000.00		5,000.00		5,000.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.7 Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP		1.1.7 Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP		Activity 1.1.7		Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP.		001981		UNDP		75700		Training, Workshops and Confer		4,375.00		0.00				4,375.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		4,375.00		4,375.00		4,375.00		4,375.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.7 Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP		1.1.7 Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP						009562		SOM-Min. Environ. & Climate Ch		Total				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.7 Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP		1.1.7 Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP						009562		SOM-Min. Environ. & Climate Ch		71800		Contractual Services-Imp Partn		0.00		0.00				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.7 Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP		1.1.7 Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP						009562		SOM-Min. Environ. & Climate Ch		75700		Training, Workshops and Confer		0.00		0.00				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.7 Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP		1.1.7 Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP		Activity 1.1.7 MOECC		Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP.		009562		SOM-Min. Environ. & Climate Ch		Total				0.00		0.00		0.00		0.00		25,075.00		25,075.00		0.00		25,075.00		0.00		25,075.00		31,563.00		25,075.00		6,488.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-25,075.00		-31,563.00		-25,075.00		-25,075.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.7 Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP		1.1.7 Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP		Activity 1.1.7 MOECC		Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP.		009562		SOM-Min. Environ. & Climate Ch		71600		Travel		0.00		0.00				0.00		10,000.00		10,000.00		0.00		10,000.00		0.00		10,000.00		5,000.00		10,000.00		-5,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-10,000.00		-5,000.00		-10,000.00		-10,000.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.7 Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP		1.1.7 Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP		Activity 1.1.7 MOECC		Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP.		009562		SOM-Min. Environ. & Climate Ch		71800		Contractual Services-Imp Partn		0.00		0.00				0.00		5,000.00		5,000.00		0.00		5,000.00		0.00		5,000.00		16,563.00		5,000.00		11,563.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-5,000.00		-16,563.00		-5,000.00		-5,000.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.7 Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP		1.1.7 Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP		Activity 1.1.7 MOECC		Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP.		009562		SOM-Min. Environ. & Climate Ch		74500		Miscellaneous Expenses		0.00		0.00				0.00		75.00		75.00		0.00		75.00		0.00		75.00		0.00		75.00		-75.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-75.00		0.00		-75.00		-75.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.7 Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP		1.1.7 Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP		Activity 1.1.7 MOECC		Building on the results of the EAS, identify an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP.		009562		SOM-Min. Environ. & Climate Ch		75700		Training, Workshops and Confer		0.00		0.00				0.00		10,000.00		10,000.00		0.00		10,000.00		0.00		10,000.00		10,000.00		10,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-10,000.00		-10,000.00		-10,000.00		-10,000.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.8 An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project, the umbrella program to support development of biodiversity finance plans, and other initiatives such as BIOFIN.		1.1.8 An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project, the umbrella program to support development of biodiversity finance plans, and other initiatives such as BIOFIN.		Total												42,946.00		0.00		0.00		42,946.00		28,121.20		28,121.20		0.00		28,121.20		0.00		28,121.20		31,563.00		28,121.20		3,441.80		4,375.00		3,125.00		1,250.00		3,571.00		2,321.00		1,250.00		0.00		0.00		0.00		0.00		0.00		0.00		9,378.80		3,437.00		14,824.80		14,824.80

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.8 An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project, the umbrella program to support development of biodiversity finance plans, and other initiatives such as BIOFIN.		1.1.8 An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project, the umbrella program to support development of biodiversity finance plans, and other initiatives such as BIOFIN.		Activity 1.1.8		An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project.		001981		UNDP		Total				42,946.00		0.00		0.00		42,946.00		2,896.20		2,896.20		0.00		2,896.20		0.00		2,896.20		0.00		2,896.20		-2,896.20		4,375.00		3,125.00		1,250.00		3,571.00		2,321.00		1,250.00		0.00		0.00		0.00		0.00		0.00		0.00		34,603.80		35,000.00		40,049.80		40,049.80

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.8 An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project, the umbrella program to support development of biodiversity finance plans, and other initiatives such as BIOFIN.		1.1.8 An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project, the umbrella program to support development of biodiversity finance plans, and other initiatives such as BIOFIN.		Activity 1.1.8		An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project.		001981		UNDP		71300		Local Consultants		24,196.00		0.00				24,196.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		3,125.00		3,125.00		0.00		2,321.00		2,321.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		18,750.00		18,750.00		24,196.00		24,196.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.8 An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project, the umbrella program to support development of biodiversity finance plans, and other initiatives such as BIOFIN.		1.1.8 An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project, the umbrella program to support development of biodiversity finance plans, and other initiatives such as BIOFIN.		Activity 1.1.8		An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project.		001981		UNDP		71400		Contractual Services - Individ		9,375.00		0.00				9,375.00		2,896.20		2,896.20		0.00		2,896.20		0.00		2,896.20		0.00		2,896.20		-2,896.20		1,250.00		0.00		1,250.00		1,250.00		0.00		1,250.00		0.00		0.00		0.00		0.00		0.00		0.00		6,478.80		6,875.00		6,478.80		6,478.80

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.8 An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project, the umbrella program to support development of biodiversity finance plans, and other initiatives such as BIOFIN.		1.1.8 An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project, the umbrella program to support development of biodiversity finance plans, and other initiatives such as BIOFIN.		Activity 1.1.8		An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project.		001981		UNDP		71600		Travel		5,000.00		0.00				5,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		5,000.00		5,000.00		5,000.00		5,000.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.8 An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project, the umbrella program to support development of biodiversity finance plans, and other initiatives such as BIOFIN.		1.1.8 An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project, the umbrella program to support development of biodiversity finance plans, and other initiatives such as BIOFIN.		Activity 1.1.8		An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project.		001981		UNDP		75700		Training, Workshops and Confer		4,375.00		0.00				4,375.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		4,375.00		4,375.00		4,375.00		4,375.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.8 An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project, the umbrella program to support development of biodiversity finance plans, and other initiatives such as BIOFIN.		1.1.8 An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project, the umbrella program to support development of biodiversity finance plans, and other initiatives such as BIOFIN.						009562		SOM-Min. Environ. & Climate Ch		Total				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.8 An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project, the umbrella program to support development of biodiversity finance plans, and other initiatives such as BIOFIN.		1.1.8 An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project, the umbrella program to support development of biodiversity finance plans, and other initiatives such as BIOFIN.						009562		SOM-Min. Environ. & Climate Ch		71600		Travel		0.00		0.00				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.8 An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project, the umbrella program to support development of biodiversity finance plans, and other initiatives such as BIOFIN.		1.1.8 An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project, the umbrella program to support development of biodiversity finance plans, and other initiatives such as BIOFIN.						009562		SOM-Min. Environ. & Climate Ch		71800		Contractual Services-Imp Partn		0.00		0.00				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.8 An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project, the umbrella program to support development of biodiversity finance plans, and other initiatives such as BIOFIN.		1.1.8 An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project, the umbrella program to support development of biodiversity finance plans, and other initiatives such as BIOFIN.						009562		SOM-Min. Environ. & Climate Ch		75700		Training, Workshops and Confer		0.00		0.00				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.8 An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project, the umbrella program to support development of biodiversity finance plans, and other initiatives such as BIOFIN.		1.1.8 An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project, the umbrella program to support development of biodiversity finance plans, and other initiatives such as BIOFIN.		Activity 1.1.8 MOECC		An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project.		009562		SOM-Min. Environ. & Climate Ch		Total				0.00		0.00		0.00		0.00		25,225.00		25,225.00		0.00		25,225.00		0.00		25,225.00		31,563.00		25,225.00		6,338.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-25,225.00		-31,563.00		-25,225.00		-25,225.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.8 An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project, the umbrella program to support development of biodiversity finance plans, and other initiatives such as BIOFIN.		1.1.8 An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project, the umbrella program to support development of biodiversity finance plans, and other initiatives such as BIOFIN.		Activity 1.1.8 MOECC		An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project.		009562		SOM-Min. Environ. & Climate Ch		71600		Travel				0.00				0.00		0.00		0.00		0.00		0.00		0.00		0.00		5,000.00		0.00		5,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-5,000.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.8 An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project, the umbrella program to support development of biodiversity finance plans, and other initiatives such as BIOFIN.		1.1.8 An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project, the umbrella program to support development of biodiversity finance plans, and other initiatives such as BIOFIN.		Activity 1.1.8 MOECC		An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project.		009562		SOM-Min. Environ. & Climate Ch		71800		Contractual Services-Imp Partn		0.00		0.00				0.00		7,500.00		15,000.00		0.00		7,500.00		0.00		7,500.00		16,563.00		7,500.00		9,063.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-7,500.00		-16,563.00		-7,500.00		-7,500.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.8 An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project, the umbrella program to support development of biodiversity finance plans, and other initiatives such as BIOFIN.		1.1.8 An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project, the umbrella program to support development of biodiversity finance plans, and other initiatives such as BIOFIN.		Activity 1.1.8 MOECC		An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project.		009562		SOM-Min. Environ. & Climate Ch		74500		Miscellaneous Expenses		0.00		0.00				0.00		7,725.00		225.00		0.00		7,725.00		0.00		7,725.00		0.00		7,725.00		-7,725.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-7,725.00		0.00		-7,725.00		-7,725.00

		1259824		01003136		GEF		62000		10003		1. Revision and updating of National Biodiversity Strategies and Action Plans		N/A 1.1.8 An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project, the umbrella program to support development of biodiversity finance plans, and other initiatives such as BIOFIN.		1.1.8 An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project, the umbrella program to support development of biodiversity finance plans, and other initiatives such as BIOFIN.		Activity 1.1.8 MOECC		An assessment of gaps in capacities and resources available undertaken and on that basis, develop plans or strategies for capacity development and resource mobilization, building on the work undertaken under the early support action project.		009562		SOM-Min. Environ. & Climate Ch		75700		Training, Workshops and Confer		0.00		0.00				0.00		10,000.00		10,000.00		0.00		10,000.00		0.00		10,000.00		10,000.00		10,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-10,000.00		-10,000.00		-10,000.00		-10,000.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		Total																100,000.00		0.00		0.00		100,000.00		8,627.50		8,627.50		0.00		8,627.50		0.00		8,627.50		30,624.00		8,627.50		21,996.50		55,000.00		60,624.00		-5,624.00		5,000.00		5,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		25,748.50		9,376.00		91,372.50		91,372.50

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.1 Brief overview of the process of preparation of the report is completed.		2.1.1 Brief overview of the process of preparation of the report is completed.		Total												20,000.00		0.00		0.00		20,000.00		2,537.50		2,537.50		0.00		2,537.50		0.00		2,537.50		6,000.00		2,537.50		3,462.50		11,000.00		12,000.00		-1,000.00		1,000.00		1,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		4,462.50		2,000.00		17,462.50		17,462.50

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.1 Brief overview of the process of preparation of the report is completed.		2.1.1 Brief overview of the process of preparation of the report is completed.						009562		SOM-Min. Environ. & Climate Ch		Total				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.1 Brief overview of the process of preparation of the report is completed.		2.1.1 Brief overview of the process of preparation of the report is completed.						009562		SOM-Min. Environ. & Climate Ch		71800		Contractual Services-Imp Partn		0.00		0.00				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.1 Brief overview of the process of preparation of the report is completed.		2.1.1 Brief overview of the process of preparation of the report is completed.		Activiy 2.1.1		Preparation of the report is completed		001981		UNDP		Total				20,000.00		0.00		0.00		20,000.00		0.00		0.00		0.00		0.00		0.00		0.00		1,000.00		0.00		1,000.00		11,000.00		12,000.00		-1,000.00		1,000.00		1,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		7,000.00		7,000.00		20,000.00		20,000.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.1 Brief overview of the process of preparation of the report is completed.		2.1.1 Brief overview of the process of preparation of the report is completed.		Activiy 2.1.1		Preparation of the report is completed		001981		UNDP		71300		Local Consultants		17,000.00		0.00				17,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		10,000.00		10,000.00		0.00		1,000.00		1,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		6,000.00		6,000.00		17,000.00		17,000.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.1 Brief overview of the process of preparation of the report is completed.		2.1.1 Brief overview of the process of preparation of the report is completed.		Activiy 2.1.1		Preparation of the report is completed		001981		UNDP		71400		Contractual Services - Individ		2,000.00		0.00				2,000.00		0.00		0.00		0.00		0.00		0.00		0.00		1,000.00		0.00		1,000.00		1,000.00		2,000.00		-1,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		2,000.00		2,000.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.1 Brief overview of the process of preparation of the report is completed.		2.1.1 Brief overview of the process of preparation of the report is completed.		Activiy 2.1.1		Preparation of the report is completed		001981		UNDP		71600		Travel		1,000.00		0.00				1,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		1,000.00		1,000.00		1,000.00		1,000.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.1 Brief overview of the process of preparation of the report is completed.		2.1.1 Brief overview of the process of preparation of the report is completed.		Activiy 2.1.1 MOECC		Preparation of the report is completed		009562		SOM-Min. Environ. & Climate Ch		Total				0.00		0.00		0.00		0.00		2,537.50		2,537.50		0.00		2,537.50		0.00		2,537.50		5,000.00		2,537.50		2,462.50		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-2,537.50		-5,000.00		-2,537.50		-2,537.50

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.1 Brief overview of the process of preparation of the report is completed.		2.1.1 Brief overview of the process of preparation of the report is completed.		Activiy 2.1.1 MOECC		Preparation of the report is completed		009562		SOM-Min. Environ. & Climate Ch		71800		Contractual Services-Imp Partn		0.00		0.00				0.00		2,500.00		2,500.00		0.00		2,500.00		0.00		2,500.00		5,000.00		2,500.00		2,500.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-2,500.00		-5,000.00		-2,500.00		-2,500.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.1 Brief overview of the process of preparation of the report is completed.		2.1.1 Brief overview of the process of preparation of the report is completed.		Activiy 2.1.1 MOECC		Preparation of the report is completed		009562		SOM-Min. Environ. & Climate Ch		74500		Miscellaneous Expenses		0.00		0.00				0.00		37.50		37.50		0.00		37.50		0.00		37.50		0.00		37.50		-37.50		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-37.50		0.00		-37.50		-37.50

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.2 Status of the revised or updated national biodiversity strategy and action plan (NBSAP) in the light of the Kunming-Montreal Global Biodiversity Framework.		2.1.2 Status of the revised or updated national biodiversity strategy and action plan (NBSAP) in the light of the Kunming-Montreal Global Biodiversity Framework.		Total												20,000.00		0.00		0.00		20,000.00		0.00		0.00		0.00		0.00		0.00		0.00		5,562.00		0.00		5,562.00		11,000.00		11,562.00		-562.00		1,000.00		1,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		7,438.00		2,438.00		20,000.00		20,000.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.2 Status of the revised or updated national biodiversity strategy and action plan (NBSAP) in the light of the Kunming-Montreal Global Biodiversity Framework.		2.1.2 Status of the revised or updated national biodiversity strategy and action plan (NBSAP) in the light of the Kunming-Montreal Global Biodiversity Framework.						009562		SOM-Min. Environ. & Climate Ch		Total				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.2 Status of the revised or updated national biodiversity strategy and action plan (NBSAP) in the light of the Kunming-Montreal Global Biodiversity Framework.		2.1.2 Status of the revised or updated national biodiversity strategy and action plan (NBSAP) in the light of the Kunming-Montreal Global Biodiversity Framework.						009562		SOM-Min. Environ. & Climate Ch		71800		Contractual Services-Imp Partn		0.00		0.00				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.2 Status of the revised or updated national biodiversity strategy and action plan (NBSAP) in the light of the Kunming-Montreal Global Biodiversity Framework.		2.1.2 Status of the revised or updated national biodiversity strategy and action plan (NBSAP) in the light of the Kunming-Montreal Global Biodiversity Framework.		Activity 2.1.2		Status of the revised NBSAP		001981		UNDP		Total				20,000.00		0.00		0.00		20,000.00		0.00		0.00		0.00		0.00		0.00		0.00		562.00		0.00		562.00		11,000.00		11,562.00		-562.00		1,000.00		1,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		7,438.00		7,438.00		20,000.00		20,000.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.2 Status of the revised or updated national biodiversity strategy and action plan (NBSAP) in the light of the Kunming-Montreal Global Biodiversity Framework.		2.1.2 Status of the revised or updated national biodiversity strategy and action plan (NBSAP) in the light of the Kunming-Montreal Global Biodiversity Framework.		Activity 2.1.2		Status of the revised NBSAP		001981		UNDP		71300		Local Consultants		17,000.00		0.00				17,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		10,000.00		10,000.00		0.00		1,000.00		1,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		6,000.00		6,000.00		17,000.00		17,000.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.2 Status of the revised or updated national biodiversity strategy and action plan (NBSAP) in the light of the Kunming-Montreal Global Biodiversity Framework.		2.1.2 Status of the revised or updated national biodiversity strategy and action plan (NBSAP) in the light of the Kunming-Montreal Global Biodiversity Framework.		Activity 2.1.2		Status of the revised NBSAP		001981		UNDP		71400		Contractual Services - Individ		2,000.00		0.00				2,000.00		0.00		0.00		0.00		0.00		0.00		0.00		562.00		0.00		562.00		1,000.00		1,562.00		-562.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		438.00		438.00		2,000.00		2,000.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.2 Status of the revised or updated national biodiversity strategy and action plan (NBSAP) in the light of the Kunming-Montreal Global Biodiversity Framework.		2.1.2 Status of the revised or updated national biodiversity strategy and action plan (NBSAP) in the light of the Kunming-Montreal Global Biodiversity Framework.		Activity 2.1.2		Status of the revised NBSAP		001981		UNDP		71600		Travel		1,000.00		0.00				1,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		1,000.00		1,000.00		1,000.00		1,000.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.2 Status of the revised or updated national biodiversity strategy and action plan (NBSAP) in the light of the Kunming-Montreal Global Biodiversity Framework.		2.1.2 Status of the revised or updated national biodiversity strategy and action plan (NBSAP) in the light of the Kunming-Montreal Global Biodiversity Framework.		Activity 2.1.2 MOECC		Status of the revised NBSAP		009562		SOM-Min. Environ. & Climate Ch		Total				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		5,000.00		0.00		5,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-5,000.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.2 Status of the revised or updated national biodiversity strategy and action plan (NBSAP) in the light of the Kunming-Montreal Global Biodiversity Framework.		2.1.2 Status of the revised or updated national biodiversity strategy and action plan (NBSAP) in the light of the Kunming-Montreal Global Biodiversity Framework.		Activity 2.1.2 MOECC		Status of the revised NBSAP		009562		SOM-Min. Environ. & Climate Ch		71800		Contractual Services-Imp Partn				0.00				0.00		0.00		0.00		0.00		0.00		0.00		0.00		5,000.00		0.00		5,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-5,000.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.3 Assessment of progress towards national targets are completed;		2.1.3 Assessment of progress towards national targets are completed;		Total												20,000.00		0.00		0.00		20,000.00		2,537.50		2,537.50		0.00		2,537.50		0.00		2,537.50		5,062.00		2,537.50		2,524.50		11,000.00		11,062.00		-62.00		1,000.00		1,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		5,400.50		2,938.00		17,462.50		17,462.50

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.3 Assessment of progress towards national targets are completed;		2.1.3 Assessment of progress towards national targets are completed;						009562		SOM-Min. Environ. & Climate Ch		Total				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.3 Assessment of progress towards national targets are completed;		2.1.3 Assessment of progress towards national targets are completed;						009562		SOM-Min. Environ. & Climate Ch		71800		Contractual Services-Imp Partn		0.00		0.00				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.3 Assessment of progress towards national targets are completed;		2.1.3 Assessment of progress towards national targets are completed;		Activity 2.1.3		Assessment of progress towards national targets are completed		001981		UNDP		Total				20,000.00		0.00		0.00		20,000.00		0.00		0.00		0.00		0.00		0.00		0.00		62.00		0.00		62.00		11,000.00		11,062.00		-62.00		1,000.00		1,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		7,938.00		7,938.00		20,000.00		20,000.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.3 Assessment of progress towards national targets are completed;		2.1.3 Assessment of progress towards national targets are completed;		Activity 2.1.3		Assessment of progress towards national targets are completed		001981		UNDP		71300		Local Consultants		17,000.00		0.00				17,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		10,000.00		10,000.00		0.00		1,000.00		1,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		6,000.00		6,000.00		17,000.00		17,000.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.3 Assessment of progress towards national targets are completed;		2.1.3 Assessment of progress towards national targets are completed;		Activity 2.1.3		Assessment of progress towards national targets are completed		001981		UNDP		71400		Contractual Services - Individ		2,000.00		0.00				2,000.00		0.00		0.00		0.00		0.00		0.00		0.00		62.00		0.00		62.00		1,000.00		1,062.00		-62.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		938.00		938.00		2,000.00		2,000.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.3 Assessment of progress towards national targets are completed;		2.1.3 Assessment of progress towards national targets are completed;		Activity 2.1.3		Assessment of progress towards national targets are completed		001981		UNDP		71600		Travel		1,000.00		0.00				1,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		1,000.00		1,000.00		1,000.00		1,000.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.3 Assessment of progress towards national targets are completed;		2.1.3 Assessment of progress towards national targets are completed;		Activity 2.1.3 MOECC		Assessment of progress towards national targets are completed		009562		SOM-Min. Environ. & Climate Ch		Total				0.00		0.00		0.00		0.00		2,537.50		2,537.50		0.00		2,537.50		0.00		2,537.50		5,000.00		2,537.50		2,462.50		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-2,537.50		-5,000.00		-2,537.50		-2,537.50

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.3 Assessment of progress towards national targets are completed;		2.1.3 Assessment of progress towards national targets are completed;		Activity 2.1.3 MOECC		Assessment of progress towards national targets are completed		009562		SOM-Min. Environ. & Climate Ch		71800		Contractual Services-Imp Partn		0.00		0.00				0.00		2,500.00		2,500.00		0.00		2,500.00		0.00		2,500.00		5,000.00		2,500.00		2,500.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-2,500.00		-5,000.00		-2,500.00		-2,500.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.3 Assessment of progress towards national targets are completed;		2.1.3 Assessment of progress towards national targets are completed;		Activity 2.1.3 MOECC		Assessment of progress towards national targets are completed		009562		SOM-Min. Environ. & Climate Ch		74500		Miscellaneous Expenses		0.00		0.00				0.00		37.50		37.50		0.00		37.50		0.00		37.50		0.00		37.50		-37.50		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-37.50		0.00		-37.50		-37.50

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.4. Assessment of progress related to the goals and targets of the Kunming-Montreal Global Biodiversity Framework is completed;		2.1.4. Assessment of progress related to the goals and targets of the Kunming-Montreal Global Biodiversity Framework is completed;		Total												20,000.00		0.00		0.00		20,000.00		3,552.50		3,552.50		0.00		3,552.50		0.00		3,552.50		6,000.00		3,552.50		2,447.50		11,000.00		12,000.00		-1,000.00		1,000.00		1,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		3,447.50		2,000.00		16,447.50		16,447.50

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.4. Assessment of progress related to the goals and targets of the Kunming-Montreal Global Biodiversity Framework is completed;		2.1.4. Assessment of progress related to the goals and targets of the Kunming-Montreal Global Biodiversity Framework is completed;						009562		SOM-Min. Environ. & Climate Ch		Total				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.4. Assessment of progress related to the goals and targets of the Kunming-Montreal Global Biodiversity Framework is completed;		2.1.4. Assessment of progress related to the goals and targets of the Kunming-Montreal Global Biodiversity Framework is completed;						009562		SOM-Min. Environ. & Climate Ch		71800		Contractual Services-Imp Partn		0.00		0.00				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.4. Assessment of progress related to the goals and targets of the Kunming-Montreal Global Biodiversity Framework is completed;		2.1.4. Assessment of progress related to the goals and targets of the Kunming-Montreal Global Biodiversity Framework is completed;		Activity 2.1.4		Assessment of progress related to the goals and targets		001981		UNDP		Total				20,000.00		0.00		0.00		20,000.00		0.00		0.00		0.00		0.00		0.00		0.00		1,000.00		0.00		1,000.00		11,000.00		12,000.00		-1,000.00		1,000.00		1,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		7,000.00		7,000.00		20,000.00		20,000.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.4. Assessment of progress related to the goals and targets of the Kunming-Montreal Global Biodiversity Framework is completed;		2.1.4. Assessment of progress related to the goals and targets of the Kunming-Montreal Global Biodiversity Framework is completed;		Activity 2.1.4		Assessment of progress related to the goals and targets		001981		UNDP		71300		Local Consultants		17,000.00		0.00				17,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		10,000.00		10,000.00		0.00		1,000.00		1,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		6,000.00		6,000.00		17,000.00		17,000.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.4. Assessment of progress related to the goals and targets of the Kunming-Montreal Global Biodiversity Framework is completed;		2.1.4. Assessment of progress related to the goals and targets of the Kunming-Montreal Global Biodiversity Framework is completed;		Activity 2.1.4		Assessment of progress related to the goals and targets		001981		UNDP		71400		Contractual Services - Individ		2,000.00		0.00				2,000.00		0.00		0.00		0.00		0.00		0.00		0.00		1,000.00		0.00		1,000.00		1,000.00		2,000.00		-1,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		2,000.00		2,000.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.4. Assessment of progress related to the goals and targets of the Kunming-Montreal Global Biodiversity Framework is completed;		2.1.4. Assessment of progress related to the goals and targets of the Kunming-Montreal Global Biodiversity Framework is completed;		Activity 2.1.4		Assessment of progress related to the goals and targets		001981		UNDP		71600		Travel		1,000.00		0.00				1,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		1,000.00		1,000.00		1,000.00		1,000.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.4. Assessment of progress related to the goals and targets of the Kunming-Montreal Global Biodiversity Framework is completed;		2.1.4. Assessment of progress related to the goals and targets of the Kunming-Montreal Global Biodiversity Framework is completed;		Activity 2.1.4 MOECC		Assessment of progress related to the goals and targets		009562		SOM-Min. Environ. & Climate Ch		Total				0.00		0.00		0.00		0.00		3,552.50		3,552.50		0.00		3,552.50		0.00		3,552.50		5,000.00		3,552.50		1,447.50		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-3,552.50		-5,000.00		-3,552.50		-3,552.50

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.4. Assessment of progress related to the goals and targets of the Kunming-Montreal Global Biodiversity Framework is completed;		2.1.4. Assessment of progress related to the goals and targets of the Kunming-Montreal Global Biodiversity Framework is completed;		Activity 2.1.4 MOECC		Assessment of progress related to the goals and targets		009562		SOM-Min. Environ. & Climate Ch		71800		Contractual Services-Imp Partn		0.00		0.00				0.00		3,500.00		3,500.00		0.00		3,500.00		0.00		3,500.00		5,000.00		3,500.00		1,500.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-3,500.00		-5,000.00		-3,500.00		-3,500.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.4. Assessment of progress related to the goals and targets of the Kunming-Montreal Global Biodiversity Framework is completed;		2.1.4. Assessment of progress related to the goals and targets of the Kunming-Montreal Global Biodiversity Framework is completed;		Activity 2.1.4 MOECC		Assessment of progress related to the goals and targets		009562		SOM-Min. Environ. & Climate Ch		74500		Miscellaneous Expenses		0.00		0.00				0.00		52.50		52.50		0.00		52.50		0.00		52.50		0.00		52.50		-52.50		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-52.50		0.00		-52.50		-52.50

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.5 Conclusions on the implementation of the Convention and the Kunming-Montreal Global Biodiversity Framework are completed.		2.1.5 Conclusions on the implementation of the Convention and the Kunming-Montreal Global Biodiversity Framework are completed.		Total												20,000.00		0.00		0.00		20,000.00		0.00		0.00		0.00		0.00		0.00		0.00		8,000.00		0.00		8,000.00		11,000.00		14,000.00		-3,000.00		1,000.00		1,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		5,000.00		0.00		20,000.00		20,000.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.5 Conclusions on the implementation of the Convention and the Kunming-Montreal Global Biodiversity Framework are completed.		2.1.5 Conclusions on the implementation of the Convention and the Kunming-Montreal Global Biodiversity Framework are completed.						009562		SOM-Min. Environ. & Climate Ch		Total				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.5 Conclusions on the implementation of the Convention and the Kunming-Montreal Global Biodiversity Framework are completed.		2.1.5 Conclusions on the implementation of the Convention and the Kunming-Montreal Global Biodiversity Framework are completed.						009562		SOM-Min. Environ. & Climate Ch		71800		Contractual Services-Imp Partn		0.00		0.00				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.5 Conclusions on the implementation of the Convention and the Kunming-Montreal Global Biodiversity Framework are completed.		2.1.5 Conclusions on the implementation of the Convention and the Kunming-Montreal Global Biodiversity Framework are completed.		Activity 2.1.5		Conclusions on the implementation of the Convention		001981		UNDP		Total				20,000.00		0.00		0.00		20,000.00		0.00		0.00		0.00		0.00		0.00		0.00		3,000.00		0.00		3,000.00		11,000.00		14,000.00		-3,000.00		1,000.00		1,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		5,000.00		5,000.00		20,000.00		20,000.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.5 Conclusions on the implementation of the Convention and the Kunming-Montreal Global Biodiversity Framework are completed.		2.1.5 Conclusions on the implementation of the Convention and the Kunming-Montreal Global Biodiversity Framework are completed.		Activity 2.1.5		Conclusions on the implementation of the Convention		001981		UNDP		71300		Local Consultants		17,000.00		0.00				17,000.00		0.00		0.00		0.00		0.00		0.00		0.00		1,000.00		0.00		1,000.00		10,000.00		11,000.00		-1,000.00		1,000.00		1,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		5,000.00		5,000.00		17,000.00		17,000.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.5 Conclusions on the implementation of the Convention and the Kunming-Montreal Global Biodiversity Framework are completed.		2.1.5 Conclusions on the implementation of the Convention and the Kunming-Montreal Global Biodiversity Framework are completed.		Activity 2.1.5		Conclusions on the implementation of the Convention		001981		UNDP		71400		Contractual Services - Individ		2,000.00		0.00				2,000.00		0.00		0.00		0.00		0.00		0.00		0.00		1,000.00		0.00		1,000.00		1,000.00		2,000.00		-1,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		2,000.00		2,000.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.5 Conclusions on the implementation of the Convention and the Kunming-Montreal Global Biodiversity Framework are completed.		2.1.5 Conclusions on the implementation of the Convention and the Kunming-Montreal Global Biodiversity Framework are completed.		Activity 2.1.5		Conclusions on the implementation of the Convention		001981		UNDP		71600		Travel		1,000.00		0.00				1,000.00		0.00		0.00		0.00		0.00		0.00		0.00		1,000.00		0.00		1,000.00		0.00		1,000.00		-1,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		1,000.00		1,000.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.5 Conclusions on the implementation of the Convention and the Kunming-Montreal Global Biodiversity Framework are completed.		2.1.5 Conclusions on the implementation of the Convention and the Kunming-Montreal Global Biodiversity Framework are completed.		Activity 2.1.5 MOECC		Conclusions on the implementation of the Convention		009562		SOM-Min. Environ. & Climate Ch		Total				0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		5,000.00		0.00		5,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-5,000.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		2. Complete 7th National Reports on Biodiversity		N/A 2.1.5 Conclusions on the implementation of the Convention and the Kunming-Montreal Global Biodiversity Framework are completed.		2.1.5 Conclusions on the implementation of the Convention and the Kunming-Montreal Global Biodiversity Framework are completed.		Activity 2.1.5 MOECC		Conclusions on the implementation of the Convention		009562		SOM-Min. Environ. & Climate Ch		71800		Contractual Services-Imp Partn				0.00				0.00		0.00		0.00		0.00		0.00		0.00		0.00		5,000.00		0.00		5,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-5,000.00		0.00		0.00

		1259824		01003136		GEF		62000		10003		PMC		Total																20,000.00		0.00		0.00		20,000.00		10,000.00		10,000.00		0.00		10,000.00		0.00		10,000.00		10,000.00		10,000.00		0.00		5,000.00		5,000.00		0.00		5,000.00		5,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		10,000.00		10,000.00

		1259824		01003136		GEF		62000		10003		PMC		N/A PMC		PMC		Total												20,000.00		0.00		0.00		20,000.00		10,000.00		10,000.00		0.00		10,000.00		0.00		10,000.00		10,000.00		10,000.00		0.00		5,000.00		5,000.00		0.00		5,000.00		5,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		10,000.00		10,000.00

		1259824		01003136		GEF		62000		10003		PMC		N/A PMC		PMC		PMC		PMC		001981		UNDP		Total				20,000.00		0.00		0.00		20,000.00		10,000.00		10,000.00		0.00		10,000.00		0.00		10,000.00		10,000.00		10,000.00		0.00		5,000.00		5,000.00		0.00		5,000.00		5,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		10,000.00		10,000.00

		1259824		01003136		GEF		62000		10003		PMC		N/A PMC		PMC		PMC		PMC		001981		UNDP		74596		Services to Projects - GOEs		20,000.00		0.00				20,000.00		10,000.00		0.00		0.00		10,000.00		0.00		10,000.00		0.00		10,000.00		-10,000.00		0.00		5,000.00		-5,000.00		0.00		5,000.00		-5,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		20,000.00		10,000.00		10,000.00

		1259824		01003136		GEF		62000		10003		PMC		N/A PMC		PMC		PMC		PMC		001981		UNDP		74500		Miscellaneous Expenses				0.00				0.00		0.00		10,000.00		0.00		0.00		0.00		0.00		10,000.00		0.00		10,000.00		5,000.00		0.00		5,000.00		5,000.00		0.00		5,000.00		0.00		0.00		0.00		0.00		0.00		0.00		0.00		-20,000.00		0.00		0.00

		Project Total - including Undepreciated Fixed Assets (18000), Prepayments (16065), Inventory (14602) - excluding Advances (16005, 16006, 16007, 16105, 16106, 16107, 16108)																												463,547.00		0.00		0.00		463,547.00		257,588.63		257,551.13		0.00		257,588.63		0.00		257,588.63		330,000.00		257,588.63		72,411.37		95,000.00		101,318.79		-6,318.79		38,547.00		37,297.00		1,250.00		0.00		0.00		0.00		0.00		0.00		0.00		67,342.58		0.00		205,958.37		205,958.37

		Budget Cells matching with Quantum: 				800

		Budget Cells not matching with Quantum: 				80






