UNDP Somalia Annual/Quarterly Narrative Reporting Template

PROJECT INFORMATION

| Project Title: Umbrella Programme to support NBSAP and the 7th National Reports |  |
| --- | --- |
| Project ID: 01003136 |  |
| Duration: |  |
| CPD Outcome: Output 3.2: Improved measures in place for environmental governance, resilience to climatic shocks and the management of natural resources |  |
| Total Budget: $463,547 |  |
| Implementing Partner: MOECC |  |
| Responsible Parties: |  |
| Reporting Period: | From: 01/06/2025 to: 31/12/2025 |
| Date Submitted: |  |

| - Executive Summary (Highlights) HIGHLIGHTS - The revised National Biodiversity Strategy and Action Plan (NBSAP) was consolidated into a coherent draft aligned with the Kunming–Montreal Global Biodiversity Framework and ready for validation. - A comprehensive capacity and financing assessment identified key governance gaps and proposed actionable reforms to strengthen biodiversity institutions, data systems, and resource mobilization. - Somalia’s first national spatial prioritization framework was produced, identifying priority ecosystems, restoration areas, corridors, and candidate protected areas with supporting biodiversity and pressure maps. - The Seventh National Report to the Convention on Biological Diversity confirmed Somalia’s foundational biodiversity governance is largely in place, while emphasizing the urgent need for effective execution and resourcing. - The thematic review and stakeholder consultations generated actionable recommendations to update national targets and improve integration of biodiversity into development planning and governance. |  |
| --- | --- |
| - Progress Review per Project Output: - OUTCOME 1: - Activities undertaken during the reporting period (2025) - Developed and initiated implementation of a comprehensive stakeholder engagement plan to support an all-of-society approach to the NBSAP update, engaging government, civil society, academia, the private sector, and local communities. - Conducted a national gender analysis and prepared a draft gender action plan to support gender mainstreaming in consultations and in actions informing the NBSAP revision. - Identified and prioritized key gaps and inconsistencies in the existing NBSAP based on Early Action Support (EAS) results, to inform alignment of the updated NBSAP with the Kunming–Montreal Global Biodiversity Framework. - Undertook policy alignment reviews and drafted an NBSAP section addressing policy coherence and biodiversity mainstreaming across key sectors. - Carried out an environmental and social impact assessment to identify potential risks associated with implementation of the updated NBSAP, with findings documented in draft form. - Developed a first draft spatial prioritization for GBF Target 1 using national and global data, and prepared a draft spatialized action plan for area-based targets including Targets 2, 3, 8, 9, 11, and 12. - Drafted an action plan to eliminate or phase out harmful subsidies and incentives in line with GBF Target 18. - Assessed gaps in institutional capacity and available resources and drafted capacity development and resource mobilization strategies, building on EAS findings and biodiversity finance initiatives. - b. Achievements by sectors/outputs - During 2025, Outcome 1 recorded steady progress toward updating Somalia’s NBSAP in line with the Kunming–Montreal Global Biodiversity Framework. Stakeholder engagement structures were established and used to support inclusive consultations, and a national gender analysis with a draft gender action plan was completed to inform gender-responsive NBSAP actions. Key gaps in the existing NBSAP were identified, and draft sections on policy alignment, biodiversity mainstreaming, and environmental and social safeguards were prepared. Initial spatial priorities and draft spatialized action plans for GBF Target 1 and other area-based targets were developed, alongside a draft action plan to phase out harmful subsidies. Capacity and resource gaps were assessed, and draft strategies for capacity development and resource mobilization were prepared, strengthening the foundation for effective NBSAP implementation. - OUTCOME 2: - Activities undertaken during the reporting period - Prepared a draft overview of the process for developing Somalia’s Seventh National Report to the Convention on Biological Diversity, including initial data compilation and technical inputs. - Conducted a draft assessment of the status of the revised National Biodiversity Strategy and Action Plan (NBSAP) in light of the Kunming–Montreal Global Biodiversity Framework. - Developed a draft assessment of progress towards national biodiversity targets based on available national information and evidence. - Prepared a draft assessment of progress related to the goals and targets of the Kunming–Montreal Global Biodiversity Framework. - Drafted preliminary conclusions on Somalia’s implementation of the Convention on Biological Diversity and the Kunming–Montreal Global Biodiversity Framework, including initial identification of gaps and priority actions. - Achievements by sectors/outputs ## During 2025, Somalia advanced its Seventh National Report to the CBD, producing a more evidence-based assessment of biodiversity progress and readiness to implement the Kunming–Montreal GBF. The report confirms that foundational governance steps are largely in place, identifies gaps in capacity, data, monitoring, and financing, and highlights that the main challenge is translating existing policies and pilot initiatives into fully resourced and enforceable systems that deliver measurable biodiversity and livelihood outcomes. OUTCOME 1. Indicator; Baseline; Cumulative target; Progress for reporting period (disaggregated data to be used); Cumulative progress (disaggregated data to be used); Comments. 1.1.1: Number of stakeholders engaged and level of diversity in representation within the NBSAP process.; 1.1.1: No comprehensive stakeholder engagement plan exists; limited stakeholder involvement.; 1 engagement plan developed; ≥80% of identified stakeholder groups engaged; Draft stakeholder engagement plan developed and applied in consultations; participation included government, CSOs, academia, private sector, women’s groups, and FMS representatives; Engagement plan in draft; stakeholder participation expanded significantly from baseline, with improved diversity including women and sub-national actors. 1.1.2: Existence of a gender analysis report and a corresponding action plan. Indicator; 1.1.2: No national gender analysis or action plan in place.; 1 gender analysis and 1 gender action plan developed; National gender analysis drafted; draft gender action plan prepared; women’s participation documented qualitatively; Gender analysis drafted; draft action plan available but not yet finalized or adopted. 1.1.3: Number of identified gaps and prioritized action areas documented; 1.1.3: No detailed gap analysis available.; 1 comprehensive gap analysis and prioritized action list; Draft gap analysis prepared identifying priority alignment gaps with GBF; Gap analysis exists in draft form; priorities identified but pending validation. 1.1.4: Number of sectors integrating biodiversity considerations into their policy frameworks.; 1.1.4: Limited or no sectoral integration of biodiversity considerations.; At least 3 key sectors integrate biodiversity; Policy alignment review conducted; draft NBSAP sections prepared referencing multiple sectors; Sectoral integration initiated conceptually;. 1.1.5: Number of environmental and social impact assessments (ESIAs) conducted.; 1.1.5: No ESIAs for the updated NBSAP.; 1 ESIA conducted with mitigation measures; Draft ESIA completed identifying potential environmental and social risks; ESIA completed in draft form; mitigation measures outlined. 1.1.6: Number of spatial priorities identified and mapped; Spatialized action plans for area-based targets finalized and integrated.; 1.1.6: No spatial priorities or spatialized action plans integrated into the NBSAP.; 100% of spatial priorities mapped and action plans finalized; Draft spatial prioritization prepared using national and global datasets; area-based targets spatialized in draft; Initial spatial priorities and maps produced; action plans remain draft and unvalidated. 1.1.7: Action plan for phasing out harmful subsidies developed and adopted.; 1.1.7: No actionable plans or mechanisms in place.; Action plan developed and endorsed; Draft action plan prepared identifying key harmful subsidies; Draft plan produced;. 1.1.8: Capacity and resource gap assessment report finalized; Number of strategies or plans developed and approved.; 1.1.8: No comprehensive assessments or strategies available.; Assessment completed; strategies developed and approved; Capacity and resource gap assessment drafted; draft capacity development and resource mobilization strategies prepared; Assessment and strategies available in draft form;. OUTCOME 2. 2.1.1: Scope, parameters, and categories defined and validated.; 2.1.1: No established parameters or scope for assessments.; 2.1.1: Framework and parameters developed and validated.; Draft scope and assessment framework prepared for the 7th National Report; Parameters defined in draft; validation pending. 2.1.2: Percentage of alignment between updated NBSAP and Kunming-Montreal Framework.; 2.1.2: Current NBSAP does not reflect the Kunming-Montreal Framework.; 2.1.2: Full alignment and updated NBSAP approved.; Initial alignment analysis conducted between draft NBSAP and GBF goals and targets; Partial alignment assessed in draft; full alignment pending NBSAP finalization. 2.1.3: Number of progress assessment reports finalized and shared.; 2.1.3: No assessment available.; 2.1.3: Complete and share progress reports.; Draft progress assessment prepared using available national data; Draft assessment exists; dissemination pending. 2.1.4: Assessment of progress related to the goals and targets of the Kunming-Montreal Global Biodiversity Framework is completed.; 2.1.4: No assessment aligned with Kunming-Montreal Framework.; 2.1.4: Comprehensive assessment report finalized and disseminated.; Draft assessment completed covering GBF goals and targets; Assessment completed in draft form; not finalized. 2.1.5: Conclusions on the implementation of the Convention and the Kunming-Montreal Global Biodiversity Framework are completed.; 2.1.5: Conclusion on the Implementation of the Convention and the Kunming-Montreal Global Biodiversity Framework not reviewed.; 2.1.5: Implementation report finalized.; Draft conclusions prepared identifying readiness, gaps, and priorities; Conclusions documented in draft; final review pending. - Project monitoring reports Government and/or programme monitoring Reports with photographs and attendance lists.. Progress toward Outcome 1 shows a clear transition from a zero baseline to draft GBF-aligned planning outputs that strengthen the foundation for an updated NBSAP. A draft stakeholder engagement plan expanded participation and diversity compared to the baseline of limited involvement (Indicator 1.1.1), while a national gender analysis and draft action plan addressed a major gap and improved consideration of women’s roles and impacts (Indicator 1.1.2). Draft gap analysis, policy alignment, ESIA, spatial prioritization, harmful subsidy reform, and capacity and resource assessments demonstrate partial achievement of annual targets that were absent at baseline (Indicators 1.1.3–1.1.8). While most outputs remain in draft form and sectoral integration is still evolving, they collectively contribute to the outcome by improving coherence, safeguards, and evidence-based planning Progress under Outcome 2 reflects steady advancement toward improved national reporting under the CBD and the Kunming–Montreal Global Biodiversity Framework, starting from a baseline of no defined scope or assessments. Draft parameters and scope for national reporting have been developed (Indicator 2.1.1), alongside initial analysis of NBSAP alignment with the GBF, though full alignment and approval are pending (Indicator 2.1.2). Draft assessments of progress toward national targets and GBF goals and targets, as well as preliminary conclusions on CBD and GBF implementation, indicate partial achievement of annual targets (Indicators 2.1.3–2.1.5). These outputs strengthen the national evidence base and clarify gaps in capacity, data, financing, and gender-disaggregated information |
| - Challenges and Remedial Actions |  |
| Challenges | Remedial Actions |
| Delay in procurement and onboarding of the technical team at the ministry. | Revised workplan and amended the LOA to align timelines and deliverables |
| Limited availability of biodiversity data for assessment and reporting. | Hired an international consultant to develop a standardized methodology for primary data collection, and national researchers to collect data; produced a national biodiversity assessment report. |
| Delayed stakeholder workshops to ensure full representation from all states and sectors, causing delayed liquidation and pushing remaining workshops into 2026. | Remaining workshops carried forward to 2026. |
| - Recommendations: (Recommendations to improve future programming). Maximum one page - Ensure early agreement and timely signing of the Letter of Agreement (LoA) and any necessary amendments before work begins to prevent delays. - Strengthen risk management by integrating adaptive planning and a risk register to respond quickly to delays, security challenges, or shifts in political priorities. - Mainstream biodiversity early into national development plans, climate strategies, and sector policies to ensure long-term integration rather than stand-alone interventions. - Adopt flexible delivery modalities for workshops, using hybrid or decentralized models to ensure participation while minimizing logistical delays and costs. |  |
| - Lessons Learned: - Early procurement planning matters more than expected. Delays in recruiting the technical team showed that procurement timelines can shape the entire delivery schedule. - Ensure early agreement and timely signing of the Letter of Agreement (LoA) and any necessary amendments before work begins to prevent procurement delays and enable faster onboarding of consultants. - Strengthen risk management by integrating adaptive planning and a risk register to respond quickly to delays, security challenges, or shifts in political priorities. - Reinforce monitoring, evaluation, and learning through regular progress reviews and learning loops that allow implementation to be adjusted based on evidence. |  |
| - List of in complete activities to be carried over to the next period - Workshops for the assessment of gaps in capacities and resources available undertaken, and on that basis, develop plans or strategies for capacity development and resource mobilization. - Workshops for development of a first approximation of spatial priorities for Target 1.9 and develop a spatialized action plan for other area-based targets. - Workshops for the identification of an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP. - Workshops for the assessment of gaps in capacities and resources available undertaken, and on that basis, develop plans or strategies for capacity development and resource mobilization. |  |
| - Annexe1: List of trainings: Course/Training name; Date; M; F; Total; Facilitated by. Stakeholder engagement session to ensure whole government and whole of society approach.; 1-2/09/2025; 53; 19; 72. Workshop to identify and prioritize key gaps and inconsistencies between the existing NBSAP and the updates needed to align with the Global Biodiversity Framework; 5-6/10/2025; 42; 30; 72. Workshop for developing National Gender Analysis and Action Plans; 7-8/10/2025; 40; 28; 68. Consultations to address policy alignment and coherence and biodiversity mainstreaming into key sectors within the NBSAP; 3-4/09/2025; 55; 18; 73. Workshop for the assessment of the potential environmental and social impacts and potential risks of the implementation of the updated NBSAP.; 23/10/2025; 51; 23; 74. Workshop for the identification of an action plan for eliminating or phasing out harmful subsidies and incentives within the NBSAP.; 15-16/11/2025; 39; 26; 65. Workshop for the assessment of gaps in capacities and resources available undertaken, and on that basis, develop plans or strategies for capacity development and resource mobilization; 26/11/2025; 37; 23; 60. |
| - Annex 2: Expenditure Report - Annex 3: Photos and social media coverage - Update Project risks in Quantum - List of evidence and links |  |

Annex 2: Expenditure Report

Annex 3: Photos and Social Media Links:

- https://www.facebook.com/share/p/1C7FeNfK33/?mibextid=wwXIfr

- https://www.facebook.com/share/p/1DZRPLFe8Q/?mibextid=wwXIfr

- https://www.facebook.com/share/v/1GC4poWHhz/?mibextid=wwXIfr

- https://www.facebook.com/share/p/17YJNJFZXD/?mibextid=wwXIfr

- https://www.facebook.com/share/p/1FbnijxxUL/?mibextid=wwXIfr

- https://www.facebook.com/share/p/1APhfeK8pv/?mibextid=wwXIfr

- https://www.facebook.com/share/p/17zPLZiby3/?mibextid=wwXIfr