Project: Strengthening Disaster Response through the Establishment of Evacuation Shelters

Project Number: 1003142

Implementing Partner: UNDP Lao PDR

Start Date: 19 November 2024	End Date: 19 November 2027		PAC Meeting date: 26 May 2025

Brief Description

The project's objective is to safeguard the lives of vulnerable communities impacted by seasonal flooding by ensuring access to safe evacuation centers and updating the National Evacuation Center guidelines based on practical feedback. The Lao People's Democratic Republic (Lao PDR) is significantly susceptible to flooding due to its geographical characteristics, with approximately 39.7% of the population exposed to flood risks, rendering it the sixth most flood-prone country in terms of population exposure. Ongoing financial constraints have impeded the government's capacity to respond to disasters, resulting in the isolation of remote communities during flood events, with women, children, the elderly, and individuals with disabilities being disproportionately affected. Prior to the crisis in 2022, the government had made advancements in disaster risk governance, which included the enactment of disaster management legislation and the adoption of the National Strategy on Disaster Risk Reduction for 2021-2030. Nonetheless, challenges such as inadequate funding, limited inter-agency coordination, and accessibility issues for non-governmental organizations continue to obstruct the effective implementation of policies. The project aims to enhance human security in flood-prone communities in the provinces of Khammouane, Saravane, and Champasack through inclusive designs that prioritize safety and privacy. Insights gained from this project will contribute to developing national guidelines, thereby improving their relevance and practicality. The Ministry of Labour and Social Welfare will collaborate with other ministries to ensure the effectiveness of the project implementation. In order to achieve the said outcomes, the project focuses on two main outputs: 1. Analysing risk knowledge and community needs to develop detailed implementation plans, & 2. Enhancing human security by establishing and sustainably operating 12 inclusive evacuation centers.

| Contributing Outcome (UNSDCF, CPD, RPD ): (UNSDCF) 2022-2026 – Strategic Priority 4 (Environment, Climate Change, And Resilience), CPD 2022-2026 –Outcome 2 - (Accelerate structural transformations for sustainable development). Indicative Output(s) with gender marker: Output 1 Risk knowledge and community needs are analyzed and detailed plans are developed to effective implementation of the project. (GEN2) Output 2 Human Security in target communities is enhanced through the establishment and sustainable operation of 12 evacuation centers with inclusive planning and design. (GEN) |  | Total resources required: | 3,898,325.10 |  |
| --- | --- | --- | --- | --- |
|  |  | Total resources allocated: | $3,898,325.10 |  |
|  |  |  | UNDP TRAC: | - |
|  |  |  | Donor: | 3,898,325.10 |
|  |  |  | Government: | - |
|  |  |  | In-Kind: | - |
|  |  | Unfunded: |  |  |

Agreed by (signatures):

| Department of Social Welfare, Ministry of Labour and Social Welfare | United Nations Development Programme (UNDP) |
| --- | --- |
| Print Name: | Print Name: |
| Date: | Date: |

# Development Challenge

Lao People’s Democratic Republic (Lao PDR) is a landlocked country in Southeast Asia with a population of about 7 million. It borders Thailand, Vietnam, Cambodia, Myanmar, and China, and its total land area is approximately 236,800 KM2. The Mekong River is a defining landscape feature, as 60% of its length runs through Lao PDR. The western border largely follows along the Mekong River, which is also the center for agricultural products due to the fertility of the river valleys.

Lao PDR has a vast network of rivers and channels, with significant water discharges from the Mekong River and its tributaries, which are heavily laden with sediments. It also has a substantial portion of mountainous and forested areas, contributing to an increased risk of flash floods. The country also has a high degree of seasonal weather variability each year, including southwest monsoon. With its geographical location, land characteristics and monsoon climate, Lao PDR is highly vulnerable to natural hazards, particularly floods.

About 39.7% of the population (2.99 people) are exposed to flood risks, making Lao PDR the 6th most flood-prone country by population exposure out of 188 countries). Flooding and landslides, in addition, incur a high risk of new exposure to ordnance (UXO) despite being already vulnerable to the contamination of UXO, with 25% of all villages in Lao PDR.

The Three  provinces in central and southern– Khammoune, Champasak, and Saravanne, have a combined population of 1,483,017 (Khammouane: 392,052, Saravane: 396,942, Champasack: 694,023) according to the latest Census conducted in 2015), experience flood damage yearly from the Mekong River and its tributaries, such as the Xe Ban Fai and Xe Don Rivers. In 2022 and 2023, over 40 billion KIP was lost from the damages caused by flooding in the three provinces.

| Province | Year | Villages affected | Household affected | Population affected | Economic loss (LAK) |
| --- | --- | --- | --- | --- | --- |
| Khammouane | 2022 | 5 | N/A | N/A | 13,179,529,608 |
|  | 2023 | 87 | 9,496 | 54,205 | 434,279,091,866 |
| Saravane | 2022 | 241 | 11,508 | 82,685 | 226,952,370,734 |
|  | 2023 | N/A | N/A | N/A | N/A |
| Champasack | 2022 | 54 | 220 | 1,023 | 2,560,621,344 |
|  | 2023 | 25 | 1,024 | N/A | 41,673,000,000 |

Source: MOLSW

The impact of floods goes beyond economic impact; there are significant impacts on the lives and livelihoods of the people. It is notable that people at risk of the effects of disaster, including flooding, are women, children, the elderly, and those with disabilities. Due to the traditional practices and system, women are also often disproportionately affected among the poor demographics, which reduces opportunities available for women to support themselves financially, especially during the post-disaster period.

Due to the ongoing financial crisis since 2022, the Government of Lao PDR's capacity to provide disaster response and recovery support has significantly decreased due to solvency and liquidity challenges. At the end of 2022, public debt was estimated at over 110% of GDP.  This resulted in the Government’s constrained ability to invest in preventative infrastructure and respond to disasters. The depreciation of Lao KIP and domestic inflation have reduced real incomes, weakening the coping capacity of the most vulnerable households. Some remote communities are regularly isolated and left on their own to sustain their lives for weeks in displacement as their access roads and bridges become flooded. Women, children, the elderly, people with disabilities, and other vulnerable groups are most exposed to these risks.

It is also important to note that despite the interlink between vulnerability to disaster risks and poverty, it is not absolute. While people in poverty suffer from disasters, their vulnerability is impacted by many other factors, in addition to poverty, which includes gender, class, ethnicity, community structure, and decision-making. Therefore, it is essential to also take these dimensions into consideration while developing a methodology to reduce people's disaster risk vulnerability.

The Government of Lao PDR has made significant progress in disaster risk governance, including i). the enactment of the law on Disaster Management, ii). the adoption of the National Strategy on Disaster Risk Reduction 2021-2030, iii). The relaunch of the disaster damage database, LaoDi, and iv). the development of the Early Warnings for All (EW4ALL) Roadmap 2024-2027 to reduce disaster risks through disaster management and resilience-building efforts.

The Ministry of Labour and Social Welfare of Lao PDR (MOLSW) drafted the National Guidelines for the Selection and Assessment of Evacuation Centers in Lao PDR with support from UNICEF and inputs from other development partners, including UNDP.

To overcome the challenges, this project intends to mobilize finance and partnerships for furthering the feasibility study and assessment of the needs in order to establish safe evacuation sites for the selected vulnerable communities. In addition, the project will gather lessons learned and the best practies through the construction, rehabilitation, reinforcement, and operation of evacuation centers to provide feedback into the National Guideline to improve its relevance and practical use.

# Strategy

The Project for Strengthening Disaster Response Capacity through the Improvement of Evacuation Shelters, also known as the Evacuation Center Project, aligns with the Lao PDR United Nations Sustainable Development Cooperation Framework (UNSDCF) 2022-2026 – specifically Strategic Priority 42 (Environment, Climate Change, And Resilience), and the UNDP Lao PDR Country Programme Document 2022-2026 – particularly outcome 2 (Accelerate structural transformations for sustainable development). The main goal of this project is to enhance human security in vulnerable communities in the central and southern part of Lao PDR, specifically in Khammouane, Saravane, and Champasack Province, by increasing resilience to natural hazards-induced disasters and climate change. This will be achieved by establishing inclusive design evacuation centers to address the regular flooding damage in these areas.

The Evacuation Center project is the continuity of the two past projects – the Urban Risk Management and Resilience – Integrated Resilience Building for Lao PDR’s Sustainable Growth (Urban Risks) (2020-2021) and the Enhance Integrated Water Management and Climate Resilience in Vulnerable Urban Areas of the Mekong River Basin (ROK Mekong) (2021-2025), which objective is to strengthen resilience capacity the climate and disaster resilience of people and communities in vulnerable regions of Lao PDR. Through the two projects, UNDP has learned from past experiences in supporting the Government of Lao PDR in constructing evacuation centers in Saravane province and in providing equipment to meet standards in Champasack province.

In addition, during the implementation of the ROK Mekong project, a site assessment report was carried out to select potential locations for building evacuation centers in six target communities in Khammouane (Namphou, Hadsayfong, Xiengvean) and Champasack (Xong, Phothak, Solonoy) provinces, Lao PDR. The report provided recommendations for site selection in each village and appropriate risk mitigation plans. The selected location is prioritized during the implementation of the evacuation center project for effective use of resources and timely implementation.

Site Assessment Report by ROK Mekong Project:

The ROK Mekong project conducted a community-based problem analysis and mapping exercise in 2023, focusing on six communities in Khammouane (Namphou, Hadsayfong, Xiengvean) and Champasack (Xong, Phothak, Solonoy) provinces to assess their resilience to natural hazards. The survey revealed that the communities require evacuation centers as a response measure during disaster events. Although some of the target areas have temporary facilities such as schools or public buildings that can be used as evacuation centers, most of these facilities are in poor condition.

The approaches for the site assessment follow two steps – data preparation and assessment matrix. The assessment was conducted based on the result of the data collection and survey form that captured the information required for site selection and drawing a preparable decision that meets the technical criteria, namely - i) type of disaster, ii) location and elevation, iii) accessibility, iv) site condition, v) environmental and safety factors, vi) population and household size, and vii) available facilities (water, toilets, health services). The assessment matrix evaluates each site based on various criteria, such as location, safety, accessibility, site slope, other conditions, and information for building design based on international guidelines and engineering considerations.

The assessment identified Solonoy village in Champasack province as the most preferred site, meeting all the six criteria, with the most advantages and the least drawback among other sites. While the rest of the village did not meet all the requirements and were less suitable for the EC construction, the sites could be improved to reduce the risks.

Strategic Approaches:

      - Promote equitable implementation and contribute to the sustainable development goals (SDGs). The project will prioritize vulnerable and marginalized communities, ensuring equitable access to disaster preparedness resources while promoting social justice. The project aligns with key Sustainable Development Goals (SDGs) by reducing poverty, improving health, addressing inequalities, and enhancing climate resilience. Through sustainable construction practices and capacity building, the project will ensure long-term resilience, creating safer, more inclusive, and sustainable communities in Lao PDR.

- The project will integrate gender-sensitive and inclusive approaches by actively involving the local community, including women, ethnic minorities, and people with disasters, in risk assessments, planning, and decision-making processes of the Evacuation Center construction design. The project ensures design with safe features, including safe evacuation routes accessible to those with limited mobility, clearly separated facilities to prevent sexual violence, and accessible toilets and showers for people with disabilities, the elderly and young children.

- The project will promote sustainable and cost-effective use of evacuation centers by retrofitting existing community infrastructure, such as schools or temples, located in safe, accessible areas. The project also encourages community ownership and ensures long-term maintenance. These centers will be utilized for non-emergency purposes, including community events, small businesses, and extra classrooms. The project will also engage community members in light manual work through a cash-for-work program, with special provisions to include women-headed households, caregivers, and people with disabilities who may be unable to participate in manual labor. The cash transfer mechanism will be carefully designed to ensure accountability and direct benefits to all participants, fostering a sense of ownership and shared responsibility within the community.

Alignment to National Strategies

- Lao’s Vision 2030 and 10 years Socio-Economic Development Strategy 2016-2025 focus on building a resilient nation by significantly increasing disaster risk management capabilities, reducing disasters' impact, and improving recovery efforts' speed and effectiveness. The vision emphasizes the integration of disaster risk reduction into national development planning, aiming to protect lives, livelihoods, and infrastructure while promoting sustainable development. The Evacuation Center project aligns with the strategy’s commitments to integrating disaster risk reduction into national development planning. The project supports disaster preparedness and resilience for vulnerable communities. It also promotes community ownership and multifunctional use of the center to ensure sustainability and equitable participation. This helps mitigate the impacts of disasters and supports long-term national growth and stability, reinforcing the country's resilience in line with Vision 2030.

- The project aligns with the Government of Lao PDR's 9th National Socio-Economic Development Policy (9NSEDP) by prioritizing sustainable development that balances economic and socio-cultural progress with environmental protection, and preparedness for natural disasters. Specifically, Outcome 4 focuses on enhanced environmental protection and reduced disaster risks through Output 3, which aims to strengthen disaster prevention, management, and recovery capacities. The project demonstrates the policy's commitment by supporting the enhancement of disaster prevention, control, and recovery capacities for both natural and man-made disasters.

- The project aligns with the Lao PDR Disaster Risk Management Law, particularly with Articles 21 and 22, by focusing on disaster control and ensuring safety during disasters. The project’s establishment of safe evacuation centers contributes to limiting the severe effects of disasters on health, lives, and assets, which is a key component of disaster control.

- The National Strategy on Disaster Risk Reduction (NSDRR) 2021-2030 aims to prevent and reduce disaster risks, prepare and coordinate for emergency response, and restore economic, social, and environmental infrastructure after a disaster, which includes the need to strengthen community resilience and capacity to respond to disasters. In particular, the severe impacts of disasters in vulnerable communities, especially in remote rural areas, highlight how important it is to improve community reliance through the Government’s ongoing efforts in poverty reduction and sustainable development, as well as community-based disaster risk reduction (CBDRR).

- The Lao PDR Resilience Framework 2022-2025, especially Pillar 5—Green Growth, Resilience to Climate Change, and Disaster Risk Management, addresses opportunities to strengthen green growth, build resilience, and manage risks to bring the Lao PDR closer to its development goals, including prioritizing increasing community-disaster-level capacity building in disaster management.

# Results and Partnerships

Expected Results

The project aims to contribute to the update of the National Guidelines for the Selection and Assessment of the Evacuation Centers in Lao PDR, which was drafted by the Ministry of Labor and Social Welfare (MOLSW) with the support of UNICEF. The guidelines aim at establishing standards for safe and inclusive design for evacuation centers, e.g. inclusive design toilets for people with disabilities, pregnant women, elderlies and young children. As the draft guidelines have yet to be piloted, the project's result will significantly contribute to updating the national guideline through feedback and best practices, including practical uses considering different needs based on areas and characteristics. This will help refine the guidelines to ensure they are more practical and adaptable to the diverse needs of different areas and communities in Lao PDR. Two indicators expected at the project-level outcomes are i). The number of people benefitting from the project through updating the National Guidelines, and ii). The number of people benefit from considering their provinces' hydrometeorological and geomorphological characteristics in the National Guidelines.

The project comprises a set of measures that span across two key outputs with corresponding country-level outputs, as follows:

- Develop a detailed plan for the project's effective implementation by conducting risk knowledge and community need analysis.

- Enhance human security in the target communities by establishing and sustainable operating the twelve evacuation centers through inclusive planning and design.

Output 1 Risk knowledge and community needs are analyzed, and detailed plans are developed for effective implementation of the project.

  - Conduct needs assessments and feasibility study:

    - Identify 12 locations for establishing new evacuation centers or retrofitting existing evacuation centers to test the implementation of the national guidelines. The locations will be selected to collect feedback from a variety of sample communities, including urban/rural, size of the building, renovation/new construction, geological characteristics, etc. To ensure timely implementation and effective use of resources, the priority will be given to the villages surveyed/supported in previous UNDP projects listed below:

| Province | District | Village | Previous support and current status |
| --- | --- | --- | --- |
| Khammouane | Nongbok | Namphou | Surveyed and equipment provided |
|  |  | Hadsayfong | Surveyed and equipment provided |
|  | Thakek | Xiengvean | Surveyed and equipment provided |
|  |  | Donedone | Surveyed and equipment provided |
| Saravane | Kongsed-one | Tuangse, Hadsaykham | Pilot EC constructed by UNDP/MOLSW in 2022 and used by 2 villages. Requires additional facilities to meet the standards. |
| Champasack | Pakse | Xong | Surveyed and equipment provided |
|  |  | Phothak | Surveyed and equipment provided |
|  | Xanasom-boune | Solonoy | Surveyed and equipment provided |
|  |  | Khili | EC constructed by the Government in 2023 and equipment provided by UNDP/MONRE. Requires additional facilities to meet the standards. |

- Conduct detailed needs assessment, including the number of potential evacuees, cultural practices, demographic characteristics, and capacity for maintenance and operation. A special consideration must be taken for the needs of women, children, elderly, ethnic minorities, and people with disabilities, using GESI (Gender Equality and Social Inclusion) methodologies.

- Conduct detailed feasibility study, including a site assessment survey and detailed designs in accordance with relevant national and international guidelines and standards. In case there is a safe building in publicly owned land, it is recommended to retrofit existing buildings to enhance safety, accessibility, and functionality to meet the standard. However, the safety of the location, including flood risks must be thoroughly and objectively assessed during the site assessment survey.

- Develop an operation and maintenance plan for each village through a participatory planning process.

  - Assess and plan for managing risks and ensure quality.

- Conduct risk assessments, including targeted assessments based on Social and Environmental Standards (SES). Develop risk management plans based on inclusive community consultations. Inform stakeholders on potential risks, risk management plans, and grievance mechanisms.

- Examples for the recommended design for safe, inclusive, and sustainable design:

  - Establishment of safe evacuation routes from the potential evacuee's residences, accessible for people with limited mobility.

  - Clearly separated entrances for men’s and women’s toilets to prevent sexual violence.

  - An accessible toilet and shower room for people with disability, pregnant women, elderlies, and young children.

  - Plans for the communities to use the evacuation center budlings in non-emergency times to ensure sustainable and cost-effective operation and maintenance, for example:

    - Retrofitting existing community infrastructures that are in the safe and accessible location, such as a school, temple, community market, or village office.

    - Collecting fees for the use of the buildings, such as conducting wedding or other ceremonies or running small businesses.

Output 2 Human Security in target communities is enhanced through the establishment and sustainable operation of 12 evacuation centers with inclusive planning and design.

2.1) Retrofit existing building or newly construct evacuation centers

- Commission construction works through fair and open bidding process following UNDP rules and procedures.

- Monitor the progress and risks during the construction process through site visits by field support staff and quality assurance by an engineering expert.

- Procure and install equipment for sustainable operation of the evacuation centers, including solar panels, water tanks, and fire extinguishing system.

2.2) Enhance community ownership and knowledge sharing

- Engage community members in light manual work through a cash-for-work program. Specific consideration must be taken to ensure women-headed households, women with family care duties, or people with disabilities who may not be able to participate in the manual labor are not excluded from the beneficiaries of this activity. The cash transfer mechanism needs to be carefully designed to ensure accountability and direct benefit to the community members.

- Plan and conduct evacuation drills in the communities to enhance preparedness and awareness. Amplify the impact on awareness-raising and visibility to the national and international level through a campaign on International Day on Disaster Risk Reduction (13 October). Possible collaboration with UNICEF will be explored where the drills are conducted at schools.

- Compile and analyze knowledge, lessons, and best practices as knowledge management materials and provide feedback to improve the national guideline.

- Share the knowledge in the country and globally to replicate the model for establishing and operating inclusive and sustainable evacuation centers.

2.3) Strengthening policies, regulation, and institutional Lao PDR on the Disaster Risk Reduction

- Review and update the National Guidelines for the Selection and Assessment of Evacuation Centers and other relevant policies; improve institutional capacity through learning

Resources Required to Achieve the Expected Results

To achieve the desired outcome, the estimated resources required are USD3,898,325.10 The detailed budget is included in the annexe section at the end of the document. Below is a summary of the budget:

| Output 1 Risk knowledge and community needs are analyzed and detailed plans are developed to effective implementation of the project. | $ 382,750.21 |
| --- | --- |
| Output 2 Human Security in target communities is enhanced through the establishment and sustainable operation of 12 evacuation centers with inclusive planning and design. | $ 2,894,616.00 |
| Project Management Cost | $ 582,416.87 |
| Total Project Cost | $ 3,859,783.08 |
| UN Coordination mandatory Levy (1% of Total Project Cost + GMS) | $ 324,451.88 |
| Grand Total | $ 3,898,325.10 |

Partnerships

The project builds on UNDP’s existing partnership with the Ministry of Labour and Social Welfare (MOLSW) from the previous Urban Risk project, reinforcing collaboration at both national and subnational levels. Coordination and consultation with other relevant ministries, including the Ministry of Public Works (MPW), Ministry of Education and Sports (MES), and Ministry of Natural Resources and Environment (MONRE) are crucial. Active and effective collaboration is encouraged to ensure alignment with the goal, vision, and strategies of the Government of Lao PDR and the achievement of sustainable development goals (SDGs) through adaptation and preparedness.

UNDP has also secured pre-approval from the Tokyo Association of Architectural Firms (TAAF) to apply its “Hinanjo Model Plan”, which offers detailed, inclusive design guidelines for evacuation centers, emphasizing women’s safety and privacy. The project will also leverage Japan's experience and technological advancements by collaborating with Japanese private sectors listed on platforms like A-PLAT and JRPSI, overseen by the Ministry of the Environment of Japan. The project is committed to inclusivity, focusing on understanding the needs and risks faced by vulnerable groups, including women, children, the elderly, people with disabilities, and ethnic minorities, ensuring their interests are central to the project’s implementation.

UNDP will also coordinate with other development partners who have expertise in this field, such as the Japanese International Cooperation Agency (JICA), the United Nations Human Settlements Programme (UN-Habitat), the United Nations International Children’s Emergency Fund (UNICEF), and the United Nations for Disaster Risk Reduction (UNDRR), to enhance the national evacuation center guidelines with the collection of best practices and lesson learnt through the construction, rehabilitation, reinforcement, and operation of the evacuation centers.

Risks and Assumptions

The project has identified 15 potential risks, two of which are significant. The construction of the evacuation center comes with a range of potential risks that must be carefully managed to ensure successful project implementation. One significant concern is the risk of no qualified construction companies bidding on the project or contractors lacking the capacity to deliver the assigned tasks, which could delay the project or compromise the quality of the work. Even with qualified contractors, construction delays and cost overruns are still risky, which can be exacerbated by unforeseen challenges such as supply chain disruptions or weather conditions.

The risk treatment plan is designed to ensure the quality and timely completion of the project. This involves ensuring high-quality Bill of Quantity (BoQ), design drawings, and structural designs and promptly addressing any questions from contractors or bidders. UNDP will also assess the risks associated with potential contractors before entering into contracts with them. Performance assurance is guaranteed through performance bonds and retention money mechanisms. Contract payments will be made based on the verification and certification of the engineer, and any poor-quality work will not be accepted. An independent engineer recruited by UNDP will continuously monitor the construction site. The UNDP's Procurement Unit is responsible for implementing these measures.

In addition, as the target communities are prone to seasonal flooding and potential landslides, they pose a significant risk to the structural integrity of evacuation centers, potentially leading to structural or fractural failure. Poorly designed or inadequately constructed buildings may be unable to withstand the pressure exerted by shifting soil, water accumulation, or landslide debris. The risk is particularly heightened in regions with unstable terrain or where drainage systems cannot handle heavy rainfall.

To ensure the structural integrity of the building and to prevent potential harm caused by the collapse of the building, considering the targeted community are prone to natural disasters such as floods and landslides, the project will first conduct a site assessment and feasibility studies to identify suitable locations for the construction of the evacuation shelter. Qualified experts will then carry out an Environmental and Social Management Framework (ESMF) to evaluate the potential impacts on each site and recommend actions to minimize risks and mitigate any potential project impacts. Additionally, the project will develop both an Environmental and Social Management Plan (ESMP) and a Construction Environmental and Social Management Plan (CESMP) to effectively manage risks and minimize impacts during the project implementation and construction activities.

Other than the two addressed substantial risks, there are other risks including exposure to unsafe environments or sexual abuse for women and girls during the construction and use of the shelters. Environmental and social risks accompany construction activities, such as generating noise, pollution, physical hazards, and straining local resources, which can heighten social tensions within the community. Many other potential risks that require attention can be found in detail in the annexe below. Find below for the elaboration of the cause and treatment of each risk.

Stakeholder Engagement

Beneficiaries: The project's primary beneficiaries are the residents of the 12 selected villages in the three provinces—Champasack, Pakse, and Saravanne—which are prone to disasters like flooding. The marginalized groups within the community, including women, children, the elderly, people with disabilities, and ethnic minorities, are taken into consideration and prioritised. The project emphasises understanding the specific needs and risks these groups face through active community engagement and consultations. The project will utilize a Cash-for-Work (CfW) program for non-technical manual labor. This program aims to support the community's livelihood during the project's implementation (Output 2). The multifunctional nature of the center will enable maintenance and long-term sustainable use of the facilities after the project concludes.

Government: The project requires support and extensive collaboration with the Government of Lao PDR, mainly as discussed above, through close coordination and consultation with Ministry of Labour and Social Welfare (MOLSW), Ministry of Education and Sports (MES), Ministry of Public Work (MPW), Ministry of Planning and Investment (MPI), Ministry of Foreign Affairs (MOFA) and Ministry of Natural Resources and Environment (MONRE). Collaborative mechanisms need to work effectively to ensure timely delivery, alignment with the National commitment, goals, and visions, and the efficient use of resources.

Private Sector: The project harnesses the expertise of the Japanese private sector, particularly the Tokyo Association of Architectural Firms (TAAF), in partnership with domestic companies that have a good understanding of socio-economic conditions in Lao PDR. The private sector’s role is crucial in bringing innovation and ensuring that the project adopts cutting-edge practices, making the evacuation center efficient and effective in both disaster scenarios and non-emergency/post-disaster scenarios.

Development Partners: The project collaborates with key development partners with relevant field expertise. JICA, for instance, have implemented many large-scale evacuation centers in the region, including JICA’s Project for Construction of Multipurpose Cyclone Shelters in Bangladesh and Project for Evacuation Shelter Construction in Disaster Vulnerable Areas in the Province of Albay in the Philippines. The partnership with UNICEF, UN-Habitat, and UNDRR is essential for refining the drafted National Guidelines for the Selection and Assessment of Evacuation Center in Lao PDR through knowledge facilitation and lessons learned from the previous implementation of the projects both within and outside Lao PDR.

Knowledge

The project's expected outcome includes contributing to the drafted National Guidelines for the Selection and Assessment of Evacuation Centers in Lao PDR. The project is implemented by the MOLSW, with support from UNICEF and inputs from other development partners, including UNDP. The guidelines aim to establish standards for safe and inclusive design for evacuation centers. For example, inclusive design toilets for people with disabilities, pregnant women, elderly, and children. The project intends to gather lessons learned from its implementation to support the drafted guidelines by providing feedback and practical improvements for different needs based on area characteristics.

The project aims to not only contribute to the National Guidelines but also to improve beneficiaries' understanding of natural hazards, resilience, and preparedness in the face of emergency situations resulting from disasters. It intends to achieve this goal through targeted educational initiatives and drill training. These efforts are designed to provide community members with essential insights into effectively responding to emergencies, minimizing risks, and establishing resilience against disasters. The objective is to equip individuals with practical skills and knowledge, empowering them to make informed decisions during crises and implement preventive measures. Ultimately, the project seeks to increase awareness and preparedness, helping communities protect themselves and support each other. By fostering a culture of collective resilience and preparedness, the project aims to strengthen overall disaster response capabilities.

The project will also identify, analyse and share lessons learnt from its implementation that might benefit future design projects’ designs and implementations. Other than progress report, the project will highlight its progress and achievements through visibility products such as feature story, impact story and other publications through existing information-sharing networks and forums.

Sustainability and Scaling Up

The development of a sense of ownership within the community will be crucial for the long-term success of the project. To achieve this, we plan to involve community leaders and villagers in the planning and decision-making processes. We believe that this approach will foster a stronger sense of responsibility and commitment to maintaining the outcomes of the project.

The design of the evacuation shelters will be carefully tailored to ensure practical use during non-emergency periods, based on a thorough assessment of the community's needs. By understanding the specific requirements of the village, the shelters will be constructed to serve multiple purposes, such as functioning as markets, schools, places of worship, community gathering spaces for religious ceremonies, and event-hosting halls. This multipurpose approach ensures that the facility remains an active and valuable asset to the community, promoting its long-term sustainability and ongoing maintenance while meeting a range of social and cultural needs beyond its primary function as a disaster shelter.

By integrating the evacuation center into regular community activities, the village ensures that the facility remains well-maintained, functional, and sustainable beyond the project's initial investment. To further ensure cost-effectiveness, as part of the village selection criteria, each village will be required to develop a maintenance and operation plan for the evacuation center, taking into account the emergency and non-emergency periods. This will ensure that the project is implemented in areas with a clear commitment to the center's long-term upkeep and sustainability.

The project will embed its activities within Lao PDR’s existing national frameworks to ensure alignment with broader government priorities and long-term sustainability. By collaborating closely with government ministries like the Ministry of Labour and Social Welfare and other relevant ministries at the national and subnational levels, the project will facilitate the integration of lessons learned and best practices for the construction of evacuation center into the drafted National Guidelines for the Selection and Assessment of Evacuation Center, contributing to the future evacuation center construction plan.

Scaling up will be facilitated by documenting and disseminating best practices and lessons learned throughout the project. These insights will be shared within Lao PDR and with other regions, through platforms like UNDP and partnerships with organizations including the UN agency. By doing so, the project will ensure its sustainability and pave the way for the replication and expansion of successful strategies across the country, further enhancing Lao PDR’s resilience to disasters on a larger scale.

# Project Management

Cost Efficiency and Effectiveness

Cost efficiency and effectiveness in project management will be achieved through adherence to the UNDP Programme and Operations Policies and Procedures (POPP) and reviewed regularly through the governance mechanism. In addition, there are specific measures for ensuring cost-efficient use of resources through using a portfolio management approach. This project will leverage existing related activities as well as partnerships to improve cost-effectiveness.

Project Management

The project will be implemented under Direct Implementation Modality (DIM), whereby UNDP will run operational procedures (procurement, finance, HR, admin/logistics, IT, etc.) in accordance with applicable UNDP rules, policies and procedures. The Project Management Unit (PMU) will be established and sit in the project office located in Vientiane, Lao PDR. The Ministry of Labour and Social Welfare (MOLSW) will provide the space for the project office within the same building with its Department of Social Welfare as an in-kind contribution to the project. As the project target sites are in the southern region of the country, PMU will monitor implementation of activities through field visits, communication with local authorities, and locally hired construction site supervisors.   The PMU will also have adequate and appropriate computer and telecommunications facilities, including the Internet, to enable them to efficiently and effectively undertake their activities, which will be covered by the project budget.

# Results Framework

Intended Outcome as stated in the UNDAF/Country Programme Results and Resource Framework (UNSDCF 2022-2026): Outcome 4: Environment, Climate Change, and Resilience

Outcome indicators as stated in the Country Programme Results and Resources Framework, including baseline and targets (CPD UNDP Lao PDR 2022-2026): By 2026, people, especially the most vulnerable and marginalized, and institutions will be better able to sustainably access, manage, preserve and benefit from natural resources and promote green growth that is risk informed and disaster and climate-resilient

Applicable Output(s) from the UNDP Strategic Plan (2022-2025): Outcome 2 – Accelerate structural transformations for sustainable development

Project title and Quantum Project Number: 1003142

| EXPECTED OUTPUTS | OUTPUT INDICATORS | DATA SOURCE | BASELINE |  | ## TARGETS (by frequency of data collection) |  |  |  | ## DATA COLLECTION METHODS & RISKS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Value | Year | 2025 | 2026 | 2027 | ## FINAL |  |
| Project-level Outcome | Number of people benefitting from the project through the update of the National Guidelines | Estimated # of vulnerable people affected by disasters (IACP) | 0 | 2024 | 0 | 0 | 150,000 | ## 150,000 | Data collection: Policy and Reports Review, Key Informant interview (national and provincial disaster focal agencies), and Analysis of population estimate Household surveys and Provincial Planning reports ## Risk: Government approval of the updated Guidelines may be delayed. |
|  | Number of people benefitting from consideration of hydrometeorologic and geomorphological characteristics of their provinces in the National Guidelines | Population of the target Provinces (2015 or 2025 Census) | 0 | 2024 | 0 | 0 | 50,000 | ## 50,000 |  |
| Output 1 Risk knowledge in the 3 target provinces and needs of 12 target communities, especially those most vulnerable to the floods, are mapped and analysed | 1.1 Number of needs assessments and feasibility studies conducted using GESI (Gender Equality and Social Inclusion) methodologies | Published survey results | 0 | 2024 | 8 | 5 | - | 12 | Data collection method: Review of Project report, Survey, focus group discussions, and key informant interview Risk: The survey results may not accurately reflect the needs of the most vulnerable groups. |
|  | 1.2 % of women included in community consultations for needs survey, risk management, and O&M planning activities | Gender-disaggregated participants list | 0 | 2024 | 40% | 50% | 60% | 50% | Data collection method: Review of attendance records, survey and field observations Risk: The effective participation of women may not be accurately reflected in the survey results. |
|  | 1.3 Number of workshop and consultation on the risk assessments and management plans | Published SES assessment reports and plans | 0 | 2024 | 2 | 0 | 0 | 2 | Data collection method: Review of SES reports, attendance records, and Project Progres Report Risk: Concerns of target beneficiaries on social and environmental issues may not be addressed without an inclusive consultation process and grievance mechanisms. |
| Output 2 Human Security in target communities is enhanced through the establishment and sustainable operation of 12 evacuation centers with inclusive planning and design | 2.1 Number of people directly benefitting from the evacuation centers established and fully operationalized | Project Annual Progress Report | 0 | 2024 | 4,000 | 4,000 | 6,000 | 9,600*1 | Data collection method: Analysis of project progress report, observation checklist assessment, and benefitciaries interview. Information is verified by project staff and local authorities during monitoring visits. Risk: Construction may be delayed during the rainy season. |
|  | 2.2 Number of people participated from the Cash-for-Work programme | Participants list and Project Annual Progress Report | 0 | 2024 | 0 | 1,000 | 800 | 1,800*2 | Data collection method: Records of Participants with attendance logs and review of project progress report Risk: Women-headed households and family with people with disabilities may be excluded as they could not participate in manual labour. |
|  | 2.3 % of people who passed the post-training tests on safe evacuation and sustainable operation of evacuation centers (passing threshold: 80% correct answers) | Training reports | 0 | 2024 | 80% | 80% | 80% | 80% | Data collection method: Pre & Post training assessment tests & review of project progress report Risk: Community knowledge and awareness may not be effectively enhanced if the training coverage is low |

*1: Average population of the village supported 800ppl x 12 target communities: 9,600

*2: (Total budget CfW/12 locations)/ No. Days = Number of People benefit from CfW

# Monitoring And Evaluation

Project-level monitoring and evaluation will be undertaken in compliance with UNDP requirements as outlined in the UNDP’s Programming Policies and Procedures (POPP). The following is the monitoring plan of the project:

Monitoring Plan

| Monitoring Activity | Purpose | Frequency | Expected Action |
| --- | --- | --- | --- |
| Inception Workshop | Present project overview, governance structure, roles and responsibilities, monitoring and reporting requirements, review work plan and budget and approve the work plan for the 1st year | Once, within 3 months after the signature of the project document | Inception Workshop Report prepared and shared with participants to formalize various agreements and plans decided during the meeting |
| Track results progress | Progress data against the results indicators in the RRF will be collected and analysed to assess the progress of the project in achieving the agreed outputs. | Quarterly | Slower-than-expected progress will be addressed by project management. |
| Monitor and Manage Risk | Identify specific risks that may threaten the achievement of intended results. Identify and monitor risk management actions using a risk log. This includes monitoring measures and plans that may have been required as per UNDP’s Social and Environmental Standards. Audits will be conducted in accordance with UNDP’s audit policy to manage financial risk. | Quarterly | Risks are identified by project management and actions are taken to manage risk. The risk log is actively maintained to keep track of identified risks and actions taken. |
| Learn | Knowledge, good practices and lessons will be captured regularly, as well as actively sourced from other projects and partners and integrated back into the project. | At least annually | Relevant lessons are captured by the project team and used to inform management decisions. |
| Annual Project Quality Assurance | The quality of the project will be assessed against UNDP’s quality standards to identify project strengths and weaknesses and to inform management decision making to improve the project. | Annually | Areas of strength and weakness will be reviewed by project management and used to inform decisions to improve project performance. |
| Review and Make Course Corrections | Internal review of data and evidence from all monitoring actions to inform decision making. | At least annually | Performance data, risks, lessons and quality will be discussed by the project board and used to make course corrections. |
| Project Report | A progress report will be presented to the Project Board and key stakeholders, consisting of progress data showing the results achieved against pre-defined annual targets at the output level, the annual project quality rating summary, an updated risk long with mitigation measures, and any evaluation or review reports prepared over the period. | Annually, and at the end of the project (final report) |  |
| Project Review (Project Board) | The project’s governance mechanism (i.e., project board) will hold regular project reviews to assess the performance of the project and review the Multi-Year Work Plan to ensure realistic budgeting over the life of the project. In the project’s final year, the Project Board shall hold an end-of project review to capture lessons learned and discuss opportunities for scaling up and to socialize project results and lessons learned with relevant audiences. | Annually | Any quality concerns or slower than expected progress should be discussed by the project board and management actions agreed to address the issues identified. |

Inception Workshop

The Inception Workshop will be held within the three months of the project's start with those with assigned roles in the project organization structure, UNDP, and other stakeholders. The Workshop is crucial to building ownership for the project results and to planning the first-year annual work plan.

The Inception Workshop addressed a number of key issues, including:

a) Assist all partners in fully understanding and taking ownership of the project. Detail the roles, support services, and complementary responsibilities of UNDP CO vis à vis the project team.

b) Discuss the roles, functions, and responsibilities within the project’s decision-making structures, including reporting and communication lines, as well as conflict resolution mechanisms.

c) Finalize the first annual work plan Based on the project results framework and, if appropriate, the relevant tracking tool. Review and agree on the indicators, targets, and their means of verification, and recheck assumptions and risks.

d) Provide a detailed overview of reporting, monitoring and evaluation (M&E) requirements. The Monitoring and Evaluation work plan and budget should be agreed and scheduled.

e) Discuss financial reporting procedures, obligations, and annual audit arrangements.

f) Plan and schedule Project Steering Committee meetings. The roles and responsibilities of all project organisation structures should be clarified, and meetings should be planned. The first Project Steering Committee meeting should be held within the first eight months following the inception workshop.

The minutes of the Inception Workshop will be produced as a key reference document. They must be prepared and shared with participants to formalize various agreements and plans decided during the meeting.

# Multi-Year Work Plan

All anticipated programmatic and operational costs to support the project, including development effectiveness and implementation support arrangements, need to be identified, estimated and fully costed in the project budget under the relevant output(s). This includes activities that directly support the project, such as communication, human resources, procurement, finance, audit, policy advisory, quality assurance, reporting, management, etc. All services which are directly related to the project need to be disclosed transparently in the project document.

| Expected Project Outputs | Planned Activitues Quantum Activity (GEF Output) | Activity Narrative | Quantum Responsible Party (UNDP, IP, or Responsible Party ) | Quantum Fund ID | Quantum Donor ID | Quantum Budgetary Account Code | Quantum Budget Account Description | Amount ($) Year 2 - 2025 | Amount ($) Year 3 - 2026 | Amount ($) Year 4 - 2027 | Total Budget (USD) | Budget Note |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Output 1: Risk knowledge and community needs are analysed and detailed plans are developed to effective implementation of the project. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1 Risk knowledge and community needs are analyzed and detailed plans are developed to effective implementation of the project. | 1.1. Conduct needs assessments and feasibility study | Need assessment and feasibilities will be conducted in the 8 areas | UNDP (001981) | 32045 | 000141 | 72100 | National consulting firm for feasibility study and design | $100,000.00 |  |  | $100,000.00 | 1 |
|  |  |  | UNDP (001981) | 32045 | 000141 | 71300 | National consultant to conduct needs assessment, community mapping and gender/stakeholder engagement | $32,000.00 |  |  | $32,000.00 | 2 |
|  |  |  | UNDP (001981) | 32045 | 000141 | 71600 | Domestic travel for project sites | $40,500.00 | $10,000.00 | $8,200.00 | $58,700.00 | 3 |
|  |  |  | UNDP (001981) | 32045 | 000141 | 75700 | Workshop cost | $27,700.00 | $5,500.00 |  | $33,200.00 | 4 |
|  |  |  | UNDP (001981) | 32045 | 000141 | 71200 | International engineering Consultant for oversight | $17,000.00 |  |  | $17,000.00 | 5 |
|  |  |  | UNDP (001981) | 32045 | 000141 | 75100 | General Management Support (GMS) (8%) | $17,376.00 | $1,240.00 | $656.00 | $19,272.00 | 6 |
|  |  |  | Total activity 1.1 |  |  |  |  | $234,576.00 | $16,740.00 | $8,856.00 | $260,172.00 |  |
|  | 1.2 Assess and plan for managing risks and ensure quality | Conduct risk assessments and implement quality assurance plans to identify, mitigate, and manage potential risks including the Environmental and Social Management Framework (ESMF), Environmental and Social Management Plan (ESMP) | UNDP (001981) | 32045 | 000141 | 64300 | Project Manager P2 | $14,166.00 | $14,166.00 | $14,166.34 | $42,498.34 | 7 |
|  |  |  | UNDP (001981) | 32045 | 000141 | 71200 | International SES consultant and risk mapping | $53,000.00 |  |  | $53,000.00 | 8 |
|  |  |  | UNDP (001981) | 32045 | 000141 | 71600 | Domestic travel for project sites | $10,000.00 |  |  | $10,000.00 | 9 |
|  |  |  | UNDP (001981) | 32045 | 000141 | 75700 | Workshop cost | $8,000.00 |  |  | $8,000.00 | 10 |
|  |  |  | UNDP (001981) | 32045 | 000141 | 75100 | General Management Support (GMS) (8%) | $6,813.28 | $1,133.28 | $1,133.31 | $9,079.87 | 11 |
|  |  |  | Total activity 1.2 |  |  |  |  | $91,979.28 | $15,299.28 | $15,299.65 | $122,578.21 |  |
| Total Output 1 |  |  |  |  |  |  |  | $326,555.28 | $32,039.28 | $24,155.65 | $382,750.21 |  |
| Output 2: Human Security in target communities is enhanced through the establishment and sustainbale operation of 15 evacuation centers with inclusive planning and design. |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.1 Retrofit existing building or newly construct evacuation centers | Construct 8 new evacuation centers and conduct 4 retrofitting for the existing evacuation center to ensure a secure and inclusive design for all during the emergency times | UNDP (001981) | 32045 | 000141 | 71600 | Domestic travel for project sites | $9,000.00 | $9,000.00 | $9,000.00 | $27,000.00 | 12 |
|  |  |  | UNDP (001981) | 32045 | 000141 | 72100 | Construction, Retrofitting and Monitoring costs | $1,934,000.00 | $79,000.00 | $55,000.00 | $2,068,000.00 | 13 |
|  |  |  | UNDP (001981) | 32045 | 000141 | 75700 | Workshop cost | $17,000.00 | $6,000.00 | $5,000.00 | $28,000.00 | 14 |
|  |  |  | UNDP (001981) | 32045 | 000141 | 75100 | General Management Support (GMS) (8%) | $156,800.00 | $7,520.00 | $5,520.00 | $169,840.00 | 15 |
|  |  |  | Total activity 2.1 |  |  |  |  | $2,116,800.00 | $101,520.00 | $74,520.00 | $2,292,840.00 |  |
|  | 2.2 Enhance community ownership and knowledge sharing through training and communication and advocacy | Ensure and enhance community ownership and knowledge sharing through training on safe evacuation and how to manage and operate evacuation center | UNDP (001981) | 32045 | 000141 | 64300 | Project Manager P2 | $70,900.00 | $70,900.00 | $70,900.00 | $212,700.00 | 16 |
|  |  |  | UNDP (001981) | 32045 | 000141 | 71300 | National consultant for graphic design and publications | $4,500.00 | $3,000.00 | $2,000.00 | $9,500.00 | 17 |
|  |  |  | UNDP (001981) | 32045 | 000141 | 71600 | Domestic travel for project sites | $3,000.00 | $7,500.00 | $7,500.00 | $18,000.00 | 18 |
|  |  |  | UNDP (001981) | 32045 | 000141 | 72600 | Grants (NGO for community engagement and CfW) | $180,000.00 |  | $50,000.00 | $230,000.00 | 19 |
|  |  |  | UNDP (001981) | 32045 | 000141 | 75100 | General Management Support (GMS) (8%) | $20,672.00 | $6,512.00 | $10,432.00 | $37,616.00 | 20 |
|  |  |  | Total activity 2.2 |  |  |  |  | $279,072.00 | $87,912.00 | $140,832.00 | $507,816.00 |  |
|  | 2.3. Strengthening policies, regulation and institutional Lao PDR on DRR | Review and update the National Guidelines for the Selection and Assessment of Evacuation Centers and other relevant policies; improve institutional capacity through learning | UNDP (001981) | 32045 | 000141 | 75700 | Workshop cost | $10,500.00 | $13,500.00 | $12,000.00 | $36,000.00 | 21 |
|  |  |  | UNDP (001981) | 32045 | 000141 | 71600 | Travel | $6,000.00 | $5,000.00 | $5,000.00 | $16,000.00 | 22 |
|  |  |  | UNDP (001981) | 32045 | 000141 | 71200 | International Consultant for Mid-Term Evaluation |  | $27,000.00 |  | $27,000.00 | 23 |
|  |  |  | UNDP (001981) | 32045 | 000141 | 71300 | National Consultant for supporting the Project Mid-Term Evaluation |  | $8,000.00 |  | $8,000.00 | 24 |
|  |  |  | UNDP (001981) | 32045 | 000141 | 75100 | General Management Support (GMS) (8%) | $1,320.00 | $4,280.00 | $1,360.00 | $6,960.00 | 25 |
|  |  |  | Total activity 2.3 |  |  |  |  | $17,820.00 | $57,780.00 | $18,360.00 | $93,960.00 |  |
| Total Output 2 |  |  |  |  |  |  |  | $2,413,692.00 | $247,212.00 | $233,712.00 | $2,894,616.00 |  |
| Project Management Cost (PMC) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | DES | IP salary | UNDP (001981) | 32045 | 000141 | 64300 | Project Manager P2 and DES (IP Salary) | $87,500.00 | $84,000.88 | $82,500.00 | $254,000.88 | 26 |
|  | Consultant | National Consultant | UNDP (001981) | 32045 | 000141 | 71300 | National Coordination Consultant | $12,000.00 |  |  | $12,000.00 | 27 |
|  | Project Staff | Project Coordinator NPSA9 & Project Assistant NPSA7 Monitoring, Evaluation & Learning Specialist | UNDP (001981) | 32045 | 000141 | 71400 | Project Coordinator NPSA9 Project Assistant NPSA7 Monitoring, Evaluation & Learning Specialist | $47,000.00 | $53,200.00 | $56,000.00 | $156,200.00 | 28 |
|  | Supplies | Office Equipment | UNDP (001981) | 32045 | 000141 | 72200 | Office equipment and funiture | $4,000.00 | $1,000.00 | $1,000.00 | $6,000.00 | 29 |
|  |  |  | UNDP (001981) | 32045 | 000141 | 72500 | Office supplies | $1,000.00 | $1,000.00 | $1,000.00 | $3,000.00 | 30 |
|  |  |  | UNDP (001981) | 32045 | 000141 | 72800 | ICT equipment | $17,000.00 |  |  | $17,000.00 | 31 |
|  |  | Miscellaneous equipment | UNDP (001981) | 32045 | 000141 | 72400 | Miscellaneous equipment | $500.00 |  |  | $500.00 | 32 |
|  |  | Printing and Media | UNDP (001981) | 32045 | 000141 | 74200 | Printing and publication of guidelines, goods, and documents | $4,500.00 | $5,500.00 | $5,500.00 | $15,500.00 | 33 |
|  | DES | Transactional Cost | UNDP (001981) | 32045 | 000141 | 74500 | DES (transactional cost) | $32,000.00 | $21,537.00 | $21,537.00 | $75,074.00 | 34 |
|  | GMS | Facilities and Administration | UNDP (001981) | 32045 | 000141 | 75100 | General Management Support (GMS) (8%) | $16,440.00 | $13,299.03 | $13,402.96 | $43,141.99 | 35 |
| Total Output 3 |  |  |  |  |  |  |  | $221,940.00 | $179,536.91 | $180,939.96 | $582,416.87 |  |
| Project Total |  |  |  |  |  |  |  | $2,962,187.28 | $458,788.19 | $438,807.61 | $3,859,783.08 |  |
| Levy (1%) Based on HQ advice |  |  |  |  |  |  |  |  |  |  | $38,542.02 |  |
| Full Amount |  |  |  |  |  |  |  | $2,962,187.28 | $458,788.19 | $438,807.61 | $3,898,325.10 |  |

Budget Note

| No | Budget Line | Budget Account Description | Description of cost items |
| --- | --- | --- | --- |
| COMPONENT 1. Risk knowledge and community needs are analysed and detailed plans are developed to effective implementation of the project. |  |  |  |
| Activity 1.1 |  |  |  |
| 1 | 72100 | National consulting firm for feasibility study and design | National consulting firm for feasibility study and design (Output 1.1) |
| 2 | 71300 | National consultant to conduct needs assessment, community mapping and gender/stakeholder engagement | National consultant to conduct needs assessment, community mapping and gender/stakeholder engagement |
| 3 | 71600 | Domestic travel for project sites | Travel costs for UNDP staff (transportation and DSA, per diem, etc.,) and stakeholders for within the country to potential locations to for community mapping and identification of construction and retrofitting locations |
| 4 | 75700 | Workshop cost | Costs associated with planning, organizing, and managing including renting location, training materials, facilitator/trainer fees, catering (lunch/coffee break) for several invents including International day of disaster risk reduction (DRR day) and Architecture Design Competition. |
| 5 | 71200 | International engineering Consultant for oversight | Additional ToRs for International Engineering Consultant to review designs and BoQ submitted by consulting firm, construction documents for bidding, and bidding documents submitted by interested bidders, |
| 6 | 75100 | General Management Support (GMS) (8%) | - |
| Activity 1.2 |  |  |  |
| 7 | 64300 | Project Manager P2 | Provision of the project management in terms of overseeing the entire project: planning, organizing, monitoring budget, timeline, and deliverables. USD127,401 * 3 years = USD 382,203 Split between Activity 1.2, 2.2, PMC |
| 8 | 71200 | International SES consultant and risk mapping | International Social and Environmental Standards (SES) consultant for ensuring the project complies with environmental and social impact standards. To conduct ESMF, ESIA in 12 sites, ESMP, GRM plus training. |
| 9 | 71600 | Domestic travel for project sites | Travel costs for UNDP staff (transportation and DSA, per diem, etc.,) and stakeholders for within the country to construction and retrofitting locations for risk assessment and quality assurance plan |
| 10 | 75700 | Workshop cost | Costs associated with planning, organizing, and managing including renting location, training materials, facilitator/trainer fees, catering (lunch/coffee break) consultation workshops with provincial and district authorities in relation to risk assessment and quality assurance plan |
| 11 | 75100 | General Management Support (GMS) (8%) | - |
| COMPONENT 2. Human Security in target communities is enhanced through the establishment and sustainbale operation of 15 evacuation centers with inclusive planning and design. |  |  |  |
| Activity 2.1 |  |  |  |
| 12 | 71600 | Domestic travel for project sites | Travel costs (transportation and DSA, per diem, etc.,) for UNDP and project staff and stakeholders within the country to project sites for construction and retrofitting monitoring |
| 13 | 72100 | Construction, Retrofitting and Monitoring costs | 1. Work contractor for the construction of retrofitting for the existing evacuation center to ensure a secure and inclusive design for all during the emergencies time; Construction cost for 8 evacuation centers and retrofitting of 4 existing centers. Work contractor for the installation of Equipment, including solar panels, water tank, fire extinguisher, and other furniture and equipment. 2. Civil Engineer consultancy firm to provide construction work monitoring services. |
| 14 | 75700 | Workshop cost | Costs associated with planning, organizing, and managing including renting location, training materials, facilitator/trainer fees, catering (lunch/coffee break) for consultation with provincial and district authorities on the progress, quality, and other issues that may arise from construction/retrofitting. |
| 15 | 75100 | General Management Support (GMS) (8%) | - |
| Activity 2.2 |  |  |  |
| 16 | 64300 | Project Manager P2 | Provision of the project management in terms of overseeing the entire project: planing, organizing, monitoring budget, timeline, and deliverables. USD127,401 * 3 years = USD 382,203 Split between Activity 1.2, 2.2, PMC |
| 17 | 71300 | National consultant for graphic design and publications | 1. National consultant for designing materials like brochures, posters, banners, and infographics for the project, ensuring visual consistency across all communication materials. USD250 * 20 working days + travel USD2,000 2. Internship stipend |
| 18 | 71600 | Domestic travel for project sites | Travel costs (transportation and DSA, per diem, etc.,) for UNDP and project staff and stakeholders within the country for the implementation of NGO for community engagement and CfW |
| 19 | 72600 | Grants (NGO for community engagement and CfW) | Provide funding to NGO that involve communities in the project through engagement or "Cash for Work" initiatives. - Empower local communities by providing them with temporary employment during the construction process. - Emergency preparedness planning, EC O&M planning, and evacuation drills |
| 20 | 75100 | General Management Support (GMS) (8%) | - |
| Activity 2.3 |  |  |  |
| 21 | 75700 | Workshop cost | Costs associated with planning, organizing, and managing including renting location, training materials, facilitator/trainer fees, catering (lunch/coffee break) for consultation workshops with provincial and district authorities to update, validate and approve the National Guidelines for the Selection and Assessment of Evacuation Centers and other relevant policies |
| 22 | 71600 | Travel | Travel costs (transportation and DSA, per diem, etc.,) for UNDP and project staff and stakeholders within the country for consultation with provincial and district authorities to update, validate and approve the National Guidelines for the Selection and Assessment of Evacuation Centers and other relevant policies |
| 23 | 71200 | International Consultant for Mid-Term Evaluation | International consultant for conducting an evaluation of the project’s progress at the midpoint, providing recommendations for course corrections and identifying areas for improvement. |
| 24 | 71300 | National Consultant for supporting the Project Mid-Term Evaluation | Local consultant for assisting the international consultant during the mid-term evaluation. Ensuring that the project document aligns with national development strategies |
| 25 | 75100 | General Management Support (GMS) (8%) | - |
| COMPONENT 3. Project Management Cost (PMC) |  |  |  |
| 26 | 64300 | Project Manager P2 and DES (IP Salary) | 1. Provision of the project management in terms of overseeing the entire project: planing, organizing, monitoring budget, timeline, and deliverables. USD127,401 * 3 years = USD 382,203 Split between Activity 1.2, 2.2, PMC 2. UNDP oversight roles |
| 27 | 71300 | National Coordination Consultant | Coordination with the Government partner and other stakeholders. Managing the overall project implementation, ensuring activities align with project goals. Providing project monitoring including budget, procurement, finance, and administration matters, from May to August 2025 |
| 28 | 71400 | Project Coordinator NPSA9 Project Assistant NPSA7 Monitoring, Evaluation & Learning Specialist | 1. Coordination with the Government partner and other stakeholders. Managing the overall project implementation, ensuring activities align with project goals. Providing project monitoring including budget, procurement, finance, and administration matters. Annual cost NPSA9 USD25,000 + NPSA7 USD14,000 in 2025 (5% increase/year) 2. Monitoring, Evaluation & Learning Specialist for assessing project outcomes, including the effectiveness of project implementation (Share cost with IWRM & FARM project). |
| 29 | 72200 | Office equipment and funiture | Equipment purchased for project-related activities including furniture, equipment, including office equipment for workspace settings. |
| 30 | 72500 | Office supplies | Office supplies including stationeries and other office equipment |
| 31 | 72800 | ICT equipment | Laptops, printer, other accessories used to facilitate communication, and project management |
| 32 | 72400 | Miscellaneous equipment | Other communication and IT related equipment |
| 33 | 74200 | Printing and publication of guidelines, goods, and documents | Printing evacuation guidelines for community members and stakeholders, producing educational materials for disaster preparedness, printing of documents and materials for project visibility |
| 34 | 74500 | DES (transactional cost) | Transactional costs for operational expenses to facilitate activities. |
| 35 | 75100 | General Management Support (GMS) (8%) | - |

# Governance and Management Arrangements

Given the project implementation modality (DIM), the Implementing Partner for this project is the United Nations Development Programme (UNDP). UNDP will closely work with the key Government partner for this project, primarily the Department of Social Welfare, MOLSW, but also with the Ministry of Education and Sports, the Ministry of Public Works and Transport, and the Ministry of Natural Resources and Environment in fulfilling this role. The Department of Social Welfare will provide technical and policy advice to the implementation of the project and ensure the sustainability of the project’s impact.

MOLSW’s role is crucial in this project in finalizing, adopting and disseminating the national guidelines for establishing and operating evacuation centers and ensuring sustainable use and maintenance of the evacuation centers established under the project.

UNDP will run operational procedures (procurement, finance, HR, admin/logistics, IT, etc.) in accordance with applicable UNDP rules, policies and procedures. The Project Management Unit (PMU) will implement the project on behalf of the IP. UNDP will recruit PMU staff, a Project Manager, a Project Coordinator, and a Project Administrative and Finance Associate with the project resources. The Project Manager will work under the direct supervision of the Team Leader, Natural Resources Management, Climate Change and Disaster Risk Reduction Unit of UNDP, and is fully responsible for project implementation and delivering outputs envisaged in the Project Document. Procurement of local and international consultants will also be carried out by UNDP under its rules and procedures, and they report to the Project Manager.

The Implementing Partner is responsible for the following tasks:

  - Project planning, coordination, management, monitoring and evaluation (M&E) and reporting. This includes providing all required information and data necessary for timely, comprehensive and evidence-based project reporting, including results and financial data, as necessary. The Implementing Partner will strive to ensure project-level M&E is undertaken and is aligned with national systems so that the data used and generated by the project supports national systems.

  - Risk management as outlined in this Project Document;

  - Procurement of goods and services, including human resources;

  - Entering into an Agreement with Responsible Parties for the implementation of specific activities (if needed)

  - Financial management, including overseeing financial expenditures against project budgets;

  - Approving and signing the annual workplan;

  - Approving and signing the combined delivery report at the end of the year;

  - Aligning the financial report or the funding authorisation and certificate of expenditures.

  - Accountability to the donor for the implementation of this project. This includes the oversight of project execution to ensure that the project is carried out in accordance with agreed standards and provisions ;

  - Delivering the project cycle management services comprising project approval and start-up, project supervision and oversight, and project completion and evaluation.

  - Project Assurance role of the Project Board/Steering Committee.

The project implementation and governance will be structured as follows:

Figure 1: Project Organisation Structure A

# Legal Context

This project document shall be the instrument referred to as such in Article 1 of the Standard Basic Assistance Agreement between the Government of Lao People’s Democratic Republic and UNDP, signed on 10 October 1988.  All references in the SBAA to “Executing Agency” shall be deemed to refer to “Implementing Partner.”

This project will be implemented by the United Nations Development Programme (“Implementing Partner”) in accordance with its financial regulations, rules, practices, and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

# Risk Management

UNDP (DIM)

- UNDP, as the Implementing Partner, will comply with the policies, procedures and practices of the United Nations Security Management System (UNSMS.)

- UNDP as the Implementing Partner will undertake all reasonable efforts to ensure that none of the [project funds] [UNDP funds received pursuant to the Project Document] are used to provide support to individuals or entities associated with terrorism , that the recipients of any amounts provided by UNDP hereunder do not appear on the United Nations Security Council Consolidated Sanctions List, and that no UNDP funds received pursuant to the Project Document are used for money laundering activities. The United Nations Security Council Consolidated Sanctions List can be accessed via https://www.un.org/securitycouncil/content/un-sc-consolidated-list. This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document.

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

- UNDP as the Implementing Partner will: (a) conduct project and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

- In the implementation of the activities under this Project Document, UNDP as the Implementing Partner will handle any sexual exploitation and abuse (“SEA”) and sexual harassment (“SH”) allegations in accordance with its regulations, rules, policies and procedures.

- All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any programme or project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

- UNDP as the Implementing Partner will ensure that the following obligations are binding on each responsible party, subcontractor, and sub-recipient:

  - Consistent with the Article III of the SBAA [or the Supplemental Provisions to the Project Document], the responsibility for the safety and security of each responsible party, subcontractor and sub-recipient and its personnel and property, and of UNDP’s property in such responsible party’s, subcontractor’s and sub-recipient’s custody, rests with such responsible party, subcontractor and sub-recipient.  To this end, each responsible party, subcontractor and sub-recipient shall:

    - put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

    - assume all risks and liabilities related to such responsible party’s, subcontractor’s and sub-recipient’s security, and the full implementation of the security plan.

  - UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the responsible party’s, subcontractor’s and sub-recipient’s obligations under this Project Document.

  - Each responsible party, subcontractor and sub-recipient (each a “sub-party” and together “sub-parties”) acknowledges and agrees that UNDP will not tolerate sexual harassment and sexual exploitation and abuse of anyone by the sub-parties, and other entities involved in Project implementation, either as contractors or subcontractors and their personnel, and any individuals performing services for them under the Project Document.

(a) In the implementation of the activities under this Project Document, each sub-party shall comply with the standards of conduct set forth in the Secretary General’s Bulletin ST/SGB/2003/13 of 9 October 2003, concerning “Special measures for protection from sexual exploitation and sexual abuse” (“SEA”).

(b) Moreover, and without limitation to the application of other regulations, rules, policies and procedures bearing upon the performance of the activities under this Project Document, in the implementation of activities, each sub-party, shall not engage in any form of sexual harassment (“SH”). SH is defined as any unwelcome conduct of a sexual nature that might reasonably be expected or be perceived to cause offense or humiliation, when such conduct interferes with work, is made a condition of employment or creates an intimidating, hostile or offensive work environment. SH may occur in the workplace or in connection with work. While typically involving a pattern of conduct, SH may take the form of a single incident. In assessing the reasonableness of expectations or perceptions, the perspective of the person who is the target of the conduct shall be considered.

  - In the performance of the activities under this Project Document, each sub-party shall (with respect to its own activities), and shall require from its sub-parties (with respect to their activities) that they, have minimum standards and procedures in place, or a plan to develop and/or improve such standards and procedures in order to be able to take effective preventive and investigative action. These should include: policies on sexual harassment and sexual exploitation and abuse; policies on whistleblowing/protection against retaliation; and complaints, disciplinary and investigative mechanisms. In line with this, sub-parties will and will require that their respective sub-parties will take all appropriate measures to:

(i) Prevent its employees, agents or any other persons engaged to perform any services under this Project Document, from engaging in SH or SEA;

(ii) Offer employees and associated personnel training on prevention and response to SH and SEA, where sub-parties have not put in place its own training regarding the prevention of SH and SEA, sub-parties may use the training material available at UNDP;

(iii) Report and monitor allegations of SH and SEA of which any of the sub-parties have been informed or have otherwise become aware, and status thereof;

(iv) Refer victims/survivors of SH and SEA to safe and confidential victim assistance; and

(v) Promptly and confidentially record and investigate any allegations credible enough to warrant an investigation of SH or SEA. Each sub-party shall advise UNDP of any such allegations received and investigations being conducted by itself or any of its sub-parties with respect to their activities under the Project Document, and shall keep UNDP informed during the investigation by it or any of such sub-parties, to the extent that such notification (i) does not jeopardize the conduct of the investigation, including but not limited to the safety or security of persons, and/or (ii) is not in contravention of any laws applicable to it. Following the investigation, the relevant sub-party shall advise UNDP of any actions taken by it or any of the other entities further to the investigation.

  - Each sub-party shall establish that it has complied with the foregoing, to the satisfaction of UNDP, when requested by UNDP or any party acting on its behalf to provide such confirmation. Failure of the relevant sub-party to comply of the foregoing, as determined by UNDP, shall be considered grounds for suspension or termination of the Project.

  - Each responsible party, subcontractor and sub-recipient will ensure that any project activities undertaken by them will be implemented in a manner consistent with the UNDP Social and Environmental Standards and shall ensure that any incidents or issues of non-compliance shall be reported to UNDP in accordance with UNDP Social and Environmental Standards.

  - Each responsible party, subcontractor and sub-recipient will take appropriate steps to prevent misuse of funds, fraud, corruption or other financial irregularities, by its officials, consultants, subcontractors and sub-recipients in implementing the project or programme or using the UNDP funds.  It will ensure that its financial management, anti-corruption, anti-fraud, and anti-money laundering and countering the financing of terrorism policies are in place and enforced for all funding received from or through UNDP.

  - The requirements of the following documents, then in force at the time of signature of the Project Document, apply to each responsible party, subcontractor and sub-recipient: (a) UNDP Policy on Fraud and other Corrupt Practices (b) UNDP Anti-Money Laundering and Countering the Financing of Terrorism Policy; and (c) UNDP Office of Audit and Investigations Investigation Guidelines. Each responsible party, subcontractor and sub-recipient agrees to the requirements of the above documents, which are an integral part of this Project Document and are available online at www.undp.org.

  - In the event that an investigation is required, UNDP will conduct investigations relating to any aspect of UNDP programmes and projects. Each responsible party, subcontractor and sub-recipient will provide its full cooperation, including making available personnel, relevant documentation, and granting access to its (and its consultants’, subcontractors’ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with it to find a solution.

  - Each responsible party, subcontractor and sub-recipient will promptly inform UNDP as the Implementing Partner in case of any incidence of inappropriate use of funds, or credible allegation of fraud, corruption other financial irregularities with due confidentiality.

Where it becomes aware that a UNDP project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption, each responsible party, subcontractor and sub-recipient will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). It will provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

  - UNDP will be entitled to a refund from the responsible party, subcontractor or sub-recipient of any funds provided that have been used inappropriately, including through fraud corruption, other financial irregularities or otherwise paid other than in accordance with the terms and conditions of this Project Document.  Such amount may be deducted by UNDP from any payment due to the responsible party, subcontractor or sub-recipient under this or any other agreement.  Recovery of such amount by UNDP shall not diminish or curtail any responsible party’s, subcontractor’s or sub-recipient’s obligations under this Project Document.

Where such funds have not been refunded to UNDP, the responsible party, subcontractor or sub-recipient agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Project Document, may seek recourse to such responsible party, subcontractor or sub-recipient for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud, corruption or other financial irregularities, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Note:  The term “Project Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Project Document, including those with responsible parties, subcontractors and sub-recipients.

  - Each contract issued by the responsible party, subcontractor or sub-recipient in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from it shall cooperate with any and all investigations and post-payment audits.

  - Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the project or programme, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

  - Each responsible party, subcontractor and sub-recipient shall ensure that all of its obligations set forth under this section entitled “Risk Management” are passed on to its subcontractors and sub-recipients and that all the clauses under this section entitled “Risk Management Standard Clauses” are adequately reflected, mutatis mutandis, in all its sub-contracts or sub-agreements entered into further to this Project Document.

# ANNEXES

- Project Quality Assurance Report

EC_QAProcedure_Approved.pdf

- Social and Environmental Screening

Project Information

| Project Information |  |
| --- | --- |
| 1. Project Title | Strengthening Disaster Response through the Establishment of Evacuation Shelters |
| 2. Project Number (i.e. Atlas project ID, PIMS+) | 1003142 |
| 3. Location (Global/Region/Country) | Country Office - Lao PDR |
| 4. Project stage (Design or Implementation) | Design |
| 5. Date |  |

Part A. Integrating Programming Principles to Strengthen Social and Environmental Sustainability

QUESTION 1: How Does the Project Integrate the Programming Principles in Order to Strengthen Social and Environmental Sustainability?

Briefly describe in the space below how the project mainstreams the human rights-based approach

The three provinces – Khammoune, Champasak and Saravanne with the total population of 1,483,017 (Khammouane: 392,052, Saravane: 396,942, Champasack: 694,023) according to the latest Census conducted in 2015), experience flood damage yearly from the Mekong River and its tributaries, such as the Xe Ban Fai and Xe Don Rivers. In 2022 and 2023. The flood affected the livelihood of the people in the region, posing significant human rights concerns, including the right to necessity, from the lack of necessities such as access to clean water and food, the disruption of education, the security risk, including child trafficking, sexual harassment, violence comes from the dire situation. The prolonged effects of the disaster led to the prevalence of psychosocial suffering in both adults and children, and the rise of potential outbreaks of viruses and diseases, including waterborne diseases due to the unsafe environment caused by the flood, exacerbated the vulnerability of the people. In addition, flooding further undermines the household's financial security, leading to long-term economic drains. The Evacuation Center project aims to improve human security during disasters such as flooding by strengthening the affected communities' capabilities to access safe, inclusive, and fully operational centers. It also aims to assist the Government of Lao PDR in developing National Guidelines for the selection and assessment of evacuation centers by providing feedback and lessons learned from the project's best practices. This project incorporates human rights approaches by ensuring that the design, implementation, and operation of the centers are inclusive, equitable, and responsive to the needs of vulnerable and marginalized groups. The project will actively involve women, ethnic minorities, people with disabilities, and other vulnerable populations in the planning and decision-making process to ensure that all voices are heard and all needs are met. Additionally, the design of the facilities will prioritize safety and privacy, especially for women, pregnant women, and people with disabilities.

Briefly describe in the space below how the project is likely to improve gender equality and women’s empowerment

The project contributes to gender equality and women’s empowerment in several ways. The evacuation center design within the project activities significantly prioritizes women’s safety during emergency situations. It has incorporated partner recommendations by including separate entry points for restrooms in the evacuation center, a critical element that ensures safety and minimizes the risk of sexual harassment of women. During the design phase, the project encourages strong participation from women to engage all aspects of the project, from assessment studies to construction and operation of the centers, to better understand the needs of women and vulnerable groups. This inclusive approach not only ensures that the specific needs of women are met but also empowers them to take a leading role in disaster preparedness and community resilience efforts. Additionally, the Cash for Work (CfW) program provides women with opportunities to achieve financial stability during the construction period. By participating in CfW, women can earn an income, supporting their families and enhancing their economic independence and empowerment. The program is designed to be inclusive, ensuring that even women who may not be able to engage in heavy manual labour, such as those with family care duties or disabilities, can still benefit.

Briefly describe in the space below how the project mainstreams sustainability and resilience

The project ensures that communities are prepared for annual flooding by providing well-designed and well-equipped evacuation facilities for their safety and to meet their essential needs. Evacuation drill training will be conducted to further enhance preparedness and resilience to the disaster. Additionally, the project promotes sustainability through the multifunctional use of the facilities during non-emergency situations, such as hosting community events, schools, and other types of gatherings. The income generated from such activities is utilized for maintenance, ensuring the long-term impact of the project. This strategy collectively guarantees that the centers remain functional and well-maintained and become integral to the community’s resilience efforts. Beyond building the facilities, the project aims to help develop Lao PDR's national evacuation center guidelines. The MOLSW and UNICEF have drafted the guideline, but it hasn't been piloted or approved. This project will share lessons learned and best practices to update the guideline, enhancing long-term disaster response and preparedness.

Briefly describe in the space below how the project strengthens accountability to stakeholders

The project envisages participatory approach by stakeholder engagement throughout the project cycle. The stakeholder engagement plan will be prepared during the project preparation phase. The project will also have a project specific GRM. The project team will ensure that the GRM is publicly accessible and that all grievances are addressed in a timely and acceptable manner in line with the UNDP SES. Community mapping will be carried out to understand the cultural, social, and livelihood dynamics of each target area. This will be achieved through inclusive stakeholder consultation and focus group discussions. The project aims to involve the community throughout the project cycles—ranging from site selection and design to construction and operationalization. The project incorporates an innovative design competition with criteria of gender and social inclusion, ensuring that the infrastructure and services developed respond to the needs of all community members. During construction, the project will implement cash-for-work initiatives to promote local engagement and ownership while also assisting communities in developing maintenance, financial, and operational plans.

Part B. Identifying and Managing Social and Environmental Risks

| QUESTION 2: What are the Potential Social and Environmental Risks? Note: Complete SESP Attachment 1 before responding to Question 2. | QUESTION 3: What is the level of significance of the potential social and environmental risks? Note: Respond to Questions 4 and 5 below before proceeding to Question 5 |  |  |  | QUESTION 6: Describe the assessment and management measures for each risk rated Moderate, Substantial or High |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Description (broken down by event, cause, impact) | Impact and Likelihood (1-5) | Significance (Low, Moderate Substantial, High) | Comments (optional) |  | Description of assessment and management measures for risks rated as Moderate, Substantial or High |  |  |
| Risk 1: Marginalized and vulnerable groups, including but not limited to women, ethnic minorities, and persons with disabilities, may be excluded from decision-making processes due to limited capacity, accessibility barriers, and a lack of support or grievance mechanisms. This exclusion may result in their needs begin neglected, leading to projects that do not effectively address the impact of disaster on these groups. It could also cause stakeholder dissatisfaction objections. P.3, P.5. P.9 P.10 P.13 P.14 S6.1 | I = 3 L =3 | Moderate |  |  | To address the risk, the project will implement the following plans: - Stakeholder Engagement Plan (SEP), including the Communication and Information Dissemination Plan, to ensure inclusive, accessible, and culturally appropriate engagement. This will include an inclusive communication strategy that provides information in multiple formats – such as large, printed signs with disabilities in rural areas. - Gender Equality and Social Inclusion (GAP/GEDSI) Plan: to promote the meaningful participation of women and marginalized groups in all project stages. The project will ensure that evacuation shelters are equipped with accessible entrances, restrooms, and facilities and that the evacuation drills include people with disabilities. - Indigenous People Plan (IPP), if applicable, to ensure the rights and participation of Indigenous communities are respected and upheld. - Grievance Redress Mechanism (GRM), including an internal mechanism within the project team, which will be communicated to all staff and shared with local communities and relevant stakeholders to ensure transparency and accountability. |  |  |
| Risk 2: There is a risk of violence, harassment, and gender-based violence (GBV), particularly in the context of construction and facility protection activities. The risk may be exacerbated by the influx of workers (construction workers, security personnel and personnels) – especially in male-dominated sectors – into local communities, which may increase the risk of sexual exploitation, abuse, and harassment, particularly affecting women and girls. It could result in leading to harm against women and girls and damage to the project's reputation and community trust. P.12 P.14; S.3.7 S3.8 | I = 4 L = 2 | Moderate |  |  | To prevent sexual harassment, abuse, and any related gender-based violence, the procurement team will communicate with the contractor to establish a workers' code of conduct to reduce the risk of sexual harassment and gender-based violence. The code of conduct and appropriate policies will be included in the procurement clauses and the contract. The contractor will also be required to set up transparent reporting and response mechanisms for any incidents. All construction workers and security personnel will be required to sign and adhere to a strict code of conduct that explicitly prohibits any form of violence, harassment, or GBV. The code will be reinforced through mandatory training and regular monitoring. The project will establish the grievances redress mechanism and ensure that the nearby communities, staff and contractors are aware of this. In addition, the security guards stationed onsite would be provided behavioral training by the Contractor on communicating with local community and workforce members in case of any grievances. |  |  |
| Risk 3: Given the area's vulnerability to floods and landslides, there is a significant risk of structural and infrastructure failures. Site selection, inadequate engineering design, or substandard construction practices could compromise the structural integrity of the facilities under extreme weather conditions, especially as the targeted provinces are impacted by seasonal floods. Failure could result in serious consequences, including the loss of project assets, environmental degradation, damage to surrounding property, injury, or loss of life. Additionally, flooding, landslide and/or land preparation, foundation excavation, and construction activities may expose unexposed Ordnance (UXO) presenting safety risks for workers. These incidents could also lead to reputational harm for the project, the organization, and its partners, undermining community trust and stakeholder confidence. This risk goes beyond the project's lifecycle. It is also critical for the operational and safe use during the emergency period after the project ends. S. 2.1, S2.2, S. 3.3 | I = 4 L = 3 | Substantial |  |  | The project will conduct the site assessment and feasibility studies to determine suitable sites for the construction of the evacuation shelter. The project will conduct the Environmental and Social Management Framework (ESMF) to outline how the Social and Environmental Standard (SES) will be applied during screening and site assessment. The Environmental and Social Impact Assessment (ESIA) will be conducted following the site assessment to assess the risks and impacts of the identified/proposed sites. The ESIA is to evaluate potential risks and impacts such as: Slope instability (due to vegetation clearance), landslide risk from the disturbed topography, drainage system that could contribute to the landslide/flood risk, community access route and any other physical hazards, such as those associated with UXO. Based on the assessment, the project will also develop an Environmental and Social Management Plan (ESMP) for each site to manage risks and mitigate impacts during project implementation and construction activities. Those include and not limited to: - The disaster response or emergency response plan - Surface water management, including drainage planning to reduce flood and landslide risk - Soil management plan outlining measures to prevent movement, erosion sedimentation of excavated soil. - Monitoring plan for the regular site inspections to monitor soil movement or instability. - The project will ensure comprehensive UXO clearance and secure official work to mitigate this hazard. To ensure that, the UXO Clearance Plan will also be prepared for the Management Plan (MP). |  |  |
| Risk 4: The shelter's construction contributes to greenhouse gas emissions, along with the release of pollutants, including wastes, that could cause adverse effects on the local community's environment and well-being. The construction will likely create noise, pollution, traffic, hazards, and consume raw materials, energy, and water. S. 2.4, S 3.1, S 3.2, S 8.1, S 8.2 S8.6 | I = 3 L =3 | Moderate |  |  | The ESMP will map out the management plan and strategy for responding to the identified risks and impacts. The project team will work closely with the engineer and design team to involve the use of low carbon or recycled/reclaimed materials, construction methods that reduce the amount of cement, and use of local resources (wood and bamboo) and local purchasing. The project will also provide support with solar panel installation that encourages the use of renewable energy. As part of the ESMP, some of the MP are: - Environmental Management Plan - Waste Management Plan - Resource Management Plan - Health and Safety Management Plan - Noise and Vibration Management Plan - Traffic and Access Management Plan UNDP will also hire a National Consultant for field assistance who will monitor the progress of the work, the site preparation and installation of the equipment, ensuring minimal possible impact on the well-being and the environment surrounding the community. S/He role is also to ensure the mitigation of this risk. |  |  |
| Risk 5: Due to its location in rural areas, finding workers within the areas/communities will be challenging. The influx of construction workers could strain local resources and heighten social tensions between villagers and outsiders. Additionally, while security measures will be in place to protect the construction sites, there remains a risk of potential conflicts and violence, which could further complicate the project's implementation. P7. S. 3.7, 3.8 | I = 3 L = 3 | Moderate |  |  | During the construction phase, the project will mobilize local companies and workers as much as possible. However, the contractor should inform the project management team if they plan to hire workers from outside the local community. The project will engage with local communities early, ensuring clear communication and equitable resource distribution. Security measures and conflict resolution mechanisms (different from GRM) will be in place to address any disputes that arise. |  |  |
| Risk 6: There is a risk that the construction of the Evacuation centers required the land, territories, or resources used or held by the local community, the indigenous group (with or without legal titles possession to such areas), or/and as the site with historical, cultural, artistic, traditional, or religious value, which could lead to ownership disputes or loss of access to land used. In areas where the indigenous peoples are present, the project also risks affecting their human rights, traditional livelihoods, and access to natural resources. P14 S1.3 S4.1 S4.3 S5.4 S6.1 S6.2 S6.3 | I = 3 L =1 | Low |  |  | The project will not select a site if the construction would result in displacement or resettlement. In principle, the project will prioritize publicly owned land for shelter construction. Privately owned land will only be considered in exceptional cases—such as when no suitable public land is available in a safe location—and only if land use arrangements are formally facilitated and validated by government partners. The project shall conduct thorough land due diligence to verify ownership and ensure a clear title before beginning. It could be done through the landownership survey. The project will ensure transparent engagement with local communities and landowners regarding any potential disputes. Legal agreements shall be secured to formalize access rights. Additionally, a grievance redress mechanism will be established to receive comments, feedback and objections from the community, while the conflict resolution mechanism will be used to handle disputes efficiently. Contingency plans should be developed to identify alternative routes or sites if access issues cannot be resolved promptly. |  |  |
| Risk 7: There is a potential violation of national labor laws and international standards. This includes the common practice of using child labor and forced labor or the employment of workers without formal contracts or adequate safeguards. Contractors may also fail to uphold fundamental labor rights, including the insufficient provision of protection gear that is likely to lead to safety risks that could cause injuries or fatalities. Harm and losses might occur due to vehicles, machinery, and the failure of the structure integrity during and after the completion of the construction. S. 3.3 S7.1 S7.2 S7.3 S7.4 S7.5 S7.6 | I = 3 L = 3 | Moderate | On the risk of potential violation of national labor laws and international standards. The project will review the National Labour Law and UNDP Health, Safety and Working Conditions Standards and consult ILO. The Labour Law (2013) defines the principles, regulations and measures on administration, monitoring, labour skills development, recruitment, and labour protection in order to enhance the quality and productivity of work in society so as to ensure the transformation to modernization and industrialization aimed at safeguarding the rights of employees and employers, as well as the legitimate interests and the continual improvement of their livelihoods, while contributing to the promotion of investment, national socio-economic development, and regional and international links. Further, a Decree on Labour Safety and health was enacted in 2019. This decree stated that the workers have the legal right to require their employers to ensure occupational health and safety. Employees can submit petitions to labour management agencies to intervene if their employers do not improve the workplace environment to meet health and safety standards in line with workers' requests. Labourers also have the right to reject a job assigned by their employee if the work is deemed to be highly risky, in accordance with the decree. Further to this, this decree also gives employees the right to receive information or knowledge concerning any risky or dangerous conditions and to be informed of precautionary measures that would avoid risks and dangers. |  | Risk Management Practices and Plans are expected from the contractors prior to the commencement of the construction activities, including: - Occupational Safety and Health (OSH) assessment - Emergency response and recovery plan - Contract Labour Management Plan - Design route and system, including alarm system for heavy vehicles and machinery - Structure designs of the shelters The contractor shall also be briefed and expected to have the following arrangements in place before the construction activities: - All workers have their age verified through Identity Cards or family book - Worker records are on site and ready for inspection. - Worker bank account details or wage details are recorded and maintained. The project requires the clauses mentioned in procurement and contracts that require the contractor to have the occupational health and safety procedure in place before the commencement of the work. Those should also include the availability of protective gear and the installation of fall prevention infrastructure, including guard rails and devices, including lifelines and harnesses. After the completion of the construction, an individual consultant should inspect the integrity of the structure to ensure the safety of the building structure, which is to be subsequently reviewed and approved by UNDP. A grievances redress mechanism will also be established internally in their team and communicated to all staff. This information will also be disseminated to the local communities. |  |  |
| Risk 8: The construction of the Evacuation Shelter might require the clearance of vegetation and land preparation for building. This could result in the loss or fragmentation of natural habitats, disruption of local biodiversity and wildlife movement, soil erosion, reduced soil fertility, and a decrease in ecosystem services such as water regulation. S1.1, S1.3, S1.4, S1.7 | I = 3 L = 3 | Moderate |  |  | As noted above, the project will conduct site-specific Environmental and Social Impacts Assessments (ESIAs) to identify ecologically sensitive areas, assess soil stability, and evaluate potential impacts on biodiversity and ecosystem services. Appropriate measures to mitigate any identified risks will be included in the site-specific ESMPs. The project will ensure the minimal and selective removal of vegetation on land, prioritizing the preservation of critical natural habitats and mature tree cover wherever possible. The project will approach sloped terrains with caution; if removal is unavoidable, different measures such as terracing, retaining walls, slope stabilization, and erosion control systems will be adopted to prevent any risk (landslide prevention and structural failure risk mentioned above with mitigation measures). |  |  |
| Risk 9: In the event of a disaster, evacuation shelters may become overcrowded and serve as temporary living spaces for extended periods. There is a risk of transmission of communicable diseases, including measles, influenza, Covid-19, and other respiratory or contact-based illnesses. Without proper consideration to space, ventilation, and hygiene or sanitation facilities, this risk can increase, affecting people within the shelter and beyond, particularly vulnerable groups such as children, the elderly, or individuals with compromised immune systems. S3.4 | I = 3 L = 3 | Moderate |  |  | The project will incorporate preventive public health measures in both the design and operation of the evacuation shelter. Each shelter requires a designated isolation area to temporarily separate and care for individuals with symptoms of infectious illness, helping to prevent outbreaks in crowded conditions. The shelter will be designed with optimal natural ventilation – cross-ventilation layouts and high ceilings with appropriate air purification systems or fans installed to improve indoor air quality. The shelter will be equipped with adequate sanitation and hygiene infrastructure, including a clean water supply, gender-sensitive and accessible toilets, and a handwashing station. |  |  |
|  | QUESTION 4: What is the overall project risk categorization? |  |  |  |  |  |  |
|  | Low Risk |  |  | ☐ |  |  |  |
|  | Moderate Risk |  |  | ☐ |  |  |  |
|  | Substantial Risk |  |  | X |  |  |  |
|  | High Risk |  |  | ☐ |  |  |  |
|  | QUESTION 5: Based on the identified risks and risk categorization, what requirements of the SES are triggered? (check all that apply) |  |  |  |  |  |  |
|  | Question only required for Moderate, Substantial and High Risk projects |  |  |  |  |  |  |
|  | Is assessment required? (check if “yes”) |  |  | X |  |  | Status? Planned |
|  | if yes, indicate overall type and status |  |  |  | X | Targeted assessment(s) Site Assessment of 6 targeted villages of Kammoune and Champasack provinces from previous project (2023) Stakeholder Analysis: - Stakeholder mapping and analysis including identification of ethnic minorities in the area - Gender, Disability and Social Inclusion Analysis | Completed Planned |
|  |  |  |  |  | X | ESIA (Environmental and Social Impact Assessment), include mitigation measures such as: - Land ownership survey and due diligence process - Site assessment and feasibility studies - Potential impacts on biodiversity, soil, water resources, livelihoods, cultural, heritage, etc. - Landslide/flood risk assessment (soil, slope stability, hydrological flows, drainage patterns. etc.) - UXO risk - Pollutions (air quality, dust noise, traffic, etc.) | Planned |
|  |  |  |  |  | ☐ | SESA (Strategic Environmental and Social Assessment) |  |
|  | Are management plans required? (check if “yes) |  |  | ☐ |  |  |  |
|  | If yes, indicate overall type |  |  |  | X | Targeted management plans: Stakeholder Engagement Plan: - including communication/ information dissemination plan and Ingenious People Plan - GEDSI Action plan - Conflict Resolution Mechanism - Grievance Redress Mechanism | Planned |

|  |  |  | X | ESMP (Environmental and Social Management Plan) including a range of site-specific targeted plans, as follows: - Emergency response and recovery plan - Contract Labour Management Plan - Waste Management Plan - Resource Management Plan - Health and Safety Management Plan - Pollution Prevention plan - Erosion Management plan - Landslide mitigation plan - UXO Management/Clearance Plan - Traffic and Access Management Plan - Workers Code of Conduct (to include aspects pertaining to GBV related mitigation measures) - Worker Accommodation Plan (if required) - Cultural heritage Management plan (if required) | Planned |
| --- | --- | --- | --- | --- | --- |
|  |  |  | X | ESMF (Environmental and Social Management Framework) | (Before site identification) Planned |
|  | Based on identified risks, which Principles/Project- level Standards triggered? |  | Comments (not required) |  |  |
|  | Overarching Principle: Leave No One Behind |  |  |  |  |
|  | Human Rights | X |  |  |  |
|  | Gender Equality and Women’s Empowerment | X |  |  |  |
|  | Accountability | X |  |  |  |
|  | 1. Biodiversity Conservation and Sustainable Natural Resource Management | X |  |  |  |
|  | 2. Climate Change and Disaster Risks | X |  |  |  |
|  | 3. Community Health, Safety and Security | X |  |  |  |
|  | 4. Cultural Heritage | X |  |  |  |
|  | 5. Displacement and Resettlement | X |  |  |  |
|  | 6. Indigenous Peoples | X |  |  |  |
|  | 7. Labour and Working Conditions | X |  |  |  |
|  | 8. Pollution Prevention and Resource Efficiency | X |  |  |  |

Final Sign Off

Final Screening at the design-stage is not complete until the following signatures are included

| Signature | Date | Description |
| --- | --- | --- |
| QA Assessor |  |  |
| QA Approver |  | Deputy Resident Representative, UNDP Lao PDR |
| PAC Chair |  | Resident Representative, UNDP Lao PDR |

#### SESP Attachment 1. Social and Environmental Risk Screening Checklist

| Checklist Potential Social and Environmental Risks |  |  |
| --- | --- | --- |
| INSTRUCTIONS: The risk screening checklist will assist in answering Questions 2-6 of the Screening Template. Answers to the checklist questions help to (1) identify potential risks, (2) determine the overall risk categorization of the project, and (3) determine required level of assessment and management measures. Refer to the SES toolkit for further guidance on addressing screening questions. |  |  |
| Overarching Principle: Leave No One Behind Human Rights |  | Answer (Yes/No) |
| P.1 | Have local communities or individuals raised human rights concerns regarding the project (e.g. during the stakeholder engagement process, grievance processes, public statements)? | No |
| P.2 | Is there a risk that duty-bearers (e.g. government agencies) do not have the capacity to meet their obligations in the project? | No |
| P.3 | Is there a risk that rights-holders (e.g. project-affected persons) do not have the capacity to claim their rights? | Yes |
| Would the project potentially involve or lead to: |  |  |
| P.4 | adverse impacts on the enjoyment of the human rights (civil, political, economic, social or cultural) of the affected population and particularly of marginalized groups? | No |
| P.5 | inequitable or discriminatory impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups, including persons with disabilities? 16 | Yes |
| P.6 | restrictions in availability, quality of and/or access to resources or basic services, in particular to marginalized individuals or groups, including persons with disabilities? | No |
| P.7 | exacerbation of conflicts among and/or the risk of violence to project-affected communities and individuals? | Yes |
| Gender Equality and Women’s Empowerment |  |  |
| P.8 | Have women’s groups/leaders raised gender equality concerns regarding the project, (e.g. during the stakeholder engagement process, grievance processes, public statements)? | No |
| Would the project potentially involve or lead to: |  |  |
| P.9 | adverse impacts on gender equality and/or the situation of women and girls? | Yes |
| P.10 reproducing discriminations against women based on gender, especially regarding participation in design and implementation or access to opportunities and benefits? |  | Yes |
| P.11 limitations on women’s ability to use, develop and protect natural resources, taking into account different roles and positions of women and men in accessing environmental goods and services? For example, activities that could lead to natural resources degradation or depletion in communities who depend on these resources for their livelihoods and well being |  | No |
| P.12 exacerbation of risks of gender-based violence? For example, through the influx of workers to a community, changes in community and household power dynamics, increased exposure to unsafe public places and/or transport, etc. |  | Yes |

16 Prohibited grounds of discrimination include race, ethnicity, sex, age, language, disability, sexual orientation, gender identity, religion, political or other opinion, national or social or geographical origin, property, birth or other status including as an indigenous person or as a member of a minority. References to “women and men” or similar is understood to include women and men, boys and girls, and other groups discriminated against based on their gender identities, such as transgender and transsexual people.

| Sustainability and Resilience: Screening questions regarding risks associated with sustainability and resilience are encompassed by the Standard-specific questions below |  |
| --- | --- |
| Accountability |  |
| Would the project potentially involve or lead to: |  |
| P.13 exclusion of any potentially affected stakeholders, in particular marginalized groups and excluded individuals (including persons with disabilities), from fully participating in decisions that may affect them? | Yes |
| P.14 grievances or objections from potentially affected stakeholders? | Yes |
| P.15 risks of retaliation or reprisals against stakeholders who express concerns or grievances, or who seek to participate in or to obtain information on the project? | No |
| Project-Level Standards |  |
| Standard 1: Biodiversity Conservation and Sustainable Natural Resource Management |  |
| Would the project potentially involve or lead to: |  |
| 1.1 adverse impacts to habitats (e.g. modified, natural, and critical habitats) and/or ecosystems and ecosystem services? For example, through habitat loss, conversion or degradation, fragmentation, hydrological changes | Yes |
| 1.2 activities within or adjacent to critical habitats and/or environmentally sensitive areas, including (but not limited to) legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities? | No |
| 1.3 changes to the use of lands and resources that may have adverse impacts on habitats, ecosystems, and/or livelihoods? (Note: if restrictions and/or limitations of access to lands would apply, refer to Standard 5) | Yes |
| 1.4 risks to endangered species (e.g. reduction, encroachment on habitat)? | Yes |
| 1.5 exacerbation of illegal wildlife trade? | No |
| 1.6 introduction of invasive alien species? | No |
| 1.7 adverse impacts on soils? | Yes |
| 1.8 harvesting of natural forests, plantation development, or reforestation? | No |
| 1.9 significant agricultural production? | No |
| 1.10 animal husbandry or harvesting of fish populations or other aquatic species? | No |
| 1.11 significant extraction, diversion or containment of surface or ground water? For example, construction of dams, reservoirs, river basin developments, groundwater extraction | No |
| 1.12 handling or utilization of genetically modified organisms/living modified organisms?17 | No |
| 1.13 utilization of genetic resources? (e.g. collection and/or harvesting, commercial development)18 | No |
| 1.14 adverse transboundary or global environmental concerns? | No |
| Standard 2: Climate Change and Disaster Risks |  |
| Would the project potentially involve or lead to: |  |

17 See the Convention on Biological Diversity and its Cartagena Protocol on Biosafety.

18 See the Convention on Biological Diversity and its Nagoya Protocol on access and benefit sharing from use of genetic resources.

| 2.1 areas subject to hazards such as earthquakes, floods, landslides, severe winds, storm surges, tsunami or volcanic eruptions? | Yes |
| --- | --- |
| 2.2 outputs and outcomes sensitive or vulnerable to potential impacts of climate change or disasters? For example, through increased precipitation, drought, temperature, salinity, extreme events, earthquakes | Yes |
| 2.3 increases in vulnerability to climate change impacts or disaster risks now or in the future (also known as maladaptive or negative coping practices)? For example, changes to land use planning may encourage further development of floodplains, potentially increasing the population’s vulnerability to climate change, specifically flooding | No |
| 2.4 increases of greenhouse gas emissions, black carbon emissions or other drivers of climate change? | Yes |
| Standard 3: Community Health, Safety and Security |  |
| Would the project potentially involve or lead to: |  |
| 3.1 construction and/or infrastructure development (e.g. roads, buildings, dams)? (Note: the GEF does not finance projects that would involve the construction or rehabilitation of large or complex dams) | Yes |
| 3.2 air pollution, noise, vibration, traffic, injuries, physical hazards, poor surface water quality due to runoff, erosion, sanitation? | Yes |
| 3.3 harm or losses due to failure of structural elements of the project (e.g. collapse of buildings or infrastructure)? | Yes |
| 3.4 risks of water-borne or other vector-borne diseases (e.g. temporary breeding habitats), communicable and noncommunicable diseases, nutritional disorders, mental health? | Yes |
| 3.5 transport, storage, and use and/or disposal of hazardous or dangerous materials (e.g. explosives, fuel and other chemicals during construction and operation)? | No |
| 3.6 adverse impacts on ecosystems and ecosystem services relevant to communities’ health (e.g. food, surface water purification, natural buffers from flooding)? | No |
| 3.7 influx of project workers to project areas? | Yes |
| 3.8 engagement of security personnel to protect facilities and property or to support project activities? | Yes |
| Standard 4: Cultural Heritage |  |
| Would the project potentially involve or lead to: |  |
| 4.1 activities adjacent to or within a Cultural Heritage site? | Yes |
| 4.2 significant excavations, demolitions, movement of earth, flooding or other environmental changes? | No |
| 4.3 adverse impacts to sites, structures, or objects with historical, cultural, artistic, traditional or religious values or intangible forms of culture (e.g. knowledge, innovations, practices)? (Note: projects intended to protect and conserve Cultural Heritage may also have inadvertent adverse impacts) | Yes |
| 4.4 alterations to landscapes and natural features with cultural significance? | No |
| 4.5 utilization of tangible and/or intangible forms (e.g. practices, traditional knowledge) of Cultural Heritage for commercial or other purposes? | No |
| Standard 5: Displacement and Resettlement |  |
| Would the project potentially involve or lead to: |  |
| 5.1 temporary or permanent and full or partial physical displacement (including people without legally recognizable claims to land)? | No |

| 5.2 economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation)? | No |
| --- | --- |
| 5.3 risk of forced evictions?19 | No |
| 5.4 impacts on or changes to land tenure arrangements and/or community based property rights/customary rights to land, territories and/or resources? | Yes |
| Standard 6: Indigenous Peoples |  |
| Would the project potentially involve or lead to: |  |
| 6.1 areas where indigenous peoples are present (including project area of influence)? | Yes |
| 6.2 activities located on lands and territories claimed by indigenous peoples? | Yes |
| 6.3 impacts (positive or negative) to the human rights, lands, natural resources, territories, and traditional livelihoods of indigenous peoples (regardless of whether indigenous peoples possess the legal titles to such areas, whether the project is located within or outside of the lands and territories inhabited by the affected peoples, or whether the indigenous peoples are recognized as indigenous peoples by the country in question)? If the answer to screening question 6.3 is “yes”, then Standard 6 requirements apply, and the potential significance of risks related to impacts on indigenous peoples must be Moderate or above. * | Yes |
| 6.4 the absence of culturally appropriate consultations carried out with the objective of achieving FPIC on matters that may affect the rights and interests, lands, resources, territories and traditional livelihoods of the indigenous peoples concerned? | No |
| 6.5 the utilization and/or commercial development of natural resources on lands and territories claimed by indigenous peoples? | No |
| 6.6 forced eviction or the whole or partial physical or economic displacement of indigenous peoples, including through access restrictions to lands, territories, and resources? Consider, and where appropriate ensure, consistency with the answers under Standard 5 above | No |
| 6.7 adverse impacts on the development priorities of indigenous peoples as defined by them? | No |
| 6.8 risks to the physical and cultural survival of indigenous peoples? | No |
| 6.9 impacts on the Cultural Heritage of indigenous peoples, including through the commercialization or use of their traditional knowledge and practices? Consider, and where appropriate ensure, consistency with the answers under Standard 4 above. | No |
| Standard 7: Labour and Working Conditions |  |
| Would the project potentially involve or lead to: (note: applies to project and contractor workers) |  |
| 7.1 working conditions that do not meet national labour laws and international commitments? | Yes |
| 7.2 working conditions that may deny freedom of association and collective bargaining? | Yes |
| 7.3 use of child labour? | Yes |
| 7.4 use of forced labour? | Yes |
| 7.5 discriminatory working conditions and/or lack of equal opportunity? | Yes |
| 7.6 occupational health and safety risks due to physical, chemical, biological and psychosocial hazards (including violence and harassment) throughout the project life-cycle? | Yes |
| Standard 8: Pollution Prevention and Resource Efficiency |  |
| Would the project potentially involve or lead to: |  |
| 8.1 the release of pollutants to the environment due to routine or non-routine circumstances with the potential for adverse local, regional, and/or transboundary impacts? | Yes |
| 8.2 the generation of waste (both hazardous and non-hazardous)? | Yes |
| 8.3 the manufacture, trade, release, and/or use of hazardous materials and/or chemicals? | No |
| 8.4 the use of chemicals or materials subject to international bans or phase-outs? For example, DDT, PCBs and other chemicals listed in international conventions such as the Montreal Protocol, Minamata Convention, Basel Convention, Rotterdam Convention, Stockholm Convention | No |
| 8.5 the application of pesticides that may have a negative effect on the environment or human health? | No |
| 8.6 significant consumption of raw materials, energy, and/or water? | Yes |

- Risk Analysis. Use the standard Risk Register template. Please refer to the Deliverable Description of the Risk Register for instructions

| Portfolio/Project Title: | Portfolio/Project Number: | Date: Click or tap to enter a date. |
| --- | --- | --- |

| # | Event | Cause | Impact(s) | Risk Category and Sub-category (including Risk Appetite) | Impact, Likelihood & Risk Level (see Annex 3 Risk Matrix) | Risk Valid From/To | Risk Owner (individual team accountable for managing the risk) | Risk Treatment and Treatment Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | There is the risk that there will be no qualified construction company bidder | As a result of the limited domestic market and limited reach of procurement advertisement | Which will delay the construction work | 4. ORGANIZATIONAL (4.9. Procurement) - UNDP Risk Appetite: EXPLORATORY TO OPEN | Likelihood: 2 - Low likelihood Impact: 2 - Minor Risk level: LOW (equates to a risk appetite of MINIMAL) | From: 01-Jun-25 To: 31-Mar-27 | UNDP, Programme Analyst | Risk Treatment 1.1: Reaching out to the National Construction Association to inform them about this tender opportunity. Risk Treatment Owner: Project Manager Risk Treatment 1.2: Procurement unit to conduct market survey by issuing of an Expression of interest (EOI) to prequalify construction companies and mapping location capacities. Risk Owner: Project Manager |
| 2 | There is a risk that the contractor/service providers have limited capacity to deliver the assigned tasks (including construction) | As a result of the ambiguity in the advertised scope of work and poor management of contractors | Which will impact possible cost overrun | 4. ORGANIZATIONAL (4.9. Procurement) - UNDP Risk Appetite: EXPLORATORY TO OPEN | Likelihood: 4 - Highly likely Impact: 4 - Extensive Risk level: SUBSTANTIAL (equates to a risk appetite of OPEN) | From: 01-Jun-25 To: 31-Mar-27 | UNDP, Programme Analyst | Risk Treatment 2.1: High-quality Bill of Quality (BoQ), design drawings and structure designs are required. Should there be any questions or confusion, UNDP will ensure that the selected contractor/bidder raises the matters to UNDP in a timely manner. Risk Treatment Owner: Project Manager |
|  |  |  |  |  |  |  |  | Risk Treatment 2.2: Bidders will propose a detailed sequence of activities. UNDP will conduct a risk assessment of potential contractors before contracting (e.g., due diligence and post-qualification procedures). Risk Treatment Owner: Project Manager Risk Treatment 2.3: Performance assurance. The selected contractor will be required to submit a performance bond or a. In addition, retention money mechanism (percentage in accordance with UNDP rules and regulations) will be withheld from each payment. Risk Treatment Owner: Project Manager Risk Treatment 2.4: Safeguard Payment. The selected Contractor will receive payments based on the verification and certification of the engineer of work conducted. Poor quality deliverables will be rejected, and payment will be withheld until quality deliverables are submitted. Risk Treatment Owner: Project Manager Risk Treatment 2.5: Monitoring by an independent engineer. An independent engineer will be recruited by UNDP to provide continuous monitoring of the construction to ensure the quality and timely progress of the project. The engineer will sign a Declaration of Impartiality and Confidentiality. They will evaluate work in progress and will provide monthly progress reports of the construction project to UNDP. Risk Treatment Owner: Project Manager Risk Treatment 2.6: Conduct site visit checks to monitor progress and verify the quality of performance and results. Risk Treatment Owner: Project Manager |
| 3 | There is a risk of a delay in construction and retrofitting of the building. | As a result of unforeseen issues, including but not limited to natural disasters, the change of conditions of terrains and weather for construction, the delay in procuring contractors, and the delay in materials delivery, that impact the timeline of the implementation | Which will impact the timeline of project implementation and project closure | 3. OPERATIONAL (3.6. Transition and exit strategy) - UNDP Risk Appetite: EXPLORATORY TO OPEN | Likelihood: 3 - Moderately likely Impact: 3 - Intermediate Risk level: MODERATE (equates to a risk appetite of EXPLORATORY) | From: 01-Sep-25 To: 30-Jun-27 | UNDP, Programme Analyst | Risk Treatment 3.1: If unavoidable, an additional timeline shall be added. Additional months to the estimated construction periods shall be added in advance in case of unforeseen circumstances. It shall be emphasized in the contract between UNDP and Contractor. Contractor shall be asked to provide the timeline and the duration of the construction. Risk Treatment Owner: UNDP Procurement Team |
| 4 | There is a risk that there will be a cost overrun | As a result of several factors, including but not limited to the delay of the construction, inaccurate estimation, materials price fluctuation, shortage of skills and labors, and unforeseen site conditions, .etc. | This will impact the successful implementation of the project's set target and require additional funds to meet desirable outcomes. | 3. OPERATIONAL (3.6. Transition and exit strategy) - UNDP Risk Appetite: EXPLORATORY TO OPEN | Likelihood: 2 - Low likelihood Impact: 4 - Extensive Risk level: MODERATE (equates to a risk appetite of EXPLORATORY) | From: 01-Jun-25 To: 30-Jun-27 | UNDP, Programme Analyst | Risk Treatment 4.1: An independent consultant who is an expert in the field will develop a high-quality BOQ. The BOQ will be used to evaluate the bidder/contractor's offer. All estimated prices of the materials will be in USD, which will not be impacted by the fluctuating market prices. Risk Treatment Owner: Project Manager |
| 5 | SES Risk 5: There is the risk that Marginalized and vulnerable groups, including but not limited to women, ethnic minorities, and persons with disabilities, may be excluded from decision-making processes. | As a result of: limited capacity, accessibility barriers, and a lack of support or grievance mechanisms | Which will impact their needs begin neglected, leading to projects that do not effectively address the impact of disaster on these groups. It could also cause stakeholder dissatisfaction objections. | 1. SOCIAL AND ENVIRONMENTAL (1.3. Grievances (Accountability to stakeholders)) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 3 - Moderately likely Impact: 3 - Intermediate Risk level: MODERATE (equates to a risk appetite of EXPLORATORY) | From: 30-Nov-24 To: 30-Nov-27 | UNDP, Programme Analyst | Risk Treatment 5.1: The project shall develop and implement an inclusive communication strategy. This strategy will ensure that information is accessible in various formats, such as large printed signs with visuals, community-based channels for information dissemination, and audio resources. The project will identify and map out the accessible evacuation route. Risk Treatment Owner: Project Manager Risk Treatment 5.2: the project shall ensure inclusivity through its practices. The shelters will be equipped to accommodate people with disabilities, including accessible entrances, restrooms, and facilities. Risk Treatment Owner: Project Manager Risk Treatment 5.3: Evacuation drill training will be considered for people with disabilities as part of the project’s activities. Risk Treatment Owner: Project Manager Risk Treatment 5.4: The environmental and Social Management plan including number of counter measure/targeted MP – Stakeholder Engagement Plan (SEP) including the Communication and Information Dissemination Plan, Gender Equality and Social Inclusion Plan, and Indigenous People Planwill be developed and be implemented to ensure inclusivity and genuine equality for all people . Risk Treatment Owner: Project Manager Risk Treatment 5.5: To prevent sexual harassment, abuse, and any related gender-based violence, the procurement team will communicate with the contractor to establish a code of conduct for sexual harassment and gender-based violence. The procurement clauses and contract will include the code of conduct and appropriate policies. The contractor must also set up transparent reporting and response mechanisms for incidents. Risk Treatment Owner: Project Manager Risk Treatment 5.6: An internal grievances redress mechanism will be established within the team and communicated to all staff. This information will also be shared with the local communities. Risk Treatment Owner: Project Manager |
| 6 | SES Risk: There is a risk of violence, harassment, and gender-based violence (GBV), particularly in the context of construction and facility protection activities. | Due to the risk may be exacerbated by the influx of workers (construction workers, security personnel and personnels) – especially in male-dominated sectors – into local communities. | which may increase the risk of sexual exploitation, abuse, and harassment, particularly affecting women and girls. It could result in leading to harm against women and girls and damage to the project's reputation and community trust. | 1. SOCIAL AND ENVIRONMENTAL (1.2. Gender equality and women’s empowerment) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 4 - Highly likely Impact: 2 - Minor Risk level: MODERATE (equates to a risk appetite of EXPLORATORY) | From: 30-Nov-24 To: 30-Nov-27 | UNDP, Programme Analyst | Risk Treatment 6.1: The workers, including contraactors and security personnel, will be required to sign a Code of Conduct that strictly prohibits any form of GBV or sexual exploitation, abuse, and harassment (SEAH). This will accompany by mandatories training session to raise awareness about the GBV risks promote respectful behavior, and inform all personnel of appropriate reporting protocol/lines. Risk Treatment Owner: Project Manager Risk Treatment 6.2: Procurement team will provide support in integrating any relevant safeguard clauses address GBV and SEAH in all contractual agreements with partners and contractors. These clauses will require partners to take proactive measures, including gender-sensitive supervision on worksites. The contractor or site supervisor under the guidance of the Project Manager and Safeguards Specialist, will ensure compliance on the ground. Risk Treatment Owner: Project Manager Risk Treatment 6.3: The project will establish the GRM mechanism allowing lines for reporting should there be any incidents or attempts. The project team responsible for communicating the communication means to the local community. Risk Treatment Owner: Project Manager |
| 7 | SES Risk: There is a risk of structural and infrastructure failures. S. 2.1, S. 3.2, 3.3 | As a result of the area’s vulnerability to floods and landslides. | Which will impact in causing harm and death to workers and the beneficiaries, and affect the outcomes of the project. | 1. SOCIAL AND ENVIRONMENTAL (1.6. Community health, safety and security) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 3 - Moderately likely Impact: 4 - Extensive Risk level: SUBSTANTIAL (equates to a risk appetite of OPEN) | From: 01-Sep-25 To: 30-Jun-27 | UNDP, Programme Analyst | Risk Treatment 7.1: The project will conduct the site assessment and feasibility studies to determine suitable sites for the construction of the evacuation shelter. The project will conduct the Environmental and Social Management Framework (ESMF) to outline how the Social and Environmental Standard (SES) will be applied during screening and site assessment. The Environmental and Social Impact Assessment (ESIA) will be conducted following the site assessment to assess the risks and impacts of the identified/proposed sites. The ESIA is to evaluate potential risks and impacts such as: Slope instability (due to vegetation clearance), landslide risk from the disturbed topography, drainage system that could contribute to the landslide/flood risk, community access route and any other physical hazards, such as those associated with UXO. Based on the assessment, the project will also develop an Environmental and Social Management Plan (ESMP) for each site to manage risks and mitigate impacts during project implementation and construction activities. Those include and not limited to: - The disaster response or emergency response plan - Surface water management, including drainage planning to reduce flood and landslide risk - Soil management plan outlining measures to prevent movement, erosion sedimentation of excavated soil. - Monitoring plan for the regular site inspections to monitor soil movement or instability. The project will ensure comprehensive UXO clearance and secure official work to mitigate this hazard. To ensure that, the UXO Clearance Plan will also be prepared for the Management Plan (MP). Risk Treatment Owner: Project Manager |
| 8 | SES Risk: There is a risk of GHG emission, noise generation, and pollutants, including wastes and physical hazard, being released into the local communities and the surrounding environment. S. 3.1, 8.1, 8.2 | As a result of the presence of the construction activities and facilities set up to support the construction activities and workers in the communities. | Which will impact in health, safety and the well-being of the people in the communities and the surrounding environment. | 1. SOCIAL AND ENVIRONMENTAL (1.6. Community health, safety and security) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 3 - Moderately likely Impact: 3 - Intermediate Risk level: MODERATE (equates to a risk appetite of EXPLORATORY) | From: 01-Sep-25 To: 30-Jun-27 | UNDP, Programme Analyst | Risk Treatment 8.1: The contractor will be required to arrange the working and the curfew time in the morning and in the evening. The contractor will be required to have the policies the on health and safety, taking into consideration danger aspects of the construction activities to the workers and the people in community surrounding the site. Those include but not limited to heavy vehicles route and alarms, danger barrier and traffic management, dust and water sprinkling activities, and other essential issues. Risk Treatment Owner: Project Manager Risk Treatment 8.2: The project will identify any potential pollution from project activities, especially from construction activities, that could impact the environment and the well-being of the people in the community. The ESMP and CESMP will further map out a management plan and strategy responding to the identified risks and impacts. Risk Treatment Owner: Project Manager Risk Treatment 8.3 UNDP will also hire a National Consultant for field assistance who will monitor the progress of the work, the site preparation and installation of the equipment, ensuring minimal possible impact on the well-being and the environment surrounding the community. S/He role is also to ensure the mitigation of this risk. Risk Treatment Owner: Project Manager |
| 9 | SES Risk: There is a risk that the local resources will be strained, and social tension will be heightened. S. 3.7, 3.8 | As a result of the influx of construction workers in the local communities. | This will cause potential conflicts and violence, further complicating the project’s implementation. | 1. SOCIAL AND ENVIRONMENTAL (1.6. Community health, safety and security) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 3 - Moderately likely Impact: 3 - Intermediate Risk level: MODERATE (equates to a risk appetite of EXPLORATORY) | From: 01-Sep-25 To: 30-Jun-27 | UNDP, Programme Analyst | Risk Treatment 9.1: The contractor shall inform the project management team if they plan to hire workers from outside the local community. Risk Treatment Owner: Project Manager Risk Treatment 9.2: The project shall engage with local communities early, ensuring clear communication and equitable resource distribution. Security measures, and conflict resolution mechanisms will be in place to address any disputes that arise. Risk Treatment Owner: Project Manager |
| 10 | SES Risk: There is a risk of ownership disputes or access to the terrains for construction. S. 5.4, S4.3, 6.3 | As a result of the use of land for construction activities. | Which will impact in the delay or/and the implementation of project. | 1. SOCIAL AND ENVIRONMENTAL (1.8. Displacement and resettlement) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 1 - Not likely Impact: 3 - Intermediate Risk level: LOW (equates to a risk appetite of CAUTIOUS) | From: 01-Jun-25 To: 30-Jun-27 | UNDP, Programme Analyst | Risk Treatment 10.1: The project shall conduct thorough land due diligence to verify ownership and ensure a clear title before beginning. Ensure transparent engagement with local communities and landowners regarding any potential disputes. Legal agreements shall be secured to formalize access rights. Additionally, a conflict resolution mechanism should be established to handle disputes efficiently, and contingency plans should be developed to identify alternative routes or sites if access issues cannot be resolved promptly. Risk Treatment Owner: Project Manager |
| 11 | SES Risk: During the project's implementation, there is a risk of a potential violation of national labour laws and international standards. S. 3.3, 7.1, 7.3, 7.5, 7.6 | As a result of - the use child labour in construction works. - Insufficient health and safety measures, including protection gears for the construction activities. | Which will lead to the use of child labour and any potential acts against the national labour law and international standards during the construction activities, and causing injuries and fatalities during the construction activities | 1. SOCIAL AND ENVIRONMENTAL (1.10. Labour and working conditions) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 3 - Moderately likely Impact: 3 - Intermediate Risk level: MODERATE (equates to a risk appetite of EXPLORATORY) | From: 01-Sep-25 To: 30-Jun-27 | UNDP, Programme Analyst | Risk Treatment 11.1: The project will ensure that child labour is not used during its implementation through close oversight of the project site. It will also be included in the procurement clauses and in the contract to ensure that the contractors are aware of the appreciation policies on this issue. The procurement team will further communicate with contractors on the code of conduct against the use of child labour. The contractor shall also be briefed and expected to have the following arrangements in place before the construction activities: - All staff have their age verified through Identity Cards or family book - Staff records are on site and ready for inspection. - Staff bank account details or wage details are recorded and maintained. Risk Treatment Owner: Project Manager Risk Treatment 11.2: The project requires the clauses mentioned in procurement and contracts that require the contractor to have the occupational health and safety procedure in place before the commencement of the work. Those should also include the availability of protective gear and the installation of fall prevention infrastructure, including guard rails and devices, including lifelines and harnesses. Risk Treatment Owner: Project Manager Risk Treatment 11.3: Risk Management Practices and Plans are expected from the contractors prior to the commencement of the construction activities, including: - Emergency response and recovery plan - Contract Labour Management Plan - Design route and system, including alarm system for heavy vehicles and machinery - Structure designs of the shelters Risk Treatment Owner: Project Manager Risk Treatment 11.4: After the completion of the construction, an individual consultant should inspect the integrity of the structure to ensure the safety of the building structure, which is to be subsequently reviewed and approved by UNDP. Risk Treatment Owner: Project Manager Risk Treatment 11.5: A grievances redress mechanism will also be established internally in their team and communicated to all staff. This information will also be disseminated to the local communities. Risk Treatment Owner: Project Manager |
| 12 | SES Risk: There is the risk of the loss or fragmentation of natural habitats | As the result of the construction of the Evacuation Shelter might require the clearance of vegetation and land preparation for building. | This could result disruption of local biodiversity and wildlife movement, soil erosion, reduced soil fertility, and a decrease in ecosystem services such as water regulation. | 1. SOCIAL AND ENVIRONMENTAL (1.4. Biodiversity conservation and sustainable natural resource management) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 3 - Moderately likely Impact: 3 - Intermediate Risk level: MODERATE (equates to a risk appetite of EXPLORATORY) | From: 01-Jan-26 To: 31-Jul-27 | UNDP, Programme Analyst | Risk Treatment 12.1: The project will conduct site-specific Environmental and Social Impacts Assessments (ESIAs) to identify ecologically sensitive areas, assess soil stability, and evaluate potential impacts on biodiversity and ecosystem services. Appropriate measures to mitigate any identified risks will be included in the site-specific ESMPs. The project will ensure the minimal and selective removal of vegetation on land, prioritizing the preservation of critical natural habitats and mature tree cover wherever possible. The project will approach sloped terrains with caution; if removal is unavoidable, different measures such as terracing, retaining walls, slope stabilization, and erosion control systems will be adopted to prevent any risk (landslide prevention and structural failure risk mentioned above with mitigation measures). Risk Treatment Owner: Project Manager |
| 13 | SES Risk: There is a risk of transmission of communicable diseases, including measles, influenza, Covid-19, and other respiratory or contact-based illnesses. | As the result of the lack of proper consideration to space, ventilation, and hygiene or sanitation facilities. In the event of a disaster, evacuation shelters may become overcrowded and serve as temporary living spaces for extended periods. | It will result in the increase, affecting people within the shelter and beyond, particularly vulnerable groups such as children, the elderly, or individuals with compromised immune systems. | 1. SOCIAL AND ENVIRONMENTAL (1.6. Community health, safety and security) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 3 - Moderately likely Impact: 3 - Intermediate Risk level: MODERATE (equates to a risk appetite of EXPLORATORY) | From: 01-Jul-25 To: 31-Jul-27 | UNDP, Programme Analyst | Risk Treatment 13.1: The project will incorporate preventive public health measures in both the design and operation of the evacuation shelter. Each shelter requires a designated isolation area to temporarily separate and care for individuals with symptoms of infectious illness, helping to prevent outbreaks in crowded conditions. The shelter will be designed with optimal natural ventilation – cross-ventilation layouts and high ceilings with appropriate air purification systems or fans installed to improve indoor air quality. The shelter will be equipped with adequate sanitation and hygiene infrastructure, including a clean water supply, gender-sensitive and accessible toilets, and a handwashing station. Risk Treatment Owner: Project Manager |

- Project Board Terms of Reference and TORs of key management positions.

- Background

All UNDP projects must be governed by a multi-stakeholder board or committee established to review performance based on established monitoring and evaluation metrics and high-level implementation issues to ensure quality delivery of results. For the purpose of this ToR and to ensure standardization, henceforth, as regards project documentation, such a body shall only be referred to by one of two names: ‘Project Board’ or ‘Project Steering Committee.’ The Project Board is the most senior, dedicated oversight body for a UNDP ‘Development Project’, which is defined in the PPM as an instrument where UNDP “Delivers outputs where UNDP has accountability for design, oversight and quality assurance of the entire project.”

- Duties and Responsibilities

The two prominent (mandatory) roles of the Project Board are as follows:

- High-level oversight of the project (as explained in the “Provide Oversight” section of the PPM). This is the primary function of the Project Board. The Project Board reviews evidence of project performance based on monitoring, evaluation and reporting, including progress reports, monitoring missions' reports, evaluations, risk logs, quality assessments, and the combined delivery report. The Project Board is the main body responsible for taking corrective actions as needed to ensure the project achieves the desired results. And its function includes oversight of annual (and as-needed) assessments of any major risks to the programme or project, and related decisions/agreements on any management actions or remedial measures to address them effectively.

The Project Board also carries the role of quality assurance of the project taking decisions informed by, among other inputs, the project quality assessment. In this role the Board is supported by the quality assurer, whose function is to assess the quality of the project against the corporate standard criteria. This function is performed by a UNDP programme or monitoring and evaluation officer to maintain independence from the project manager regardless of the project ‘s implementation modality.

The Project Board reviews updates to the project risk log.

- Approval of key project execution decisions (as explained in the “Manage Change” section of the PPM). The Project Board has an equally important, secondary role in approving certain adjustments above provided tolerance levels, including substantive programmatic revisions (major/minor amendments), budget revisions, requests for suspension or extension and other major changes (subject to additional funding partner/donor requirements).

The Project Board is responsible for making management decisions by consensus when required, including the approval of project plans and revisions, and the project manager’s tolerances. The Project Board approves annual work plans and reviews updates to the project risk log.

Within the overall governance and management arrangements of the project, the role of the Project Board as regards these two key functions (‘High-level oversight of the project’ and ‘Approval of key project execution decisions’) is distinct from the roles of entities involved in the implementation of the project, namely the implementing partner (IP), responsibilities parties (if applicable), service providers and project staff.

The diagram below outlines the main entities involved (and their respective responsibilities) in the ‘oversight/approval of key execution decisions’ layer and the ‘implementation’ layer of the project structure.

Diagram 1 – Standard Figure of Project Organization Structure vis-à-vis oversight & approval and implementation roles

In order to ensure UNDP’s ultimate accountability, the Project Board decisions should be made in accordance with the Quality Standards for Programming that shall ensure management for development results, best value money, fairness, integrity, transparency and effective national and international competition. An effective Project Board needs credible data, evidence, quality assurance and reporting to aid decision making (see next section on supporting functions to the Board). The Project Board also needs to be accountable to protect against conflicts of interest and fraud.

Specific responsibilities of the Project Board include the following:

- Provide overall guidance and direction to the project, ensuring it remains within any specified constraints, and promote gender equality and social inclusion (LNOB) in the project implementation;

- Review project performance based on monitoring, evaluation and reporting, including standard quality assurance checks, progress reports, risk logs, spot checks/audit reports and the combined delivery report;

- Address any high-level project issues as raised by the project manager and project assurance;

- Provide guidance on emerging and/or pressing project risks and agree on possible mitigation and management actions to address specific risks (including ensuring compliance with UNDP’s Social and Environmental Standards, Fraud/corruption, Sexual Exploitation and Abuse and Sexual Harassment);

- Agree or decide on project manager’s tolerances as required, within the parameters set by UNDP (Manage Change in the PPM) and the donor, and provide direction and decisions for exceptional situations when the project manager’s tolerances are exceeded;

- Advise on major and minor amendments to the project within the parameters set by UNDP and the donor;

- Agree or decide on a project suspension or cancellation, if required; (note that for GEF and GCF projects it is UNDP that decides to suspend or cancel and project and the Project Board is informed/consulted only).

- Provide high-level direction and recommendations to the project management unit to ensure that the agreed deliverables are produced satisfactorily according to plans.

- Receive and address project level grievance, including overseeing whatever specific compliance and stakeholder response (or grievance) mechanisms have been put in place so that individuals and communities potentially affected by the project have access to effective mechanisms and procedures for raising concerns about the social and environmental performance of the project.

- Engage in the low value grant selection process where there is no Grant Selection Committee, as guided by the Low Value Grants – UNDP Operational Guide.

Note: Specific requirements may apply for donor-funded projects, such as GEF- or GCF-financed projects. Please refer to the provisions in the project document.

Additional responsibilities of the Project Board can include, but are not limited to, the following:

- Ensure coordination between the various donors and government-funded projects and programmes;

- Report to relevant inter-ministerial bodies or higher-level oversight bodies;

- Ensure coordination with multiple government agencies and their participation in project activities;

- Appraise the annual project implementation report, including the quality assessment rating report;

- Review the final project report package during an end-of-project review meeting to discuss lessons learned and opportunities for scaling up.

- Composition of the Project Board

As noted in the diagram below, every Project Board in a UNDP project has three categories of formal members (e.g. voting members). The role of every formal Project Board member must correspond to one of these three roles and be identified accordingly in the project documentation.

Diagram 2 – Standard Figure for a Project Organization Structure

The three categories of Project Board members are the following:

1). Project Director/Executive(s): This is an individual(s) who represents ownership of the project and chairs (or co-chairs) the Project Board. The executive usually is the most senior national counterpart for nationally implemented projects (typically from the same entity as the Implementing Partner), and it must be UNDP for projects that are direct implementation (DIM). In exceptional cases, two individuals from different entities can co-share this role and/or co-chair the Project Board. If the project executive co-chairs the Project Board with a representative of another category, it typically does so with a development partner representative. The Project Executive is:  Resident Representative of UNDP Lao PDR.

- Beneficiary Representative(s): This is an individual(s) representing the interests of those groups of stakeholders who will ultimately benefit from the project. Their primary function within the Board is to ensure the realization of project results from the perspective of project beneficiaries. Often representatives from civil society, industry associations, community groups or other government entities benefiting from the project can fulfil this role. If the project has a specific geographic focus, often representatives from the government entities in the targeted area/region will play this role. There can be multiple beneficiary representatives in a Project Board. The Beneficiary Representative(s) is: Ministry of Planning and Investment (MPI), Ministry of Labour and Social Welfare (MOLSW), Ministry of Public Work (MPW), Ministry of Education and Sport (MOES), and Ministry of Natural Resources and Environment (MONRE). ​

- Development Partner(s): Individuals representing the interests of the parties concerned that provide funding, strategic guidance and/or technical expertise to the project. There can be multiple development partners representatives in a Project Board. The Development Partner(s) representative(s) is: Embassy of Japan to Lao PDR.

A UNDP representative must always be represented in the Project Board in either the project executive or development partner role.

Where applicable, representatives from responsible parties to the project cannot sit on the Project Board as a formal voting member; they can (if requested) attend board meetings as observers. Since the chief responsibility of the Board is to provide high-level oversight of project implementation, to avoid any conflicts of interest, it is not appropriate for representatives of third party entities engaged by the project to provide services – whether responsible parties or contractors/service providers – to concurrently sit on the Board. Representatives of responsible parties can attend board meetings (as observers) but can have no official role in board decision-making. The same principle applies to the project manager who in attending and presenting at board meetings, does so in a non-voting capacity.

In cases where the inputs and guidance of responsible parties or other entities formally engaged in providing goods or services to the project are needed by the Board on a recurring basis, it is recommended to establish appropriate advisory or technical committees or working groups composed of those entities that can formally report to the Board, while ensuring the impartiality and integrity of board decisions happening independent of those bodies (see Section V of the ToR).

- Standard Project Board Protocols

The Project Board must meet at least once a year. It is recommended that the timing of board meetings be agreed upon in advance and correspond to key project reporting or work planning milestones. This Project Board will meet once per year, according to the provisional schedule.

Project Board members cannot receive remuneration from project funds for their participation in the Board. However, it is allowable for board members to be reimbursed from project funds for certain reasonable, qualified expenses related to travel or lodging to attend board meetings. Such protocols are outlined in this ToR, and the benefits apply to all eligible board members.

All Project Boards must have rules for quorum and documentation/minuting of board decisions. All board decisions and minutes should be kept by the project management unit and UNDP. Guidelines on decisions taken in between board meetings or virtually should be clearly elaborated in the Terms of Reference (ToR) of the Project Board.

Unless otherwise specified, Project Board decisions are made by unanimous consensus. If a consensus cannot be reached within the Board, the final decision shall rest with the UNDP representative on the Project Board or a UNDP staff member with delegated authority as the programme manager.

It is required that as per internationally recognized professional standards and principles of sound governance, conflicts of interest affecting board members in performing their duties must be formally disclosed if not avoidable. Where a board member has a specific personal conflict of interest with a given matter before the board, he/she must recuse oneself from their participation in a decision. No board member can vote or deliberate on a question in which he/she has a direct personal or pecuniary interest not common to other members of the board.

All board members should be presented with a ToR for the Project Board, which will include the responsibilities already outlined and indicate agreed board practices and logistics.

Note: Designated Board members must sign or otherwise indicate written acceptance of the final ToR (via formal signature of the ToR, an exchange of letters or e-mail acknowledgment) for the Project Board as a precondition for serving on the Project Board. Please see Annex A for possible options to codify this acceptance (which preferably would be done at the appraise and approve stage but which could also be done early in implementation). The formal written acceptance of the ToR by all board members will be documented and kept by UNDP.

- Standard Outputs of Project Board Meetings

In its oversight function, the Project Board will (at a minimum) review and assess the following project-related evidence at each meeting:

- Assessment of project progress to date against project output indicators (as documented in the project document results framework)

- Approval/review of annual work plans

- Assessment of the relevant Monitoring & Evaluation mechanisms, including all evaluations

- Review and assessment of the Project Risk Log (with updating/amendments as needed)

- Assessment of project spending, based on a review of the combined delivery report

- Review of required resources versus available funding (if applicabel) and steps taken to reduce funding gap identified at the project design stage

This will be in addition to the review and approval of any required project execution decisions.

The output of every Project Board should be a written record (minutes) that captures the agenda and issues discussed and the agreed upon action items and decisions (if applicable). Each report should clearly document the members attending the meeting (as well as all participants in the meeting) and the modality used to agree on a certain action or decision (whether formal voting or no-objection or other mechanism). All records of board meetings should be documented and kept by UNDP in their quality assurance function (see next section).

- Support Functions to the Project Board

There are two main entities/functions outside the Project Board structure whose role is to report to the Project Board and support board members in effectively fulfilling their roles: project assurance and project management.

The diagram below explains the primary role of these two entities in the context of their support to Board operations.

Diagram 3 – Standard Figure of Project Organization Structure – Board Support Entities

Project Assurance: Project assurance is the responsibility of each Project Board member; however, UNDP has a distinct assurance role for all UNDP projects in carrying out objective and independent project oversight and monitoring functions. UNDP performs quality assurance and supports the Project Board (and Project Management Unit) by carrying out objective and independent project oversight and monitoring functions, including applying UNDP’s social and environmental management system to ensure the SES are applied through the project cycle. The Project Board cannot delegate any of its quality assurance responsibilities to the project manager. Project assurance is totally independent of project execution.

A designated representative of UNDP playing the project assurance role is expected to attend all Project Board meetings and support board processes as a non-voting representative. It should be noted that while in certain cases, UNDP’s project assurance role across the project may encompass activities happening at several levels (e.g. global, regional), at least one UNDP representative playing that function must, as part of their duties, specifically attend board meetings and provide board members with the required documentation required to perform their duties.

The UNDP representative playing the main project assurance function is: Head of Unit and Team leader of the NRM, CC & DRR unit.

Project Support, this function is often covered by the Project Management Unit: The Project Manager (PM) (also called project coordinator) is the senior most representative of the Project Management Unit (PMU) and is responsible for the overall management of the project on behalf of the Implementing Partner, including the mobilization of all project inputs, supervision over project staff, responsible parties, consultants and sub-contractors. The project manager typically presents key deliverables and documents to the Board for review and approval, including progress reports, annual work plans, adjustments to tolerance levels and risk logs.

A designated representative of the PMU is expected to attend all board meetings and present the required progress reports and other documentation as a non-voting representative to support board processes.

The primary PMU representative attending board meetings is: Project Manager.

The Gender Marker measures how much a project invests in gender equality and women’s empowerment. Select one for each output: GEN3 (Gender equality as a principle objective); GEN2 (Gender equality as a significant objective); GEN1 (Limited contribution to gender equality); GEN0 (No contribution to gender quality)

Note: Adjust signatures as needed

Nature (2023). Flood exposure and poverty in 188 countries.

Lao National Unexploded Ordnance Programme (UXO Lao), Impact of the UXO Problem in Lao PDR

https://lao.unfpa.org/en/publications/results-population-and-housing-census-2015-english-version

World Bank (2024), Lao Economic Monitor, April 2024: Accelerating Reforms for Growth: Key Findings

https://adaptation-platform.nies.go.jp/en/index.html

https://jprsi.go.jp/en

UNDP publishes its project information (indicators, baselines, targets and results) to meet the International Aid Transparency Initiative (IATI) standards.  Make sure that indicators are S.M.A.R.T. (Specific, Measurable, Attainable, Relevant and Time-bound), provide accurate baselines and targets underpinned by reliable evidence and data, and avoid acronyms so that external audience clearly understand the results of the project.

It is recommended that projects use output indicators from the Strategic Plan IRRF, as relevant, in addition to project-specific results indicators. Indicators should be disaggregated by sex or for other targeted groups where relevant.

Cost definitions and classifications for programme and development effectiveness costs to be charged to the project are defined in the Executive Board decision DP/2010/32

Changes to a project budget affecting the scope (outputs), completion date, or total estimated project costs require a formal budget revision that must be signed by the project board. In other cases, the UNDP programme manager alone may sign the revision provided the other signatories have no objection. This procedure may be applied for example when the purpose of the revision is only to re-phase activities among years.

To be used where UNDP is the Implementing Partner

To be used where the UN, a UN fund/programme or a specialized agency is the Implementing Partner

https://lao.unfpa.org/en/publications/results-population-and-housing-census-2015-english-version

***Note: revised July 2022 modifying presumption of risk significance from Substantial or higher to Moderate or higher.

The responsibilities of the board in this regard should follow UNDP’s Social and Environmental Standards (SES) as codified in the PPM. It should be noted that while a project board can play a role in addressing or assisting with the compliance and stakeholder response (or grievance) mechanisms put in in place for a given project (as part of their quality assurance and oversight function), this will be in addition to and does not substitute for UNDP’s core responsibility to ensure compliance with the SES throughout the project management cycle as part of UNDP’s Programming Quality Assurance system.

With the exception of responsible parties or any firms/entities engaged by the project to provide technical expertise with project funds

UNDP has this special right since the ultimate legal and fiduciary accountability for a UNDP project, irrespective of modality, rests with UNDP and UNDP must (in line with its obligations to donors and to the Executive Board) be able to ensure that no action is taken by any body in a UNDP project that contravenes UNDP rules and regulations.

Including audit reports and spot checks.