Country Results Report

The Biodiversity Finance Initiative (BIOFIN) programme in the Kyrgyz Republic

REPORTING PERIOD: January to December 2025

December, 2025

BIOFIN COUNTRY PROGRAMME

W: https://www.biofin.org/index.php/[Kyrgyzstan

BIOFIN COUNTRY PROGRAMME PROFILE

Country: the Kyrgyz Republic (KR)

Geographic coverage: Country-wide

Programme period (as funded by Phase II/Phase II Extended funds): 2019-2030

Budget (from Phase II/Phase II Extended funds): USD 2,242,865

Alignment with United National Development Program (UNDP) country programme strategic outcomes: Country program document for the Kyrgyz Republic (2023-2027): COOPERATION FRAMEWORK (OR EQUIVALENT) OUTCOME INVOLVING UNDP 3: By 2027, the Kyrgyz Republic started the transition to low-carbon development and risk informed climate resilience, contributing to people’s fair and equitable access to ecosystem benefits and to empowerment of vulnerable communities in the governance of natural resources and disaster prevention.

The Biodiversity Finance Initiative (BIOFIN) programme team in the Kyrgyz Republic would like to thank our partners – namely, the Governments of Germany, Switzerland, United Kingdom and the European Union (EU) – for their support in making the implementation of BIOFIN in the Kyrgyz Republic possible.

This report is collaboratively authored by members of the programme team, with support from the BIOFIN global programme management team.

- Table of Contents

Table of Contents	1

Abbreviations and Acronyms	3

Executive summary	4

A.	Country factsheet: the country’s biodiversity finance profile and the programming approach	11

A.1.	Biodiversity finance profile	11

A.2.	National implementation context	13

B.	Overview of key results	14

B.1.	FS 1 «Establishment of the Biodiversity Conservation Trust Fund»	14

B.1.1.	Activities and results related to output areas	15

B.2.	FS 2 « Reforming harmful agricultural subsidies to remove barriers to green/organic agriculture», FS 9 “Introduction of monitoring and evaluation practices for subsidy effectiveness in Kyrgyzstan with a focus on potentially harmful to biodiversity subsidies”	16

B.2.1.	Activities and results related to output areas	17

B.3.	FS 3 « Improving the procedures of budget formulation and execution of protected areas and forestry enterprises», FS 4 “Scaling up the adoption of performance programme-based budgeting in Protected Areas” and FS 5 “Scaling up of the Financial Solutions No. 3 and 4”	19

B.3.1.	Activities and results related to output areas	20

B.4.	FS 6 «Debt-for-Nature Swap in the Kyrgyz Republic»	21

B.4.1.	Activities and results related to output areas	21

B.5.	FS 7 “Introduction of an effective system of financial self-sufficiency in protected areas (PAs)	22

B.5.1.	Activities and results related to output areas	22

B.6.	FS 8: Digitalization of rental payments for leasing forest plots	25

B.6.1.	Activities and results related to output areas	25

B.7.	FS 10: Integrating environmental considerations into the financial sector	27

B.7.1.	Activities and results related to output areas	27

C.	Lessons learned and adaptive measures:	28

D.	Risks	28

D.1.	Programmatic risks (risks to the programme)	28

D.2.	Social and environmental risks (of the programme)	29

List of annexes and related notes	29

Annex 1: Indicator Tracking Table (in Excel)	29

- Abbreviations and Acronyms

| AIS | Automated Information System |
| --- | --- |
| BFP | Biodiversity Finance Plan |
| BIOFIN | Biodiversity Finance Initiative |
| BER | Biodiversity Expenditure Review |
| BMZ | German Federal Ministry for Economic Cooperation and Development |
| COP | Conference of the Parties |
| CTF | Conservation Trust Fund |
| DBCPA | Department for Biodiversity Conservation and Protected Areas |
| DfNS | Debt-for-Nature Swap |
| EU | European Union |
| ESG | Environment, Social and Governance |
| FS | Financial Solution |
| FS | Forest Service |
| FNA | Financial Needs Assessment |
| FE | Forestry Enterprise |
| KGS | Kyrgyzstan Som |
| KR | Kyrgyz Republic |
| MPTF | Multi-Partner Trust Fund |
| M&E | Monitoring and Evaluation |
| NBKR | National Bank of the Kyrgyz Republic |
| NGO | Non-Governmental Organization |
| NBSAP | National Biodiversity Strategy and Action Plan |
| PA | Protected Area |
| PIR | Policy and Institutional Review |
| RBB | Results-Based Budgeting |
| SESP | Social and Environmental Sustainability Programming |
| ToC | Theory of Change |
| ToR | Terms of Reference |
| UK | United Kingdom |
| UN | United Nations |
| UNDP | United Nations Development Programme |
| USD | United States Dollar |

- Executive summary

Progress toward targeted results

Finance solution 1: Establish Biodiversity Conservation Trust Fund (CTF) as a new mechanism for the resource mobilization

The establishment of the Biodiversity Conservation Trust Fund (CTF) is a flagship financial solution designed to address the critical funding gap in biodiversity conservation in Kyrgyzstan, as identified by the Biodiversity Finance Policy and Institutional Review (PIR), Biodiversity Expenditure Review (BER), and Biodiversity Financial Needs Assessment (FNA). With financing gap of approximately USD 55 million against the total estimated needs of 184 million USD for the new National Biodiversity Strategy and Action Plan (NBSAP) for 2025-2030 implementation (currently is under approval process), and continued underfunding from public, donor, and private sectors, the CTF aims to mobilize additional, sustainable financing for priority biodiversity initiatives. The updated NBSAP will form the programmatic foundation for the Fund.

In 2023, a feasibility study evaluated various models for establishing CTF, including domestic and international options. Due to legal and procedural barriers associated with national models, UNDP proposed leveraging the UN Multi-Partner Trust Fund (MPTF) mechanism as a practical interim solution. The concept was presented at a high-level roundtable in 2024 with wide participation from government agencies, diplomatic missions, UN entities, and development partners.

Following the multi-stakeholder support, the development of the foundational documents for the CTF—comprising the Terms of Reference (ToR) and Operations Manual have been initiated in 2024.

During the reporting period, the foundational documents were completed, including:

- the CTF Terms of Reference defining objectives, governance, and programmatic focus;

- a comprehensive Operations Manual, establishing transparent procedures for fund management, project selection, and oversight.

As the UN Multi-Partner Trust Fund (MPTF) model requires that the Conservation Trust Fund (CTF) be established by at least two UN agencies, a key institutional milestone was achieved through the formalization of a joint UN partnership model, with UNDP, UNEP, FAO, and WFP confirmed as UN co-founding partners under the leadership of the UN Resident Coordinator. This multi-agency arrangement ensures coherent, multisectoral support for biodiversity conservation.

To operationalize fundraising efforts, a CTF Outreach Plan was developed. The structured engagement with senior government counterparts resulted in confirmation that the Government of the Kyrgyz Republic is considering a financial contribution to the CTF, a critical step for demonstrating national commitment and leveraging additional donor financing. However, the question was raised regarding whether the Government’s contribution could be transferred to a national account rather than through the UN Multi-Partner Trust Fund (MPTF). Following consultations with the UN MPTF Office, it was clarified that, as CTF is being established as a pooled fund under the MPTF mechanism, all contributions must be channeled through a single UN MPTF account. Discussions with government counterparts on the Government’s contribution will continue based on this clarification.

In addition, agreement was reached with national counterparts to convene a joint donor engagement event in early 2026, aimed at securing initial capitalization commitments and launching the CTF’s first programmatic cycle.

Advocacy and communication tools—including a promotional video and informational booklet—were produced to strengthen donor engagement.

Finance solution 2: Reform harmful agricultural subsidies to remove barriers to green/organic agriculture

Finance solution 9: Introduction of monitoring and evaluation practices for subsidy effectiveness in Kyrgyzstan with a focus on potentially harmful to biodiversity subsidies

Agriculture in Kyrgyzstan exerts significant pressure on biodiversity through uncontrolled expansion into wildlife habitats, overgrazing, inefficient water use, water pollution, and the application of agrochemicals. The sector receives substantial public support, with various subsidies and budget allocations covering measures such as concessional loans, free animal vaccinations, and tax exemptions. Reforming or greening environmentally harmful subsidies is increasingly recognized as a strategic approach to simultaneously reduce the fiscal burden on the state, improve environmental outcomes, and enhance economic efficiency by encouraging the adoption of sustainable agricultural practices.

Recognizing the need to address these challenges, BIOFIN has prioritized the development of financial solutions (FS) to reform harmful subsidies. Financial Solution 2 aims to design and implement measures to gradually reform or green environmentally harmful subsidies in an efficient and socially responsible manner, minimizing adverse impacts on the most vulnerable groups. Financial Solution 9 was developed as a follow-up to the findings identified during the implementation of FS 2, and aims at filling a critical gap: the lack of mechanisms to assess the environmental impacts and effectiveness of subsidies.

Integrating the agenda of reforming environmentally harmful subsidies into national development programs is essential for ensuring policy coherence, long-term sustainability, and effective implementation of biodiversity goals in Kyrgyzstan. Embedding phasing out the harmful subsidies into national programs elevates the issue from a technical recommendation to a formal policy commitment. In this context, BIOFIN has integrated specific measures and indicators targeted at phasing out or repurposing environmentally harmful into national policy frameworks, including the Green Economy Development Program (2024–2028) and the National Biodiversity Strategy and Action Plan 2025-2030 (NBSAP), marking the first time measures targeting the reduction of the negative impact of subsidies on the environment has been mainstreamed into national development planning.

An analysis conducted in 2019 under FS 2 revealed approximately 30 subsidies with potentially harmful environmental effects and confirmed that Kyrgyzstan lacks both ex-ante and ex-post evaluation mechanisms for such support measures. To address these issues, a comprehensive package of interventions was designed and to be launched in 2026, including:

- Development and piloting of a methodology to assess the environmental impact and effectiveness of subsidies,

- A survey to understand public awareness and perceptions of harmful subsidies, and based on survey findings, provide evidence-based recommendations for policymakers,

- A communication campaign to build public and political support for reform.

Finance solution 3: Improving the procedures of budget formulation and execution of protected areas (PAs) and forestry enterprises (FEs)

Finance solution 4: Scaling up the adoption of performance programme-based budgeting in PAs

Finance solution 5: Scaling up of the Financial Solutions No. 3 and 4

Financial Solutions 3, 4, and 5 were developed under the BIOFIN initiative in Kyrgyzstan to address longstanding inefficiencies in the public financing of environmental protection institutions, particularly Protected Areas (PAs) and Forestry Enterprises (FEs). The first phase of BIOFIN revealed critical challenges such as weak alignment between budgets and strategic plans, limited use of functional budget classifications, and significant delays in financing seasonal conservation activities—issues that undermined the operational capacity of PAs and FEs to fulfill biodiversity mandates.

Financial Solution 3 (FS3) focused on revising budget rules to establish clear and consistent principles for financing biodiversity conservation. Financial Solution 4 (FS4) aimed to enhance the efficiency and accountability of public financial management by aligning budget allocations with strategic goals and measurable results. Financial Solution 5 (FS5) built on these foundations, integrating the objectives of FS3 and FS4 to create an enabling environment for results-based budgeting and secure more adequate and performance-linked funding for biodiversity institutions.

By the end of 2024, implementation of all three Financial Solutions was completed. With BIOFIN support, program-based budgeting (PBB) was introduced across all PAs and FEs through the development and official endorsement of sector-specific methodological guidelines, comprehensive training programs, and the development of structured management plans for all PAs.

To sustain this progress, follow-up support is necessary to reinforce institutional capacity, foster a cultural shift toward performance-based planning, and ensure continued alignment with evolving national budgeting regulations. In 2025, the Ministry of Finance initiated revisions to the Instruction on the Formation, Review, and Execution of Program-Based Budgets. Once adopted, these changes will require corresponding updates to the sectoral PBB guidelines used by PAs and FEs.

To support the next phase of implementation, BIOFIN Kyrgyzstan has secured new funding from the European Union. This funding will focus on continued technical assistance, institutional support, and capacity building to ensure the full and sustainable integration of program-based budgeting in the environmental sector. The specific scope of work will be defined following finalization of the revised national PBB framework.

Finance solution 6: Debt-for-Nature Swap in the Kyrgyz Republic

The Debt-for-Nature Swap (DfNS) presents a strategic opportunity for Kyrgyzstan to mobilize additional funding for environmental protection without reducing expenditures in other critical sectors. This financial solution is designed to guide the Government of Kyrgyzstan through the planning, negotiation, and implementation of a DfNS mechanism, with technical support including analytical reports, policy recommendations, a detailed roadmap, and capacity building for key government stakeholders—primarily the Ministry of Finance.

Based on the findings of a feasibility study conducted in previous reporting periods, Germany was identified as a promising potential creditor for a DfNS arrangement. In May 2024, UNDP facilitated consultations with the German Representation Office (GRO), presenting a concept note on the Conservation Trust Fund (CTF) and briefing materials on Germany’s DfNS instruments. Although the GRO expressed openness to supporting initial dialogue and connecting Kyrgyzstan with key stakeholders at Germany’s Federal Ministry for Economic Cooperation and Development (BMZ), these efforts have not yet produced tangible results.

To support future engagement, BIOFIN developed a comprehensive set of briefing materials and debt analyses to inform upcoming high-level discussions between UNDP and the German government. However, the planned visit and negotiations did not take place during the reporting period.

Further advancement of the DfNS agenda will resume once the Conservation Trust Fund is fully operationalized. Drawing on international experience, it is evident that creditors require a credible, independent implementation mechanism to manage the financial flows from a debt swap transparently and effectively. The CTF is positioned to fulfill this role, serving as a trusted vehicle for channeling DfNS proceeds toward priority biodiversity and climate-related objectives in Kyrgyzstan.

Finance solution 7: Introduction of an effective system of financial self-sufficiency in protected areas (PAs)

This financial solution addresses the urgent need to diversify and strengthen financing mechanisms for biodiversity conservation in Kyrgyzstan. With limited prospects for increased allocations from the state budget, establishing reliable and credible sources of revenue beyond public funding is essential to ensure the long-term sustainability of conservation efforts.

The solution aims to lay the groundwork for necessary institutional reforms—both organizational and regulatory—to support the implementation of various income-generating mechanisms for Protected Areas (PAs).

During the previous reporting period, a feasibility study identified six viable income-generation options for PAs. Following consultations, the Department of Biodiversity and Protected Areas Conservation (DBPCA) selected three priority options for immediate development:

- Adjusting entrance fees and expanding tourism-related services,

- Streamlining the allocation of land lease revenues into special accounts, including legislative revisions,

- Accessing funding from regional development funds.

Intervention 1. Revision of Entrance Fees for Protected Areas and Forest Enterprises

This intervention aims to transform entrance fees from a nominal charge into an effective, transparent, and sustainable conservation financing instrument.

During the reporting period, BIOFIN completed the full analytical and methodological groundwork required for reforming entrance fees across selected PAs and FEs. This included regulatory and legal analysis, assessment of current fee levels and retention practices, evaluation of ecotourism infrastructure, and estimation of visitors’ willingness and ability to pay.

The analysis revealed that while a legal basis for entrance fees exists, systemic weaknesses—including fragmented regulations, non-standardized fee administration, limited visitor accounting, and low digitalization—significantly constrain revenue potential and management effectiveness. Current fees were found to be largely symbolic and insufficient to cover real conservation and maintenance costs.

As a result, two reform scenarios were developed (a unified centralized model and a standardized differentiated model), alongside practical recommendations on tariff setting, administration, marketing, and governance. These outputs provide a robust evidence base for the second phase of the intervention in 2026, which will focus on adopting and implementing revised entrance fee tariffs.

Intervention 2. Strengthening Access of PAs and FEs to Regional Development Funds (RDFs)

This intervention aims to address the Institutional barriers limiting PA and FE access to the financing from the regional development funds - organizations established to support and stimulate the socio-economic development of the country's regions:  to strengthen the ability of PAs and FEs to secure funding from RDFs, establish mechanisms for regular cooperation with these funds, and advocate for the inclusion of dedicated biodiversity quotas in regional financing frameworks.

During the reporting period, BIOFIN conducted a comprehensive review of the regulatory, institutional, and procedural framework governing Regional Development Funds (RDFs) and identified key constraints preventing PA and FE participation—most notably limited technical capacity to prepare competitive applications.

In response, BIOFIN delivered practical, implementation-ready tools, including:

- Step-by-step application guidelines covering the full RDF project cycle;

- Standardized proposal templates for common economic and social-infrastructure project types and nature-based solution projects;

- Targeted recommendations to improve alignment between RDF priorities and biodiversity objectives.

The second phase of the intervention in 2026 will translate this readiness into tangible financing by supporting the preparation and submission of full RDF application packages.

Intervention 3. Streamlining Allocation of Land-Lease and Other PA Revenues into Special Accounts of PAs

The objective of this intervention is to strengthen the financial sustainability of the Kyrgyz Republic’s system of Protected Areas (PAs) by assessing and expanding legally permissible revenue-generation mechanisms and improving institutional arrangements for income management and use. Particular emphasis is placed on ensuring the sustainable and targeted use of PA-generated revenues through their allocation to special accounts that are directly accessible to the PAs themselves.

During the reporting period, BIOFIN completed a comprehensive legal and institutional assessment covering the national budget framework, special accounts regulations, and 26 potential revenue streams for PAs. The work produced a technical note that clearly distinguishes:

- Revenues immediately permissible under existing legislation;

- Revenues requiring regulatory amendments;

- Revenues to be formalized through inclusion in the Unified Register of State Services.

Extensive consultations with the Ministries of Natural Resources and Finance strengthened institutional awareness and initiated formal consideration of reforms to improve revenue retention and management, including enhancing the budgetary role of the Department of Biodiversity and Protected Areas.

This intervention lays the groundwork for long-term financial self-sufficiency of Protected Areas by enabling predictable, retained revenues to be reinvested directly into conservation and management priorities. Implementation support for regulatory changes is planned for 2026.

Finance solution 8: Digitalization of rental payments for leasing forest plots

This financial solution aims to modernize the payment system of the Forest Service and Forestry Enterprises (FEs) in Kyrgyzstan by transitioning all service-related transactions to non-cash, digital formats. The primary objective is to enhance transparency, traceability, and timeliness of financial operations, ensuring that all payments are instantly recorded in an integrated electronic system.

In addition to improving financial accountability, the solution expands payment accessibility, allowing users—particularly those in remote areas—to make payments through a wide range of digital channels, including payment terminals, e-wallets, and online platforms. Furthermore, it aims to streamline internal business processes and improve operational efficiency across the forestry sector.

The upgraded system delivered tangible operational and governance improvements:

- Improved accessibility and inclusion: Leaseholders can now make payments remotely using mobile banking, e-wallets, payment terminals, and QR-code–based payment identifiers—significantly reducing barriers for users in remote areas.

- Real-time transparency and control: Payments are reflected instantly in the system, enabling Forest Service staff to verify transactions in real time and eliminating manual processing of paper receipts.

- Enhanced financial oversight: Centralized dashboards and analytical reports allow monitoring of revenues by leaseholder, forest enterprise, region, and type of forest use, while enabling real-time tracking of outstanding receivables.

- Improved payment discipline: Automated notifications and reminders for overdue payments have reduced delays and strengthened compliance.

The upgraded AIS was fully deployed and operationalized in November 2025, marking a structural shift in how forest-use revenues are administered and monitored.

Finance solution 10: Integrating environmental considerations into the financial sector

This financial solution aims to integrate ESG and environmental risk considerations into the policies, supervision, and operations of the financial sector players, enabling the redirection of financial flows toward sustainable, nature-positive economic activities while strengthening financial system resilience.

During the reporting period, BIOFIN supported the National Bank of the Kyrgyz Republic (NBKR)—as the country’s central bank and financial sector regulator—in embedding ESG principles into its institutional architecture. During the reporting period, a comprehensive ESG self-assessment was conducted across all NBKR structural divisions, identifying priority gaps, risks, and entry points for ESG integration.

Based on this assessment, a detailed ESG Integration Roadmap was developed and approved by the NBKR Management Board. The Roadmap defines short-, medium-, and long-term actions, assigns institutional responsibilities, and outlines resource needs and risk mitigation measures. It provides practical guidance for integrating ESG into financial supervision, monetary policy analysis, internal operations, procurement, reporting, and governance, aligned with international good practices and the Sustainable Development Goals.

As a result, NBKR’s institutional readiness and internal awareness of ESG risks and opportunities were significantly strengthened, and a clear, sequenced implementation pathway was established. The intervention laid the foundation for systematic ESG implementation, monitoring, and disclosure within the central bank and created a replicable reference point for supervised financial institutions.

In 2026, targeted capacity-building and practical ESG training will support implementation of the Roadmap, alongside identification of further cooperation entry points with NBKR.

- Country factsheet: the country’s biodiversity finance profile and the programming approach

Biodiversity finance profile

The Kyrgyz Republic, being a landlocked country, is among the 200 priority ecological regions of the planet. This is due to a high concentration of species diversity; about 2% of the world’s known flora and 3% of the world’s known fauna can be found in the country. Biodiversity and ecosystems of the Kyrgyz Republic play an important role in the economy and traditions of the country. Ecosystems provide services for people of Kyrgyzstan and downstream countries which are essential to human wellbeing for this populated, arid, climate sensitive and disaster vulnerable region: fresh water, regulation of regional climate, food, biological pest control, maintenance of soil structure and fertility, natural protection against common natural hazards, nutrient cycling and hydrological services, carbon sequestration, support for biodiversity and cultural services.

Analysis of the environmental status shows that, currently, the national economy primarily applies technologies and practices that lead to environmental degradation and deterioration of livelihood environment, in general. Natural resources are being depleted, pollution is increasing and the dynamics of loss of biodiversity can be observed. All this reduces the regenerative capacity of the natural environment. Economic entities, energy, transport, mining, and agriculture sectors in particular affect the environment. There is a general lack of policies and economic mechanisms which aim to internalize the external costs to society caused by these entities including emissions, pollution and other degrading activities. This results in an overuse of the environment and natural resources.

The country’s commitment to and engagement in protecting its biological diversity and preventing further loss

The Kyrgyz Republic has acceded to the Convention on biological diversity by the Law of the Kyrgyz Republic No. 40. dated July 26, 1996.  In order to implement the provisions of the Convention on Biological Diversity and Strategic Plan for Conservation and Sustainable Use of biodiversity, including the Kunming-Montreal Global Biodiversity Framework, the country has developed:

- National Development Program of the Kyrgyz Republic until 2030 which defines the key actions necessary for the sustainable development of the country;

- National Strategy and Action Plan on Biodiversity Conservation 2025-2040 (in the process of approval).

- Concepts for the development of the forest industry for the period up to 2040.

- Green Economy development programme until 2029

The country’s financial profile: recent economic developments

In 2025, Kyrgyzstan’s economy demonstrated strong and sustained growth, with GDP increasing by 10% year-on-year, reaching KGS 1.427 trillion (preliminary) by the end of October 2025, driven primarily by investment-led expansion in construction, manufacturing, mining, energy, and municipal infrastructure, alongside resilient domestic demand in services such as trade, transport, hospitality, and communications. The structural composition of GDP shows a continuing shift toward industrialization and services, with commodity production accounting for 35% and services for 50% of GDP.

On the fiscal side, tax revenues rose by 12.0%, though their share in GDP decreased slightly to 16.6%, reflecting strong nominal GDP growth. Despite global uncertainties, inflation moderated to mid-single digits, supported by the National Bank of the Kyrgyz Republic’s prudent monetary policy. The fiscal position remained stable, with a continued push by the government to phase out energy subsidies and strengthen domestic revenue mobilization for long-term sustainability.

Looking ahead, the economic outlook remains positive. The Eurasian Development Bank (EDB) projects GDP growth of 10.3% for the full year, reflecting continued momentum in construction and industry. However, multilateral institutions caution that sustaining this trajectory will require structural reforms in energy, governance, and public investment management, alongside increased efforts to enhance climate resilience and address vulnerabilities such as high informality, regional instability, and commodity price volatility.

Though the economy of the country has recovered from the COVID-19 impact and is showing positive development in the last 2 years, due to the geo-political situation, the government of the country is placing the priorities on other sectors, which entail low allocation in the state budget expenditures, especially in relation to low-priority and non-priority sectors, which usually include the environmental sector.

National implementation context

The Biodiversity Finance Plan (BFP) of the Kyrgyz Republic is aimed at addressing the following issues identified as a result of the analysis of the status of biodiversity financing in the country:

1) Poor management of ecosystems and ecosystem services;

2) Actual lack of alternative sources of financing for biodiversity conservation,

3) Existing public policy measures that are harmful to biodiversity;

4) Lack of a system for optimal use of financial resources for environmental activities to be implemented by public authorities and local self-governments.

Thus, they aim to reduce the financial gap and to introduce new instruments to mobilize additional resources for the conservation of nature through achieving the following objectives:

-	Objective 1: Establish a framework for effective ecosystem management

-	Objective 2: Introduce alternative sources of financing for biodiversity conservation

-	Objective 3: Reform of government subsidies: transforming harmful and introducing biodiversity-friendly subsidies

-	Objective 4: Enabling the optimal financing of environmental protection activities of state bodies

It is impossible to achieve these objectives by one organization alone. Therefore, the programme's approach is guided by the principles of broad participation and partnership (across the public and private sectors as well as civil society), and the capacity development of the key partners to ensure the country ownership and sustainability of results.

Overview of key results

The sub-sections below outline the country programme’s progress related to its targeted results. Progress towards the targeted results is described according to the key result areas of the BIOFIN Theory of Change (ToC), which is shown below.

Figure 1: The BIOFIN theory of change

FS 1 «Establishment of the Biodiversity Conservation Trust Fund»

The Biodiversity Finance Policy and Institutional Review (PIR) and Biodiversity Expenditure Review (BER) highlighted a critical funding gap in biodiversity conservation, with limited contributions from public, donor, and private sectors. The Biodiversity Financial Needs Assessment (FNA) updated in 2025, estimated that around 184 million USD is required to implement Kyrgyzstan’s National Biodiversity Strategy and Action Plan (NBSAP) for 2025–2030 that was developed in 2025 and is currently undergoing the approval process. The FNA also revealed the financing gap of around 55 million USD, underscoring the further need for developing and implementing the innovative financing mechanisms to close this financing gap.

The Biodiversity Conservation Trust Fund (CTF) aims to attract additional financial resources to support priority biodiversity conservation initiatives and ensure the successful implementation of conservation initiatives. NBSAP forms the basis for the programmatic part of the CTF.

B.1.1.	Activities and results related to output areas

The key stakeholders for this FS are the Ministry of Natural Resources, Ecology and Technical Supervision, Ministry of Finance, and the Ministry of Emergency Situations.

Leveraging UN MPTF gateway for establishing the CTF in the Kyrgyz Republic

In 2023, a feasibility study was launched to evaluate the legal, tax, and institutional frameworks for establishing CTF. The study analyzed various models, including the potential for establishing the Fund within Kyrgyzstan or abroad. While viable options were identified, legal barriers indicated that any chosen model would require significant time for implementation.

Given the urgency and strong political will, UNDP proposed leveraging the UN Multi-Partner Trust Fund (MPTF) mechanism as an interim solution to expedite the Fund's establishment.

The concept of the CTF under the UN MPTF mechanism has been presented in 2024, at a high-level round table with participation of government agencies, diplomatic missions, UN bodies, financial institutions, and environmental organizations and received the support of stakeholders.

Foundational Document Development:

The foundational documents for the establishment of the Conservation Trust Fund (CTF) include the Terms of Reference (ToR), which outlines the Fund’s objectives, governance structure, and programmatic framework, as well as the Operations Manual. During the reporting period, the CTF ToR and Operations Manual were finalized.

CTF’s UN co-founding partners:

The Multi-Partner Trust Fund (MPTF) model requires that the Conservation Trust Fund (CTF) be established by at least two UN agencies. Following the presentation of the CTF Terms of Reference (ToR) to Kyrgyzstan’s UN Country Team in early 2025, several UN agencies — including UNEP, FAO, WFP, and WHO — expressed interest in joining the initiative. After a comprehensive assessment of each agency’s mandate and its alignment with the CTF’s Theory of Change, it was agreed that UNDP, UNEP, FAO, and WFP will serve as the UN co-founding partners of the Fund, with coordination led by the UN Resident Coordinator in Kyrgyzstan. This joint UN collaboration will ensure coherent, multisectoral support for biodiversity conservation efforts in the country.

Resource Mobilization and Launch:

The successful operationalization of the Conservation Trust Fund (CTF) hinges on securing adequate capitalization. While UNDP has maintained active engagement with a broad range of stakeholders to expand resource mobilization opportunities, these efforts have not yet resulted in formal funding commitments—despite expressed interest from various partners.

To support these efforts, an Outreach Plan was developed to guide structured engagement with government counterparts and development partners. In line with the Plan, a series of technical and high-level meetings were conducted with key national stakeholders. A central objective of the high-level engagements was to explore the possibility of a Government financial contribution to the Conservation Trust Fund (CTF). Such a contribution is critical both to demonstrate national commitment to biodiversity conservation and the sustainable management of natural resources, and to catalyze additional external financing, as government co-financing serves as an important signal to international partners and donors.

High-level consultations with government stakeholders at the level of Deputy Ministers resulted in national partners confirming that the Government of the Kyrgyz Republic would consider providing a financial contribution to the CTF. During these discussions, a question was raised regarding the necessity of channeling the Government’s contribution through the United Nations Multi-Partner Trust Fund (MPTF), with a request to consider the option of transferring funds to a nationally based account. Following consultations with the UN MPTF Office, it was clarified that, as the CTF is being established as a pooled fund under the UN MPTF mechanism, all resources intended for the CTF must be consolidated within a single UN MPTF account. Further discussions with government counterparts on the Government’s contribution to the CTF will continue based on this clarification.

Recognizing the importance of mobilizing resources from additional sources, it was also agreed with national partners to jointly organize a donor engagement event with development partners in early 2026. The event will serve to formally introduce the CTF and explore potential financing commitments from the donor community.

To complement the resource mobilization efforts, communication materials—including a promotional video and an informational booklet were produced to support advocacy and fundraising activities.

  - FS 2 « Reforming harmful agricultural subsidies to remove barriers to green/organic agriculture», FS 9 “Introduction of monitoring and evaluation practices for subsidy effectiveness in Kyrgyzstan with a focus on potentially harmful to biodiversity subsidies”

Agriculture in Kyrgyzstan exerts significant pressure on biodiversity through uncontrolled expansion into wildlife habitats, overgrazing, inefficient water use, water pollution, and the application of agrochemicals. The sector receives substantial public support, with various subsidies and budget allocations covering measures such as concessional loans, free animal vaccinations, and tax exemptions. Reforming or greening environmentally harmful subsidies is increasingly recognized as a strategic approach to simultaneously reduce the fiscal burden on the state, improve environmental outcomes, and enhance economic efficiency by encouraging the adoption of sustainable agricultural practices.

The objective of Financial Solution 2 is to design and implement measures to gradually reform or green environmentally harmful subsidies in an efficient and socially responsible manner, minimizing adverse impacts on the most vulnerable groups.

Financial Solution 9 emerged as a follow-up to the findings identified during the implementation of FS2. It addresses a critical gap: the absence of robust monitoring and evaluation (M&E) systems for subsidies that negatively affect biodiversity and the environment in Kyrgyzstan. This solution aims to develop methodologies to assess the environmental and biodiversity impacts of such subsidies and to evaluate their overall effectiveness.

    - Activities and results related to output areas

The key stakeholders for the FS 2 and 9 are the Ministry of Economy and Commerce, the Ministry of Agriculture and the Ministry of Finance.

As part of the implementation of Financial Solution 2, an analysis of state subsidies undertaken in 2019 revealed approximately 30 subsidies that have harmful effects on biodiversity and the environment. Moreover, it was found that there is currently no mechanism in Kyrgyzstan for conducting either ex-ante (prior) or ex-post (after) assessments of the environmental and biodiversity impacts of subsidies. Additionally, there is no established practice for evaluating the effectiveness of subsidies once implemented.

To address these gaps, a comprehensive scope of work on harmful subsidies—comprising three key components indicated below was planned to be initiated in 2025 under the framework of Financial Solutions 2 and 9. However, per the request of the national partner, this work was postponed to 2026. The work will be preceded by updating the analysis of the state subsidies.

  - Developing and Piloting Assessment Methodology

- A robust methodology will be developed to assess both the environmental impact and the effectiveness of state subsidies.

- The methodology will be piloted on three selected subsidies to refine the approach and demonstrate its practical applicability.

- BIOFIN will advocate for the institutionalization of the methodology by promoting its integration into Kyrgyzstan’s legislative and regulatory framework

  - Conducting a Nationwide Survey of Harmful Subsidies among the targeted group.

Harmful subsidies have pervasive effects on society, influencing consumer behavior, economic dynamics, and environmental sustainability. Understanding public perceptions, awareness levels, and attitudes towards harmful subsidies is crucial for informing evidence-based policy decisions, fostering public engagement, and promoting sustainable development. To ensure broad geographic representation, the survey will target a minimum of 30 respondents from each of the seven provinces of Kyrgyzstan. Therefore, the primary objectives of the research/survey will be:

- Assess public awareness and understanding of harmful subsidies across targeted sectors, particular in the agriculture.

- Identify public perceptions of the impacts of harmful subsidies on individuals, communities, and the environment.

- Explore public opinion and priorities regarding the reform or phasing out of harmful subsidies.

- Based on survey findings, provide actionable recommendations for policymakers, civil society organizations, and other stakeholders on strategies to enhance public awareness and engagement in subsidy reform efforts.

  - Communication Campaign to Catalyze Subsidy Reform

A communication campaign will be launched to raise awareness about the impacts of harmful subsidies and mobilize collective action toward reform. This campaign will leverage insights from the research/survey on harmful subsidies to tailor messages and strategies for maximum impact.

The campaign objectives will be:

- To increase understanding among the public about the concept, impacts, and implications of harmful subsidies across various sectors.

- To engage policymakers, civil society organizations, businesses, and academia in discussions about the need for subsidy reform and alternative policy approaches.

- To advocate for evidence-based policy reforms aimed at phasing out or redesigning harmful subsidies to promote economic efficiency, social equity, and environmental conservation.

Building Political Support for Subsidy Reform

The work in the previous phase has shown the importance of government support in advancing the agenda of harmful subsidies. Political support is essential for successful reform as it provides the necessary legitimacy, authority, and institutional resources for effective implementation. Strong backing from the government also helps to overcome resistance from vested interests, align various stakeholders, and ensure policy continuity despite potential changes in government administration.  In this context, we’re currently exploring cooperation with a government agency to serve as the Responsible Party for implementing Components 1 and 2 outlined above. In 2024, a government agency was identified to serve as the Responsible Party for the financial solution on harmful subsidy reform, and an assessment of its financial and management capacities was conducted. However, prior to the formalization of the agreement, the agency underwent a restructuring process, which was completed in March 2025. As a result of the restructuring, the agency’s revised mandate and strategic focus were found to be in conflict with the objectives of the financial solution. Consequently, a new public institution will be explored in 2026 once the work on the subsidies will be resumed.

Integrating Subsidy Reform Measures into the National Programs

BIOFIN Kyrgyzstan supported the development of the Green Economy Development Program of Kyrgyzstan for 2024-2028, specifically the section on Natural Ecosystems and Biodiversity. This strategic framework aims to guide the country’s transition toward a more sustainable and environmentally responsible economy.

Under the task “Development and optimization of fiscal mechanisms to support and incentivize sustainable economic development of the Kyrgyz Republic and reduce negative impacts on the environment”, a measure “To develop and implement a methodology and indicators for assessing the effectiveness of government support measures in the context of the green economy” was integrated.

In addition, BIOFIN Kyrgyzstan has integrated a specific measure and indicator targeted at phasing out or repurposing at least 3 environmentally harmful subsidies by 2030 into the National Biodiversity Strategy and Action Plan (NBSAP) which Kyrgyzstan is currently updating.

For the first time, measures targeting the reduction of the negative impact of subsidies on the environment were mainstreamed in a key national development plan. The inclusion of these measures marks a significant step forward in aligning public finance instruments with the national goals of environmental sustainability and biodiversity protection. Their implementation will be further supported by BIOFIN Kyrgyzstan.

  - FS 3 « Improving the procedures of budget formulation and execution of protected areas and forestry enterprises», FS 4 “Scaling up the adoption of performance programme-based budgeting in Protected Areas” and FS 5 “Scaling up of the Financial Solutions No. 3 and 4”

The first phase of BIOFIN in the Kyrgyz Republic identified several challenges in public budget financing for environmental protection institutions, including:

- Weak alignment between budgets and strategic plans.

- Limited use of functional budget classifications.

- Disruptive delays in financing activities, particularly those critical for seasonal operations.

These inefficiencies hinder the ability of Protected Areas (PAs) and Forestry Enterprises (FEs) to effectively implement biodiversity conservation priorities.

Financial Solution 3 (FS 3) addresses these challenges, by focusing on revision of budgeting rules to establish clear principles for public financing of PAs and FEs. By improving budget formulation and execution, this financial solution aims to create a robust foundation for sustainable financial management within environmental protection institutions.

The budget allocation in PAs is insufficiently correlated to performance indicators. Most of the budget is allocated to the salaries of the employees and often there are no funds to maintain facilities, purchase equipment and cover other implementation costs. Thus, the objective of Financial Solution 4 (FS 4) is to enhance the efficiency, transparency, and accountability of public financial management by aligning resource allocation with strategic objectives and measurable outcomes.

Financial Solution 5 (FS 5) integrates and builds on the objectives of FS 3 and FS 4, focusing on creating conditions for results-oriented budgeting and ensuring sufficient funding for PAs and FEs. This approach ensures that budget allocations are tied to performance indicators and strategic biodiversity objectives.

    - Activities and results related to output areas

The key partners in the implementation of the FS are the Ministry of Finance, the Ministry of Natural Resources, Ecology and Technical Supervision, and the Ministry of Emergency Situations.

The implementation of the FSs has been completed in 2024. With BIOFIN support, all Protected areas (PAs) and Forest enterprises (FEs) introduced program-based budgeting (PBB) through the development and formal approval of methodological guidelines on PBB for PAs and FEs and comprehensive capacity building measures. Additionally, hand-on support was provided to develop well-structured management plans for all PAs to ensure an effective budgeting process.

To sustain and build upon the results achieved during the previous phase, follow-up support is essential. The transition to a results-based budgeting system requires not only technical knowledge but also a significant shift in institutional mindset and operational culture. Continued training and capacity building for PA and FE staff are necessary to ensure that newly acquired skills and practices become institutionalized. Furthermore, follow-up efforts will help identify and address any remaining gaps or implementation challenges.

In 2025, the Ministry of Finance initiated a revision of the Instruction on the Formation, Review, and Execution of Program-Based Budgets. Once these revisions are finalized, corresponding updates will need to be made to the methodological guidelines used by PAs and FEs to align with the national PBB framework.

In support of these efforts, BIOFIN Kyrgyzstan has secured new funding from the European Union in 2025. One of the key focus areas of this funding will be to provide continued technical and capacity-building support for the effective implementation of program-based budgeting in Protected Areas and Forest Enterprises. The specific scope of work for the next phase will be defined following the adoption of the revised national PBB framework.

  - FS 6 «Debt-for-Nature Swap in the Kyrgyz Republic»

A debt-for-nature swap (DfNS) presents an opportunity to increase funding for environmental activities without reducing expenditure in other critical sectors.

The financial solution aims to guide the Government of Kyrgyzstan in implementing a debt-for-nature swap mechanism. Necessary analytical reports and technical notes will be provided, recommendations on how to implement and negotiate will be developed, a road map will be proposed, and the capacity of relevant staff will be enhanced.

    - Activities and results related to output areas

The key partner in the implementation is the Ministry of Finance

Based on the conclusions of the DfNS feasibility study conducted in the previous reporting periods, Germany was identified as one of the creditors most likely to engage in DfNS, the Kyrgyz Government has been actively advancing efforts to establish a DfNS agreement with Germany. In May 2024, UNDP organized consultations with the UNDP German Representation Office (GRO), presenting a concept note on the Conservation Trust Fund (CTF) and briefing materials on Germany's DfNS mechanisms. While GRO expressed a willingness to facilitate connections between Kyrgyzstan and key stakeholders at BMZ (Germany's operational body for DfNS) and to support preliminary discussions, these efforts have not yet yielded concrete results.

Furthermore, BIOFIN developed comprehensive briefing notes and analyses regarding Kyrgyzstan's debt with Germany to guide discussions between UNDP Headquarters and the German government during a planned visit. However, the visit and subsequent negotiations did not take place.

Further advancement of the DfNS agenda will resume once the Conservation Trust Fund is fully operationalized. Experience from DfNS arrangements in other countries demonstrates that creditors typically require a credible and independent implementation entity capable of ensuring transparent, accountable, and results-oriented management of financial proceeds. CTF can potentially serve as a transparent and accountable financial mechanism to channel and manage funds resulting from a potential debt swap.

  - FS 7 “Introduction of an effective system of financial self-sufficiency in protected areas (PAs)

This financial solution responds to the pressing need for alternative financing mechanisms for biodiversity conservation in Kyrgyzstan. Given the limited prospects for increased biodiversity financing from the state budget in the near future, the development of reliable and credible mechanisms to mobilize additional resources beyond the national budget is essential.

The Financial Solution aims to provide the necessary foundation for planning the necessary institutional changes (organizational and regulatory) to implement new mechanisms of income generation: adoption of public and private partnership mechanism to PA needs, inclusion of some PA services to the list of paid public services (this will allow charging fees from PA service consumers), set up profitable and balanced entrance fee pricing scheme (-s), payment for ecosystem services, concessions, earmarking and retention of biodiversity revenues, corporative social responsibility, philanthropy, promotion of conservation themed items, and others from the BIOFIN financial solutions catalogue. By implementing this financial solution, the enabling conditions for enhanced financial sustainability and long-term viability of biodiversity conservation action plans will be established.

    - Activities and results related to output areas

The Ministry of Natural Resources, Ecology, and Technical Supervision has been identified as the key partner in implementing this initiative.

During the previous reporting period, the feasibility study led to the development of a proposal outlining six viable options for income generation within Protected Areas (PAs). The proposed options included:

- Adjusting entrance fees to PAs and offering additional services to tourists.

- Generating income from permitted economic activities.

- Strengthening cooperation with NGOs and development partners.

- Streamlining land lease revenue allocation into special accounts, including necessary legislative amendments.

- Accessing financing from regional development funds.

- Supporting PA-related initiatives, such as selling thematic merchandise, branded products, "adoption certificates," and crowdfunding campaigns.

Following a series of discussions, the Department of Biodiversity and Protected Areas Conservation (DBPCA) endorsed three priority options for further development:

- Adjusting entrance fees to Protected areas and Forest enterprises.

- Streamlining land lease revenues allocation into special accounts, including legislative adjustments.

- Accessing financing from regional development funds.

Adjusting entrance fees to Protected areas and Forest enterprises.

The objective of the intervention “Increase of Entrance Fees to Protected Areas and Forest Enterprises” is to strengthen the financial sustainability and institutional capacity of the Kyrgyz Republic’s system of Protected Areas (PAs) and Forest Enterprises (FEs) through the development and implementation of an economically justified, socially inclusive, and operationally feasible entrance fee system.

During the reporting period, the first phase of the intervention was implemented, focusing on comprehensive analytical and preparatory work. This phase included::

- Analysis of regulation of entrance fees to PAs and FEs - detailed analysis for all selected PAs and FEs

- Analysis of the current state of entrance fees in PAs and FEs, including retention of fees by PAs and FEs and fees collection system, and conducted comparison with regional and international practices

- Assessment of existing ecotourism infrastructure and modernization needs

- Methodology and evaluation of visitors' payment capacity and the impact of tariff changes on attendance

- Development of the preliminary recommendations for implementing new entrance fee rates, including regulatory, legal, administrative, and marketing aspects, which includes:

  - Scenario 1. Introduction of a Unified Centralized Entry Fee System

  - Scenario 2. Standardized Differentiated Fee Model

  - Recommendations for Improving the Protected Areas and Forest Enterprises Sector

The analysis demonstrated that, while the current system of charging entrance fees for visits to PAs and FEs is generally supported by an existing legal and regulatory framework, it is constrained by a number of systemic weaknesses that limit its effectiveness as a sustainable financing instrument for conservation. Key challenges include inconsistencies across regulatory acts and variations in their practical application at the regional level, resulting in ambiguous tariff-setting procedures and uneven enforcement. The absence of unified standards for entrance fee administration further reduces transparency in visitor accounting and complicates the assessment of actual recreational pressure on natural areas.

In practice, current entrance fee levels and collection mechanisms do not reflect the real costs associated with territory protection, infrastructure maintenance, and the implementation of conservation measures. In most cases, entrance fees remain largely nominal and do not function as an effective economic tool for managing visitor flows or mitigating anthropogenic impacts. Additional institutional and technical constraints were identified, including a limited number of access control points, insufficient use of digital solutions, challenges in applying the Costing and Technical Calculation methodology, and limited institutional capacity to substantiate tariffs based on actual service delivery costs.

At the same time, the study confirms significant potential to improve the financial sustainability of PAs and FEs through reforms to tariff policy, the introduction of transparent and standardized visitor accounting systems, and a clearer differentiation between fees for access to natural resources and other paid services. The implementation of these measures could strengthen conservation outcomes, reduce ecosystem degradation risks, and promote a more balanced and equitable model of interaction among the state, local communities, and visitors.

This comprehensive analytical work and the resulting preliminary recommendations provide a solid foundation for the second phase of the intervention, which is planned for implementation in 2026 and will focus on the development and introduction of revised, increased entrance fee tariffs for Protected Areas and Forest Enterprises.

Accessing financing from regional development funds.

Regional Development Funds in Kyrgyzstan are organizations established to support and stimulate the socio-economic development of the country's regions. RDFs operate in all oblasts and rayons. PAs and FEs can apply for RDF funding.

However, a recent assessment revealed a key constraint: many PAs and FEs lack the technical capacity to develop and submit high-quality applications to RDFs. As a result, biodiversity and ecological priorities are often underrepresented in funding proposals. This interventions presents an initiative designed to bridge this gap through targeted capacity development, preparation of practical guidelines and templates, and facilitation of stronger collaboration between environmental institutions and RDFs.

This intervention aims to strengthen the ability of PAs and FEs to secure funding from RDFs, establish mechanisms for regular cooperation with these funds, and advocate for the inclusion of dedicated biodiversity quotas in regional financing frameworks.

During the reporting period, an analytical report was prepared based on a comprehensive review of the regulatory and institutional framework governing the operation of the Regional Development Funds (RDFs), including procedures for the submission, review, and financing of project applications. The analysis covered key legal acts, application forms, and monitoring requirements, and identified both opportunities and key barriers for the participation of Protected Areas (PAs) and Forest Enterprises (FEs). Practical recommendations were developed to improve accessibility of RDF mechanisms, strengthen the integration of conservation and nature-based solutions, and enhance internal application processes.

Building on the findings, clear and practical step-by-step instructions were developed for PA and FE staff, covering the full application cycle—from project concept development and preparation of environmental and financial justifications to approval, contracting, and reporting. These guidelines aim to improve the quality and success rate of PA and FE applications to RDFs.

In addition, standardized application templates and supporting documentation were developed for the most common economic and social-infrastructure project types, including selected nature-based solutions. The templates are designed to simplify application preparation, improve proposal quality and competitiveness, and promote the integration of biodiversity and conservation considerations into RDF-financed projects.

In 2026, the 2nd phase of the intervention will focus on supporting the PAs and Fes in developing the full package of application to be submitted for financing by the RDFs.

Streamlining land lease revenues allocation into special accounts, including legislative adjustments.

The objective of this intervention is to strengthen the financial sustainability of the Kyrgyz Republic’s system of Protected Areas (PAs) by assessing and expanding legally permissible revenue-generation mechanisms and improving institutional arrangements for income management and use. Particular emphasis is placed on ensuring the sustainable and targeted use of PA-generated revenues through their allocation to special accounts that are directly accessible to the PAs themselves.

During the reporting period, a comprehensive legal and institutional analysis was conducted, examining the national budget framework, special accounts regulations, and 26 potential revenue sources for PAs. The work resulted in a technical note with concrete, legally grounded recommendations identifying revenue streams that can be implemented immediately, those requiring regulatory amendments, and those subject to inclusion in the Unified Register of State Services. In parallel, extensive consultations were held with the Ministry of Natural Resources, the Ministry of Finance, and relevant departments, leading to increased government awareness of revenue diversification opportunities and formal consideration of regulatory and institutional reforms, including strengthening the budgetary role of the Department of Biodiversity Conservation and Protected Areas. As a result, the intervention established a clear, evidence-based roadmap for diversifying PA revenues and laid the groundwork for subsequent policy and regulatory action to enhance long-term financial self-sufficiency of the protected area system.

In 2026, the second phase of the intervention will focus on supporting the implementation of these follow-up policy and regulatory measures, enabling eligible revenues to be effectively transferred to and managed through the special accounts of Protected Areas.

  - FS 8: Digitalization of rental payments for leasing forest plots

This financial solution, supported by funding from the Government of Germany, aims to digitalize payments for services provided by the Forest Service and Forestry Enterprises (FEs) by transitioning all transactions to non-cash formats. This shift will improve the transparency, traceability, and timeliness of financial operations, ensuring that payments are immediately recorded in an electronic database

In addition, the solution will expand payment channels, enabling users in remote areas to make payments through various financial instruments such as terminals, e-wallets, and other digital platforms. It will also streamline and optimize existing business processes, improving efficiency and accessibility across the system.

    - Activities and results related to output areas

The key partner in implementation is the Forest Service under the Ministry of Emergency Situations.

BIOFIN has supported the implementation of the Financial Solution (FS) by enhancing the Forest Service's automated information system (AIS) "Forest Management" through integration with relevant state IT systems. This effort included the development of new modules and functionalities, as well as the expansion of existing ones, to enable the transition of all payments to non-cash formats.

One of the system’s key objectives is the transition of forest-use payments to an electronic format through the national government payment gateway.

The changes introduced following the AIS update:

1. Simplified and accessible payment process for users

Prior to the implementation of AIS, leaseholders were required to visit banks in person, wait in queues, and submit paper payment receipts to the Forest Service.

Following implementation, the payment process has been fully streamlined. Users can now:

- make payments remotely from any location;

- use multiple payment channels, including mobile banking, e-wallets, payment terminals, and other digital platforms;

- pay lease fees and other charges using generated payment codes (including QR codes), without visiting a bank.

2. Improved transparency and real-time payment tracking

AIS automatically generates payment codes and sends them to leaseholders. Once payment is made:

- transaction information is reflected in the system in real time;

- Forest Service staff can verify payments down to the exact time of receipt;

- manual verification of paper receipts is no longer required.

This has significantly reduced human error, administrative workload, and processing time.

3. Centralized control and enhanced analytics

The system enables now:

- centralized monitoring of all payments within a single database;

- generation of consolidated reports by individual leaseholders, types of forest use, forest enterprises, regions, and at the national level;

- real-time tracking of outstanding receivables.

- Designated financial staff have access to aggregated analytical reports, strengthening financial oversight and management capacity.

4. Automated notifications and improved payment discipline

The system includes an automated notification function:

- leaseholders receive payment details upon generation of a payment code;

- overdue payments trigger automatic email reminders.

This has contributed to improved payment discipline and reduced payment delays.

The updated AIS was put into full deployment and operationalization at the end of November 2025. The financial impact of the above-mentioned changes will be further monitored.

  - FS 10: Integrating environmental considerations into the financial sector

This financial solution aims to integrate ESG and environmental risk considerations into the policies, supervision, and operations of the financial sector players, enabling the redirection of financial flows toward sustainable, nature-positive economic activities while strengthening financial system resilience.

As the 1st component of the FS, the FS will focus supporting the National Bank of the Kyrgyz Republic to integrate the ESG principles into its policies and operations. As the central bank and financial sector regulator, NBKR is uniquely positioned to mainstream environmental considerations across the banking and non-bank financial sectors, while also leading by example through its own institutional practices.

    - Activities and results related to output areas

The key partner in implementation is National Bank of the Kyrgyz Republic.

The objective of this intervention was to support the National Bank of the Kyrgyz Republic in systematically integrating Environmental, Social, and Governance (ESG) principles into its policies, operations, and supervisory practices, thereby strengthening its role as a driver of sustainable finance and financial system resilience.

During the reporting period, a comprehensive institutional self-assessment was conducted across all structural divisions of the National Bank, followed by the development of a detailed ESG Roadmap outlining short-, medium-, and long-term actions, responsible units, resource needs, and risk mitigation measures. The Roadmap provides practical guidance on embedding ESG into monetary policy analysis, financial supervision, internal operations, procurement, reporting, and governance arrangements, aligned with international standards and the Sustainable Development Goals. As a result, the intervention established a coherent, evidence-based framework for ESG integration, enhanced institutional readiness and awareness, and laid the foundation for systematic ESG implementation, monitoring, and reporting, positioning the National Bank as a national benchmark for sustainable and responsible governance in the financial sector.

The developed ESG integration roadmap was approved by the Management Board of the NBKR. In 2026, the training on ESG and practical instruments necessary for the roadmap implementation will be conducted. In addition, following the discussion with the NBKR, the entry points for further cooperation with the NBKR will be identified.

Lessons learned and adaptive measures:

The implementation of various BIOFIN financial solutions in Kyrgyzstan has generated important lessons and informed adaptive measures for future work:

- Political will and institutional commitment are critical for the success of long-term biodiversity finance mechanisms. Progress on initiatives such as the Conservation Trust Fund (CTF) and subsidy reform has demonstrated that government support enables policy alignment, inter-agency cooperation, and stakeholder buy-in. We’re currently exploring the cooperation with the government agency to carry out the implementation of the financial solution on Harmful subsidies as Responsible Party.

- Legal, regulatory, and operational readiness must be assessed early. Several solutions, including the CTF and digitalization initiatives, faced delays due to legal or technical barriers. Early feasibility studies, flexible design, and interim mechanisms (e.g. use of the UN MPTF) proved essential to mitigate risks.

- Capacity building is not a one-time activity. Sustained implementation of tools like program-based budgeting requires ongoing training and institutionalization to ensure long-term impact.

- Public and stakeholder engagement enhances effectiveness. Nationwide consultations, surveys, and communications campaigns are key to building awareness and support for reform measures, particularly around harmful subsidies.

Risks

Programmatic risks (risks to the programme)

Frequent changes of key project focal points from the national partners—represent a high-likelihood, high-impact programmatic risk that has already led to delays in the implementation of several Financial Solutions. These institutional shifts often disrupt continuity, undermine institutional memory, and require repeated onboarding and advocacy efforts. During the reporting period, the key focal point from the senior management of the Ministry of Finance and the Forest Service were replaced. New appointees frequently lack a background in biodiversity conservation, making it challenging for them to fully grasp the importance of conservation financing or to prioritize the implementation of related measures. To mitigate this, the project team maintains continuous coordination with multiple staff members within partner institutions to build and retain institutional memory and ensure progress despite personnel turnover.

Additionally, a broader political risk lies in the limited political will to adopt and advance recommendations related to biodiversity finance. Amid shifting geopolitical dynamics and growing pressure to address immediate economic and security concerns, government priorities have increasingly shifted toward sectors perceived as more urgent. This has resulted in continuously reduced state budget allocations for the environmental sector, which is often categorized as a low or non-priority area. In this fiscal climate, efforts to reform public budgeting procedures, including results-based and program-based budgeting for conservation, face significant challenges due to limited financial resources and lack of high-level support.

To address these risks, BIOFIN will continue its engagement with high-level stakeholders, integrate biodiversity finance measures into national development frameworks (e.g., the Green Economy Program and NBSAP), and align conservation financing efforts with broader sustainable development and economic recovery goals.

Social and environmental risks (of the programme)

The programme is designed to enhance biodiversity conservation and sustainable financing and, as such, is expected to have positive social and environmental outcomes. However, some components may carry limited risks if not carefully managed. For example, efforts to reform or repurpose harmful subsidies could indirectly affect the livelihoods of vulnerable populations. If these reforms are introduced without adequate social safeguards or compensatory measures, there may be unintended socioeconomic consequences. Therefore, the program fill thoroughly assess this impact to mitigate this risk. As mentioned in the Section related to Harmful subsidies, we plan to conduct the broad survey among the targeted group of population which will provide insights to manage this risk.

Special attention is given to ensuring that the needs and perspectives of vulnerable groups are considered in policy design and implementation. Additionally, environmental safeguards are upheld in all technical and feasibility assessments to ensure that new financing mechanisms do not result in adverse ecological impacts or undermine existing conservation objectives. Overall, the programme’s risk profile remains low, with safeguards in place to ensure that its social and environmental impacts are positive and equitable.

- List of annexes and related notes

The following annexes are included in this report:

- Annex 1: Indicator Tracking Table (in Excel)