## Please enable macros (hidden)
Please enable macros to use this document.
If this message appears below the ribbon, click the "Enable Content" button.
If a security warning window pops up, click the "Yes" or "Enable macros" button.
If you don't see either option, go to "File" > "Options" > "Trust Center"
Then go to "Trust Center Settings" > "Macro Settings." Select "Enable all macros" then close and reopen this document.

## Dashboard
Progress dashboard |  |  |  |  | About the dashboard
Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003)
UNDP Sri Lanka
ACTIVITIES COMPLETED |  | OUTPUTS COMPLETED
0 / 20 |  | 0 / 12
PROJECT PROGRESS | [9 empty] | EXPENDITURE BY ACTIVITY (CCAC funding) | [8 empty] | SUMMARY BY COST CATEGORY
Description | Delivery date | Reporting period: 11/10/2024 - 30/06/2025 | Reporting period: 01/07/2025-31/12/2025 | Reporting period: 01/01/2026-30/06/2026 | Reporting period: 01/07/2026-30/11/2026 | Reporting period: | Activity complete | Output complete | Outcome completed | Related activity | Category | Total budget | Total expenditure | Reporting period: 11/10/2024 - 30/06/2025 | Reporting period: 01/07/2025-31/12/2025 | Reporting period: 01/01/2026-30/06/2026 | Reporting period: 01/07/2026-30/11/2026 |  | Category | Total budget | Total expenditure | Variance
Output 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | 2024-12-31 | On track | Delayed |  |  |  | no | no | no |  | Total | 697675 | 136779 | 0 | 136779 | 0 | 0 | 0 | Total | 639600 | 136779 | -78.61%
Activity 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | Project end | On track | On track |  |  |  | no | no | no | Activity 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | Staff and Other Personnel Costs | 25000 | 38260 | 0 | 38260 | 0 | 0 | 0 | Contractual Services | 79000 | 6517 | -91.75%
Activity 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Project end | On track | On track |  |  |  | no | no | no | Activity 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | Staff and Other Personnel Costs | 12000 | 13033 | 0 | 13033 | 0 | 0 | 0 | Equipment Vehicles and Furniture | 225000 | 0 | -100%
Output 1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | 2025-06-30 | On track | Delayed |  |  |  | no | no | no | Activity 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | Travel | 500 | 0 | 0 | 0 | 0 | 0 | 0 | Operating and Other Direct Costs | 0 | 0
Activity 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | Project end | On track | On track |  |  |  | no | no | no | Activity 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | Travel | 3840 | 0 | 0 | 0 | 0 | 0 | 0 | Staff and Other Personnel Costs | 275600 | 130262 | -52.74%
Output 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | 2024-11-30 | On track | On track |  |  |  | no | no | no | Activity 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | Travel | 1220 | 0 | 0 | 0 | 0 | 0 | 0 | Supplies Commodities and Materials | 12740 | 0 | -100%
Activity 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | Project end | On track | On track |  |  |  | no | no | no | Activity 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Staff and Other Personnel Costs | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | Travel | 47260 | 0 | -100%
Activity 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | Project end | On track | Not started |  |  |  | no | no | no | Activity 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Staff and Other Personnel Costs | 4000 | 0 | 0 | 0 | 0 | 0 | 0
Activity 1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | Project end | On track | Not started |  |  |  | no | no | no | Activity 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Supplies Commodities and Materials | 500 | 0 | 0 | 0 | 0 | 0 | 0
Output 1.6 Programme Support | 2025-02-28 | Not started | Not started |  |  |  | no | no | no | Activity 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Travel | 500 | 0 | 0 | 0 | 0 | 0 | 0
Activity 1.6.1 Project Support | Project end | Not started | Not started |  |  |  | no | no | no | Activity 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Travel | 1344 | 0 | 0 | 0 | 0 | 0 | 0
Output 2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | 2025-08-30 | Not started | Delayed |  |  |  | no | no | no | Activity 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Travel | 610 | 0 | 0 | 0 | 0 | 0 | 0
Activity 2.1.1Viability assessment of EV charging stations is completed and approved | Project end | Not started | On track |  |  |  | no | no | no | Activity 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | Staff and Other Personnel Costs | 25000 | 16291 | 0 | 16291 | 0 | 0 | 0
Activity 2.1.2An Analytical gender (including elderly, children, specific needs commuter) specific report on safety, security, accessibility aspects of public transport buses in Sri Lanka | Project end | Not started | On track |  |  |  | no | no | no | Activity 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | Staff and Other Personnel Costs | 15000 | 0 | 0 | 0 | 0 | 0 | 0
Output 2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 2025-11-30 | Not started | Delayed |  |  |  | no | no | no | Activity 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | Travel | 1000 | 0 | 0 | 0 | 0 | 0 | 0
Activity 2.2.1Training programs designed and delivered for government institutional stakeholders | Project end | On track | On track |  |  |  | no | no | no | Activity 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | Travel | 3840 | 0 | 0 | 0 | 0 | 0 | 0
Output 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 2025-10-31 | Not started | Delayed |  |  |  | no | no | no | Activity 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | Travel | 1464 | 0 | 0 | 0 | 0 | 0 | 0
Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Project end | Not started | Not started |  |  |  | no | no | no | Activity 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | Staff and Other Personnel Costs | 10000 | 19884 | 0 | 19884 | 0 | 0 | 0
Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Project end | Not started | Not started |  |  |  | no | no | no | Activity 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | Staff and Other Personnel Costs | 8000 | 0 | 0 | 0 | 0 | 0 | 0
Output 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | 2025-11-30 | Not started | Delayed |  |  |  | no | no | no | Activity 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | Travel | 500 | 0 | 0 | 0 | 0 | 0 | 0
Activity 3.2.1Mass media promotional campaigns on benefits of public transport | Project end | Not started | On track |  |  |  | no | no | no | Activity 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | Travel | 1920 | 0 | 0 | 0 | 0 | 0 | 0
Activity 3.2.2Targeted promotional events on benefits of public transport | Project end | Not started | On track |  |  |  | no | no | no | Activity 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | Travel | 854 | 0 | 0 | 0 | 0 | 0 | 0
Activity 3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | Project end | Not started | On track |  |  |  | no | no | no | Activity 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | Staff and Other Personnel Costs | 10000 | 0 | 0 | 0 | 0 | 0 | 0
Output 4.1 5 small/medium 9-metre buses deployed through public private partnerships in Colombo Municipal area after selection of vendor/OEM through a competitive tender process as per UN procurement rules | 2026-05-15 | Not started | Delayed |  |  |  | no | no | no | Activity 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | Staff and Other Personnel Costs | 10000 | 0 | 0 | 0 | 0 | 0 | 0
Activity 4.1.1Technical assistance to setup a mechanism for channelling of enhanced grants as capital subsidy scheme | Project end | Not started | Not started |  |  |  | no | no | no | Activity 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | Travel | 500 | 0 | 0 | 0 | 0 | 0 | 0
Activity 4.1.2Five electric buses on public transport routes are procured and deployed with support from enhanced capital subsidy scheme and leased to public/private bus operator | Project end | Not started | Not started |  |  |  | no | no | no | Activity 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | Travel | 1920 | 0 | 0 | 0 | 0 | 0 | 0
Output 5.1 A 45- to 60-minute webinar about the project approach and outcomes delivered to CCAC partners and project stakeholders no later than the project end date | 2026-05-15 | Not started | On track |  |  |  | no | no | no | Activity 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | Travel | 976 | 0 | 0 | 0 | 0 | 0 | 0
Activity 5.1.1 A 45- to 60-minute webinar about the project approach and outcomes developed and delivered to CCAC partners and project stakeholders | Project end | Not started | Not started |  |  |  | no | no | no | Activity 1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | Staff and Other Personnel Costs | 2500 | 0 | 0 | 0 | 0 | 0 | 0
Output 5.2 A 5- to 10-page case study or guidance document to support the replication or scale up of the project activities and/or results for potential public and private sector operators/stakeholders | 2026-05-31 | Not started | Not started |  |  |  | no | no | no | Activity 1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | Staff and Other Personnel Costs | 2000 | 0 | 0 | 0 | 0 | 0 | 0
Activity 5.2.1 A 5- to 10-page case study to facilitate scale up of project's activities | Project end | Not started | Not started |  |  |  | no | no | no | Activity 1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | Travel | 244 | 0 | 0 | 0 | 0 | 0 | 0
Output 5.3 A report tracking mitigation potential and actual emission reduction during and immediately after project period by the deployment of 5 electric buses, for Ministry of Transport and Highways /Ministry of Environment for NDC reporting | 2026-05-31 | Not started | On track |  |  |  | no | no | no | Activity 1.6.1 Project Support | UN-PSC | 58075 | 0 | 0 | 0 | 0 | 0 | 0
Activity 5.3.1 A report/system tracking actual emission reduction from deployment of 5 e-buses against mitigation potential | Project end | Not started | Not started |  |  |  | no | no | no | Activity 2.1.1Viability assessment of EV charging stations is completed and approved | Staff and Other Personnel Costs | 10000 | 16291 | 0 | 16291 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 2.1.1Viability assessment of EV charging stations is completed and approved | Staff and Other Personnel Costs | 8000 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 2.1.1Viability assessment of EV charging stations is completed and approved | Travel | 500 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 2.1.1Viability assessment of EV charging stations is completed and approved | Travel | 1920 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 2.1.1Viability assessment of EV charging stations is completed and approved | Travel | 854 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 2.1.2An Analytical gender (including elderly, children, specific needs commuter) specific report on safety, security, accessibility aspects of public transport buses in Sri Lanka | Staff and Other Personnel Costs | 12000 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 2.1.2An Analytical gender (including elderly, children, specific needs commuter) specific report on safety, security, accessibility aspects of public transport buses in Sri Lanka | Travel | 1220 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 2.2.1Training programs designed and delivered for government institutional stakeholders | Staff and Other Personnel Costs | 15000 | 6517 | 0 | 6517 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 2.2.1Training programs designed and delivered for government institutional stakeholders | Staff and Other Personnel Costs | 10000 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 2.2.1Training programs designed and delivered for government institutional stakeholders | Supplies Commodities and Materials | 2000 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 2.2.1Training programs designed and delivered for government institutional stakeholders | Travel | 1000 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 2.2.1Training programs designed and delivered for government institutional stakeholders | Travel | 3264 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 2.2.1Training programs designed and delivered for government institutional stakeholders | Travel | 1708 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Contractual Services | 2000 | 6517 | 0 | 6517 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Staff and Other Personnel Costs | 7500 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Staff and Other Personnel Costs | 6000 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Supplies Commodities and Materials | 1740 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Travel | 500 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Travel | 2880 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Travel | 1708 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Contractual Services | 2000 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Staff and Other Personnel Costs | 15000 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Staff and Other Personnel Costs | 8000 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Supplies Commodities and Materials | 2000 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Travel | 500 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Travel | 3264 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Travel | 1708 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 3.2.1Mass media promotional campaigns on benefits of public transport | Contractual Services | 30000 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 3.2.1Mass media promotional campaigns on benefits of public transport | Staff and Other Personnel Costs | 5600 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 3.2.1Mass media promotional campaigns on benefits of public transport | Supplies Commodities and Materials | 2500 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 3.2.1Mass media promotional campaigns on benefits of public transport | Travel | 854 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 3.2.2Targeted promotional events on benefits of public transport | Contractual Services | 30000 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 3.2.2Targeted promotional events on benefits of public transport | Staff and Other Personnel Costs | 6000 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 3.2.2Targeted promotional events on benefits of public transport | Supplies Commodities and Materials | 2000 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 3.2.2Targeted promotional events on benefits of public transport | Travel | 854 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | Contractual Services | 15000 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | Staff and Other Personnel Costs | 6000 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | Supplies Commodities and Materials | 2000 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | Travel | 854 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 4.1.1Technical assistance to setup a mechanism for channelling of enhanced grants as capital subsidy scheme | Staff and Other Personnel Costs | 20000 | 13405 | 0 | 13405 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 4.1.1Technical assistance to setup a mechanism for channelling of enhanced grants as capital subsidy scheme | Travel | 2440 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 4.1.2Five electric buses on public transport routes are procured and deployed with support from enhanced capital subsidy scheme and leased to public/private bus operator | Equipment Vehicles and Furniture | 225000 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 5.1.1 A 45- to 60-minute webinar about the project approach and outcomes developed and delivered to CCAC partners and project stakeholders | Staff and Other Personnel Costs | 3000 | 6581 | 0 | 6581 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 5.2.1 A 5- to 10-page case study to facilitate scale up of project's activities | Staff and Other Personnel Costs | 3000 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 5.3.1 A report/system tracking actual emission reduction from deployment of 5 e-buses against mitigation potential | Staff and Other Personnel Costs | 6000 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | Activity 5.4.1 An MRV system setup and managed by PMU to track project progress and report to the Project Board and CCAC | Staff and Other Personnel Costs | 6000 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0

## 1.Signature page
1. Signature & submission page
ADMINISTRATIVE INFORMATION |  |  | INSTRUCTIONS
Project title | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) |  | This page must be completed, signed and sent to the CCAC Secretariat each reporting period along with the completed Progress Report template in Excel. The Cover Page can be saved as a PDF or printed. Insert logo --Click "Insert" in the ribbon / tool bar --Click "Illustrations", then "Pictures" --Select the location of the logo --Select the image file (file such as JPG) and click "Insert" --Move and/or resize logo over top the red text Sign the cover page Option 1 - insert signature as image --Scan and save your signature as an image (JPG or PNG) --In the Progress Report template, select the cell into which you want to add your signature --Click "Insert" in the ribbon / tool bar --Click "Illustrations", then "Pictures" --Select the location of the signature --Select the image file and click "Insert" --Move and/or resize signature as needed Option 2 - sign digital or printed copy --Complete all required fields on the cover page (except signature) --Click "File" in the ribbon / tool bar --Click "Print" --Select your printer OR print to PDF
Implementer | UNDP Sri Lanka
Co-implementers
Agreement ID | 24-035-HDV-23-003
Name of contact person | Buddika Hapuarachchi
Buddika.Hapuarachchi@undp.org
Funding cycle (programme ID) | POW 2024-2025
Budget line (WBSE) | S1-32SLP-000036/ SB-022934.02.01.04.04
Contract amount $US | 697675
Project amount $US | 1357675.68
BP number | 1400000226
Subprogramme | Climate Change
Contract start date (dd/mm/yyyy) | 2024-10-11
Contract end date (dd/mm/yyyy) | 2027-11-30
Activities end date (dd/mm/yyyy) | 2026-11-30
STATUS SUMMARY - FIRST REPORTING PERIOD
First reporting period dates: (dd/mm/yy - dd/mm/yy) | 11/10/2024 - 30/06/2025
| Summary/description (max. 500 characters) | Status
Schedule | The project faced delays due to pending approval from the National Planning Department (NPD), required prior to project implementation, and a donor request to temporarily hold project activities. The Local Project Appraisal Committee meeting, co-chaired by the Ministry of Transport and UNDP, was held on 26 June 2025.All key Stakeholders participated and reached consensus on the strategy and next steps, enabling the project to move forward. | On track
Budget | During the reporting period, no expenditures were incurred due to the delay in obtaining the necessary approval from the Government of Sri Lanka. With the Local Project Appraisal Committee meeting is held on 26 June, the Project can now move forward. Key preparatory activities such as developing Terms of References and conducting preliminary stakeholder consultations have been initiated using UNDP resources until the Project Document is signed. | Issues
Scope | During this reporting period, there were no changes to the project scope, including activities, deliverables, or indicators of success. The project remains aligned with the original plan and approved results framework. During the LPAC meeting, Ministry of Transport (MOT) has requested the Project to include national transport policy revision, which will be considered after consulting the Secretary, MOT. | On track
Payments received to date | 348837.5
Sign here before submitting your report:
| Signature | Date
Read and approved by CCAC Secretariat/UNEP:
| Signature | Date
STATUS SUMMARY - 2ND REPORTING PERIOD
Second reporting period dates: (dd/mm/yy - dd/mm/yy) | 01/07/2025-31/12/2025
| Summary/description (max. 500 characters) | Status
Schedule | The Project was able to able to commence only after receiving the required approval from the Government in Nov 2025. The Ministry of Transport appointed a Project Monitoring Committee to oversee project implementatation. The project is now in full implementation and is accelerating activities to recover some of the time lost during the initial phase. A review of activity timelines is planned for Feb 2026 following which a request for a no-cost extension will be submitted if required. | Issues
Budget | Major expenditure during the reporting period include an institutional contract covering regulatory reforms, technical analyses and pilot feasibility design, as well as workshop-related costs. Two additional contracts for commincations and awareness, and for training needs assessment and program delivery are planned for Q1 2026, while the major e-bus pilot procurement is scheduled for Q2 2026. | On track
Scope | The project incurred no changes to its scope—including activities, deliverables or indicators—and remains aligned with the approved RF. Follwing discussions, the Ministry of Transport requested project assistance for developing an E-Mobility Action Plan and Roadmap, which is under consideration. In parellel, the project has secured FCDO/UK support to mobilize complemenatary technical assistance through the GCIEP, with a focus on bus sector reforms aligned with the project objectives. | On track
Payments received to date | 697675
Sign here before submitting your report:
| Signature: Buddika Hapuarachchi - Policy Specialist and Team Leader | Date: 01/27/2026
Read and approved by CCAC Secretariat/UNEP:
| Signature | Date
STATUS SUMMARY - 3RD REPORTING PERIOD
Third reporting period dates: (dd/mm/yy - dd/mm/yy) | 01/01/2026-30/06/2026
| Summary/description (max. 500 characters) | Status
Schedule
Budget
Scope
Payments received to date | 0
Sign here before submitting your report:
| Signature | Date
Read and approved by CCAC Secretariat/UNEP:
| Signature | Date
STATUS SUMMARY - 4TH REPORTING PERIOD
Fourth reporting period dates: (dd/mm/yy - dd/mm/yy) | 01/07/2026-30/11/2026
| Summary/description (max. 500 characters) | Status
Schedule
Budget
Scope
Payments received to date | 0
Sign here before submitting your report:
| Signature | Date
Read and approved by CCAC Secretariat/UNEP:
| Signature | Date
STATUS SUMMARY - 5TH REPORTING PERIOD
Fifth reporting period dates: (dd/mm/yy - dd/mm/yy)
| Summary/description (max. 500 characters) | Status
Schedule
Budget
Scope
Payments received to date | 0
Sign here before submitting your report:
| Signature | Date
Read and approved by CCAC Secretariat/UNEP:
| Signature | Date

## 2. Narrative
2. Narrative report |  |  | See instructions
Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003)
UNDP Sri Lanka
PLANNED | [15 empty] | FIRST REPORTING PERIOD: 11/10/2024 - 30/06/2025 | [5 empty] | SECOND REPORTING PERIOD: 01/07/2025-31/12/2025 | [5 empty] | THIRD REPORTING PERIOD: 01/01/2026-30/06/2026 | [5 empty] | FOURTH REPORTING PERIOD: 01/07/2026-30/11/2026 | [5 empty] | FIFTH REPORTING PERIOD:
Deliverable | Indicator | Target | Unit | Delivery date | Proof of delivery | Description2 | Acceptance criteria | Project name | Full code | Implementer | Sector | Beneficiary | Other beneficiary | blank1 | blank2 | Status at end of 1st period | Progress made during 1st period | Variance during 1st period | Further actions at end of 1st period | Proof of delivery (document URLs or file names) 1st period | Type of document 1st period | Status at end of 2nd period | Progress made during 2nd period | Variance during 2nd period | Further actions at end of 2nd period | Proof of delivery (document URLs or file names) 2nd period | Type of document 2nd period | Status at end of 3rd period | Progress made during 3rd period | Variance during 3rd period | Further actions at end of 3rd period | Proof of delivery (document URLs or file names) 3rd period | Type of document 3rd period | Status at end of 4th period | Progress made during 4th period | Variance during 4th period | Further actions at end of 4th period | Proof of delivery (document URLs or file names) 4th period | Type of document 4th period | Status at end of 5th period | Progress made during 5th period | Variance during 5th period | Further actions at end of 5th period | Proof of delivery (document URLs or file names) 5th period | Type of document 5th period | Status | INSTRUCTIONS â
Output 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Number of plans, policies, laws, or regulations drafted or updated | 1 | Planning document | 2024-12-31 | Policy, regulation or other guideline | A long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document would inform the design of policy, regulatory and fiscal/financial incentive schemes/programs for the Government of Sri Lanka to support the implementation of electric public transport to initiate low carbon transport development in Sri Lanka through a participatory and consultative process | Plan approved and adopted by Government of Sri Lanka | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003/1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council |  |  | On track | Preliminary stakeholder consultations with all relevant stakeholders were initiated to inform the structure and scope of the ‘Sustainable Low-Carbon Transport Planning’ document. This marks the first step toward developing a national framework to guide policies, regulations, and incentive schemes supporting electric public transport in Sri Lanka. | During stakeholder consultations, the Ministry of Transport(MoT) informed that an e-mobility policy has already been developed for Sri Lanka. Therefore,MoT requested project support to develop a comprehensive national transport policy that integrates the existing e-mobility policy and prioritizes the proposed policy studies under the project. | As requested by the MoT,the project will prioritize the proposed studies to align with national transport policy development needs and will act as the convener for stakeholder discussions to support the integrated policy development process. | https://drive.google.com/drive/folders/1yw3D1n1KfFFT8QULOoRzAmeTlbESfi5y?usp=sharing https://docs.google.com/document/d/1LnGebV5KI5nxSxPJiN7ZSpqMVmTcE_ah/edit?usp=sharing&ouid=114488615266959522143&rtpof=true&sd=true |  | Delayed | Following the change in Government in 2025, several discussions were held with the new administration, resulting in an agreement to reformulate the Planning Document as the Sustainable and Inclusive E‑Mobility Action Plan. This revised approach retains the original scope while expanding it to explicitly incorporate inclusiveness. | With delays in implementation kick-off and changes to the requirements, the project had closely worked with the Ministry to identify the new scope, and the project working group worked to catch up on delays by handling simultaneous tasks. | The Project commissioned a major consultancy contract to undertake this task, among several other assessments and target studies. The Project is to complete this action plan in Q2 of 2026. The Project is to complete the initial consultations and review of existing work, such as the e-mobility policy (draft), in Jan-Feb 2026. | GOSL Approval: https://drive.google.com/file/d/1-XJ9I6T0tm4LSUyA6zvxkmjFeshuJMSS/view?usp=sharing Monitoring Committee Appointment: https://drive.google.com/file/d/1SOhO7KzhWr4dPLI5WpJcNabS7_ZXihjt/view?usp=drive_link Inception (draft): https://drive.google.com/file/d/1R8FWlUHAlo0x9OZUk8sPw5G3JYvHIWtu/view?usp=sharing | Meeting report | [19 empty] | The first 8 columns in this table contain the planned project items (outcomes, outputs, and activities) for this implementer agreement. These items are listed in ascending order by item number. Scroll up and down the list to ensure you see all project items. Columns to the right of the project item list contain fields that must be completed for each project item at the indicated reporting period. Scroll left and right to find the relevant reporting period under which to enter results. Note that results entered for previous reporting periods will be locked for editing and cannot be changed once they have been approved. Complete all cells for each project item in the relevant reporting period. No cell should be left blank. If there is no progress to report for an item, enter "N/A", "Not started", or "No change". Cells with grey backgrounds are locked from editing. This includes projects items that have been marked as complete in the previous reporting period.
Activity 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | Policy, project, or tool design | #VALUE! | null | By project end | Policy, regulation or other guideline | A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-carbon Transport Masterplan' document prepared for Sri Lanka, that includes a multi-modal transport plan for Sri Lanka detailing the role of different modes of transport - rail, public transport buses, private buses, private passenger vehicles, commercial vehicles, bicycles, pedestrian pathways and others based on the principles of low-carbon, sustainable transport. The Masterplan document would serve as a guidance for all future transport sector programs, activities and investments in Sri Lanka, including the low-carbon electric public bus transport deployment activity proposed under this CCAC project. | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003/1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council |  |  | On track | A draft gender analysis was prepared to support stakeholder discussions.The analysis aimed to identify gender gaps and opportunities in public transport sector. Initial consultations with key stakeholders were conducted to inform the structure and direction of a gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document for Sri Lanka. | N/A | The Ministry of Transport expressed interest in prioritizing this study to inform national transport policy development and to strengthen gender and inclusivity considerations within the policy framework.As a result, this activity will be prioritized, and the planning document will be drafted and finalized through further stakeholder consultations. | https://drive.google.com/drive/folders/1cTKRr-W2XZukl5k7G3OXM5ZeS0ruBOqP?usp=sharing |  | On track | The project has started revising project's gender action plan in light of the latest (land) transport policy and the proposed e-mobility action plan. Gender and inclusive development actions be integrated across above E-Mobility Action Plan and other project activities in Q1 and Q 2, 2026. | N/A |  | GCIEP Technical Assiatnce to be implemented in parellel; https://docs.google.com/document/d/1AfNuiFgDzZvH7-VsXEBAitPkVoc_hslY/edit?usp=sharing&ouid=114728566611712740051&rtpof=true&sd=true
Activity 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Developing and/or delivering training | #VALUE! | null | By project end | Participant list with gender breakdown | Training modules developed and training programs that will build capacity of at least 20 trainees (30% of them being women) delivered on 'Long-term Sustainable Low-carbon Transport Planning' for government stakeholders (MoTH, MoP&E, NTC, WPRPTA, SLTB) and private stakeholders (bus operators, others as necessary); the training modules will include gender-specific, climate change adaptation and accessibility/inclusivity aspects as well. | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003/1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council |  |  | On track | Draft Terms of Reference (ToRs) were developed to recruit service providers for the design and delivery of training modules on ‘Long-term Sustainable Low-Carbon Transport Planning. | N/A | Initiate the procurement process to recruit service providers for conducting training needs assessments and developing training modules. |  |  | On track | The project has contracted the initial training module development, and training is to begin in Q1 2026. The training programme series will include targeted training for GoSL entities on policy and regulatory reforms, commercial and financial institutions, and private sector operators. The training module development is being undertaken in parellel to the E-Mobility Action plan (Output 1.2 above). |  |  | TOR (Section on Awareness and Training) : https://drive.google.com/file/d/1nYWEXMnROKqFX5-HqhV3dtxQ7ZnNY0E4/view?usp=sharing
Output 1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | Number of plans, policies, laws, or regulations drafted or updated | 1 | Policy and regulatory framework | 2025-06-30 | Policy, regulation or other guideline, Policy, regulation or other guideline | A comprehensive policy on operationalising electric buses for public transport in Sri Lanka developed through necessary assessments will be the first step towards deploying low-carbon transport for use in the country. This includes policy and regulatory framework on defining electric buses, technical and safety features of such buses to be procured, their operation mechanism including charging, end of life use, battery and vehicle disposal etc | Policy and regulatory framework approved and adopted by Government of Sri Lanka | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003/1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council |  |  | On track | During the reporting period, UNDP consulted various stakeholders, including regular discussions with the World Bank, which recently completed a study on "Supporting the Modernization of the Bus Transport Sector in Sri Lanka." A key outcome of these discussions, supported by all stakeholders, was the consensus to ensure that ongoing and planned e-mobility initiatives are complementary and avoid duplication. | N/A | UNDP will build upon the World Bank’s study, conducting further analysis and making necessary adjustments to avoid any duplication of efforts. | https://drive.google.com/drive/folders/1yw3D1n1KfFFT8QULOoRzAmeTlbESfi5y?usp=sharing |  | Delayed | The policy and regulatory framework assessment has been started after a series of stakeholder consultations in Dec 2025. The analysis is due in Q1 of 2026.
Activity 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | Policy, project, or tool design | #VALUE! | null | By project end | Policy, regulation or other guideline | A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' will be developed together with the Ministry of Transport and Highways, NTC and WPRPTA. It will then be submitted for Government and Stakeholder feedback; Framework will be revised/updated based on feedback and final Framework approved and operationalized by the Government of Sri Lanka. | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003/1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council |  |  | On track | An initial draft of the gender and inclusivity gap assessment was developed to support stakeholder discussions. This was aimed to inform the development of a comprehensive, gender-sensitive, and inclusive Electric Bus Mobility Policy and Regulatory Framework with the support of the Ministry of Transport.The Terms of Reference (ToR) to recruit consultants for developing the framework has been drafted. | N/A | Initiate the procurement process to recruit the service providers | https://drive.google.com/drive/folders/1cTKRr-W2XZukl5k7G3OXM5ZeS0ruBOqP?usp=sharing |  | On track | The policy and regulatory framework assessment in progress inlcudes gender equity and social inclusion analysis. The work completed includes the consultations of key stakeholders on these focus aspects including the Ministry of Women and Child Affairs. The initial completed gender and inclsive development assessment will be stregthened through further consultations and analysis, and this work is due in Q1 of 2026 with final round of key stakeholder consultations to validate the task outcomes. | N/A
Output 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Number of SLCP knowledge resources or tools produced | 3 | Studies/reports | 2024-11-30 | Research or study | Impact studies, analytical reports on identification of gaps to implementing low-carbon transport and electric vehicles in Sri Lanka on various aspects as well as recommendations on future scale-up of such transport and electric vehicle deployment and disposal of ICE vehicles will be conducted under this output. | Studies/reports are reviewed and approved by CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003/1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council |  |  | On track | Based on discussions with MoT and relevant instituitions ,the studies and analytical reports planned under this activity will be considered a priority towards the policy formulation.Draft ToRs were developed and shared with stakeholder review for their review |  | Finalize the draft ToR in consultation with stakeholders and initiate the procurement process |  |  | On track | The project is to undertake a series of analytical studies in Q1 2026, including Total Cost of Ownership (TCO) analyses to identify financing gaps for promoting e-mobility, supporting the phase-out of older ICE vehicles, and developing battery disposal plans. These are in addition to the route-specific e-bus pilot techno-economic analysis and design. These analyses will be supported by the same lead contractor. (linked with Output 1.2 -1.4)
Activity 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | Research, data collection, and/or report writing | #VALUE! | null | By project end | Research or study | An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved together with Public Utilities Commission of Sri Lanka (PUCSL) and Ceylon Electricity Board (CEB), under the guidance of Ministry of Power and Energy(MoP&E). | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003/1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Power and Energy, Public Utilities Commission of Sri Lanka, Ceylon Electricity Board |  |  | On track | Discussions were held with the Public Utilities Commission of Sri Lanka (PUCSL), Ceylon Electricity Board (CEB), and other key stakeholders on the impact of electric public bus transport on the national grid. It was recognized that a proper analysis is pending, and all stakeholders welcomed and requested prioritization of the proposed project study. The Terms of Reference (ToR) to recruit a consultant to develop the (study has been drafted. (the strikethrough is the typo from the formula) | N/A | Initiate the procurement process to recruit service providers to conduct the electricity grid impact study and engage relevant stakeholders throughout the assessment. |  |  | On track | The consultant group is onboard, and initial desk analysis and stakeholder consulations have been completed. An initial assessment is to be completed in Q1 of 2026.
Activity 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | Research, data collection, and/or report writing | #VALUE! | null | By project end | Research or study | An analytical report on gaps in policies and regulatory framework, institutional, private and financial sector capacity/training needs and financial gap is completed and approved, with a focus on bridging this gap to ensure scaling up of EV integration into the transport sector in Sri Lanka | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003/1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council |  |  | On track | The draft Terms of Reference to recruit consultancy services in developing the analytical report has been developed. | N/A | Initiate the procurement process to recruit consultants to develop the analytical report and support subsequent activities. |  |  | Not started | The consultancy group is on board. The task is to begin in Q1 2026.
Activity 1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | Research, data collection, and/or report writing | #VALUE! | null | By project end | Research or study | A report on recommendations and planning of disposal of old buses and vehicles if replaced with electric buses (vehicles) during future project scale-up | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003/1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council |  |  | On track | The draft Terms of Reference to recruit consultants for drafting the report on planning the replacement of ICE buses for public transport in Sri Lanka have been developed. | N/A | Initiate the procurement process in coordination with stakeholders to recruit consultants for drafting the ICE bus replacement report. |  |  | Not started | The consultancy group is on board. The task is to begin in Q1 2026.
Output 1.6 Programme Support | 0 |  | 0 | 2025-02-28 | Research or study | Viability assessments on operability of electric buses on various aspects is conducted; analytical report on improved safety, security and accessibility aspects of electric buses to make it more accommodative for women, children and physically challenged persons is also conducted | Studies/reports are reviewed and approved by CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003/1.6 Programme Support | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, Public Utilities Commission of Sri Lanka, Ceylon Electricity Board |  |  | Not started | N/A | N/A | Based on the outcomes of the stakeholder discussions, this activity was not initiated during the reporting period and is planned to commence in Q2 of the next year. |  |  | Not started | The work is to commence in Q1 2026. | [22 empty] | Not started
Activity 1.6.1 Project Support | Other | #VALUE! | null | By project end | Research or study | Viability assessment - technical, operational, financial - is completed to identify locations, EV charging technology standards (SAE Combined Charging System (CCS), CHAdeMO, Type 2 charging, Tesla Superchargers etc.) and suitable entities to own and operate these charging stations, together with necessary regulatory feasibility is completed and approved. (Typically bus charging units are sold together with the electric buses by Original Equipment Manufacturers (OEMs). However, for future scale-up, deploying solar powered charging stations are envisaged, and thus this activity becomes essential.) | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003/1.6.1 Project Support | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Power and Energy, Public Utilities Commission of Sri Lanka, Ceylon Electricity Board |  |  | Not started | N/A |  |  |  |  | Not started | The consultancy group was onboarded, and they are to begin the required analysis in Q1 & Q2 of 2026. The analysis will inform the appropriate EV charging technology, charger network ownership and business models, and technical, policy, and regulatory recommendations to improve the existing charger network to accommodate commercial transport, as applicable. This analysis will also be informed by the Grid Impact Analysis to be completed under Activity 1.4.1. | [22 empty] | Not started
Output 2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Number of SLCP knowledge resources or tools produced | 2 | Studies/reports | 2025-08-30 | Training materials, Participant list with gender breakdown, Training materials, Participant list with gender breakdown | Design and delivery of training programs for capacity building of government institutional stakeholders on various aspects of operationalising electric buses in Sri Lanka will be conducted under this output. | Attendance sheet and feedback from trainees shared with CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003/2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Private bus operators' association and private bus operators, drivers, workshop technicians, Finance House association, Insurance association, commercial banks, leasing and financing companies |  |  | Not started | N/A | N/A | N/A | N/A | N/A | Delayed | Technical, policy, and regulatory analysis is in progress, and the gaps and improvement requirements are under study. This information will be used to design a suitable training programme for GoSL institutions. | [22 empty] | Delayed
Activity 2.1.1Viability assessment of EV charging stations is completed and approved | Research, data collection, and/or report writing | #VALUE! | null | By project end | Research or study | An Analytical report on safety, security, accessibility aspects of public transport buses in Sri Lanka, particularly from the perspective of women's safety and ease of accessibility of public transport buses for elderly/children/special needs commuters is completed | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003/2.1.1Viability assessment of EV charging stations is completed and approved | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council |  |  | Not started | N/A | N/A | N/A | N/A | N/A | On track | Technical and economic analysis on the feasibility and viability of EV charging stations and grid infrastructure as a whole are progressing, and the work will be completed in Q1 of 2026. | [22 empty] | On track
Activity 2.1.2An Analytical gender (including elderly, children, specific needs commuter) specific report on safety, security, accessibility aspects of public transport buses in Sri Lanka | Research, data collection, and/or report writing | #VALUE! | null | By project end | Participant list with gender breakdown | Training programs, training at least 60 trainees (30% being women), designed and delivered for government institutional stakeholders (MoTH, MoPE, NTC, SLTB, WPRPTA, CMC) on techno-commercial (such as procurement, planning, performance evaluation, scheduling and charging infrastructure of electric bus systems), financial/economic and policy/regulatory (best practices etc.) frameworks for enabling electric bus deployment for public transport and associated bus charging stations in Sri Lanka; the training program needs to include gender-specific and accessibility/inclusivity aspects as well. | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003/2.1.2An Analytical gender (including elderly, children, specific needs commuter) specific report on safety, security, accessibility aspects of public transport buses in Sri Lanka | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council |  |  | Not started | N/A | N/A | N/A | N/A | N/A | On track | The on-boarded consultancy group has started expanding the initial gender analysis to include the safety, security, and accessibility aspects of public transport application. According to the findings of this analysis, the consultancy firm is to deliver a customized training/awareness event for key stakeholder groups in Q2 of 2026. | [22 empty] | On track
Output 2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Number of person hours of training provided | 6720 | Person hours | 2025-11-30 | Training materials, Training materials, Participant list with gender breakdown, Training materials, Training materials, Participant list with gender breakdown | Design and delivery of training programs for capacity building of private sector stakeholders on technical features of electric buses, economic/financial viability of e-buses will be conducted under this output. | Attendance sheet and feedback from trainees shared with CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003/2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council |  |  | Not started | N/A | N/A | N/A | N/A | N/A | Delayed | The selected contractual service provider is to design a general training programme series for local stakeholders (MoTH, MoP&E, NTC, DMT, WPRPTA, etc.). These will be delivered in Q1 & Q2 of 2026. | The overall progress of this output has been delayed due to the late commencement of project implementation. | [21 empty] | Delayed
Activity 2.2.1Training programs designed and delivered for government institutional stakeholders | Developing and/or delivering training | #VALUE! | null | By project end | Participant list with gender breakdown | Training programs, training at least 30 trainees (50% being women), designed and delivered for commercial banks/financial institutions (loan officers and senior executives of banks/leasing and financing companies involved in or interested in lending to electric bus mobility sector) on techno-commercial, financial/economic and policy/regulatory frameworks for enabling electric bus deployment for public transport and associated bus charging stations in Sri Lanka; the training program needs to include gender-specific and accessibility/inclusivity aspects as well. | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003/2.2.1Training programs designed and delivered for government institutional stakeholders | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Finance House association, Insurance association, commercial banks, leasing and financing companies |  |  | On track | The draft Terms of Reference (ToR) have been prepared to recruit a service provider for designing and delivering training programs for government institutional stakeholders. | N/A | Initiate the procurement process to recruit a service provider for the design and delivery of training programs for government institutional stakeholders. | N/A | N/A | On track | Planned training programme will be completed in Q1 & Q2 of 2026. | [22 empty] | On track
Output 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Number of person hours of training provided | 9840 | Person hours | 2025-10-31 | Tool, Tool, Photo or video, Tool, Tool, Photo or video | Various targeted promotional events and public awareness campaigns on benefits of using low-carbon public transport in Sri Lanka will be held to gain public support for above transition | Campaign materials and photos shared with CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003/3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public |  |  | Not started | N/A | N/A | N/A | N/A | N/A | Delayed | The project’s selected service provider contractor’s scope includes the initial training and awareness improvement of key targeted stakeholders (both public and private operators, owners, bankers, and commercial lending institutions). Planned programmes to be launched in Q1 and Q2 2026 will include at least 30% women trainees. | The overall training and awareness programme has been delayed due to the delayed start of the project. | [21 empty] | Delayed
Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Developing and/or delivering training | #VALUE! | null | By project end | Participant list with gender breakdown | Training programs, training at least 60 trainees (10% being women), designed and delivered to private bus operators, their bus drivers and workshop technicians on electric bus operational and financial feasibility (vs ICE buses), e-bus driving techniques, safety (including women's safety) and security aspects and maintenance, management of EV batteries/their scientific disposal. | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003/3.1.1Training programs designed and delivered for commercial banks/financial institutions | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Private bus operators' association and private bus operators, drivers, workshop technicians |  |  | Not started | N/A | N/A | N/A | N/A | N/A | Not started | This activity will be completed in Q2 of 2026 | [22 empty] | Not started
Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Developing and/or delivering training | #VALUE! | null | By project end | Photo or video | At least 5 multi-channel mass media, social media and PIS promotional/advertising campaign designed and executed about the benefits of public transport, particularly low-carbon options such as electric buses, rail transport, park-and-ride schemes, bicycling, walking etc. This should include ongoing television/radio advertisements, print/newspaper campaigns running for about a month. | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003/3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public |  |  | Not started | N/A | N/A | N/A | N/A | N/A | Not started | This activity will be completed in Q2 of 2026 | [22 empty] | Not started
Output 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Number of partnerships, associations, or campaigns launched to drive SLCP action | 35 | Campaigns | 2025-11-30 | Inventory, Funding proposal, Photo or video | Technical assistance provided to the government of Sri Lanka to setup and operationalise subsidy scheme to enable procurement and deployment of the first electric buses for public transport in Sri Lanka | Procurement documents reviewed and approved by CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003/3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council |  |  | Not started | N/A | N/A | N/A | N/A | N/A | Delayed | A draft Terms of Reference is available to recruit a professional service provider company to undertake a comprehensive media and public awareness campaign regarding the benefits of using public transport in general. | [22 empty] | Delayed
Activity 3.2.1Mass media promotional campaigns on benefits of public transport | Producing and distributing communications materials | #VALUE! | null | By project end | Photo or video | At least 20 targeted promotional events (town-level/community-level, at SLTB bus stations, schools or corporate offices) designed, planned and executed on the benefits of using public transport | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003/3.2.1Mass media promotional campaigns on benefits of public transport | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public |  |  | Not started | N/A | N/A | N/A | N/A | N/A | On track | This scope is also included in above contractual assignment. | [22 empty] | On track
Activity 3.2.2Targeted promotional events on benefits of public transport | Organising, holding, or participating in a meeting or event | #VALUE! | null | By project end | Photo or video | At least 10 targeted campaigns planned and executed on safety and comfort features on public transport buses, such as women's safety due to installation of CCTV cameras and road/driver safety features on electric buses | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003/3.2.2Targeted promotional events on benefits of public transport | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public |  |  | Not started | N/A | N/A | N/A | N/A | N/A | On track | This scope is also included in above contractual assignment. | [22 empty] | On track
Activity 3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | Producing and distributing communications materials | #VALUE! | null | By project end | Tool | Enhanced capital subsidy scheme (including the procedure for application, evaluation, verification and disbursement of capital subsidies) is instituted under a government programme, offering subsidies up to an indicative level of 30% of capital costs of an electric bus based on current estimates of capital costs. | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003/3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council |  |  | Not started | N/A | N/A | N/A | N/A | N/A | On track | This scope is also included in above contractual assignment. | [22 empty] | On track
Output 4.1 5 small/medium 9-metre buses deployed through public private partnerships in Colombo Municipal area after selection of vendor/OEM through a competitive tender process as per UN procurement rules | Number of tools, equipment, or technologies installed | 5 | Electric buses | 2026-05-15 | Meeting report, Participant list with gender breakdown, Photo or video, Meeting report, Participant list with gender breakdown, Photo or video, Meeting report, Participant list with gender breakdown, Photo or video, Meeting report, Participant list with gender breakdown, Photo or video | An informative webinar will be conducted to convey the project's objectives, approach, outcomes achieved and learnings to all relevant participants. | Webinar material reviewed and approved by CCAC; webinar attended by CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003/4.1 5 small/medium 9-metre buses deployed through public private partnerships in Colombo Municipal area after selection of vendor/OEM through a competitive tender process as per UN procurement rules | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | null |  |  | Not started | N/A | N/A | N/A | N/A | N/A | Delayed | Discussions are ongoing with the new administration to identify suitable routes and PPP models. The Ministry’s political and administrative leadership has agreed to provide route suggestions aligned with national priorities by the end of Jan 2026, which will inform UNDP’s planning. The PPP model has been discussed in principle, with further studies underway to finalize the implementation approach. | The initial approval delay has delayed the kick-off of this major activity. The two consulting partners are fully equipped with the necessary technical experts to guide the development of the pilot and its deployment. | [21 empty] | Delayed
Activity 4.1.1Technical assistance to setup a mechanism for channelling of enhanced grants as capital subsidy scheme | Policy, project, or tool design | #VALUE! | null | By project end | Inventory | Five electric buses on public transport routes within Colombo city are procured and deployed with support from capital subsidy instituted in the previous activity. | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003/4.1.1Technical assistance to setup a mechanism for channelling of enhanced grants as capital subsidy scheme | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | null |  |  | Not started | N/A | N/A | N/A | N/A | N/A | Not started | [23 empty] | Not started
Activity 4.1.2Five electric buses on public transport routes are procured and deployed with support from enhanced capital subsidy scheme and leased to public/private bus operator | Other | #VALUE! | null | By project end | Meeting report | Webinar materials will be developed and delivered to all project stakeholders and CCAC | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003/4.1.2Five electric buses on public transport routes are procured and deployed with support from enhanced capital subsidy scheme and leased to public/private bus operator | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | null |  |  | Not started | N/A | N/A | N/A | N/A | N/A | Not started | [23 empty] | Not started
Output 5.1 A 45- to 60-minute webinar about the project approach and outcomes delivered to CCAC partners and project stakeholders no later than the project end date | Number of public events, webinars, or side events hosted | 1 | Number of webinars held | 2026-05-15 | Research or study, Research or study | A case study on the project experience will be produced to help guide future scale-up and active involvement of private sector. | Case study reviewed and approved by CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003/5.1 A 45- to 60-minute webinar about the project approach and outcomes delivered to CCAC partners and project stakeholders no later than the project end date | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | null |  |  | Not started | N/A | N/A | N/A | N/A | N/A | On track | This task is included in the selected lead contractual service provider's scope of work and will begin in Q2 2026. The lead contractor is to organize and conduct one webinar for project partners and national stakeholders to share project outcomes, lessons learned, pilot specific-case studies, and recommendations. | [22 empty] | On track
Activity 5.1.1 A 45- to 60-minute webinar about the project approach and outcomes developed and delivered to CCAC partners and project stakeholders | Producing and distributing communications materials | #VALUE! | null | By project end | Research or study | A case-study will be developed on project objectives, outcomes achieved, learnings and guidance for future scale-up | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003/5.1.1 A 45- to 60-minute webinar about the project approach and outcomes developed and delivered to CCAC partners and project stakeholders | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | null |  |  | Not started | N/A | N/A | N/A | N/A | N/A | Not started | [23 empty] | Not started
Output 5.2 A 5- to 10-page case study or guidance document to support the replication or scale up of the project activities and/or results for potential public and private sector operators/stakeholders | Number of SLCP knowledge resources or tools produced | 1 | Document | 2026-05-31 | Tool, Tool, Inventory, Research or study | A GHG emission reduction tracking system introduced by the project will produce a report on GHG emissions reduced , after deployment of five electric buses under this project during project period and after, to compare if mitigation potential is achieved for the reporting purposes of the government of Sri Lanka | Mitigation report reviewed and approved by CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003/5.2 A 5- to 10-page case study or guidance document to support the replication or scale up of the project activities and/or results for potential public and private sector operators/stakeholders | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Environment |  |  | Not started | N/A |  | N/A | N/A | N/A | Not started | [23 empty] | Not started
Activity 5.2.1 A 5- to 10-page case study to facilitate scale up of project's activities | Producing and distributing communications materials | #VALUE! | null | By project end | Tool | A report tracking GHG emissions reductions will be instituted that will also help Sri Lankan government track its emissions reductions against its NDC targets. | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003/5.2.1 A 5- to 10-page case study to facilitate scale up of project's activities | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Environment |  |  | Not started | N/A |  | N/A | N/A | N/A | Not started | [23 empty] | Not started
Output 5.3 A report tracking mitigation potential and actual emission reduction during and immediately after project period by the deployment of 5 electric buses, for Ministry of Transport and Highways /Ministry of Environment for NDC reporting | Number of SLCP assessments, emissions inventories, and other emissions datasets produced | 1 | Report | 2026-05-31 | Tool, Tool, Research or study | A project monitoring, reporting and verification system will be developed to track project progress against objectives and update the Project Board on the same during board meetings. | Monitoring report reviewed and approved by CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003/5.3 A report tracking mitigation potential and actual emission reduction during and immediately after project period by the deployment of 5 electric buses, for Ministry of Transport and Highways /Ministry of Environment for NDC reporting | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | null |  |  | Not started | N/A |  | N/A | N/A | N/A | On track | This task is included in the selected contractual service provider's scope of work and will begin in Q1 2026. The project is to design MRVing methodology in Q1 and be implemented for e-Bus pilot programme in Q2 & Q3 of 2026. | [22 empty] | On track
Activity 5.3.1 A report/system tracking actual emission reduction from deployment of 5 e-buses against mitigation potential | Research, data collection, and/or report writing | #VALUE! | null | By project end | Tool | A monitoring, reporting and verification system is setup to track progress of project' activities and outcomes achieved are in line with its objectives | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003/5.3.1 A report/system tracking actual emission reduction from deployment of 5 e-buses against mitigation potential | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | null |  |  | Not started | N/A |  | N/A | N/A | N/A | Not started | [23 empty] | Not started
-
-
-
-
-
-
-
-
-
-
-
-

## 3. Expenditures
3. Expenditure report |  |  |  | See instructions
Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003)
UNDP Sri Lanka
PLANNED | [9 empty] | FIRST REPORTING PERIOD: 11/10/2024 - 30/06/2025 |  | SECOND REPORTING PERIOD: 01/07/2025-31/12/2025 |  | THIRD REPORTING PERIOD: 01/01/2026-30/06/2026 |  | FOURTH REPORTING PERIOD: 01/07/2026-30/11/2026 |  | FIFTH REPORTING PERIOD: |  | TOTAL EXPENDITURE
Related activity | Category | Source | Total budget | Year 1 Cost (US$) | Year 2 Cost (US$) | Year 3 cost (US$) | Implementer agreement | Project | Unique code | Expenditure (US$) during 1st period | Comments on 1st period | Expenditure (US$) during 2nd period | Comments on 2nd period | Expenditure (US$) during 3rd period | Comments on 3rd period | Expenditure (US$) during 4th period | Comments on 4th period | Expenditure (US$) during 5th period | Comments on 5th period | Total Expenditure | Variance | Var.% | INSTRUCTIONS
Activity 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | Staff and Other Personnel Costs | CCAC | 25000 | 25000 | 0 | 0 | HDV-23-003/1.2.1-1 International consultant | Vehicles & Engines | 25000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation. | 38260 | [7 empty] | 38260 | 13260 | 53.04% | The first 12 columns in this table contain the budgeted costs for this implementer agreement. These costs are listed in ascending order by expenditure number. Scroll up and down the list to ensure you see all expenditure items. Columns to the right of the budget list contain fields that must be completed for each expenditure item at the indicated reporting period. Scroll left and right to find the relevant reporting period under which to enter expenditures. Note that expenditures and comments entered for previous reporting periods will be locked for editing and cannot be changed once they have been approved. Complete all cells for each expenditure item in the relevant reporting period. No cell should be left blank. If there is no expenditure to report for an item, enter "0" in the expenditure column and "N/A" or "Not started" in the notes column.
Activity 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | Staff and Other Personnel Costs | CCAC | 12000 | 12000 | 0 | 0 | HDV-23-003/1.2.1-2 National consultant | Vehicles & Engines | 12000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation. | 13033 | [7 empty] | 13033 | 1033 | 8.608%
Activity 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | Travel | CCAC | 500 | 500 | 0 | 0 | HDV-23-003/1.2.1-3 Travel fare | Vehicles & Engines | 500 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | Travel | CCAC | 3840 | 3840 | 0 | 0 | HDV-23-003/1.2.1-4 DSA for international consultant | Vehicles & Engines | 3840 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | Travel | CCAC | 1220 | 1220 | 0 | 0 | HDV-23-003/1.2.1-5 DSA for national consultant | Vehicles & Engines | 1220 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Staff and Other Personnel Costs | CCAC | 5000 | 5000 | 0 | 0 | HDV-23-003/1.2.2-1 International consultant | Vehicles & Engines | 5000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Staff and Other Personnel Costs | CCAC | 4000 | 4000 | 0 | 0 | HDV-23-003/1.2.2-2 National consultant | Vehicles & Engines | 4000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Supplies Commodities and Materials | CCAC | 500 | 500 | 0 | 0 | HDV-23-003/1.2.2-6 Printing materials, handouts, audio-visual material | Vehicles & Engines | 500 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Travel | CCAC | 500 | 500 | 0 | 0 | HDV-23-003/1.2.2-3 Travel fare | Vehicles & Engines | 500 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Travel | CCAC | 1344 | 1344 | 0 | 0 | HDV-23-003/1.2.2-4 DSA for international consultant | Vehicles & Engines | 1344 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Travel | CCAC | 610 | 610 | 0 | 0 | HDV-23-003/1.2.2-5 DSA for national consultant | Vehicles & Engines | 610 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | Staff and Other Personnel Costs | CCAC | 25000 | 25000 | 0 | 0 | HDV-23-003/1.3.1-1 International consultant | Vehicles & Engines | 25000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation. | 16291 | [7 empty] | 16291 | -8709 | -34.84%
Activity 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | Staff and Other Personnel Costs | CCAC | 15000 | 15000 | 0 | 0 | HDV-23-003/1.3.1-2 National consultant | Vehicles & Engines | 15000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | Travel | CCAC | 1000 | 1000 | 0 | 0 | HDV-23-003/1.3.1-3 Travel fare | Vehicles & Engines | 1000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | Travel | CCAC | 3840 | 3840 | 0 | 0 | HDV-23-003/1.3.1-4 DSA for international consultant | Vehicles & Engines | 3840 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | Travel | CCAC | 1464 | 1464 | 0 | 0 | HDV-23-003/1.3.1-5 DSA for national consultant | Vehicles & Engines | 1464 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | Staff and Other Personnel Costs | CCAC | 10000 | 10000 | 0 | 0 | HDV-23-003/1.4.1-1 International consultant | Vehicles & Engines | 10000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation. | 19884 | [7 empty] | 19884 | 9884 | 98.84%
Activity 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | Staff and Other Personnel Costs | CCAC | 8000 | 8000 | 0 | 0 | HDV-23-003/1.4.1-2 National consultant | Vehicles & Engines | 8000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | Travel | CCAC | 500 | 500 | 0 | 0 | HDV-23-003/1.4.1-3 Travel fare | Vehicles & Engines | 500 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | Travel | CCAC | 1920 | 1920 | 0 | 0 | HDV-23-003/1.4.1-4 DSA for international consultant | Vehicles & Engines | 1920 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | Travel | CCAC | 854 | 854 | 0 | 0 | HDV-23-003/1.4.1-5 DSA for national consultant | Vehicles & Engines | 854 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | Staff and Other Personnel Costs | CCAC | 10000 | 10000 | 0 | 0 | HDV-23-003/1.4.2-1 International consultant | Vehicles & Engines | 10000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | Staff and Other Personnel Costs | CCAC | 10000 | 10000 | 0 | 0 | HDV-23-003/1.4.2-2 National consultant | Vehicles & Engines | 10000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | Travel | CCAC | 500 | 500 | 0 | 0 | HDV-23-003/1.4.2-3 Travel fare | Vehicles & Engines | 500 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | Travel | CCAC | 1920 | 1920 | 0 | 0 | HDV-23-003/1.4.2-4 DSA for international consultant | Vehicles & Engines | 1920 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | Travel | CCAC | 976 | 976 | 0 | 0 | HDV-23-003/1.4.2-5 DSA for national consultant | Vehicles & Engines | 976 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | Staff and Other Personnel Costs | CCAC | 2500 | 2500 | 0 | 0 | HDV-23-003/1.4.3-1 International consultant | Vehicles & Engines | 2500 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | Staff and Other Personnel Costs | CCAC | 2000 | 2000 | 0 | 0 | HDV-23-003/1.4.3-2 National consultant | Vehicles & Engines | 2000 |  | "No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | Travel | CCAC | 244 | 244 | 0 | 0 | HDV-23-003/1.4.3-3 DSA for national consultant | Vehicles & Engines | 244 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 1.6.1 Project Support | UN-PSC | CCAC | 58075 | 58075 | 0 | 0 | HDV-23-003/1.6.1-3 GMS and UN Coordinator Levy | Vehicles & Engines | 58075 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 2.1.1Viability assessment of EV charging stations is completed and approved | Staff and Other Personnel Costs | CCAC | 10000 | 10000 | 0 | 0 | HDV-23-003/2.1.1-1 International consultant | Vehicles & Engines | 10000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation. | 16291 | [7 empty] | 16291 | 6291 | 62.91%
Activity 2.1.1Viability assessment of EV charging stations is completed and approved | Staff and Other Personnel Costs | CCAC | 8000 | 8000 | 0 | 0 | HDV-23-003/2.1.1-2 National consultant | Vehicles & Engines | 8000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 2.1.1Viability assessment of EV charging stations is completed and approved | Travel | CCAC | 500 | 500 | 0 | 0 | HDV-23-003/2.1.1-3 Travel fare | Vehicles & Engines | 500 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 2.1.1Viability assessment of EV charging stations is completed and approved | Travel | CCAC | 1920 | 1920 | 0 | 0 | HDV-23-003/2.1.1-4 DSA for international consultant | Vehicles & Engines | 1920 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 2.1.1Viability assessment of EV charging stations is completed and approved | Travel | CCAC | 854 | 854 | 0 | 0 | HDV-23-003/2.1.1-5 DSA for national consultant | Vehicles & Engines | 854 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 2.1.2An Analytical gender (including elderly, children, specific needs commuter) specific report on safety, security, accessibility aspects of public transport buses in Sri Lanka | Staff and Other Personnel Costs | CCAC | 12000 | 12000 | 0 | 0 | HDV-23-003/2.1.2-1 National consultant | Vehicles & Engines | 12000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 2.1.2An Analytical gender (including elderly, children, specific needs commuter) specific report on safety, security, accessibility aspects of public transport buses in Sri Lanka | Travel | CCAC | 1220 | 1220 | 0 | 0 | HDV-23-003/2.1.2-2 DSA for national consultant | Vehicles & Engines | 1220 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 2.2.1Training programs designed and delivered for government institutional stakeholders | Staff and Other Personnel Costs | CCAC | 15000 | 0 | 15000 | 0 | HDV-23-003/2.2.1-1 International consultant | Vehicles & Engines | 15000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation. | 6517 | [7 empty] | 6517 | -8483 | -56.55%
Activity 2.2.1Training programs designed and delivered for government institutional stakeholders | Staff and Other Personnel Costs | CCAC | 10000 | 0 | 10000 | 0 | HDV-23-003/2.2.1-2 National consultant | Vehicles & Engines | 10000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 2.2.1Training programs designed and delivered for government institutional stakeholders | Supplies Commodities and Materials | CCAC | 2000 | 0 | 2000 | 0 | HDV-23-003/2.2.1-6 Printing materials, handouts, audio-visual material | Vehicles & Engines | 2000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 2.2.1Training programs designed and delivered for government institutional stakeholders | Travel | CCAC | 1000 | 0 | 1000 | 0 | HDV-23-003/2.2.1-3 Travel fare | Vehicles & Engines | 1000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 2.2.1Training programs designed and delivered for government institutional stakeholders | Travel | CCAC | 3264 | 0 | 3264 | 0 | HDV-23-003/2.2.1-4 DSA for international consultant | Vehicles & Engines | 3264 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 2.2.1Training programs designed and delivered for government institutional stakeholders | Travel | CCAC | 1708 | 0 | 1708 | 0 | HDV-23-003/2.2.1-5 DSA for national consultant | Vehicles & Engines | 1708 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Contractual Services | CCAC | 2000 | 0 | 2000 | 0 | HDV-23-003/3.1.1-7 Training venue and other contractual services | Vehicles & Engines | 2000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation. | 6517 | [7 empty] | 6517 | 4517 | 225.9%
Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Staff and Other Personnel Costs | CCAC | 7500 | 0 | 7500 | 0 | HDV-23-003/3.1.1-1 International consultant | Vehicles & Engines | 7500 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Staff and Other Personnel Costs | CCAC | 6000 | 0 | 6000 | 0 | HDV-23-003/3.1.1-2 National consultant | Vehicles & Engines | 6000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Supplies Commodities and Materials | CCAC | 1740 | 0 | 1740 | 0 | HDV-23-003/3.1.1-6 Printing materials, handouts, audio-visual material | Vehicles & Engines | 1740 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Travel | CCAC | 500 | 0 | 500 | 0 | HDV-23-003/3.1.1-3 Travel fare | Vehicles & Engines | 500 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Travel | CCAC | 2880 | 0 | 2880 | 0 | HDV-23-003/3.1.1-4 DSA for international consultant | Vehicles & Engines | 2880 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Travel | CCAC | 1708 | 0 | 1708 | 0 | HDV-23-003/3.1.1-5 DSA for national consultant | Vehicles & Engines | 1708 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Contractual Services | CCAC | 2000 | 0 | 2000 | 0 | HDV-23-003/3.1.2-7 Training venue and other contractual services | Vehicles & Engines | 2000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Staff and Other Personnel Costs | CCAC | 15000 | 0 | 15000 | 0 | HDV-23-003/3.1.2-1 International consultant | Vehicles & Engines | 15000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Staff and Other Personnel Costs | CCAC | 8000 | 0 | 8000 | 0 | HDV-23-003/3.1.2-2 National consultant | Vehicles & Engines | 8000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Supplies Commodities and Materials | CCAC | 2000 | 0 | 2000 | 0 | HDV-23-003/3.1.2-6 Printing materials, handouts, audio-visual material | Vehicles & Engines | 2000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Travel | CCAC | 500 | 0 | 500 | 0 | HDV-23-003/3.1.2-3 Travel fare | Vehicles & Engines | 500 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Travel | CCAC | 3264 | 0 | 3264 | 0 | HDV-23-003/3.1.2-4 DSA for international consultant | Vehicles & Engines | 3264 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Travel | CCAC | 1708 | 0 | 1708 | 0 | HDV-23-003/3.1.2-5 DSA for national consultant | Vehicles & Engines | 1708 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 3.2.1Mass media promotional campaigns on benefits of public transport | Contractual Services | CCAC | 30000 | 20000 | 10000 | 0 | HDV-23-003/3.2.1-4 Training venue and other contractual services | Vehicles & Engines | 30000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 3.2.1Mass media promotional campaigns on benefits of public transport | Staff and Other Personnel Costs | CCAC | 5600 | 5600 | 0 | 0 | HDV-23-003/3.2.1-1 National consultant | Vehicles & Engines | 5600 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 3.2.1Mass media promotional campaigns on benefits of public transport | Supplies Commodities and Materials | CCAC | 2500 | 1666.6667 | 833.3333 | 0 | HDV-23-003/3.2.1-3 Audio visual material, posters, handouts | Vehicles & Engines | 2500 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 3.2.1Mass media promotional campaigns on benefits of public transport | Travel | CCAC | 854 | 854 | 0 | 0 | HDV-23-003/3.2.1-2 DSA for national consultant | Vehicles & Engines | 854 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 3.2.2Targeted promotional events on benefits of public transport | Contractual Services | CCAC | 30000 | 0 | 30000 | 0 | HDV-23-003/3.2.2-4 Training venue and other contractual services | Vehicles & Engines | 30000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 3.2.2Targeted promotional events on benefits of public transport | Staff and Other Personnel Costs | CCAC | 6000 | 0 | 6000 | 0 | HDV-23-003/3.2.2-1 National consultant | Vehicles & Engines | 6000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 3.2.2Targeted promotional events on benefits of public transport | Supplies Commodities and Materials | CCAC | 2000 | 0 | 2000 | 0 | HDV-23-003/3.2.2-3 Audio visual material, posters, handouts | Vehicles & Engines | 2000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 3.2.2Targeted promotional events on benefits of public transport | Travel | CCAC | 854 | 0 | 854 | 0 | HDV-23-003/3.2.2-2 DSA for national consultant | Vehicles & Engines | 854 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | Contractual Services | CCAC | 15000 | 0 | 15000 | 0 | HDV-23-003/3.2.3-4 Training venue and other contractual services | Vehicles & Engines | 15000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | Staff and Other Personnel Costs | CCAC | 6000 | 0 | 6000 | 0 | HDV-23-003/3.2.3-1 National consultant | Vehicles & Engines | 6000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | Supplies Commodities and Materials | CCAC | 2000 | 0 | 2000 | 0 | HDV-23-003/3.2.3-3 Audio visual material, posters, handouts | Vehicles & Engines | 2000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | Travel | CCAC | 854 | 0 | 854 | 0 | HDV-23-003/3.2.3-2 DSA for national consultant | Vehicles & Engines | 854 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 4.1.1Technical assistance to setup a mechanism for channelling of enhanced grants as capital subsidy scheme | Staff and Other Personnel Costs | CCAC | 20000 | 0 | 20000 | 0 | HDV-23-003/4.1.1-1 National consultant | Vehicles & Engines | 20000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation. | 13405 | [7 empty] | 13405 | -6595 | -32.98%
Activity 4.1.1Technical assistance to setup a mechanism for channelling of enhanced grants as capital subsidy scheme | Travel | CCAC | 2440 | 0 | 2440 | 0 | HDV-23-003/4.1.1-2 DSA for national consultant | Vehicles & Engines | 2440 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 4.1.2Five electric buses on public transport routes are procured and deployed with support from enhanced capital subsidy scheme and leased to public/private bus operator | Equipment Vehicles and Furniture | CCAC | 225000 | 0 | 225000 | 0 | HDV-23-003/4.1.2-1 Procurement of Electric Buses | Vehicles & Engines | 225000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 5.1.1 A 45- to 60-minute webinar about the project approach and outcomes developed and delivered to CCAC partners and project stakeholders | Staff and Other Personnel Costs | CCAC | 3000 | 0 | 0 | 3000 | HDV-23-003/5.1.1-1 National consultant | Vehicles & Engines | 3000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation. | 6581 | [7 empty] | 6581 | 3581 | 119.4%
Activity 5.2.1 A 5- to 10-page case study to facilitate scale up of project's activities | Staff and Other Personnel Costs | CCAC | 3000 | 0 | 0 | 3000 | HDV-23-003/5.2.1-1 National consultant | Vehicles & Engines | 3000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 5.3.1 A report/system tracking actual emission reduction from deployment of 5 e-buses against mitigation potential | Staff and Other Personnel Costs | CCAC | 6000 | 0 | 6000 | 0 | HDV-23-003/5.3.1-1 National consultant | Vehicles & Engines | 6000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.
Activity 5.4.1 An MRV system setup and managed by PMU to track project progress and report to the Project Board and CCAC | Staff and Other Personnel Costs | CCAC | 6000 | 6000 | 0 | 0 | HDV-23-003/5.4.1-1 National consultant | Vehicles & Engines | 6000 |  | No expenditures were incurred due to the delay in obtaining approval from the National Planning Department(NPD), which is mandatory before project implementation.

## 4. Outputs
4. Output indicators |  | See instructions
Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003)
UNDP Sri Lanka
Outputs to report by project end: 12 | [12 empty] | RELEVANT DOCUMENT 1 (optional) | [7 empty] | RELEVANT DOCUMENT 2 (optional)
Output | Indicator | Target | Unit | Indicator unit of measure | Amount delivered | Disaggregation info instructions 1 | Dissagregation info (if requested) | Disaggregation info instructions 2 | Dissagregation info (if requested)2 | Additional info instructions | Additional info (if requested) | Pollutants directly addressed | Document title | Document summary | Document URL | Add to the CCAC website? | Document type | Authors | Sources | Date published (m yy) | Document title2 | Document summary2 | Document URL2 | Add to the CCAC website?2 | Document type2 | Authors2 | Sources2 | Date published (m yy)2 | Unique code | Sector | Project | Beneficiaries | Implementer | Complete? | INSTRUCTIONS
Output 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Number of plans, policies, laws, or regulations drafted or updated | 1 | Planning document | Amount: |  | Type: |  | Scale: |  | SLCP mitigation actions and/or targets included: | [18 empty] | HDV-23-003/1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Sri Lanka | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | no | The first 4 columns in this table list the outputs, indicators, and targets for this implementer agreement in ascending order by output number. Columns to the right of the output list contain instructions on how to report on the performance indicators selected for the output. Information in this table is reported only once for each output and only after the output is marked as "Complete" in the tab "2. Narrative." All cells in this table must be completed unless they are marked as "optional".
Output 1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | Number of plans, policies, laws, or regulations drafted or updated | 1 | Policy and regulatory framework | Amount: |  | Type: |  | Scale: |  | SLCP mitigation actions and/or targets included: | [18 empty] | HDV-23-003/1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Sri Lanka | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | no
Output 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Number of SLCP knowledge resources or tools produced | 3 | Studies/reports | Number of resources produced: |  | Type of resource: |  | n/a |  | Briefly descbribe how the resource is being used by the intended audience: | [18 empty] | HDV-23-003/1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Sri Lanka | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | no
Output 1.6 Programme Support | 0 | 0 | 0 | [25 empty] | HDV-23-003/1.6 Programme Support | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Sri Lanka | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | no
Output 2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Number of SLCP knowledge resources or tools produced | 2 | Studies/reports | Number of resources produced: |  | Type of resource: |  | n/a |  | Briefly descbribe how the resource is being used by the intended audience: | [18 empty] | HDV-23-003/2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Sri Lanka | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | no
Output 2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Number of person hours of training provided | 6720 | Person hours | Number of initiatives: |  | Type of action: |  | Scale: |  | Mitigation actions, targets: | [18 empty] | HDV-23-003/2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Sri Lanka | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | #VALUE!
Output 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Number of person hours of training provided | 9840 | Person hours | Number of initiatives: |  | Type of action: |  | Scale: |  | Mitigation actions, targets: | [18 empty] | HDV-23-003/3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Sri Lanka | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | #VALUE!
Output 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Number of partnerships, associations, or campaigns launched to drive SLCP action | 35 | Campaigns | Number of initiatives: |  | Type of action: |  | Scale: |  | Mitigation actions, targets: | [18 empty] | HDV-23-003/3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Sri Lanka | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | no
Output 4.1 5 small/medium 9-metre buses deployed through public private partnerships in Colombo Municipal area after selection of vendor/OEM through a competitive tender process as per UN procurement rules | Number of tools, equipment, or technologies installed | 5 | Electric buses | Number of resources produced: |  | Type of resource: |  | n/a |  | Briefly descbribe how the resource is being used by the intended audience: | [18 empty] | HDV-23-003/4.1 5 small/medium 9-metre buses deployed through public private partnerships in Colombo Municipal area after selection of vendor/OEM through a competitive tender process as per UN procurement rules | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Sri Lanka | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | no
Output 5.1 A 45- to 60-minute webinar about the project approach and outcomes delivered to CCAC partners and project stakeholders no later than the project end date | Number of public events, webinars, or side events hosted | 1 | Number of webinars held | Number of events hosted: |  | Size of event: |  | n/a |  | Link to the event details: | [18 empty] | HDV-23-003/5.1 A 45- to 60-minute webinar about the project approach and outcomes delivered to CCAC partners and project stakeholders no later than the project end date | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Sri Lanka | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | no
Output 5.2 A 5- to 10-page case study or guidance document to support the replication or scale up of the project activities and/or results for potential public and private sector operators/stakeholders | Number of SLCP knowledge resources or tools produced | 1 | Document | Number of resources produced: |  | Type of resource: |  | n/a |  | Briefly descbribe how the resource is being used by the intended audience: | [18 empty] | HDV-23-003/5.2 A 5- to 10-page case study or guidance document to support the replication or scale up of the project activities and/or results for potential public and private sector operators/stakeholders | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Sri Lanka | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | no
Output 5.3 A report tracking mitigation potential and actual emission reduction during and immediately after project period by the deployment of 5 electric buses, for Ministry of Transport and Highways /Ministry of Environment for NDC reporting | Number of SLCP assessments, emissions inventories, and other emissions datasets produced | 1 | Report | Amount: |  | Type: |  | n/a |  | Briefly describe what was produced and how this information will be used by the beneficiary: | [18 empty] | HDV-23-003/5.3 A report tracking mitigation potential and actual emission reduction during and immediately after project period by the deployment of 5 electric buses, for Ministry of Transport and Highways /Ministry of Environment for NDC reporting | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Sri Lanka | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | no

## Paste Implementation Plan here (hidden)
1. Paste entire Implementation Plan table here. 2. Check that columns match. Delete duplicate headings. 3. Click: Data > Refresh all 4. Filter by implementer + (blank). Save a copy for each implementer 5. "Permanently" hide this tab - Developer > Visual basic.
Selected agreement:
Agreement
United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
RELATED ACTIVITY | EXPENDITURE CATEGORY | EXPENDITURE # | DESCRIPTION OF EXPENDITURE | IMPLEMENTER | NOTES | SOURCE OF FUNDING | QUANTITY | UNIT | UNIT COST ($US) | TOTAL COST | YEAR 1 COST ($US) | YEAR 2 COST ($US) | YEAR 3 COST ($US) | ADD UP TO TOTAL? | Activity code | Expenditure for summary | Related activity for summary | Implementer agreement | Unique code | Expenditure/Code | Expenditure/Level above | Expenditure/Level | Project | Activities.RELATED OUTPUT | Activities.ACTIVITY # | Activities.ACTIVITY NAME | Activities.ACTIVITY DESCRIPTION | Activities.ACTIVITY CATEGORY | Activities.AMOUNT | Activities.UNIT | Activities.IMPLEMENTER | Activities.LOCATION | Activities.BENEFICIARY COUNTRIES | Activities.OTHER BENEFICIARIES | Activities.ACTIVITY START DATE | Activities.ACTIVITY END DATE | Activities.PROOF OF DELIVERY TYPE | Delivery description | Activities.DELIVERY DATE | Activities.CCAC ACCEPTANCE CRITERIA | Activities.Output # for formula | Activities.Activity for summary | Activities.Related output for summary | Activities.Activity name for list | Activities.Activity/Unique code | Activities.Activity/Code/Name | Activities.Activity/Level above | Activities.Activity/Level | Activities.Activity/Project | Outputs.OUTPUT # | Outputs.OUTPUT NAME | Outputs.DESCRIPTION | Outputs.RELATED OUTCOME | Outputs.INDICATOR | Outputs.AMOUNT | Outputs.UNIT | Outputs.IMPLEMENTER | Outputs.USERS/BENEFICIARIES | Outputs.OTHER BENEFICIARIES | Outputs.INTENDED USE | Outputs.PROOF OF DELIVERY TYPE | Outputs.DELIVERY DESCRIPTION | Outputs.DELIVERY DATE | Outputs.CCAC ACCEPTANCE CRITERIA | Outputs.Output for dropdown | Outputs.Output for summary | Outputs.Related outcome for summary | Outputs.Output/Unique code | Outputs.Output/Code/Name | Outputs.Output/Level | Outputs.Output/Level above | Outputs.Output/Project | Outcomes.OUTCOME # | Outcomes.OUTCOME NAME | Outcomes.OUTCOME DESCRIPTION | Outcomes.OUTCOME INDICATOR | Outcomes.TARGET | Outcomes.TARGET UNIT | Outcomes.Outcome for dropdown | Outcomes.Outcome for summary | Outcomes.Unique code | Outcomes.Outcome/Code | Outcomes.Outcome/Level above | Outcomes.Oucome/Level | Outcomes.Outcome/Project | Project.1.PROJECT # | Project.1.Sector | Project.1.Full project name | Expenditure.Agreement-Implementer | Output.Agreement-Implementer | Activity.Agreement-Implementer | Kolom1 | Kolom2 | Kolom3 | Kolom4 | Kolom5 | Kolom6 | Kolom7 | Kolom8 | Kolom9 | Kolom10 | Kolom11 | Kolom12 | Kolom13 | Kolom14 | Kolom15
1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | Staff and Other Personnel Costs | 1.2.1-1 | International consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 50 | Days | 500 | 25000 | 25000 | 0 | 0 | Yes. | 1/2/2001 | Expenditure 1.2.1-1 International consultant | Activity 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.2.1-1 | HDV-23-003/1.2.1-1 International consultant | HDV-23-003/1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | 1.2.1 | 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-carbon Transport Masterplan' document prepared for Sri Lanka, that includes a multi-modal transport plan for Sri Lanka detailing the role of different modes of transport - rail, public transport buses, private buses, private passenger vehicles, commercial vehicles, bicycles, pedestrian pathways and others based on the principles of low-carbon, sustainable transport. The Masterplan document would serve as a guidance for all future transport sector programs, activities and investments in Sri Lanka, including the low-carbon electric public bus transport deployment activity proposed under this CCAC project. | Policy, project, or tool design | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | 7/1/2024 | 12/31/2024 | Policy, regulation or other guideline | null | null | null | 1.2 | Activity 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | Output 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | HDV-23-003/1.2.1 | HDV-23-003/1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | HDV-23-003/1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.2 | Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | A long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document would inform the design of policy, regulatory and fiscal/financial incentive schemes/programs for the Government of Sri Lanka to support the implementation of electric public transport to initiate low carbon transport development in Sri Lanka through a participatory and consultative process | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Number of plans, policies, laws, or regulations drafted or updated | 1 | Planning document | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Technical assistance and training provided under this output will enable the beneficiaries to develop a comprehensive low-carbon transport planning and guidance document for Sri Lanka; thus also creating an enabling policy, regulatory and institutional environment for low carbon transport in general and electric vehicles in particular. | Policy, regulation or other guideline | null | 12/31/2024 | Plan approved and adopted by Government of Sri Lanka | 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Output 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1.2 | HDV-23-003/1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Output | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1 | Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | By providing necessary technical assistance to develop a Sustainable Transport Plan and formulating relevant regulatory policy for using electric vehicles, specifically electric buses for public transport in Sri Lanka, including training for government stakholders and various feasibility studies for actual deployment of electric buses. Estimated completion date: 18 months from project start date | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 3 | 1 national policy/plan/ regulations drafted or updated.1 guidelines and 1 assessment completed | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1. | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | Staff and Other Personnel Costs | 1.2.1-2 | National consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 60 | Days | 200 | 12000 | 12000 | 0 | 0 | Yes. | 1/2/2001 | Expenditure 1.2.1-2 National consultant | Activity 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.2.1-2 | HDV-23-003/1.2.1-2 National consultant | HDV-23-003/1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | 1.2.1 | 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-carbon Transport Masterplan' document prepared for Sri Lanka, that includes a multi-modal transport plan for Sri Lanka detailing the role of different modes of transport - rail, public transport buses, private buses, private passenger vehicles, commercial vehicles, bicycles, pedestrian pathways and others based on the principles of low-carbon, sustainable transport. The Masterplan document would serve as a guidance for all future transport sector programs, activities and investments in Sri Lanka, including the low-carbon electric public bus transport deployment activity proposed under this CCAC project. | Policy, project, or tool design | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | 7/1/2024 | 12/31/2024 | Policy, regulation or other guideline | null | null | null | 1.2 | Activity 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | Output 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | HDV-23-003/1.2.1 | HDV-23-003/1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | HDV-23-003/1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.2 | Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | A long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document would inform the design of policy, regulatory and fiscal/financial incentive schemes/programs for the Government of Sri Lanka to support the implementation of electric public transport to initiate low carbon transport development in Sri Lanka through a participatory and consultative process | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Number of plans, policies, laws, or regulations drafted or updated | 1 | Planning document | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Technical assistance and training provided under this output will enable the beneficiaries to develop a comprehensive low-carbon transport planning and guidance document for Sri Lanka; thus also creating an enabling policy, regulatory and institutional environment for low carbon transport in general and electric vehicles in particular. | Policy, regulation or other guideline | null | 12/31/2024 | Plan approved and adopted by Government of Sri Lanka | 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Output 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1.2 | HDV-23-003/1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Output | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1 | Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | By providing necessary technical assistance to develop a Sustainable Transport Plan and formulating relevant regulatory policy for using electric vehicles, specifically electric buses for public transport in Sri Lanka, including training for government stakholders and various feasibility studies for actual deployment of electric buses. Estimated completion date: 18 months from project start date | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 3 | 1 national policy/plan/ regulations drafted or updated.1 guidelines and 1 assessment completed | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1. | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | Travel | 1.2.1-3 | Travel fare | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 1 | Ticket fare for consultants | 500 | 500 | 500 | 0 | 0 | Yes. | 1/2/2001 | Expenditure 1.2.1-3 Travel fare | Activity 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.2.1-3 | HDV-23-003/1.2.1-3 Travel fare | HDV-23-003/1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | 1.2.1 | 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-carbon Transport Masterplan' document prepared for Sri Lanka, that includes a multi-modal transport plan for Sri Lanka detailing the role of different modes of transport - rail, public transport buses, private buses, private passenger vehicles, commercial vehicles, bicycles, pedestrian pathways and others based on the principles of low-carbon, sustainable transport. The Masterplan document would serve as a guidance for all future transport sector programs, activities and investments in Sri Lanka, including the low-carbon electric public bus transport deployment activity proposed under this CCAC project. | Policy, project, or tool design | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | 7/1/2024 | 12/31/2024 | Policy, regulation or other guideline | null | null | null | 1.2 | Activity 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | Output 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | HDV-23-003/1.2.1 | HDV-23-003/1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | HDV-23-003/1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.2 | Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | A long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document would inform the design of policy, regulatory and fiscal/financial incentive schemes/programs for the Government of Sri Lanka to support the implementation of electric public transport to initiate low carbon transport development in Sri Lanka through a participatory and consultative process | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Number of plans, policies, laws, or regulations drafted or updated | 1 | Planning document | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Technical assistance and training provided under this output will enable the beneficiaries to develop a comprehensive low-carbon transport planning and guidance document for Sri Lanka; thus also creating an enabling policy, regulatory and institutional environment for low carbon transport in general and electric vehicles in particular. | Policy, regulation or other guideline | null | 12/31/2024 | Plan approved and adopted by Government of Sri Lanka | 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Output 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1.2 | HDV-23-003/1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Output | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1 | Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | By providing necessary technical assistance to develop a Sustainable Transport Plan and formulating relevant regulatory policy for using electric vehicles, specifically electric buses for public transport in Sri Lanka, including training for government stakholders and various feasibility studies for actual deployment of electric buses. Estimated completion date: 18 months from project start date | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 3 | 1 national policy/plan/ regulations drafted or updated.1 guidelines and 1 assessment completed | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1. | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | Travel | 1.2.1-4 | DSA for international consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 20 | Days | 192 | 3840 | 3840 | 0 | 0 | Yes. | 1/2/2001 | Expenditure 1.2.1-4 DSA for international consultant | Activity 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.2.1-4 | HDV-23-003/1.2.1-4 DSA for international consultant | HDV-23-003/1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | 1.2.1 | 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-carbon Transport Masterplan' document prepared for Sri Lanka, that includes a multi-modal transport plan for Sri Lanka detailing the role of different modes of transport - rail, public transport buses, private buses, private passenger vehicles, commercial vehicles, bicycles, pedestrian pathways and others based on the principles of low-carbon, sustainable transport. The Masterplan document would serve as a guidance for all future transport sector programs, activities and investments in Sri Lanka, including the low-carbon electric public bus transport deployment activity proposed under this CCAC project. | Policy, project, or tool design | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | 7/1/2024 | 12/31/2024 | Policy, regulation or other guideline | null | null | null | 1.2 | Activity 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | Output 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | HDV-23-003/1.2.1 | HDV-23-003/1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | HDV-23-003/1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.2 | Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | A long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document would inform the design of policy, regulatory and fiscal/financial incentive schemes/programs for the Government of Sri Lanka to support the implementation of electric public transport to initiate low carbon transport development in Sri Lanka through a participatory and consultative process | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Number of plans, policies, laws, or regulations drafted or updated | 1 | Planning document | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Technical assistance and training provided under this output will enable the beneficiaries to develop a comprehensive low-carbon transport planning and guidance document for Sri Lanka; thus also creating an enabling policy, regulatory and institutional environment for low carbon transport in general and electric vehicles in particular. | Policy, regulation or other guideline | null | 12/31/2024 | Plan approved and adopted by Government of Sri Lanka | 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Output 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1.2 | HDV-23-003/1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Output | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1 | Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | By providing necessary technical assistance to develop a Sustainable Transport Plan and formulating relevant regulatory policy for using electric vehicles, specifically electric buses for public transport in Sri Lanka, including training for government stakholders and various feasibility studies for actual deployment of electric buses. Estimated completion date: 18 months from project start date | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 3 | 1 national policy/plan/ regulations drafted or updated.1 guidelines and 1 assessment completed | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1. | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | Travel | 1.2.1-5 | DSA for national consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 10 | Days | 122 | 1220 | 1220 | 0 | 0 | Yes. | 1/2/2001 | Expenditure 1.2.1-5 DSA for national consultant | Activity 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.2.1-5 | HDV-23-003/1.2.1-5 DSA for national consultant | HDV-23-003/1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | 1.2.1 | 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-carbon Transport Masterplan' document prepared for Sri Lanka, that includes a multi-modal transport plan for Sri Lanka detailing the role of different modes of transport - rail, public transport buses, private buses, private passenger vehicles, commercial vehicles, bicycles, pedestrian pathways and others based on the principles of low-carbon, sustainable transport. The Masterplan document would serve as a guidance for all future transport sector programs, activities and investments in Sri Lanka, including the low-carbon electric public bus transport deployment activity proposed under this CCAC project. | Policy, project, or tool design | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | 7/1/2024 | 12/31/2024 | Policy, regulation or other guideline | null | null | null | 1.2 | Activity 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | Output 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | HDV-23-003/1.2.1 | HDV-23-003/1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | HDV-23-003/1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.2 | Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | A long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document would inform the design of policy, regulatory and fiscal/financial incentive schemes/programs for the Government of Sri Lanka to support the implementation of electric public transport to initiate low carbon transport development in Sri Lanka through a participatory and consultative process | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Number of plans, policies, laws, or regulations drafted or updated | 1 | Planning document | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Technical assistance and training provided under this output will enable the beneficiaries to develop a comprehensive low-carbon transport planning and guidance document for Sri Lanka; thus also creating an enabling policy, regulatory and institutional environment for low carbon transport in general and electric vehicles in particular. | Policy, regulation or other guideline | null | 12/31/2024 | Plan approved and adopted by Government of Sri Lanka | 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Output 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1.2 | HDV-23-003/1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Output | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1 | Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | By providing necessary technical assistance to develop a Sustainable Transport Plan and formulating relevant regulatory policy for using electric vehicles, specifically electric buses for public transport in Sri Lanka, including training for government stakholders and various feasibility studies for actual deployment of electric buses. Estimated completion date: 18 months from project start date | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 3 | 1 national policy/plan/ regulations drafted or updated.1 guidelines and 1 assessment completed | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1. | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Staff and Other Personnel Costs | 1.2.2-1 | International consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 10 | Days | 500 | 5000 | 5000 | 0 | 0 | Yes. | 1/2/2002 | Expenditure 1.2.2-1 International consultant | Activity 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.2.2-1 | HDV-23-003/1.2.2-1 International consultant | HDV-23-003/1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | 1.2.2 | 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Training modules developed and training programs that will build capacity of at least 20 trainees (30% of them being women) delivered on 'Long-term Sustainable Low-carbon Transport Planning' for government stakeholders (MoTH, MoP&E, NTC, WPRPTA, SLTB) and private stakeholders (bus operators, others as necessary); the training modules will include gender-specific, climate change adaptation and accessibility/inclusivity aspects as well. | Developing and/or delivering training | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | 12/1/2024 | 12/31/2024 | Participant list with gender breakdown | null | null | null | 1.2 | Activity 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Output 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | HDV-23-003/1.2.2 | HDV-23-003/1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | HDV-23-003/1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.2 | Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | A long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document would inform the design of policy, regulatory and fiscal/financial incentive schemes/programs for the Government of Sri Lanka to support the implementation of electric public transport to initiate low carbon transport development in Sri Lanka through a participatory and consultative process | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Number of plans, policies, laws, or regulations drafted or updated | 1 | Planning document | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Technical assistance and training provided under this output will enable the beneficiaries to develop a comprehensive low-carbon transport planning and guidance document for Sri Lanka; thus also creating an enabling policy, regulatory and institutional environment for low carbon transport in general and electric vehicles in particular. | Policy, regulation or other guideline | null | 12/31/2024 | Plan approved and adopted by Government of Sri Lanka | 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Output 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1.2 | HDV-23-003/1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Output | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1 | Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | By providing necessary technical assistance to develop a Sustainable Transport Plan and formulating relevant regulatory policy for using electric vehicles, specifically electric buses for public transport in Sri Lanka, including training for government stakholders and various feasibility studies for actual deployment of electric buses. Estimated completion date: 18 months from project start date | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 3 | 1 national policy/plan/ regulations drafted or updated.1 guidelines and 1 assessment completed | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1. | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Staff and Other Personnel Costs | 1.2.2-2 | National consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 20 | Days | 200 | 4000 | 4000 | 0 | 0 | Yes. | 1/2/2002 | Expenditure 1.2.2-2 National consultant | Activity 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.2.2-2 | HDV-23-003/1.2.2-2 National consultant | HDV-23-003/1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | 1.2.2 | 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Training modules developed and training programs that will build capacity of at least 20 trainees (30% of them being women) delivered on 'Long-term Sustainable Low-carbon Transport Planning' for government stakeholders (MoTH, MoP&E, NTC, WPRPTA, SLTB) and private stakeholders (bus operators, others as necessary); the training modules will include gender-specific, climate change adaptation and accessibility/inclusivity aspects as well. | Developing and/or delivering training | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | 12/1/2024 | 12/31/2024 | Participant list with gender breakdown | null | null | null | 1.2 | Activity 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Output 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | HDV-23-003/1.2.2 | HDV-23-003/1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | HDV-23-003/1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.2 | Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | A long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document would inform the design of policy, regulatory and fiscal/financial incentive schemes/programs for the Government of Sri Lanka to support the implementation of electric public transport to initiate low carbon transport development in Sri Lanka through a participatory and consultative process | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Number of plans, policies, laws, or regulations drafted or updated | 1 | Planning document | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Technical assistance and training provided under this output will enable the beneficiaries to develop a comprehensive low-carbon transport planning and guidance document for Sri Lanka; thus also creating an enabling policy, regulatory and institutional environment for low carbon transport in general and electric vehicles in particular. | Policy, regulation or other guideline | null | 12/31/2024 | Plan approved and adopted by Government of Sri Lanka | 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Output 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1.2 | HDV-23-003/1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Output | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1 | Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | By providing necessary technical assistance to develop a Sustainable Transport Plan and formulating relevant regulatory policy for using electric vehicles, specifically electric buses for public transport in Sri Lanka, including training for government stakholders and various feasibility studies for actual deployment of electric buses. Estimated completion date: 18 months from project start date | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 3 | 1 national policy/plan/ regulations drafted or updated.1 guidelines and 1 assessment completed | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1. | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Travel | 1.2.2-3 | Travel fare | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 1 | Ticket fare for consultants | 500 | 500 | 500 | 0 | 0 | Yes. | 1/2/2002 | Expenditure 1.2.2-3 Travel fare | Activity 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.2.2-3 | HDV-23-003/1.2.2-3 Travel fare | HDV-23-003/1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | 1.2.2 | 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Training modules developed and training programs that will build capacity of at least 20 trainees (30% of them being women) delivered on 'Long-term Sustainable Low-carbon Transport Planning' for government stakeholders (MoTH, MoP&E, NTC, WPRPTA, SLTB) and private stakeholders (bus operators, others as necessary); the training modules will include gender-specific, climate change adaptation and accessibility/inclusivity aspects as well. | Developing and/or delivering training | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | 12/1/2024 | 12/31/2024 | Participant list with gender breakdown | null | null | null | 1.2 | Activity 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Output 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | HDV-23-003/1.2.2 | HDV-23-003/1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | HDV-23-003/1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.2 | Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | A long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document would inform the design of policy, regulatory and fiscal/financial incentive schemes/programs for the Government of Sri Lanka to support the implementation of electric public transport to initiate low carbon transport development in Sri Lanka through a participatory and consultative process | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Number of plans, policies, laws, or regulations drafted or updated | 1 | Planning document | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Technical assistance and training provided under this output will enable the beneficiaries to develop a comprehensive low-carbon transport planning and guidance document for Sri Lanka; thus also creating an enabling policy, regulatory and institutional environment for low carbon transport in general and electric vehicles in particular. | Policy, regulation or other guideline | null | 12/31/2024 | Plan approved and adopted by Government of Sri Lanka | 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Output 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1.2 | HDV-23-003/1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Output | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1 | Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | By providing necessary technical assistance to develop a Sustainable Transport Plan and formulating relevant regulatory policy for using electric vehicles, specifically electric buses for public transport in Sri Lanka, including training for government stakholders and various feasibility studies for actual deployment of electric buses. Estimated completion date: 18 months from project start date | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 3 | 1 national policy/plan/ regulations drafted or updated.1 guidelines and 1 assessment completed | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1. | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Travel | 1.2.2-4 | DSA for international consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 7 | Days | 192 | 1344 | 1344 | 0 | 0 | Yes. | 1/2/2002 | Expenditure 1.2.2-4 DSA for international consultant | Activity 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.2.2-4 | HDV-23-003/1.2.2-4 DSA for international consultant | HDV-23-003/1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | 1.2.2 | 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Training modules developed and training programs that will build capacity of at least 20 trainees (30% of them being women) delivered on 'Long-term Sustainable Low-carbon Transport Planning' for government stakeholders (MoTH, MoP&E, NTC, WPRPTA, SLTB) and private stakeholders (bus operators, others as necessary); the training modules will include gender-specific, climate change adaptation and accessibility/inclusivity aspects as well. | Developing and/or delivering training | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | 12/1/2024 | 12/31/2024 | Participant list with gender breakdown | null | null | null | 1.2 | Activity 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Output 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | HDV-23-003/1.2.2 | HDV-23-003/1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | HDV-23-003/1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.2 | Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | A long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document would inform the design of policy, regulatory and fiscal/financial incentive schemes/programs for the Government of Sri Lanka to support the implementation of electric public transport to initiate low carbon transport development in Sri Lanka through a participatory and consultative process | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Number of plans, policies, laws, or regulations drafted or updated | 1 | Planning document | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Technical assistance and training provided under this output will enable the beneficiaries to develop a comprehensive low-carbon transport planning and guidance document for Sri Lanka; thus also creating an enabling policy, regulatory and institutional environment for low carbon transport in general and electric vehicles in particular. | Policy, regulation or other guideline | null | 12/31/2024 | Plan approved and adopted by Government of Sri Lanka | 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Output 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1.2 | HDV-23-003/1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Output | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1 | Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | By providing necessary technical assistance to develop a Sustainable Transport Plan and formulating relevant regulatory policy for using electric vehicles, specifically electric buses for public transport in Sri Lanka, including training for government stakholders and various feasibility studies for actual deployment of electric buses. Estimated completion date: 18 months from project start date | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 3 | 1 national policy/plan/ regulations drafted or updated.1 guidelines and 1 assessment completed | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1. | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Travel | 1.2.2-5 | DSA for national consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 5 | Days | 122 | 610 | 610 | 0 | 0 | Yes. | 1/2/2002 | Expenditure 1.2.2-5 DSA for national consultant | Activity 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.2.2-5 | HDV-23-003/1.2.2-5 DSA for national consultant | HDV-23-003/1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | 1.2.2 | 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Training modules developed and training programs that will build capacity of at least 20 trainees (30% of them being women) delivered on 'Long-term Sustainable Low-carbon Transport Planning' for government stakeholders (MoTH, MoP&E, NTC, WPRPTA, SLTB) and private stakeholders (bus operators, others as necessary); the training modules will include gender-specific, climate change adaptation and accessibility/inclusivity aspects as well. | Developing and/or delivering training | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | 12/1/2024 | 12/31/2024 | Participant list with gender breakdown | null | null | null | 1.2 | Activity 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Output 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | HDV-23-003/1.2.2 | HDV-23-003/1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | HDV-23-003/1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.2 | Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | A long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document would inform the design of policy, regulatory and fiscal/financial incentive schemes/programs for the Government of Sri Lanka to support the implementation of electric public transport to initiate low carbon transport development in Sri Lanka through a participatory and consultative process | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Number of plans, policies, laws, or regulations drafted or updated | 1 | Planning document | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Technical assistance and training provided under this output will enable the beneficiaries to develop a comprehensive low-carbon transport planning and guidance document for Sri Lanka; thus also creating an enabling policy, regulatory and institutional environment for low carbon transport in general and electric vehicles in particular. | Policy, regulation or other guideline | null | 12/31/2024 | Plan approved and adopted by Government of Sri Lanka | 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Output 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1.2 | HDV-23-003/1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Output | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1 | Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | By providing necessary technical assistance to develop a Sustainable Transport Plan and formulating relevant regulatory policy for using electric vehicles, specifically electric buses for public transport in Sri Lanka, including training for government stakholders and various feasibility studies for actual deployment of electric buses. Estimated completion date: 18 months from project start date | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 3 | 1 national policy/plan/ regulations drafted or updated.1 guidelines and 1 assessment completed | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1. | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Supplies Commodities and Materials | 1.2.2-6 | Printing materials, handouts, audio-visual material | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 1 | Training materials | 500 | 500 | 500 | 0 | 0 | Yes. | 1/2/2002 | Expenditure 1.2.2-6 Printing materials, handouts, audio-visual material | Activity 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.2.2-6 | HDV-23-003/1.2.2-6 Printing materials, handouts, audio-visual material | HDV-23-003/1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | 1.2.2 | 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Training modules developed and training programs that will build capacity of at least 20 trainees (30% of them being women) delivered on 'Long-term Sustainable Low-carbon Transport Planning' for government stakeholders (MoTH, MoP&E, NTC, WPRPTA, SLTB) and private stakeholders (bus operators, others as necessary); the training modules will include gender-specific, climate change adaptation and accessibility/inclusivity aspects as well. | Developing and/or delivering training | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | 12/1/2024 | 12/31/2024 | Participant list with gender breakdown | null | null | null | 1.2 | Activity 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Output 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | HDV-23-003/1.2.2 | HDV-23-003/1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | HDV-23-003/1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.2 | Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | A long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document would inform the design of policy, regulatory and fiscal/financial incentive schemes/programs for the Government of Sri Lanka to support the implementation of electric public transport to initiate low carbon transport development in Sri Lanka through a participatory and consultative process | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Number of plans, policies, laws, or regulations drafted or updated | 1 | Planning document | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Technical assistance and training provided under this output will enable the beneficiaries to develop a comprehensive low-carbon transport planning and guidance document for Sri Lanka; thus also creating an enabling policy, regulatory and institutional environment for low carbon transport in general and electric vehicles in particular. | Policy, regulation or other guideline | null | 12/31/2024 | Plan approved and adopted by Government of Sri Lanka | 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Output 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1.2 | HDV-23-003/1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Output | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1 | Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | By providing necessary technical assistance to develop a Sustainable Transport Plan and formulating relevant regulatory policy for using electric vehicles, specifically electric buses for public transport in Sri Lanka, including training for government stakholders and various feasibility studies for actual deployment of electric buses. Estimated completion date: 18 months from project start date | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 3 | 1 national policy/plan/ regulations drafted or updated.1 guidelines and 1 assessment completed | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1. | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | Staff and Other Personnel Costs | 1.3.1-1 | International consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 50 | Days | 500 | 25000 | 25000 | 0 | 0 | Yes. | 1/3/2001 | Expenditure 1.3.1-1 International consultant | Activity 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.3.1-1 | HDV-23-003/1.3.1-1 International consultant | HDV-23-003/1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | 1.3.1 | 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' will be developed together with the Ministry of Transport and Highways, NTC and WPRPTA. It will then be submitted for Government and Stakeholder feedback; Framework will be revised/updated based on feedback and final Framework approved and operationalized by the Government of Sri Lanka. | Policy, project, or tool design | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | 7/1/2024 | 7/30/2025 | Policy, regulation or other guideline | null | null | null | 1.3 | Activity 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | Output 1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | HDV-23-003/1.3.1 | HDV-23-003/1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | HDV-23-003/1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.3 | Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | A comprehensive policy on operationalising electric buses for public transport in Sri Lanka developed through necessary assessments will be the first step towards deploying low-carbon transport for use in the country. This includes policy and regulatory framework on defining electric buses, technical and safety features of such buses to be procured, their operation mechanism including charging, end of life use, battery and vehicle disposal etc | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Number of plans, policies, laws, or regulations drafted or updated | 1 | Policy and regulatory framework | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | technical assistance and training provided under this output will enable the beneficiaries to develop a comprehensive electric bus policy and regulatory framework for operationalising use of e-buses in Sri Lanka; thus also helping create an enabling policy, regulatory and institutional environment for electric vehicles overall in the future. | Policy, regulation or other guideline, Policy, regulation or other guideline | null | 6/30/2025 | Policy and regulatory framework approved and adopted by Government of Sri Lanka | 1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | Output 1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1.3 | HDV-23-003/1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | Output | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1 | Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | By providing necessary technical assistance to develop a Sustainable Transport Plan and formulating relevant regulatory policy for using electric vehicles, specifically electric buses for public transport in Sri Lanka, including training for government stakholders and various feasibility studies for actual deployment of electric buses. Estimated completion date: 18 months from project start date | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 3 | 1 national policy/plan/ regulations drafted or updated.1 guidelines and 1 assessment completed | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1. | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | Staff and Other Personnel Costs | 1.3.1-2 | National consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 75 | Days | 200 | 15000 | 15000 | 0 | 0 | Yes. | 1/3/2001 | Expenditure 1.3.1-2 National consultant | Activity 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.3.1-2 | HDV-23-003/1.3.1-2 National consultant | HDV-23-003/1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | 1.3.1 | 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' will be developed together with the Ministry of Transport and Highways, NTC and WPRPTA. It will then be submitted for Government and Stakeholder feedback; Framework will be revised/updated based on feedback and final Framework approved and operationalized by the Government of Sri Lanka. | Policy, project, or tool design | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | 7/1/2024 | 7/30/2025 | Policy, regulation or other guideline | null | null | null | 1.3 | Activity 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | Output 1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | HDV-23-003/1.3.1 | HDV-23-003/1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | HDV-23-003/1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.3 | Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | A comprehensive policy on operationalising electric buses for public transport in Sri Lanka developed through necessary assessments will be the first step towards deploying low-carbon transport for use in the country. This includes policy and regulatory framework on defining electric buses, technical and safety features of such buses to be procured, their operation mechanism including charging, end of life use, battery and vehicle disposal etc | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Number of plans, policies, laws, or regulations drafted or updated | 1 | Policy and regulatory framework | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | technical assistance and training provided under this output will enable the beneficiaries to develop a comprehensive electric bus policy and regulatory framework for operationalising use of e-buses in Sri Lanka; thus also helping create an enabling policy, regulatory and institutional environment for electric vehicles overall in the future. | Policy, regulation or other guideline, Policy, regulation or other guideline | null | 6/30/2025 | Policy and regulatory framework approved and adopted by Government of Sri Lanka | 1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | Output 1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1.3 | HDV-23-003/1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | Output | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1 | Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | By providing necessary technical assistance to develop a Sustainable Transport Plan and formulating relevant regulatory policy for using electric vehicles, specifically electric buses for public transport in Sri Lanka, including training for government stakholders and various feasibility studies for actual deployment of electric buses. Estimated completion date: 18 months from project start date | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 3 | 1 national policy/plan/ regulations drafted or updated.1 guidelines and 1 assessment completed | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1. | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | Travel | 1.3.1-3 | Travel fare | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 2 | Ticket fare for consultants | 500 | 1000 | 1000 | 0 | 0 | Yes. | 1/3/2001 | Expenditure 1.3.1-3 Travel fare | Activity 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.3.1-3 | HDV-23-003/1.3.1-3 Travel fare | HDV-23-003/1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | 1.3.1 | 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' will be developed together with the Ministry of Transport and Highways, NTC and WPRPTA. It will then be submitted for Government and Stakeholder feedback; Framework will be revised/updated based on feedback and final Framework approved and operationalized by the Government of Sri Lanka. | Policy, project, or tool design | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | 7/1/2024 | 7/30/2025 | Policy, regulation or other guideline | null | null | null | 1.3 | Activity 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | Output 1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | HDV-23-003/1.3.1 | HDV-23-003/1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | HDV-23-003/1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.3 | Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | A comprehensive policy on operationalising electric buses for public transport in Sri Lanka developed through necessary assessments will be the first step towards deploying low-carbon transport for use in the country. This includes policy and regulatory framework on defining electric buses, technical and safety features of such buses to be procured, their operation mechanism including charging, end of life use, battery and vehicle disposal etc | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Number of plans, policies, laws, or regulations drafted or updated | 1 | Policy and regulatory framework | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | technical assistance and training provided under this output will enable the beneficiaries to develop a comprehensive electric bus policy and regulatory framework for operationalising use of e-buses in Sri Lanka; thus also helping create an enabling policy, regulatory and institutional environment for electric vehicles overall in the future. | Policy, regulation or other guideline, Policy, regulation or other guideline | null | 6/30/2025 | Policy and regulatory framework approved and adopted by Government of Sri Lanka | 1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | Output 1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1.3 | HDV-23-003/1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | Output | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1 | Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | By providing necessary technical assistance to develop a Sustainable Transport Plan and formulating relevant regulatory policy for using electric vehicles, specifically electric buses for public transport in Sri Lanka, including training for government stakholders and various feasibility studies for actual deployment of electric buses. Estimated completion date: 18 months from project start date | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 3 | 1 national policy/plan/ regulations drafted or updated.1 guidelines and 1 assessment completed | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1. | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | Travel | 1.3.1-4 | DSA for international consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 20 | Days | 192 | 3840 | 3840 | 0 | 0 | Yes. | 1/3/2001 | Expenditure 1.3.1-4 DSA for international consultant | Activity 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.3.1-4 | HDV-23-003/1.3.1-4 DSA for international consultant | HDV-23-003/1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | 1.3.1 | 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' will be developed together with the Ministry of Transport and Highways, NTC and WPRPTA. It will then be submitted for Government and Stakeholder feedback; Framework will be revised/updated based on feedback and final Framework approved and operationalized by the Government of Sri Lanka. | Policy, project, or tool design | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | 7/1/2024 | 7/30/2025 | Policy, regulation or other guideline | null | null | null | 1.3 | Activity 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | Output 1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | HDV-23-003/1.3.1 | HDV-23-003/1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | HDV-23-003/1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.3 | Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | A comprehensive policy on operationalising electric buses for public transport in Sri Lanka developed through necessary assessments will be the first step towards deploying low-carbon transport for use in the country. This includes policy and regulatory framework on defining electric buses, technical and safety features of such buses to be procured, their operation mechanism including charging, end of life use, battery and vehicle disposal etc | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Number of plans, policies, laws, or regulations drafted or updated | 1 | Policy and regulatory framework | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | technical assistance and training provided under this output will enable the beneficiaries to develop a comprehensive electric bus policy and regulatory framework for operationalising use of e-buses in Sri Lanka; thus also helping create an enabling policy, regulatory and institutional environment for electric vehicles overall in the future. | Policy, regulation or other guideline, Policy, regulation or other guideline | null | 6/30/2025 | Policy and regulatory framework approved and adopted by Government of Sri Lanka | 1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | Output 1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1.3 | HDV-23-003/1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | Output | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1 | Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | By providing necessary technical assistance to develop a Sustainable Transport Plan and formulating relevant regulatory policy for using electric vehicles, specifically electric buses for public transport in Sri Lanka, including training for government stakholders and various feasibility studies for actual deployment of electric buses. Estimated completion date: 18 months from project start date | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 3 | 1 national policy/plan/ regulations drafted or updated.1 guidelines and 1 assessment completed | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1. | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | Travel | 1.3.1-5 | DSA for national consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 12 | Days | 122 | 1464 | 1464 | 0 | 0 | Yes. | 1/3/2001 | Expenditure 1.3.1-5 DSA for national consultant | Activity 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.3.1-5 | HDV-23-003/1.3.1-5 DSA for national consultant | HDV-23-003/1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | 1.3.1 | 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' will be developed together with the Ministry of Transport and Highways, NTC and WPRPTA. It will then be submitted for Government and Stakeholder feedback; Framework will be revised/updated based on feedback and final Framework approved and operationalized by the Government of Sri Lanka. | Policy, project, or tool design | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | 7/1/2024 | 7/30/2025 | Policy, regulation or other guideline | null | null | null | 1.3 | Activity 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | Output 1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | HDV-23-003/1.3.1 | HDV-23-003/1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | HDV-23-003/1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.3 | Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | A comprehensive policy on operationalising electric buses for public transport in Sri Lanka developed through necessary assessments will be the first step towards deploying low-carbon transport for use in the country. This includes policy and regulatory framework on defining electric buses, technical and safety features of such buses to be procured, their operation mechanism including charging, end of life use, battery and vehicle disposal etc | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Number of plans, policies, laws, or regulations drafted or updated | 1 | Policy and regulatory framework | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | technical assistance and training provided under this output will enable the beneficiaries to develop a comprehensive electric bus policy and regulatory framework for operationalising use of e-buses in Sri Lanka; thus also helping create an enabling policy, regulatory and institutional environment for electric vehicles overall in the future. | Policy, regulation or other guideline, Policy, regulation or other guideline | null | 6/30/2025 | Policy and regulatory framework approved and adopted by Government of Sri Lanka | 1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | Output 1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1.3 | HDV-23-003/1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | Output | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1 | Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | By providing necessary technical assistance to develop a Sustainable Transport Plan and formulating relevant regulatory policy for using electric vehicles, specifically electric buses for public transport in Sri Lanka, including training for government stakholders and various feasibility studies for actual deployment of electric buses. Estimated completion date: 18 months from project start date | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 3 | 1 national policy/plan/ regulations drafted or updated.1 guidelines and 1 assessment completed | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1. | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | Staff and Other Personnel Costs | 1.4.1-1 | International consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 20 | Days | 500 | 10000 | 10000 | 0 | 0 | Yes. | 1/4/2001 | Expenditure 1.4.1-1 International consultant | Activity 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.4.1-1 | HDV-23-003/1.4.1-1 International consultant | HDV-23-003/1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | 1.4.1 | 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved together with Public Utilities Commission of Sri Lanka (PUCSL) and Ceylon Electricity Board (CEB), under the guidance of Ministry of Power and Energy(MoP&E). | Research, data collection, and/or report writing | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Power and Energy, Public Utilities Commission of Sri Lanka, Ceylon Electricity Board | 9/1/2024 | 11/30/2024 | Research or study | null | null | null | 1.4 | Activity 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | Output 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | HDV-23-003/1.4.1 | HDV-23-003/1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | HDV-23-003/1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.4 | Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Impact studies, analytical reports on identification of gaps to implementing low-carbon transport and electric vehicles in Sri Lanka on various aspects as well as recommendations on future scale-up of such transport and electric vehicle deployment and disposal of ICE vehicles will be conducted under this output. | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Number of SLCP knowledge resources or tools produced | 3 | Studies/reports | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | The studies/reports approved under this output will be knowledge resources used by relevant government institutions to understand and solve policy/regulatory, operational and financial challenges and plan for future scale up of low carbon transport in the country. | Research or study | null | 11/30/2024 | Studies/reports are reviewed and approved by CCAC | 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Output 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1.4 | HDV-23-003/1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Output | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1 | Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | By providing necessary technical assistance to develop a Sustainable Transport Plan and formulating relevant regulatory policy for using electric vehicles, specifically electric buses for public transport in Sri Lanka, including training for government stakholders and various feasibility studies for actual deployment of electric buses. Estimated completion date: 18 months from project start date | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 3 | 1 national policy/plan/ regulations drafted or updated.1 guidelines and 1 assessment completed | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1. | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | Staff and Other Personnel Costs | 1.4.1-2 | National consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 40 | Days | 200 | 8000 | 8000 | 0 | 0 | Yes. | 1/4/2001 | Expenditure 1.4.1-2 National consultant | Activity 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.4.1-2 | HDV-23-003/1.4.1-2 National consultant | HDV-23-003/1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | 1.4.1 | 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved together with Public Utilities Commission of Sri Lanka (PUCSL) and Ceylon Electricity Board (CEB), under the guidance of Ministry of Power and Energy(MoP&E). | Research, data collection, and/or report writing | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Power and Energy, Public Utilities Commission of Sri Lanka, Ceylon Electricity Board | 9/1/2024 | 11/30/2024 | Research or study | null | null | null | 1.4 | Activity 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | Output 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | HDV-23-003/1.4.1 | HDV-23-003/1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | HDV-23-003/1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.4 | Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Impact studies, analytical reports on identification of gaps to implementing low-carbon transport and electric vehicles in Sri Lanka on various aspects as well as recommendations on future scale-up of such transport and electric vehicle deployment and disposal of ICE vehicles will be conducted under this output. | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Number of SLCP knowledge resources or tools produced | 3 | Studies/reports | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | The studies/reports approved under this output will be knowledge resources used by relevant government institutions to understand and solve policy/regulatory, operational and financial challenges and plan for future scale up of low carbon transport in the country. | Research or study | null | 11/30/2024 | Studies/reports are reviewed and approved by CCAC | 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Output 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1.4 | HDV-23-003/1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Output | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1 | Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | By providing necessary technical assistance to develop a Sustainable Transport Plan and formulating relevant regulatory policy for using electric vehicles, specifically electric buses for public transport in Sri Lanka, including training for government stakholders and various feasibility studies for actual deployment of electric buses. Estimated completion date: 18 months from project start date | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 3 | 1 national policy/plan/ regulations drafted or updated.1 guidelines and 1 assessment completed | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1. | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | Travel | 1.4.1-3 | Travel fare | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 1 | Ticket fare for consultants | 500 | 500 | 500 | 0 | 0 | Yes. | 1/4/2001 | Expenditure 1.4.1-3 Travel fare | Activity 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.4.1-3 | HDV-23-003/1.4.1-3 Travel fare | HDV-23-003/1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | 1.4.1 | 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved together with Public Utilities Commission of Sri Lanka (PUCSL) and Ceylon Electricity Board (CEB), under the guidance of Ministry of Power and Energy(MoP&E). | Research, data collection, and/or report writing | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Power and Energy, Public Utilities Commission of Sri Lanka, Ceylon Electricity Board | 9/1/2024 | 11/30/2024 | Research or study | null | null | null | 1.4 | Activity 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | Output 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | HDV-23-003/1.4.1 | HDV-23-003/1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | HDV-23-003/1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.4 | Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Impact studies, analytical reports on identification of gaps to implementing low-carbon transport and electric vehicles in Sri Lanka on various aspects as well as recommendations on future scale-up of such transport and electric vehicle deployment and disposal of ICE vehicles will be conducted under this output. | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Number of SLCP knowledge resources or tools produced | 3 | Studies/reports | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | The studies/reports approved under this output will be knowledge resources used by relevant government institutions to understand and solve policy/regulatory, operational and financial challenges and plan for future scale up of low carbon transport in the country. | Research or study | null | 11/30/2024 | Studies/reports are reviewed and approved by CCAC | 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Output 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1.4 | HDV-23-003/1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Output | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1 | Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | By providing necessary technical assistance to develop a Sustainable Transport Plan and formulating relevant regulatory policy for using electric vehicles, specifically electric buses for public transport in Sri Lanka, including training for government stakholders and various feasibility studies for actual deployment of electric buses. Estimated completion date: 18 months from project start date | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 3 | 1 national policy/plan/ regulations drafted or updated.1 guidelines and 1 assessment completed | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1. | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | Travel | 1.4.1-4 | DSA for international consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 10 | Days | 192 | 1920 | 1920 | 0 | 0 | Yes. | 1/4/2001 | Expenditure 1.4.1-4 DSA for international consultant | Activity 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.4.1-4 | HDV-23-003/1.4.1-4 DSA for international consultant | HDV-23-003/1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | 1.4.1 | 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved together with Public Utilities Commission of Sri Lanka (PUCSL) and Ceylon Electricity Board (CEB), under the guidance of Ministry of Power and Energy(MoP&E). | Research, data collection, and/or report writing | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Power and Energy, Public Utilities Commission of Sri Lanka, Ceylon Electricity Board | 9/1/2024 | 11/30/2024 | Research or study | null | null | null | 1.4 | Activity 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | Output 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | HDV-23-003/1.4.1 | HDV-23-003/1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | HDV-23-003/1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.4 | Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Impact studies, analytical reports on identification of gaps to implementing low-carbon transport and electric vehicles in Sri Lanka on various aspects as well as recommendations on future scale-up of such transport and electric vehicle deployment and disposal of ICE vehicles will be conducted under this output. | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Number of SLCP knowledge resources or tools produced | 3 | Studies/reports | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | The studies/reports approved under this output will be knowledge resources used by relevant government institutions to understand and solve policy/regulatory, operational and financial challenges and plan for future scale up of low carbon transport in the country. | Research or study | null | 11/30/2024 | Studies/reports are reviewed and approved by CCAC | 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Output 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1.4 | HDV-23-003/1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Output | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1 | Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | By providing necessary technical assistance to develop a Sustainable Transport Plan and formulating relevant regulatory policy for using electric vehicles, specifically electric buses for public transport in Sri Lanka, including training for government stakholders and various feasibility studies for actual deployment of electric buses. Estimated completion date: 18 months from project start date | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 3 | 1 national policy/plan/ regulations drafted or updated.1 guidelines and 1 assessment completed | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1. | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | Travel | 1.4.1-5 | DSA for national consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 7 | Days | 122 | 854 | 854 | 0 | 0 | Yes. | 1/4/2001 | Expenditure 1.4.1-5 DSA for national consultant | Activity 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.4.1-5 | HDV-23-003/1.4.1-5 DSA for national consultant | HDV-23-003/1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | 1.4.1 | 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved together with Public Utilities Commission of Sri Lanka (PUCSL) and Ceylon Electricity Board (CEB), under the guidance of Ministry of Power and Energy(MoP&E). | Research, data collection, and/or report writing | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Power and Energy, Public Utilities Commission of Sri Lanka, Ceylon Electricity Board | 9/1/2024 | 11/30/2024 | Research or study | null | null | null | 1.4 | Activity 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | Output 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | HDV-23-003/1.4.1 | HDV-23-003/1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | HDV-23-003/1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.4 | Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Impact studies, analytical reports on identification of gaps to implementing low-carbon transport and electric vehicles in Sri Lanka on various aspects as well as recommendations on future scale-up of such transport and electric vehicle deployment and disposal of ICE vehicles will be conducted under this output. | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Number of SLCP knowledge resources or tools produced | 3 | Studies/reports | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | The studies/reports approved under this output will be knowledge resources used by relevant government institutions to understand and solve policy/regulatory, operational and financial challenges and plan for future scale up of low carbon transport in the country. | Research or study | null | 11/30/2024 | Studies/reports are reviewed and approved by CCAC | 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Output 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1.4 | HDV-23-003/1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Output | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1 | Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | By providing necessary technical assistance to develop a Sustainable Transport Plan and formulating relevant regulatory policy for using electric vehicles, specifically electric buses for public transport in Sri Lanka, including training for government stakholders and various feasibility studies for actual deployment of electric buses. Estimated completion date: 18 months from project start date | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 3 | 1 national policy/plan/ regulations drafted or updated.1 guidelines and 1 assessment completed | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1. | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | Staff and Other Personnel Costs | 1.4.2-1 | International consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 20 | Days | 500 | 10000 | 10000 | 0 | 0 | Yes. | 1/4/2002 | Expenditure 1.4.2-1 International consultant | Activity 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.4.2-1 | HDV-23-003/1.4.2-1 International consultant | HDV-23-003/1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | 1.4.2 | 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | An analytical report on gaps in policies and regulatory framework, institutional, private and financial sector capacity/training needs and financial gap is completed and approved, with a focus on bridging this gap to ensure scaling up of EV integration into the transport sector in Sri Lanka | Research, data collection, and/or report writing | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | 9/1/2024 | 11/30/2024 | Research or study | null | null | null | 1.4 | Activity 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | Output 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | HDV-23-003/1.4.2 | HDV-23-003/1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | HDV-23-003/1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.4 | Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Impact studies, analytical reports on identification of gaps to implementing low-carbon transport and electric vehicles in Sri Lanka on various aspects as well as recommendations on future scale-up of such transport and electric vehicle deployment and disposal of ICE vehicles will be conducted under this output. | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Number of SLCP knowledge resources or tools produced | 3 | Studies/reports | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | The studies/reports approved under this output will be knowledge resources used by relevant government institutions to understand and solve policy/regulatory, operational and financial challenges and plan for future scale up of low carbon transport in the country. | Research or study | null | 11/30/2024 | Studies/reports are reviewed and approved by CCAC | 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Output 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1.4 | HDV-23-003/1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Output | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1 | Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | By providing necessary technical assistance to develop a Sustainable Transport Plan and formulating relevant regulatory policy for using electric vehicles, specifically electric buses for public transport in Sri Lanka, including training for government stakholders and various feasibility studies for actual deployment of electric buses. Estimated completion date: 18 months from project start date | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 3 | 1 national policy/plan/ regulations drafted or updated.1 guidelines and 1 assessment completed | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1. | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | Staff and Other Personnel Costs | 1.4.2-2 | National consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 50 | Days | 200 | 10000 | 10000 | 0 | 0 | Yes. | 1/4/2002 | Expenditure 1.4.2-2 National consultant | Activity 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.4.2-2 | HDV-23-003/1.4.2-2 National consultant | HDV-23-003/1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | 1.4.2 | 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | An analytical report on gaps in policies and regulatory framework, institutional, private and financial sector capacity/training needs and financial gap is completed and approved, with a focus on bridging this gap to ensure scaling up of EV integration into the transport sector in Sri Lanka | Research, data collection, and/or report writing | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | 9/1/2024 | 11/30/2024 | Research or study | null | null | null | 1.4 | Activity 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | Output 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | HDV-23-003/1.4.2 | HDV-23-003/1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | HDV-23-003/1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.4 | Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Impact studies, analytical reports on identification of gaps to implementing low-carbon transport and electric vehicles in Sri Lanka on various aspects as well as recommendations on future scale-up of such transport and electric vehicle deployment and disposal of ICE vehicles will be conducted under this output. | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Number of SLCP knowledge resources or tools produced | 3 | Studies/reports | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | The studies/reports approved under this output will be knowledge resources used by relevant government institutions to understand and solve policy/regulatory, operational and financial challenges and plan for future scale up of low carbon transport in the country. | Research or study | null | 11/30/2024 | Studies/reports are reviewed and approved by CCAC | 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Output 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1.4 | HDV-23-003/1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Output | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1 | Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | By providing necessary technical assistance to develop a Sustainable Transport Plan and formulating relevant regulatory policy for using electric vehicles, specifically electric buses for public transport in Sri Lanka, including training for government stakholders and various feasibility studies for actual deployment of electric buses. Estimated completion date: 18 months from project start date | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 3 | 1 national policy/plan/ regulations drafted or updated.1 guidelines and 1 assessment completed | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1. | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | Travel | 1.4.2-3 | Travel fare | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 1 | Ticket fare for consultants | 500 | 500 | 500 | 0 | 0 | Yes. | 1/4/2002 | Expenditure 1.4.2-3 Travel fare | Activity 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.4.2-3 | HDV-23-003/1.4.2-3 Travel fare | HDV-23-003/1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | 1.4.2 | 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | An analytical report on gaps in policies and regulatory framework, institutional, private and financial sector capacity/training needs and financial gap is completed and approved, with a focus on bridging this gap to ensure scaling up of EV integration into the transport sector in Sri Lanka | Research, data collection, and/or report writing | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | 9/1/2024 | 11/30/2024 | Research or study | null | null | null | 1.4 | Activity 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | Output 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | HDV-23-003/1.4.2 | HDV-23-003/1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | HDV-23-003/1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.4 | Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Impact studies, analytical reports on identification of gaps to implementing low-carbon transport and electric vehicles in Sri Lanka on various aspects as well as recommendations on future scale-up of such transport and electric vehicle deployment and disposal of ICE vehicles will be conducted under this output. | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Number of SLCP knowledge resources or tools produced | 3 | Studies/reports | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | The studies/reports approved under this output will be knowledge resources used by relevant government institutions to understand and solve policy/regulatory, operational and financial challenges and plan for future scale up of low carbon transport in the country. | Research or study | null | 11/30/2024 | Studies/reports are reviewed and approved by CCAC | 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Output 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1.4 | HDV-23-003/1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Output | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1 | Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | By providing necessary technical assistance to develop a Sustainable Transport Plan and formulating relevant regulatory policy for using electric vehicles, specifically electric buses for public transport in Sri Lanka, including training for government stakholders and various feasibility studies for actual deployment of electric buses. Estimated completion date: 18 months from project start date | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 3 | 1 national policy/plan/ regulations drafted or updated.1 guidelines and 1 assessment completed | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1. | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | Travel | 1.4.2-4 | DSA for international consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 10 | Days | 192 | 1920 | 1920 | 0 | 0 | Yes. | 1/4/2002 | Expenditure 1.4.2-4 DSA for international consultant | Activity 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.4.2-4 | HDV-23-003/1.4.2-4 DSA for international consultant | HDV-23-003/1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | 1.4.2 | 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | An analytical report on gaps in policies and regulatory framework, institutional, private and financial sector capacity/training needs and financial gap is completed and approved, with a focus on bridging this gap to ensure scaling up of EV integration into the transport sector in Sri Lanka | Research, data collection, and/or report writing | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | 9/1/2024 | 11/30/2024 | Research or study | null | null | null | 1.4 | Activity 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | Output 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | HDV-23-003/1.4.2 | HDV-23-003/1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | HDV-23-003/1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.4 | Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Impact studies, analytical reports on identification of gaps to implementing low-carbon transport and electric vehicles in Sri Lanka on various aspects as well as recommendations on future scale-up of such transport and electric vehicle deployment and disposal of ICE vehicles will be conducted under this output. | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Number of SLCP knowledge resources or tools produced | 3 | Studies/reports | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | The studies/reports approved under this output will be knowledge resources used by relevant government institutions to understand and solve policy/regulatory, operational and financial challenges and plan for future scale up of low carbon transport in the country. | Research or study | null | 11/30/2024 | Studies/reports are reviewed and approved by CCAC | 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Output 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1.4 | HDV-23-003/1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Output | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1 | Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | By providing necessary technical assistance to develop a Sustainable Transport Plan and formulating relevant regulatory policy for using electric vehicles, specifically electric buses for public transport in Sri Lanka, including training for government stakholders and various feasibility studies for actual deployment of electric buses. Estimated completion date: 18 months from project start date | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 3 | 1 national policy/plan/ regulations drafted or updated.1 guidelines and 1 assessment completed | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1. | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | Travel | 1.4.2-5 | DSA for national consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 8 | Days | 122 | 976 | 976 | 0 | 0 | Yes. | 1/4/2002 | Expenditure 1.4.2-5 DSA for national consultant | Activity 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.4.2-5 | HDV-23-003/1.4.2-5 DSA for national consultant | HDV-23-003/1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | 1.4.2 | 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | An analytical report on gaps in policies and regulatory framework, institutional, private and financial sector capacity/training needs and financial gap is completed and approved, with a focus on bridging this gap to ensure scaling up of EV integration into the transport sector in Sri Lanka | Research, data collection, and/or report writing | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | 9/1/2024 | 11/30/2024 | Research or study | null | null | null | 1.4 | Activity 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | Output 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | HDV-23-003/1.4.2 | HDV-23-003/1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | HDV-23-003/1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.4 | Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Impact studies, analytical reports on identification of gaps to implementing low-carbon transport and electric vehicles in Sri Lanka on various aspects as well as recommendations on future scale-up of such transport and electric vehicle deployment and disposal of ICE vehicles will be conducted under this output. | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Number of SLCP knowledge resources or tools produced | 3 | Studies/reports | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | The studies/reports approved under this output will be knowledge resources used by relevant government institutions to understand and solve policy/regulatory, operational and financial challenges and plan for future scale up of low carbon transport in the country. | Research or study | null | 11/30/2024 | Studies/reports are reviewed and approved by CCAC | 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Output 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1.4 | HDV-23-003/1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Output | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1 | Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | By providing necessary technical assistance to develop a Sustainable Transport Plan and formulating relevant regulatory policy for using electric vehicles, specifically electric buses for public transport in Sri Lanka, including training for government stakholders and various feasibility studies for actual deployment of electric buses. Estimated completion date: 18 months from project start date | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 3 | 1 national policy/plan/ regulations drafted or updated.1 guidelines and 1 assessment completed | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1. | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | Staff and Other Personnel Costs | 1.4.3-1 | International consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 5 | Days | 500 | 2500 | 2500 | 0 | 0 | Yes. | 1/4/2003 | Expenditure 1.4.3-1 International consultant | Activity 1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.4.3-1 | HDV-23-003/1.4.3-1 International consultant | HDV-23-003/1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | 1.4.3 | 1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | A report on recommendations and planning of disposal of old buses and vehicles if replaced with electric buses (vehicles) during future project scale-up | Research, data collection, and/or report writing | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | 9/1/2024 | 11/30/2024 | Research or study | null | null | null | 1.4 | Activity 1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | Output 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | 1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | HDV-23-003/1.4.3 | HDV-23-003/1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | HDV-23-003/1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.4 | Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Impact studies, analytical reports on identification of gaps to implementing low-carbon transport and electric vehicles in Sri Lanka on various aspects as well as recommendations on future scale-up of such transport and electric vehicle deployment and disposal of ICE vehicles will be conducted under this output. | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Number of SLCP knowledge resources or tools produced | 3 | Studies/reports | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | The studies/reports approved under this output will be knowledge resources used by relevant government institutions to understand and solve policy/regulatory, operational and financial challenges and plan for future scale up of low carbon transport in the country. | Research or study | null | 11/30/2024 | Studies/reports are reviewed and approved by CCAC | 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Output 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1.4 | HDV-23-003/1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Output | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1 | Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | By providing necessary technical assistance to develop a Sustainable Transport Plan and formulating relevant regulatory policy for using electric vehicles, specifically electric buses for public transport in Sri Lanka, including training for government stakholders and various feasibility studies for actual deployment of electric buses. Estimated completion date: 18 months from project start date | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 3 | 1 national policy/plan/ regulations drafted or updated.1 guidelines and 1 assessment completed | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1. | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | Staff and Other Personnel Costs | 1.4.3-2 | National consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 10 | Days | 200 | 2000 | 2000 | 0 | 0 | Yes. | 1/4/2003 | Expenditure 1.4.3-2 National consultant | Activity 1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.4.3-2 | HDV-23-003/1.4.3-2 National consultant | HDV-23-003/1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | 1.4.3 | 1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | A report on recommendations and planning of disposal of old buses and vehicles if replaced with electric buses (vehicles) during future project scale-up | Research, data collection, and/or report writing | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | 9/1/2024 | 11/30/2024 | Research or study | null | null | null | 1.4 | Activity 1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | Output 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | 1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | HDV-23-003/1.4.3 | HDV-23-003/1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | HDV-23-003/1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.4 | Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Impact studies, analytical reports on identification of gaps to implementing low-carbon transport and electric vehicles in Sri Lanka on various aspects as well as recommendations on future scale-up of such transport and electric vehicle deployment and disposal of ICE vehicles will be conducted under this output. | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Number of SLCP knowledge resources or tools produced | 3 | Studies/reports | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | The studies/reports approved under this output will be knowledge resources used by relevant government institutions to understand and solve policy/regulatory, operational and financial challenges and plan for future scale up of low carbon transport in the country. | Research or study | null | 11/30/2024 | Studies/reports are reviewed and approved by CCAC | 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Output 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1.4 | HDV-23-003/1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Output | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1 | Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | By providing necessary technical assistance to develop a Sustainable Transport Plan and formulating relevant regulatory policy for using electric vehicles, specifically electric buses for public transport in Sri Lanka, including training for government stakholders and various feasibility studies for actual deployment of electric buses. Estimated completion date: 18 months from project start date | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 3 | 1 national policy/plan/ regulations drafted or updated.1 guidelines and 1 assessment completed | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1. | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | Travel | 1.4.3-3 | DSA for national consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 2 | Days | 122 | 244 | 244 | 0 | 0 | Yes. | 1/4/2003 | Expenditure 1.4.3-3 DSA for national consultant | Activity 1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.4.3-3 | HDV-23-003/1.4.3-3 DSA for national consultant | HDV-23-003/1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | 1.4.3 | 1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | A report on recommendations and planning of disposal of old buses and vehicles if replaced with electric buses (vehicles) during future project scale-up | Research, data collection, and/or report writing | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | 9/1/2024 | 11/30/2024 | Research or study | null | null | null | 1.4 | Activity 1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | Output 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | 1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | HDV-23-003/1.4.3 | HDV-23-003/1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | HDV-23-003/1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.4 | Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Impact studies, analytical reports on identification of gaps to implementing low-carbon transport and electric vehicles in Sri Lanka on various aspects as well as recommendations on future scale-up of such transport and electric vehicle deployment and disposal of ICE vehicles will be conducted under this output. | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Number of SLCP knowledge resources or tools produced | 3 | Studies/reports | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | The studies/reports approved under this output will be knowledge resources used by relevant government institutions to understand and solve policy/regulatory, operational and financial challenges and plan for future scale up of low carbon transport in the country. | Research or study | null | 11/30/2024 | Studies/reports are reviewed and approved by CCAC | 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Output 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1.4 | HDV-23-003/1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Output | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1 | Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | By providing necessary technical assistance to develop a Sustainable Transport Plan and formulating relevant regulatory policy for using electric vehicles, specifically electric buses for public transport in Sri Lanka, including training for government stakholders and various feasibility studies for actual deployment of electric buses. Estimated completion date: 18 months from project start date | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 3 | 1 national policy/plan/ regulations drafted or updated.1 guidelines and 1 assessment completed | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1. | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
2.1.1Viability assessment of EV charging stations is completed and approved | Staff and Other Personnel Costs | 2.1.1-1 | International consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 20 | Days | 500 | 10000 | 10000 | 0 | 0 | Yes. | 2/1/2001 | Expenditure 2.1.1-1 International consultant | Activity 2.1.1Viability assessment of EV charging stations is completed and approved | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/2.1.1-1 | HDV-23-003/2.1.1-1 International consultant | HDV-23-003/2.1.1Viability assessment of EV charging stations is completed and approved | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | 2.1.1 | 2.1.1Viability assessment of EV charging stations is completed and approved | An Analytical report on safety, security, accessibility aspects of public transport buses in Sri Lanka, particularly from the perspective of women's safety and ease of accessibility of public transport buses for elderly/children/special needs commuters is completed | Research, data collection, and/or report writing | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | 12/1/2024 | 2/28/2025 | Research or study | null | null | null | 2.1 | Activity 2.1.1Viability assessment of EV charging stations is completed and approved | Output 2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | 2.1.1Viability assessment of EV charging stations is completed and approved | HDV-23-003/2.1.1 | HDV-23-003/2.1.1Viability assessment of EV charging stations is completed and approved | HDV-23-003/2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2.1 | Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Design and delivery of training programs for capacity building of government institutional stakeholders on various aspects of operationalising electric buses in Sri Lanka will be conducted under this output. | 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Number of SLCP knowledge resources or tools produced | 2 | Studies/reports | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Private bus operators' association and private bus operators, drivers, workshop technicians, Finance House association, Insurance association, commercial banks, leasing and financing companies | Improved technical capacity of officials of public institutions on electric buses in an inclusive manner. Government officials with improved capacities will be able to confidently engage in promotion of low carbon public transport development in Sri Lanka | Training materials, Participant list with gender breakdown, Training materials, Participant list with gender breakdown | null | 8/30/2025 | Attendance sheet and feedback from trainees shared with CCAC | 2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Output 2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Outcome 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | HDV-23-003/2.1 | HDV-23-003/2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Output | HDV-23-003/2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2 | Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | By conducting needs based assessments, and identifying kind of training government and other public institutional stakeholders require, designing and delivering training programs accordingly to selected officers in the respective public institutions. Estimated completion date: EoP | Number of government entities with a demonstrated improved capacity for SLCP action | 6 | Government entities with improved capacity | 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Outcome 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | HDV-23-003/2. | HDV-23-003/2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
2.1.1Viability assessment of EV charging stations is completed and approved | Staff and Other Personnel Costs | 2.1.1-2 | National consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 40 | Days | 200 | 8000 | 8000 | 0 | 0 | Yes. | 2/1/2001 | Expenditure 2.1.1-2 National consultant | Activity 2.1.1Viability assessment of EV charging stations is completed and approved | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/2.1.1-2 | HDV-23-003/2.1.1-2 National consultant | HDV-23-003/2.1.1Viability assessment of EV charging stations is completed and approved | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | 2.1.1 | 2.1.1Viability assessment of EV charging stations is completed and approved | An Analytical report on safety, security, accessibility aspects of public transport buses in Sri Lanka, particularly from the perspective of women's safety and ease of accessibility of public transport buses for elderly/children/special needs commuters is completed | Research, data collection, and/or report writing | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | 12/1/2024 | 2/28/2025 | Research or study | null | null | null | 2.1 | Activity 2.1.1Viability assessment of EV charging stations is completed and approved | Output 2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | 2.1.1Viability assessment of EV charging stations is completed and approved | HDV-23-003/2.1.1 | HDV-23-003/2.1.1Viability assessment of EV charging stations is completed and approved | HDV-23-003/2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2.1 | Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Design and delivery of training programs for capacity building of government institutional stakeholders on various aspects of operationalising electric buses in Sri Lanka will be conducted under this output. | 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Number of SLCP knowledge resources or tools produced | 2 | Studies/reports | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Private bus operators' association and private bus operators, drivers, workshop technicians, Finance House association, Insurance association, commercial banks, leasing and financing companies | Improved technical capacity of officials of public institutions on electric buses in an inclusive manner. Government officials with improved capacities will be able to confidently engage in promotion of low carbon public transport development in Sri Lanka | Training materials, Participant list with gender breakdown, Training materials, Participant list with gender breakdown | null | 8/30/2025 | Attendance sheet and feedback from trainees shared with CCAC | 2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Output 2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Outcome 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | HDV-23-003/2.1 | HDV-23-003/2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Output | HDV-23-003/2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2 | Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | By conducting needs based assessments, and identifying kind of training government and other public institutional stakeholders require, designing and delivering training programs accordingly to selected officers in the respective public institutions. Estimated completion date: EoP | Number of government entities with a demonstrated improved capacity for SLCP action | 6 | Government entities with improved capacity | 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Outcome 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | HDV-23-003/2. | HDV-23-003/2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
2.1.1Viability assessment of EV charging stations is completed and approved | Travel | 2.1.1-3 | Travel fare | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 1 | Ticket fare for consultants | 500 | 500 | 500 | 0 | 0 | Yes. | 2/1/2001 | Expenditure 2.1.1-3 Travel fare | Activity 2.1.1Viability assessment of EV charging stations is completed and approved | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/2.1.1-3 | HDV-23-003/2.1.1-3 Travel fare | HDV-23-003/2.1.1Viability assessment of EV charging stations is completed and approved | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | 2.1.1 | 2.1.1Viability assessment of EV charging stations is completed and approved | An Analytical report on safety, security, accessibility aspects of public transport buses in Sri Lanka, particularly from the perspective of women's safety and ease of accessibility of public transport buses for elderly/children/special needs commuters is completed | Research, data collection, and/or report writing | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | 12/1/2024 | 2/28/2025 | Research or study | null | null | null | 2.1 | Activity 2.1.1Viability assessment of EV charging stations is completed and approved | Output 2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | 2.1.1Viability assessment of EV charging stations is completed and approved | HDV-23-003/2.1.1 | HDV-23-003/2.1.1Viability assessment of EV charging stations is completed and approved | HDV-23-003/2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2.1 | Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Design and delivery of training programs for capacity building of government institutional stakeholders on various aspects of operationalising electric buses in Sri Lanka will be conducted under this output. | 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Number of SLCP knowledge resources or tools produced | 2 | Studies/reports | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Private bus operators' association and private bus operators, drivers, workshop technicians, Finance House association, Insurance association, commercial banks, leasing and financing companies | Improved technical capacity of officials of public institutions on electric buses in an inclusive manner. Government officials with improved capacities will be able to confidently engage in promotion of low carbon public transport development in Sri Lanka | Training materials, Participant list with gender breakdown, Training materials, Participant list with gender breakdown | null | 8/30/2025 | Attendance sheet and feedback from trainees shared with CCAC | 2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Output 2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Outcome 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | HDV-23-003/2.1 | HDV-23-003/2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Output | HDV-23-003/2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2 | Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | By conducting needs based assessments, and identifying kind of training government and other public institutional stakeholders require, designing and delivering training programs accordingly to selected officers in the respective public institutions. Estimated completion date: EoP | Number of government entities with a demonstrated improved capacity for SLCP action | 6 | Government entities with improved capacity | 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Outcome 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | HDV-23-003/2. | HDV-23-003/2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
2.1.1Viability assessment of EV charging stations is completed and approved | Travel | 2.1.1-4 | DSA for international consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 10 | Days | 192 | 1920 | 1920 | 0 | 0 | Yes. | 2/1/2001 | Expenditure 2.1.1-4 DSA for international consultant | Activity 2.1.1Viability assessment of EV charging stations is completed and approved | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/2.1.1-4 | HDV-23-003/2.1.1-4 DSA for international consultant | HDV-23-003/2.1.1Viability assessment of EV charging stations is completed and approved | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | 2.1.1 | 2.1.1Viability assessment of EV charging stations is completed and approved | An Analytical report on safety, security, accessibility aspects of public transport buses in Sri Lanka, particularly from the perspective of women's safety and ease of accessibility of public transport buses for elderly/children/special needs commuters is completed | Research, data collection, and/or report writing | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | 12/1/2024 | 2/28/2025 | Research or study | null | null | null | 2.1 | Activity 2.1.1Viability assessment of EV charging stations is completed and approved | Output 2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | 2.1.1Viability assessment of EV charging stations is completed and approved | HDV-23-003/2.1.1 | HDV-23-003/2.1.1Viability assessment of EV charging stations is completed and approved | HDV-23-003/2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2.1 | Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Design and delivery of training programs for capacity building of government institutional stakeholders on various aspects of operationalising electric buses in Sri Lanka will be conducted under this output. | 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Number of SLCP knowledge resources or tools produced | 2 | Studies/reports | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Private bus operators' association and private bus operators, drivers, workshop technicians, Finance House association, Insurance association, commercial banks, leasing and financing companies | Improved technical capacity of officials of public institutions on electric buses in an inclusive manner. Government officials with improved capacities will be able to confidently engage in promotion of low carbon public transport development in Sri Lanka | Training materials, Participant list with gender breakdown, Training materials, Participant list with gender breakdown | null | 8/30/2025 | Attendance sheet and feedback from trainees shared with CCAC | 2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Output 2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Outcome 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | HDV-23-003/2.1 | HDV-23-003/2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Output | HDV-23-003/2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2 | Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | By conducting needs based assessments, and identifying kind of training government and other public institutional stakeholders require, designing and delivering training programs accordingly to selected officers in the respective public institutions. Estimated completion date: EoP | Number of government entities with a demonstrated improved capacity for SLCP action | 6 | Government entities with improved capacity | 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Outcome 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | HDV-23-003/2. | HDV-23-003/2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
2.1.1Viability assessment of EV charging stations is completed and approved | Travel | 2.1.1-5 | DSA for national consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 7 | Days | 122 | 854 | 854 | 0 | 0 | Yes. | 2/1/2001 | Expenditure 2.1.1-5 DSA for national consultant | Activity 2.1.1Viability assessment of EV charging stations is completed and approved | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/2.1.1-5 | HDV-23-003/2.1.1-5 DSA for national consultant | HDV-23-003/2.1.1Viability assessment of EV charging stations is completed and approved | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | 2.1.1 | 2.1.1Viability assessment of EV charging stations is completed and approved | An Analytical report on safety, security, accessibility aspects of public transport buses in Sri Lanka, particularly from the perspective of women's safety and ease of accessibility of public transport buses for elderly/children/special needs commuters is completed | Research, data collection, and/or report writing | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | 12/1/2024 | 2/28/2025 | Research or study | null | null | null | 2.1 | Activity 2.1.1Viability assessment of EV charging stations is completed and approved | Output 2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | 2.1.1Viability assessment of EV charging stations is completed and approved | HDV-23-003/2.1.1 | HDV-23-003/2.1.1Viability assessment of EV charging stations is completed and approved | HDV-23-003/2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2.1 | Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Design and delivery of training programs for capacity building of government institutional stakeholders on various aspects of operationalising electric buses in Sri Lanka will be conducted under this output. | 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Number of SLCP knowledge resources or tools produced | 2 | Studies/reports | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Private bus operators' association and private bus operators, drivers, workshop technicians, Finance House association, Insurance association, commercial banks, leasing and financing companies | Improved technical capacity of officials of public institutions on electric buses in an inclusive manner. Government officials with improved capacities will be able to confidently engage in promotion of low carbon public transport development in Sri Lanka | Training materials, Participant list with gender breakdown, Training materials, Participant list with gender breakdown | null | 8/30/2025 | Attendance sheet and feedback from trainees shared with CCAC | 2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Output 2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Outcome 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | HDV-23-003/2.1 | HDV-23-003/2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Output | HDV-23-003/2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2 | Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | By conducting needs based assessments, and identifying kind of training government and other public institutional stakeholders require, designing and delivering training programs accordingly to selected officers in the respective public institutions. Estimated completion date: EoP | Number of government entities with a demonstrated improved capacity for SLCP action | 6 | Government entities with improved capacity | 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Outcome 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | HDV-23-003/2. | HDV-23-003/2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
2.1.2An Analytical gender (including elderly, children, specific needs commuter) specific report on safety, security, accessibility aspects of public transport buses in Sri Lanka | Staff and Other Personnel Costs | 2.1.2-1 | National consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 60 | Days | 200 | 12000 | 12000 | 0 | 0 | Yes. | 2/1/2002 | Expenditure 2.1.2-1 National consultant | Activity 2.1.2An Analytical gender (including elderly, children, specific needs commuter) specific report on safety, security, accessibility aspects of public transport buses in Sri Lanka | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/2.1.2-1 | HDV-23-003/2.1.2-1 National consultant | HDV-23-003/2.1.2An Analytical gender (including elderly, children, specific needs commuter) specific report on safety, security, accessibility aspects of public transport buses in Sri Lanka | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | 2.1.2 | 2.1.2An Analytical gender (including elderly, children, specific needs commuter) specific report on safety, security, accessibility aspects of public transport buses in Sri Lanka | Training programs, training at least 60 trainees (30% being women), designed and delivered for government institutional stakeholders (MoTH, MoPE, NTC, SLTB, WPRPTA, CMC) on techno-commercial (such as procurement, planning, performance evaluation, scheduling and charging infrastructure of electric bus systems), financial/economic and policy/regulatory (best practices etc.) frameworks for enabling electric bus deployment for public transport and associated bus charging stations in Sri Lanka; the training program needs to include gender-specific and accessibility/inclusivity aspects as well. | Research, data collection, and/or report writing | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | 3/1/2025 | 8/30/2025 | Participant list with gender breakdown | null | null | null | 2.1 | Activity 2.1.2An Analytical gender (including elderly, children, specific needs commuter) specific report on safety, security, accessibility aspects of public transport buses in Sri Lanka | Output 2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | 2.1.2An Analytical gender (including elderly, children, specific needs commuter) specific report on safety, security, accessibility aspects of public transport buses in Sri Lanka | HDV-23-003/2.1.2 | HDV-23-003/2.1.2An Analytical gender (including elderly, children, specific needs commuter) specific report on safety, security, accessibility aspects of public transport buses in Sri Lanka | HDV-23-003/2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2.1 | Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Design and delivery of training programs for capacity building of government institutional stakeholders on various aspects of operationalising electric buses in Sri Lanka will be conducted under this output. | 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Number of SLCP knowledge resources or tools produced | 2 | Studies/reports | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Private bus operators' association and private bus operators, drivers, workshop technicians, Finance House association, Insurance association, commercial banks, leasing and financing companies | Improved technical capacity of officials of public institutions on electric buses in an inclusive manner. Government officials with improved capacities will be able to confidently engage in promotion of low carbon public transport development in Sri Lanka | Training materials, Participant list with gender breakdown, Training materials, Participant list with gender breakdown | null | 8/30/2025 | Attendance sheet and feedback from trainees shared with CCAC | 2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Output 2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Outcome 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | HDV-23-003/2.1 | HDV-23-003/2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Output | HDV-23-003/2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2 | Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | By conducting needs based assessments, and identifying kind of training government and other public institutional stakeholders require, designing and delivering training programs accordingly to selected officers in the respective public institutions. Estimated completion date: EoP | Number of government entities with a demonstrated improved capacity for SLCP action | 6 | Government entities with improved capacity | 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Outcome 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | HDV-23-003/2. | HDV-23-003/2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
2.1.2An Analytical gender (including elderly, children, specific needs commuter) specific report on safety, security, accessibility aspects of public transport buses in Sri Lanka | Travel | 2.1.2-2 | DSA for national consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 10 | Days | 122 | 1220 | 1220 | 0 | 0 | Yes. | 2/1/2002 | Expenditure 2.1.2-2 DSA for national consultant | Activity 2.1.2An Analytical gender (including elderly, children, specific needs commuter) specific report on safety, security, accessibility aspects of public transport buses in Sri Lanka | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/2.1.2-2 | HDV-23-003/2.1.2-2 DSA for national consultant | HDV-23-003/2.1.2An Analytical gender (including elderly, children, specific needs commuter) specific report on safety, security, accessibility aspects of public transport buses in Sri Lanka | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | 2.1.2 | 2.1.2An Analytical gender (including elderly, children, specific needs commuter) specific report on safety, security, accessibility aspects of public transport buses in Sri Lanka | Training programs, training at least 60 trainees (30% being women), designed and delivered for government institutional stakeholders (MoTH, MoPE, NTC, SLTB, WPRPTA, CMC) on techno-commercial (such as procurement, planning, performance evaluation, scheduling and charging infrastructure of electric bus systems), financial/economic and policy/regulatory (best practices etc.) frameworks for enabling electric bus deployment for public transport and associated bus charging stations in Sri Lanka; the training program needs to include gender-specific and accessibility/inclusivity aspects as well. | Research, data collection, and/or report writing | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | 3/1/2025 | 8/30/2025 | Participant list with gender breakdown | null | null | null | 2.1 | Activity 2.1.2An Analytical gender (including elderly, children, specific needs commuter) specific report on safety, security, accessibility aspects of public transport buses in Sri Lanka | Output 2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | 2.1.2An Analytical gender (including elderly, children, specific needs commuter) specific report on safety, security, accessibility aspects of public transport buses in Sri Lanka | HDV-23-003/2.1.2 | HDV-23-003/2.1.2An Analytical gender (including elderly, children, specific needs commuter) specific report on safety, security, accessibility aspects of public transport buses in Sri Lanka | HDV-23-003/2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2.1 | Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Design and delivery of training programs for capacity building of government institutional stakeholders on various aspects of operationalising electric buses in Sri Lanka will be conducted under this output. | 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Number of SLCP knowledge resources or tools produced | 2 | Studies/reports | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Private bus operators' association and private bus operators, drivers, workshop technicians, Finance House association, Insurance association, commercial banks, leasing and financing companies | Improved technical capacity of officials of public institutions on electric buses in an inclusive manner. Government officials with improved capacities will be able to confidently engage in promotion of low carbon public transport development in Sri Lanka | Training materials, Participant list with gender breakdown, Training materials, Participant list with gender breakdown | null | 8/30/2025 | Attendance sheet and feedback from trainees shared with CCAC | 2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Output 2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Outcome 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | HDV-23-003/2.1 | HDV-23-003/2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Output | HDV-23-003/2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2 | Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | By conducting needs based assessments, and identifying kind of training government and other public institutional stakeholders require, designing and delivering training programs accordingly to selected officers in the respective public institutions. Estimated completion date: EoP | Number of government entities with a demonstrated improved capacity for SLCP action | 6 | Government entities with improved capacity | 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Outcome 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | HDV-23-003/2. | HDV-23-003/2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
2.2.1Training programs designed and delivered for government institutional stakeholders | Staff and Other Personnel Costs | 2.2.1-1 | International consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 30 | Days | 500 | 15000 | 0 | 15000 | 0 | Yes. | 2/2/2001 | Expenditure 2.2.1-1 International consultant | Activity 2.2.1Training programs designed and delivered for government institutional stakeholders | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/2.2.1-1 | HDV-23-003/2.2.1-1 International consultant | HDV-23-003/2.2.1Training programs designed and delivered for government institutional stakeholders | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 2.2.1 | 2.2.1Training programs designed and delivered for government institutional stakeholders | Training programs, training at least 30 trainees (50% being women), designed and delivered for commercial banks/financial institutions (loan officers and senior executives of banks/leasing and financing companies involved in or interested in lending to electric bus mobility sector) on techno-commercial, financial/economic and policy/regulatory frameworks for enabling electric bus deployment for public transport and associated bus charging stations in Sri Lanka; the training program needs to include gender-specific and accessibility/inclusivity aspects as well. | Developing and/or delivering training | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Finance House association, Insurance association, commercial banks, leasing and financing companies | 6/1/2025 | 8/30/2025 | Participant list with gender breakdown | null | null | null | 2.2 | Activity 2.2.1Training programs designed and delivered for government institutional stakeholders | Output 2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 2.2.1Training programs designed and delivered for government institutional stakeholders | HDV-23-003/2.2.1 | HDV-23-003/2.2.1Training programs designed and delivered for government institutional stakeholders | HDV-23-003/2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2.2 | Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Design and delivery of training programs for capacity building of private sector stakeholders on technical features of electric buses, economic/financial viability of e-buses will be conducted under this output. | 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Number of person hours of training provided | 6720 | Person hours | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Improved technical capacity of private sector stakeholders on electric buses. This will encourage them to invest and engage in deployment of E buses for public transport | Training materials, Training materials, Participant list with gender breakdown, Training materials, Training materials, Participant list with gender breakdown | null | 11/30/2025 | Attendance sheet and feedback from trainees shared with CCAC | 2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output 2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Outcome 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | HDV-23-003/2.2 | HDV-23-003/2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output | HDV-23-003/2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2 | Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | By conducting needs based assessments, and identifying kind of training government and other public institutional stakeholders require, designing and delivering training programs accordingly to selected officers in the respective public institutions. Estimated completion date: EoP | Number of government entities with a demonstrated improved capacity for SLCP action | 6 | Government entities with improved capacity | 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Outcome 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | HDV-23-003/2. | HDV-23-003/2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
2.2.1Training programs designed and delivered for government institutional stakeholders | Staff and Other Personnel Costs | 2.2.1-2 | National consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 50 | Days | 200 | 10000 | 0 | 10000 | 0 | Yes. | 2/2/2001 | Expenditure 2.2.1-2 National consultant | Activity 2.2.1Training programs designed and delivered for government institutional stakeholders | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/2.2.1-2 | HDV-23-003/2.2.1-2 National consultant | HDV-23-003/2.2.1Training programs designed and delivered for government institutional stakeholders | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 2.2.1 | 2.2.1Training programs designed and delivered for government institutional stakeholders | Training programs, training at least 30 trainees (50% being women), designed and delivered for commercial banks/financial institutions (loan officers and senior executives of banks/leasing and financing companies involved in or interested in lending to electric bus mobility sector) on techno-commercial, financial/economic and policy/regulatory frameworks for enabling electric bus deployment for public transport and associated bus charging stations in Sri Lanka; the training program needs to include gender-specific and accessibility/inclusivity aspects as well. | Developing and/or delivering training | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Finance House association, Insurance association, commercial banks, leasing and financing companies | 6/1/2025 | 8/30/2025 | Participant list with gender breakdown | null | null | null | 2.2 | Activity 2.2.1Training programs designed and delivered for government institutional stakeholders | Output 2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 2.2.1Training programs designed and delivered for government institutional stakeholders | HDV-23-003/2.2.1 | HDV-23-003/2.2.1Training programs designed and delivered for government institutional stakeholders | HDV-23-003/2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2.2 | Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Design and delivery of training programs for capacity building of private sector stakeholders on technical features of electric buses, economic/financial viability of e-buses will be conducted under this output. | 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Number of person hours of training provided | 6720 | Person hours | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Improved technical capacity of private sector stakeholders on electric buses. This will encourage them to invest and engage in deployment of E buses for public transport | Training materials, Training materials, Participant list with gender breakdown, Training materials, Training materials, Participant list with gender breakdown | null | 11/30/2025 | Attendance sheet and feedback from trainees shared with CCAC | 2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output 2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Outcome 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | HDV-23-003/2.2 | HDV-23-003/2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output | HDV-23-003/2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2 | Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | By conducting needs based assessments, and identifying kind of training government and other public institutional stakeholders require, designing and delivering training programs accordingly to selected officers in the respective public institutions. Estimated completion date: EoP | Number of government entities with a demonstrated improved capacity for SLCP action | 6 | Government entities with improved capacity | 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Outcome 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | HDV-23-003/2. | HDV-23-003/2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
2.2.1Training programs designed and delivered for government institutional stakeholders | Travel | 2.2.1-3 | Travel fare | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 2 | Ticket fare for consultants | 500 | 1000 | 0 | 1000 | 0 | Yes. | 2/2/2001 | Expenditure 2.2.1-3 Travel fare | Activity 2.2.1Training programs designed and delivered for government institutional stakeholders | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/2.2.1-3 | HDV-23-003/2.2.1-3 Travel fare | HDV-23-003/2.2.1Training programs designed and delivered for government institutional stakeholders | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 2.2.1 | 2.2.1Training programs designed and delivered for government institutional stakeholders | Training programs, training at least 30 trainees (50% being women), designed and delivered for commercial banks/financial institutions (loan officers and senior executives of banks/leasing and financing companies involved in or interested in lending to electric bus mobility sector) on techno-commercial, financial/economic and policy/regulatory frameworks for enabling electric bus deployment for public transport and associated bus charging stations in Sri Lanka; the training program needs to include gender-specific and accessibility/inclusivity aspects as well. | Developing and/or delivering training | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Finance House association, Insurance association, commercial banks, leasing and financing companies | 6/1/2025 | 8/30/2025 | Participant list with gender breakdown | null | null | null | 2.2 | Activity 2.2.1Training programs designed and delivered for government institutional stakeholders | Output 2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 2.2.1Training programs designed and delivered for government institutional stakeholders | HDV-23-003/2.2.1 | HDV-23-003/2.2.1Training programs designed and delivered for government institutional stakeholders | HDV-23-003/2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2.2 | Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Design and delivery of training programs for capacity building of private sector stakeholders on technical features of electric buses, economic/financial viability of e-buses will be conducted under this output. | 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Number of person hours of training provided | 6720 | Person hours | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Improved technical capacity of private sector stakeholders on electric buses. This will encourage them to invest and engage in deployment of E buses for public transport | Training materials, Training materials, Participant list with gender breakdown, Training materials, Training materials, Participant list with gender breakdown | null | 11/30/2025 | Attendance sheet and feedback from trainees shared with CCAC | 2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output 2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Outcome 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | HDV-23-003/2.2 | HDV-23-003/2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output | HDV-23-003/2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2 | Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | By conducting needs based assessments, and identifying kind of training government and other public institutional stakeholders require, designing and delivering training programs accordingly to selected officers in the respective public institutions. Estimated completion date: EoP | Number of government entities with a demonstrated improved capacity for SLCP action | 6 | Government entities with improved capacity | 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Outcome 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | HDV-23-003/2. | HDV-23-003/2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
2.2.1Training programs designed and delivered for government institutional stakeholders | Travel | 2.2.1-4 | DSA for international consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 17 | Days | 192 | 3264 | 0 | 3264 | 0 | Yes. | 2/2/2001 | Expenditure 2.2.1-4 DSA for international consultant | Activity 2.2.1Training programs designed and delivered for government institutional stakeholders | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/2.2.1-4 | HDV-23-003/2.2.1-4 DSA for international consultant | HDV-23-003/2.2.1Training programs designed and delivered for government institutional stakeholders | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 2.2.1 | 2.2.1Training programs designed and delivered for government institutional stakeholders | Training programs, training at least 30 trainees (50% being women), designed and delivered for commercial banks/financial institutions (loan officers and senior executives of banks/leasing and financing companies involved in or interested in lending to electric bus mobility sector) on techno-commercial, financial/economic and policy/regulatory frameworks for enabling electric bus deployment for public transport and associated bus charging stations in Sri Lanka; the training program needs to include gender-specific and accessibility/inclusivity aspects as well. | Developing and/or delivering training | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Finance House association, Insurance association, commercial banks, leasing and financing companies | 6/1/2025 | 8/30/2025 | Participant list with gender breakdown | null | null | null | 2.2 | Activity 2.2.1Training programs designed and delivered for government institutional stakeholders | Output 2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 2.2.1Training programs designed and delivered for government institutional stakeholders | HDV-23-003/2.2.1 | HDV-23-003/2.2.1Training programs designed and delivered for government institutional stakeholders | HDV-23-003/2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2.2 | Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Design and delivery of training programs for capacity building of private sector stakeholders on technical features of electric buses, economic/financial viability of e-buses will be conducted under this output. | 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Number of person hours of training provided | 6720 | Person hours | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Improved technical capacity of private sector stakeholders on electric buses. This will encourage them to invest and engage in deployment of E buses for public transport | Training materials, Training materials, Participant list with gender breakdown, Training materials, Training materials, Participant list with gender breakdown | null | 11/30/2025 | Attendance sheet and feedback from trainees shared with CCAC | 2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output 2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Outcome 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | HDV-23-003/2.2 | HDV-23-003/2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output | HDV-23-003/2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2 | Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | By conducting needs based assessments, and identifying kind of training government and other public institutional stakeholders require, designing and delivering training programs accordingly to selected officers in the respective public institutions. Estimated completion date: EoP | Number of government entities with a demonstrated improved capacity for SLCP action | 6 | Government entities with improved capacity | 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Outcome 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | HDV-23-003/2. | HDV-23-003/2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
2.2.1Training programs designed and delivered for government institutional stakeholders | Travel | 2.2.1-5 | DSA for national consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 14 | Days | 122 | 1708 | 0 | 1708 | 0 | Yes. | 2/2/2001 | Expenditure 2.2.1-5 DSA for national consultant | Activity 2.2.1Training programs designed and delivered for government institutional stakeholders | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/2.2.1-5 | HDV-23-003/2.2.1-5 DSA for national consultant | HDV-23-003/2.2.1Training programs designed and delivered for government institutional stakeholders | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 2.2.1 | 2.2.1Training programs designed and delivered for government institutional stakeholders | Training programs, training at least 30 trainees (50% being women), designed and delivered for commercial banks/financial institutions (loan officers and senior executives of banks/leasing and financing companies involved in or interested in lending to electric bus mobility sector) on techno-commercial, financial/economic and policy/regulatory frameworks for enabling electric bus deployment for public transport and associated bus charging stations in Sri Lanka; the training program needs to include gender-specific and accessibility/inclusivity aspects as well. | Developing and/or delivering training | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Finance House association, Insurance association, commercial banks, leasing and financing companies | 6/1/2025 | 8/30/2025 | Participant list with gender breakdown | null | null | null | 2.2 | Activity 2.2.1Training programs designed and delivered for government institutional stakeholders | Output 2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 2.2.1Training programs designed and delivered for government institutional stakeholders | HDV-23-003/2.2.1 | HDV-23-003/2.2.1Training programs designed and delivered for government institutional stakeholders | HDV-23-003/2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2.2 | Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Design and delivery of training programs for capacity building of private sector stakeholders on technical features of electric buses, economic/financial viability of e-buses will be conducted under this output. | 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Number of person hours of training provided | 6720 | Person hours | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Improved technical capacity of private sector stakeholders on electric buses. This will encourage them to invest and engage in deployment of E buses for public transport | Training materials, Training materials, Participant list with gender breakdown, Training materials, Training materials, Participant list with gender breakdown | null | 11/30/2025 | Attendance sheet and feedback from trainees shared with CCAC | 2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output 2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Outcome 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | HDV-23-003/2.2 | HDV-23-003/2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output | HDV-23-003/2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2 | Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | By conducting needs based assessments, and identifying kind of training government and other public institutional stakeholders require, designing and delivering training programs accordingly to selected officers in the respective public institutions. Estimated completion date: EoP | Number of government entities with a demonstrated improved capacity for SLCP action | 6 | Government entities with improved capacity | 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Outcome 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | HDV-23-003/2. | HDV-23-003/2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
2.2.1Training programs designed and delivered for government institutional stakeholders | Supplies Commodities and Materials | 2.2.1-6 | Printing materials, handouts, audio-visual material | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 1 | Training materials | 2000 | 2000 | 0 | 2000 | 0 | Yes. | 2/2/2001 | Expenditure 2.2.1-6 Printing materials, handouts, audio-visual material | Activity 2.2.1Training programs designed and delivered for government institutional stakeholders | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/2.2.1-6 | HDV-23-003/2.2.1-6 Printing materials, handouts, audio-visual material | HDV-23-003/2.2.1Training programs designed and delivered for government institutional stakeholders | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 2.2.1 | 2.2.1Training programs designed and delivered for government institutional stakeholders | Training programs, training at least 30 trainees (50% being women), designed and delivered for commercial banks/financial institutions (loan officers and senior executives of banks/leasing and financing companies involved in or interested in lending to electric bus mobility sector) on techno-commercial, financial/economic and policy/regulatory frameworks for enabling electric bus deployment for public transport and associated bus charging stations in Sri Lanka; the training program needs to include gender-specific and accessibility/inclusivity aspects as well. | Developing and/or delivering training | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Finance House association, Insurance association, commercial banks, leasing and financing companies | 6/1/2025 | 8/30/2025 | Participant list with gender breakdown | null | null | null | 2.2 | Activity 2.2.1Training programs designed and delivered for government institutional stakeholders | Output 2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 2.2.1Training programs designed and delivered for government institutional stakeholders | HDV-23-003/2.2.1 | HDV-23-003/2.2.1Training programs designed and delivered for government institutional stakeholders | HDV-23-003/2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2.2 | Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Design and delivery of training programs for capacity building of private sector stakeholders on technical features of electric buses, economic/financial viability of e-buses will be conducted under this output. | 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Number of person hours of training provided | 6720 | Person hours | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Improved technical capacity of private sector stakeholders on electric buses. This will encourage them to invest and engage in deployment of E buses for public transport | Training materials, Training materials, Participant list with gender breakdown, Training materials, Training materials, Participant list with gender breakdown | null | 11/30/2025 | Attendance sheet and feedback from trainees shared with CCAC | 2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output 2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Outcome 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | HDV-23-003/2.2 | HDV-23-003/2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output | HDV-23-003/2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 2 | Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | By conducting needs based assessments, and identifying kind of training government and other public institutional stakeholders require, designing and delivering training programs accordingly to selected officers in the respective public institutions. Estimated completion date: EoP | Number of government entities with a demonstrated improved capacity for SLCP action | 6 | Government entities with improved capacity | 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Outcome 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | HDV-23-003/2. | HDV-23-003/2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
3.1.1Training programs designed and delivered for commercial banks/financial institutions | Staff and Other Personnel Costs | 3.1.1-1 | International consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 15 | Days | 500 | 7500 | 0 | 7500 | 0 | Yes. | 3/1/2001 | Expenditure 3.1.1-1 International consultant | Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.1.1-1 | HDV-23-003/3.1.1-1 International consultant | HDV-23-003/3.1.1Training programs designed and delivered for commercial banks/financial institutions | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 3.1.1 | 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Training programs, training at least 60 trainees (10% being women), designed and delivered to private bus operators, their bus drivers and workshop technicians on electric bus operational and financial feasibility (vs ICE buses), e-bus driving techniques, safety (including women's safety) and security aspects and maintenance, management of EV batteries/their scientific disposal. | Developing and/or delivering training | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Private bus operators' association and private bus operators, drivers, workshop technicians | 6/1/2025 | 11/30/2025 | Participant list with gender breakdown | null | null | null | 3.1 | Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Output 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 3.1.1Training programs designed and delivered for commercial banks/financial institutions | HDV-23-003/3.1.1 | HDV-23-003/3.1.1Training programs designed and delivered for commercial banks/financial institutions | HDV-23-003/3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.1 | Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Various targeted promotional events and public awareness campaigns on benefits of using low-carbon public transport in Sri Lanka will be held to gain public support for above transition | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Number of person hours of training provided | 9840 | Person hours | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | To raise public awareness on benefits of using public transport, especially low-carbon public transport, and to encourage usage of public transport in the country. | Tool, Tool, Photo or video, Tool, Tool, Photo or video | null | 10/31/2025 | Campaign materials and photos shared with CCAC | 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3.1 | HDV-23-003/3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3 | Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Designing and delivering training programs for various private sector stakeholders to improve technical capacity and financial/economic understanding of operating electric buses for public transport to help further uptake of electric buses even after the completion of the project. Raising public awareness on benefits of using low carbon public transport through various media, campaigns and events will help create demand for such transport. Estimated completion date: | Number of non-government entities with a demonstrated improved capacity for SLCP action | 7 | 7 non-government entities with improved capacity | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3. | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
3.1.1Training programs designed and delivered for commercial banks/financial institutions | Staff and Other Personnel Costs | 3.1.1-2 | National consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 30 | Days | 200 | 6000 | 0 | 6000 | 0 | Yes. | 3/1/2001 | Expenditure 3.1.1-2 National consultant | Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.1.1-2 | HDV-23-003/3.1.1-2 National consultant | HDV-23-003/3.1.1Training programs designed and delivered for commercial banks/financial institutions | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 3.1.1 | 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Training programs, training at least 60 trainees (10% being women), designed and delivered to private bus operators, their bus drivers and workshop technicians on electric bus operational and financial feasibility (vs ICE buses), e-bus driving techniques, safety (including women's safety) and security aspects and maintenance, management of EV batteries/their scientific disposal. | Developing and/or delivering training | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Private bus operators' association and private bus operators, drivers, workshop technicians | 6/1/2025 | 11/30/2025 | Participant list with gender breakdown | null | null | null | 3.1 | Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Output 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 3.1.1Training programs designed and delivered for commercial banks/financial institutions | HDV-23-003/3.1.1 | HDV-23-003/3.1.1Training programs designed and delivered for commercial banks/financial institutions | HDV-23-003/3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.1 | Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Various targeted promotional events and public awareness campaigns on benefits of using low-carbon public transport in Sri Lanka will be held to gain public support for above transition | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Number of person hours of training provided | 9840 | Person hours | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | To raise public awareness on benefits of using public transport, especially low-carbon public transport, and to encourage usage of public transport in the country. | Tool, Tool, Photo or video, Tool, Tool, Photo or video | null | 10/31/2025 | Campaign materials and photos shared with CCAC | 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3.1 | HDV-23-003/3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3 | Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Designing and delivering training programs for various private sector stakeholders to improve technical capacity and financial/economic understanding of operating electric buses for public transport to help further uptake of electric buses even after the completion of the project. Raising public awareness on benefits of using low carbon public transport through various media, campaigns and events will help create demand for such transport. Estimated completion date: | Number of non-government entities with a demonstrated improved capacity for SLCP action | 7 | 7 non-government entities with improved capacity | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3. | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
3.1.1Training programs designed and delivered for commercial banks/financial institutions | Travel | 3.1.1-3 | Travel fare | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 1 | Ticket fare for consultants | 500 | 500 | 0 | 500 | 0 | Yes. | 3/1/2001 | Expenditure 3.1.1-3 Travel fare | Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.1.1-3 | HDV-23-003/3.1.1-3 Travel fare | HDV-23-003/3.1.1Training programs designed and delivered for commercial banks/financial institutions | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 3.1.1 | 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Training programs, training at least 60 trainees (10% being women), designed and delivered to private bus operators, their bus drivers and workshop technicians on electric bus operational and financial feasibility (vs ICE buses), e-bus driving techniques, safety (including women's safety) and security aspects and maintenance, management of EV batteries/their scientific disposal. | Developing and/or delivering training | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Private bus operators' association and private bus operators, drivers, workshop technicians | 6/1/2025 | 11/30/2025 | Participant list with gender breakdown | null | null | null | 3.1 | Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Output 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 3.1.1Training programs designed and delivered for commercial banks/financial institutions | HDV-23-003/3.1.1 | HDV-23-003/3.1.1Training programs designed and delivered for commercial banks/financial institutions | HDV-23-003/3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.1 | Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Various targeted promotional events and public awareness campaigns on benefits of using low-carbon public transport in Sri Lanka will be held to gain public support for above transition | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Number of person hours of training provided | 9840 | Person hours | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | To raise public awareness on benefits of using public transport, especially low-carbon public transport, and to encourage usage of public transport in the country. | Tool, Tool, Photo or video, Tool, Tool, Photo or video | null | 10/31/2025 | Campaign materials and photos shared with CCAC | 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3.1 | HDV-23-003/3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3 | Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Designing and delivering training programs for various private sector stakeholders to improve technical capacity and financial/economic understanding of operating electric buses for public transport to help further uptake of electric buses even after the completion of the project. Raising public awareness on benefits of using low carbon public transport through various media, campaigns and events will help create demand for such transport. Estimated completion date: | Number of non-government entities with a demonstrated improved capacity for SLCP action | 7 | 7 non-government entities with improved capacity | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3. | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
3.1.1Training programs designed and delivered for commercial banks/financial institutions | Travel | 3.1.1-4 | DSA for international consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 15 | Days | 192 | 2880 | 0 | 2880 | 0 | Yes. | 3/1/2001 | Expenditure 3.1.1-4 DSA for international consultant | Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.1.1-4 | HDV-23-003/3.1.1-4 DSA for international consultant | HDV-23-003/3.1.1Training programs designed and delivered for commercial banks/financial institutions | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 3.1.1 | 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Training programs, training at least 60 trainees (10% being women), designed and delivered to private bus operators, their bus drivers and workshop technicians on electric bus operational and financial feasibility (vs ICE buses), e-bus driving techniques, safety (including women's safety) and security aspects and maintenance, management of EV batteries/their scientific disposal. | Developing and/or delivering training | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Private bus operators' association and private bus operators, drivers, workshop technicians | 6/1/2025 | 11/30/2025 | Participant list with gender breakdown | null | null | null | 3.1 | Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Output 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 3.1.1Training programs designed and delivered for commercial banks/financial institutions | HDV-23-003/3.1.1 | HDV-23-003/3.1.1Training programs designed and delivered for commercial banks/financial institutions | HDV-23-003/3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.1 | Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Various targeted promotional events and public awareness campaigns on benefits of using low-carbon public transport in Sri Lanka will be held to gain public support for above transition | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Number of person hours of training provided | 9840 | Person hours | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | To raise public awareness on benefits of using public transport, especially low-carbon public transport, and to encourage usage of public transport in the country. | Tool, Tool, Photo or video, Tool, Tool, Photo or video | null | 10/31/2025 | Campaign materials and photos shared with CCAC | 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3.1 | HDV-23-003/3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3 | Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Designing and delivering training programs for various private sector stakeholders to improve technical capacity and financial/economic understanding of operating electric buses for public transport to help further uptake of electric buses even after the completion of the project. Raising public awareness on benefits of using low carbon public transport through various media, campaigns and events will help create demand for such transport. Estimated completion date: | Number of non-government entities with a demonstrated improved capacity for SLCP action | 7 | 7 non-government entities with improved capacity | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3. | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
3.1.1Training programs designed and delivered for commercial banks/financial institutions | Travel | 3.1.1-5 | DSA for national consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 14 | Days | 122 | 1708 | 0 | 1708 | 0 | Yes. | 3/1/2001 | Expenditure 3.1.1-5 DSA for national consultant | Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.1.1-5 | HDV-23-003/3.1.1-5 DSA for national consultant | HDV-23-003/3.1.1Training programs designed and delivered for commercial banks/financial institutions | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 3.1.1 | 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Training programs, training at least 60 trainees (10% being women), designed and delivered to private bus operators, their bus drivers and workshop technicians on electric bus operational and financial feasibility (vs ICE buses), e-bus driving techniques, safety (including women's safety) and security aspects and maintenance, management of EV batteries/their scientific disposal. | Developing and/or delivering training | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Private bus operators' association and private bus operators, drivers, workshop technicians | 6/1/2025 | 11/30/2025 | Participant list with gender breakdown | null | null | null | 3.1 | Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Output 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 3.1.1Training programs designed and delivered for commercial banks/financial institutions | HDV-23-003/3.1.1 | HDV-23-003/3.1.1Training programs designed and delivered for commercial banks/financial institutions | HDV-23-003/3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.1 | Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Various targeted promotional events and public awareness campaigns on benefits of using low-carbon public transport in Sri Lanka will be held to gain public support for above transition | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Number of person hours of training provided | 9840 | Person hours | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | To raise public awareness on benefits of using public transport, especially low-carbon public transport, and to encourage usage of public transport in the country. | Tool, Tool, Photo or video, Tool, Tool, Photo or video | null | 10/31/2025 | Campaign materials and photos shared with CCAC | 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3.1 | HDV-23-003/3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3 | Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Designing and delivering training programs for various private sector stakeholders to improve technical capacity and financial/economic understanding of operating electric buses for public transport to help further uptake of electric buses even after the completion of the project. Raising public awareness on benefits of using low carbon public transport through various media, campaigns and events will help create demand for such transport. Estimated completion date: | Number of non-government entities with a demonstrated improved capacity for SLCP action | 7 | 7 non-government entities with improved capacity | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3. | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
3.1.1Training programs designed and delivered for commercial banks/financial institutions | Supplies Commodities and Materials | 3.1.1-6 | Printing materials, handouts, audio-visual material | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 1 | Training materials | 1740 | 1740 | 0 | 1740 | 0 | Yes. | 3/1/2001 | Expenditure 3.1.1-6 Printing materials, handouts, audio-visual material | Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.1.1-6 | HDV-23-003/3.1.1-6 Printing materials, handouts, audio-visual material | HDV-23-003/3.1.1Training programs designed and delivered for commercial banks/financial institutions | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 3.1.1 | 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Training programs, training at least 60 trainees (10% being women), designed and delivered to private bus operators, their bus drivers and workshop technicians on electric bus operational and financial feasibility (vs ICE buses), e-bus driving techniques, safety (including women's safety) and security aspects and maintenance, management of EV batteries/their scientific disposal. | Developing and/or delivering training | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Private bus operators' association and private bus operators, drivers, workshop technicians | 6/1/2025 | 11/30/2025 | Participant list with gender breakdown | null | null | null | 3.1 | Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Output 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 3.1.1Training programs designed and delivered for commercial banks/financial institutions | HDV-23-003/3.1.1 | HDV-23-003/3.1.1Training programs designed and delivered for commercial banks/financial institutions | HDV-23-003/3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.1 | Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Various targeted promotional events and public awareness campaigns on benefits of using low-carbon public transport in Sri Lanka will be held to gain public support for above transition | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Number of person hours of training provided | 9840 | Person hours | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | To raise public awareness on benefits of using public transport, especially low-carbon public transport, and to encourage usage of public transport in the country. | Tool, Tool, Photo or video, Tool, Tool, Photo or video | null | 10/31/2025 | Campaign materials and photos shared with CCAC | 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3.1 | HDV-23-003/3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3 | Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Designing and delivering training programs for various private sector stakeholders to improve technical capacity and financial/economic understanding of operating electric buses for public transport to help further uptake of electric buses even after the completion of the project. Raising public awareness on benefits of using low carbon public transport through various media, campaigns and events will help create demand for such transport. Estimated completion date: | Number of non-government entities with a demonstrated improved capacity for SLCP action | 7 | 7 non-government entities with improved capacity | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3. | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
3.1.1Training programs designed and delivered for commercial banks/financial institutions | Contractual Services | 3.1.1-7 | Training venue and other contractual services | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 1 | Venue, food and others | 2000 | 2000 | 0 | 2000 | 0 | Yes. | 3/1/2001 | Expenditure 3.1.1-7 Training venue and other contractual services | Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.1.1-7 | HDV-23-003/3.1.1-7 Training venue and other contractual services | HDV-23-003/3.1.1Training programs designed and delivered for commercial banks/financial institutions | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 3.1.1 | 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Training programs, training at least 60 trainees (10% being women), designed and delivered to private bus operators, their bus drivers and workshop technicians on electric bus operational and financial feasibility (vs ICE buses), e-bus driving techniques, safety (including women's safety) and security aspects and maintenance, management of EV batteries/their scientific disposal. | Developing and/or delivering training | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Private bus operators' association and private bus operators, drivers, workshop technicians | 6/1/2025 | 11/30/2025 | Participant list with gender breakdown | null | null | null | 3.1 | Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Output 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 3.1.1Training programs designed and delivered for commercial banks/financial institutions | HDV-23-003/3.1.1 | HDV-23-003/3.1.1Training programs designed and delivered for commercial banks/financial institutions | HDV-23-003/3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.1 | Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Various targeted promotional events and public awareness campaigns on benefits of using low-carbon public transport in Sri Lanka will be held to gain public support for above transition | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Number of person hours of training provided | 9840 | Person hours | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | To raise public awareness on benefits of using public transport, especially low-carbon public transport, and to encourage usage of public transport in the country. | Tool, Tool, Photo or video, Tool, Tool, Photo or video | null | 10/31/2025 | Campaign materials and photos shared with CCAC | 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3.1 | HDV-23-003/3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3 | Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Designing and delivering training programs for various private sector stakeholders to improve technical capacity and financial/economic understanding of operating electric buses for public transport to help further uptake of electric buses even after the completion of the project. Raising public awareness on benefits of using low carbon public transport through various media, campaigns and events will help create demand for such transport. Estimated completion date: | Number of non-government entities with a demonstrated improved capacity for SLCP action | 7 | 7 non-government entities with improved capacity | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3. | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Staff and Other Personnel Costs | 3.1.2-1 | International consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 30 | Days | 500 | 15000 | 0 | 15000 | 0 | Yes. | 3/1/2002 | Expenditure 3.1.2-1 International consultant | Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.1.2-1 | HDV-23-003/3.1.2-1 International consultant | HDV-23-003/3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 3.1.2 | 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | At least 5 multi-channel mass media, social media and PIS promotional/advertising campaign designed and executed about the benefits of public transport, particularly low-carbon options such as electric buses, rail transport, park-and-ride schemes, bicycling, walking etc. This should include ongoing television/radio advertisements, print/newspaper campaigns running for about a month. | Developing and/or delivering training | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | 11/1/2024 | 4/28/2025 | Photo or video | null | null | null | 3.1 | Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Output 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | HDV-23-003/3.1.2 | HDV-23-003/3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | HDV-23-003/3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.1 | Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Various targeted promotional events and public awareness campaigns on benefits of using low-carbon public transport in Sri Lanka will be held to gain public support for above transition | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Number of person hours of training provided | 9840 | Person hours | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | To raise public awareness on benefits of using public transport, especially low-carbon public transport, and to encourage usage of public transport in the country. | Tool, Tool, Photo or video, Tool, Tool, Photo or video | null | 10/31/2025 | Campaign materials and photos shared with CCAC | 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3.1 | HDV-23-003/3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3 | Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Designing and delivering training programs for various private sector stakeholders to improve technical capacity and financial/economic understanding of operating electric buses for public transport to help further uptake of electric buses even after the completion of the project. Raising public awareness on benefits of using low carbon public transport through various media, campaigns and events will help create demand for such transport. Estimated completion date: | Number of non-government entities with a demonstrated improved capacity for SLCP action | 7 | 7 non-government entities with improved capacity | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3. | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Staff and Other Personnel Costs | 3.1.2-2 | National consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 40 | Days | 200 | 8000 | 0 | 8000 | 0 | Yes. | 3/1/2002 | Expenditure 3.1.2-2 National consultant | Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.1.2-2 | HDV-23-003/3.1.2-2 National consultant | HDV-23-003/3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 3.1.2 | 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | At least 5 multi-channel mass media, social media and PIS promotional/advertising campaign designed and executed about the benefits of public transport, particularly low-carbon options such as electric buses, rail transport, park-and-ride schemes, bicycling, walking etc. This should include ongoing television/radio advertisements, print/newspaper campaigns running for about a month. | Developing and/or delivering training | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | 11/1/2024 | 4/28/2025 | Photo or video | null | null | null | 3.1 | Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Output 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | HDV-23-003/3.1.2 | HDV-23-003/3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | HDV-23-003/3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.1 | Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Various targeted promotional events and public awareness campaigns on benefits of using low-carbon public transport in Sri Lanka will be held to gain public support for above transition | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Number of person hours of training provided | 9840 | Person hours | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | To raise public awareness on benefits of using public transport, especially low-carbon public transport, and to encourage usage of public transport in the country. | Tool, Tool, Photo or video, Tool, Tool, Photo or video | null | 10/31/2025 | Campaign materials and photos shared with CCAC | 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3.1 | HDV-23-003/3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3 | Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Designing and delivering training programs for various private sector stakeholders to improve technical capacity and financial/economic understanding of operating electric buses for public transport to help further uptake of electric buses even after the completion of the project. Raising public awareness on benefits of using low carbon public transport through various media, campaigns and events will help create demand for such transport. Estimated completion date: | Number of non-government entities with a demonstrated improved capacity for SLCP action | 7 | 7 non-government entities with improved capacity | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3. | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Travel | 3.1.2-3 | Travel fare | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 1 | Ticket fare for consultants | 500 | 500 | 0 | 500 | 0 | Yes. | 3/1/2002 | Expenditure 3.1.2-3 Travel fare | Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.1.2-3 | HDV-23-003/3.1.2-3 Travel fare | HDV-23-003/3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 3.1.2 | 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | At least 5 multi-channel mass media, social media and PIS promotional/advertising campaign designed and executed about the benefits of public transport, particularly low-carbon options such as electric buses, rail transport, park-and-ride schemes, bicycling, walking etc. This should include ongoing television/radio advertisements, print/newspaper campaigns running for about a month. | Developing and/or delivering training | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | 11/1/2024 | 4/28/2025 | Photo or video | null | null | null | 3.1 | Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Output 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | HDV-23-003/3.1.2 | HDV-23-003/3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | HDV-23-003/3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.1 | Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Various targeted promotional events and public awareness campaigns on benefits of using low-carbon public transport in Sri Lanka will be held to gain public support for above transition | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Number of person hours of training provided | 9840 | Person hours | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | To raise public awareness on benefits of using public transport, especially low-carbon public transport, and to encourage usage of public transport in the country. | Tool, Tool, Photo or video, Tool, Tool, Photo or video | null | 10/31/2025 | Campaign materials and photos shared with CCAC | 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3.1 | HDV-23-003/3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3 | Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Designing and delivering training programs for various private sector stakeholders to improve technical capacity and financial/economic understanding of operating electric buses for public transport to help further uptake of electric buses even after the completion of the project. Raising public awareness on benefits of using low carbon public transport through various media, campaigns and events will help create demand for such transport. Estimated completion date: | Number of non-government entities with a demonstrated improved capacity for SLCP action | 7 | 7 non-government entities with improved capacity | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3. | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Travel | 3.1.2-4 | DSA for international consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 17 | Days | 192 | 3264 | 0 | 3264 | 0 | Yes. | 3/1/2002 | Expenditure 3.1.2-4 DSA for international consultant | Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.1.2-4 | HDV-23-003/3.1.2-4 DSA for international consultant | HDV-23-003/3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 3.1.2 | 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | At least 5 multi-channel mass media, social media and PIS promotional/advertising campaign designed and executed about the benefits of public transport, particularly low-carbon options such as electric buses, rail transport, park-and-ride schemes, bicycling, walking etc. This should include ongoing television/radio advertisements, print/newspaper campaigns running for about a month. | Developing and/or delivering training | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | 11/1/2024 | 4/28/2025 | Photo or video | null | null | null | 3.1 | Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Output 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | HDV-23-003/3.1.2 | HDV-23-003/3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | HDV-23-003/3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.1 | Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Various targeted promotional events and public awareness campaigns on benefits of using low-carbon public transport in Sri Lanka will be held to gain public support for above transition | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Number of person hours of training provided | 9840 | Person hours | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | To raise public awareness on benefits of using public transport, especially low-carbon public transport, and to encourage usage of public transport in the country. | Tool, Tool, Photo or video, Tool, Tool, Photo or video | null | 10/31/2025 | Campaign materials and photos shared with CCAC | 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3.1 | HDV-23-003/3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3 | Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Designing and delivering training programs for various private sector stakeholders to improve technical capacity and financial/economic understanding of operating electric buses for public transport to help further uptake of electric buses even after the completion of the project. Raising public awareness on benefits of using low carbon public transport through various media, campaigns and events will help create demand for such transport. Estimated completion date: | Number of non-government entities with a demonstrated improved capacity for SLCP action | 7 | 7 non-government entities with improved capacity | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3. | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Travel | 3.1.2-5 | DSA for national consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 14 | Days | 122 | 1708 | 0 | 1708 | 0 | Yes. | 3/1/2002 | Expenditure 3.1.2-5 DSA for national consultant | Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.1.2-5 | HDV-23-003/3.1.2-5 DSA for national consultant | HDV-23-003/3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 3.1.2 | 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | At least 5 multi-channel mass media, social media and PIS promotional/advertising campaign designed and executed about the benefits of public transport, particularly low-carbon options such as electric buses, rail transport, park-and-ride schemes, bicycling, walking etc. This should include ongoing television/radio advertisements, print/newspaper campaigns running for about a month. | Developing and/or delivering training | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | 11/1/2024 | 4/28/2025 | Photo or video | null | null | null | 3.1 | Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Output 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | HDV-23-003/3.1.2 | HDV-23-003/3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | HDV-23-003/3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.1 | Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Various targeted promotional events and public awareness campaigns on benefits of using low-carbon public transport in Sri Lanka will be held to gain public support for above transition | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Number of person hours of training provided | 9840 | Person hours | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | To raise public awareness on benefits of using public transport, especially low-carbon public transport, and to encourage usage of public transport in the country. | Tool, Tool, Photo or video, Tool, Tool, Photo or video | null | 10/31/2025 | Campaign materials and photos shared with CCAC | 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3.1 | HDV-23-003/3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3 | Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Designing and delivering training programs for various private sector stakeholders to improve technical capacity and financial/economic understanding of operating electric buses for public transport to help further uptake of electric buses even after the completion of the project. Raising public awareness on benefits of using low carbon public transport through various media, campaigns and events will help create demand for such transport. Estimated completion date: | Number of non-government entities with a demonstrated improved capacity for SLCP action | 7 | 7 non-government entities with improved capacity | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3. | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Supplies Commodities and Materials | 3.1.2-6 | Printing materials, handouts, audio-visual material | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 1 | Training materials | 2000 | 2000 | 0 | 2000 | 0 | Yes. | 3/1/2002 | Expenditure 3.1.2-6 Printing materials, handouts, audio-visual material | Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.1.2-6 | HDV-23-003/3.1.2-6 Printing materials, handouts, audio-visual material | HDV-23-003/3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 3.1.2 | 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | At least 5 multi-channel mass media, social media and PIS promotional/advertising campaign designed and executed about the benefits of public transport, particularly low-carbon options such as electric buses, rail transport, park-and-ride schemes, bicycling, walking etc. This should include ongoing television/radio advertisements, print/newspaper campaigns running for about a month. | Developing and/or delivering training | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | 11/1/2024 | 4/28/2025 | Photo or video | null | null | null | 3.1 | Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Output 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | HDV-23-003/3.1.2 | HDV-23-003/3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | HDV-23-003/3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.1 | Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Various targeted promotional events and public awareness campaigns on benefits of using low-carbon public transport in Sri Lanka will be held to gain public support for above transition | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Number of person hours of training provided | 9840 | Person hours | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | To raise public awareness on benefits of using public transport, especially low-carbon public transport, and to encourage usage of public transport in the country. | Tool, Tool, Photo or video, Tool, Tool, Photo or video | null | 10/31/2025 | Campaign materials and photos shared with CCAC | 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3.1 | HDV-23-003/3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3 | Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Designing and delivering training programs for various private sector stakeholders to improve technical capacity and financial/economic understanding of operating electric buses for public transport to help further uptake of electric buses even after the completion of the project. Raising public awareness on benefits of using low carbon public transport through various media, campaigns and events will help create demand for such transport. Estimated completion date: | Number of non-government entities with a demonstrated improved capacity for SLCP action | 7 | 7 non-government entities with improved capacity | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3. | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Contractual Services | 3.1.2-7 | Training venue and other contractual services | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 1 | Venue, food and others | 2000 | 2000 | 0 | 2000 | 0 | Yes. | 3/1/2002 | Expenditure 3.1.2-7 Training venue and other contractual services | Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.1.2-7 | HDV-23-003/3.1.2-7 Training venue and other contractual services | HDV-23-003/3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 3.1.2 | 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | At least 5 multi-channel mass media, social media and PIS promotional/advertising campaign designed and executed about the benefits of public transport, particularly low-carbon options such as electric buses, rail transport, park-and-ride schemes, bicycling, walking etc. This should include ongoing television/radio advertisements, print/newspaper campaigns running for about a month. | Developing and/or delivering training | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | 11/1/2024 | 4/28/2025 | Photo or video | null | null | null | 3.1 | Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Output 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | HDV-23-003/3.1.2 | HDV-23-003/3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | HDV-23-003/3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.1 | Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Various targeted promotional events and public awareness campaigns on benefits of using low-carbon public transport in Sri Lanka will be held to gain public support for above transition | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Number of person hours of training provided | 9840 | Person hours | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | To raise public awareness on benefits of using public transport, especially low-carbon public transport, and to encourage usage of public transport in the country. | Tool, Tool, Photo or video, Tool, Tool, Photo or video | null | 10/31/2025 | Campaign materials and photos shared with CCAC | 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3.1 | HDV-23-003/3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3 | Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Designing and delivering training programs for various private sector stakeholders to improve technical capacity and financial/economic understanding of operating electric buses for public transport to help further uptake of electric buses even after the completion of the project. Raising public awareness on benefits of using low carbon public transport through various media, campaigns and events will help create demand for such transport. Estimated completion date: | Number of non-government entities with a demonstrated improved capacity for SLCP action | 7 | 7 non-government entities with improved capacity | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3. | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
3.2.1Mass media promotional campaigns on benefits of public transport | Staff and Other Personnel Costs | 3.2.1-1 | National consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 28 | Days | 200 | 5600 | 5600 | 0 | 0 | Yes. | 3/2/2001 | Expenditure 3.2.1-1 National consultant | Activity 3.2.1Mass media promotional campaigns on benefits of public transport | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.2.1-1 | HDV-23-003/3.2.1-1 National consultant | HDV-23-003/3.2.1Mass media promotional campaigns on benefits of public transport | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | 3.2.1 | 3.2.1Mass media promotional campaigns on benefits of public transport | At least 20 targeted promotional events (town-level/community-level, at SLTB bus stations, schools or corporate offices) designed, planned and executed on the benefits of using public transport | Producing and distributing communications materials | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | 5/1/2025 | 10/31/2025 | Photo or video | null | null | null | 3.2 | Activity 3.2.1Mass media promotional campaigns on benefits of public transport | Output 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | 3.2.1Mass media promotional campaigns on benefits of public transport | HDV-23-003/3.2.1 | HDV-23-003/3.2.1Mass media promotional campaigns on benefits of public transport | HDV-23-003/3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.2 | Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Technical assistance provided to the government of Sri Lanka to setup and operationalise subsidy scheme to enable procurement and deployment of the first electric buses for public transport in Sri Lanka | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Number of partnerships, associations, or campaigns launched to drive SLCP action | 35 | Campaigns | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | To have a capital subsidy scheme for electric buses through which future envisaged funding can be channelled to scale-up and deploy more electric buses for public transport. This scheme will enable to rollout the first set of electric buses through a capital subsidy scheme. | Inventory, Funding proposal, Photo or video | null | 11/30/2025 | Procurement documents reviewed and approved by CCAC | 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Output 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3.2 | HDV-23-003/3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Output | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3 | Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Designing and delivering training programs for various private sector stakeholders to improve technical capacity and financial/economic understanding of operating electric buses for public transport to help further uptake of electric buses even after the completion of the project. Raising public awareness on benefits of using low carbon public transport through various media, campaigns and events will help create demand for such transport. Estimated completion date: | Number of non-government entities with a demonstrated improved capacity for SLCP action | 7 | 7 non-government entities with improved capacity | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3. | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
3.2.1Mass media promotional campaigns on benefits of public transport | Travel | 3.2.1-2 | DSA for national consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 7 | Days | 122 | 854 | 854 | 0 | 0 | Yes. | 3/2/2001 | Expenditure 3.2.1-2 DSA for national consultant | Activity 3.2.1Mass media promotional campaigns on benefits of public transport | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.2.1-2 | HDV-23-003/3.2.1-2 DSA for national consultant | HDV-23-003/3.2.1Mass media promotional campaigns on benefits of public transport | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | 3.2.1 | 3.2.1Mass media promotional campaigns on benefits of public transport | At least 20 targeted promotional events (town-level/community-level, at SLTB bus stations, schools or corporate offices) designed, planned and executed on the benefits of using public transport | Producing and distributing communications materials | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | 5/1/2025 | 10/31/2025 | Photo or video | null | null | null | 3.2 | Activity 3.2.1Mass media promotional campaigns on benefits of public transport | Output 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | 3.2.1Mass media promotional campaigns on benefits of public transport | HDV-23-003/3.2.1 | HDV-23-003/3.2.1Mass media promotional campaigns on benefits of public transport | HDV-23-003/3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.2 | Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Technical assistance provided to the government of Sri Lanka to setup and operationalise subsidy scheme to enable procurement and deployment of the first electric buses for public transport in Sri Lanka | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Number of partnerships, associations, or campaigns launched to drive SLCP action | 35 | Campaigns | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | To have a capital subsidy scheme for electric buses through which future envisaged funding can be channelled to scale-up and deploy more electric buses for public transport. This scheme will enable to rollout the first set of electric buses through a capital subsidy scheme. | Inventory, Funding proposal, Photo or video | null | 11/30/2025 | Procurement documents reviewed and approved by CCAC | 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Output 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3.2 | HDV-23-003/3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Output | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3 | Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Designing and delivering training programs for various private sector stakeholders to improve technical capacity and financial/economic understanding of operating electric buses for public transport to help further uptake of electric buses even after the completion of the project. Raising public awareness on benefits of using low carbon public transport through various media, campaigns and events will help create demand for such transport. Estimated completion date: | Number of non-government entities with a demonstrated improved capacity for SLCP action | 7 | 7 non-government entities with improved capacity | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3. | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
3.2.1Mass media promotional campaigns on benefits of public transport | Supplies Commodities and Materials | 3.2.1-3 | Audio visual material, posters, handouts | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 1 | Campaign/event materials | 2500 | 2500 | 1666.6667 | 833.3333 | 0 | Yes. | 3/2/2001 | Expenditure 3.2.1-3 Audio visual material, posters, handouts | Activity 3.2.1Mass media promotional campaigns on benefits of public transport | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.2.1-3 | HDV-23-003/3.2.1-3 Audio visual material, posters, handouts | HDV-23-003/3.2.1Mass media promotional campaigns on benefits of public transport | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | 3.2.1 | 3.2.1Mass media promotional campaigns on benefits of public transport | At least 20 targeted promotional events (town-level/community-level, at SLTB bus stations, schools or corporate offices) designed, planned and executed on the benefits of using public transport | Producing and distributing communications materials | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | 5/1/2025 | 10/31/2025 | Photo or video | null | null | null | 3.2 | Activity 3.2.1Mass media promotional campaigns on benefits of public transport | Output 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | 3.2.1Mass media promotional campaigns on benefits of public transport | HDV-23-003/3.2.1 | HDV-23-003/3.2.1Mass media promotional campaigns on benefits of public transport | HDV-23-003/3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.2 | Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Technical assistance provided to the government of Sri Lanka to setup and operationalise subsidy scheme to enable procurement and deployment of the first electric buses for public transport in Sri Lanka | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Number of partnerships, associations, or campaigns launched to drive SLCP action | 35 | Campaigns | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | To have a capital subsidy scheme for electric buses through which future envisaged funding can be channelled to scale-up and deploy more electric buses for public transport. This scheme will enable to rollout the first set of electric buses through a capital subsidy scheme. | Inventory, Funding proposal, Photo or video | null | 11/30/2025 | Procurement documents reviewed and approved by CCAC | 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Output 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3.2 | HDV-23-003/3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Output | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3 | Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Designing and delivering training programs for various private sector stakeholders to improve technical capacity and financial/economic understanding of operating electric buses for public transport to help further uptake of electric buses even after the completion of the project. Raising public awareness on benefits of using low carbon public transport through various media, campaigns and events will help create demand for such transport. Estimated completion date: | Number of non-government entities with a demonstrated improved capacity for SLCP action | 7 | 7 non-government entities with improved capacity | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3. | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
3.2.1Mass media promotional campaigns on benefits of public transport | Contractual Services | 3.2.1-4 | Training venue and other contractual services | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 1 | Venue, food and others | 30000 | 30000 | 20000 | 10000 | 0 | Yes. | 3/2/2001 | Expenditure 3.2.1-4 Training venue and other contractual services | Activity 3.2.1Mass media promotional campaigns on benefits of public transport | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.2.1-4 | HDV-23-003/3.2.1-4 Training venue and other contractual services | HDV-23-003/3.2.1Mass media promotional campaigns on benefits of public transport | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | 3.2.1 | 3.2.1Mass media promotional campaigns on benefits of public transport | At least 20 targeted promotional events (town-level/community-level, at SLTB bus stations, schools or corporate offices) designed, planned and executed on the benefits of using public transport | Producing and distributing communications materials | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | 5/1/2025 | 10/31/2025 | Photo or video | null | null | null | 3.2 | Activity 3.2.1Mass media promotional campaigns on benefits of public transport | Output 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | 3.2.1Mass media promotional campaigns on benefits of public transport | HDV-23-003/3.2.1 | HDV-23-003/3.2.1Mass media promotional campaigns on benefits of public transport | HDV-23-003/3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.2 | Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Technical assistance provided to the government of Sri Lanka to setup and operationalise subsidy scheme to enable procurement and deployment of the first electric buses for public transport in Sri Lanka | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Number of partnerships, associations, or campaigns launched to drive SLCP action | 35 | Campaigns | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | To have a capital subsidy scheme for electric buses through which future envisaged funding can be channelled to scale-up and deploy more electric buses for public transport. This scheme will enable to rollout the first set of electric buses through a capital subsidy scheme. | Inventory, Funding proposal, Photo or video | null | 11/30/2025 | Procurement documents reviewed and approved by CCAC | 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Output 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3.2 | HDV-23-003/3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Output | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3 | Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Designing and delivering training programs for various private sector stakeholders to improve technical capacity and financial/economic understanding of operating electric buses for public transport to help further uptake of electric buses even after the completion of the project. Raising public awareness on benefits of using low carbon public transport through various media, campaigns and events will help create demand for such transport. Estimated completion date: | Number of non-government entities with a demonstrated improved capacity for SLCP action | 7 | 7 non-government entities with improved capacity | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3. | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
3.2.2Targeted promotional events on benefits of public transport | Staff and Other Personnel Costs | 3.2.2-1 | National consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 30 | Days | 200 | 6000 | 0 | 6000 | 0 | Yes. | 3/2/2002 | Expenditure 3.2.2-1 National consultant | Activity 3.2.2Targeted promotional events on benefits of public transport | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.2.2-1 | HDV-23-003/3.2.2-1 National consultant | HDV-23-003/3.2.2Targeted promotional events on benefits of public transport | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | 3.2.2 | 3.2.2Targeted promotional events on benefits of public transport | At least 10 targeted campaigns planned and executed on safety and comfort features on public transport buses, such as women's safety due to installation of CCTV cameras and road/driver safety features on electric buses | Organising, holding, or participating in a meeting or event | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | 5/1/2025 | 10/31/2025 | Photo or video | null | null | null | 3.2 | Activity 3.2.2Targeted promotional events on benefits of public transport | Output 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | 3.2.2Targeted promotional events on benefits of public transport | HDV-23-003/3.2.2 | HDV-23-003/3.2.2Targeted promotional events on benefits of public transport | HDV-23-003/3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.2 | Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Technical assistance provided to the government of Sri Lanka to setup and operationalise subsidy scheme to enable procurement and deployment of the first electric buses for public transport in Sri Lanka | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Number of partnerships, associations, or campaigns launched to drive SLCP action | 35 | Campaigns | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | To have a capital subsidy scheme for electric buses through which future envisaged funding can be channelled to scale-up and deploy more electric buses for public transport. This scheme will enable to rollout the first set of electric buses through a capital subsidy scheme. | Inventory, Funding proposal, Photo or video | null | 11/30/2025 | Procurement documents reviewed and approved by CCAC | 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Output 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3.2 | HDV-23-003/3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Output | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3 | Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Designing and delivering training programs for various private sector stakeholders to improve technical capacity and financial/economic understanding of operating electric buses for public transport to help further uptake of electric buses even after the completion of the project. Raising public awareness on benefits of using low carbon public transport through various media, campaigns and events will help create demand for such transport. Estimated completion date: | Number of non-government entities with a demonstrated improved capacity for SLCP action | 7 | 7 non-government entities with improved capacity | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3. | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
3.2.2Targeted promotional events on benefits of public transport | Travel | 3.2.2-2 | DSA for national consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 7 | Days | 122 | 854 | 0 | 854 | 0 | Yes. | 3/2/2002 | Expenditure 3.2.2-2 DSA for national consultant | Activity 3.2.2Targeted promotional events on benefits of public transport | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.2.2-2 | HDV-23-003/3.2.2-2 DSA for national consultant | HDV-23-003/3.2.2Targeted promotional events on benefits of public transport | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | 3.2.2 | 3.2.2Targeted promotional events on benefits of public transport | At least 10 targeted campaigns planned and executed on safety and comfort features on public transport buses, such as women's safety due to installation of CCTV cameras and road/driver safety features on electric buses | Organising, holding, or participating in a meeting or event | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | 5/1/2025 | 10/31/2025 | Photo or video | null | null | null | 3.2 | Activity 3.2.2Targeted promotional events on benefits of public transport | Output 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | 3.2.2Targeted promotional events on benefits of public transport | HDV-23-003/3.2.2 | HDV-23-003/3.2.2Targeted promotional events on benefits of public transport | HDV-23-003/3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.2 | Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Technical assistance provided to the government of Sri Lanka to setup and operationalise subsidy scheme to enable procurement and deployment of the first electric buses for public transport in Sri Lanka | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Number of partnerships, associations, or campaigns launched to drive SLCP action | 35 | Campaigns | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | To have a capital subsidy scheme for electric buses through which future envisaged funding can be channelled to scale-up and deploy more electric buses for public transport. This scheme will enable to rollout the first set of electric buses through a capital subsidy scheme. | Inventory, Funding proposal, Photo or video | null | 11/30/2025 | Procurement documents reviewed and approved by CCAC | 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Output 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3.2 | HDV-23-003/3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Output | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3 | Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Designing and delivering training programs for various private sector stakeholders to improve technical capacity and financial/economic understanding of operating electric buses for public transport to help further uptake of electric buses even after the completion of the project. Raising public awareness on benefits of using low carbon public transport through various media, campaigns and events will help create demand for such transport. Estimated completion date: | Number of non-government entities with a demonstrated improved capacity for SLCP action | 7 | 7 non-government entities with improved capacity | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3. | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
3.2.2Targeted promotional events on benefits of public transport | Supplies Commodities and Materials | 3.2.2-3 | Audio visual material, posters, handouts | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 1 | Campaign/event materials | 2000 | 2000 | 0 | 2000 | 0 | Yes. | 3/2/2002 | Expenditure 3.2.2-3 Audio visual material, posters, handouts | Activity 3.2.2Targeted promotional events on benefits of public transport | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.2.2-3 | HDV-23-003/3.2.2-3 Audio visual material, posters, handouts | HDV-23-003/3.2.2Targeted promotional events on benefits of public transport | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | 3.2.2 | 3.2.2Targeted promotional events on benefits of public transport | At least 10 targeted campaigns planned and executed on safety and comfort features on public transport buses, such as women's safety due to installation of CCTV cameras and road/driver safety features on electric buses | Organising, holding, or participating in a meeting or event | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | 5/1/2025 | 10/31/2025 | Photo or video | null | null | null | 3.2 | Activity 3.2.2Targeted promotional events on benefits of public transport | Output 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | 3.2.2Targeted promotional events on benefits of public transport | HDV-23-003/3.2.2 | HDV-23-003/3.2.2Targeted promotional events on benefits of public transport | HDV-23-003/3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.2 | Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Technical assistance provided to the government of Sri Lanka to setup and operationalise subsidy scheme to enable procurement and deployment of the first electric buses for public transport in Sri Lanka | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Number of partnerships, associations, or campaigns launched to drive SLCP action | 35 | Campaigns | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | To have a capital subsidy scheme for electric buses through which future envisaged funding can be channelled to scale-up and deploy more electric buses for public transport. This scheme will enable to rollout the first set of electric buses through a capital subsidy scheme. | Inventory, Funding proposal, Photo or video | null | 11/30/2025 | Procurement documents reviewed and approved by CCAC | 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Output 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3.2 | HDV-23-003/3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Output | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3 | Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Designing and delivering training programs for various private sector stakeholders to improve technical capacity and financial/economic understanding of operating electric buses for public transport to help further uptake of electric buses even after the completion of the project. Raising public awareness on benefits of using low carbon public transport through various media, campaigns and events will help create demand for such transport. Estimated completion date: | Number of non-government entities with a demonstrated improved capacity for SLCP action | 7 | 7 non-government entities with improved capacity | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3. | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
3.2.2Targeted promotional events on benefits of public transport | Contractual Services | 3.2.2-4 | Training venue and other contractual services | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 1 | Venue, food and others | 30000 | 30000 | 0 | 30000 | 0 | Yes. | 3/2/2002 | Expenditure 3.2.2-4 Training venue and other contractual services | Activity 3.2.2Targeted promotional events on benefits of public transport | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.2.2-4 | HDV-23-003/3.2.2-4 Training venue and other contractual services | HDV-23-003/3.2.2Targeted promotional events on benefits of public transport | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | 3.2.2 | 3.2.2Targeted promotional events on benefits of public transport | At least 10 targeted campaigns planned and executed on safety and comfort features on public transport buses, such as women's safety due to installation of CCTV cameras and road/driver safety features on electric buses | Organising, holding, or participating in a meeting or event | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | 5/1/2025 | 10/31/2025 | Photo or video | null | null | null | 3.2 | Activity 3.2.2Targeted promotional events on benefits of public transport | Output 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | 3.2.2Targeted promotional events on benefits of public transport | HDV-23-003/3.2.2 | HDV-23-003/3.2.2Targeted promotional events on benefits of public transport | HDV-23-003/3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.2 | Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Technical assistance provided to the government of Sri Lanka to setup and operationalise subsidy scheme to enable procurement and deployment of the first electric buses for public transport in Sri Lanka | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Number of partnerships, associations, or campaigns launched to drive SLCP action | 35 | Campaigns | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | To have a capital subsidy scheme for electric buses through which future envisaged funding can be channelled to scale-up and deploy more electric buses for public transport. This scheme will enable to rollout the first set of electric buses through a capital subsidy scheme. | Inventory, Funding proposal, Photo or video | null | 11/30/2025 | Procurement documents reviewed and approved by CCAC | 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Output 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3.2 | HDV-23-003/3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Output | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3 | Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Designing and delivering training programs for various private sector stakeholders to improve technical capacity and financial/economic understanding of operating electric buses for public transport to help further uptake of electric buses even after the completion of the project. Raising public awareness on benefits of using low carbon public transport through various media, campaigns and events will help create demand for such transport. Estimated completion date: | Number of non-government entities with a demonstrated improved capacity for SLCP action | 7 | 7 non-government entities with improved capacity | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3. | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | Staff and Other Personnel Costs | 3.2.3-1 | National consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 30 | Days | 200 | 6000 | 0 | 6000 | 0 | Yes. | 3/2/2003 | Expenditure 3.2.3-1 National consultant | Activity 3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.2.3-1 | HDV-23-003/3.2.3-1 National consultant | HDV-23-003/3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | 3.2.3 | 3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | Enhanced capital subsidy scheme (including the procedure for application, evaluation, verification and disbursement of capital subsidies) is instituted under a government programme, offering subsidies up to an indicative level of 30% of capital costs of an electric bus based on current estimates of capital costs. | Producing and distributing communications materials | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | 2/1/2025 | 5/31/2025 | Tool | null | null | null | 3.2 | Activity 3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | Output 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | 3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | HDV-23-003/3.2.3 | HDV-23-003/3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | HDV-23-003/3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.2 | Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Technical assistance provided to the government of Sri Lanka to setup and operationalise subsidy scheme to enable procurement and deployment of the first electric buses for public transport in Sri Lanka | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Number of partnerships, associations, or campaigns launched to drive SLCP action | 35 | Campaigns | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | To have a capital subsidy scheme for electric buses through which future envisaged funding can be channelled to scale-up and deploy more electric buses for public transport. This scheme will enable to rollout the first set of electric buses through a capital subsidy scheme. | Inventory, Funding proposal, Photo or video | null | 11/30/2025 | Procurement documents reviewed and approved by CCAC | 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Output 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3.2 | HDV-23-003/3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Output | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3 | Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Designing and delivering training programs for various private sector stakeholders to improve technical capacity and financial/economic understanding of operating electric buses for public transport to help further uptake of electric buses even after the completion of the project. Raising public awareness on benefits of using low carbon public transport through various media, campaigns and events will help create demand for such transport. Estimated completion date: | Number of non-government entities with a demonstrated improved capacity for SLCP action | 7 | 7 non-government entities with improved capacity | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3. | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | Travel | 3.2.3-2 | DSA for national consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 7 | Days | 122 | 854 | 0 | 854 | 0 | Yes. | 3/2/2003 | Expenditure 3.2.3-2 DSA for national consultant | Activity 3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.2.3-2 | HDV-23-003/3.2.3-2 DSA for national consultant | HDV-23-003/3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | 3.2.3 | 3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | Enhanced capital subsidy scheme (including the procedure for application, evaluation, verification and disbursement of capital subsidies) is instituted under a government programme, offering subsidies up to an indicative level of 30% of capital costs of an electric bus based on current estimates of capital costs. | Producing and distributing communications materials | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | 2/1/2025 | 5/31/2025 | Tool | null | null | null | 3.2 | Activity 3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | Output 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | 3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | HDV-23-003/3.2.3 | HDV-23-003/3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | HDV-23-003/3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.2 | Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Technical assistance provided to the government of Sri Lanka to setup and operationalise subsidy scheme to enable procurement and deployment of the first electric buses for public transport in Sri Lanka | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Number of partnerships, associations, or campaigns launched to drive SLCP action | 35 | Campaigns | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | To have a capital subsidy scheme for electric buses through which future envisaged funding can be channelled to scale-up and deploy more electric buses for public transport. This scheme will enable to rollout the first set of electric buses through a capital subsidy scheme. | Inventory, Funding proposal, Photo or video | null | 11/30/2025 | Procurement documents reviewed and approved by CCAC | 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Output 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3.2 | HDV-23-003/3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Output | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3 | Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Designing and delivering training programs for various private sector stakeholders to improve technical capacity and financial/economic understanding of operating electric buses for public transport to help further uptake of electric buses even after the completion of the project. Raising public awareness on benefits of using low carbon public transport through various media, campaigns and events will help create demand for such transport. Estimated completion date: | Number of non-government entities with a demonstrated improved capacity for SLCP action | 7 | 7 non-government entities with improved capacity | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3. | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | Supplies Commodities and Materials | 3.2.3-3 | Audio visual material, posters, handouts | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 1 | Campaign/event materials | 2000 | 2000 | 0 | 2000 | 0 | Yes. | 3/2/2003 | Expenditure 3.2.3-3 Audio visual material, posters, handouts | Activity 3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.2.3-3 | HDV-23-003/3.2.3-3 Audio visual material, posters, handouts | HDV-23-003/3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | 3.2.3 | 3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | Enhanced capital subsidy scheme (including the procedure for application, evaluation, verification and disbursement of capital subsidies) is instituted under a government programme, offering subsidies up to an indicative level of 30% of capital costs of an electric bus based on current estimates of capital costs. | Producing and distributing communications materials | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | 2/1/2025 | 5/31/2025 | Tool | null | null | null | 3.2 | Activity 3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | Output 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | 3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | HDV-23-003/3.2.3 | HDV-23-003/3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | HDV-23-003/3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.2 | Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Technical assistance provided to the government of Sri Lanka to setup and operationalise subsidy scheme to enable procurement and deployment of the first electric buses for public transport in Sri Lanka | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Number of partnerships, associations, or campaigns launched to drive SLCP action | 35 | Campaigns | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | To have a capital subsidy scheme for electric buses through which future envisaged funding can be channelled to scale-up and deploy more electric buses for public transport. This scheme will enable to rollout the first set of electric buses through a capital subsidy scheme. | Inventory, Funding proposal, Photo or video | null | 11/30/2025 | Procurement documents reviewed and approved by CCAC | 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Output 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3.2 | HDV-23-003/3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Output | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3 | Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Designing and delivering training programs for various private sector stakeholders to improve technical capacity and financial/economic understanding of operating electric buses for public transport to help further uptake of electric buses even after the completion of the project. Raising public awareness on benefits of using low carbon public transport through various media, campaigns and events will help create demand for such transport. Estimated completion date: | Number of non-government entities with a demonstrated improved capacity for SLCP action | 7 | 7 non-government entities with improved capacity | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3. | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | Contractual Services | 3.2.3-4 | Training venue and other contractual services | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 1 | Venue, food and others | 15000 | 15000 | 0 | 15000 | 0 | Yes. | 3/2/2003 | Expenditure 3.2.3-4 Training venue and other contractual services | Activity 3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.2.3-4 | HDV-23-003/3.2.3-4 Training venue and other contractual services | HDV-23-003/3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | 3.2.3 | 3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | Enhanced capital subsidy scheme (including the procedure for application, evaluation, verification and disbursement of capital subsidies) is instituted under a government programme, offering subsidies up to an indicative level of 30% of capital costs of an electric bus based on current estimates of capital costs. | Producing and distributing communications materials | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | 2/1/2025 | 5/31/2025 | Tool | null | null | null | 3.2 | Activity 3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | Output 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | 3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | HDV-23-003/3.2.3 | HDV-23-003/3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | HDV-23-003/3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3.2 | Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Technical assistance provided to the government of Sri Lanka to setup and operationalise subsidy scheme to enable procurement and deployment of the first electric buses for public transport in Sri Lanka | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Number of partnerships, associations, or campaigns launched to drive SLCP action | 35 | Campaigns | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | To have a capital subsidy scheme for electric buses through which future envisaged funding can be channelled to scale-up and deploy more electric buses for public transport. This scheme will enable to rollout the first set of electric buses through a capital subsidy scheme. | Inventory, Funding proposal, Photo or video | null | 11/30/2025 | Procurement documents reviewed and approved by CCAC | 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Output 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3.2 | HDV-23-003/3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Output | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 3 | Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Designing and delivering training programs for various private sector stakeholders to improve technical capacity and financial/economic understanding of operating electric buses for public transport to help further uptake of electric buses even after the completion of the project. Raising public awareness on benefits of using low carbon public transport through various media, campaigns and events will help create demand for such transport. Estimated completion date: | Number of non-government entities with a demonstrated improved capacity for SLCP action | 7 | 7 non-government entities with improved capacity | 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | HDV-23-003/3. | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
4.1.1Technical assistance to setup a mechanism for channelling of enhanced grants as capital subsidy scheme | Staff and Other Personnel Costs | 4.1.1-1 | National consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 100 | Days | 200 | 20000 | 0 | 20000 | 0 | Yes. | 4/1/2001 | Expenditure 4.1.1-1 National consultant | Activity 4.1.1Technical assistance to setup a mechanism for channelling of enhanced grants as capital subsidy scheme | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/4.1.1-1 | HDV-23-003/4.1.1-1 National consultant | HDV-23-003/4.1.1Technical assistance to setup a mechanism for channelling of enhanced grants as capital subsidy scheme | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 4.1 5 small/medium 9-metre buses deployed through public private partnerships in Colombo Municipal area after selection of vendor/OEM through a competitive tender process as per UN procurement rules | 4.1.1 | 4.1.1Technical assistance to setup a mechanism for channelling of enhanced grants as capital subsidy scheme | Five electric buses on public transport routes within Colombo city are procured and deployed with support from capital subsidy instituted in the previous activity. | Policy, project, or tool design | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | null | 6/1/2025 | 11/30/2025 | Inventory | null | null | null | 4.1 | Activity 4.1.1Technical assistance to setup a mechanism for channelling of enhanced grants as capital subsidy scheme | Output 4.1 5 small/medium 9-metre buses deployed through public private partnerships in Colombo Municipal area after selection of vendor/OEM through a competitive tender process as per UN procurement rules | 4.1.1Technical assistance to setup a mechanism for channelling of enhanced grants as capital subsidy scheme | HDV-23-003/4.1.1 | HDV-23-003/4.1.1Technical assistance to setup a mechanism for channelling of enhanced grants as capital subsidy scheme | HDV-23-003/4.1 5 small/medium 9-metre buses deployed through public private partnerships in Colombo Municipal area after selection of vendor/OEM through a competitive tender process as per UN procurement rules | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 4.1 | 5 small/medium 9-metre buses deployed through public private partnerships in Colombo Municipal area after selection of vendor/OEM through a competitive tender process as per UN procurement rules | An informative webinar will be conducted to convey the project's objectives, approach, outcomes achieved and learnings to all relevant participants. | 4. Private sector bus operators engage in low carbon public transport through financial incentive package for electric buses by end of the project | Number of tools, equipment, or technologies installed | 5 | Electric buses | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | null | To communicate to wider audiences about such a project being completed in Sri Lanka, which has enabled introduction of electric buses and helped the country transition towards low-carbon transport. This will strengthen the knowledge base on E bus deployment. | Meeting report, Participant list with gender breakdown, Photo or video, Meeting report, Participant list with gender breakdown, Photo or video, Meeting report, Participant list with gender breakdown, Photo or video, Meeting report, Participant list with gender breakdown, Photo or video | null | 5/15/2026 | Webinar material reviewed and approved by CCAC; webinar attended by CCAC | 4.1 5 small/medium 9-metre buses deployed through public private partnerships in Colombo Municipal area after selection of vendor/OEM through a competitive tender process as per UN procurement rules | Output 4.1 5 small/medium 9-metre buses deployed through public private partnerships in Colombo Municipal area after selection of vendor/OEM through a competitive tender process as per UN procurement rules | Outcome 4. Private sector bus operators engage in low carbon public transport through financial incentive package for electric buses by end of the project | HDV-23-003/4.1 | HDV-23-003/4.1 5 small/medium 9-metre buses deployed through public private partnerships in Colombo Municipal area after selection of vendor/OEM through a competitive tender process as per UN procurement rules | Output | HDV-23-003/4. Private sector bus operators engage in low carbon public transport through financial incentive package for electric buses by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 4 | Private sector bus operators engage in low carbon public transport through financial incentive package for electric buses by end of the project | Setting up and operationalising an attractive financing mechanism for the actual deployment of 5 electric buses in Colombo city as a pilot, resulting in rapid deployment of more number of electric buses by both public and private sector operators. Estimated completion date: EoP | Number of SLCP mitigation tools, technologies, or practices adopted | 5 | 5 electric buses deployed in Colombo city | 4. Private sector bus operators engage in low carbon public transport through financial incentive package for electric buses by end of the project | Outcome 4. Private sector bus operators engage in low carbon public transport through financial incentive package for electric buses by end of the project | HDV-23-003/4. | HDV-23-003/4. Private sector bus operators engage in low carbon public transport through financial incentive package for electric buses by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
4.1.1Technical assistance to setup a mechanism for channelling of enhanced grants as capital subsidy scheme | Travel | 4.1.1-2 | DSA for national consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 20 | Days | 122 | 2440 | 0 | 2440 | 0 | Yes. | 4/1/2001 | Expenditure 4.1.1-2 DSA for national consultant | Activity 4.1.1Technical assistance to setup a mechanism for channelling of enhanced grants as capital subsidy scheme | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/4.1.1-2 | HDV-23-003/4.1.1-2 DSA for national consultant | HDV-23-003/4.1.1Technical assistance to setup a mechanism for channelling of enhanced grants as capital subsidy scheme | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 4.1 5 small/medium 9-metre buses deployed through public private partnerships in Colombo Municipal area after selection of vendor/OEM through a competitive tender process as per UN procurement rules | 4.1.1 | 4.1.1Technical assistance to setup a mechanism for channelling of enhanced grants as capital subsidy scheme | Five electric buses on public transport routes within Colombo city are procured and deployed with support from capital subsidy instituted in the previous activity. | Policy, project, or tool design | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | null | 6/1/2025 | 11/30/2025 | Inventory | null | null | null | 4.1 | Activity 4.1.1Technical assistance to setup a mechanism for channelling of enhanced grants as capital subsidy scheme | Output 4.1 5 small/medium 9-metre buses deployed through public private partnerships in Colombo Municipal area after selection of vendor/OEM through a competitive tender process as per UN procurement rules | 4.1.1Technical assistance to setup a mechanism for channelling of enhanced grants as capital subsidy scheme | HDV-23-003/4.1.1 | HDV-23-003/4.1.1Technical assistance to setup a mechanism for channelling of enhanced grants as capital subsidy scheme | HDV-23-003/4.1 5 small/medium 9-metre buses deployed through public private partnerships in Colombo Municipal area after selection of vendor/OEM through a competitive tender process as per UN procurement rules | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 4.1 | 5 small/medium 9-metre buses deployed through public private partnerships in Colombo Municipal area after selection of vendor/OEM through a competitive tender process as per UN procurement rules | An informative webinar will be conducted to convey the project's objectives, approach, outcomes achieved and learnings to all relevant participants. | 4. Private sector bus operators engage in low carbon public transport through financial incentive package for electric buses by end of the project | Number of tools, equipment, or technologies installed | 5 | Electric buses | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | null | To communicate to wider audiences about such a project being completed in Sri Lanka, which has enabled introduction of electric buses and helped the country transition towards low-carbon transport. This will strengthen the knowledge base on E bus deployment. | Meeting report, Participant list with gender breakdown, Photo or video, Meeting report, Participant list with gender breakdown, Photo or video, Meeting report, Participant list with gender breakdown, Photo or video, Meeting report, Participant list with gender breakdown, Photo or video | null | 5/15/2026 | Webinar material reviewed and approved by CCAC; webinar attended by CCAC | 4.1 5 small/medium 9-metre buses deployed through public private partnerships in Colombo Municipal area after selection of vendor/OEM through a competitive tender process as per UN procurement rules | Output 4.1 5 small/medium 9-metre buses deployed through public private partnerships in Colombo Municipal area after selection of vendor/OEM through a competitive tender process as per UN procurement rules | Outcome 4. Private sector bus operators engage in low carbon public transport through financial incentive package for electric buses by end of the project | HDV-23-003/4.1 | HDV-23-003/4.1 5 small/medium 9-metre buses deployed through public private partnerships in Colombo Municipal area after selection of vendor/OEM through a competitive tender process as per UN procurement rules | Output | HDV-23-003/4. Private sector bus operators engage in low carbon public transport through financial incentive package for electric buses by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 4 | Private sector bus operators engage in low carbon public transport through financial incentive package for electric buses by end of the project | Setting up and operationalising an attractive financing mechanism for the actual deployment of 5 electric buses in Colombo city as a pilot, resulting in rapid deployment of more number of electric buses by both public and private sector operators. Estimated completion date: EoP | Number of SLCP mitigation tools, technologies, or practices adopted | 5 | 5 electric buses deployed in Colombo city | 4. Private sector bus operators engage in low carbon public transport through financial incentive package for electric buses by end of the project | Outcome 4. Private sector bus operators engage in low carbon public transport through financial incentive package for electric buses by end of the project | HDV-23-003/4. | HDV-23-003/4. Private sector bus operators engage in low carbon public transport through financial incentive package for electric buses by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
4.1.2Five electric buses on public transport routes are procured and deployed with support from enhanced capital subsidy scheme and leased to public/private bus operator | Equipment Vehicles and Furniture | 4.1.2-1 | Procurement of Electric Buses | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 5 | Electric buses | 45000 | 225000 | 0 | 225000 | 0 | Yes. | 4/1/2002 | Expenditure 4.1.2-1 Procurement of Electric Buses | Activity 4.1.2Five electric buses on public transport routes are procured and deployed with support from enhanced capital subsidy scheme and leased to public/private bus operator | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/4.1.2-1 | HDV-23-003/4.1.2-1 Procurement of Electric Buses | HDV-23-003/4.1.2Five electric buses on public transport routes are procured and deployed with support from enhanced capital subsidy scheme and leased to public/private bus operator | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 4.1 5 small/medium 9-metre buses deployed through public private partnerships in Colombo Municipal area after selection of vendor/OEM through a competitive tender process as per UN procurement rules | 4.1.2 | 4.1.2Five electric buses on public transport routes are procured and deployed with support from enhanced capital subsidy scheme and leased to public/private bus operator | Webinar materials will be developed and delivered to all project stakeholders and CCAC | Other | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | null | 4/1/2026 | 5/15/2026 | Meeting report | null | null | null | 4.1 | Activity 4.1.2Five electric buses on public transport routes are procured and deployed with support from enhanced capital subsidy scheme and leased to public/private bus operator | Output 4.1 5 small/medium 9-metre buses deployed through public private partnerships in Colombo Municipal area after selection of vendor/OEM through a competitive tender process as per UN procurement rules | 4.1.2Five electric buses on public transport routes are procured and deployed with support from enhanced capital subsidy scheme and leased to public/private bus operator | HDV-23-003/4.1.2 | HDV-23-003/4.1.2Five electric buses on public transport routes are procured and deployed with support from enhanced capital subsidy scheme and leased to public/private bus operator | HDV-23-003/4.1 5 small/medium 9-metre buses deployed through public private partnerships in Colombo Municipal area after selection of vendor/OEM through a competitive tender process as per UN procurement rules | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 4.1 | 5 small/medium 9-metre buses deployed through public private partnerships in Colombo Municipal area after selection of vendor/OEM through a competitive tender process as per UN procurement rules | An informative webinar will be conducted to convey the project's objectives, approach, outcomes achieved and learnings to all relevant participants. | 4. Private sector bus operators engage in low carbon public transport through financial incentive package for electric buses by end of the project | Number of tools, equipment, or technologies installed | 5 | Electric buses | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | null | To communicate to wider audiences about such a project being completed in Sri Lanka, which has enabled introduction of electric buses and helped the country transition towards low-carbon transport. This will strengthen the knowledge base on E bus deployment. | Meeting report, Participant list with gender breakdown, Photo or video, Meeting report, Participant list with gender breakdown, Photo or video, Meeting report, Participant list with gender breakdown, Photo or video, Meeting report, Participant list with gender breakdown, Photo or video | null | 5/15/2026 | Webinar material reviewed and approved by CCAC; webinar attended by CCAC | 4.1 5 small/medium 9-metre buses deployed through public private partnerships in Colombo Municipal area after selection of vendor/OEM through a competitive tender process as per UN procurement rules | Output 4.1 5 small/medium 9-metre buses deployed through public private partnerships in Colombo Municipal area after selection of vendor/OEM through a competitive tender process as per UN procurement rules | Outcome 4. Private sector bus operators engage in low carbon public transport through financial incentive package for electric buses by end of the project | HDV-23-003/4.1 | HDV-23-003/4.1 5 small/medium 9-metre buses deployed through public private partnerships in Colombo Municipal area after selection of vendor/OEM through a competitive tender process as per UN procurement rules | Output | HDV-23-003/4. Private sector bus operators engage in low carbon public transport through financial incentive package for electric buses by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 4 | Private sector bus operators engage in low carbon public transport through financial incentive package for electric buses by end of the project | Setting up and operationalising an attractive financing mechanism for the actual deployment of 5 electric buses in Colombo city as a pilot, resulting in rapid deployment of more number of electric buses by both public and private sector operators. Estimated completion date: EoP | Number of SLCP mitigation tools, technologies, or practices adopted | 5 | 5 electric buses deployed in Colombo city | 4. Private sector bus operators engage in low carbon public transport through financial incentive package for electric buses by end of the project | Outcome 4. Private sector bus operators engage in low carbon public transport through financial incentive package for electric buses by end of the project | HDV-23-003/4. | HDV-23-003/4. Private sector bus operators engage in low carbon public transport through financial incentive package for electric buses by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
5.1.1 A 45- to 60-minute webinar about the project approach and outcomes developed and delivered to CCAC partners and project stakeholders | Staff and Other Personnel Costs | 5.1.1-1 | National consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 15 | Days | 200 | 3000 | 0 | 0 | 3000 | Yes. | 5/1/2001 | Expenditure 5.1.1-1 National consultant | Activity 5.1.1 A 45- to 60-minute webinar about the project approach and outcomes developed and delivered to CCAC partners and project stakeholders | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/5.1.1-1 | HDV-23-003/5.1.1-1 National consultant | HDV-23-003/5.1.1 A 45- to 60-minute webinar about the project approach and outcomes developed and delivered to CCAC partners and project stakeholders | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 5.1 A 45- to 60-minute webinar about the project approach and outcomes delivered to CCAC partners and project stakeholders no later than the project end date | 5.1.1 | 5.1.1 A 45- to 60-minute webinar about the project approach and outcomes developed and delivered to CCAC partners and project stakeholders | A case-study will be developed on project objectives, outcomes achieved, learnings and guidance for future scale-up | Producing and distributing communications materials | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | null | 4/1/2026 | 5/15/2026 | Research or study | null | null | null | 5.1 | Activity 5.1.1 A 45- to 60-minute webinar about the project approach and outcomes developed and delivered to CCAC partners and project stakeholders | Output 5.1 A 45- to 60-minute webinar about the project approach and outcomes delivered to CCAC partners and project stakeholders no later than the project end date | 5.1.1 A 45- to 60-minute webinar about the project approach and outcomes developed and delivered to CCAC partners and project stakeholders | HDV-23-003/5.1.1 | HDV-23-003/5.1.1 A 45- to 60-minute webinar about the project approach and outcomes developed and delivered to CCAC partners and project stakeholders | HDV-23-003/5.1 A 45- to 60-minute webinar about the project approach and outcomes delivered to CCAC partners and project stakeholders no later than the project end date | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 5.1 | A 45- to 60-minute webinar about the project approach and outcomes delivered to CCAC partners and project stakeholders no later than the project end date | A case study on the project experience will be produced to help guide future scale-up and active involvement of private sector. | 5. Increased knowledge and awareness about low carbon transport including SLCPs among all stakeholders including general public by end of the project | Number of public events, webinars, or side events hosted | 1 | Number of webinars held | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | null | To help guide future scale-up and replication of business models for other types of electric vehicles for transport such as three-wheelers, and potential participation and funding from DFIs and private sector alike. | Research or study, Research or study | null | 5/15/2026 | Case study reviewed and approved by CCAC | 5.1 A 45- to 60-minute webinar about the project approach and outcomes delivered to CCAC partners and project stakeholders no later than the project end date | Output 5.1 A 45- to 60-minute webinar about the project approach and outcomes delivered to CCAC partners and project stakeholders no later than the project end date | Outcome 5. Increased knowledge and awareness about low carbon transport including SLCPs among all stakeholders including general public by end of the project | HDV-23-003/5.1 | HDV-23-003/5.1 A 45- to 60-minute webinar about the project approach and outcomes delivered to CCAC partners and project stakeholders no later than the project end date | Output | HDV-23-003/5. Increased knowledge and awareness about low carbon transport including SLCPs among all stakeholders including general public by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 5 | Increased knowledge and awareness about low carbon transport including SLCPs among all stakeholders including general public by end of the project | Setting up tracking, monitoring and reporting systems for appropriate implementation of project's activities and calculating emissions mitigation versus the potential mentioned; in addition creating two external communications products to deliver via webinar or as guidelines regarding the project's outcomes, achievements and learnings, not only to CCAC and project stakeholders but also in other relevant public forums to help scale up such projects in the future. Estimated completion date: EoP | Number of monitoring, reporting, and verification (MRV) systems developed or updated that include SLCPs | 4 | 2 external communications products created and distributed, 2 monitoring reports/systems created | 5. Increased knowledge and awareness about low carbon transport including SLCPs among all stakeholders including general public by end of the project | Outcome 5. Increased knowledge and awareness about low carbon transport including SLCPs among all stakeholders including general public by end of the project | HDV-23-003/5. | HDV-23-003/5. Increased knowledge and awareness about low carbon transport including SLCPs among all stakeholders including general public by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
5.2.1 A 5- to 10-page case study to facilitate scale up of project's activities | Staff and Other Personnel Costs | 5.2.1-1 | National consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 15 | Days | 200 | 3000 | 0 | 0 | 3000 | Yes. | 5/2/2001 | Expenditure 5.2.1-1 National consultant | Activity 5.2.1 A 5- to 10-page case study to facilitate scale up of project's activities | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/5.2.1-1 | HDV-23-003/5.2.1-1 National consultant | HDV-23-003/5.2.1 A 5- to 10-page case study to facilitate scale up of project's activities | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 5.2 A 5- to 10-page case study or guidance document to support the replication or scale up of the project activities and/or results for potential public and private sector operators/stakeholders | 5.2.1 | 5.2.1 A 5- to 10-page case study to facilitate scale up of project's activities | A report tracking GHG emissions reductions will be instituted that will also help Sri Lankan government track its emissions reductions against its NDC targets. | Producing and distributing communications materials | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Environment | 6/1/2025 | 3/31/2026 | Tool | null | null | null | 5.2 | Activity 5.2.1 A 5- to 10-page case study to facilitate scale up of project's activities | Output 5.2 A 5- to 10-page case study or guidance document to support the replication or scale up of the project activities and/or results for potential public and private sector operators/stakeholders | 5.2.1 A 5- to 10-page case study to facilitate scale up of project's activities | HDV-23-003/5.2.1 | HDV-23-003/5.2.1 A 5- to 10-page case study to facilitate scale up of project's activities | HDV-23-003/5.2 A 5- to 10-page case study or guidance document to support the replication or scale up of the project activities and/or results for potential public and private sector operators/stakeholders | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 5.2 | A 5- to 10-page case study or guidance document to support the replication or scale up of the project activities and/or results for potential public and private sector operators/stakeholders | A GHG emission reduction tracking system introduced by the project will produce a report on GHG emissions reduced , after deployment of five electric buses under this project during project period and after, to compare if mitigation potential is achieved for the reporting purposes of the government of Sri Lanka | 5. Increased knowledge and awareness about low carbon transport including SLCPs among all stakeholders including general public by end of the project | Number of SLCP knowledge resources or tools produced | 1 | Document | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Environment | To track GHG emission reduction against estimated mitigation potential and help Ministry of Environment develop tracking system/document for reductions against the country's NDC targets. | Tool, Tool, Inventory, Research or study | null | 5/31/2026 | Mitigation report reviewed and approved by CCAC | 5.2 A 5- to 10-page case study or guidance document to support the replication or scale up of the project activities and/or results for potential public and private sector operators/stakeholders | Output 5.2 A 5- to 10-page case study or guidance document to support the replication or scale up of the project activities and/or results for potential public and private sector operators/stakeholders | Outcome 5. Increased knowledge and awareness about low carbon transport including SLCPs among all stakeholders including general public by end of the project | HDV-23-003/5.2 | HDV-23-003/5.2 A 5- to 10-page case study or guidance document to support the replication or scale up of the project activities and/or results for potential public and private sector operators/stakeholders | Output | HDV-23-003/5. Increased knowledge and awareness about low carbon transport including SLCPs among all stakeholders including general public by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 5 | Increased knowledge and awareness about low carbon transport including SLCPs among all stakeholders including general public by end of the project | Setting up tracking, monitoring and reporting systems for appropriate implementation of project's activities and calculating emissions mitigation versus the potential mentioned; in addition creating two external communications products to deliver via webinar or as guidelines regarding the project's outcomes, achievements and learnings, not only to CCAC and project stakeholders but also in other relevant public forums to help scale up such projects in the future. Estimated completion date: EoP | Number of monitoring, reporting, and verification (MRV) systems developed or updated that include SLCPs | 4 | 2 external communications products created and distributed, 2 monitoring reports/systems created | 5. Increased knowledge and awareness about low carbon transport including SLCPs among all stakeholders including general public by end of the project | Outcome 5. Increased knowledge and awareness about low carbon transport including SLCPs among all stakeholders including general public by end of the project | HDV-23-003/5. | HDV-23-003/5. Increased knowledge and awareness about low carbon transport including SLCPs among all stakeholders including general public by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
5.3.1 A report/system tracking actual emission reduction from deployment of 5 e-buses against mitigation potential | Staff and Other Personnel Costs | 5.3.1-1 | National consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 30 | Days | 200 | 6000 | 0 | 6000 | 0 | Yes. | 5/3/2001 | Expenditure 5.3.1-1 National consultant | Activity 5.3.1 A report/system tracking actual emission reduction from deployment of 5 e-buses against mitigation potential | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/5.3.1-1 | HDV-23-003/5.3.1-1 National consultant | HDV-23-003/5.3.1 A report/system tracking actual emission reduction from deployment of 5 e-buses against mitigation potential | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 5.3 A report tracking mitigation potential and actual emission reduction during and immediately after project period by the deployment of 5 electric buses, for Ministry of Transport and Highways /Ministry of Environment for NDC reporting | 5.3.1 | 5.3.1 A report/system tracking actual emission reduction from deployment of 5 e-buses against mitigation potential | A monitoring, reporting and verification system is setup to track progress of project' activities and outcomes achieved are in line with its objectives | Research, data collection, and/or report writing | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | null | 4/1/2024 | 5/31/2026 | Tool | null | null | null | 5.3 | Activity 5.3.1 A report/system tracking actual emission reduction from deployment of 5 e-buses against mitigation potential | Output 5.3 A report tracking mitigation potential and actual emission reduction during and immediately after project period by the deployment of 5 electric buses, for Ministry of Transport and Highways /Ministry of Environment for NDC reporting | 5.3.1 A report/system tracking actual emission reduction from deployment of 5 e-buses against mitigation potential | HDV-23-003/5.3.1 | HDV-23-003/5.3.1 A report/system tracking actual emission reduction from deployment of 5 e-buses against mitigation potential | HDV-23-003/5.3 A report tracking mitigation potential and actual emission reduction during and immediately after project period by the deployment of 5 electric buses, for Ministry of Transport and Highways /Ministry of Environment for NDC reporting | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 5.3 | A report tracking mitigation potential and actual emission reduction during and immediately after project period by the deployment of 5 electric buses, for Ministry of Transport and Highways /Ministry of Environment for NDC reporting | A project monitoring, reporting and verification system will be developed to track project progress against objectives and update the Project Board on the same during board meetings. | 5. Increased knowledge and awareness about low carbon transport including SLCPs among all stakeholders including general public by end of the project | Number of SLCP assessments, emissions inventories, and other emissions datasets produced | 1 | Report | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | null | To help track implementation of project's activities against estimated timelines, budgets, outputs delivered and outcomes achieved for successful completion of the project. | Tool, Tool, Research or study | null | 5/31/2026 | Monitoring report reviewed and approved by CCAC | 5.3 A report tracking mitigation potential and actual emission reduction during and immediately after project period by the deployment of 5 electric buses, for Ministry of Transport and Highways /Ministry of Environment for NDC reporting | Output 5.3 A report tracking mitigation potential and actual emission reduction during and immediately after project period by the deployment of 5 electric buses, for Ministry of Transport and Highways /Ministry of Environment for NDC reporting | Outcome 5. Increased knowledge and awareness about low carbon transport including SLCPs among all stakeholders including general public by end of the project | HDV-23-003/5.3 | HDV-23-003/5.3 A report tracking mitigation potential and actual emission reduction during and immediately after project period by the deployment of 5 electric buses, for Ministry of Transport and Highways /Ministry of Environment for NDC reporting | Output | HDV-23-003/5. Increased knowledge and awareness about low carbon transport including SLCPs among all stakeholders including general public by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 5 | Increased knowledge and awareness about low carbon transport including SLCPs among all stakeholders including general public by end of the project | Setting up tracking, monitoring and reporting systems for appropriate implementation of project's activities and calculating emissions mitigation versus the potential mentioned; in addition creating two external communications products to deliver via webinar or as guidelines regarding the project's outcomes, achievements and learnings, not only to CCAC and project stakeholders but also in other relevant public forums to help scale up such projects in the future. Estimated completion date: EoP | Number of monitoring, reporting, and verification (MRV) systems developed or updated that include SLCPs | 4 | 2 external communications products created and distributed, 2 monitoring reports/systems created | 5. Increased knowledge and awareness about low carbon transport including SLCPs among all stakeholders including general public by end of the project | Outcome 5. Increased knowledge and awareness about low carbon transport including SLCPs among all stakeholders including general public by end of the project | HDV-23-003/5. | HDV-23-003/5. Increased knowledge and awareness about low carbon transport including SLCPs among all stakeholders including general public by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
5.4.1 An MRV system setup and managed by PMU to track project progress and report to the Project Board and CCAC | Staff and Other Personnel Costs | 5.4.1-1 | National consultant | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 30 | Days | 200 | 6000 | 6000 | 0 | 0 | Yes. | 5/4/2001 | Expenditure 5.4.1-1 National consultant | Activity 5.4.1 An MRV system setup and managed by PMU to track project progress and report to the Project Board and CCAC | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/5.4.1-1 | HDV-23-003/5.4.1-1 National consultant | HDV-23-003/5.4.1 An MRV system setup and managed by PMU to track project progress and report to the Project Board and CCAC | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 5.4 An MRV system tracking project implementation activities and outputs for Project Board | 5.4.1 | 5.4.1 An MRV system setup and managed by PMU to track project progress and report to the Project Board and CCAC | null | Research, data collection, and/or report writing | null | null | null | null | null | null | null | null | null | null | null | null | 5.4 | Activity 5.4.1 An MRV system setup and managed by PMU to track project progress and report to the Project Board and CCAC | Output 5.4 An MRV system tracking project implementation activities and outputs for Project Board | 5.4.1 An MRV system setup and managed by PMU to track project progress and report to the Project Board and CCAC | HDV-23-003/5.4.1 | HDV-23-003/5.4.1 An MRV system setup and managed by PMU to track project progress and report to the Project Board and CCAC | HDV-23-003/5.4 An MRV system tracking project implementation activities and outputs for Project Board | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 5.4 | An MRV system tracking project implementation activities and outputs for Project Board | null | 5. Increased knowledge and awareness about low carbon transport including SLCPs among all stakeholders including general public by end of the project | Number of SLCP knowledge resources or tools produced | 1 | Report | null | null | null | null | null | null | null | null | 5.4 An MRV system tracking project implementation activities and outputs for Project Board | Output 5.4 An MRV system tracking project implementation activities and outputs for Project Board | Outcome 5. Increased knowledge and awareness about low carbon transport including SLCPs among all stakeholders including general public by end of the project | HDV-23-003/5.4 | HDV-23-003/5.4 An MRV system tracking project implementation activities and outputs for Project Board | Output | HDV-23-003/5. Increased knowledge and awareness about low carbon transport including SLCPs among all stakeholders including general public by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 5 | Increased knowledge and awareness about low carbon transport including SLCPs among all stakeholders including general public by end of the project | Setting up tracking, monitoring and reporting systems for appropriate implementation of project's activities and calculating emissions mitigation versus the potential mentioned; in addition creating two external communications products to deliver via webinar or as guidelines regarding the project's outcomes, achievements and learnings, not only to CCAC and project stakeholders but also in other relevant public forums to help scale up such projects in the future. Estimated completion date: EoP | Number of monitoring, reporting, and verification (MRV) systems developed or updated that include SLCPs | 4 | 2 external communications products created and distributed, 2 monitoring reports/systems created | 5. Increased knowledge and awareness about low carbon transport including SLCPs among all stakeholders including general public by end of the project | Outcome 5. Increased knowledge and awareness about low carbon transport including SLCPs among all stakeholders including general public by end of the project | HDV-23-003/5. | HDV-23-003/5. Increased knowledge and awareness about low carbon transport including SLCPs among all stakeholders including general public by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | null | null
1.6.1 Project Support | UN-PSC | 1.6.1-3 | GMS and UN Coordinator Levy | United Nations Development Programme (UNDP) - Sri Lanka Country Office | null | CCAC | 1 | Levies | 58075 | 58075 | 58075 | 0 | 0 | Yes. | 1/6/2001 | Expenditure 1.6.1-3 GMS and UN Coordinator Levy | Activity 1.6.1 Project Support | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.6.1-3 | HDV-23-003/1.6.1-3 GMS and UN Coordinator Levy | HDV-23-003/1.6.1 Project Support | Expenditure | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.6 Programme Support | 1.6.1 | 1.6.1 Project Support | Viability assessment - technical, operational, financial - is completed to identify locations, EV charging technology standards (SAE Combined Charging System (CCS), CHAdeMO, Type 2 charging, Tesla Superchargers etc.) and suitable entities to own and operate these charging stations, together with necessary regulatory feasibility is completed and approved. (Typically bus charging units are sold together with the electric buses by Original Equipment Manufacturers (OEMs). However, for future scale-up, deploying solar powered charging stations are envisaged, and thus this activity becomes essential.) | Other | null | null | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Sri Lanka | Ministry of Power and Energy, Public Utilities Commission of Sri Lanka, Ceylon Electricity Board | 9/1/2024 | 2/28/2025 | Research or study | null | null | null | 1.6 | Activity 1.6.1 Project Support | Output 1.6 Programme Support | 1.6.1 Project Support | HDV-23-003/1.6.1 | HDV-23-003/1.6.1 Project Support | HDV-23-003/1.6 Programme Support | Activity | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1.6 | Programme Support | Viability assessments on operability of electric buses on various aspects is conducted; analytical report on improved safety, security and accessibility aspects of electric buses to make it more accommodative for women, children and physically challenged persons is also conducted | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | 0 | 0 | 0 | United Nations Development Programme (UNDP) - Sri Lanka Country Office | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, Public Utilities Commission of Sri Lanka, Ceylon Electricity Board | This will help government stakeholders understand and plan for actual deployment of electric buses as a mode of reliable, safe, comfortable and viable public transport. It will provide inputs to the development of an enabling environment to introduce E Buses for public transport in Sri Lanka | Research or study | null | 2/28/2025 | Studies/reports are reviewed and approved by CCAC | 1.6 Programme Support | Output 1.6 Programme Support | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1.6 | HDV-23-003/1.6 Programme Support | Output | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | 1 | Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | By providing necessary technical assistance to develop a Sustainable Transport Plan and formulating relevant regulatory policy for using electric vehicles, specifically electric buses for public transport in Sri Lanka, including training for government stakholders and various feasibility studies for actual deployment of electric buses. Estimated completion date: 18 months from project start date | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 3 | 1 national policy/plan/ regulations drafted or updated.1 guidelines and 1 assessment completed | 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | HDV-23-003/1. | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Outcome | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003 | Vehicles & Engines | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## INT-Pivots (hidden)
|  |  | NARRATIVE REPORT + DASHBOARD | [13 empty] | OUTPUTS | [20 empty] | Expenditure (uncheck all but expenditure) | [10 empty] | Project title | OUTPUTS | [13 empty] | Activities
|  |  | Agreement filter | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | [12 empty] | Agreement filter | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | [12 empty] | OUTCOMES REPORTING | [6 empty] | Agreement filter | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | [10 empty] | Agreement filter | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | [12 empty] | Agreement filter | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035)
Selected agreement |  |  | Level | (Multiple Items) | [12 empty] | Level | Output | [19 empty] | Level | Expenditure | [10 empty] | Level | Output | [12 empty] | Level | Activity
Agreement | Agreement number | Count of Implementer | Unique code | Component | Indicator | Target | Unit | Date | Description | Acceptance criteria | Project | Agreement | Sector | Beneficiaries | Other beneficiaries | Delivery type | Unique code | Component | Indicator | Target | Unit | Date | Description | Acceptance criteria | Project | Agreement | Sector | Beneficiaries | Other beneficiaries | Delivery type | Component | Indicator | Target | Unit | Unique code | Project | Sector | Expenditure related activity | Indicator | Budget SOURCE OF FUNDING | Project | Sector | Agreement | Unique code | Sum of TOTAL COST | Sum of YEAR 1 COST ($US) | Sum of YEAR 2 COST ($US) | Sum of YEAR 3 COST ($US) | Project | Unique code | Component | Indicator | Target | Unit | Date | Description | Acceptance criteria | Project | Agreement | Sector | Beneficiaries | Other beneficiaries | Delivery type | Unique code | Component | Indicator | Target | Unit | Date | Description | Acceptance criteria | Project | Agreement | Sector | Beneficiaries | Other beneficiaries | Delivery type
United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | 24-035 | 108 | HDV-23-003/1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Output 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Number of plans, policies, laws, or regulations drafted or updated | 1 | Planning document | 2024-12-31 | A long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document would inform the design of policy, regulatory and fiscal/financial incentive schemes/programs for the Government of Sri Lanka to support the implementation of electric public transport to initiate low carbon transport development in Sri Lanka through a participatory and consultative process | Plan approved and adopted by Government of Sri Lanka | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Policy, regulation or other guideline | HDV-23-003/1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Output 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Number of plans, policies, laws, or regulations drafted or updated | 1 | Planning document | 2024-12-31 | A long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document would inform the design of policy, regulatory and fiscal/financial incentive schemes/programs for the Government of Sri Lanka to support the implementation of electric public transport to initiate low carbon transport development in Sri Lanka through a participatory and consultative process | Plan approved and adopted by Government of Sri Lanka | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Policy, regulation or other guideline | Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 3 | 1 national policy/plan/ regulations drafted or updated.1 guidelines and 1 assessment completed | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | Activity 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | Staff and Other Personnel Costs | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.2.1-1 International consultant | 25000 | 25000 | 0 | 0 | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | HDV-23-003/1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Output 1.2 Designing and developing a long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document that provides a policy and regulatory framework for electric bus transport | Number of plans, policies, laws, or regulations drafted or updated | 1 | Planning document | 2024-12-31 | A long-term comprehensive 'Sustainable Low-Carbon Transport Planning' document would inform the design of policy, regulatory and fiscal/financial incentive schemes/programs for the Government of Sri Lanka to support the implementation of electric public transport to initiate low carbon transport development in Sri Lanka through a participatory and consultative process | Plan approved and adopted by Government of Sri Lanka | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Policy, regulation or other guideline | HDV-23-003/1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | Activity 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | Policy, project, or tool design | null | null | (blank) | A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-carbon Transport Masterplan' document prepared for Sri Lanka, that includes a multi-modal transport plan for Sri Lanka detailing the role of different modes of transport - rail, public transport buses, private buses, private passenger vehicles, commercial vehicles, bicycles, pedestrian pathways and others based on the principles of low-carbon, sustainable transport. The Masterplan document would serve as a guidance for all future transport sector programs, activities and investments in Sri Lanka, including the low-carbon electric public bus transport deployment activity proposed under this CCAC project. | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Policy, regulation or other guideline
|  |  | HDV-23-003/1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | Activity 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | Policy, project, or tool design | null | null | (blank) | A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-carbon Transport Masterplan' document prepared for Sri Lanka, that includes a multi-modal transport plan for Sri Lanka detailing the role of different modes of transport - rail, public transport buses, private buses, private passenger vehicles, commercial vehicles, bicycles, pedestrian pathways and others based on the principles of low-carbon, sustainable transport. The Masterplan document would serve as a guidance for all future transport sector programs, activities and investments in Sri Lanka, including the low-carbon electric public bus transport deployment activity proposed under this CCAC project. | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Policy, regulation or other guideline | HDV-23-003/1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | Output 1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | Number of plans, policies, laws, or regulations drafted or updated | 1 | Policy and regulatory framework | 2025-06-30 | A comprehensive policy on operationalising electric buses for public transport in Sri Lanka developed through necessary assessments will be the first step towards deploying low-carbon transport for use in the country. This includes policy and regulatory framework on defining electric buses, technical and safety features of such buses to be procured, their operation mechanism including charging, end of life use, battery and vehicle disposal etc | Policy and regulatory framework approved and adopted by Government of Sri Lanka | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Policy, regulation or other guideline, Policy, regulation or other guideline | Outcome 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Number of government entities with a demonstrated improved capacity for SLCP action | 6 | Government entities with improved capacity | HDV-23-003/2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | Activity 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | Staff and Other Personnel Costs | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.2.1-2 National consultant | 12000 | 12000 | 0 | 0 |  | HDV-23-003/1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | Output 1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | Number of plans, policies, laws, or regulations drafted or updated | 1 | Policy and regulatory framework | 2025-06-30 | A comprehensive policy on operationalising electric buses for public transport in Sri Lanka developed through necessary assessments will be the first step towards deploying low-carbon transport for use in the country. This includes policy and regulatory framework on defining electric buses, technical and safety features of such buses to be procured, their operation mechanism including charging, end of life use, battery and vehicle disposal etc | Policy and regulatory framework approved and adopted by Government of Sri Lanka | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Policy, regulation or other guideline, Policy, regulation or other guideline | HDV-23-003/1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Activity 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Developing and/or delivering training | null | null | (blank) | Training modules developed and training programs that will build capacity of at least 20 trainees (30% of them being women) delivered on 'Long-term Sustainable Low-carbon Transport Planning' for government stakeholders (MoTH, MoP&E, NTC, WPRPTA, SLTB) and private stakeholders (bus operators, others as necessary); the training modules will include gender-specific, climate change adaptation and accessibility/inclusivity aspects as well. | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Participant list with gender breakdown
|  |  | HDV-23-003/1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Activity 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Developing and/or delivering training | null | null | (blank) | Training modules developed and training programs that will build capacity of at least 20 trainees (30% of them being women) delivered on 'Long-term Sustainable Low-carbon Transport Planning' for government stakeholders (MoTH, MoP&E, NTC, WPRPTA, SLTB) and private stakeholders (bus operators, others as necessary); the training modules will include gender-specific, climate change adaptation and accessibility/inclusivity aspects as well. | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Participant list with gender breakdown | HDV-23-003/1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Output 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Number of SLCP knowledge resources or tools produced | 3 | Studies/reports | 2024-11-30 | Impact studies, analytical reports on identification of gaps to implementing low-carbon transport and electric vehicles in Sri Lanka on various aspects as well as recommendations on future scale-up of such transport and electric vehicle deployment and disposal of ICE vehicles will be conducted under this output. | Studies/reports are reviewed and approved by CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Research or study | Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Number of non-government entities with a demonstrated improved capacity for SLCP action | 7 | 7 non-government entities with improved capacity | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | Activity 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | Travel | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.2.1-3 Travel fare | 500 | 500 | 0 | 0 |  | HDV-23-003/1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Output 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Number of SLCP knowledge resources or tools produced | 3 | Studies/reports | 2024-11-30 | Impact studies, analytical reports on identification of gaps to implementing low-carbon transport and electric vehicles in Sri Lanka on various aspects as well as recommendations on future scale-up of such transport and electric vehicle deployment and disposal of ICE vehicles will be conducted under this output. | Studies/reports are reviewed and approved by CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Research or study | HDV-23-003/1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | Activity 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | Policy, project, or tool design | null | null | (blank) | A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' will be developed together with the Ministry of Transport and Highways, NTC and WPRPTA. It will then be submitted for Government and Stakeholder feedback; Framework will be revised/updated based on feedback and final Framework approved and operationalized by the Government of Sri Lanka. | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Policy, regulation or other guideline
|  |  | HDV-23-003/1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | Output 1.3 Developing a comprehensive policy, regulatory and guidelines framework to enable e-bus deployment in Sri Lanka for public transport for the Ministry of Transport and Highways | Number of plans, policies, laws, or regulations drafted or updated | 1 | Policy and regulatory framework | 2025-06-30 | A comprehensive policy on operationalising electric buses for public transport in Sri Lanka developed through necessary assessments will be the first step towards deploying low-carbon transport for use in the country. This includes policy and regulatory framework on defining electric buses, technical and safety features of such buses to be procured, their operation mechanism including charging, end of life use, battery and vehicle disposal etc | Policy and regulatory framework approved and adopted by Government of Sri Lanka | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Policy, regulation or other guideline, Policy, regulation or other guideline | HDV-23-003/1.6 Programme Support | Output 1.6 Programme Support | 0 | 0 | 0 | 2025-02-28 | Viability assessments on operability of electric buses on various aspects is conducted; analytical report on improved safety, security and accessibility aspects of electric buses to make it more accommodative for women, children and physically challenged persons is also conducted | Studies/reports are reviewed and approved by CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, Public Utilities Commission of Sri Lanka, Ceylon Electricity Board | Research or study | Outcome 4. Private sector bus operators engage in low carbon public transport through financial incentive package for electric buses by end of the project | Number of SLCP mitigation tools, technologies, or practices adopted | 5 | 5 electric buses deployed in Colombo city | HDV-23-003/4. Private sector bus operators engage in low carbon public transport through financial incentive package for electric buses by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | Activity 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | Travel | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.2.1-4 DSA for international consultant | 3840 | 3840 | 0 | 0 |  | HDV-23-003/1.6 Programme Support | Output 1.6 Programme Support | 0 | 0 | 0 | 2025-02-28 | Viability assessments on operability of electric buses on various aspects is conducted; analytical report on improved safety, security and accessibility aspects of electric buses to make it more accommodative for women, children and physically challenged persons is also conducted | Studies/reports are reviewed and approved by CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, Public Utilities Commission of Sri Lanka, Ceylon Electricity Board | Research or study | HDV-23-003/1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | Activity 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | Research, data collection, and/or report writing | null | null | (blank) | An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved together with Public Utilities Commission of Sri Lanka (PUCSL) and Ceylon Electricity Board (CEB), under the guidance of Ministry of Power and Energy(MoP&E). | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Power and Energy, Public Utilities Commission of Sri Lanka, Ceylon Electricity Board | Research or study
|  |  | HDV-23-003/1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | Activity 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | Policy, project, or tool design | null | null | (blank) | A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' will be developed together with the Ministry of Transport and Highways, NTC and WPRPTA. It will then be submitted for Government and Stakeholder feedback; Framework will be revised/updated based on feedback and final Framework approved and operationalized by the Government of Sri Lanka. | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Policy, regulation or other guideline | HDV-23-003/2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Output 2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Number of SLCP knowledge resources or tools produced | 2 | Studies/reports | 2025-08-30 | Design and delivery of training programs for capacity building of government institutional stakeholders on various aspects of operationalising electric buses in Sri Lanka will be conducted under this output. | Attendance sheet and feedback from trainees shared with CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Private bus operators' association and private bus operators, drivers, workshop technicians, Finance House association, Insurance association, commercial banks, leasing and financing companies | Training materials, Participant list with gender breakdown, Training materials, Participant list with gender breakdown | Outcome 5. Increased knowledge and awareness about low carbon transport including SLCPs among all stakeholders including general public by end of the project | Number of monitoring, reporting, and verification (MRV) systems developed or updated that include SLCPs | 4 | 2 external communications products created and distributed, 2 monitoring reports/systems created | HDV-23-003/5. Increased knowledge and awareness about low carbon transport including SLCPs among all stakeholders including general public by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | Activity 1.2.1 A long-term, integrated comprehensive, gender-sensitive and inclusive 'Sustainable Low-Carbon Transport Planning' document prepared for Sri Lanka | Travel | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.2.1-5 DSA for national consultant | 1220 | 1220 | 0 | 0 |  | HDV-23-003/2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Output 2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Number of SLCP knowledge resources or tools produced | 2 | Studies/reports | 2025-08-30 | Design and delivery of training programs for capacity building of government institutional stakeholders on various aspects of operationalising electric buses in Sri Lanka will be conducted under this output. | Attendance sheet and feedback from trainees shared with CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Private bus operators' association and private bus operators, drivers, workshop technicians, Finance House association, Insurance association, commercial banks, leasing and financing companies | Training materials, Participant list with gender breakdown, Training materials, Participant list with gender breakdown | HDV-23-003/1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | Activity 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | Research, data collection, and/or report writing | null | null | (blank) | An analytical report on gaps in policies and regulatory framework, institutional, private and financial sector capacity/training needs and financial gap is completed and approved, with a focus on bridging this gap to ensure scaling up of EV integration into the transport sector in Sri Lanka | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Research or study
|  |  | HDV-23-003/1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Output 1.4 Feasibility studies and analysis that lead to scaling up of low-carbon transport in Sri Lanka, and recommendations for disposal of old vehicles for the Ministry of Transport and Highways and Ministry of Environment | Number of SLCP knowledge resources or tools produced | 3 | Studies/reports | 2024-11-30 | Impact studies, analytical reports on identification of gaps to implementing low-carbon transport and electric vehicles in Sri Lanka on various aspects as well as recommendations on future scale-up of such transport and electric vehicle deployment and disposal of ICE vehicles will be conducted under this output. | Studies/reports are reviewed and approved by CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Research or study | HDV-23-003/2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output 2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Number of person hours of training provided | 6720 | Person hours | 2025-11-30 | Design and delivery of training programs for capacity building of private sector stakeholders on technical features of electric buses, economic/financial viability of e-buses will be conducted under this output. | Attendance sheet and feedback from trainees shared with CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Training materials, Training materials, Participant list with gender breakdown, Training materials, Training materials, Participant list with gender breakdown | [7 empty] | Activity 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Staff and Other Personnel Costs | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.2.2-1 International consultant | 5000 | 5000 | 0 | 0 |  | HDV-23-003/2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output 2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Number of person hours of training provided | 6720 | Person hours | 2025-11-30 | Design and delivery of training programs for capacity building of private sector stakeholders on technical features of electric buses, economic/financial viability of e-buses will be conducted under this output. | Attendance sheet and feedback from trainees shared with CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Training materials, Training materials, Participant list with gender breakdown, Training materials, Training materials, Participant list with gender breakdown | HDV-23-003/1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | Activity 1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | Research, data collection, and/or report writing | null | null | (blank) | A report on recommendations and planning of disposal of old buses and vehicles if replaced with electric buses (vehicles) during future project scale-up | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Research or study
|  |  | HDV-23-003/1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | Activity 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | Research, data collection, and/or report writing | null | null | (blank) | An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved together with Public Utilities Commission of Sri Lanka (PUCSL) and Ceylon Electricity Board (CEB), under the guidance of Ministry of Power and Energy(MoP&E). | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Power and Energy, Public Utilities Commission of Sri Lanka, Ceylon Electricity Board | Research or study | HDV-23-003/3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Number of person hours of training provided | 9840 | Person hours | 2025-10-31 | Various targeted promotional events and public awareness campaigns on benefits of using low-carbon public transport in Sri Lanka will be held to gain public support for above transition | Campaign materials and photos shared with CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | Tool, Tool, Photo or video, Tool, Tool, Photo or video | [7 empty] | Activity 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Staff and Other Personnel Costs | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.2.2-2 National consultant | 4000 | 4000 | 0 | 0 |  | HDV-23-003/3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Number of person hours of training provided | 9840 | Person hours | 2025-10-31 | Various targeted promotional events and public awareness campaigns on benefits of using low-carbon public transport in Sri Lanka will be held to gain public support for above transition | Campaign materials and photos shared with CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | Tool, Tool, Photo or video, Tool, Tool, Photo or video | HDV-23-003/1.6.1 Project Support | Activity 1.6.1 Project Support | Other | null | null | (blank) | Viability assessment - technical, operational, financial - is completed to identify locations, EV charging technology standards (SAE Combined Charging System (CCS), CHAdeMO, Type 2 charging, Tesla Superchargers etc.) and suitable entities to own and operate these charging stations, together with necessary regulatory feasibility is completed and approved. (Typically bus charging units are sold together with the electric buses by Original Equipment Manufacturers (OEMs). However, for future scale-up, deploying solar powered charging stations are envisaged, and thus this activity becomes essential.) | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Power and Energy, Public Utilities Commission of Sri Lanka, Ceylon Electricity Board | Research or study
|  |  | HDV-23-003/1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | Activity 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | Research, data collection, and/or report writing | null | null | (blank) | An analytical report on gaps in policies and regulatory framework, institutional, private and financial sector capacity/training needs and financial gap is completed and approved, with a focus on bridging this gap to ensure scaling up of EV integration into the transport sector in Sri Lanka | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Research or study | HDV-23-003/3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Output 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Number of partnerships, associations, or campaigns launched to drive SLCP action | 35 | Campaigns | 2025-11-30 | Technical assistance provided to the government of Sri Lanka to setup and operationalise subsidy scheme to enable procurement and deployment of the first electric buses for public transport in Sri Lanka | Procurement documents reviewed and approved by CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Inventory, Funding proposal, Photo or video | [7 empty] | Activity 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Supplies Commodities and Materials | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.2.2-6 Printing materials, handouts, audio-visual material | 500 | 500 | 0 | 0 |  | HDV-23-003/3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Output 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Number of partnerships, associations, or campaigns launched to drive SLCP action | 35 | Campaigns | 2025-11-30 | Technical assistance provided to the government of Sri Lanka to setup and operationalise subsidy scheme to enable procurement and deployment of the first electric buses for public transport in Sri Lanka | Procurement documents reviewed and approved by CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Inventory, Funding proposal, Photo or video | HDV-23-003/2.1.1Viability assessment of EV charging stations is completed and approved | Activity 2.1.1Viability assessment of EV charging stations is completed and approved | Research, data collection, and/or report writing | null | null | (blank) | An Analytical report on safety, security, accessibility aspects of public transport buses in Sri Lanka, particularly from the perspective of women's safety and ease of accessibility of public transport buses for elderly/children/special needs commuters is completed | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Research or study
|  |  | HDV-23-003/1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | Activity 1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | Research, data collection, and/or report writing | null | null | (blank) | A report on recommendations and planning of disposal of old buses and vehicles if replaced with electric buses (vehicles) during future project scale-up | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Research or study | HDV-23-003/4.1 5 small/medium 9-metre buses deployed through public private partnerships in Colombo Municipal area after selection of vendor/OEM through a competitive tender process as per UN procurement rules | Output 4.1 5 small/medium 9-metre buses deployed through public private partnerships in Colombo Municipal area after selection of vendor/OEM through a competitive tender process as per UN procurement rules | Number of tools, equipment, or technologies installed | 5 | Electric buses | 2026-05-15 | An informative webinar will be conducted to convey the project's objectives, approach, outcomes achieved and learnings to all relevant participants. | Webinar material reviewed and approved by CCAC; webinar attended by CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | null | Meeting report, Participant list with gender breakdown, Photo or video, Meeting report, Participant list with gender breakdown, Photo or video, Meeting report, Participant list with gender breakdown, Photo or video, Meeting report, Participant list with gender breakdown, Photo or video | [7 empty] | Activity 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Travel | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.2.2-3 Travel fare | 500 | 500 | 0 | 0 |  | HDV-23-003/4.1 5 small/medium 9-metre buses deployed through public private partnerships in Colombo Municipal area after selection of vendor/OEM through a competitive tender process as per UN procurement rules | Output 4.1 5 small/medium 9-metre buses deployed through public private partnerships in Colombo Municipal area after selection of vendor/OEM through a competitive tender process as per UN procurement rules | Number of tools, equipment, or technologies installed | 5 | Electric buses | 2026-05-15 | An informative webinar will be conducted to convey the project's objectives, approach, outcomes achieved and learnings to all relevant participants. | Webinar material reviewed and approved by CCAC; webinar attended by CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | null | Meeting report, Participant list with gender breakdown, Photo or video, Meeting report, Participant list with gender breakdown, Photo or video, Meeting report, Participant list with gender breakdown, Photo or video, Meeting report, Participant list with gender breakdown, Photo or video | HDV-23-003/2.1.2An Analytical gender (including elderly, children, specific needs commuter) specific report on safety, security, accessibility aspects of public transport buses in Sri Lanka | Activity 2.1.2An Analytical gender (including elderly, children, specific needs commuter) specific report on safety, security, accessibility aspects of public transport buses in Sri Lanka | Research, data collection, and/or report writing | null | null | (blank) | Training programs, training at least 60 trainees (30% being women), designed and delivered for government institutional stakeholders (MoTH, MoPE, NTC, SLTB, WPRPTA, CMC) on techno-commercial (such as procurement, planning, performance evaluation, scheduling and charging infrastructure of electric bus systems), financial/economic and policy/regulatory (best practices etc.) frameworks for enabling electric bus deployment for public transport and associated bus charging stations in Sri Lanka; the training program needs to include gender-specific and accessibility/inclusivity aspects as well. | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Participant list with gender breakdown
|  |  | HDV-23-003/1.6 Programme Support | Output 1.6 Programme Support | 0 | 0 | 0 | 2025-02-28 | Viability assessments on operability of electric buses on various aspects is conducted; analytical report on improved safety, security and accessibility aspects of electric buses to make it more accommodative for women, children and physically challenged persons is also conducted | Studies/reports are reviewed and approved by CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, Public Utilities Commission of Sri Lanka, Ceylon Electricity Board | Research or study | HDV-23-003/5.1 A 45- to 60-minute webinar about the project approach and outcomes delivered to CCAC partners and project stakeholders no later than the project end date | Output 5.1 A 45- to 60-minute webinar about the project approach and outcomes delivered to CCAC partners and project stakeholders no later than the project end date | Number of public events, webinars, or side events hosted | 1 | Number of webinars held | 2026-05-15 | A case study on the project experience will be produced to help guide future scale-up and active involvement of private sector. | Case study reviewed and approved by CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | null | Research or study, Research or study | [7 empty] | Activity 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Travel | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.2.2-4 DSA for international consultant | 1344 | 1344 | 0 | 0 |  | HDV-23-003/5.1 A 45- to 60-minute webinar about the project approach and outcomes delivered to CCAC partners and project stakeholders no later than the project end date | Output 5.1 A 45- to 60-minute webinar about the project approach and outcomes delivered to CCAC partners and project stakeholders no later than the project end date | Number of public events, webinars, or side events hosted | 1 | Number of webinars held | 2026-05-15 | A case study on the project experience will be produced to help guide future scale-up and active involvement of private sector. | Case study reviewed and approved by CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | null | Research or study, Research or study | HDV-23-003/2.2.1Training programs designed and delivered for government institutional stakeholders | Activity 2.2.1Training programs designed and delivered for government institutional stakeholders | Developing and/or delivering training | null | null | (blank) | Training programs, training at least 30 trainees (50% being women), designed and delivered for commercial banks/financial institutions (loan officers and senior executives of banks/leasing and financing companies involved in or interested in lending to electric bus mobility sector) on techno-commercial, financial/economic and policy/regulatory frameworks for enabling electric bus deployment for public transport and associated bus charging stations in Sri Lanka; the training program needs to include gender-specific and accessibility/inclusivity aspects as well. | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Finance House association, Insurance association, commercial banks, leasing and financing companies | Participant list with gender breakdown
|  |  | HDV-23-003/1.6.1 Project Support | Activity 1.6.1 Project Support | Other | null | null | (blank) | Viability assessment - technical, operational, financial - is completed to identify locations, EV charging technology standards (SAE Combined Charging System (CCS), CHAdeMO, Type 2 charging, Tesla Superchargers etc.) and suitable entities to own and operate these charging stations, together with necessary regulatory feasibility is completed and approved. (Typically bus charging units are sold together with the electric buses by Original Equipment Manufacturers (OEMs). However, for future scale-up, deploying solar powered charging stations are envisaged, and thus this activity becomes essential.) | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Power and Energy, Public Utilities Commission of Sri Lanka, Ceylon Electricity Board | Research or study | HDV-23-003/5.2 A 5- to 10-page case study or guidance document to support the replication or scale up of the project activities and/or results for potential public and private sector operators/stakeholders | Output 5.2 A 5- to 10-page case study or guidance document to support the replication or scale up of the project activities and/or results for potential public and private sector operators/stakeholders | Number of SLCP knowledge resources or tools produced | 1 | Document | 2026-05-31 | A GHG emission reduction tracking system introduced by the project will produce a report on GHG emissions reduced , after deployment of five electric buses under this project during project period and after, to compare if mitigation potential is achieved for the reporting purposes of the government of Sri Lanka | Mitigation report reviewed and approved by CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Environment | Tool, Tool, Inventory, Research or study | [7 empty] | Activity 1.2.2 Training modules developed and training programs delivered on 'Long-term Sustainable Low-carbon Transport Planning' to government and private sector stakeholders | Travel | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.2.2-5 DSA for national consultant | 610 | 610 | 0 | 0 |  | HDV-23-003/5.2 A 5- to 10-page case study or guidance document to support the replication or scale up of the project activities and/or results for potential public and private sector operators/stakeholders | Output 5.2 A 5- to 10-page case study or guidance document to support the replication or scale up of the project activities and/or results for potential public and private sector operators/stakeholders | Number of SLCP knowledge resources or tools produced | 1 | Document | 2026-05-31 | A GHG emission reduction tracking system introduced by the project will produce a report on GHG emissions reduced , after deployment of five electric buses under this project during project period and after, to compare if mitigation potential is achieved for the reporting purposes of the government of Sri Lanka | Mitigation report reviewed and approved by CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Environment | Tool, Tool, Inventory, Research or study | HDV-23-003/3.1.1Training programs designed and delivered for commercial banks/financial institutions | Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Developing and/or delivering training | null | null | (blank) | Training programs, training at least 60 trainees (10% being women), designed and delivered to private bus operators, their bus drivers and workshop technicians on electric bus operational and financial feasibility (vs ICE buses), e-bus driving techniques, safety (including women's safety) and security aspects and maintenance, management of EV batteries/their scientific disposal. | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Private bus operators' association and private bus operators, drivers, workshop technicians | Participant list with gender breakdown
|  |  | HDV-23-003/2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Output 2.1 Technical, operational, financial, economic and regulatory analysis of electric bus mobility opportunity in Sri Lanka is completed | Number of SLCP knowledge resources or tools produced | 2 | Studies/reports | 2025-08-30 | Design and delivery of training programs for capacity building of government institutional stakeholders on various aspects of operationalising electric buses in Sri Lanka will be conducted under this output. | Attendance sheet and feedback from trainees shared with CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Private bus operators' association and private bus operators, drivers, workshop technicians, Finance House association, Insurance association, commercial banks, leasing and financing companies | Training materials, Participant list with gender breakdown, Training materials, Participant list with gender breakdown | HDV-23-003/5.3 A report tracking mitigation potential and actual emission reduction during and immediately after project period by the deployment of 5 electric buses, for Ministry of Transport and Highways /Ministry of Environment for NDC reporting | Output 5.3 A report tracking mitigation potential and actual emission reduction during and immediately after project period by the deployment of 5 electric buses, for Ministry of Transport and Highways /Ministry of Environment for NDC reporting | Number of SLCP assessments, emissions inventories, and other emissions datasets produced | 1 | Report | 2026-05-31 | A project monitoring, reporting and verification system will be developed to track project progress against objectives and update the Project Board on the same during board meetings. | Monitoring report reviewed and approved by CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | null | Tool, Tool, Research or study | [7 empty] | Activity 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | Staff and Other Personnel Costs | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.3.1-1 International consultant | 25000 | 25000 | 0 | 0 |  | HDV-23-003/5.3 A report tracking mitigation potential and actual emission reduction during and immediately after project period by the deployment of 5 electric buses, for Ministry of Transport and Highways /Ministry of Environment for NDC reporting | Output 5.3 A report tracking mitigation potential and actual emission reduction during and immediately after project period by the deployment of 5 electric buses, for Ministry of Transport and Highways /Ministry of Environment for NDC reporting | Number of SLCP assessments, emissions inventories, and other emissions datasets produced | 1 | Report | 2026-05-31 | A project monitoring, reporting and verification system will be developed to track project progress against objectives and update the Project Board on the same during board meetings. | Monitoring report reviewed and approved by CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | null | Tool, Tool, Research or study | HDV-23-003/3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Developing and/or delivering training | null | null | (blank) | At least 5 multi-channel mass media, social media and PIS promotional/advertising campaign designed and executed about the benefits of public transport, particularly low-carbon options such as electric buses, rail transport, park-and-ride schemes, bicycling, walking etc. This should include ongoing television/radio advertisements, print/newspaper campaigns running for about a month. | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | Photo or video
|  |  | HDV-23-003/2.1.1Viability assessment of EV charging stations is completed and approved | Activity 2.1.1Viability assessment of EV charging stations is completed and approved | Research, data collection, and/or report writing | null | null | (blank) | An Analytical report on safety, security, accessibility aspects of public transport buses in Sri Lanka, particularly from the perspective of women's safety and ease of accessibility of public transport buses for elderly/children/special needs commuters is completed | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Research or study | [21 empty] | Activity 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | Staff and Other Personnel Costs | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.3.1-2 National consultant | 15000 | 15000 | 0 | 0 | [15 empty] | HDV-23-003/3.2.1Mass media promotional campaigns on benefits of public transport | Activity 3.2.1Mass media promotional campaigns on benefits of public transport | Producing and distributing communications materials | null | null | (blank) | At least 20 targeted promotional events (town-level/community-level, at SLTB bus stations, schools or corporate offices) designed, planned and executed on the benefits of using public transport | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | Photo or video
|  |  | HDV-23-003/2.1.2An Analytical gender (including elderly, children, specific needs commuter) specific report on safety, security, accessibility aspects of public transport buses in Sri Lanka | Activity 2.1.2An Analytical gender (including elderly, children, specific needs commuter) specific report on safety, security, accessibility aspects of public transport buses in Sri Lanka | Research, data collection, and/or report writing | null | null | (blank) | Training programs, training at least 60 trainees (30% being women), designed and delivered for government institutional stakeholders (MoTH, MoPE, NTC, SLTB, WPRPTA, CMC) on techno-commercial (such as procurement, planning, performance evaluation, scheduling and charging infrastructure of electric bus systems), financial/economic and policy/regulatory (best practices etc.) frameworks for enabling electric bus deployment for public transport and associated bus charging stations in Sri Lanka; the training program needs to include gender-specific and accessibility/inclusivity aspects as well. | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Participant list with gender breakdown | [21 empty] | Activity 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | Travel | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.3.1-3 Travel fare | 1000 | 1000 | 0 | 0 | [15 empty] | HDV-23-003/3.2.2Targeted promotional events on benefits of public transport | Activity 3.2.2Targeted promotional events on benefits of public transport | Organising, holding, or participating in a meeting or event | null | null | (blank) | At least 10 targeted campaigns planned and executed on safety and comfort features on public transport buses, such as women's safety due to installation of CCTV cameras and road/driver safety features on electric buses | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | Photo or video
|  |  | HDV-23-003/2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output 2.2 Knowledge and capacity improved amongst local stakeholders (MoTH, MoP&E, NTC, WPRPTA, CMC, and public bus operators) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Number of person hours of training provided | 6720 | Person hours | 2025-11-30 | Design and delivery of training programs for capacity building of private sector stakeholders on technical features of electric buses, economic/financial viability of e-buses will be conducted under this output. | Attendance sheet and feedback from trainees shared with CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Training materials, Training materials, Participant list with gender breakdown, Training materials, Training materials, Participant list with gender breakdown | [21 empty] | Activity 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | Travel | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.3.1-4 DSA for international consultant | 3840 | 3840 | 0 | 0 | [15 empty] | HDV-23-003/3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | Activity 3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | Producing and distributing communications materials | null | null | (blank) | Enhanced capital subsidy scheme (including the procedure for application, evaluation, verification and disbursement of capital subsidies) is instituted under a government programme, offering subsidies up to an indicative level of 30% of capital costs of an electric bus based on current estimates of capital costs. | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Tool
|  |  | HDV-23-003/2.2.1Training programs designed and delivered for government institutional stakeholders | Activity 2.2.1Training programs designed and delivered for government institutional stakeholders | Developing and/or delivering training | null | null | (blank) | Training programs, training at least 30 trainees (50% being women), designed and delivered for commercial banks/financial institutions (loan officers and senior executives of banks/leasing and financing companies involved in or interested in lending to electric bus mobility sector) on techno-commercial, financial/economic and policy/regulatory frameworks for enabling electric bus deployment for public transport and associated bus charging stations in Sri Lanka; the training program needs to include gender-specific and accessibility/inclusivity aspects as well. | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Finance House association, Insurance association, commercial banks, leasing and financing companies | Participant list with gender breakdown | [21 empty] | Activity 1.3.1 A comprehensive, gender-sensitive and inclusive 'Electric Bus Mobility Policy and Regulatory Framework' is developed | Travel | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.3.1-5 DSA for national consultant | 1464 | 1464 | 0 | 0 | [15 empty] | HDV-23-003/4.1.1Technical assistance to setup a mechanism for channelling of enhanced grants as capital subsidy scheme | Activity 4.1.1Technical assistance to setup a mechanism for channelling of enhanced grants as capital subsidy scheme | Policy, project, or tool design | null | null | (blank) | Five electric buses on public transport routes within Colombo city are procured and deployed with support from capital subsidy instituted in the previous activity. | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | null | Inventory
|  |  | HDV-23-003/3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Output 3.1 Improved knowledge and capacity among local private stakeholders (private bus operator association, bus drivers’ and workshop technicians’ associations, and commercial banks/financial institutions/finance and insurance associations) on risks, technical standards, and operational issues of deployment of electric buses. All capacity building measures will include a certain minimum percentage of women trainees. | Number of person hours of training provided | 9840 | Person hours | 2025-10-31 | Various targeted promotional events and public awareness campaigns on benefits of using low-carbon public transport in Sri Lanka will be held to gain public support for above transition | Campaign materials and photos shared with CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | Tool, Tool, Photo or video, Tool, Tool, Photo or video | [21 empty] | Activity 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | Staff and Other Personnel Costs | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.4.1-1 International consultant | 10000 | 10000 | 0 | 0 | [15 empty] | HDV-23-003/4.1.2Five electric buses on public transport routes are procured and deployed with support from enhanced capital subsidy scheme and leased to public/private bus operator | Activity 4.1.2Five electric buses on public transport routes are procured and deployed with support from enhanced capital subsidy scheme and leased to public/private bus operator | Other | null | null | (blank) | Webinar materials will be developed and delivered to all project stakeholders and CCAC | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | null | Meeting report
|  |  | HDV-23-003/3.1.1Training programs designed and delivered for commercial banks/financial institutions | Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Developing and/or delivering training | null | null | (blank) | Training programs, training at least 60 trainees (10% being women), designed and delivered to private bus operators, their bus drivers and workshop technicians on electric bus operational and financial feasibility (vs ICE buses), e-bus driving techniques, safety (including women's safety) and security aspects and maintenance, management of EV batteries/their scientific disposal. | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Private bus operators' association and private bus operators, drivers, workshop technicians | Participant list with gender breakdown | [21 empty] | Activity 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | Staff and Other Personnel Costs | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.4.1-2 National consultant | 8000 | 8000 | 0 | 0 | [15 empty] | HDV-23-003/5.1.1 A 45- to 60-minute webinar about the project approach and outcomes developed and delivered to CCAC partners and project stakeholders | Activity 5.1.1 A 45- to 60-minute webinar about the project approach and outcomes developed and delivered to CCAC partners and project stakeholders | Producing and distributing communications materials | null | null | (blank) | A case-study will be developed on project objectives, outcomes achieved, learnings and guidance for future scale-up | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | null | Research or study
|  |  | HDV-23-003/3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Developing and/or delivering training | null | null | (blank) | At least 5 multi-channel mass media, social media and PIS promotional/advertising campaign designed and executed about the benefits of public transport, particularly low-carbon options such as electric buses, rail transport, park-and-ride schemes, bicycling, walking etc. This should include ongoing television/radio advertisements, print/newspaper campaigns running for about a month. | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | Photo or video | [21 empty] | Activity 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | Travel | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.4.1-3 Travel fare | 500 | 500 | 0 | 0 | [15 empty] | HDV-23-003/5.2.1 A 5- to 10-page case study to facilitate scale up of project's activities | Activity 5.2.1 A 5- to 10-page case study to facilitate scale up of project's activities | Producing and distributing communications materials | null | null | (blank) | A report tracking GHG emissions reductions will be instituted that will also help Sri Lankan government track its emissions reductions against its NDC targets. | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Environment | Tool
|  |  | HDV-23-003/3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Output 3.2 Increased awareness and sensitization among local residents regarding the benefits of using public transport in general, and low-carbon electric mobility in particular, including safety aspects for women | Number of partnerships, associations, or campaigns launched to drive SLCP action | 35 | Campaigns | 2025-11-30 | Technical assistance provided to the government of Sri Lanka to setup and operationalise subsidy scheme to enable procurement and deployment of the first electric buses for public transport in Sri Lanka | Procurement documents reviewed and approved by CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Inventory, Funding proposal, Photo or video | [21 empty] | Activity 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | Travel | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.4.1-4 DSA for international consultant | 1920 | 1920 | 0 | 0 | [15 empty] | HDV-23-003/5.3.1 A report/system tracking actual emission reduction from deployment of 5 e-buses against mitigation potential | Activity 5.3.1 A report/system tracking actual emission reduction from deployment of 5 e-buses against mitigation potential | Research, data collection, and/or report writing | null | null | (blank) | A monitoring, reporting and verification system is setup to track progress of project' activities and outcomes achieved are in line with its objectives | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | null | Tool
|  |  | HDV-23-003/3.2.1Mass media promotional campaigns on benefits of public transport | Activity 3.2.1Mass media promotional campaigns on benefits of public transport | Producing and distributing communications materials | null | null | (blank) | At least 20 targeted promotional events (town-level/community-level, at SLTB bus stations, schools or corporate offices) designed, planned and executed on the benefits of using public transport | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | Photo or video | [21 empty] | Activity 1.4.1 An 'Electricity Grid Impact Study due to Electric Vehicle Integration' is completed and approved | Travel | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.4.1-5 DSA for national consultant | 854 | 854 | 0 | 0
|  |  | HDV-23-003/3.2.2Targeted promotional events on benefits of public transport | Activity 3.2.2Targeted promotional events on benefits of public transport | Organising, holding, or participating in a meeting or event | null | null | (blank) | At least 10 targeted campaigns planned and executed on safety and comfort features on public transport buses, such as women's safety due to installation of CCTV cameras and road/driver safety features on electric buses | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council, private bus operators, commuters, public | Photo or video | [21 empty] | Activity 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | Staff and Other Personnel Costs | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.4.2-1 International consultant | 10000 | 10000 | 0 | 0
|  |  | HDV-23-003/3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | Activity 3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | Producing and distributing communications materials | null | null | (blank) | Enhanced capital subsidy scheme (including the procedure for application, evaluation, verification and disbursement of capital subsidies) is instituted under a government programme, offering subsidies up to an indicative level of 30% of capital costs of an electric bus based on current estimates of capital costs. | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Transport and Highways, Ministry of Power and Energy, National Transport Commission, Sri Lanka Transport Board, Western Province Road Passenger Transport Authority, Colombo Municipal Council | Tool | [21 empty] | Activity 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | Staff and Other Personnel Costs | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.4.2-2 National consultant | 10000 | 10000 | 0 | 0
|  |  | HDV-23-003/4.1 5 small/medium 9-metre buses deployed through public private partnerships in Colombo Municipal area after selection of vendor/OEM through a competitive tender process as per UN procurement rules | Output 4.1 5 small/medium 9-metre buses deployed through public private partnerships in Colombo Municipal area after selection of vendor/OEM through a competitive tender process as per UN procurement rules | Number of tools, equipment, or technologies installed | 5 | Electric buses | 2026-05-15 | An informative webinar will be conducted to convey the project's objectives, approach, outcomes achieved and learnings to all relevant participants. | Webinar material reviewed and approved by CCAC; webinar attended by CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | null | Meeting report, Participant list with gender breakdown, Photo or video, Meeting report, Participant list with gender breakdown, Photo or video, Meeting report, Participant list with gender breakdown, Photo or video, Meeting report, Participant list with gender breakdown, Photo or video | [21 empty] | Activity 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | Travel | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.4.2-3 Travel fare | 500 | 500 | 0 | 0
|  |  | HDV-23-003/4.1.1Technical assistance to setup a mechanism for channelling of enhanced grants as capital subsidy scheme | Activity 4.1.1Technical assistance to setup a mechanism for channelling of enhanced grants as capital subsidy scheme | Policy, project, or tool design | null | null | (blank) | Five electric buses on public transport routes within Colombo city are procured and deployed with support from capital subsidy instituted in the previous activity. | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | null | Inventory | [21 empty] | Activity 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | Travel | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.4.2-4 DSA for international consultant | 1920 | 1920 | 0 | 0
|  |  | HDV-23-003/4.1.2Five electric buses on public transport routes are procured and deployed with support from enhanced capital subsidy scheme and leased to public/private bus operator | Activity 4.1.2Five electric buses on public transport routes are procured and deployed with support from enhanced capital subsidy scheme and leased to public/private bus operator | Other | null | null | (blank) | Webinar materials will be developed and delivered to all project stakeholders and CCAC | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | null | Meeting report | [21 empty] | Activity 1.4.2 An analytical report on gaps for implementing low-carbon transport in Sri Lanka | Travel | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.4.2-5 DSA for national consultant | 976 | 976 | 0 | 0
|  |  | HDV-23-003/5.1 A 45- to 60-minute webinar about the project approach and outcomes delivered to CCAC partners and project stakeholders no later than the project end date | Output 5.1 A 45- to 60-minute webinar about the project approach and outcomes delivered to CCAC partners and project stakeholders no later than the project end date | Number of public events, webinars, or side events hosted | 1 | Number of webinars held | 2026-05-15 | A case study on the project experience will be produced to help guide future scale-up and active involvement of private sector. | Case study reviewed and approved by CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | null | Research or study, Research or study | [21 empty] | Activity 1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | Staff and Other Personnel Costs | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.4.3-1 International consultant | 2500 | 2500 | 0 | 0
|  |  | HDV-23-003/5.1.1 A 45- to 60-minute webinar about the project approach and outcomes developed and delivered to CCAC partners and project stakeholders | Activity 5.1.1 A 45- to 60-minute webinar about the project approach and outcomes developed and delivered to CCAC partners and project stakeholders | Producing and distributing communications materials | null | null | (blank) | A case-study will be developed on project objectives, outcomes achieved, learnings and guidance for future scale-up | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | null | Research or study | [21 empty] | Activity 1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | Staff and Other Personnel Costs | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.4.3-2 National consultant | 2000 | 2000 | 0 | 0
|  |  | HDV-23-003/5.2 A 5- to 10-page case study or guidance document to support the replication or scale up of the project activities and/or results for potential public and private sector operators/stakeholders | Output 5.2 A 5- to 10-page case study or guidance document to support the replication or scale up of the project activities and/or results for potential public and private sector operators/stakeholders | Number of SLCP knowledge resources or tools produced | 1 | Document | 2026-05-31 | A GHG emission reduction tracking system introduced by the project will produce a report on GHG emissions reduced , after deployment of five electric buses under this project during project period and after, to compare if mitigation potential is achieved for the reporting purposes of the government of Sri Lanka | Mitigation report reviewed and approved by CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Environment | Tool, Tool, Inventory, Research or study | [21 empty] | Activity 1.4.3 A report on planning replacement of ICE buses for public transport in Sri Lanka | Travel | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.4.3-3 DSA for national consultant | 244 | 244 | 0 | 0
|  |  | HDV-23-003/5.2.1 A 5- to 10-page case study to facilitate scale up of project's activities | Activity 5.2.1 A 5- to 10-page case study to facilitate scale up of project's activities | Producing and distributing communications materials | null | null | (blank) | A report tracking GHG emissions reductions will be instituted that will also help Sri Lankan government track its emissions reductions against its NDC targets. | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | Ministry of Environment | Tool | [21 empty] | Activity 1.6.1 Project Support | UN-PSC | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/1.6.1-3 GMS and UN Coordinator Levy | 58075 | 58075 | 0 | 0
|  |  | HDV-23-003/5.3 A report tracking mitigation potential and actual emission reduction during and immediately after project period by the deployment of 5 electric buses, for Ministry of Transport and Highways /Ministry of Environment for NDC reporting | Output 5.3 A report tracking mitigation potential and actual emission reduction during and immediately after project period by the deployment of 5 electric buses, for Ministry of Transport and Highways /Ministry of Environment for NDC reporting | Number of SLCP assessments, emissions inventories, and other emissions datasets produced | 1 | Report | 2026-05-31 | A project monitoring, reporting and verification system will be developed to track project progress against objectives and update the Project Board on the same during board meetings. | Monitoring report reviewed and approved by CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | null | Tool, Tool, Research or study | [21 empty] | Activity 2.1.1Viability assessment of EV charging stations is completed and approved | Staff and Other Personnel Costs | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/2.1.1-1 International consultant | 10000 | 10000 | 0 | 0
|  |  | HDV-23-003/5.3.1 A report/system tracking actual emission reduction from deployment of 5 e-buses against mitigation potential | Activity 5.3.1 A report/system tracking actual emission reduction from deployment of 5 e-buses against mitigation potential | Research, data collection, and/or report writing | null | null | (blank) | A monitoring, reporting and verification system is setup to track progress of project' activities and outcomes achieved are in line with its objectives | null | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | Vehicles & Engines | Sri Lanka | null | Tool | [21 empty] | Activity 2.1.1Viability assessment of EV charging stations is completed and approved | Staff and Other Personnel Costs | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/2.1.1-2 National consultant | 8000 | 8000 | 0 | 0
[38 empty] | Activity 2.1.1Viability assessment of EV charging stations is completed and approved | Travel | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/2.1.1-3 Travel fare | 500 | 500 | 0 | 0
[38 empty] | Activity 2.1.1Viability assessment of EV charging stations is completed and approved | Travel | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/2.1.1-4 DSA for international consultant | 1920 | 1920 | 0 | 0
[38 empty] | Activity 2.1.1Viability assessment of EV charging stations is completed and approved | Travel | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/2.1.1-5 DSA for national consultant | 854 | 854 | 0 | 0
[38 empty] | Activity 2.1.2An Analytical gender (including elderly, children, specific needs commuter) specific report on safety, security, accessibility aspects of public transport buses in Sri Lanka | Staff and Other Personnel Costs | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/2.1.2-1 National consultant | 12000 | 12000 | 0 | 0
[38 empty] | Activity 2.1.2An Analytical gender (including elderly, children, specific needs commuter) specific report on safety, security, accessibility aspects of public transport buses in Sri Lanka | Travel | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/2.1.2-2 DSA for national consultant | 1220 | 1220 | 0 | 0
[38 empty] | Activity 2.2.1Training programs designed and delivered for government institutional stakeholders | Staff and Other Personnel Costs | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/2.2.1-1 International consultant | 15000 | 0 | 15000 | 0
[38 empty] | Activity 2.2.1Training programs designed and delivered for government institutional stakeholders | Staff and Other Personnel Costs | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/2.2.1-2 National consultant | 10000 | 0 | 10000 | 0
[38 empty] | Activity 2.2.1Training programs designed and delivered for government institutional stakeholders | Supplies Commodities and Materials | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/2.2.1-6 Printing materials, handouts, audio-visual material | 2000 | 0 | 2000 | 0
[38 empty] | Activity 2.2.1Training programs designed and delivered for government institutional stakeholders | Travel | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/2.2.1-3 Travel fare | 1000 | 0 | 1000 | 0
[38 empty] | Activity 2.2.1Training programs designed and delivered for government institutional stakeholders | Travel | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/2.2.1-4 DSA for international consultant | 3264 | 0 | 3264 | 0
[38 empty] | Activity 2.2.1Training programs designed and delivered for government institutional stakeholders | Travel | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/2.2.1-5 DSA for national consultant | 1708 | 0 | 1708 | 0
[38 empty] | Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Contractual Services | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.1.1-7 Training venue and other contractual services | 2000 | 0 | 2000 | 0
[38 empty] | Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Staff and Other Personnel Costs | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.1.1-1 International consultant | 7500 | 0 | 7500 | 0
[38 empty] | Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Staff and Other Personnel Costs | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.1.1-2 National consultant | 6000 | 0 | 6000 | 0
[38 empty] | Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Supplies Commodities and Materials | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.1.1-6 Printing materials, handouts, audio-visual material | 1740 | 0 | 1740 | 0
[38 empty] | Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Travel | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.1.1-3 Travel fare | 500 | 0 | 500 | 0
[38 empty] | Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Travel | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.1.1-4 DSA for international consultant | 2880 | 0 | 2880 | 0
[38 empty] | Activity 3.1.1Training programs designed and delivered for commercial banks/financial institutions | Travel | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.1.1-5 DSA for national consultant | 1708 | 0 | 1708 | 0
[38 empty] | Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Contractual Services | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.1.2-7 Training venue and other contractual services | 2000 | 0 | 2000 | 0
[38 empty] | Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Staff and Other Personnel Costs | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.1.2-1 International consultant | 15000 | 0 | 15000 | 0
[38 empty] | Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Staff and Other Personnel Costs | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.1.2-2 National consultant | 8000 | 0 | 8000 | 0
[38 empty] | Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Supplies Commodities and Materials | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.1.2-6 Printing materials, handouts, audio-visual material | 2000 | 0 | 2000 | 0
[38 empty] | Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Travel | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.1.2-3 Travel fare | 500 | 0 | 500 | 0
[38 empty] | Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Travel | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.1.2-4 DSA for international consultant | 3264 | 0 | 3264 | 0
[38 empty] | Activity 3.1.2Training programs designed and delivered to private bus operators and their bus drivers and workshop technicians | Travel | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.1.2-5 DSA for national consultant | 1708 | 0 | 1708 | 0
[38 empty] | Activity 3.2.1Mass media promotional campaigns on benefits of public transport | Contractual Services | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.2.1-4 Training venue and other contractual services | 30000 | 20000 | 10000 | 0
[38 empty] | Activity 3.2.1Mass media promotional campaigns on benefits of public transport | Staff and Other Personnel Costs | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.2.1-1 National consultant | 5600 | 5600 | 0 | 0
[38 empty] | Activity 3.2.1Mass media promotional campaigns on benefits of public transport | Supplies Commodities and Materials | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.2.1-3 Audio visual material, posters, handouts | 2500 | 1666.6667 | 833.3333 | 0
[38 empty] | Activity 3.2.1Mass media promotional campaigns on benefits of public transport | Travel | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.2.1-2 DSA for national consultant | 854 | 854 | 0 | 0
[38 empty] | Activity 3.2.2Targeted promotional events on benefits of public transport | Contractual Services | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.2.2-4 Training venue and other contractual services | 30000 | 0 | 30000 | 0
[38 empty] | Activity 3.2.2Targeted promotional events on benefits of public transport | Staff and Other Personnel Costs | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.2.2-1 National consultant | 6000 | 0 | 6000 | 0
[38 empty] | Activity 3.2.2Targeted promotional events on benefits of public transport | Supplies Commodities and Materials | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.2.2-3 Audio visual material, posters, handouts | 2000 | 0 | 2000 | 0
[38 empty] | Activity 3.2.2Targeted promotional events on benefits of public transport | Travel | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.2.2-2 DSA for national consultant | 854 | 0 | 854 | 0
[38 empty] | Activity 3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | Contractual Services | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.2.3-4 Training venue and other contractual services | 15000 | 0 | 15000 | 0
[38 empty] | Activity 3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | Staff and Other Personnel Costs | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.2.3-1 National consultant | 6000 | 0 | 6000 | 0
[38 empty] | Activity 3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | Supplies Commodities and Materials | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.2.3-3 Audio visual material, posters, handouts | 2000 | 0 | 2000 | 0
[38 empty] | Activity 3.2.3Targeted campaigns on safety/accessibility features of low-carbon transport options | Travel | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/3.2.3-2 DSA for national consultant | 854 | 0 | 854 | 0
[38 empty] | Activity 4.1.1Technical assistance to setup a mechanism for channelling of enhanced grants as capital subsidy scheme | Staff and Other Personnel Costs | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/4.1.1-1 National consultant | 20000 | 0 | 20000 | 0
[38 empty] | Activity 4.1.1Technical assistance to setup a mechanism for channelling of enhanced grants as capital subsidy scheme | Travel | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/4.1.1-2 DSA for national consultant | 2440 | 0 | 2440 | 0
[38 empty] | Activity 4.1.2Five electric buses on public transport routes are procured and deployed with support from enhanced capital subsidy scheme and leased to public/private bus operator | Equipment Vehicles and Furniture | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/4.1.2-1 Procurement of Electric Buses | 225000 | 0 | 225000 | 0
[38 empty] | Activity 5.1.1 A 45- to 60-minute webinar about the project approach and outcomes developed and delivered to CCAC partners and project stakeholders | Staff and Other Personnel Costs | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/5.1.1-1 National consultant | 3000 | 0 | 0 | 3000
[38 empty] | Activity 5.2.1 A 5- to 10-page case study to facilitate scale up of project's activities | Staff and Other Personnel Costs | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/5.2.1-1 National consultant | 3000 | 0 | 0 | 3000
[38 empty] | Activity 5.3.1 A report/system tracking actual emission reduction from deployment of 5 e-buses against mitigation potential | Staff and Other Personnel Costs | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/5.3.1-1 National consultant | 6000 | 0 | 6000 | 0
[38 empty] | Activity 5.4.1 An MRV system setup and managed by PMU to track project progress and report to the Project Board and CCAC | Staff and Other Personnel Costs | CCAC | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines | United Nations Development Programme (UNDP) - Sri Lanka Country Office (24-035) | HDV-23-003/5.4.1-1 National consultant | 6000 | 6000 | 0 | 0

## Indicator validation (hidden)
Main indicator | Unit of measure | Instructions for first dropdown | 1st dropdown list | Instructions for 2nd dropdown | 2nd dropdown list | Instructions for open text | Level | Level | Outcome |  |  |  | Level | Output |  |  |  | Level | Outcome | Level | Outcome | Level | Output | Level | Output
Amount of external funding (“catalysed funding”) for SLCP actions | Amount in USD: | Type of funding: | Grant, Loan, Private equity | n/a | n/a | List the funding organisations: | Outcome
Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | Number of plans: | Type of plan: | Policy, Action plan, National budget, Long-term strategy, Recovery plan or stimulus package, Development plan | Status: | Adopted, Implemented | List the SLCP-relevant details included in the plan, including the sectors, pollutants, mitigation actions or targets mentioned: | Outcome | Main indicator | Unit of measure | Instructions for first dropdown | Instructions for 2nd dropdown | Instructions for open text | Main indicator | Unit of measure | Instructions for first dropdown | Instructions for 2nd dropdown | Instructions for open text | Main indicator | 1st dropdown list | Main indicator | 2nd dropdown list | Main indicator | 1st dropdown list | Main indicator | 2nd dropdown list |  |  | Black carbon
Number of articles published in scientific journals as the result of CCAC support | Number of published articles: | n/a | n/a | n/a | n/a | Name of journal and link to the article: | Outcome | Amount of external funding (“catalysed funding”) for SLCP actions | Amount in USD: | Type of funding: | n/a | List the funding organisations: | Amount of co-funding secured to support SLCP projects | Amount in USD: | Type: | n/a | Name of funding source(s): | Amount of external funding (“catalysed funding”) for SLCP actions | Grant | Amount of external funding (“catalysed funding”) for SLCP actions | n/a | Amount of co-funding secured to support SLCP projects | Co-funding | Amount of co-funding secured to support SLCP projects | n/a | Output first list | OFFSET('Indicator validation'!$AC$3,MATCH('4. Outputs'!$C$12,'Indicator validation'!$AB$4:$AB$59,0),0,COUNTIF('Indicator validation'!$AB$4:$AB$59,'4. Outputs'!$C$12),1) | HFCs
Number of commitments to reduce SLCPs through international or regional agreements | Number of entities making commitment (enter total): | Type of commitment: | Bilateral agreement, Legally-binding decision or treaty, Memorandum of Understanding (MoU), Voluntary international framework, Multilateral agreement | Type of entity: | National governments, Businesses, Subnational governments, NGO or IGO | List the SLCP-relevant details included in the commitment or agreement, including the sectors, pollutants, mitigation actions or targets mentioned: | Outcome | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | Number of plans: | Type of plan: | Status: | List the SLCP-relevant details included in the plan, including the sectors, pollutants, mitigation actions or targets mentioned: | Number of decision makers participating in outreach events | Number of attendees: | Type of decision maker: | n/a | List the attendees: | Amount of external funding (“catalysed funding”) for SLCP actions | Loan | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | Adopted | Amount of co-funding secured to support SLCP projects | In-kind contribution | Number of decision makers participating in outreach events | n/a | Output second list | OFFSET('Indicator validation'!$AF$3,MATCH('4. Outputs'!$C$12,'Indicator validation'!$AE$4:$AE$59,0),0,COUNTIF('Indicator validation'!$AE$4:$AE$59,'4. Outputs'!$C$12),1) | Methane
Number of government entities with a demonstrated improved capacity for SLCP action | Number of entities: | Type of entity: | Regional entity, National government, Sub-national government | n/a | n/a | List the government entities by name: | Outcome | Number of articles published in scientific journals as the result of CCAC support | Number of published articles: | n/a | n/a | Name of journal and link to the article: | Number of partnerships, associations, or campaigns launched to drive SLCP action | Number of initiatives: | Type of action: | Scale: | Mitigation actions, targets: | Amount of external funding (“catalysed funding”) for SLCP actions | Private equity | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | Implemented | Number of decision makers participating in outreach events | Head of State | Number of partnerships, associations, or campaigns launched to drive SLCP action | National |  |  | Tropospheric ozone
Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | Number of instruments: | Type: | Law, Regulation, By-law, Standard | Status: | Adopted, Implemented | List the SLCP-relevant details included in the regulation, including the sectors, pollutants, mitigation actions or targets mentioned: | Outcome | Number of commitments to reduce SLCPs through international or regional agreements | Number of entities making commitment (enter total): | Type of commitment: | Type of entity: | List the SLCP-relevant details included in the commitment or agreement, including the sectors, pollutants, mitigation actions or targets mentioned: | Number of plans, policies, laws, or regulations drafted or updated | Amount: | Type: | Scale: | SLCP mitigation actions and/or targets included: | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | Action plan | Number of articles published in scientific journals as the result of CCAC support | n/a | Number of decision makers participating in outreach events | Leader of organisation | Number of partnerships, associations, or campaigns launched to drive SLCP action | Sub-national | Outcome first list | OFFSET('Indicator validation'!$W$3,MATCH('5. Outcomes'!$C$11,'Indicator validation'!$V$4:$V$59,0),0,COUNTIF('Indicator validation'!$V$4:$V$59,'5. Outcomes'!$C$11),1) | All SLCPs
Number of mentions of SLCPs or the CCAC by a Minister or equivalent | Number of mentions: | n/a | n/a | n/a | n/a | Provide the name of the Minister, date of mention, and link to more details where possible: | Outcome | Number of government entities with a demonstrated improved capacity for SLCP action | Number of entities: | Type of entity: | n/a | List the government entities by name: | Number of public events, webinars, or side events hosted | Number of events hosted: | Size of event: | n/a | Link to the event details: | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | Development plan | Number of commitments to reduce SLCPs through international or regional agreements | Businesses | Number of decision makers participating in outreach events | Mayor | Number of partnerships, associations, or campaigns launched to drive SLCP action | Regional/International | Outcome second list | OFFSET('Indicator validation'!$Z$3,MATCH('5. Outcomes'!$C$11,'Indicator validation'!$Y$4:$Y$59,0),0,COUNTIF('Indicator validation'!$Y$4:$Y$59,'5. Outcomes'!$C$11),1)
Number of NDCs that include SLCPs | Number of NDCs: | CCAC involvement: | CCAC-funded, CCAC partner, Non-partner | n/a | n/a | List the SLCP-relevant details included in the NDC, including the sectors, pollutants, mitigation actions or targets mentioned: | Outcome | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | Number of instruments: | Type: | Status: | List the SLCP-relevant details included in the regulation, including the sectors, pollutants, mitigation actions or targets mentioned: | Number of SLCP assessments, emissions inventories, and other emissions datasets produced | Amount: | Type: | n/a | Briefly describe what was produced and how this information will be used by the beneficiary: | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | Long-term strategy | Number of commitments to reduce SLCPs through international or regional agreements | National governments | Number of decision makers participating in outreach events | Minister or equivalent | Number of plans, policies, laws, or regulations drafted or updated | National
Number of news outlets that have covered CCAC-funded activities | Number of articles: | Reach: | Regional, National, Local | n/a | n/a | Name of media outlets and links to overage: | Outcome | Number of mentions of SLCPs or the CCAC by a Minister or equivalent | Number of mentions: | n/a | n/a | Provide the name of the Minister, date of mention, and link to more details where possible: | Number of SLCP knowledge resources or tools produced | Number of resources produced: | Type of resource: | n/a | Briefly descbribe how the resource is being used by the intended audience: | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | National budget | Number of commitments to reduce SLCPs through international or regional agreements | NGO or IGO | Number of partnerships, associations, or campaigns launched to drive SLCP action | Binding | Number of plans, policies, laws, or regulations drafted or updated | Sub-national |  | #N/A
Number of non-government entities with a demonstrated improved capacity for SLCP action | Number of government entities: | Type of entity: | NGO, IGO, Company, Independent/self-employed | n/a | n/a | List the government entities by name: | Outcome | Number of monitoring, reporting, and verification (MRV) systems developed or updated that include SLCPs | Quantity: | n/a | n/a | List the SLCP-relevant details covered, including the sectors and pollutants: | Number of tools, equipment, or technologies installed or tested | Quantity: | Type of recipient: | n/a | Briefly descbribe the tool or technology and its intended use: | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | Policy | Number of commitments to reduce SLCPs through international or regional agreements | Subnational governments | Number of partnerships, associations, or campaigns launched to drive SLCP action | Voluntary | Number of plans, policies, laws, or regulations drafted or updated | Regional/International
Number of SLCP mitigation tools, technologies, or practices adopted | Number of changes: | Level of change: | Individual or household, Entity or institution, Industry | n/a | n/a | Describe the practice or technology: | Outcome | Number of NDCs that include SLCPs | Number of NDCs: | CCAC involvement: | n/a | List the SLCP-relevant details included in the NDC, including the sectors, pollutants, mitigation actions or targets mentioned: | Number of training sessions, workshops delivered | Person hours of training (# participants x # of hours of training): | Type of training: | Type of trainees: | Number of male and female trainees: | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | Recovery plan or stimulus package | Number of government entities with a demonstrated improved capacity for SLCP action | n/a | Number of plans, policies, laws, or regulations drafted or updated | Action plan | Number of public events, webinars, or side events hosted | n/a
Number of monitoring, reporting, and verification (MRV) systems developed or updated that include SLCPs | Quantity: | n/a | n/a | n/a | n/a | List the SLCP-relevant details covered, including the sectors and pollutants: | Outcome | Number of news outlets that have covered CCAC-funded activities | Number of articles: | Reach: | n/a | Name of media outlets and links to overage: | [5 empty] | Number of articles published in scientific journals as the result of CCAC support | n/a | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | Adopted | Number of plans, policies, laws, or regulations drafted or updated | By-law | Number of SLCP assessments, emissions inventories, and other emissions datasets produced | n/a
Amount of co-funding secured to support SLCP projects | Amount in USD: | Type: | Co-funding, In-kind contribution | n/a | n/a | Name of funding source(s): | Output | Number of non-government entities with a demonstrated improved capacity for SLCP action | Number of government entities: | Type of entity: | n/a | List the government entities by name: | [5 empty] | Number of commitments to reduce SLCPs through international or regional agreements | Bilateral agreement | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | Implemented | Number of plans, policies, laws, or regulations drafted or updated | Development plan | Number of SLCP knowledge resources or tools produced | n/a
Number of decision makers participating in outreach events | Number of attendees: | Type of decision maker: | Head of State, Minister or equivalent, Mayor, Leader of organisation | n/a | n/a | List the attendees: | Output | Number of SLCP mitigation tools, technologies, or practices adopted | Number of changes: | Level of change: | n/a | Describe the practice or technology: | [5 empty] | Number of commitments to reduce SLCPs through international or regional agreements | Legally-binding decision or treaty | Number of mentions of SLCPs or the CCAC by a Minister or equivalent | n/a | Number of plans, policies, laws, or regulations drafted or updated | Law | Number of tools, equipment, or technologies installed or tested | n/a
Number of partnerships, associations, or campaigns launched to drive SLCP action | Number of initiatives: | Type of action: | Binding, Voluntary | Scale: | Regional/International, National, Sub-national | Mitigation actions, targets: | Output | [10 empty] | Number of commitments to reduce SLCPs through international or regional agreements | Memorandum of Understanding (MoU) | Number of NDCs that include SLCPs | n/a | Number of plans, policies, laws, or regulations drafted or updated | Long-term strategy | Number of training sessions, workshops delivered | For-profit organisation
Number of plans, policies, laws, or regulations drafted or updated | Amount: | Type: | Policy, Action plan, National budget, Long-term strategy, Recovery plan or stimulus package, Development plan, Law, Regulation, By-law, Standard | Scale: | Regional/International, National, Sub-national | SLCP mitigation actions and/or targets included: | Output | [10 empty] | Number of commitments to reduce SLCPs through international or regional agreements | Multilateral agreement | Number of news outlets that have covered CCAC-funded activities | n/a | Number of plans, policies, laws, or regulations drafted or updated | National budget | Number of training sessions, workshops delivered | Government
Number of public events, webinars, or side events hosted | Number of events hosted: | Size of event: | Small (<50), Medium (50-100), Large (>100) | n/a | n/a | Link to the event details: | Output | [10 empty] | Number of commitments to reduce SLCPs through international or regional agreements | Voluntary international framework | Number of non-government entities with a demonstrated improved capacity for SLCP action | n/a | Number of plans, policies, laws, or regulations drafted or updated | Policy | Number of training sessions, workshops delivered | Non-profit organisation
Number of SLCP assessments, emissions inventories, and other emissions datasets produced | Amount: | Type: | Assessment, Benefits calculation, Inventory, Projection | n/a | n/a | Briefly describe what was produced and how this information will be used by the beneficiary: | Output | [10 empty] | Number of government entities with a demonstrated improved capacity for SLCP action | National government | Number of SLCP mitigation tools, technologies, or practices adopted | n/a | Number of plans, policies, laws, or regulations drafted or updated | Recovery plan or stimulus package | Number of training sessions, workshops delivered | Self-employed
Number of SLCP knowledge resources or tools produced | Number of resources produced: | Type of resource: | Awareness material, Best practice, Case study or report, Guideline or tool, Knowledge platform, Scientific research, Training material | n/a | n/a | Briefly descbribe how the resource is being used by the intended audience: | Output | [10 empty] | Number of government entities with a demonstrated improved capacity for SLCP action | Regional entity | Number of monitoring, reporting, and verification (MRV) systems developed or updated that include SLCPs | n/a | Number of plans, policies, laws, or regulations drafted or updated | Regulation
Number of tools, equipment, or technologies installed or tested | Quantity: | Type of recipient: | Individual or household, Entity or institution, Industry | n/a | n/a | Briefly descbribe the tool or technology and its intended use: | Output | [10 empty] | Number of government entities with a demonstrated improved capacity for SLCP action | Sub-national government |  |  | Number of plans, policies, laws, or regulations drafted or updated | Standard
Number of training sessions, workshops delivered | Person hours of training (# participants x # of hours of training): | Type of training: | General awarenesss, Policy or planning, Technical skills or practices | Type of trainees: | For-profit organisation, Government, Non-profit organisation, Self-employed | Number of male and female trainees: | Output | [10 empty] | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | By-law |  |  | Number of public events, webinars, or side events hosted | Large (>100)
[18 empty] | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | Law |  |  | Number of public events, webinars, or side events hosted | Medium (50-100)
[18 empty] | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | Regulation |  |  | Number of public events, webinars, or side events hosted | Small (<50)
[18 empty] | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | Standard |  |  | Number of SLCP assessments, emissions inventories, and other emissions datasets produced | Assessment
[18 empty] | Number of mentions of SLCPs or the CCAC by a Minister or equivalent | n/a |  |  | Number of SLCP assessments, emissions inventories, and other emissions datasets produced | Benefits calculation
[18 empty] | Number of monitoring, reporting, and verification (MRV) systems developed or updated that include SLCPs | n/a |  |  | Number of SLCP assessments, emissions inventories, and other emissions datasets produced | Inventory
[18 empty] | Number of NDCs that include SLCPs | CCAC partner |  |  | Number of SLCP assessments, emissions inventories, and other emissions datasets produced | Projection
[18 empty] | Number of NDCs that include SLCPs | CCAC-funded |  |  | Number of SLCP knowledge resources or tools produced | Awareness material
[18 empty] | Number of NDCs that include SLCPs | Non-partner |  |  | Number of SLCP knowledge resources or tools produced | Best practice
[18 empty] | Number of news outlets that have covered CCAC-funded activities | Local |  |  | Number of SLCP knowledge resources or tools produced | Case study or report
OFFSET(Indicators!$P$1,MATCH('2. Results'!$D$10,Indicators!$O$2:$O$67,0),0,COUNTIF(Indicators!$O$2:$O$67,'2. Results'!$D$10),1) | [5 empty] | OFFSET(Indicators!$S$1,MATCH('2. Results'!$D$10,Indicators!$R$2:$R$40,0),0,COUNTIF(Indicators!$R$2:$R$40,'2. Results'!$D$10),1) | [11 empty] | Number of news outlets that have covered CCAC-funded activities | National |  |  | Number of SLCP knowledge resources or tools produced | Guideline or tool
[18 empty] | Number of news outlets that have covered CCAC-funded activities | Regional |  |  | Number of SLCP knowledge resources or tools produced | Knowledge platform
[18 empty] | Number of non-government entities with a demonstrated improved capacity for SLCP action | Company |  |  | Number of SLCP knowledge resources or tools produced | Scientific research
[18 empty] | Number of non-government entities with a demonstrated improved capacity for SLCP action | IGO |  |  | Number of SLCP knowledge resources or tools produced | Training material
[18 empty] | Number of non-government entities with a demonstrated improved capacity for SLCP action | Independent/self-employed |  |  | Number of tools, equipment, or technologies installed or tested | Entity or institution
[18 empty] | Number of non-government entities with a demonstrated improved capacity for SLCP action | NGO |  |  | Number of tools, equipment, or technologies installed or tested | Individual or household
[18 empty] | Number of SLCP mitigation tools, technologies, or practices adopted | Entity or institution |  |  | Number of tools, equipment, or technologies installed or tested | Industry
[18 empty] | Number of SLCP mitigation tools, technologies, or practices adopted | Individual or household |  |  | Number of training sessions, workshops delivered | General awarenesss
[18 empty] | Number of SLCP mitigation tools, technologies, or practices adopted | Industry |  |  | Number of training sessions, workshops delivered | Policy or planning
[22 empty] | Number of training sessions, workshops delivered | Technical skills or practices

## Form validation (hidden)
Project status | Activity status | Output status | Objective status | UNEP expenditure | Type of expenditure | Activity category | Means of verification | Reporting periods | CCAC objective | Sectors | Regions | Pollutants addressed | Resource type | Regional scope
On track | Not started | Not started | Achieved | Consultants | Contractual Services | Developing and/or delivering training | Nothing to deliver this period | 2022-01-15 | Drive an ambitious agenda | Agriculture | Africa | All SLCPs | Awareness materials | Global
Issues | On track | On track | Not yet achieved | Operating costs | Equipment Vehicles and Furniture | Organising, holding, or participating in a meeting or event | Funding proposal | 2022-07-15 | Support national action | Assessments | Asia and the Pacific | Black carbon and co-pollutants | Event documents | Regional
| Delayed | Delayed |  | Personnel | Operating and Other Direct Costs | Policy, project, or tool design | Inventory | 2023-01-15 | Support transformative actions | Bricks | Europe | Hydrofluorocarbons (HFCs) | Guidelines & tools | National
| Complete | Complete |  | Travel & workshops | Staff and Other Personnel Costs | Producing and distributing communications materials | Meeting report | 2023-07-15 | Advance policy-relevant research and analysis | Cooling | Global | Methane | Knowledge platforms | Local
[5 empty] | Supplies Commodities and Materials | Project management | Participant list with gender breakdown | 2024-01-15 |  | Health | Latin America and the Caribbean | Tropospheric ozone | Official statements
[5 empty] | Travel | Research, data collection, and/or writing | Photo or video | 2024-07-15 |  | Household energy | North America |  | Online training & related materials
[5 empty] | UN-PSC | Other | Policy paper | 2025-01-15 |  | National planning | West Asia |  | Policies, plans & regulations
[7 empty] | Policy, regulation or other guideline | 2025-07-15 |  | Oil & gas |  |  | Reports, case studies & assessments
[7 empty] | Publication | 2026-01-15 |  | Vehicles |  |  | Scientific publications
[7 empty] | Research or study | 2026-07-15 |  | Waste
Tool
Training materials
Web article
Work plan
Enable multiple choice

## Import order (hidden)
Component
Indicator
Target
Unit
Date
Delivery type
Description
Acceptance criteria
Project
Unique code
Agreement
Sector
Beneficiaries
Agreement filter
Other beneficiaries
Implementer
Delivery description
Level

## 5. Outcomes
5. Outcome indicators |  | See instructions
Project: Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003)
UNDP Sri Lanka
Outcomes to report by project end: 3 | [11 empty] | RELEVANT DOCUMENT 1 | [7 empty] | RELEVANT DOCUMENT 2
Outcome | Indicator | Target | Unit | Unit of measure | Amount | Disaggregation info instructions | Disaggregation info (if applicable) | Disaggregation info instructions2 | Disaggregation info (if applicable)2 | Additional info (if applicable) | Additional info | Title Document 1 | Summary Document 1 | URL Document 1 | Add to CCAC website? Document 1 | Type Document 1 | Authors Document 1 | Sources Document 1 | Date published (mmmm yyyy) Document 1 | Title Document 2 | Summary Document 2 | URL Document 2 | Add to CCAC website? Document 2 | Type Document 2 | Authors Document 2 | Sources Document 2 | Date published (mmmm yyyy) Document 2 | Sector | Beneficiaries | Contract | Beneficiary | Complete | INSTRUCTIONS
Outcome 1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 3 | 1 national policy/plan/ regulations drafted or updated.1 guidelines and 1 assessment completed | Number of instruments: |  | Type: |  | Status: |  | List the SLCP-relevant details included in the regulation, including the sectors, pollutants, mitigation actions or targets mentioned: | [17 empty] | HDV-23-003/1. Policy and regulatory framework for electric public bus transport in Sri Lanka endorsed by the government of Sri Lanka by the end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines |  | #N/A | The first 4 columns in this table list the outcomes, indicators, and targets for this implementer agreement in ascending order by outcome number. Columns to the right of the outcome list contain instructions on how to report on the performance indicators selected for the outcome. Information in this table is reported only once for each output and only after the output is marked as "Complete" in the tab "2. Narrative." All cells in this table must be completed unless they are marked as "optional".
Outcome 2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Number of government entities with a demonstrated improved capacity for SLCP action | 6 | Government entities with improved capacity | Number of entities: |  | Type of entity: |  | n/a |  | List the government entities by name: | [17 empty] | HDV-23-003/2. Public stakeholders will gain technical and operational capacity to deploy low carbon public transport by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines |  | #N/A
Outcome 3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Number of non-government entities with a demonstrated improved capacity for SLCP action | 7 | 7 non-government entities with improved capacity | Number of government entities: |  | Type of entity: |  | n/a |  | List the government entities by name: | [17 empty] | HDV-23-003/3. Private sector’s awareness on low carbon public transport raised and their capacity built by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines |  | #N/A
Outcome 4. Private sector bus operators engage in low carbon public transport through financial incentive package for electric buses by end of the project | Number of SLCP mitigation tools, technologies, or practices adopted | 5 | 5 electric buses deployed in Colombo city | Number of changes: |  | Level of change: |  | n/a |  | Describe the practice or technology: | [17 empty] | HDV-23-003/4. Private sector bus operators engage in low carbon public transport through financial incentive package for electric buses by end of the project | Enabling Environment for Electric Buses for Public Transport and their Pilot Deployment in Colombo, Sri Lanka (HDV-23-003) | Vehicles & Engines |  | #N/A
Outcome 5. Increased knowledge and awareness about low carbon transport including SLCPs among all stakeholders including general public by end of the project | Number of monitoring, reporting, and verification (MRV) systems developed or updated that include SLCPs | 4 | 2 external communications products created and distributed, 2 monitoring reports/systems created | Quantity: |  | n/a |  | n/a |  | List the SLCP-relevant details covered, including the sectors and pollutants: | [17 empty] | HDV-23-003/5. Increased knowledge and awareness about low carbon transport including SLCPs among all stakeholders including general public by end of the project