PROGRAMME PROPOSAL

Programme Title: Sustainable private sector engagement in developing inclusive forest products markets in Ethiopia (Full title)

Sustainable Private Sector in Forestry Programme – SPSF (Short version)

Principal Implementing Partner: Ethiopian Forestry Development, Ministry of Agriculture

Responsible Parties to the IP: CIFOR and SLU

Market Systems Development Partner: International Development Enterprise (iDE)

Start Date:   December  2024	End Date: December 2027

# Brief Description of the Proposed Programme

The " Sustainable private sector engagement in developing inclusive forest products markets in Ethiopia." programme aims to create a vibrant and inclusive forestry sector in Ethiopia. This sector will actively engage the private sector to significantly increase its contribution to the national economy, create green jobs, and reduce poverty while enhancing biodiversity conservation and the flow of environmental goods and services. The programme seeks to achieve systemic change in the market systems of the forestry sector, thereby improving livelihoods and providing decent work opportunities for at least 70,000 rural and peri-urban poor, primarily women and youth.

The proposed programme is in line with and contributes to Ethiopia’s National Long-Term Low Emission Development Strategy, which aims to enhance the socio-economic development of the nation while also making the economy carbon neutral. Additionally, the Programme aligns with the 10-year development plan, contributing to all five National Forest Sector Development Plan pillars:

- Enabling environment and institutional capacity for sustainable use of natural resources.

- Sustainable forest production and value chains for food security and resilience building.

- Enhanced role of forest for rural livelihoods to create jobs and reduce outmigration.

- Enhanced biodiversity conservation and environmental services provision.

- Integrating gender and other cross-cutting issues.

The proposed programme is also in line with Sweden’s Development Cooperation Strategy for Ethiopia (2022-2026), which emphasizes sustainable development, poverty reduction, and gender equality. Specifically, the programme aligns with:

- Result Area 2: Environment, climate, and sustainable use of natural resources, which aims to strengthen the conditions for sustainable management and use of natural resources and ecosystems, including biodiversity.

- Result Area 3: Inclusive economic development, which focuses on improving conditions for productive employment, decent work, and access to improved social security.

By enhancing private sector engagement in the forestry sector and developing inclusive forest product markets, the programme contributes to these strategic areas by fostering sustainable management of natural resources, promoting economic opportunities, and enhancing resilience to climate change. The Programme will employ a hybrid approach combining Market Systems Development (MSD) and direct support to achieve its objectives. This approach includes:

- Market Systems Development (MSD):

  - Focus on private sector engagement and the development of pro-poor forest products markets and inclusive value chains.

  - Identify and address key constraints within the market systems, leveraging the Adopt-Adapt- Expand -Respond (AAER) framework to ensure sustainability and scalability.

- Direct Support:

  - Enhance the enabling environment for private sector engagement through policy and institutional reforms.

  - Build the capacity of state and non-state institutions involved in the forestry sector to support market development.

The hybrid approach ensures that while immediate needs and gaps in the market system are addressed through direct support, the long-term sustainability/resilience and scalability of the interventions are secured through systemic market changes facilitated by MSD. This will all be underpinned by ensuring that women, youth, and local communities’ groups are direct beneficiaries with increased economic opportunities through an energized private sector.

| Contributing Outcome (UNSDCF/CPD, RPD or GPD): OUTCOME 3 By 2025, all people in Ethiopia live in a society resilient to environmental risks and adapted to climate change OUTPUT 3.2 Gender-responsive legal and regulatory frameworks, policies and institutions strengthened, and solutions adopted to address conservation, sustainable use and equitable benefit sharing of natural resources in line with international conventions and national legislation.. | Total resources required:; USD 75.7 million SEK. UNDP TRAC:; 10,683,760. Sweden:; SEK 65 million. |
| --- | --- |

Agreed by (signatures):

| Government | UNDP | Implementing Partner |
| --- | --- | --- |
| Print Name: | Print Name: | Print Name: H.E. Ato Kebede Yimam |
| Date: | Date: | Date: |

# Executive summary

This program is a follow up phase of the SIDA funded Phase 1 support program to Ethiopia. It is in line with and contributes to, among others, Ethiopia’s National Long Term Low Emission Development Strategy that aims to enhance socio-economic development of the nation by also making the economy carbon neutral, and the forestry sectors 10-year development plan, as well as the National Forest Sector Development Plan pillars.  The program is also in line with the Thematic priorities of Sweden’s current Development Cooperation Strategy, i.e., Combating poverty through job creation, trade and education. It contributes directly to the two objectives stated in the Strategy for Sweden’s development cooperation with Ethiopia 2022-2026, i.e. Environment, climate, and sustainable use of natural resources (Result area 2) that aims at strengthening conditions for sustainable management and use of natural resources and ecosystems, including biodiversity; and improving the conditions for food security and strengthening adaptation and resilience to climate change and environmental and natural disasters. And to Inclusive economic development (Result area 3) which aims at improving conditions for productive employment and decent work; and at improving access to social security.

The proposed program follows a hybrid approach that combines:

(i) Market Systems Development Approach - to enhance private sector engagement in the forestry sector and in developing pro-poor forest products markets; and

(ii) Direct support to create an enabling environment for private sector engagement and the development of pro-poor forest product markets through identifying gaps in policy and institutional aspects, and in the capacity of institutions (both state and non-state) that are engaged in the forest product markets systems.

Taken together the program will contribute to developing systemic institutional capacity development within the forestry sector. The programme will specifically target women, youth and other local communities’ groups to ensure that there is sustainability of the programme interventions resulting in increased economic empowerment.

The goal of the program is to foster the development of a resilient and inclusive private sector ecosystem that promotes sustainable management and equitable marketing of forest products, significantly increase sector’s contribution to the national economy, creates green jobs and reduces poverty while enhancing biodiversity conservation and flow of environmental services and goods to better adapt to and mitigate climate change which will particularly benefit local communities , thereby contributing to poverty reduction, environmental conservation, and economic growth in Ethiopia.

To contribute to the above stated goal, the program is designed to achieve objectives of enhancing private sector engagement in forestry and developing pro-poor forest product markets (using a Market Systems Development approach) that in turn would substantially improve livelihoods and decent work opportunities for at least 70,000 rural and peri-urban poor (mainly women and youth) through systemic change in market systems within an improved sustainably managed forestry sector. By so doing, the program plans to:

- Enhance the capacity of private sector actors, including small-scale producers, traders, cooperatives to engage in sustainable forest product marketing practices in Ethiopia.

- Strengthen institutional support systems and regulatory frameworks to create an enabling environment for private sector engagement in pro-poor forest products marketing, ensuring equitable access and fair-trade practices.

- Facilitate the development of market linkages, value chains, and distribution networks for pro-poor forest products, promoting inclusive economic opportunities and livelihood enhancement for local communities in Ethiopia.

The proposed Programme has two outcomes.

Outcome 1.  Private sector engagement in forestry and development of pro-poor forest product markets enhanced. Enhancing the engagement of the private sector in forestry and developing pro-poor forest product market systems help create jobs and assist smallholders in diversifying their livelihood options and increasing their income. By enhancing the participation in the markets of forest-based cooperatives, members’ income will increase, and this creates incentives for cooperatives to engage more in new commercial plantations. This in turn will reduce pressure on natural forests and hence will have positive conservation impacts. The selected markets to develop, notably seedling raising, and the collection and marketing of gums engage the poor and women, and hence the Programme will contribute to reducing poverty. As forest cooperatives to be engaged in commercial plantations will be required to have their lands properly selected (mainly degraded lands) and demarcated (by involving the surrounding communities and the local land administration office), the Programme will contribute towards efforts of landscape restoration and to reducing potential land related conflicts.  By working through forest-based cooperatives, members access to finance will also be improved to actively engage in the forest products markets. Their access to market information and forestry extension will also be enhanced so that the productivity of their stands can be improved. Improved income from forest products such as from gums and resins will be an incentive for forest dependent communities to sustainably manage dry forests. Support to seedlings and gums and resins markets development contributes to gender equality as women stand to benefit equally from the development of such markets.

Under outcome 1. Two outputs are expected. These are:

- Market system of round wood, tree seedlings, and NTFPs mapped, analysed and binding constraints identified

- Intervention options to bring about desired changes in round wood, tree seedlings, and NTFPs market systems selected and implemented, and performance monitored

Outcome 2.  Enabling environment for private sector engagement in forestry and for developing more inclusive forest product market systems created. Studies point at the policy and legal gaps as well as institutional limitations that hinder the engagement of the private sector in forestry and the development of pro-poor forest products markets in Ethiopia. The second outcome of the Programme entails identifying the gaps in policy and legal instruments including consideration of specific gender and social inclusion constraints in order to make concrete implementable suggestions for change as well as exposing the capacity limitations of institutions engaged in the core functions, supplementary and regulatory activities of forest product market systems.

Two outcomes are expected under outcome 1. These are:

- challenges limiting private sector engagement in forestry and the participation of poor women, youth and local communities’ groups and men in growing forest product market systems identified, and improvement measures proposed.

- Capacity of institutions to support private sector engagement in forestry and to develop more inclusive forest product market systems strengthened.

Taken together these outputs will pave the way to make forest products work better for the poor and other local communities’ groups. The behaviour of market actors is expected to change in ways that would improve the overall market performance and ensure the inclusion of and benefits for the poor. Growing and efficient markets help to create green jobs, and institutions such as vocational training centres that will be assisted to help build the knowledge and skills of the youth so that they too will be better able to actively participate and benefit from the growth of forest product markets.

As different private sector actors (e.g., forest-based cooperatives, tree growers’ associations, private investors,) face different constraints (e.g., access to market information, access to finance, access to technology and forestry extension, etc.), the leverage points that work best will be clearly identified and addressed within the inception phase. One commonly cited constraint is access to finance. The Programme will explore options to address this constraint by exploring innovative finance flows, and improving access to credits, market information (using appropriate social media platforms) and forestry extension/advisory services for the youth, poor women and men and other local communities’ groups.  This also contributes to the creation of an enabling environment through institutional capacity strengthening so that the rules to engage with the forestry private sector and to facilitate engagement of the poor in forest products markets which will be updated, better coordinated, and more systematically enforced.

The Programme will be implemented in areas where productive forests were developed during Phase 1 of the support, in areas where commercial private plantations have been expanding, and in areas where sustainable collection and marketing of NTFPs serves the purpose of promoting sustainable forest management, as is the case in dry forests where gums and resins producing cooperatives have been operational. The Programme will pay particular attention to gender, conflict, democracy, and human rights as cross cutting themes. And the risk assessment, management and mitigation measures will be kept under constant review in order to adapt to any emerging external issues that could adversely impact on the delivery of the programme.

The program will be financed by Swedish International Development Cooperation Agency (SIDA). UNDP will co-finance the program. The total cost of the Programme is 75.7 million SEK, of which 65 million is expected from SIDA and one million USD from UNDP. Contribution from SIDA is expected to be disbursed in instalments of 25 MSEK, 30 MSEK, , and 10MSEK, during year I, II and III, respectively. The illustrative budget is also included. The budget lines and detailed allocations will be further elaborated during the inception phase of the programme.

# Acronyms

AAER               Adopt-Adapt- Expand -Respond

AAGR               Average Annual Growth Rate

CBO                  Community Based Organizations

CIFOR              Center for International Forestry Research

CRGE               Climate Resilient Green Economy

EFD                  Ethiopian Forestry Development

FBI		Forest Based Industries

FDRE               Federal Republic of Ethiopia

GDP                 Growth Domestic Product

GHG                Green House Gas

GII                   Gender Inequality Index

GLI                  Green Legacy Initiative

HDI                  Human Development Index

iDE		International Development Enterprise

NDC                  Nationally Determined Contributions

NFSDP              National Forest Sector Development Program

NGO                  Non-Governmental Organizations

NTFP                 Non-Timber Forest Product

PPP                    Public Private Partnership

SDG                   Sustainable Development Goals

SIDA                  Swedish International Development Cooperation Agency

SLU                    Swedish University of Agricultural Sciences

SME                   Small and Medium Scale Enterprises

TBL                    Tree Based Livelihood

ToC                    Theory of Change

UNDP                United Nations Development Programme

Table of Contents

Brief Description of the Proposed Programme	i

Executive summary	iii

Acronyms	vi

1.	Development Challenge	1

1.1	The National Context	1

1.2 Problems to be addressed by the Programme	3

1.2.1 Analysis of Systemic Issues and Root Causes	5

2.	Justification for the Programme strategic approach	5

2.1 Programme Alignment	7

2.2 Programme Theory of Change	8

3. Proposed goal and approach of the Programme	12

3.1 Overall Goal and Objective	12

3.2. 	Approach of the Programme	15

3.3. Thrust of the Programme	17

3.4. Increasing impact, taking good practices to scale, and enhancing sustainability	17

3.5. Phases and planned activities	17

3.5.1. Inception Phase (3-4 months)	17

3.5.2.  Implementation Phase	19

4.	Operationalization of the Programme	21

4.1 	Programme design and targeted forest products	21

4.1.1. Promoting quality tree seedling production by youth and women	21

4.1.2.	Improving production and marketing of gums and resins from dry forests	22

4.1.3.	Improving the marketing of round wood	24

4.1.4 Improving production and marketing of honey and other products from forests and restoration sites	25

4.1.5.  Producing and marketing briquettes from Prosopis juliflora	27

5. 	Programme Management	28

5.1.	Programme management principles	28

5.2	Stakeholders’ Engagement and Partnerships	28

5.2.1.	Stakeholders’ Engagement	28

5.2.2.	Partnerships	28

5.3.	 Programme Implementation Arrangements	29

5.3.1.	Roles and responsibilities of UNDP	29

5.3.2.	Roles and responsibilities of Ethiopian Forestry Development	29

5.4.	Organization and contractual agreements	30

5.5. Programme governance	30

5.6. Coordination	31

6.	Knowledge Management, Learning and Communication	31

7. 	Monitoring and Evaluation	31

8.  	Reporting and Auditing	31

8.1.	Reporting	31

8.2	Auditing	32

9. 	Replicability, Sustainability and Exit Strategy	32

9.1	Replicability	32

9.2.	Sustainability	32

9.3.  Exit Strategy	32

10.	Safeguards and Risks	33

10.1	Environmental and Social Safeguards	33

10.2. Risks Analysis and Mitigation Options	33

11.	Budget	34

12. 	Multi-Year Work Plan	36

13.	Legal Context	37

Annexes	38

Annex 1. Results framework of the Programme	38

Annex 2. Profile of UNDP	47

Annex 3. Profile of Ethiopian Forestry Development	49

Annex 4. Profile of Center for International Forestry Research	50

Annex 5. Profile of SLU and its partner institutions	52

Annex 6. Profile of iDE	53

Annex 7. Proposed governance & management structure of the Programme	55

Annex 8a.  Monitoring plan of the Programme	48

Annex 8b. Proposed evaluation plan of the Programme	49

Annex 9: Social and Environmental Safeguard report	50

Annex 10. Programme Risk Assessment Matrix	63

Annex 11. UNDP-Ethiopia Partnerships and Communications Strategy and Action Plan (PCAP)	65

Annex 12. Strategic Critical Risks and Mitigation Measures	75

Annex 13. Detailed multiyear budget for planned activities aggregated by outputs and outcomes as well as by implementing partners	75

# Development Challenge

## 1.1	The National Context

Ethiopia’s population is expanding rapidly, with an average annual growth rate (AAGR) of approximately 2.5%. The population, estimated at 105.17 million in 2022, is projected to reach 122.32 million by 2030 and 136.8 million by 2037 (CSA, 2013). However, alternative sources provide higher estimates, such as 120.5 million in 2022 by the World Bank and 149.3 million by 2030 according to the UN (2022). The demographic composition is heavily skewed towards youth and children, who make up two-thirds of the population (66.6%) in 2022. Notably, three out of ten Ethiopians are youth (aged 15-29), with 74.9% residing in rural areas (CSA, 2013).

Ethiopia is among the six largest economies in Africa, with a GDP of 127 billion USD in 2023 (Trading Economics, 2023). The real GDP has seen significant growth, reaching 2.35 trillion Birr in FY 2021/22, up from 9,776.20 Birr per person in FY 2007/08 to 22,542.2 Birr per person in FY 2021/22 (NBE, 2023). This represents an average annual real growth rate of about 8% over the last 15 years. Consequently, the poverty rate has decreased from 29.6% in 2010 to 23.5% in 2015. Based on the international poverty line of 2.15 USD per day (2017 PPP USD), poverty declined from 30.8% to 27% during the same period. However, income inequality has risen, with the Gini Index increasing from 33.2 in 2010 to 35 in 2015 (World Bank, 2023). The poorest are further burdened by rising inflation and climate change.

Unemployment exacerbates poverty. The unemployment rate increased from 4.5% in 2013 to 8% in 2021 (CSA, 2021b), underscoring the challenge of job creation. The number of unemployed individuals aged 15-64 rose from 2.13 million in 2013 to 4.81 million in 2021. Female unemployment rates are higher, increasing from 6.5% for females and 2.7% for males in 2013 to 11.7% for females and 5% for males in 2021. Youth unemployment is particularly high, with a rate of 11.8% in 2021 (7.4% for male youth and 16.4% for female youth), and 51.8% of unemployed youth living in rural areas, predominantly landless, while the remaining 48.2% are in urban areas (CSA, 2021). Ethiopia’s Human Development Index (HDI) for 2021 is 0.499, significantly lower than the Sub-Saharan Africa average. This suggests that a child born in Ethiopia today will only be 49.9% as productive as they could be with full education and health. Ethiopia’s Gender Development Index for 2021 was 0.921, showing progress but also substantial gaps in gender equality. Addressing inequities in opportunities and severe resource degradation through interventions that create employment, increase income levels for poor men and women, and conserve and sustainably use natural resources is essential for sustainable development and reducing potential conflicts.

The humanitarian and development landscape in Ethiopia has undergone significant upheaval since 2020, driven by a confluence of crises. Conflicts and recurrent droughts and floods have wreaked havoc on people’s livelihoods, exacerbating humanitarian needs, particularly among the most vulnerable Ethiopians. This has placed immense strain on the country’s development trajectory, highlighting the urgent need for sustainable solutions that empower communities and reduce reliance on external aid. While humanitarian assistance remains essential for providing immediate relief, there is a growing recognition of the necessity to pivot towards more sustainable approaches, limiting the country’s dependency on humanitarian assistance, and working towards sustainable development solutions that strengthen the resilience of the country and its people.

Key Contributions of the Forestry Sector:

The forestry sector holds significant potential for driving improved economic development, promoting environmental sustainability, and reducing poverty particularly for women, youth, and local communities’ groups. Such potential exists through job creation – especially for the poor – by enhancing private sector engagement in developing more inclusive forest product markets. The programme will target the assistance to impact on the lives and economic empowerment of 70,000 women and youth. The private sector can invest in establishing commercial plantations and developing forest product-based industries (FBIs) that process and market forest products. The increasing demand for housing, construction materials, furniture, packaging, agricultural goods, and sports goods indicates that FBIs are poised for rapid growth. This growth, however, will widen the gap between demand and supply for wood and biomass unless the national wood supply increases. Without quality industrial products produced domestically, the nation’s import bill will continue to rise, which are unsustainable, as evidenced by the trends in Figures 1 and 2 below:

Figure 1: Trend of wood products import, 1997–2020 Source: Compiled from data gathered from records of Ethiopian Customs Commission, 2021.

Figure 2: Trend of wood products trade balance, 1997–2020 Source: Compiled from data gathered from records of Ethiopian Customs Commission, 2021.

Recognizing this gap, the private sector has begun to engage in the sector, and exports are gradually increasing. Enhanced private sector engagement is expected to accelerate growth in forest-based industries, commercial plantations, and the number of forest products-based industries. Challenges in obtaining inputs like spare parts and chemicals need to be addressed for this growth to be competitive in national wood markets and processed wood products.

Figure 3: Trend of wood products export, 1997–2020 Source: Compiled from data gathered from records of Ethiopian Customs Commission, 2021.

These figures illustrate the challenges in meeting the demand for processed wood products yet at the same time present tremendous opportunities and potential for private sector engagement in developing FBIs and pro-poor forest product markets. This programme aims to identify key forest products to focus on and leverage market systems development to enhance private sector engagement in developing pro-poor forest product markets.

## 1.2 Problems to be addressed by the Programme

Despite this potential, the sector is currently underperforming due to various systemic constraints. While a thorough market systems analysis is essential to identify these constraints, understanding the underlying causes, and developing interventions that can lead to sustainable and inclusive growth are to be delivered by the programme.

Indicative key constraints are as follows:

- Limited private sector engagement: Enhanced engagement of the private sector expedites the development of the forestry sector if supported with the correct supportive and regulatory framework. The private sector, especially those with the capacity to engage in commercial forestry and forest-based industries as well as in the marketing of forest products and services, can make vital contributions to the development of the forestry sector given their capital and access to better technologies and up-to-date market information. Engagement of the private sector through private-public-partnership (PPP) schemes is still also underdeveloped in the forest sector, although a law has recently been passed to facilitate PPP. The expansion and development of small-scale wood-based enterprises has been very slow owing to limited access to land in urban areas, credit, training opportunities, business development services and market information. Existing industries and enterprises are also weak in terms of equipment and machinery they use, their capital base, and the skill level of their staff to operate and maintain machines. They also suffer from lack of inputs such as chemicals and spare parts. This reduces their overall efficiency and competitiveness in product markets.

- Fragmented Market Structure: The forestry sector in Ethiopia is characterized by a fragmented market structure with limited/ineffective coordination among actors, resulting in inefficiencies and reduced competitiveness. The lack of cohesive linkages between different market players hampers effective collaboration and value chain integration.

- Limited Access to Finance: Small and medium-sized enterprises (SMEs) within the forestry sector face significant barriers in accessing finance. This limitation inhibits their ability to invest in technologies and practices that could enhance productivity and sustainability. High perceived risks and the lack of collateral exacerbate these financial challenges.

- Inadequate Market Information: The absence of reliable, accessible market information and data impedes market actors' capacity to make informed decisions and respond effectively to market demands. The lack of comprehensive data collection and dissemination systems further complicates the dearth of market intelligence.

- Weak Institutional Capacities: Both public and private institutions involved in the forestry sector often lack the technical and organizational capacity required to support market development and sustainable forest management. Insufficient expertise, inadequate organizational structures, and limited resources undermine their effectiveness.

- Regulatory and Policy Barriers: Inconsistent and unclear regulatory frameworks create uncertainties for market actors, discouraging investment and innovation. Bureaucratic inefficiencies and a lack of policy clarity further impede sector growth and development.

- Environmental Degradation and unsustainable practices: Deforestation, land degradation, and unsustainable harvesting practices are prevalent, threatening the long-term viability of forest resources and ecosystem services. Overharvesting, illegal logging, and limited awareness of sustainable practices exacerbate these environmental challenges.

- Women and Youth disparities in the forest sector: Women and youth face numerous disadvantages that hamper their ability to engage in economic activity, particularly in rural areas. Overall, these disadvantages include limited access to information, decision-making power, and ownership rights to land and forest resources. For youth, specific challenges include lack of access to capital, markets, business development skills, suitable working spaces, education, training, and government support.

### 1.2.1 Analysis of Systemic Issues and Root Causes

Beyond understanding the key constraints, it is also vital to understand the root causes driving the underperformance of the Forestry Sector and how addressing these can help identify interventions that support the achievement of sustainable and inclusive green growth:

- Fragmented Market Structure: Lack of coordination mechanisms, inadequate infrastructure, and weak linkages between market actors.

- Limited Access to Finance: High perceived risks, lack of collateral, and limited financial products tailored to the forestry sector.

- Inadequate Market Information: Limited data collection and dissemination systems, lack of market intelligence services.

- Weak Institutional Capacities: Insufficient technical expertise, inadequate organizational structures, and limited resources.

- Regulatory and Policy Barriers: Inconsistent regulations, lack of clarity in policy implementation, and bureaucratic inefficiencies.

- Environmental Degradation and Unsustainable Practices: Overharvesting, illegal logging, and lack of awareness about sustainable practices.

- Gender and Social Inclusion Issues: Structural gender inequalities and social exclusion, limit access to resources and opportunities for women and local communities’ groups.

Phase 2 support for the forestry sector aims to build upon the foundational work and to enhance private sector engagement in developing forest products markets that work better for poor women and men, creating jobs and additional income opportunities for approximately 70,000 Ethiopians. The programme will address systemic barriers, creating an enabling environment for increased private sector engagement, enhancing institutional capacities, promoting gender equality and social inclusion, and integrating environmental sustainability. By addressing these challenges, the programme will contribute to Ethiopia’s broader development goals and the Sustainable Development Goals (SDGs), ensuring a comprehensive and impactful approach to forestry sector development.

# 2.	Justification for the Programme strategic approach

The justification for enhancing private sector engagement in developing pro-poor forest products markets in Ethiopia is grounded in a comprehensive understanding of the country's context, challenges within the forestry sector, and its potential for increasing livelihoods and job creation through inclusive green growth. This proposal leverages national strategies, global commitments, and lessons learned from the initial phase of the programme. By integrating insights from Ethiopia’s HGER and the Climate Resilient Green Economy (CRGE) strategy and aligning with Sweden’s development cooperation priorities on sustainable natural resource use, climate resilience, and inclusive economic development, the programme establishes a robust foundation for fostering increased private sector engagement and enhancing inclusive forest market systems. The strategic importance of the programme is further underscored by its alignment with the Sustainable Development Goals (SDGs) and the pillars of the National Forestry Sector Development Program (NFSDP).

- Centrality of Ethiopia's Forestry Sector for Inclusive Green Growth: Ethiopia’s forestry sector is pivotal to the country's development strategy, serving both economic and environmental objectives. The 10-year development plan (10YDP) for 2021-2030 emphasizes sustainable development through enhancing, maintaining, and protecting the country's natural environment, forests, wildlife, and biodiversity. The plan aims to increase national forest coverage from 15.5% to 30%, underscoring the sector's role in achieving environmental sustainability and resilience. The National Forest Sector Development Programme (NFSDP) for 2018-2028 projects significant Socio-Economic benefits, including a net present value of USD 30.8 billion and the creation of approximately 633,000 full-time jobs. Additionally, the programme is expected to generate USD 8.5 billion in carbon benefits and enhance the value of agriculture and other sectors by USD 3.2 billion due to reduced soil erosion and improved water retention.

- Foundations for Forest Products Market Development: The demand for forest products in Ethiopia is projected to increase by about 27% over the next 20 years, reaching an annual consumption of 158 million cubic meters by 2033. This growing demand necessitates addressing a supply gap of 4.4 million cubic meters of industrial roundwood. Ethiopia has approximately 26.80 million hectares of land suitable for new commercial forests and 190,000 hectares of state-owned plantations available for development or improved management. Developing about 310,000 hectares of well-managed new commercial forest plantations is essential to meet industrial wood demand and reduce imports. The country's diverse ecology supports various tree species and non-timber forest products (NTFPs) such as gum arabica, incense, honey, shade-grown coffee, beeswax, and bamboo, which have significant commercial value prospects.

- Private Sector Engagement and Partnerships: Ethiopia’s development strategy underscores the private sector as a key driver of economic growth, green jobs creation, and innovation. However, private sector involvement in forestry has been limited due to regulatory barriers, lack of access to finance, and insufficient market information flow from forest production to value addition and end-market demand. The lack of knowledge and skills along the value chains in the forestry sector further restricts potential benefits. Therefore, enhancing private sector participation and building partnerships are crucial for the development of sustainable forest product markets and fostering inclusive growth.

- Lessons Learned from the previous phase: Phase 1 of the forestry programme laid a firm foundation and demonstrated the potential for market-based interventions to enhance livelihoods and promote sustainable forest management. Key successes included establishing value chains for non-timber forest products (NTFPs) and capacity building for local institutions. Despite those successes, challenges remain in scaling up interventions and ensuring long-term sustainability. Lessons learned highlight the need for stronger and more demonstrable private sector engagement, improved policy coordination, and enhanced capacity for market development and governance.

- Addressing key constraints with innovative approaches: Ethiopia's forestry sector faces significant challenges, including limited private sector engagement, underdeveloped forest product markets, fragmented value chains, inadequate institutional capacity, and insufficient policy and regulatory frameworks. These challenges are compounded by gender inequalities, social exclusion, and environmental threats from climate change. To address these systemic constraints effectively, a hybrid approach combining Market Systems Development (MSD) and direct support interventions is essential. This strategy will therefore create an enabling environment for private sector engagement, enhance institutional capacities, promote gender equality and social inclusion, and integrate environmental sustainability.

## 2.1 Programme Alignment

- Alignment with Ethiopia’s Development Strategy: The programme aligns with Ethiopia's HGER and CRGE strategy, prioritizing sustainable natural resource management and inclusive economic development. The National Forestry Sector Development Programme emphasizes forest conservation and restoration, sustainable forest management, and enhancing forest-based livelihoods. Phase II will focus on promoting greater private sector engagement, improving market access, and building institutional capacities to generate livelihoods and jobs, particularly for women and youth.

- Alignment with Sweden’s Development Cooperation Reform Agenda: Sweden’s reform agenda emphasizes sustainable development, gender equality, and poverty reduction. The programme aligns with these priorities by promoting sustainable forestry practices, enhancing economic opportunities for local community’s groups, and supporting environmental conservation. Additionally, the programme contributes to Result Area 2 of Sweden’s Development Cooperation Strategy for Ethiopia (2022-2026), focusing on the sustainable use of natural resources and increased resilience to climate change, and Result Area 3, aiming to strengthen inclusive economic development through Market Systems Development (MSD) approaches.

- Alignment with the UNSDCF and UNDP CPD: The programme Theory of Change (Toc) aligns with the UNDP’s Country Programme Document (CPD) and the United Nations Sustainable Development Cooperation Framework (UNSDCF). By enhancing market systems and building institutional capacities, the programme contributes to UNSDCF outcomes related to sustainable natural resource management, inclusive economic development, and strengthened governance frameworks. UNDP CPD supports strengthened governance frameworks, fosters enabling conditions for expanded job creation by the private sector (especially SMEs), accelerates the transition to a green economy resilient to climate change, and embeds gender equality and women’s empowerment across all areas of work.

- Alignment with Global Commitments: The programme supports Ethiopia’s commitments to international frameworks such as the Sustainable Development Goals (SDGs), particularly Goal 5 (Gender Equality) Goal 15 (Life on Land), Goal 13 (Climate Action), and Goal 8 (Decent Work and Economic Growth) and SDG 17 (Partnerships for the Goals) . By aligning with these goals, the programme underscores its commitment to sustainable development and environmental conservation.

## 2.2 Programme Theory of Change

Programme Theory of Change that informed the Programme design is depicted as follows.

| Current Situation | Barriers | Key Activities | Barriers Addressed | Key Output | Impact |
| --- | --- | --- | --- | --- | --- |
| Negative trade balances in forest products Natural and planted forests are poorly managed. Forest-dependent communities receive limited benefits due to underdeveloped forest product markets. Private sector engagement in forestry is minimal. Limited access to finance, technology, and market information restricts the benefits for poor women and men, youth & local communities’ groups. These challenges are compounded by climate variability and change, which disproportionately affect the poor | Technical: - Underdeveloped forest product market systems - low capacity of market actors. Institutional: - Lack of coordinated mechanisms, - incoherent policies, - underdeveloped financial services. Social: - unemployment, - resource scarcity, - gender & youth inequality Financial: - Limited access to finance market information for smallholders and cooperatives | Outcome 1: Private sector engagement in forestry and development of pro-poor forest product market systems enhanced. |  |  | - Creation of green jobs and reduction of poverty. - Enhanced gender & youth equality & inclusion - Economic empowerment for local communities’ groups (women, youth etc). - Sustainable management of forests and biodiversity conservation. - Sustain flow of goods and environmental services - Clear legal and policy instruments and strong forestry institutions - Sustained private sector engagement and pro-poor market development. |
|  |  | - Assessment and Mapping: - Conduct comprehensive assessments of the performance and mapping of value chains for round wood tree seedlings and NTFPs. - Document market actors, their roles, and how these affect the availability, quality, and price of forest products. - Business Environment Analysis: - Analyse the business environment to identify roles for government agencies, donors, private sector, NGOs, and research institutions. - Identification of Leverage Points: - Identify drivers of change and leverage points for sustainable and scalable impact. - Improve gender equality through the participation of women and youth producers and processors | Technical Institutional Technical | 1.1. Market system of round wood, tree seedlings, and NTFPs mapped, analysed and binding constraints identified |  |
|  |  | - Joint Identification of Options: - Use the AAER framework to identify options, plan implementation, and measure systemic change in forest product markets. - Negotiation of Roles: - Negotiate roles and responsibilities of actors in implementing intervention options. - Value Addition and Business Development: - Improve access to value addition innovations and business development services for small-scale forest product processors and traders. - Introduce and support new business models for better livelihood outcomes. | Technical & Financial Institutional Technical & Financial | 1.2. Intervention options to bring about desired changes in round wood, tree seedlings, and NTFPs market systems selected and implemented, and performance monitored |  |
|  |  | Outcome 2: Enabling environment for private sector engagement in forestry and for developing more inclusive forest product market systems created. |  |  |  |
|  |  | - Review of Policy and Legal Instruments: - Review policy and legal instruments related to governance aspects of forest product markets. - Identify sectoral policy alignment, legal, and institutional gaps. - Proposal of Improvement Measures: - Propose improvement measures to support value addition and marketing of forest products. - Improve sectoral policy alignment and coordination among relevant sectors (land, investment, trade, forestry, finance). | Institutional Institutional | 2.1. Legal and institutional challenges limiting private sector engagement in forestry and participation of poor women and men in growing forest product market systems identified and improvement measures proposed |  |
|  |  | - Capacity Building: - Provide need-based capacity building (training) for government organizations supporting forest product markets. - Technical Capacity Enhancement: - Build the technical capacity of EFD in gathering, analysing, and sharing data on forest products and market actors. - Market Information and Business Development Services: - Improve access to market information, value addition innovations, and business development services for small-scale forest products processors and traders. - Support forest-based cooperatives and small-scale enterprises to increase the quality and quantity of forest products for domestic and international markets | Institutional Technical Technical & Financial | 2.2. Capacity of institutions to support private sector engagement in forestry and to develop pro-poor forest product market systems strengthened |  |

Barriers to be Addressed:

Enhancing private sector engagement in forestry and developing pro-poor forest products market systems requires careful identification and classification of factors that can be addressed within the time and resources (scope) of the programme and identification of those that would require longer time, more resources, and changes in the policy and legal framework. The programme will focus on the former category and may include the following:

| Category | Barriers to be Addressed |
| --- | --- |
| Technical | - Underdeveloped forest products market systems - Low capacity of market actors to produce more and quality products for markets |
| Institutional | - Lack of coordinated institutional mechanism to encourage private sector engagement in forestry and to support the development of pro-poor forest product market systems - Incoherent and poorly implemented policies, regulations on forest products collection, processing, and marketing - Under development of financial service institutions |
| Social | - unemployment, resource scarcity leading to conflict and youth migration - Limited access to markets, information, and alternative livelihood options - gender inequality, limited access to resources and education |
| Financial | - Little experience to improve access to finance and market information for players in forest products markets - Limited access to finance for smallholders and cooperatives engaged in commercial tree planting and in forest products processing and marketing |

If these barriers are not adequately addressed, the following consequences are anticipated:

- Engagement of the private sector in forestry remains limited.

- Forest product market systems would hardly develop.

- Poor men and women will continue to participate less in these markets.

- Opportunities to increase income from the forestry sector will be missed.

- Increasing income and gender inequalities, deepening marginalization of the poor, women, and girls.

In formulating this proposal UNDP has considered the “How and Why” the challenges in the forestry sector can be addressed in line with the SIDA Terms of Reference.

A critical examination of policy and legal instruments (including the land, forestry, and investment proclamations), along with engagement with the Chamber of Commerce, will identify gaps in policy and legal instruments and organizational behavior of relevant government institutions. Specific improvement measures will be proposed to attract and promote private sector involvement in forestry and forest product markets. Expanded private sector engagement creates job opportunities for the unemployed and livelihood diversification options for others (e.g., those involved in out grower schemes). Increased forest product market activity helps grow forest product markets. Collectors, assemblers, processors, traders, transporters, brokers, and others will benefit. Making growing forest products markets work for the poor (women and men) will be the main undertaking of the Programme.

Market Systems Development using a hybrid approach will be used to support markets based on their nature and needs. Standard MSD steps and procedures will be followed, focusing on binding constraints and adopting sustainable interventions, which are expected to significantly reduce poverty. Social and environmental safeguards will be observed to ensure interventions have positive social and environmental benefits. By addressing policy, legal, and institutional challenges that constrain poor men and women's engagement in and equitable benefit from forest product markets, improvement measures will be proposed to policy and decision-makers to scale good practices and sustain positive gains.

Programme Impact: As a result of these changes, more green jobs will be created, helping to reduce poverty, foster greater gender equality, and sustainably manage forests to enhance biodiversity conservation and sustain the flow of goods and environmental services. Clear legal and policy instruments and strong forestry institutions will sustain continued private sector engagement in forestry and ensure the expansion of more inclusive forest product markets in Ethiopia. Taken together these actions will create inclusive economic growth opportunities that address the needs of the private sector, the regulatory frameworks and the people centered development within the forestry sector.

# 3. Proposed goal and approach of the Programme

## 3.1 Overall Goal and Objective

The proposed overall Goal and Objective of the programme is as follows

Goal: To foster the development of a resilient and inclusive private sector ecosystem that promotes sustainable management and equitable marketing of forest products, particularly benefiting local communities, thereby contributing to poverty reduction, environmental conservation, and economic growth in Ethiopia.

The programme will build a vibrant and inclusive forestry sector that actively engages the private sector to significantly increase sector’s contribution to the national economy, creates green jobs and reduces poverty while enhancing biodiversity conservation and flow of environmental services and goods to better adapt to and mitigate climate change.

Objective: Is to enhance private sector engagement in forestry and develop pro-poor forest product markets (using market systems development approach) through leveraging the AAER framework that in turn would substantially improve livelihoods and decent work opportunities for at least 70,000 rural and peri-urban poor (mainly women and youth) through systemic change in market systems of a sustainably managed forestry sector.

This will be achieved through supporting actions including:

- Enhance the capacity of private sector actors, including small-scale producers, traders, cooperatives to engage in sustainable forest product marketing practices in Ethiopia.

- Strengthen institutional support systems and regulatory frameworks to create an enabling environment for private sector engagement in pro-poor forest products marketing, ensuring equitable access and fair-trade practices.

- Facilitate the development of market linkages, value chains, and distribution networks for pro-poor forest products, promoting inclusive economic opportunities and livelihood enhancement for local communities   in Ethiopia.

The sub-objectives that the Programme include:

- Increasing private sector engagement in forestry by addressing legal and institutional barriers like access to land, mechanisms to work with community-based organizations, etc.

- Increasing market access of poor women and men in the value chains of selected forest products by improving their access to extension services, market information, inputs, and strengthening their capacity and skills to effectively participate in and benefit from forest product markets

- Promoting sustainable forest management practices to ensure that market development activities would not lead to deforestation and forest degradation.

- Addressing gender-specific barriers and promoting equal opportunities for women and men and youth so as to foster gender equality and social inclusion.

- Strengthening enabling environments for attracting and private sector engagement in forestry and to developing pro-poor forest products markets. This sub-objective is expected to contribute to bringing about desirable change in the performance, stability, and adaptability of institutions in the forestry sector.

The programme will have two high level Outcomes:

Outcome 1: Private sector engagement in forestry and development of pro-poor forest product markets enhanced.

This outcome reflects a holistic approach to forestry management that prioritizes environmental conservation, socio-economic development, and poverty reduction, ultimately contributing to more resilient and sustainable forest ecosystems and livelihoods. The outcome, if achieved, will signify a significant advancement in sustainable forest management and economic empowerment, particularly for local communities in Ethiopia. By actively involving the private sector in forestry initiatives, there is a dual benefit of promoting environmental conservation while simultaneously fostering economic growth and poverty alleviation because of two important reasons.

Firstly, enhanced private sector engagement in forestry implies increased investment, innovation, and expertise directed towards sustainable forest management practices; and partnerships between private companies and local communities will lead to responsible forest products exploitation practices, reforestation efforts, and biodiversity conservation initiatives.

Secondly, the development of pro-poor forest product markets indicates a deliberate focus on ensuring that the benefits of forestry activities trickle down to the most vulnerable segments of society through initiatives such as capacity building for local communities to sustainably harvest and process forest products, as well as the establishment of fair-trade practices that ensure equitable compensation for their contributions. Other results include the creation of jobs, diversification of livelihood options, increased income for cooperatives and their members, which will incentivise the expansion of commercial plantation and reduction of pressure on natural forests. Additionally, the programme will focus on seedling raising, collection and marketing of gums, and resins market development -all of which are predominantly led by women; thus, contributing to gender equality.

Output 1.1 Market system for round wood, tree seedlings, and non-timber forest products mapped, analysed, and binding constraints identified. Adopting a structured approach to understanding and improving market dynamics in the forestry sector, the output includes mapping the market system to identify key actors (producers, traders, processors, and consumers), and their roles, relationships, and geographical distribution. The exercise will provide a comprehensive overview of the supply chain for round wood, tree seedlings, and non-timber forest products, highlighting existing market channels and potential areas for intervention. This will be followed by an analysis of various factors that influence market dynamics, such as demand and supply trends, price fluctuations, value chain efficiencies, and regulatory frameworks. The goal of the analysis is to identify opportunities for market expansion, value addition, and product diversification as well as pinpointing specific barriers or limitations within the market system that impede its efficient functioning and inhibit growth. Some of the obstacles could include inadequate transportation infrastructure, policy barriers, restrictive regulations, etc.

Output 1.2 Intervention options to bring about desired changes in round wood, tree seedlings, and non-timber forest products market systems selected and implemented. In output 1.1 the partners would have identified and systematically assessed the binding constraints and market dynamics to determine the most effective strategies for catalysing positive change. Output 1.2 focuses on implementation of the identified options. This entails careful planning, stakeholder engagement, and coordination to ensure that interventions are effectively executed to yield tangible results. Some of the activities will include pilot projects, policy trials, capacity-building workshops, and public-private partnerships engagement forums to scale up innovative solutions. Monitoring and evaluation mechanisms to track progress, measure impact, and make necessary adjustments will be put in place. By addressing identified constraints and leveraging opportunities, the Program will help foster sustainable economic growth, promote environmental conservation, and enhance livelihoods for forest-dependent communities.

Outcome 2: Enabling environment for private sector engagement in forestry and for developing pro-poor forest product market systems created.

Studies point at the policy and legal gaps as well as institutional limitations that hinder the engagement of the private sector in forestry and the development of prop-poor forest products markets in Ethiopia. This outcome will lead to the establishment of a conducive framework that fosters collaboration between the private sector, government, and local communities to promote sustainable forest management and inclusive economic growth.

This will include policy reforms, institutional capacity building, regulatory frameworks development, and expanding market incentives. Policies that incentivize private sector investment in forestry while ensuring environmental sustainability and social equity will be in place and enforced. Some of the facets that the policies would clarify include tax incentives for sustainable forestry practices, permit processes, and clear land tenure rights. Agencies responsible for forestry management will be strengthened and civil society including cooperatives and community-based organizations will have stronger partnership platforms that facilitate knowledge sharing and coordination. Regulatory frameworks critical to setting standards and guidelines for sustainable forest management and fair-trade practices, protecting the rights of local communities, and ensuring compliance with environmental regulations would be in place.  Furthermore, market linkages, value chain development, access to finance, and capacity building for small-scale producers will be created; thus, enabling local communities to participate more effectively in the forest economy. This will increase their income opportunities and livelihood resilience.  The success of this outcome requires a multi-stakeholder approach, strong governance structures, and targeted interventions to unlock the full potential of forests as a source of economic, social, and environmental benefits for all.

Output 2.1 Legal and institutional challenges limiting private sector engagement in forestry and participation of poor women and men in growing forest product market identified and improvement measures proposed.  The output underscores the importance of addressing legal and institutional barriers to promote inclusive participation and sustainable development in the forestry sector.  It will begin with a comprehensive analysis of existing policies, regulations, and governance structures that may hinder private sector engagement and limit the participation of local communities, especially women and men living in poverty. Some of the areas to analyse include unclear land tenure arrangements, cumbersome permitting processes, inadequate access to finance and technology, and gender disparities in decision-making and resource allocation. Once these are analysed, improvement measures for each of the barriers will be identified and prioritized. Implementation activities for each prioritized intervention measure will be undertaken.  Key activities will include advocating for policy reforms to strengthen land tenure rights and promote gender equality in forest governance; support relevant agencies to streamline regulatory procedures; undertake capacity building initiatives to enhance the skills and knowledge of local communities, particularly women and men living in poverty, to actively participate in forest product value chains.

Output 2.2 Capacity of institutions to support private sector engagement in forestry and to develop pro-poor forest product market systems strengthened. This output emphasizes the importance of building institutional capacity to effectively facilitate private sector involvement and promote inclusive market development in the forestry sector. It will include strengthening relevant government institutions and civil society organizations including cooperatives to provide support and services for sustainable forestry practices and market system development. The specific activities will include: training selected government institutions in formulating policies that support private sector engagement, promote sustainable forest management, and foster inclusive market systems; training and resourcing regulatory bodies to develop and enforce regulations that ensure sustainable resource use, fair trade practices, and equitable access to forest resources for all stakeholders, especially poor and local communities  women and men; technical assistance to forestry management institutions to lead market development, value chain promotion, forest inventory, certification, marketing, and product diversification; facilitating the development of partnership platforms for government, private sector, civil society, and community cooperatives to leverage resources, share expertise, and coordinate market development.

## 3.2. 	Approach of the Programme

Phase 2 will follow a hybrid approach that combines Market Systems Development Approach - to enhance private sector engagement in the forestry sector and in developing more inclusive  forest products markets; with (direct support) to create an enabling environment for private sector engagement and the development of pro-poor forest product markets through identifying gaps in policy and institutional aspects, and also in the enhancing the capacity of institutions (both state and non-state) that are engaged in the forest product markets systems. It is hoped that these approaches taken together will contribute to developing systemic institutional in the forestry sector.

A hybrid approach that the programme will follow aims at gradually and carefully adapting the MSD approach to be better able to respond to diverse/emerging contexts and circumstances that the forest products markets face in Ethiopia. A hybrid MSD approach maintains systems perspective in analysing the market - market demand, production constraints, inclusion and empowerment concerns, climate adaption concerns, and identification of requirements for system resilience. It then attempts to turn the market analysis into a clear evidence-based vision for system change and strategy that defines how the system will work long-term without donor support, the constraints and concerns identified above, and opportunities for system actors to address these. At this stage, the Programme team will evaluate whether or not supplementary interventions or direct delivery may be required in light of the constraints identified that need to be addressed and the expected lack of capacity of system actors.  Based on the above, the team will devise a strategy/portfolio of intervention in support of commercially sustainable business models, supplementary interventions or direct delivery can then be considered in line with the gaps identified. When administered, the accumulated change of this intervention portfolio is expected to result in an increasingly resilient and sustainable system.

The types of markets to work with will be defined better, during the inception phase, and will determine the way in which the Programme will use the MSD approach. The approach can also be used even in thin or shallow markets where simple short-term facilitation could be adopted.  Depending on the context a learning modality to MSD will be followed to promote systemic development with a focus on adaptation to emerging situations.

The Programme intends to use facilitated or hybrid MSD approach as the major vehicle to developing pro-poor forest product markets. But as attracting and expanding private sector engagement in forestry in ways that also contributes to achieving long-term ecological sustainability objectives, and developing forest product markets that are inclusive require strengthening enabling environment (in terms of legal and policy and legal instruments, institutional arrangement and capacity as well as organizational behaviour), the program will also invest in direct support interventions for institutional capacity development. Accordingly, it is anticipated that close to two third of the budget (~60%) of the Program budget will be allocated for MSD (facilitated) activities and the remaining 40% of the budget goes to direct support (systemic capacity development activities.

The hybrid approach helps the Programme to balance between two desirable but at times competing, criteria, namely, “greater adaptation to context” and “more facilitation and a systems perspective” (shown in the vertical and horizontal axis in the Figure below). The figure below on hybrid market systems development taken from the experience of MSD in Uganda shows how the Program plan to adopt a hybrid approach depending on the type of market systems the Program will be working on. It does not however mean that the Program will use simultaneously the two options (applying both direct support and MSD approaches) to address a given constraint in the market system. Each one of the two should follow the required evaluation and intervention option identification process. For example, in markets where direct support intervention is a way forward, due care will be made during the intervention design stage to make sure that this builds growth, adaptive capacity and resilience of the market system to socio-economic and climatic changes in the markets (re-enforcing systemic changes) and shall in no way to distort them.

Figure 4.  How to move from classic MSD to more adaptive systemic approaches. (Source : Hirst et al, 2022, page 3. Hybrid Market Systems Development to Reinforce System Resilience and Climate Preparedness: Results and Lessons Learned from Promoting Sustainable Potato Cultivation in Uganda).

The hybrid approach will enhance the programme focus on private sector development in forestry in ways that also contribute to long-term, ecological sustainability objectives (e.g., conservation of biodiversity); and on MSD identifying and addressing constraints that limit poor women and men from participating and equitably benefiting from growing forest product markets with due consideration of the prevailing political economy and the local context. Accordingly, the MSD approach to be used in developing market system of a selected forest product will be “moderated” considering local context such as socioeconomic and cultural setting, and if the existing markets are shallow, or if the facilitation capacity of actors in the market system is weak.

## 3.3. Thrust of the Programme

Building on achievements made during Phase I of the Program, and other related donor supported Programs. Experiences gained, and studies conducted during Phase I will inform the gaps that need to be completed during the first few months of Program implementation.

- Phase 2 of the Program is informed by and contributes to key national and sectoral policies, plans and strategies.

- Alignment with key one of the key thematic areas in the SIDA new reform agenda (Combating poverty through job creation, trade and education), and contribute to two of the Result Areas of Sweden’s on-going country support program (Result Area 2 and Result Area 3).

- The focus of the Program is in line with and directly contributes to all targets set in the Long-Term Low Emission Development Strategy (LT-LEDS) of Ethiopia that aims to significantly reduce poverty and make the economy carbon neutral by 2050.

- As multitude of constraints hinder the engagement of the private sector in the forestry sector and participation in and benefit from forest product markets of poor women, only the most limiting/binding constraints that can be addressed within the capacity (resource and time of the Program) and capability and interest of market actors will be identified and addressed.

- Given the diversity of markets to work with, the Program adopted a hybrid approach with the aim of achieving optimal integration of facilitated and direct support approaches to develop markets.

- Design and development of forest product markets is implemented using MSD Program Design Pyramid.

- The Programme will be implemented in two phases – an inception phase (about 3-4 months) and the implementation phase (three years). The former will be used to undertake a number of “deep dive” analyses including an informed selection of forest product markets with potential for reducing poverty, to refine the specific activities of the MSD component, and to develop details of the tasks to be accomplished during the implementation stage.

## 3.4. Increasing impact, taking good practices to scale, and enhancing sustainability

The activities of the Program will be designed and implemented in ways that will increase impacts for the target groups (the poor – both in number and magnitude of benefit per person), work in partnership with other actors to reach more people or area or forest product (i.e., to attain scale), and to take socio-economic and environmental safety measures to ensure sustainability of gains (i.e., market actors will continue to perform their roles after the Program end date).

## 3.5. Phases and planned activities

The Programme will be implemented in two distinct phases:

### 3.5.1. Inception Phase (3-4 months)

Key activities to be conducted in the phase include:

- Context analysis – In here we assess the economic environment (economic conditions of the country, focusing on the forest products sector-e.g., conducting a macroeconomic analysis of the region to understand GDP contribution from the forestry sector, employment statistics, and income levels among forest-dependent communities); review the policy and regulatory framework (existing laws, policies, and regulations affecting forest product markets); and identify and map key stakeholders (including government agencies, private sector actors, local communities, NGOs, and international organizations) and key players such as forest product processors, local traders, international buyers, NGOs working on conservation, and government agencies.

- Market analysis – This includes, among others, understanding the current demand for various forest products and the capacity of local supply chains (demand and supply analysis); and mapping the value chain of key forest products to identify and prioritize key constraints (gaps, inefficiencies) and pinpointing the root cause(s) of market underperformance and sub-optimal participation in the markets of the private sector and the poor), and identification and prioritization of potential leverage points or intervention options. The market analysis (their structure, dynamics and performance) is used to identify high-potential products and markets and undertake value chain analysis of the selected products - the entire process from harvesting to final sale, identifying critical points where value is added and potential bottlenecks.

Figure 5. Framework that will be used for markets to make them work better for the poor(Source: Albu, M. 2008, page 14)

- Finalizing the identification of binding constraints and leverage points for the selected products and detailing the specific activities to be accomplished in MSD, including:

  - In-depth market and value chain analysis within the selected forest product for Programme and intervention design and to establish Programme baseline data

  - Political economy analysis and conflict sensitivity analysis to ensure feasibility and to reflect the Leave No One Behind and Do No Harm principles

  - Environmental Impact Assessment /Social and Environmental Safeguards

- Design results matrix

- Design risk management matrix

- Develop a Programme monitoring and evaluation framework

- Finalize relationship setup within the Consortium

- Mapping of stakeholders of the forestry sector from the Federal to lower levels of the government will be completed. Engaging stakeholders requires putting in place strong and accountable coordination mechanisms that not only brings together stakeholders but also provides space to play their roles in determining the course of the Programme. This will result in a stakeholders’ engagement plan which will be reviewed throughout the life of the programme.

- The stakeholder mapping with key capacity gaps identified will be used to inform areas which need attention

- Build relationships with strategic partners already operating in the forestry sector in the forestry market system (with a view to leverage synergies)

- Set up management structures

- Prepare agreement documents as required to manage finance – e.g., matching grants or challenge funds or guarantee schemes

- Design detailed budget

- Develop a one-year work plan

- Develop annual planning tools

- Revise the Programme proposal to become the Programme Document that captures the detailed approaches, activities, and milestones to be achieved in the implementation phase.

- The project document will also have been circulated and consulted with key stakeholders and partners to ensure ownership and will include the agreed results framework, and budget allocations for the identified activities.

### 3.5.2.  Implementation Phase

Using the detailed analyses prepared in the Inception Phase the programme will move into implementation. Tasks include:

  - Developing the intervention strategy – A hybrid approach, which takes into account sustainable forest management, modern business practices, technologies, and market mechanisms, will be used to improve access to and efficiency of forest product markets. The key task is to draft a context specific plan that outlines objectives, key activities, timelines, and responsibilities to address identified gaps and leverage opportunities. The strategy should also pay attention to sustainability and inclusivity. It shall ensure that market development strategies promote sustainable forest management and conservation (environmental sustainability), and interventions need to be designed in a way to include local communities’ groups, such as women, indigenous communities, and smallholder farmers. The Programme will develop interventions specifically aimed at empowering women, youth and local communities’ groups in the forestry sector, an example being providing targeted training and microfinance opportunities for local communities groups. Monitoring plan will also be developed to serve as plan for monitoring progress and impacts of interventions.

  - Implementation of the strategy – The envisaged key activities in implementing the strategy include:

  - Capacity building through training and institutional strengthening - Provide training for local communities and businesses about sustainable forest management, business skills, and market access will form part of the intervention. The Programme will forge partnerships with local NGOs and universities to deliver training sessions. Relevant local institutions in the forest product market systems (e.g., cooperatives and producer organizations) will be supported to better negotiate prices and access markets.

  - Implementation of the support programme for entrepreneurs and final customers, with active participation also from stakeholders in the "enabling environment”.

  - The programme will Pilot proposed low-cost and competitive (quality/costs) small-medium scale technologies for sawing and drying in rural conditions in Ethiopia.

  - Building market linkages and infrastructure – The team will create partnerships between producers, traders, and buyers. Opportunities will be explored to invest in necessary infrastructure such as improving communications, storage facilities, and processing units (market infrastructure); and in developing systems to provide real-time market information to producers and traders (market information system).

  - Policy alignment and sectoral coordination. The Programme will propose measures to improve sectoral policy alignment and coordination among relevant sectors – land, investment, trade, forestry, finance, to promote private sector engagement in the forestry sector.

- Policy advocacy and reform – This involves working with policymakers to create an enabling environment through favourable policies and regulations (policy engagement), and advocate for incentives that promote sustainable forest management, penalize unsustainable practices (incentives for sustainable practices) and are more inclusive leading to greater economic empowerment.

- Monitoring and Adaptation: This is a step in MSD approach where the team will develop its monitoring and evaluation framework and plan for adaptive management.

  - Monitoring progress – This includes a baseline data collection protocol (to gather baseline data to measure the impact of interventions) and monitoring system (to undertake regular monitoring of market developments and the impact on local communities and forests).  Mobile surveys can be used to collect data on income changes, forest health, and market access before and after Program interventions.

  - Adaptive management – The team will set up channels for stakeholders to provide feedback on interventions on a regular basis. The adaptive management feedback mechanism that the team will use will ensure continuous feedback from stakeholders and ensure greater flexibility and adaptation in order to adjust strategies based on monitoring results and feedback.

  - Scaling up and replication: The Scaling up and replication work will draw on successful models/interventions, and knowledge sharing and networking interventions.

  - Scaling up – This starts with assessing the success of pilot programme interventions and identifying factors contributing to success. Then this will be followed up by replication strategy/guide/toolkits development to scale successful models/interventions to other areas/products.

  - Knowledge sharing and networking – The focus will be on sharing lessons learned and best practices through workshops, publications, and online platforms (knowledge dissemination), and on facilitating networking among stakeholders to foster greater collaboration and share experiences (networking).

  - Assessing impact and measuring results: In evaluating whether the  interventions are leading to desired systemic changes in the market system, or to assess if a more comprehensive picture of systemic development is emerging the team will check, for example in the case of tree growers cooperatives, how production inputs (e.g., seedlings, equipment, capital investment, land, labour, etc.) are provided along with business services (e.g., financial services, technical services, business development services, information services, logistics, labour services/skill development) and the Business enabling environment (formal and informal institutions regulating economic activity, e.g., laws/regulation, polices, representation and voice, social norms, informal networks) are improving; and as a result markets are supplied with competitive products that are in demand and fetch a fair price.  Such a process is conducted to assess “productivity function” for systemic development assuming that competitive products and services will be produced when producers have access to the appropriate production inputs, services, rules, and regulations. Throughout the life of the programme disaggregated data will be gathered to assess the direct impact on women, youth and other local communities’ groups.

The Programme will also carry out cross-cutting activities such as specific studies (to gather missing information, further market analysis to help identify intervention options, to map and analyse stakeholders, etc.), M&E and measuring results, knowledge management, facilitating co-learning amongst market players, Programme evaluation, etc. These activities are needed both in the “facilitated” and “direct delivery” approaches. The Programme budget will consider the cross-cutting activities to respond to the need for targeted support related to for example gender and social inclusion.

# Operationalization of the Programme

## 4.1 	Programme design and targeted forest products

The MSD Program Design Pyramid will be organizing framework in planning and operationalizing interventions. Below are descriptions of planned activities for developing pro-poor markets for forest products selected by EFD.  The information in the PDM for each product has been drawn from studies conducted thus far and from experiences gained during Phase I.  Hence, a revised version will be produced by consortium partners after the inception phase as additional information will be available. During the inception phase, list of candidate private sectors will be produced for each product market, and a qualified MSD expert will be brought on board by IDE to engage in the market analysis work (in collaboration with CIFOR and SLU) and to identify and prioritize leverage points and to actively engage in implementing interventions. The objective, target group, geography, main constraints, proposed interventions, business models, partners, sub-facilitators, and markets are proposed below, and they will be refined more during the inception and the earlier phases of the implementation phases.

### 4.1.1. Promoting quality tree seedling production by youth and women

One of the markets selected to be developed and having significant potential to job creation and poverty reduction is the production of quality tree seedlings by youth and women. Afforestation begins with good quality seedling production in tree nurseries, which is currently done mainly by agricultural or forestry offices of the government but could also be undertaken by women’s or youth organizations. The production of seedlings from native trees takes between 8 and 14 months, depending on the tree species (the seedlings for fruit trees and coffee plants stay in the tree nursery for 1.5 to 2 years). In this way, the preparatory work such as setting up seedbeds, mixing humus and making shade covers begins each year in autumn. From December onward, the seeds are sown in plastic pots where they grow into young plants over the following months. During the growing period, these seedlings are watered, weeded and shaded. At the beginning of the rainy season (often in June in most of the central highlands), the plants are ready to be planted, and indigenous species are often planted on the mountain slopes and on the hills. Most work in tree nurseries is done by the women, who thus receive a valuable income. At the same time, when there are no seedlings to cultivate in the tree nurseries during the rainy season, these women and the women groups also engage in other works such as weaving or cultivating vegetables.

The demand for seedlings has skyrocketed following the Green Legacy Initiative, and seedling raising has created job opportunities for many. Last year national standards for nurseries and seedlings have been set, and the Program aims at introducing these standards for those who will be engaged in seedling production as a business, and significantly increase availability of quality seedlings in desired number and quantity by supporting youth and poor men and women to be engaged in seedling production.

| Promoting quality tree seedling production by youth and women |  |
| --- | --- |
| Objective | To organize unemployed youth and women to establish private tree nurseries that will produce quality seedlings and wood for markets |
| Target group | un-employed women and youth in rural and peri-urban areas. The activity will create job and income for 3,000 youth and women. |
| Geography | Adama (in Oromia) and Kombolcha in Amhara Regional State |
| Main constraints | There is a noticeable lack of awareness among youths and women about the viability of tree seedling production as a green business. Additionally, those who recognize its business potential often face challenges due to insufficient technical capacity, limited access to land, and lack of financial resources. |
| Proposed interventions | -Technical Capacity Building: Train youth and women in advanced nursery management techniques, business management, entrepreneurship and market analysis. -Provide nursery inputs so that they can start off the activity. -Acquisition of quality seeds is crucial for quality seedling production. In Ethiopia, accessing quality seeds is a challenge. Therefore, linking the organized youths and women with quality seed sources will be one of the essential activities. -Market Linkage Development: Create platforms for interaction between seedling suppliers and potential buyers, including government bodies, non-governmental organizations, and private landowners. -Innovation and Technology Transfer: Tree nurseries need fertile soil mix. These days it’s a challenge to get fertile forest soil. Hence, introduction of alternative soil improvement technologies (e.g.: organic fertilizer) is imperative, irrigation solutions are also essential to apply the required amount of water on time. -Business development and management, and access to finance -Land acquisition. |
| Business models | -identified actors: EFD; Organized Un-employed Youths and Women; Regional and district level Land Administration and Use Bureaus; Regional and district level Microfinance Institutions; Wondo Genet College of Forestry and Natural Resource; Regional Tree Seed Centers; Commercial Tree Growers, Innovative Finance Lab of UNDP, CIFOR, SLU and IDE. -Roles and responsibilities: EFD will be responsible for the overall implementation of the activity; the youths and women will be the main actors of the activity; regional and district level land Administration and Use Bureaus will avail land; Regional and district level Microfinance Institutions will facilitate access to finance for the youths and Women; Wondo Genet College of Forestry and Natural Resource will provide the technical training on nursery establishment and management; and Innovative Finance Lab of UNDP will provide training on business development, management, and entrepreneurship and facilitate access to finance; CIFOR in collaboration with IDE will undertake the market analysis and IDE will implement activities on the ground to develop efficient and inclusive market systems for tree seedlings; Regional Tree Seed Centers will be linked to provide quality tree seeds; Commercial Tree Growers will be identified and linked to seedling growers to receive produced seedlings. -Incentives: Job Creation/reduce unemployment; Quality tree seedling product, enhance quality of forest development (Tree) |
| Partners | Federal and local governments to facilitate land acquisition and finances; tree seed producers, tree seedling buyers, training centres, etc. |
| Sub-facilitators | The detailed work activity classification and responsibilities among the different implementing partners will be finalized during the inception period. This collaborative process will allow the project team to clearly define the roles and contributions of each partner organization. |
| Markets | organized un-employed youths and women |

### 4.1.2.	Improving production and marketing of gums and resins from dry forests

Another sub-sector selected for market system development by the Program, with significant potential for job creation and poverty reduction, is the production of quality gums and resins by cooperatives. Dry forests comprise the largest forest resources in Ethiopia. Their contribution to rural livelihoods, the national economy and ecosystem stability is significant, although not yet properly accounted for. An important feature of Ethiopia’s dry forests is their richness in Acacia, Boswellia and Commiphora species. These trees are the source of gums and gum resins, which are the most important export commodities of the Ethiopian forestry sector. During the past decade, the total export volume and foreign currency earnings from gums and gum resins have increased. However, it is important that this increase in the volume of products is accompanied by inclusion and benefit of poor forest dependent communities with concomitant responsibility for sustainable forest management.

| Improving production and marketing of gums and resins from dry forests |  |
| --- | --- |
| Objective | Cooperatives in dry forest sites and in dry forests |
| Target group | Gum and resin producing cooperatives. This activity is expected to benefit 7000 beneficiaries. The location of districts and number of cooperatives to be included will be determined during the inception phase. |
| Geography | Somali (number of districts and cooperatives will be identified during inception phase) |
| Sub-sectors/system: | marketing |
| Main constraints | technology (standardized extraction technology as per the species), market linkage with buyers |
| Proposed interventions | - Introduction of improved technologies and practices: Train cooperatives on gums and resins production techniques, business management, market analysis - Certification of established cooperatives, securing land ownership by cooperatives - Establish connection with potential buyers (supermarkets and export to abroad). - Link with potential exporters (private and government entities) - Market Linkage Development: Create platforms for interaction between gums and resins potential buyers, and private investors - Innovation and Technology: standardized extraction technologies - Business development (proper grading; storage) and access to finance |
| Business models | - identified actors: EFD; Cooperatives Commission; Regional and district level Land Administration and Use Bureaus, Ministry of Trade and Regional Integration (branding and exporting), Chamber of Commerce, Regional and district level Microfinance Institutions; Innovative Finance Lab of UNDP, CIFOR, SLU and IDE - Roles and responsibilities: EFD will be responsible for the overall implementation of the activity; Cooperatives commission will facilitate the organization of cooperatives and issuance of certificates; Ministry of Trade and Regional Integration (branding and exporting) and Chamber of Commerce will facilitate linking with exporters, Regional and district level Microfinance Institutions will facilitate access to finance; Innovative Finance of UNDP will provide training on business development, management, and entrepreneurship and facilitate access to finance; CIFOR in collaboration with IDE will undertake the market analysis and IDE will implement activities on the ground to develop efficient and inclusive market systems for gums and resins. - Incentives: Income generation; Sustainable environmental restoration (vegetation cover, biodiversity, spill over effect), penetrate new market targets, boost export, technology transfer. |
| Partners | Federal and local governments to cooperative establishment and access to finance; gum and resin producers, exporters etc. |
| Sub-facilitators | The detailed work activity classification and responsibilities among the different implementing partners will be finalized during the inception period. This collaborative process will allow the project team to clearly define the roles and contributions of each partner organization. |
| Markets | Cooperatives |

### 4.1.3.	Improving the marketing of round wood

Ethiopia consumes more than 130 million m3 of round wood equivalent (RWE) annually, of which 92.3% is used as wood fuel and the remaining in the form of construction materials, lumber, wooden panels, utility poles, and other goods with added value (MEFCC, 2018). Ethiopia's economic growth, rising population, expanding urbanization, and thriving construction industries are all contributing to the country's continually increasing need for wood products. Ethiopia has over one million hectares of plantations (20% public industrial plantations and 80% private or community woodlots). But these plantations are unable to sustainably fulfil the country's demand for wood products (MEFCC, 2018). Moreover, they are overgrown, poorly managed, and of low production (Tadesse et al., 2019). In 2013, the round wood supply gap was already at 1.8 million cubic meters, and it is projected to escalate to 4.4 million cubic meters by 2033. The escalating demand, expected to reach 13.9 million cubic meters RWE by 2040, further exacerbates the situation.

There is a big disparity between domestic demand and supply for wood products, forcing the country to rely heavily on imports and depleting its foreign exchange reserves. To meet the growing industrial wood demands, the country imports wood products various industrial wood products totalling 3.006 million m3 worth around USD 182.53 million in 2015 alone, and the trend of imports is rising.  In fact, between 2007 and 2015, it has more than doubled (MEFCC, 2018). MEFCC (2018) reports show that imports do not satisfy more than 30% of the country's industrial wood demand. Teshome (2021) predicts that insufficient investments in forest plantations (rate of increase for the current plantations is less than 2%) is really low and will result in a growing supply imbalance for wood products and a related trade deficit.

Figure 5: The proposed system to develop the round wood market in Ethiopia (to be developed during the inception phase)

The collection, transportation, and marketing of round wood face several market challenges. The reliance on imports negatively impacts on the trade balance and presents significant hurdles for local producers attempting to compete in the market. Hence, information needed for MSD Program Design Pyramid for developing markets of roundwood is presented below.

| Improving the marketing of round wood |  |
| --- | --- |
| Objective | to establish an MSD for round wood harvested from AR sites |
| Target group | Commercial Tree growers |
| Geography | Meket, Dessie Zuria, Alaje, Endamohoni, Sodo Gurage, Mirab Abaya, Assela, Wolemera these districts are known for their commercial tree production. The activity is expected to generate additional income and create jobs for 40,000 beneficiaries. |
| Sub-sectors/system: | processing |
| Main constraints | technology for value addition and access to finance |
| Proposed interventions | - Commercial tree producers frequently encounter difficulties in obtaining high-quality seedlings. As a result, establishing strong connections with reputable seedling producers is crucial. - Market Linkage Development: Create platforms for interaction between wood suppliers and potential roundwood buyers. - Connect with wood processing industries (e.g., chip wood) and state forest enterprises - Innovation and Technology Transfer: Introduce small scale wood processing machines for value addition. - Business development, and access to finance |
| Business models | - identified actors: EFD; Regional and district level Microfinance Institutions; State Forest enterprises; Wood Products Manufacturing Industries; Innovative Finance Lab of UNDP, CIFOR, SLU and IDE - roles and responsibilities: EFD will be responsible for the overall implementation of the activity; state forest enterprises and wood products manufacturing industries will be linked with roundwood producers to directly receive the roundwood from cooperatives. Innovative Finance of UNDP will provide training on business development, management, and entrepreneurship and facilitate access to finance; CIFOR in collaboration with IDE will undertake the market analysis and IDE will implement activities on the ground to develop efficient and inclusive market systems for gums and resins. - Incentives: create income; Quality roundwood product, enhance quality of forest development (Tree), skill and technology transfer, trigger policy change (on tax and access to finance) |
| Partners | Federal and local governments to facilitate land acquisition and finances; roundwood producers, state forest enterprises, wood products manufacturing industries, etc. |
| Sub-facilitators | The detailed work activity classification and responsibilities among the different implementing partners will be finalized during the inception period. This collaborative process will allow the project team to clearly define the roles and contributions of each partner organization. |
| Markets | Wood producing cooperatives |

### 4.1.4 Improving production and marketing of honey and other products from forests and restoration sites

Ethiopia is one among the major producers of honey in Africa with its varied ecological and climatic conditions. The country is amongst the major honey producers and consumers in Africa, though data are lacking, significant volume of honey consumed and marketed is obtained from forests and rehabilitated landscapes through are ex-closures.  The honey production provides a secondary source of income for smallholder farmers, who traditionally depend on forests and framing activities. Though the country is known to huge potential to produce hundreds of thousands of tons of honey, production levels are under 40,000 tons per annum. Apiculture has not developed so much so that over 95% the hives used in the country are traditional and low producing hives. Limited access to technology, market information and to buyers due to poor linkage is particularly severe for smallholder honey producers from forests and rehabilitated landscapes. The Program will conduct through market analysis, learn from previous efforts and identify and address binding constraints to make honey and other forest products markets work better for the poor.

Similarly, information needed for MSD Program Design Pyramid for developing markets of honey and other products such as grass form forested and/or restored landscape is presented below.

| Improving production and marketing of honey and other products from forests and restoration sites |  |
| --- | --- |
| Objective | To establish farmers cooperatives on restoration sites |
| Target group | Farmers cooperatives on ANR sites |
| Geography | Meket, Dessie Zuria, Alaje, Endamohoni, Sodo Gurage, Mirab Abaya, Assela, Wolemera these districts have well developed restoration sites. This activity is expected to benefit 20,000 beneficiaries. |
| Sub-sectors/system: | Collection/production |
| Main constraints | technology (modern beehive with honey separator, improved grass/fodder species, packaging), market linkage with buyers. |
| Proposed interventions | - Introduce modern beehives with its accessories and packaging technologies. - Establish connection with potential buyers (supermarkets and export to abroad). - Link honey producers with potential exporters (e.g., with Athlete Haile Gebreselassie) - Market Linkage Development: Create platforms for interaction between grass and honey producers and potential buyers, and private investors (fattening and dairy). - Innovation and Technology Transfer: Introduce improved grass species, honey separator, packaging. - Business development and management, and access to finance |
| Business models | - identified actors: EFD; Cooperatives Commission; Regional and district level Land Administration and Use Bureaus, Ministry of Trade and Regional Integration (branding and exporting), Chamber of Commerce, Regional and district level Microfinance Institutions; Innovative Finance Lab of UNDP, CIFOR, SLU and IDE. - roles and responsibilities: EFD will be responsible for the overall implementation of the activity; Cooperatives commission will facilitate the organization of the farmers into cooperatives and issuance of certificates; Regional and district level Land Administration and Use Bureaus will transfer the use right of the sites to the cooperatives, Ministry of Trade and Regional Integration (branding and exporting) and Chamber of Commerce will facilitate linking with exporters, Regional and district level Microfinance Institutions will facilitate access to finance; SLU/Eco-innovation and Innovative Finance Lab of UNDP will provide training on business development, management, and entrepreneurship and facilitate access to finance; CIFOR in collaboration with IDE will undertake the market analysis and IDE will implement activities on the ground to develop efficient and inclusive market systems for gums and resins.. - Incentives: Income generation; Sustainable environmental restoration (vegetation cover, biodiversity, … spill over effect), penetrate new market targets, boost export, technology transfer. |
| Partners | Federal and local governments to facilitate cooperative establishment and access finances; honey and grass producers, exporters etc. |
| Sub-facilitators | The detailed work activity classification and responsibilities among the different implementing partners will be finalized during the inception period. This collaborative process will allow the project team to clearly define the roles and contributions of each partner organization. |
| Markets | Cooperatives |

### 4.1.5.  Producing and marketing briquettes from Prosopis juliflora

Prosopis juliflora is a shrub or small tree in the family Fabaceae, a kind of mesquite that is exotic to Ethiopia. It has become an invasive plant in many parts of the country especially in Afar taking tens of thousands of hectares of grazing land. The project will promote the management of this invasive through utilization by converting the biomass into briquettes and by so doing creating jobs and improve livelihoods of people and productivity of the lands.

| Producing and marketing briquettes from Prosopis juliflora |  |
| --- | --- |
| Objective | To produce briquettes for markets by cooperatives of producers in Afar region |
| Target group | Agropastoral communities in Afar regions |
| Geography | Selected districts in Afar Region. This activity is expected to benefit 1500 beneficiaries. |
| Sub-sectors/system: | Collection, processing and marketing |
| Main constraints | technology (adoptable briquettes producing machines) packaging and market linkage with buyers. |
| Proposed interventions | - Introduce modern briquettes producing machines with its accessories and packaging technologies. - Establish connection with potential buyers (supermarkets and export to abroad). - Link honey producers with potential exporters - Market Linkage Development: Create platforms for interaction between producers and potential buyers - Business development and management, and access to finance |
| Business models | - identified actors: EFD; Cooperatives Commission; Regional and district level Land Administration and Use Bureaus, Ministry of Trade and Regional Integration (branding and exporting), Chamber of Commerce, Regional and district level Microfinance Institutions; Innovative Finance Lab of UNDP, CIFOR, SLU and IDE. - roles and responsibilities: EFD will be responsible for the overall implementation of the activity; Cooperatives commission will facilitate the organization of the farmers into cooperatives and issuance of certificates; Regional and district level Land Administration and Use Bureaus will transfer the use right of the sites to the cooperatives, Ministry of Trade and Regional Integration (branding and exporting) and Chamber of Commerce will facilitate linking with exporters, Regional and district level Microfinance Institutions will facilitate access to finance; Innovative Finance Lab of UNDP will provide training on business development, management, and entrepreneurship and facilitate access to finance; CIFOR in collaboration with IDE will undertake the market analysis and IDE will implement activities on the ground to develop efficient and inclusive market systems for gums and resins. - Incentives: Income generation; Sustainable environmental restoration (vegetation cover, biodiversity, spill over effect), penetrate new market targets, boost export, technology transfer. |
| Partners | Federal and local governments to facilitate cooperative establishment and access finances; honey and grass producers, exporters etc. |
| Sub-facilitators | The detailed work activity classification and responsibilities among the different implementing partners will be finalized during the inception period. This collaborative process will allow the project team to clearly define the roles and contributions of each partner organization. |
| Markets | Cooperatives |

# 5. 	Programme Management

## 5.1.	Programme management principles

The Program will be managed in such a way that it is implemented in a cost-effective and timely manner, promotes focus on results and adherence to best management principles to ensure that key stakeholders are engaged, binding constraints have been identified and intervention options implemented to enhance private sector engagement in forestry, and in promoting pro-poor forest markets.  As is the procedure of MSD, stakeholder engagement and putting in place feedback mechanism will be part of the management to facilitate learning and adopt adaptive management. As per the Management Response provided for the terminal evaluation of ISCFSD training on RBM will be provided for all partners to improve the timing and quality of periodic reports for Donors.  Furthermore, budgeted monitoring and evaluation prepared and annexed in the annex section. Result Framework which contains base lines, targets and indicators has also been prepared and annexed.

## 5.2	Stakeholders’ Engagement and Partnerships

### 5.2.1.	Stakeholders’ Engagement

Key stakeholders in the forestry sector from the Federal to lower levels of the government will be encouraged and supported to take part in the implementation of the Programme. Engaging stakeholders requires putting in place strong and accountable coordination mechanism that not only brings together stakeholders but also provides space to play their roles in determining the course of the Programme by having their say during key decision-making processes. The coordination especially at Federal and Regional level will be designed and resources will be allocated to this effect. It will be supported by the technical assistance it would get on demand from the responsible parties to the IP (CIFOR and SLU) and IDE for MSD. EFD, through its national delivery unit will ensure coordination among actors and between national and international partners.

### 5.2.2.	Partnerships

Drawing on lessons learnt from Phase I partnerships already established with stakeholders will be used and further refined to better respond to the needs of Phase II, especially in the context of the MSD component.  Throughout the life of the programme efforts will be made to ensure complementarity with other initiatives of the government, other Development Partner projects, NGOs, and communities in order to avoid duplication and maximize synergies which will help broaden the impact of the programme. The Swedish Embassy in Ethiopia, UNDP Country Office and EFD will provide overall strategic guidance and support to ensure smooth implementation. CIFOR, SLU and IDE will provide Programme delivery support, and active engagement in implementation of activities as defined in the project document. Taken together this will assist in overall performance management/ monitoring activities to ensure that the innovative, iterative approach of the programme remains effective and efficient.

UNDP, through the use of its global network of logistical support and access to specialists, will lead the consortium to ensure that best value for money and timely delivery of programme interventions in line with the agreed AWP are achieved. CIFOR, SLU and IDE as consortium partners will play their respective roles Phase II of the programme. Areas of responsibilities of CIFOR and SLU include ensuring the depth and quality of the market analysis work, identification of binding constraints in the market systems development component as well as the policy and legal aspects, undertaking gaps assessment and engaging in building capacity of actors, and providing support in identifying and procuring the forest products processing technologies and in delivering entrepreneurship skills training. IDE will be leading the work on the ground to develop the market systems for the identified forest products.

The criteria considered in selecting and engaging consortium partners include:

- Capacity to achieve objectives of the Programme, monitor, evaluate and learn:

- Organizational structure and management

- Resources and competences to achieve the objectives - monitoring method; competence, resources, structures and incentives for learning and adaptation.

- Competence, resources and structures for risk management and risk assessment.

- forwarding of funds.

- Capacity to ensure adequate internal control, including routines, competences and resources to ensure adequate financial management.

- the quality of the two most recent audit processes - responses and recommendations in the audit reports and management letters.

- procurement regulations.

- SIDA s audit requirements.

- Capacity to collaborate with the private sector, most importantly, capacity in the context of implementing MSD programs and interventions.

## 5.3.	 Programme Implementation Arrangements

### 5.3.1.	Roles and responsibilities of UNDP

UNDP will be the lead facilitator in the consortium. The Programme will be implemented following UNDP’s Supported National Implementation Modality in line with the Standard Basic Assistance Agreement between UNDP and the Government of Ethiopia, and the Country Programme. UNDP will be responsible for all aspects of Programme quality assurance, ensuring implementation is in accordance with the UNDP rules and procedures.

UNDPs Innovative Finance Lab (IFL) will also support the programme implementation in the provision of support to Forest Cooperatives for the identified forest products in areas related to product development, market linkage and analysis, financial management and ensuring impact and sustainability in their operations. Furthermore, IFL will provide tailored trainings and capacity enhancing measures to market players to ensure that they are equipped with key business fundamentals required in their operations. Through the knowledge sharing unit, the IFL will engage with market players and actors for the identified products to address key policy and institutional issues that affect private sector participation in the forestry sector.

The IFL using its experience of working with public and private financial institutions including the Development Bank of Ethiopia and other commercial banks and micro-finance institutions will facilitate access to finance – loans and grants to forestry cooperatives. The UNDP Finance Hub based in Istanbul shall also provide technical support to unlock the potential of the private sector to engage actively in Market System Development. One of the priorities of the Hub is to help to unlock private finance for the SDGs acceleration.

### 5.3.2.	Roles and responsibilities of Ethiopian Forestry Development

EFD is the programme Implementing Partner.  The Implementing Partner is responsible and accountable for managing this Programme, including the monitoring and evaluation of Programme interventions, achieving Programme outcomes, and for the effective use of UNDP and SIDA resources as set out in the agreed AWP. EFD is responsible for reviewing and approving Programme content and relevance to the country and for identifying and engaging implementing partners of the Programme. Accordingly, EFD has identified as Responsible Partners Center for International Forestry Research (CIFOR) and Swedish University of Agricultural Sciences (SLU) and International Development Enterprise (IDE) to assist in the design and implementation of the Programme.

## 5.4.	Organization and contractual agreements

Phase 2 of the SIDA support will be set out in a Third-Party Cost Sharing agreement between UNDP and Sweden.  UNDP will be a lead agency (Facilitator) having the flexibility of forming a consortium for the purpose of expanding the implementation capacity by pooling together the necessary skills and experiences required to meet the needs of the Programme. UNDP will be responsible for coordinating the activities of all partnerships and contractual agreements, including those for market facilitation as per the rules and regulations of UNDP. In addition, UNDP will draw on its global presence and expertise to undertake the capacity building activities of the Programme. EFD and UNDP will work closely with Ministry of Finance (MoF) and in collaboration with other Responsible Partners for monitoring Program implementation, ensure timely progress reporting to SIDA.  UNDP will also provide institutional and capacity building support to EFD in its effort to promote sustainable forest products market development.

Based on Annual Workplans to be developed by EFD and UNDP, CIFOR and SLU will sign Letter of Agreement with EFD. UNDP will engage the International Development Enterprise (IDE) as Market System Development Partner (MSD) through signing of Responsible Party Agreement. Intervention activities will involve market actors such as PFM cooperatives, SMES, and government agencies. UNDP will ensure all actors have the capacity to deliver the programme objectives.  UNDP as the lead of the consortium will promote genuine commitment and technical coherence in pursuit of the programme objectives. Within the proposed Programme approach, UNDP will have the responsibility and freedom to explore and negotiate other partnerships and contractual arrangements which will require different agreement considerations. Throughout the implementation of the programme UNDP will ensure that gender and social inclusion issues are woven into all programme activities and seek to foster relationships with local citizen groups and CSOs relative the programme focus and the forestry sector.

## 5.5. Programme governance

The overall Program coordination and implementation will be managed by the Ethiopian Forestry Development of the Ministry of Agriculture. The implementation will follow the Supported National Program Implementation Manual (SPIM) approved by the GoE and the Supported National Implementation Modality (SNIM) rules and regulations of UNDP.

The Programme will establish a Programme Advisory Board (PAB) to be chaired by EFD with UNDP as Co-Chair and members drawn from relevant organizations. Stakeholders that can make a significant contribution to the Program implementation will be invited to join and would include representatives from federal and regional authorities, research institutions, the donor community and the private sector and their associations. The key responsibilities of the PAB are to provide overall support and strategic guidance for the Programme, such as to review progress, facilitate the Programme’s business enabling environment work and coordination, but possibly also to get feedback for learning about MSD and possible policy development.

The Programme will have a Programme Coordination Office (PCO) which will lead the Programme on a day-to-day basis, under the oversight of the Director General of EFD.  The PCO will work closely with other line Ministries, MoF, UNDP, CIFOR, SLU and IDE. The functions of the PCO will include, but not limited to, coordinating the implementation of the Program, ensuring the proposed Program approaches of market systems development (MSD) are rigorously followed, ensuring that beneficiary needs and expectations are being met or managed; risks are being controlled; the Program  remains viable; internal and external communications are working; quality management procedures are properly followed; and that the SC decisions are followed, and revisions are managed in line with procedures laid down in the PIM.

## 5.6. Coordination

Several institutions are expected to play role in implementing the proposed Programme with MSD approach. Their roles and responsibilities will be refined during the Inception phase.  UNDP will lead recruitment and coordination role within the consortium of partners. UNDP will formalize and coordination efforts with stakeholders both within and outside the formal consortium. Once formalized, the roles and responsibilities coordination efforts can be undertaken independently between sub-Facilitators and stakeholders outside the consortium.

# 6.	Knowledge Management, Learning and Communication

The knowledge management and learning strategy for the programme is designed to ensure continuous improvement, inform policy decisions, and contribute to the global discourse on sustainable forestry. By capturing, disseminating, and applying knowledge effectively, the programme will not only enhance its own implementation but also provide valuable insights and innovations that can be replicated and scaled across Ethiopia and beyond. This comprehensive approach to knowledge management and learning will ensure that the program achieves its objectives and creates lasting, positive impacts. Specifically, the Programme will document the process and outcome of its MSD work, including sharing experiences widely using various targeted communication tools and facilitate learning and enhance capacity in what will be a new area of work in Ethiopia.  There will be particular attention to facilitate and provide opportunities for experience sharing and nurturing of the cross fertilization of good practices. This type of knowledge collection, analysis, publication, and sharing will form an important part of all the programme and careful documentation of proceedings and lessons emerging from implementation will be shared with all stakeholders. Particular attention will be made to ensure that the knowledge products are inclusive including translation into major local languages and made accessible to people with disabilities. The products will also increase visibility of implementing and development partners notably SIDA and UNDP.

# 7. 	Monitoring and Evaluation

The robust Monitoring and Evaluation framework for the programme will ensure effective tracking of progress, accountability, and continuous improvement. By integrating systemic change considerations, the M&E framework supports the adaptive management necessary to achieve sustainable and inclusive impacts in Ethiopia’s forestry sector. This comprehensive approach to M&E will ensure that the program remains responsive to changing contexts and delivers meaningful, long-lasting results.  The Results framework for the programme will be refined during the inception phase and will form the basis for monitoring programme implementation progress and for evaluating impact. The Programme will be monitored in accordance with UNDP’s programming policies and procedures.

# 8.  	Reporting and Auditing

## 8.1.	Reporting

All fund recipients shall submit periodic activity based financial reports. EFD shall submit quarterly financial reports to UNDP which in turn will submit financial reports to SIDA. For activities that it directly manages and implements, UNDP shall include these in its comprehensive report to SIDA. Thus, the donor will receive annual consolidated plan and financial reports from UNDP as the lead of the consortium. UNDP will ensure that all financial management and procurement activities are conducted in accordance with UNDP’s procurement and financial management policies and procedures.

## 8.2	Auditing

The Programme will be audited according to UNDP rules and regulations for Supported Nationally Implemented Programs and according to the rules and regulations of the donor.

# 9. 	Replicability, Sustainability and Exit Strategy

## 9.1	Replicability

The Programme is designed to further consolidate and build on achievements of Phase I.  The Programme will undertake activities and create knowledge management about MSD that will help to facilitate wider use of the approach and experiences gained in developing markets for other forest products in more areas producing similar forest products. The Programme will also document lessons learnt and share them internationally. Thus, replication at the international level is also envisaged. To the extent possible, the Programme will share its experience with other Programmes and forest products markets developers so that good practices can be replicated in other Programmes in Ethiopia and elsewhere.

## 9.2.	Sustainability

When implementing the MSD approach, the approach itself requires that the Programme takes measures to ensure that changes in the marketings systems continue well after the end of the Programme. Hence sustainability will be central to the implementation of the Programme. Elements of economic sustainability (ensuring that the poor derive demonstrable  economic benefits), social sustainability (inclusive participation of particularly the poor, women and girls, unemployed youth, and disadvantaged groups; transparent and participatory/inclusive  decision-making processes to reduce conflicts; etc.) and institutional sustainability (building ownership by market actors, capacity strengthening, etc.) will be reflected in the design and implementation of all  interventions in addition to environmental sustainability (i.e., private sector engagement and market expansion would not lead to further resources degradation).

## 9.3.  Exit Strategy

The exit strategy of the Programme will be articulated better during the inception phase.  The focus will be on putting in place measures that will sustain Programme impacts, ensure ongoing engagement of the poor in growing forest product markets) after the Program ends in 2027. Key aspects of this will be create incentives for market actors in terms of increased benefit so that they will continue to maintain t the proposed changes in the market system, continue building the capacity of market actors (including support service providers and regulators) to play their roles and fostering partnerships that will advocate to increase coverage/scale and impact of growing forest products markets, and ensuring that the markets continue to operate efficiently. Fostering partnerships (with forest-based coops, private sector companies, financial institutions and relevant government agencies), creating market linkages and building capacity of market actors, notably the poor, to access services such as technologies and market information will help them to continue to build their capacity to negotiate and continue to equitably benefit from growing forest product markets.

# 10.	Safeguards and Risks

## 10.1	Environmental and Social Safeguards

Legal instruments are in place, and this shows the commitment of the GoE to ensure sound environmental and social impact management of its Programs. The country has adopted Environmental and Social Safeguards Framework (ESSF) which complies with international standards (e.g., the World Bank). The Programme will adhere and apply the national environmental and social safeguards mechanism so that it fulfils all safeguard requirements. The way it is designed the Program is expected to substantially and positively to social and environmental benefits.  Social benefits of the Programme include its intended plan to support and promote the active participation of local communities, women, and minorities in forest product markets. Gender equality and women’s rights will be central to the planning and implementation of all interventions. Integrating women’s voices in the planning and assessment of interventions and hence their interests are integrated in the Program is critical to ensure sustainability of gains to be made.  In addition, the project will implement site specific environmental and social assessment and prepare mitigation management plan and undertake monitoring of management plan implementation. To this effect required budget has been allocated as shown in the budget table.

## 10.2. Risks Analysis and Mitigation Options

The comprehensive risk management framework for the programme will ensure that potential risks are systematically identified, assessed, and mitigated. By integrating regular follow-ups and adaptive management into the project’s implementation plan, the program is well-equipped to handle uncertainties and challenges, ensuring resilience and sustainability. This proactive approach to risk management will help safeguard the program’s objectives and deliver long-lasting, positive impacts in Ethiopia’s forestry sector. The initial risk analysis and management plan is built on experiences gained from Phase 1. Given the country context the single most important external risk to implementation is expected to be security, and a fluid political and economic situation, which remains fragile. It is hoped that security related challenges will improve over time. During the inception phase the risk management matrix will be revised to better reflect the on the ground situation that the programme will need to navigate.

Specific indicative risks relative to the Programme include.

| Risks | Probability of risk (high, medium, low) | Potential impacts (low, moderate, severe) | Mitigation measures |
| --- | --- | --- | --- |
| Shallow market analysis leading to interventions that will distort markets | Medium | Severe | The selection of organization to be involved in MSD work will be done carefully, and CIFOR provides oversight and quality control (adequacy of market analysis and selection of binding constraints and intervention options) |
| Weak coordination of relevant sector offices | Medium | Moderate | Early and continuous engagement of key institutions, clarification of objectives and negotiating tasks |
| Low political will and low capacity to enforce exists legal instruments to attract private sectors to engage in forestry and to regulate forest product | Medium | Moderate | Continuous engagement of key institutions, clarification of objectives and negotiating tasks |
| Absence of land use policy and plan creating competition to access land | High | Severe | Engage in advocacy and support efforts to have national land use policy and plan |
| Inadequate institutional capacity to support commercial forestry | Medium | Moderate | Build and sustain capacity and capability of experts & institutions in the forestry sector |
| Limited opportunities for women and youth to take part in forest-based business | Medium | Moderate | Identify and promote forest friendly business opportunities and link producers with the private sector |
| Limited access to land and finance for private sector investment in forest development | High | Severe | Identify and address legal, institutional, and administrative hurdles that hinder engagement of the private sector in forestry |

# 11.	Budget

The total cost of the Programs is 75.7 million SEK, of which 65 million is expected from SIDA and 10.7 million SEK (one million USD) is from UNDP. Contribution from SIDA is expected to be disbursed in instalments of 25 MSEK, 30 MSEK, and 10 MSEK. An illustrative budget is included which can be further elaborated during the inception phase.

Programme budget distribution (in SEK)

| List of outcomes | List of Outputs | 2025 (SEK) | 2026 (SEK) | 2027 (SEK) | Total (SEK) |
| --- | --- | --- | --- | --- | --- |
| Outcome 1. Private sector engagement in forestry and development of pro-poor forest product markets enhanced | Output 1.1: Market system of round wood, tree seedlings and NTFPs mapped, analyzed, and binding constraints identified | 2,711,712 | 3,254,054 | 1,084,685 | 7,050,451 |
|  | Output 1.2: Intervention options to bring about desired changes in forest product market systems selected and implemented and results monitored | 10,846,848 | 13,016,218 | 4,338,739 | 28,201,805 |
| Outcome 2. Enabling environment for private sector engagement in forestry and for developing pro-poor forest product market systems created | Output 2.1. Legal and institutional challenges limiting private sector engagement in forestry and the participation of poor women and men in growing forest product market systems identified and improvement measures proposed | 2,711,712 | 3,254,054 | 1,084,685 | 7,050,451 |
|  | Output 2.2. Capacity of institutions to support private sector engagement in forestry and to develop pro-poor forest product markets strengthened | 6,327,328 | 7,592,794 | 2,530,931 | 16,451,053 |
| Cross Cutting Activities | Cross Cutting Activities | - | 1,200,000 | 1,100,000 | 2,300,000 |
| Project Admin, |  | 1,380,000 | 1,656,000 | 552,000 | 3,588,000 |
| Monitoring and Evaluation |  | 920,000 | 1,104,000 | 368,000 | 2,392,000 |
| UNDP GMS |  | 5,200,000 |  |  | 5,200,000 |
| Grand Total |  | 31,247,600 | 32,227,120 | 12,209,040 | 75,683,760 |

# Multi-Year Work Plan

All anticipated programmatic and operational costs to support the project, including development effectiveness and implementation support arrangements, need to be identified, estimated and fully costed in the project budget under the relevant output(s). This includes activities that directly support the project, such as communication, human resources, procurement, finance, audit, advisory policy, quality assurance, reporting, management, etc. All services which are directly related to the project need to be disclosed transparently in the project document.

| EXPECTED OUTPUTS | PLANNED ACTIVITIES | Planned Budget by Year (SEK) |  |  |  | RESPONSIBLE PARTY | PLANNED BUDGET |  |  | REMARK |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2025 | 2026 | 2027 | Total |  | Funding Source | Budget Description | Amount SEK |  |
| Outcome 1: Private sector engagement in forestry and development of pro-poor forest product markets enhanced |  |  |  |  |  |  |  |  |  |  |
| Output 1.1. Market system of roundwood, tree seedlings & NTFPs mapped, analyzed, and binding constraints identified | Activity 1.1.1 Organize training in MSD for consortium partners, analyzing performance of forest products market systems, and identifying binding constraints | 1,898,303 | 2,277,964 | 759,321 | 4,935,588 | EFD 50% | Sweden | 1 = 987,063 (40%); 2 = 1,480,595 (60%) | 2,467,658 |  |
|  |  |  |  |  |  | CIFOR 30% |  | 1 = 592,238 (40%); 2 = 888,357 (60%) | 1,480,595 |  |
|  |  |  |  |  |  | iDE 20 % |  | 1 = 394825 (40%) 2 = 592238 (60%) | 987,063 |  |
|  | Activity 1.1.2 Identify leverage points to make marketing systems pro-poor and to attract private sector engagement | 813,514 | 976,216 | 325,405 | 2,115,135 | EFD 50% | Sweden | 1 = 317,270 (30%) 2 = 740,298 (70%) | 1,057,568 |  |
|  |  |  |  |  |  | CIFOR 50% |  | 1 = 317,270 (30%) 2 = 740,298 (70%) | 1,057,568 |  |
|  | Sub total output 1.1 | 2,711,712 | 3,254,054 | 1,084,685 | 7,050,451 |  |  |  | 7,050,840 |  |
| Output 1.2. Intervention options to bring about desired changes in forest product market systems selected and implemented and | Activity 1.2.1 Develop the market systems of selected forest products using AAER framework | 7,375,857 | 5,870,314 | 3,470,991 | 16,717,162 | EFD 80% | Sweden | 1 = 2,674,746 (20%); 2 = 6,686,865 (50%); 3 = 4,012,119 (30%) | 13,373,730 |  |
|  |  |  |  |  |  | iDE 15% | UNDP | 1 = 501,515 (20%) 2 = 1,253,787 (50%) 3 = 752,272 (30%) | 2,507,574 |  |
|  |  |  |  |  |  | UNDP 5% | Sweden | 2 = 250,757 (30%) 3 = 585,101 (70%) | 835,858 |  |
| Output 1.2. (continues) Intervention options to bring about desired changes in forest product market systems selected and implemented and results monitored | Activity 1.2.2 Manage interventions and monitoring the process and outcome of interventions. | 2,169,370 | 2,603,244 | 867,748 | 5,640,361 | EFD 50% | Sweden | 1 = 564,036 (20%) 2 = 2,256,144 (80%) | 2,820,180 |  |
|  |  |  |  |  |  | iDE 15% |  | 1 = 253,816 (30%) 2 = 592,238 (70%) | 846,054 |  |
|  |  |  |  |  |  | SLU 15% |  | 1 = 507,632 (60%) 2 = 169,211 (20%) 3= 169,211 (20%) | 846,054 |  |
|  |  |  |  |  |  | UNDP 20% | UNDP | 2 = 338,422 (30%) 3 = 789,651 (70%) | 1,128,072 |  |
|  | Activity 1.2.3 International Travel For Experience Sharing | 488,108 | 507,632 |  | 995,741 | UNDP 50% | UNDP | 2 = 497,870 (50%) | 497,870 |  |
|  |  |  |  |  |  | CIFOR 50% | Sweden | 2 = 497,870 (50%) | 497,870 |  |
|  | Activity 1.2.4 Conducting high level policy dialogue | 813,514 |  |  | 813,514 | CIFOR 100% | UNDP | 2 = 569,460 (70%) 3 = 244,054 (30%) | 813,514 |  |
|  | Activity 1.2.5 Setting Up Matching Grant / Challenge Fund |  | 4,035,027 |  | 4,035,027 | CIFOR 100% |  | 1 = 807,005 (20%) 2 = 807,005 (20%) 3 = 2,421,016 (60%) | 4,035,027 |  |
|  | Sub-total Output 1.2 | 10,846,848 | 13,016,218 | 4,338,739 | 28,201,805 |  |  |  | 28,201,805 |  |
| Sub-total Outcome 1. |  | 13,558,560 | 16,270,272 | 5,423,424 | 35,252,256 |  |  |  | 35,252,256 |  |
| Outcome 2: Enabling the environment for private sector engagement in forestry and for developing pro-poor forest product market systems created |  |  |  |  |  |  |  |  |  |  |
| Output 2.1. Legal and institutional challenges limiting private sector engagement in forestry and the participation of poor women and men in growing forest product market systems identified and improvement measures proposed | Activity 2.1.1 Identify gaps in policy and legal instruments, institutional settings, and sectoral coordination to attract private sector engagement and to facilitate MSD for selected forest products | 1,355,856 | 1,627,027 | 542,342 | 3,525,226 | CIFOR 50% |  | 1 = 528,782 (30%) 2 = 1,233,829 (70%) | 1,762,613 |  |
|  |  |  |  |  |  | SLU 30% |  | 1 = 326,601 (30%); 2 = 217,734 (20%); 3 = 544,335 | 1,057,568 |  |
|  |  |  |  |  |  | EFD 10% |  | 1 = 105,757 (30%) 2 = 246,766 (70%) | 352,523 |  |
|  |  |  |  |  |  | iDE 10% |  | 1 = 105,757 (30%) 2 = 246,766 (70%) | 352,523 |  |
|  | Activity 2.1.2 Propose improvement measure to attract private sector engagement and to facilitate efforts to make forest product markets work better for the poor and women | 1,355,856 | 1,627,027 | 542,342 | 3,525,226 | CIFOR 50% |  | 1 = 528,784 (30%) 2 = 881,306 (50%) 3 = 352,523 (20%) | 1,762,613 |  |
|  |  |  |  |  |  | SLU 30% |  | 1 = 317,270 (30%) 2 = 211,514 (20%) 3 = 528,784 (50%) | 1,057,568 |  |
|  |  |  |  |  |  | EFD 10% |  | 1 = 105,757 (30%) 2 = 176,261 (50%) 3 = 70,505 (20%) | 352,523 |  |
|  |  |  |  |  |  | iDE 10% |  | 1 = 105,757 (30%) 2 = 176,261 (50%) 3 = 70,505 (20%) | 352,523 |  |
|  | Subtotal for Output 2.1 | 2,711,712 | 3,254,054 | 1,084,685 | 7,050,451 |  |  |  | 7,050,451 |  |
| Output 2.2. Capacity of institutions to support private sector engagement in forestry and to develop pro-poor forest product markets strengthened | Activity 2.2.1 Undertake gaps assessment of market actors and regulators | 1,265,466 | 1,518,559 | 506,186 | 3,290,211 | CIFOR 50% | Sweden | 1 = 822,552 (50%); 2 = 822,553 (50%) | 1,645,105 |  |
|  |  |  |  |  |  | EFD 20% | UNDP | 1 = 203,218 (30%); 2 = 460,629 (70%) | 658,042 |  |
|  |  |  |  |  |  | iDE 20% | Sweden | 1 = 329,021 (50%); 2 = 329,021 (50%) | 658,042 |  |
|  |  |  |  |  |  | SLU 10% |  | 1 = 65,804 (20%) 2 = 98,706 (30%) 3=164,511 (50%) | 329,021 |  |
|  | Activity 2.2.2. Engage in need-based and actor-center capacity building activities | 5,061,862 | 6,074,235 | 2,024,745 | 13,160,842 | EFD 20% | UNDP | 1 = 789,650 (30%) 2 = 1,842,518 (70%) | 278,688 |  |
|  |  |  |  |  |  |  | Sweden |  | 2,353,480 |  |
|  |  |  |  |  |  | CIFOR 50% | Sweden | 1 = 1,974,126 (30%) 2 = 4,606,295 (70% | 4,580,421 |  |
|  |  |  |  |  |  |  | UNDP |  | 2,000,000 |  |
|  |  |  |  |  |  | iDE 20% | Sweden | 1 = 789,650 (30%) 2 = 1,842,518(70%) | 2,632,168 |  |
|  |  |  |  |  |  | SLU 10% |  | 1 = 394,852 (30%) 2 = 131,608 (10%) 3= 789,651 (60%) | 1,316,084 |  |
|  | Subtotal for Output 2.2 | 6,327,328 | 7,592,794 | 2,530,931 | 16,451,053 |  |  |  | 16,451,053 |  |
| Subtotal for Outcome 2. |  | 9,039,040 | 10,846,848 | 3,615,616 | 23,501,504 |  |  |  | 23,501,504 |  |
| Outcome 3: Cross Cutting activities |  |  |  |  |  |  |  |  |  |  |
| Cross Cutting activities | Communication and Knowledge Management |  | 400,000 | 600,000 | 1,000,000 | UNDP 50% | UNDP | 1 = 150,000 (30%) 2 = 100,000 (20%) 3 = 150,000 (30%) | 500,000 |  |
|  |  |  |  |  |  | CIFOR 50% |  | 1 = 150,000 (30%) 2 = 100,000 (20%) 3 = 150,000 (30%) | 500,000 |  |
|  | Environmental and Social Safeguard |  | 500,000 |  | 500,000 | UNDP 100% | UNDP |  | 100,000 |  |
|  | Mid-term Evaluation |  | 300,000 |  | 300,000 | UNDP 100% |  |  | 300,000 |  |
|  | Terminal Evaluation |  |  | 500,000 | 500,000 | UNDP 100% |  |  | 500,000 |  |
| Project administration |  | 1,380,000 | 1,656,000 | 552,000 | 3,588,000 | EFD 42% | Sweden | PM Admin | 1,423,31 |  |
|  |  |  |  |  |  | CIFOR 35% |  | PM Admin | 1,208,503 |  |
|  |  |  |  |  |  | iDE 15% |  | PM Admin | 500,316 |  |
|  |  |  |  |  |  | SLU 8% |  | PM Admin | 276,465 |  |
|  |  |  |  |  |  | UNDP 5% |  | PM Admin | 179,400 |  |
| Monitoring and Evaluation |  | 920,000 | 1,104,000 | 368,000 | 2,392,000 | EFD 42% | Sweden | M&E | 948,877 |  |
|  |  |  |  |  |  | CIFOR 35% |  | M&E | 805,669 |  |
|  |  |  |  |  |  | iDE 15% |  | M&E | 333,544 |  |
|  |  |  |  |  |  | SLU 8% |  | M&E | 184,310 |  |
|  |  |  |  |  |  | UNDP 5% |  | M&E | 119,600 |  |
| Project Staff Salary (UNDP, Federal and District staffs) |  | 1,150,000 | 1,150,000 | 1,150,000 | 3,450,000 | EFD | Sweden | Salary | 750,000 |  |
|  |  |  |  |  |  | CIFOR |  | Salary | 1,350,000 |  |
|  |  |  |  |  |  | UNDP |  | Salary | 1,350,000 |  |
| UNDP GMS |  | 5,200,000 |  |  |  | UNDP | Sweden | GMS | 5,200,00 |  |
| Grand Total SEK |  | 31,247,600 | 32,227,120 | 12,209,040 | 75,683,760 | EFD |  |  | 26,836,584 |  |
|  |  |  |  |  |  | CIFOR |  |  | 23,499,498 |  |
|  |  |  |  |  |  | IDE |  |  | 9,169,807 |  |
|  |  |  |  |  |  | SLU |  |  | 5,067,071 |  |
|  |  |  |  |  |  | UNDP |  |  | 11,110,801 |  |
| *Note on budget description: 1 = Personnel (Staff time, Consultant, Salary, Wages); 2 = Fieldwork, travel, workshop; 3 = Procurement (Goods and Services) |  | **25 MSEK (38%) on 1st year; 30MSEK (46%) on 2nd year; & 10 MSEK (15%) on 3rd year |  |  | *** The exchange rate for converting USD to SEK is 10.687 and for converting SEK to USD is 0.0936 reported by https://www.bloomberg.com/quote/USDSEK:CUR on October 31,2024 |  |  |  |  |  |

# 13.	Legal Context

This program document shall be the instrument referred to as such in Article 1 of the SBAA between the Government of Ethiopia and UNDP, signed on 6 February 1981. Consistent with the Article III of the Standard Basic Assistance Agreement, the responsibility for the safety and security of the implementing partner and its personnel and property, and of UNDP’s property in the implementing partner’s custody, rests with the implementing partner.  The implementing partners shall put in place an appropriate security plan and maintain the security plan, considering the security situation in the country where the project is being carried, and assume all risks related to the implementing partner’s security, and implementation of the security plan.

UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of this agreement. The implementing partners agree to undertake all reasonable efforts to ensure that none of the funds received pursuant to the Programme Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999).

## Results framework of the Programme

Intended Outcome as stated in the UNSDCF/Country [or Regional] Programme Results and Resource Framework: UNSDCF OUTCOME: By 2025, all people in Ethiopia live in a society resilient to environmental risks and adapted to climate change. UNSDCF OUTCOME: By 2025, all people in Ethiopia benefit from an inclusive, resilient, and sustainable economy.

UNSDCF Outcome indicators as stated in the Country Programme [or Regional] Results and Resources Framework, including baseline and targets: - Unemployment rate (urban), by sex26 (Goal 8.5.2) - Baseline (2018):19.1% (urban), Target 10% - 27% (Female) Target: 20% - 12.7% male , Target 7%

CPD Output 2.2 Marginalized groups, particularly the poor, women, persons with disabilities and displaced are empowered to access entrepreneurship services and financial and non-financial assets and services to build productive capacities and benefit from sustainable livelihoods and jobs. [modified IRRF 1.1.2]

Applicable Output(s) from the UNDP Strategic Plan: SP output 4.2 Public and private investment mechanisms mobilized for biodiversity, water, oceans, and climate solutions.

Programme title and Quantum Programme Number: Sustainable Private Sector in Forestry Programme – SPSF

| EXPECTED OUTPUTS | OUTPUT INDICATORS | DATA SOURCE | BASELINE |  |  | TARGETS (by frequency of data collection) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Value | Year | Year 1 |  | Year 2 | Year 3 | Year 4 |  | FINAL |
| Outcome 1 Private sector engagement in forestry and development of pro-poor forest product markets enhanced. | 1.1 Percentage/number of target women and youth who gain improved access to livelihood support services and markets due to sustainably managed forest sector. | Annual assessment reports, IPs reports and progress reports |  | 2023 |  |  | 35,000 | 35, 000 |  |  | 70,000 rural and peri urban poor mainly women and youth |
|  | 1.2 Proportion / number of private sector Enterprises/ MSMEs engaged in pro-poor forest product marketing/Tree seedling, Honey, Gum, and resins/ | IPs reports and progress reports |  | 2023 |  |  | TBD |  |  |  | TBD |
|  | 1.3 Number of green jobs created for women and youth (in forest cooperatives; commercial tree plantations, new productive forests) | IPs reports and progress reports |  | 2023 |  |  | TBD |  |  |  | TBD |
|  | 1.4 Hectare of land reclaimed due to Programme intervention | IPs reports and progress reports |  | 2023 |  |  | TBD |  |  |  | TBD |
| Outcome 2. Enabling environment for private sector engagement in forestry and for developing more inclusive forest product market systems created. | 2.1 Number of legal and institutional systems implemented for the creation of pro-poor forest product markets | IPs reports and progress reports |  | 2023 |  |  | TBD |  |  |  | TBD |
|  | 2.2 Number of pro-poor forest products for which markets are created (Tree seedling, Honey, Gum and resins) | Programme progress report |  | 2023 | 4 |  |  |  |  |  | 4 (Tree seedling, Honey, Gum, and resins |
|  | 2.3 Number of forest-based co-operatives accessing finance and markets | Programme progress report |  | 2023 | TBD |  |  |  |  |  |  |
| Output 1.1: Marketing system of round wood, tree seedlings, and NTFPs mapped, binding constraints identified, and intervention options selected | 1.1.1 Number of round tree seedling, honey, gum, and resins value chains analysis reports produced | Programme progress report |  | 2023 |  |  | 4 |  |  |  | 4 |
|  | 1.1.2 Number platforms established for interaction b/n producers and potential buyers/market linkage/information | Programme progress report |  | 2023 |  |  | TBD |  |  |  | TBD |
|  | 1.1.3 Number of youth and women with enhanced awareness on BDS | Programme progress report |  | 2023 |  |  | TBD |  |  |  | TBD |
| Output 1.2: Intervention options to bring about desired changes in round wood, tree seedlings, and NTFPs market systems selected and implemented, and performance monitored | 1.3.1 Number of value chain actors implementing identified value chain interventions | IPs reports and progress reports |  | 2023 |  |  | TBD |  |  |  | TBD |
|  | 1.3.2 Number of women and youth engaged in forest product IGAs | IPs reports and progress reports |  | 2023 |  |  | TBD |  |  |  | TBD |
|  | 1.3.3 Number of forest-based cooperatives engaged in commercial plantation | IPs reports and progress reports |  | 2023 |  |  | TBD |  |  |  | TBD |
| Output 1.3 Legal and institutional challenges limiting private sector engagement in forestry and participation of poor women and men in growing forest product market systems identified and improvement measures proposed | 1.1 1. Number of legal and institutional systems developed/updated for the creation of pro-poor forest product markets | Programme progress report |  | 2023 |  |  | TBD |  |  |  | TBD |
|  | 1.1.2 Number of value chain actors’ staff with enhanced awareness on legal and institutional systems developed/updated (disaggregated by sex) | Programme progress report |  | 2023 |  |  | TBD |  |  |  | TBD |
|  | 1.1.3 Percentage reduction in deforestation of natural forests | IPs reports and progress reports |  | 2023 |  |  | TBD |  |  |  | TBD |
| Output 2.1. Legal and institutional challenges limiting private sector engagement in forestry and participation of poor women and men in growing forest product market systems identified and improvement measures proposed | 2.1.1Number of legal and institutional systems/frameworks /mechanisms developed/revised for value addition and marketing of forest products for domestic and international markets | Programme progress report |  | 2023 |  |  | TBD |  |  |  | TBD |
|  | 2.1.2Number of value chain actors’ staff with enhanced awareness on legal and institutional systems developed/updated for value addition and marketing (disaggregated by sex) | Programme progress report |  | 2023 |  |  | TBD |  |  |  | TBD |
| Output 2.2 Capacity of institutions to support private sector engagement and to develop pro-poor forest product markets strengthened | 2.2.1 Extent of improvement of the capacity of institutions to develop pro-poor forest product markets. . 1= Low 2= Medium 3= High | Annual assessment reports, IPs reports and progress reports |  | 2023 |  |  | TBD |  |  |  | TBD |

## Proposed governance & management structure of the Programme

Program Steering Committee

Sida

Responsible parties to EFD (CIFOR and SLU)

UNDP – Program Management facilitator & Programme quality assurance

EFD (Chair) and UNDP (Co-chair)

Sub-facilitators and other key stakeholders with influence on market performance (Coops, MFIs, ..)

Relevant sectors, other related Programmes and development partners working on developing markets.

National program coordination unit at EFD

Regional Program Coordination Units

Geographical area/market system actors

(Permanent actors in the forest product market systems)

## Monitoring plan of the Programme

| Monitoring Activity | Purpose | Frequency | Expected Action | Partners | Cost (if any) |
| --- | --- | --- | --- | --- | --- |
| Track results progress | Data showing progress towards results indicators will be collected and analysed to undertake timely monitoring of Programme progress to produce planned outputs and achieve stated results. | Quarterly, or in the frequency required for each indicator. | Slower than expected progress will be addressed by Programme management. | UNDP, EFD, CIFOR, IDE and SLU | To be budgeted in the program management |
| Monitor and manage risk | Identify and monitor specific risks that may threaten achievement of intended results and take mitigation measures using a risk log. UNDP’s Social and Environmental Standards will be audited in accordance with UNDP’s audit policy to manage financial risk. | Quarterly | Risks are identified by Programme management and actions are taken to manage risk. | UNDP, Sweden Embassy and EFD | To be budgeted in the program management |
| Learn | Knowledge, good practices and lessons will be captured regularly, &those from other Programmes will be synthesized and actively integrated into annual plans of the Programme. | Annually | Relevant lessons are captured by the Programme team and used to inform planning & management decisions. | UNDP, EFD, CIFOR, IDE.,SLU, Sweden Embassy | Budgeted in the Multi Year Plan |
| Annual Programme Quality Assurance | The quality of the Programme will be assessed against UNDP’s quality standards to identify Programme strengths and weaknesses and to inform management decision making to improve planning, Programme progress and performance. | Annually | Areas of strength & weakness will be reviewed by Programme management and used to inform decisions to improve Programme performance. | UNDP and Sweden Embassy | Budgeted in the Multi Year Plan |
| Review and Make Course Corrections | Internal review of data and evidence from all monitoring actions to inform decision making. | Annually | Performance data, risks, lessons and quality will be discussed by the Programme board and used to make course corrections. | UNDP, Sweden Embassy, EFD, and other partner organizations | Budgeted in the Multi Year Plan |
| Programme Report | Progress report will be presented to the Programme management and key stakeholders to show progress and share results achieved against pre-defined annual targets at the output level, the annual Programme quality rating summary, an updated risk along with mitigation measures, and any evaluation or review reports prepared over that period. | Annually, and at the end of the Programme (final report) | Aims to draw lessons to improve performance during the Programme period, to ensure sustainability of positive impacts, and to design even better Programmes in the future | UNDP, CIFOR, SLU. IDE and EFD | Budgeted in the Multi Year Plan |
| Programme Review (Programme Board) | The Programme’s governance mechanism (i.e., Programme management) will hold regular Programme reviews to assess the performance of the Programme and review the Multi-Year Work Plan to ensure realistic budgeting over the life of the Programme. In the Programme’s final year, the Programme Management shall hold an end-of Programme review to capture lessons learned and discuss opportunities for scaling them out and up and to socialize Programme results and lessons learned with relevant audiences. | The Programme board will meet at least once annually | Any quality concerns or slower than expected progress should be discussed by the Programme board and management actions agreed to address the issues identified. | UNDP, CIFOR, SLU, IDE, EFD, and Sweden Embassy | Budgeted in the Multi Year Plan |

## Proposed evaluation plan of the Programme

| Evaluation Title | Partners (if joint) | Related Strategic Plan Output (purpose) | UNDAF/CPD Outcome | Planned Completion Date | Key Evaluation Stakeholders | Cost and Source of Funding |
| --- | --- | --- | --- | --- | --- | --- |
| Mid-Term Evaluation | Sweden Embassy, UNDP and EFD | Midterm evaluation conducted to see if change of course is needed or not to attain Programme objectives | Managerial decisions are taken to improve progress of the Programme during the second half of the Programme period | Mid 2026 | EFD and UNDP | Budgeted in the Multi Year Plan |
| Terminal Evaluation | Sweden Embassy, UNDP, and EFD | Independent evaluation is undertaken during the last quarter of the Programmes to assess if the Programme has contributed to enhancing private sector engagement in forestry and to developing forest product markets and making them work better for the poor. | Measures to ensure sustainability of positive impacts of the Programme proposed, including capacity of institutions to do so. | End of 2027 | Sweden Embassy, UNDP and MoF | Budgeted in the Multi Year Plan |

## Social and Environmental Safeguard report

Programme Information

| Programme Information |  |
| --- | --- |
| - Programme Title | Sustainable private sector engagement in developing inclusive forest products markets in Ethiopia |
| - Programme Number (i.e., Atlas Programme ID, PIMS+) |  |
| - Location (Global/Region/Country) | Ethiopia |
| - Programme stage (Design or Implementation) | Design |
| - Date | 22 May 2024 |

Part A. Integrating Programming Principles to Strengthen Social and Environmental Sustainability

QUESTION 1: How Does the Program Integrate the Programming Principles in Order to Strengthen Social and Environmental Sustainability?

Briefly describe in the space below how the Program mainstreams the human rights-based approach

This Program aims to enhance engagement of the private sector in forest product market development for inclusive and sustainable economic growth. The Program will support and organize unemployed youth and women to establish private tree nurseries for engaging in high-quality tree seedling and honey production, targeted beneficiaries are un-employed women and youth in rural and peri-urban areas. Based on the market system development model, the Program enhance access to value addition innovations and business development services of small-scale forest products processors and traders improved in ways that reduce gender gaps and enhance social inclusiveness. In the Program, rural and peri-urban communities are the main beneficiaries, and the Program will ensure the involvement of a high percentage of disadvantaged segments (un-employed women and youth) in all the targeted areas. By working closely with community-based organizations and local government authorities, the Program enhances active participation in and a more equitable distribution of benefits from the Program interventions. The Program will ensure active participation of local communities, women, and minorities; transparent and participatory decision-making processes; and equitable benefit sharing mechanisms. The stakeholder engagement promotes process respecting customs, traditions, culture and rights, and facilitates an inclusive and participatory process to ensure that all individuals and groups, regardless of sex, gender, age, ethnicity, religion, race or creed, are included and benefit from the Program’s investments. The Grievance Redress Mechanism procedure will follow principles of accessibility, which are collaborative, expeditious, and effective in resolving concerns through dialogue, joint fact-finding, negotiation, and problem solving.

Briefly describe in the space below how the Program is likely to improve gender equality and women’s empowerment

The program is gender-responsive in design & implementation & seeks to empower women through its private sector led sustainable forestry development Program. The Program will pursue a gender equality and women’s-empowerment approach focused on acknowledging gender differentiated roles and engaging poor women as decision makers and agents of change. The Program’s multi-stakeholder element involved in developing platforms and establishing effective policy will focus explicitly on gender equality and transforming the decision-making environment. In addition, the Program overall is committed to at least 60% of all beneficiaries being women. Infusing all this work is a commitment to gender transformation, recognizing that poor rural women in particular are the major actors in rural economies in terms of managing demand for natural resources including biomass energy, water resources and food security at a household level.

Briefly describe in the space below how the Program mainstreams sustainability and resilience

The Program will ensure environmental sustainability through enhance private sector engagement on forest management and developing markets for forest products including non-timber forest products (NTFPs), demonstrating additionality, and ensure that biodiversity and livelihoods are improved. Based on the market system development model, the Program enhance access to value addition innovations and business development services of small-scale forest products processors and traders improved in ways that reduce gender gaps and enhance social inclusiveness. New business models will be introduced and supported for better livelihood outcomes in terms of increased and diversified income and/or new jobs created for women and youth.

Briefly describe in the space below how the Program strengthens accountability to stakeholders

UNDP promotes accountability to Program stakeholders by (i) enabling active local community engagement and participation in decision-making, particularly those at risk of being left behind; (ii) ensuring transparency of programming interventions through provision of timely, accessible and functional information regarding supported activities, including on potential environmental and social risks and impacts and management measures; (iii) ensuring stakeholders can communicate their concerns and have access to rights-compatible complaints redress processes and mechanisms; and (iv) ensuring effective monitoring—and where appropriate, participatory monitoring with stakeholders—and reporting on implementation of social and environmental risk management measures. In the Programme Grievance Redress Mechanism (GRM) provides a formal avenue for affected individuals or communities to engage with the Program implementers or sponsors on issues of concern or unaddressed environmental and social impacts. It aims to manage and satisfactorily respond to the complaints of individuals or groups of people regarding the environmental and social performance of the Program. The Program should establish grievance redress committees for grievance/feedback redress mechanism.

Part B. Identifying and Managing Social and Environmental Risks

| QUESTION 2: What are the Potential Social and Environmental Risks? Note: Complete SESP Attachment 1 before responding to Question 2. | QUESTION 3: What is the level of significance of the potential social and environmental risks? Note: Respond to Questions 4 and 5 below before proceeding to Question 6. |  |  | QUESTION 6: Describe the assessment and management measures for each risk rated Moderate, Substantial or High. |
| --- | --- | --- | --- | --- |
| Risk Description (Broken down by event, cause, impact) | Impact and Likelihood (1-5) | Significance (Low, Moderate Substantial, High) | Comments (optional) | Description of assessment and management measures for risks rated as Moderate, Substantial or High |
| Risk 1: A risk that rights-holders (e.g., Program-affected persons) may be limited to claim their rights. The Program intervention such as nursery site establishment, honey, gum and incense production and related activities will have land acquisition and restrict resource use access to local community, but they may not have access to claim their concerns/grievances. (Triggered Principle 1: P3, P6) | I =2 P= 2 | Low |  | For the Programme affected people, the Programme Grievance Response Mechanism will enable to have an accessible, collaborative, expeditious and effective process for resolving concerns through dialogue, joint fact-finding, negotiation, and problem solving. These plans are envisaged to facilitate inclusive and participatory processes that leave no one behind and empower those that are marginalized to actively participate and to also benefit from decisions and actions that the Program finances. |
| Risk 2: Limitations on women’s ability to use, develop and protect natural resources, considering different roles and positions of women and men in accessing environmental goods and services. (Triggered Principle 2: P11) | I = 3 P = 3 | Moderate |  |  |
| Risk 3: The Program output like tree seedling production and honey related agriculture business are sensitive or vulnerable to potential impacts of climate change. (Triggered Standard 2: 2.2) | I = 3 P = 2 | Moderate | Ethiopia is vulnerable to climate change, in particular the agricultural and agroforestry sectors. The climate change risk should be considered in the Program | Climate change related risk such as drought and flooding will affect tree seedling production. Alternative water resources should be identified for nursery sites and sites should be safe from flood prone areas with proper management practices. A detailed climate risk analysis will be conducted during ESIA/ESMP development for the Program resilience measures to integrated and ensure that the impacts of climate change are minimized, and the resiliency of Program beneficiaries is strengthened. The Program should design a series of measures aims at building resilience and promoting adaptation to climate change in forestry sector. |
| Risk 4: Risk of access to resources due to land acquisition or access restrictions – even in the absence of physical relocation mainly for tree nursery development activities. (Standard 5: 5.2; 5.4) | I = 3 P = 2 | Moderate |  | Identified social and environmental issues, which will require site specific comprehensive environmental and social assessments. The Program supports Tree Seedling Production including with irrigation solutions will have land acquisition impact. The activity will have impacts on communal use and/or private landholders. |
| Risk 5: Health and safety risks during the implementation of excavation work on nursery site, gum and incense collection activities. (Triggered Standard 7: 7.6) | I = 2 P = 3 | Moderate | The Program does involve the physical activities such as excavation work on nursery site preparation and seedling production, gum and incense collection activities etc. | Adequate mitigation measures/safety measures should be in placed to mitigate adverse impacts/risks related to the Program physical activities such as excavation work on nursery site, gum and incense collection activities etc. |
| Risk 6: Risk of child labour and underpayment will occur at local level. A national Child Labour Survey conducted in 2001 with ILO assistance indicated that 52 per cent of children aged 5 – 17 years were economically active (49 per cent of those aged 5 – 14 years, or 7.4 million). A further 33 per cent were engaged in non-economic housekeeping activities, with half of them not attending school. Overall, 85 per cent of children aged 5 – 17 years were involved in economic or housekeeping activities that prevented or impeded school attendance or performance.’ The definition of a child in Ethiopia refers to ‘a "minor" of either sex who has not attained the full age of 18 years.’ (Triggered Standards: 3.8 and 7.3) | I=3 P=2 | Moderate | As per the ILO study, the need for labour assistance of children in family business, and the desire to supplement household income are the two most important reasons that drive children to work. Thus, a significant proportion of children in urban areas work to assist themselves and to get work experience. On the other hand, the majority (89 per cent) of children living in rural areas and engaged in productive activities were working in elementary agricultural and related activities, such as herding cattle and helping adults in farming. | The Program support to workers will follow government employment guidelines and target youth and adults only. Youth in Ethiopia are defined as those that have attained 18 years. |
| Risk7: Risk of the application of pesticides on nursery site for tree seedling production may have a negative effect on the environment or human health by pollute water supplies and soil directly or indirectly. (Standard 8: 8.3 and 8.5) | I=2 P=2 | Low |  | The Program will involve use of chemical to control insect pests in tree nursery, the application of pesticides may be inevitable. But its misuse can cause adverse environmental impacts. The application of pesticides kills the natural predator of harmful insects, and cause biodiversity decline and the unbalance of species. If misused, the pesticide can pollute water supplies and soil directly or indirectly. The pesticide spraying equipment might contaminate the water and soil if not cleaned correctly. |

|  | QUESTION 4: What is the overall Program risk categorization? Note: Program categorization is determined by the highest level of significance of identified risks across all potential risk areas (as rated in Question 3). |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Low Risk | ☐ |  |  |  |
|  | Moderate Risk | X | Overall, the Program environmental and social risk is manageable, localized and mostly temporal. Those impacts are identified individually, and overall risk level rated to be moderate. Therefore, for the Program comprehensive site specific environmental and social assessment/management plan should be prepared. |  |  |
|  | Substantial Risk | ☐ |  |  |  |
|  | High Risk | ☐ |  |  |  |
|  | QUESTION 5: Based on the identified risks and risk categorization, what requirements of the SES are triggered? (Check all that apply) |  |  |  |  |
|  | Question only required for Moderate, Substantial and High-Risk Programs. |  |  |  |  |
|  | Is assessment required? (Check if “yes”) | X |  |  | Status? (Completed, planned) |
|  | if yes, indicate overall type and status |  |  | Targeted assessment(s) |  |
|  |  |  | X | ESIA (Environmental and Social Impact Assessment) | Recommended to prepare site specific Program environmental and social impact assessment/ESIA/ESMP. |
|  |  |  |  | SESA (Strategic Environmental and Social Assessment) |  |
|  | Are management plans required? (Check if “yes) | X |  |  |  |
|  | If yes, indicate overall type |  |  | Targeted management plans |  |
|  |  |  | X | ESMP (Environmental and Social Management Plan) | The Program requires comprehensive environmental and social management plan (ESMP), it could be part of the environmental and social impact assessment (ESIA) as mentioned above. |
|  |  |  |  | ESMF (Environmental and Social Management Framework) |  |
|  | Based on identified risks, which Principles/Program-level Standards triggered? |  | Comments (not required) |  |  |
|  | Overarching Principle: Leave No One Behind | --- |  |  |  |
|  | Human Rights | x |  |  |  |
|  | Gender Equality and Women’s Empowerment | x |  |  |  |
|  | Accountability | x |  |  |  |
|  | 1. Biodiversity Conservation and Sustainable Natural Resource Management | x | The Program tree nursery production and honey production interventions activities have environmental social issues as identified as rick on the above. |  |  |
|  | 2. Climate Change and Disaster Risks | x | Climate change related risk such as drought and flooding will affect tree nursery sites. Alternative water resources should be identified for nursery sites and should be safe from flood prone areas. |  |  |
|  | 3. Community Health, Safety and Security | x |  |  |  |
|  | 4. Cultural Heritage |  |  |  |  |
|  | 5. Displacement and Resettlement | x | As mentioned, the Program will have impact of access to resources due to land acquisition or access restrictions – even in the absence of physical relocation mainly during tree seedling development activities. |  |  |
|  | 6. Indigenous Peoples/Vulnerable People |  |  |  |  |
|  | 7. Labour and Working Conditions | x | Risk of violation of ILO standards, including child labour and underpayment. Hence in order to supplement the site-level ESMPs prepared including Labor Management Plan to mitigate risks around wages and working conditions, with particular monitoring of the use of Child Labour, and accompanying sensitization and mitigation measures. |  |  |
|  | 8. Pollution Prevention and Resource Efficiency | x |  |  |  |

Final Sign Off

| Signature | Date | Description |
| --- | --- | --- |
| QA Assessor |  | UNDP staff member responsible for the Program, typically a UNDP Programme Officer. Final signature confirms they have “checked” to ensure that the SESP is adequately conducted. |
| QA Approver |  | UNDP senior manager, typically the UNDP Deputy Country Director (DCD), Country Director (CD), Deputy Resident Representative (DRR), or Resident Representative (RR). The QA Approver cannot also be the QA Assessor. Final signature confirms they have “cleared” the SESP prior to submittal to the PAC. |
| PAC Chair |  | UNDP chair of the PAC. In some cases, PAC Chair may also be the QA Approver. Final signature confirms that the SESP was considered as part of the Program appraisal and considered in recommendations of the PAC. |

SESP Attachment 1. Social and Environmental Risk Screening Checklist

| Checklist Potential Social and Environmental Risks |  |
| --- | --- |
| INSTRUCTIONS: The risk screening checklist will assist in answering Questions 2-6 of the Screening Template. Answers to the checklist questions help to (1) identify potential risks, (2) determine the overall risk categorization of the Program, and (3) determine required level of assessment and management measures. Refer to the SES toolkit for further guidance on addressing screening questions. |  |
| Overarching Principle: Leave No One Behind | Answer (Yes/No) |
| Human Rights |  |
| P.1 Have local communities or individuals raised human rights concerns regarding the Program (e.g., during the stakeholder engagement process, grievance processes, public statements)? | No |
| P.2 Is there a risk that duty-bearers (e.g., government agencies) do not have the capacity to meet their obligations in the Program? | Yes |
| P.3 Is there a risk that rights-holders (e.g., Program-affected persons) do not have the capacity to claim their rights? | Yes |
| Would the Program potentially involve or lead to: | --- |
| P.4 adverse impacts on enjoyment of the human rights (civil, political, economic, social or cultural) of the affected population and particularly of marginalized groups? | No |
| P.5 inequitable or discriminatory impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups, including persons with disabilities? | No |
| P.6 restrictions in availability, quality of and/or access to resources or basic services, in particular to marginalized individuals or groups, including persons with disabilities? | Yes |
| P.7 exacerbation of conflicts among and/or the risk of violence to Program-affected communities and individuals? | No |
| Gender Equality and Women’s Empowerment |  |
| P.8 Have women’s groups/leaders raised gender equality concerns regarding the Program (e.g., during the stakeholder engagement process, grievance processes, public statements)? | No |
| Would the Program potentially involve or lead to: | --- |
| P.9 adverse impacts on gender equality and/or the situation of women and girls? | No |
| P.10 reproducing discriminations against women based on gender, especially regarding participation in design and implementation or access to opportunities and benefits? | No |
| P.11 limitations on women’s ability to use, develop and protect natural resources, considering different roles and positions of women and men in accessing environmental goods and services? For example, activities that could lead to natural resources degradation or depletion in communities who depend on these resources for their livelihoods and well being | Yes |
| P.12 exacerbation of risks of gender-based violence? For example, through the influx of workers to a community, changes in community and household power dynamics, increased exposure to unsafe public places and/or transport, etc. | No |
| Sustainability and Resilience: Screening questions regarding risks associated with sustainability and resilience are encompassed by the Standard-specific questions below |  |
| Accountability |  |
| Would the Program potentially involve or lead to: | --- |
| P.13 exclusion of any potentially affected stakeholders, in particular marginalized groups and excluded individuals (including persons with disabilities), from fully participating in decisions that may affect them? | Yes |
| P.14 grievances or objections from potentially affected stakeholders? | Yes |
| P.15 risks of retaliation or reprisals against stakeholders who express concerns or grievances, or who seek to participate in or to obtain information on the Program? | No |
| Program-Level Standards |  |
| Standard 1: Biodiversity Conservation and Sustainable Natural Resource Management |  |
| Would the Program potentially involve or lead to: | --- |
| 1.1 adverse impacts to habitats (e.g., modified, natural, and critical habitats) and/or ecosystems and ecosystem services? For example, through habitat loss, conversion or degradation, fragmentation, hydrological changes | No |
| 1.2 activities within or adjacent to critical habitats and/or environmentally sensitive areas, including (but not limited to) legally protected areas (e.g., nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities? | No |
| 1.3 changes to the use of lands and resources that may have adverse impacts on habitats, ecosystems, and/or livelihoods? (Note: if restrictions and/or limitations of access to lands would apply, refer to Standard 5) | Yes |
| 1.4 risks to endangered species (e.g., reduction, encroachment on habitat)? | No |
| 1.5 exacerbation of illegal wildlife trade? | No |
| 1.6 introduction of invasive alien species? | No |
| 1.7 adverse impacts on soils? | No |
| 1.8 harvesting of natural forests, plantation development, or reforestation? | Yes |
| 1. 9 significant agricultural production? | No |
| 1. 10 animal husbandry or harvesting of fish populations or other aquatic species? | No |
| 1.11 significant extraction, diversion or containment of surface or ground water? For example, construction of dams, reservoirs, river basin developments, groundwater extraction | No |
| 1.12 handling or utilization of genetically modified organisms/living modified organisms? | No |
| 1.13 utilization of genetic resources? (e.g., collection and/or harvesting, commercial development) | No |
| 1.14 adverse transboundary or global environmental concerns? | No |
| Standard 2: Climate Change and Disaster Risks |  |
| Would the potentially involve or lead to: | --- |
| 2.1 areas subject to hazards such as earthquakes, floods, landslides, severe winds, storm surges, tsunami or volcanic eruptions? | No |
| 2.2 outputs and outcomes sensitive or vulnerable to potential impacts of climate change? For example, through increased precipitation, drought, temperature, salinity, extreme events | Yes |
| 2.3 direct or indirect increases in vulnerability to climate change impacts or disasters now or in the future (also known as maladaptive practices)? For example, changes to land use planning may encourage further development of floodplains, potentially increasing the population’s vulnerability to climate change, specifically flooding | No |
| 2.4 increases of greenhouse gas emissions, black carbon emissions or other drivers of climate change? | No |
| Standard 3: Community Health, Safety and Security |  |
| Would the potentially involve or lead to: | --- |
| 3.1 construction and/or infrastructure development (e.g., roads, buildings, dams)? | No |
| 3.2 air pollution, noise, vibration, traffic, injuries, physical hazards, poor surface water quality due to runoff, erosion, sanitation? | Yes |
| 3.3 harm or losses due to failure of structural elements of the Program (e.g., collapse of buildings or infrastructure)? | No |
| 3.4 risks of water-borne or other vector-borne diseases (e.g., temporary breeding habitats), communicable and noncommunicable diseases, nutritional disorders, mental health? | Yes |
| 3.5 transport, storage, and use and/or disposal of hazardous or dangerous materials (e.g., explosives, fuel and other chemicals during construction and operation)? | Yes |
| 3.6 adverse impacts on ecosystems and ecosystem services relevant to communities’ health (e.g., food, surface water purification, natural buffers from flooding)? | No |
| 3.7 influx of Program workers to Program areas? | No |
| 3.8 engagement of security personnel to protect facilities and property, or to support Program activities? | No |
| Standard 4: Cultural Heritage |  |
| Would the Program potentially involve or lead to: | --- |
| 4.1 activities adjacent to or within a Cultural Heritage site? | No |
| 4.2 significant excavations, demolitions, movement of earth, flooding or other environmental changes? | No |
| 4.3 adverse impacts to sites, structures, or objects with historical, cultural, artistic, traditional or religious values or intangible forms of culture (e.g., knowledge, innovations, practices)? (Note: Programs intended to protect and conserve Cultural Heritage may also have inadvertent adverse impacts) | No |
| 4.4 alterations to landscapes and natural features with cultural significance? | No |
| 4.5 utilization of tangible and/or intangible forms (e.g., practices, traditional knowledge) of Cultural Heritage for commercial or other purposes? | No |
| Standard 5: Displacement and Resettlement |  |
| Would the Program potentially involve or lead to: | --- |
| 5.1 temporary or permanent and full or partial physical displacement (including people without legally recognizable claims to land)? | No |
| 5.2 economic displacement (e.g., loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation)? | Yes |
| 5.3 risk of forced evictions? | No |
| 5.4 impacts on or changes to land tenure arrangements and/or community-based property rights/customary rights to land, territories and/or resources? | Yes |
| Standard 6: Indigenous Peoples/Vulnerable People |  |
| Would the Program potentially involve or lead to: | --- |
| 6.1 areas where indigenous peoples are present (including Program area of influence)? | No |
| 6.2 activities located on lands and territories claimed by indigenous peoples? | No |
| 6.3 impacts (positive or negative) to the human rights, lands, natural resources, territories, and traditional livelihoods of indigenous peoples (regardless of whether indigenous peoples possess the legal titles to such areas, whether the Program is located within or outside of the lands and territories inhabited by the affected peoples, or whether the indigenous peoples are recognized as indigenous peoples by the country in question)? | No |
| 6.4 the absence of culturally appropriate consultations carried out with the objective of achieving FPIC on matters that may affect the rights and interests, lands, resources, territories and traditional livelihoods of the indigenous peoples concerned? | No |
| 6.5 the utilization and/or commercial development of natural resources on lands and territories claimed by indigenous peoples? | No |
| 6.6 forced eviction or the whole or partial physical or economic displacement of indigenous peoples, including through access restrictions to lands, territories, and resources? Consider, and where appropriate ensure, consistency with the answers under Standard 5 above. | No |
| 6.7 adverse impacts on the development priorities of indigenous peoples as defined by them? | No |
| 6.8 risks to the physical and cultural survival of indigenous peoples? | No |
| 6.9 impacts on the Cultural Heritage of indigenous peoples, including through the commercialization or use of their traditional knowledge and practices? Consider, and where appropriate ensure, consistency with the answers under Standard 4 above. | No |
| Standard 7: Labour and Working Conditions |  |
| Would the Program potentially involve or lead to: (note: applies to Program and contractor workers) | --- |
| 7.1 working conditions that do not meet national labour laws and international commitments? | Yes |
| 7.2 working conditions that may deny freedom of association and collective bargaining? | No |
| 7.3 use of child labour? | Yes |
| 7.4 use of forced labour? | No |
| 7.5 discriminatory working conditions and/or lack of equal opportunity? | Yes |
| 7.6 occupational health and safety risks due to physical, chemical, biological and psychosocial hazards (including violence and harassment) throughout the Program life cycle? | Yes |
| Standard 8: Pollution Prevention and Resource Efficiency |  |
| Would the Program potentially involve or lead to: | --- |
| 8.1 the release of pollutants to the environment due to routine or non-routine circumstances with the potential for adverse local, regional, and/or transboundary impacts? | No |
| 8.2 the generation of waste (both hazardous and non-hazardous)? | No |
| 8.3 the manufacture, trade, release, and/or use of hazardous materials and/or chemicals? | Yes |
| 8.4 the use of chemicals or materials subject to international bans or phase-outs? For example, DDT, PCBs and other chemicals listed in international conventions such as the Montreal Protocol, Minamata Convention, Basel Convention, Rotterdam Convention, Stockholm Convention | No |
| 8.5 the application of pesticides that may have a negative effect on the environment or human health? | Yes |
| 8.6 significant consumption of raw materials, energy, and/or water? | No |

Programme Risk Assessment Matrix

| Risk |  | Proba-bility | Conse-quence | Overall risk assessment | Proposed Mitigation measures |
| --- | --- | --- | --- | --- | --- |
| Political and governance | - Low government interest to identify and address gaps in policies and strategies that limit private sector engagement in forestry | Low | Moderate | Moderate | - EFD is mandated to ensure responsible and sustainable forest products collection, processing and marketing and to enhance private sector engagement in the sector. One of its key mandates is also to identify policy gaps and ensure that appropriate policies and strategies are put in place and executed. Hence the Programme will closely work with EFD and assist its experts to work on these aspects. - Help in generating evidence of such gaps and options to addressing them based on experiences from other sectors and countries |
|  | - Failure of law enforcement in facilitating forest product markers and ensuring that laws governing forest products marketing are respected | Moderate | Moderate | Moderate | - Establish and strengthen partnership with actors in charge of governing forest product markets and other law enforcement agencies - Organised periodic consultations meeting and maintain active communications with these actors - Help build linkages between market players and relevant government agencies |
|  | - Security challenges in Programme areas can lead to slow down and/or suspension of Programme operations in target areas | Moderate | Serious | Moderate | - The Programme will adopt a risk minimization and aversive approaches during the course of the Programme implementation. - The Programme will adopt approaches that help reduce conflicts in its engagement |
| Operational | - Weak institutional capacity for implementation and coordination | Moderate | Serious | Serious | - Ensure that relevant government organizations have been involved in the process all along and that they assign staff in target areas to actively support the Programme - Strengthen/build the required skills through hands-on and practical training by also involving CIFOR and SLU as needed |
|  | - Inadequate capacity at the lower level of government structure to coordinate market actors and implement planned activities | Moderate | Serious | Serious | - The Programme will continue strengthening capacity of experts and institutions at lower levels of government structure to effectively take part in the coordination of actors, planning and implementation of interventions to bring about sustainable changes in forest products market systems and in ensuring that they benefit more poor women and men. |
|  | Inadequate involvement of the poor, women, and youth in forest product market systems | Moderate | Moderate | Moderate | - This risk of exclusion or limited involvement will be mitigated by identifying and addressing barriers that limit their active participation in and benefits from growing forest product markets - The Programme will train experts at different levels on how to engage youth and poor women and men in MSD so that they will benefit equitably from growing markets |
| Fiduciary | Delay in finance disbursement, utilization, settlement, and auditing | Moderate | Moderate | Moderate | - Ensure recruitment and/or assignment of finance officer in the target woredas - Provide periodic on-job trainings and capacity building support - Conduct periodic monitoring - Prepare customize financial manual and train the woreda finance officers |
|  | Corruption and/or mismanagement of programme resources | Moderate | Moderate | High | - Ensure proper execution of the financial and procurement policies and procedures - Create clear programme management rules and regulations with explicit delegation of authority, especially on financial oversight and management - Undertake regular financial hot-spot checks and document verifications - Undertake regular capacity building and awareness creation - Undertake regular pre-audit checks and execute annual audits in time and ensure proposed audit management actions are taken - Strengthen the internal audit capacity & take actions based on the findings without much delay |
|  | Gender inequality | Small | Serious | Substantial | - Ensure adequate women representation at all levels - Ensure that women engage in and benefit equitably in the market system - Provide preferential support such as loans and other forms of business assistance to women and girls |

## Strategic Critical Risks and Mitigation Measures

| Risk Category | Risk Description | Probability | Risk Impact | Risk Owner | Mitigation Strategy/Measures |
| --- | --- | --- | --- | --- | --- |
| Political | Internal political conflicts and tensions between regional states and/between the federal government and regional states cause unrest and instability; unrest and restrictions of human and democratic rights may derail the reform process could affect the smooth and effective programme. |  |  | GoE/IPs | Closely track & follow up the current political and security situation of the country; advocate for a peaceful settlement of political differences; promote political dialogue among regional states and political parties; |
| Environmental /Health post-pandemic | Climate related crises in the Regions; sluggish post conflict return to normal operations may cause implementation delays. |  |  | IPs | Closely follow up emerging situations national/regional crises and revisit timelines, as necessary. |
| Security Risk | Post conflict/ ongoing conflicts and tensions in various parts of the country and the fragile peace, underlying insecurity may negatively impact implementation. |  |  | IPs/UNDP | Closely follow up the situation and get security/risk analysis and proactively update & respond to the emerging situation. Work very closely with IPs and adjust the activities timelines accordingly as necessary |
| Financial Risks | The ongoing Ukraine war + Gaza & global inflation may force donors to shift their resources; ongoing & emerging humanitarian crises i.e., increased IDPs, refugees & natural disasters - drought/floods could impact the timely release of the programme funding. |  |  | UNDP/MoF | Focus on most critical /transformative activities; Scale back on planned activities; Intensify resource mobilization efforts. Use reallocation of resources/ budgets, as appropriate |
| Operational/ Organizational Risks | Procurement delays in securing goods & services may negatively affect timely implementation. Poor/delayed/lack of quality substantive/ financial reports from IPs negatively affecting timely project delivery |  |  | IPs/UNDP | Hold regular meetings between IPs to exchange views to find workable solutions; Ensure close follow up of the project implementation and maintain quality assurance. Provide need-based capacity building together with technical backstopping & support. |
| Reputational | Negative perception of UNDP’s association with sensitive interventions perpetuated by special interest groups |  |  | UNDP | Continuous communication with partners highlighting UNDP’s key achievements. |

Development Assistance for a New Era - Freedom, empowerment and sustainable growth, December 2023, page 9.

Interventions on institutional capacity development will be informed by the Capacity Development Framework of UNDP

The term Private Sector includes individual smallholders, tree growers’ associations or forest growers’ cooperatives engaged in small scale or large plantations, forestry and wood machinery suppliers; machinery maintenance service providers; forest and wood-work related skills training providers; forestry input and services providers; furniture manufacturing companies; engineered wood manufacturing companies; logistics companies; small-scale processors and traders of forest products, certification service providers; etc. (Expanded version of the note from the ToR).

Though yet to be refined, studies show that the prevailing constraints of forest products markets include under development of markets, farmers lack know-how how to grow trees for markets, smallholders’ little or no access to land, finance, information, and inputs that support good forestry practices, poorly organized markets actors, failure of market actors to make relevant inputs and services available closer to tree growers, etc.

Encouraging  market-oriented diversification and commercialization in forestry and agroforestry ('turning tree growing into a business'); exploring off-farm employment opportunities and supporting local entrepreneurship in niche markets; developing better business services and improving constraining aspects business enabling environment (e.g., in collecting and marketing forest products; encouraging geographic and ethnic inclusions in business to expand economic activities for local communities  areas or segments of communities, among others.

Gums and resins of Ethiopia, https://www.cifor-icraf.org/publications/pdf_files/infobrief/3359-infobrief.pdf

Detailed profiles are annexed to this Proposal.

Strategic risks assessment, management and mitigation is included in the suite of Annexes.

It is recommended that Programmes use output indicators from the Strategic Plan IRRF, as relevant, in addition to Programme-specific results indicators. Indicators should be disaggregated by sex or for other targeted groups where relevant.

Ibid, p. 24 rounds of discrimination include race, ethnicity, sex, age, language, disability, sexual orientation, gender identity, religion, political or other opinion, national or social or geographical origin, property, birth, or other status including as an indigenous person or as a member of a minority. References to “women and men” or similar is understood to include women and men, boys and girls, and other groups discriminated against based on their gender identities, such as transgender and transsexual people.

See the Convention on Biological Diversity and its Cartagena Protocol on Biosafety.

See the Convention on Biological Diversity and its Nagoya Protocol on access and benefit sharing from use of genetic resources.

Forced eviction is defined here as the permanent or temporary removal against their will of individuals, families, or communities from the homes and/or land which they occupy, without the provision of, and access to, appropriate forms of legal or other protection. Forced evictions constitute gross violations of a range of internationally recognized human rights.