Annex I - Description of the Action

Good Governance

Co-funded by the European Union

Summary of the Action

| Action Title | Good Governance |
| --- | --- |
| Overall Objective | By 2028 Substantially reduce corruption and bribery in its forms in Namibia to promote transparency and accountability in governance. |
| Specific Objectives | SO 1: To strengthen the management and technical capacity of the ACC of Namibia to comprehensively fulfil its mandate as well as improve its cooperation with other institutions involved in the fight against corruption - By 2028 the management and technical capacity of the Anti-Corruption Commission (ACC) of Namibia can comprehensively fulfil its mandate, with a focus on key sectors. - By 2028, the ACC has improved collaboration with other institutions engaged in combating corruption. SO2. Effective implementation of the National Anti-Corruption Strategy and Action Plan (NACSAP). - By 2028, the ACC has strengthened effectively implemented the National Anti-Corruption Strategy and Action Plan (NACSAP). |
| Geographic Scope | National Level with specific interventions at sub-national levels |
| Period of Implementation | 40 Months |

Contents

1.	List Of Acronyms and Abbreviations	1

2.	Introduction	2

*Disclaimer*	2

3.	Background and Context	2

4.	Relevance of the Action	4

5.	Objectives (overall, specific objectives and outputs)	5

2.	Methodology	14

4.	Indicative Action plan ( and half year 1 &  Work Plan Year 1)	17

7.	Implementation Arrangements	22

8.	Human Resources and Project Costs	23

9.	Synergies with other Programmes and Initiatives	23

10.	Sustainability	24

11.	Sustainability post implementation:	24

12.	Risk Analysis and contingency Plan	25

13.	General overview on Visibility and communication	26

14.	Monitoring and Evaluation	26

## List Of Acronyms and Abbreviations

UNCAC		United Nations Convention against Corruption

ACC		Anti-Corruption Commission

CSO		Civil Society Organization

CPI		Corruption Perception Index

EC		European Commission

EU		European Union

GRICE		Governance, Responsive Institutions and Civic Engagement

GRN		Government of the Republic of Namibia

HPPII		Harambee Prosperity Plan II

IPPR		Institute for Public Policy and Research

NACS		National Anti-Corruption Strategy

NACS		National Anti-Corruption Strategy

NACSAP	National Anti-Corruption Strategy and Action Plan

NDP		National Development Plan

OMA		Offices, Ministries, and Agencies

PSC		Project Steering Committee

PSC		Project Steering Committee

RBM		Results-based management

SDGs		Sustainable Development Goals

SEMER		Sustainable Environmental Management, Energy and enhanced Resilience

SIGG		Sustainable Inclusive Green Growth

UN 		United Nations

UNDP		United Nations Development Programme

UNODC		United Nations Office on Drugs and Crime

## Introduction

This Description of Action has been prepared by the United Nations Development Programme (UNDP) Namibia country office, through a comprehensive research and consultative process. This process comprised a desk review as well as meetings and other engagements which harnessed data and insights from various sources, stakeholders and partners. It is further informed by the findings from the evaluation of the first National Anti-Corruption Strategy and Action Plan (NACSAP) and is aligned to the UNDP's Africa Promise, harnessing the value of sustainable financing and digital transformation enablers, while responding to the Harambee Prosperity Plan II (HPP II) and the National Development Plans (NDP).

UNDP’s strategic enablers support the implementation of interventions, mechanisms and designing platforms for efforts to prevent corruption and illicit financial flows. Additionally, it embraces digital transformation through e-Governance for enhanced public goods access, efficiency, and corruption reduction. The action intends to achieve a significant reduction in corruption and bribery across various sectors in Namibia, through a comprehensive and inclusive approach. To achieve this goal, implementing robust governance structures, enhancing transparency, and fostering accountability mechanisms are essential components. Additionally, promoting ethical behaviour, strengthening legal frameworks, and engaging in public awareness campaigns and education, will contribute to creating an environment intolerant of corrupt practices.

Collaboration between government bodies, civil society, and the private sector is crucial to ensuring the effectiveness of the strategies outlined, ultimately fostering sustainable development in Namibia. This whole of society approach will foster a climate of integrity and trust and improve social cohesion. The Action will promote sustainable development encompassing economic, social, and environmental aspects. Promoting transparent and accountable collaboration reduces corruption, ensuring fair resource allocation and aiding in reducing inequality.The proposed interventions directly address the Namibian government's, UNDP and the EU's priorities in combating corruption, as outlined in NDP, HPPII  and Vision 2030. In addition considering the UNDP strategic plan and EU Namibia Multi-Annual Indicative Programme (MIP).

Moreover this action is also aligned with the European Commission’s (EC) priority for “Human development, peace, and governance” and will mainly contribute to progressively achieving the 2030 Agenda for Sustainable Development, particularly Sustainable Development Goal (SDG) 16 (Peace, Justice, and Strong Institutions).

*Disclaimer*

The description of action has been developed through a comprehensive consultative process that engaged a diverse range of stakeholders, ensuring the proposed strategies are relevant and effective in addressing corruption. It is essential to emphasize that the description of the action is a demand-driven response. This action reflect the needs and priorities of communities most affected by corruption, particularly in the current political environment in Namibia. The collaborative nature of the project underscores a commitment to a participatory approach, ensuring all voices are considered in formulating anti-corruption measures. By aligning efforts with the genuine demands of the populace, this initiative aims to establish a sustainable and responsive framework for combating corruption that enhances ownership, accountability, and long-term success.

## Background and Context

Corruption poses a significant development challenge in Namibia, impacting various aspects of the country's economic and governance landscape. The World Bank's Worldwide Governance Indicators and Transparency International's Corruption Perception Index have both highlighted the pervasive nature of corruption in Namibia, with the country scoring 49 out of 100 on the index in 2021. This indicates a significant level of perceived corruption, which can deter foreign investment and hinder economic growth. The country's high unemployment rate, which reached is estimated at 20.8 percent in 2022, is exacerbated by corruption, further straining the economy and contributing to income disparities. Youth unemployment in Namibia is a growing concern, with a rate of 39.78% in 2022, which can exacerbate existing inequalities by disenfranchising young people and excluding them from economic opportunities.

Support for anti-corruption interventions and the national integrity system can facilitate a smooth transition to a more inclusive democracy and improved institutional functioning in Namibia. Enhanced anti-corruption initiatives respond favorably to sustainable human development as a catalytic enabler to achieve progress on a whole range, if not all, SDGs. The Government of Namibia (GRN) has demonstrated commitment to eradicating corruption by ratifying the African Union Convention for Preventing and Combating Corruption in 2004 and as a state party to the United Nations Convention Against Corruption (UNCAC).

Article 5 of the United Nations Convention against Corruption (UNCAC) mandates State Parties to create and implement a National Anti-Corruption Strategy (NACS), which Namibia has pursued since the establishment of the Anti-Corruption Commission (ACC) in 2006. Following extensive consultations and support from the UNDP, Namibia developed its first NACS for 2016-2019, which was evaluated in 2020, leading to the formulation of the revised National Anti-Corruption Strategy and Action Plan (NACSAP) for 2021-2025, presented in March 2022. The Government of the Republic of Namibia prioritizes the fight against corruption, recognizing its detrimental impact on public trust and the country's democratic aspirations. Increasing corruption, particularly in sectors like natural resources and mining, poses significant challenges to Namibia's development goals, highlighting the urgent need for effective anti-corruption measures.

On going cases in the public domain which have caused controversy in 2019 is the ‘Fishrot scandal’ which has had a profound impact on human rights, particularly on the lives of Namibian fishing industry workers. The scandal, which involved corrupt practices in the fishing industry, led to devastating consequences for individuals who struggled to secure new employment, maintain basic living standards, and participate meaningfully in societal activities.

Additionally suspicion in cases such as the Recon Africa and the Kalahari basin exploration have raised concerns and criticism for a lack of transparency in the operations of oil and gas companies in the country. Moreover the exploitation of natural resources in the region has been marked by allegations of opacity and corruption. Namibia is in need for greater transparency and accountability in its natural resource management. The International Monetary Fund (IMF) has also emphasized the importance of transparency in foreign exchange practices to ensure the stability of a country's economy. Therefore, it is crucial for Namibia to address these issues to promote sustainable development and curb corrupt practices. Recent developments, e.g., the prospects of commercial offshore oil extraction and the preparations to produce Green Hydrogen in Namibia offer not only enormous economic and development opportunities for Namibia, but also avenues for mismanagement. The track-record of natural resource management in Namibia during the past decades has not been very successful, despite the narrative of Namibia being a model for conservation and environmental protection. The depletion of Namibia’s natural resources especially in the extractives sector can mainly be attributed to a partial failure of governance, especially transparency and accountability mechanisms.

Cases of embezzlement, conflicts of interest, nepotism, and public procurement scandals regularly surface in Namibia, in addition to large corruption scandals in the natural resource sector. Corruption is increasingly perceived in public service delivery, particularly affecting vulnerable and underserved people, and threatening development outcomes in multiple sectors, including justice, health, and education.

Delays in adopting and implementing key legislation, such as "Access to Information", "Whistle-blower Protection Act", and "Witness Protection Act", weaken the performance potential of the integrity system in terms of transparency, accessibility, and accountability. The prevalence of corruption is a significant concern for the government, citizens, donors, and development partners, as it negatively affects growth, impedes equal access to quality public services, discourages and deters domestic and foreign investors, and reduces the impact of poverty reduction programs.

Support to strengthening vital pillars and institutions of the national integrity system in Namibia, to pro-actively implement the National Anti-Corruption Strategy (NACS) and other relevant strategies and action plans, is essential for a positive transformation at the institutional level. Such support will also leverage direct positive effects on human development, reduce inequality while supporting informed public debate, enhance awareness and oversight. More transparency and access to information will decrease the information gap between the population and the government.

This action seeks to enhance the oversight and other functions of public institutions and support GRN’s efforts in delivering efficient, effective, and accountable services to its citizens. The project will focus on increased public participation and agency for enhanced accountability and transparency and dedicated technical assistance to enhance compliance, management and anti-corruption frameworks, to name a few. Anchored in the NDP5 and Vision 2030 of the country, while contributing to the fulfillment of (i) UNDP’s vision as enshrined in its 2022-25 Strategic Plan of helping “countries achieve sustainable development by eradicating poverty in all its forms and dimensions, accelerating structural transformation for sustainable development and building resilience to shocks” and (ii) the mission of UNDP’s Africa Promise, its Renewed Strategic Offer for Africa, which is to “enable the acceleration of  the SDGs, in Africa for the Decade of Action”. Further building on UNDP’s six signature solutions, and leveraging existing initiatives, the project aims to deliver results to enhance good governance, and particularly support anti-corruption interventions at various levels.

Under priority sector 3 of the Annual Action Programme “Good Governance and Gender Equality” and the respective signed financing agreement between the GRN and the EC, the results to be achieved as part of this action are:

Result 3.2.1. Enhanced capacities of the Anti-Corruption Commission

Result 3.2.2. Enhanced capacity of oversight bodies, including parliament and supreme audit authorities (EURF)

Result 3.2.3. Efficient implementation of the National Anti-Corruption strategy by relevant government institutions

## Relevance of the Action

Anti-Corruption is high on the media’s and the public’s agenda. Namibians perceive corruption as high for several reasons. The country's Corruption Perceptions Index (CPI) score of 49 in 2022 indicates a moderate level of corruption in its public sector. The perception is influenced by the country's low and fluctuating per capita income, indicating low prosperity and socioeconomic challenges. Additionally, the high unemployment rate of 20.8 percent and youth unemployment at 39.78 percent respectively  exacerbates the impact of corruption on the economy and society.

Namibia persistently endeavours to address corruption within its borders. Corruption, being a multifaceted global predicament, is susceptible to dynamic fluctuations. Notwithstanding the nation's endeavours to combat corruption through mechanisms such as the establishment of institutions mandated to respond to corruption and legal frameworks, glaring instances of grand corruption scandals persist. The Namibian government has unequivocally expressed its dedication to anti-corruption measures, with several high-profile cases and initiatives garnering substantial attention. Nevertheless, the efficacy of these endeavours can exhibit variability, and public sentiment regarding corruption may not invariably align with official actions.

Namibia has been making efforts to tackle corruption through various projects and initiatives. The Institute for Public Policy Research (IPPR) launched the Integrity Namibia project, which aims to build a national network among non-state actors to tackle corruption, including the establishment of an online reporting platform for whistle-blowers. In addition other interventions include the Corporate Governance Measures which emphasize good corporate governance to reduce corruption in the private sector and the regulatory measures are being evaluated to promote integrity in corporations and protect shareholders. Namibia developed a National Anti-Corruption Strategy and Action Plan (NACSAP) 2021-2025 which focuses on maintaining a corrupt-free Namibia through concerted efforts and 'healthy' societies.

The Namibian Whistleblower and Witness Protection Acts are highly relevant in strengthening the legal framework for combating corruption in Namibia. To fully leverage these legislation in combating corruption, there is a need to operationalize the Whistleblower Protection Act by allocating adequate resources, ensuring the independence and impartiality of the Whistleblower Office and other oversight bodies, and addressing the Act's limitations, such as the exclusion of disclosures questioning government policy. Public awareness campaigns need to be conducted to educate citizens about the available protections. Strengthening whistleblower and witness protection will create an environment that encourages reporting of corruption and misconduct, ultimately enhancing transparency and accountability in both the public and private sectors.

The Namibia Institute for Democracy (NID) led the “Zero Tolerance for Corruption Campaign aimed at combatting corruption through a strategic public-private coalition involving various public and private actors. It includes enhancing public access to information on corruption, capacity building for institutions, training workshops, and awareness campaigns.

The proposed action in the field of anti-corruption responds to Namibia’s political commitment to deter and prevent corruption in all its forms. A brief by the Institute for Public Policy and Research (IPPR, 2018) suggest that the country is lagging from an international perspective in addressing corruption. Given that corruption undermines good governance, jeopardizes inclusive growth and investments, depletes the natural environment and national resources, undermines social cohesion and the rule of law, and usually hits the poorest segments of society the hardest, a full set of anti-corruption measures in Namibia must be rigorously implemented to stop the deteriorating trend. The planned intervention for Anti-Corruption, therefore, aims at strengthening some of the main pillars of the national integrity and accountability system for efficient, transparent, and accountable institutions. The intervention will seek to contribute to the rigorous implementation of the NACSAP and will ideally result in substantially reducing corruption and bribery in all its forms across many institutions and sectors, inclusive of private sector entities.

This action design is highly relevant to the EU's objectives and priorities, as well as to promoting good governance, transparency, and accountability. It aligns with the EU's commitment to combating corruption and promoting integrity in public and private sectors. The NACSAP focuses on strengthening anti-corruption measures in institutions, improving legislation and enforcement mechanisms, and promoting a culture of integrity in Namibia. The action therefore responds to the identified capacity gaps and institutional needs in a focused, yet comprehensive manner and will contribute to the achievement of the results outlined above.

The action intends to avail targeted capacity-building opportunities to the ACC, but also other implementing Offices, Ministries, and Agencies (OMAs). Further to providing structured technical assistance through a) anti-corruption expert(s). In addition, the action will support CSOs with grants to support the achievement of the defined results.

## Objectives (overall, specific objectives and outputs)

Overall Objective/Impact: By 2028,  To strengthen democracy and transparent democratic processes.

Specific Objectives / Outcome 1:  By 2028, the ACC and relevant institutions have enhanced management and technical capacity resulting in the comprehensive fulfilment of its mandate and strengthened cooperation with other institutions engaged in the anti-corruption efforts.

Output 1.1. 	Strengthened management and technical capacity of the Anti-Corruption Commission of Namibia to comprehensively fulfil its mandate as well as improve its cooperation with other institutions involved in the fight against corruption.

Output 1.2.	The ACC has successfully strengthened its cooperation with relevant institutions engaged in anti-corruption efforts by 2028, resulting in a more coordinated and effective approach to combating corruption and promoting transparency and accountability.

Output 1.3.	By 2028, oversight bodies such as parliament, Office of the Prosecutor General and supreme audit authorities and relevant institutions have demonstrated enhanced capacity through improved training programs, improved advocacy for resource allocations, and strengthened collaboration, leading to more effective monitoring, evaluation, and oversight of government activities and expenditures.

Specific Objective / Outcome 2: By 2028, the ACC has successfully implemented/executed the National Anti-Corruption Strategy and Action Plan.

Output 2.1. 	Effective implementation of the National Anti-Corruption Strategy and Action Plan 			through the establishment of robust monitoring mechanisms, stakeholder engagement, 			capacity-building initiatives, and the enforcement of anti-corruption measures.

Output 2.2. 	The ACC has achieved all the objectives outlined in the National Anti-Corruption Strategy and Action Plan by demonstrating its commitment to fighting corruption and promoting accountability and transparency in all sectors of society.

The action also seeks to support the GRN in its endeavor to make significant progress in these two areas through supporting the implementation of the related policies and action plans in the respective sectors and through targeted capacity building and provision of technical assistance in the relevant institutions. The action will mainly contribute to progress in SDG 16 (Peace, Justice, and Strong Institutions). It will do so by supporting and strengthening both GRN and CSO’s and target priority sectors for the EU’s development cooperation in ‘Social inclusion and Human Development’, ‘Gender’, and ‘Human Rights, Democracy and Governance’. The action is design based on the analysis that, despite an overall advanced legislative framework in place in both areas of intervention, the implementation and enforcement of the respective policies and action plans are significantly lagging behind Namibia’s ambitions. This is attributed to various reasons, which range from a lack of financial, technically, human resources and coordination capacities.

| - Results Matrix |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Results | Results chain (@): Main expected results (maximum 10) | Indicators (@): (at least one indicator per expected result) | Baselines (values and years) | Targets (values and years) | Sources of data | Assumptions |
| Impact | To substantially reduce corruption and bribery in all their forms | Improved scoring/ranking of Namibia in relevant international integrity rankings** | 1 TI CPI: 59/180 (Year 1) | 1. 50/180 (Year 4) | 1. CPI Index/Transparency International, Afro barometer, Global Corruption Barometer, Ibrahim African Governance et al. | Not applicable |
| Outcome 1 | By 2028, the ACC and relevant institutions have enhanced management and technical capacity resulting in the comprehensive fulfilment of its mandate and strengthened cooperation with other institutions engaged in the anti-corruption efforts. | Extent to which the Anti-Corruption Commission is capable of comprehensively executing its mandate and cooperate with other institutions in the fight against corruption. | Qualitative indicator to be established during the inception phase of the intervention (Year 1) | To be established by the action (Year 3) | 1.1 Pre-Post action survey 1.2. Effective monitoring and reporting system; annual and final reports from the implementing organisation (EU/UNDP M&E, quality assurance verifications,) | ACC capacitated to fulfil its mandate and improve cooperation with other institutions of the national integrity system and other OMAs relevant for the implementation of the NACSAP |
| Output 1.1 | 1.1. Strengthened management and technical capacity of the Anti-Corruption Commission of Namibia to comprehensively fulfil its mandate as well as improve its cooperation with other institutions involved in the fight against corruption. | 1.1.1 Number of staff capacitated across ACC/GRN (technical staff) supporting implementation of NACSAP (ACC M&E Plan activity 2.3.3., 2.5.2., 2.6.5., 2.6.9., 3.1.3., 4.1.1., 4.1.2., 7.1.2., ) 1.1.2 Efficient monitoring and evaluation systems in place and operational 1.1.3. Technical assistance to ACC availed through dedicated anti-corruption expertise | 1.1.1. 78 (Year1) 1.1.2 1 (Year 1) 1.1.3. 5 (year 1) | 1.1.1 TBD (Year 4) 1.1.2. TBD (Year 4) 1.1.3. 10 (Year 3) | 1.1.1 EU/UNDP intervention monitoring and reporting system; annual and final reports from the implementing organisation 1.1.2 Official government data, gazettes, EU /UNDP intervention and reporting systems/mechanism. 1.1.3. Baseline assessment, end of project assessment (Survey: Pre & Post action) | Capacity development must be ensured and strengthened at individual and institutional level, due to the risk of staff turnover. ACC has access to adequate resources, including funding, personnel, and technology, to support the improvement of its management and technical capabilities. ACC operates in an environment that supports its efforts to combat corruption, with the necessary legal and regulatory frameworks in place and the cooperation of relevant stakeholders. |
| Output 1.2. | 1.2. The ACC has successfully strengthened its cooperation with relevant institutions engaged in anti-corruption efforts by 2028, resulting in a more coordinated and effective approach to combating corruption and promoting transparency and accountability. | 1.2.1.Number of agreements/commitments for effective partnership signed between the ACC and relevant institutions engaged in anti-corruption efforts. 1.2.2.Percentage increase in joint anti-corruption initiatives or operations between the ACC and relevant institutions from 2024 to 2028. | 1.2.1. 45 (Year 1) 1.2.2. 0% (Year 1) | 1.2.1. 55 (Year 3) 1.2.2. 30% (Year 4) |  | Relevant institutions engaged in anti-corruption efforts have the capacity and willingness to collaborate with the ACC to strengthen their cooperation and achieve a more coordinated and effective approach to combating corruption and promoting transparency and accountability. |
| Output 1.3. | 1.3. By 2028, oversight bodies such as parliament, Office of the Prosecutor General and supreme audit authorities and relevant institutions have demonstrated enhanced capacity through improved training programs, improved advocacy for resource allocations, and strengthened collaboration, leading to more effective monitoring, evaluation, and oversight of government activities and expenditures. | 1.3.1. Number of training capacity building interventions developed and conducted for oversight bodies from 2024 to 2028, and the percentage of oversight body staff who have participated in these programs. 1.3.2 Number of audited/reviewed government activities and expenditures (2024-2028) and implementation rate of corrective actions/recommendations | 1.3.1. 0 (Year 1) 1.3.2. 403 (Year 1) | 1.3.1. 5 (Year 4) 1.3.2. 450 (Year 4) |  | Political will and commitment to improve institutional capacity and effectiveness in oversight and accountability. Oversight bodies have access to adequate resources, including financial, human, and technological resources, to implement improved training programs and strengthen their collaboration. There is a culture of accountability and transparency in government institutions, and they are receptive to oversight and accountability mechanisms. There is a mechanism for measuring and evaluating the effectiveness of oversight bodies, and there is a culture of learning and continuous improvement. |
| Outcome 2 | By 2028, the ACC has successfully implemented/executed the National Anti-Corruption Strategy and Action Plan. | 2.1.1. Percentage of the National Anti-Corruption Strategy and Action Plan's objectives and activities that have been implemented and achieved by 2028, as measured through regular monitoring and evaluation of progress reports. | 2.1.1. 0 93% (Year 1) | 2.1. 100% (Year 4) | 2.1. Effective intervention for monitoring and reporting system; annual and final reports from the implementing organisation (EU/UNDP M&E, quality assurance verifications,) | OMSs have been capacitated to effectively implement activities the NACSAP |
| Output 2.1. | 2.1. Effective implementation of the National Anti-Corruption Strategy and Action Plan through the establishment of robust monitoring mechanisms, stakeholder engagement, capacity-building initiatives, and the enforcement of anti-corruption measures. | 2.1.1. Number of public institutions that have a code of conduct/integrity plan and monitor its implementation 2.1.2 Number of citizens awareness campaigns to combat corruption. 2.1.3. Percentage increase of the monitoring and evaluation of the Whistleblower Protection Act, 10 of 2017 and Witness Protection Act, 11 of 2017 implemented and monitored. | 2.1.1. 0 (Year 1) 2.1.2. 3 (Year 1) 2.1.3. 0% (Year 1) | 2.1.1 30 (Year 4) 2.1.2. 6 (Year 4) 2.1.3. 100% (Year 4) | 2.1.1 EU/UNDP intervention monitoring system; annual and final reports from the implementing organisations 2.1.1. EU/UNDP intervention monitoring system; annual and final reports from the implementing organisations; government and ACC reports. 2.1.3. MoJ/ACC annual reports | Strong political will and commitment from the government and relevant stakeholders to fully implement the strategy and action plan, and that there are adequate resources and capacity to support the implementation process. |
| Output 2.2. | 2.2. The ACC has achieved all the objectives outlined in the National Anti-Corruption Strategy and Action Plan by demonstrating its commitment to fighting corruption and promoting accountability and transparency in all sectors of society. | 2.2.1. Compliance Rate: Percentage of key performance indicators (KPIs) from the NACSAP that the ACC has successfully met by 2028, indicating the level of achievement towards the plan's objectives. 2.2.2. Stakeholder Perception: Reduction in citizen perception of the ACC's commitment to fighting corruption and promoting accountability and transparency in various sectors of society, providing qualitative insights into the impact and effectiveness of the ACC's efforts. | 2.2.1. 0 % (Year 1) 2.2.2. 49 (Year 1) | 2.2.1. 10% (Year 4) 2.2.2. 40 (Year 4) | Transparency International's (TI) Corruption Perception Index (CPI) Africa Peer Review Mechanism (APRM) Annual Report | The ACC operates in an environment that supports its efforts to combat corruption, with the necessary legal and regulatory frameworks in place and the cooperation of relevant stakeholders |

- Theory Of Change

NACSAP Strategic Objectives

Objective 2: Preventing corruption in government offices, ministries and agencies, public enterprises, regional councils, local and traditional authorities

Objective 3: Strengthening efforts to deter corruption

Strategic Objective 4: Conducting extensive anti-corruption education

Strategic Objective 5: Enhance measures and increase accountability to prevent corruption in the private sector

Strategic Objective 6: Engaging civil society, non-governmental organisations, and the media in combating corruption.

Strategic Objective 8: Enhance engagement and participation of youth in anticorruption programmes

Activities by Output (In Line with NACSAP Strategic Objectives)

Outcome 1: By 2028, the ACC and relevant institutions have enhanced management and technical capacity resulting in the comprehensive fulfilment of its mandate and strengthened cooperation with other institutions engaged in the anti-corruption efforts.

Output 1.1.	Strengthened management and technical capacity of the Anti-Corruption Commission of 			Namibia to comprehensively fulfil its mandate as well as improve its cooperation with other 		institutions involved in the fight against corruption.

- Access to Information

  - Provision of technical assistance in co-designing and developing a roadmap and operational plan toward establishment of an independent Information Commission which will help in the enforcement of the ATI legislation and accountability.

  - Develop or adopt guidelines and tools to promote and accelerate the implementation of access to information and transparency in government processes.

  - Implement capacity building programs to enhance the knowledge and skills of government officials, civil society organizations and communities on access to information.

- Sound Financial Management and Transparency of the procurement system:

  - Conduct assessments/review of existing financial management and procurement systems in relevant government institutions.

  - Establish a robust financial management system that ensures the proper use and accountability of public funds in the procurement process.

  - Support the establishment of internal control and or Corruption risk assessment mechanisms and systems to prevent corruption in financial management processes at all levels.

- Alignment of Legislation to International Extractive Industry Standards:

  - Conduct a comprehensive review of existing national legislation related to the extractive industry to identify gaps and inconsistencies with international standards.

  - Identify gaps and areas where alignment with international standards, such as transparency and accountability measures, are required (recommendations).

  - Provide technical assistance and support to relevant government institutions for the revision/amendment and development of legislation in line with international standards (e.g. EITI)

- Mechanisms of Allocating Fishing Quotas:

  - Conduct/review an analysis of the current mechanisms for allocating fishing quotas through conducting a corruption risk assessment in the fisheries sector.

  - Development of a comprehensive National Framework for conducting Corruption Risk Assessment and financial management in public and private institutions.

  - Support the development and implementation of transparent and accountable mechanisms for the allocation of fishing quotas, including stakeholder consultations and the establishment of clear criteria and procedures

Output 1.2.	The ACC has successfully strengthened its cooperation with relevant institutions engaged in anti-corruption efforts by 2028, resulting in a more coordinated and effective approach to combating corruption and promoting transparency and accountability.

- Strengthen Stakeholder Engagement and discourse:

  - Foster collaboration and coordination among all stakeholders, including the public sector, private sector, legislature, and civil society. Special attention to be given to the anti-corruption coordination committees, which play a crucial role in ensuring the successful implementation of NACSAP.

  - Establishing a stakeholder engagement  platform that outlines the roles and responsibilities of each stakeholder group, and the mechanisms for their participation in the plan's implementation.

  - Establishment of stakeholder network/ forums to facilitate collaboration and knowledge-sharing around the NACSAP implementation

Output 1.3.	By 2028, oversight bodies such as parliament, Office of the Prosecutor General and supreme audit authorities and relevant institutions have demonstrated enhanced capacity through improved training programs, improved advocacy for resource allocations, and strengthened collaboration, leading to more effective monitoring, evaluation, and oversight of government activities and expenditures.

- Capacity Building and Ethics Promotion:

  - Develop and implement a capacity building program for government officials, civil society organizations, and private sector actors to enhance their understanding and skills in anti-corruption measures, ethical practices, and governance and transparency standards.

  - Develop Capacity building for enhanced digital forensics, data analytics and forensic Analysis.

  - Support and refine ethics promotion campaigns for awareness raising and promote ethical behaviour among public officials, civil society organizations, and private sector actors, using various communication channels such as social media, print and electronic media, and community outreach programs.

Outcome 2: By 2028, the ACC has successfully implemented/executed the National Anti-Corruption Strategy and Action Plan.

Output 2.1. Effective implementation of the National Anti-Corruption Strategy and Action Plan through the establishment of robust monitoring mechanisms, stakeholder engagement, capacity-building initiatives, and the enforcement of anti-corruption measures.

- Strengthening Anti-Corruption Legislation:

  - Provide technical assistance and support to strengthen the legal framework for combating corruption, including the revision and development of anti-corruption laws, review whistleblower and witness protection regulations, and procedures.

  - Enhance the capacity of relevant institutions and stakeholders for effective implementation and enforcement of anti-corruption legislation.

- Strengthening the oversight and coordination role of the ACC as the secretariat of NACSAP.

  - Develop and implement a comprehensive capacity-building program for the ACC to strengthen its oversight and coordination role as the secretariat of NACSAP, including training on strategic planning, project management, and stakeholder engagement.

  - Review and action a robust monitoring and evaluation framework to assess the performance of NACSAP and its member institutions, providing regular reports to stakeholders and the public on progress towards achieving the objectives of the NACSAP.

  - Procurement of ICT Equipment/Services for Education Awareness.

  - Support evaluation of the current NACSAP to inform development of a 3rd NACSAP

Output 2.2.	The ACC has achieved all the objectives outlined in the National Ant-Corruption Strategy and 		Action Plan by demonstrating its commitment to fighting corruption and promoting 			accountability and transparency in all sectors of society.

- Engaging Civil Society and NGOs in Combatting corruption:

  - Support the organization of National anti-corruption public dialogue and corruption awareness for youth bodies at national, regional and local levels.

  - Provide support to Civil Society organisations to exercise their watchdog/awareness raising/consultative/educative function.

  - Initiate and administer a Small Grants Program aimed at providing financial support to relevant Civil Society Organizations (CSOs).

## Methodology

UNDP Namibia will be responsible for the overall coordination and management of the Action inclusive of planning, implementation, monitoring, financial management, documentation and reporting. The action will be held within UNDP Namibia’s Governance Responsive Institutions and Citizen Engagement (GRICE) portfolio. UNDP will lead the development of annual workplans with clear deliverables for a duration within the agreed timelines and partnership with relevant stakeholders. UNDP Namibia will recruit an International Anti-Corruption expert to ensure implementation and oversight of the action for the duration of the financing agreement. UNDP will include project office costs and other general operating Costs in annexure III for the budget.

The Action will follow the UNDP Programme and Project Management (PPM) procedures. The Action will promote gender and disability inclusion, while emphasizing active monitoring and evaluation to provide decision making data for adaptive implementation and agile programming. Leveraging UNDP’s comparative advantage and mandate, the action will strengthen and promote democratic, accountable, transparent, and effective government systems through a people-centred, systemic approach that is innovative and draws on the opportunities of digitalization.

The Action will pursue the following distinct methods of implementation; a) Advocacy and policy dialogue with national policy decision maker including the simplification and dissemination of laws and policies; b) reinvigorated capacity development that is people centred, co-owned and future orientated; c) knowledge management and documentation of good practices; and d) partnership and coordination including north-south, south-south and triangular cooperation.

The Action will consider innovative strategies and interventions in response to the overall action objective. UNDP will ensure observation and learning from other programs and engaging with the local social (innovation) communities, identifying ‘under the radar’ organizations and individuals with potentially disruptive solutions and insights; Communicating within and outside the country about learnings, outcomes and failures, and for strengthening implementation, monitoring and evaluating policy interventions and informing policy review efforts. Moreover ensuring seamless administration of the effort and of emerging business and governance models, making it efficient and transparent.

The UNDP Country Office will build and maintain political and institutional relationships through the UNDP Resident Representative or Deputy Resident Representative, ensuring effective liaison with strategic partners, and ensuring the Action advances national development goals. Additionally UNDP will leverage expertise within the UN system in the identification of international, regional and local technical thematic anti-corruption experts/specialists in line with National partner’s needs.

While UNDP's anti-corruption initiatives bolster public authorities' legitimacy and trust in governance, accelerating SDG achievement. Effective, transparent, and inclusive governance mechanisms and institutions are crucial to fulfilling the needs of all individuals, as enshrined in the SDGs. Through a small grants programme, UNDP will develop a small grants program, on corruption prevention to complement existing and ongoing in country corruption prevention initiatives for local communities. This will include the development of small grant goals and objectives in line with the description of action. The small grants will be based on the need to promote transparency, enhance accountability, and integrity in society.

Strengthening Transparency and Accountability in Namibia through Community-Led Corruption Prevention Initiatives

The proposed project will allocate a total of USD 50,000 in small grants to civil society organizations (CSOs) in Namibia. The value of each individual grant will be determined based on established criteria developed in partnership with the CSOs through a comprehensive consultation process. The eligibility criteria for grant applicants, such as non-governmental organizations (NGOs) and community-based organizations (CBOs) may include the requirements  legally recognized organizations in good standing, with a clear mission and objectives that align with the description of action priorities. The applicants are assessed on a proven track record of successfully implementing programs or projects related to the grant's objectives inclusive of the necessary capacity to manage and account for grant funds, including financial management and reporting requirements.

The UNDP country office will establish necessary evaluation criteria such as relevance, feasibility, impact, and sustainability. An Evaluation Committee will be formed through a selection of experts to review and evaluate grant applications, ensuring a fair and transparent evaluation process. The action will issues grants to CSOs to a total value of USD50,000.00 (approximately 45,000 Euros). The value per grant will be determined based on established criteria to be set in partnership with CSOs through comprehensive consultation.

- Grant Allocation and Criteria

The key elements of the grant allocation and criteria are as follows:

Grant Allocation:

  - Total grant funding available: USD 50,000 (+- 46,000 Euro)

  - Anticipated number of grants: Minimum 2; Maximum 3; grants

  - Average grant size: Approximately USD 16,667 - 25,000 per grant

Grant Criteria: Organizational Capacity

- Proven track record of at least three years in implementing anti-corruption initiatives.

- Demonstrated ability to manage and report on small grants, including financial and project management capabilities.

- Established governance structures and internal controls to ensure accountability and transparency.

Alignment with Action Objectives:

- Projects must align with the overarching goal of reducing corruption and bribery across various sectors in Namibia.

- Initiatives should focus on enhancing governance structures, transparency, and accountability mechanisms.

- Proposals should include components that promote ethical behaviour and strengthen legal frameworks.

Innovative Approaches:

- Emphasis on innovative and evidence-based strategies to combat corruption.

- Use of technology and digital tools to increase transparency and public engagement.

- Creative public awareness campaigns and educational programs aimed at fostering an environment intolerant of corrupt practices.

Stakeholder Engagement:

- Ability to engage a broad range of stakeholders, including government, private sector, and the general public.

- Plans for meaningful community involvement and collaboration with other organizations to amplify impact.

- Strategies for promoting public participation in governance and decision-making processes.

Measurable Impact:

- Clear, measurable objectives and outcomes that demonstrate a significant reduction in corruption and bribery.

- Detailed monitoring and evaluation plans to track progress and effectiveness of the initiatives.

- Commitment to sharing best practices and lessons learned with other CSOs and stakeholders.

Sustainability:

- Proposals should outline how the initiatives will be sustained beyond the grant period.

- Plans for securing additional funding or resources to continue anti-corruption efforts.

- Strategies for institutionalizing successful practices and integrating them into existing frameworks.

Compliance with Legal and Ethical Standards

- Adherence to all relevant legal and regulatory requirements in Namibia.

- Commitment to ethical practices, including conflict of interest policies and anti-bribery measures.

- Transparent reporting and accountability mechanisms to ensure responsible use of grant funds.

## Indicative Action plan (Year 1 & 2)

|  | Year 1 |  |  |  |  |  |  |  |  |  |  |  | Year 2 |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | (proposed) Implementing Party |
| Outcome 1: By 2028, the ACC and relevant institutions have enhanced management and technical capacity resulting in the comprehensive fulfilment of its mandate and strengthened cooperation with other institutions engaged in the anti-corruption efforts. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ouput 1.1: Strengthened management and technical capacity of the Anti-Corruption Commission of Namibia to comprehensively fulfil its mandate as well as improve its cooperation with other institutions involved in the fight against corruption |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity: 1. Access to Information |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1. Provision of Technical Assistance for Co-Designing and Developing a Roadmap and Operational Plan for an Independent Information Commission which will help in the enforcement of the ATI legislation and accountability. |  | X | x | x | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  |  |  |  |  | MICT/MoJ/ACC/MME |
| 1.2. Develop or adopt guidelines and tools to promote and accelerate the implementation of access to information and transparency in government processes. |  |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X |  |  |  |  |  |  |  |  | MICT/MOJ/ ACCLAB / UN agencies/NMT |
| 1.3. Implement capacity building programs to enhance the knowledge and skills of government officials, civil society organizations and communities on access to information. |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  |  |  |  |  | ACC/UNAM/NUST/ IUM/UoB |
| Activity: 2. Sound Financial Management and Transparency of the procurement system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1. Conduct assessments/review of existing financial management and procurement systems in relevant government institutions |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X | X | X | X | X | X |  |  |  | MoF/ACC/UN/NAMRA/CSO |
| - Establish a robust financial management system that ensures the proper use and accountability of public funds in the procurement process |  |  |  |  | X | X | X | X | X | X | X |  | x | X | X | X | X | X | X | X | X |  |  |  | MoF/ACC/UN/NAMRA/CSO |
| - Support the establishment of internal control and or Corruption risk assessment mechanisms and systems to prevent corruption in financial management processes at all levels. |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X | X | X | X | X | X |  |  |  | MoF/ACC/UN/NAMRA |
| Activity: 3. Alignment of Legislation to International Extractive Industry Standards |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1. Conduct a comprehensive review of existing national legislation related to the extractive industry to identify gaps and inconsistencies with international standards. |  |  | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | MME/NCGI/CSO/ACC |
| 3.2. Identify gaps and areas where alignment with international standards, such as transparency and accountability measures, are required (recommendations) |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  |  |  | MME/ACC/MoJ |
| 3.3. Provide technical assistance and support to relevant government institutions for the revision and development of legislation in line with international standards. |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X | X | X | X | X | X |  |  |  | MME/ACC/MoJ |
| Activity: 4. Mechanisms of Allocating Fishing Quotas |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1. Conduct an analysis of the current mechanisms for allocating fishing quotas through conducting a corruption risk assessment in the fisheries sector. |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X | X | X | X | X | X | X |  |  | MFMR/ACC/UNODC/MME/MoJ |
| 4.2. Development of a comprehensive National Framework for conducting Corruption Risk Assessment and financial management in public and private institutions. . |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X | X | X | X | X | X | X |  |  | MFMR/ACC/UNODC/MME/MoJ |
| 4.3. Support the development and implementation of transparent and accountable mechanisms for the allocation of fishing quotas, including stakeholder consultations and the establishment of clear criteria and procedures. |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X | X | X | X | X | X | X |  |  | MFMR/ACC/UNODC/MME/MoJ |
| Output 1.2. The ACC has successfully strengthened its cooperation with relevant institutions engaged in anti-corruption efforts by 2028, resulting in a more coordinated and effective approach to combating corruption and promoting transparency and accountability. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity: 5. Strengthen Stakeholder Engagement and Discourse |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.1. Foster collaboration and coordination among all stakeholders, including the public sector, private sector, legislature, and civil society. Special attention to be given to the anti-corruption coordination committees, which play a crucial role in ensuring the successful implementation of NACSAP. |  | X |  |  | X |  |  |  |  |  |  |  |  | x |  |  | x |  |  |  |  |  |  |  | MoJ/OPM/CSO/ACC |
| 5.2. Establishing a stakeholder engagement plan/platform that outlines the roles and responsibilities of each stakeholder group, and the mechanisms for their participation in the plan's implementation |  |  | x |  |  |  | x |  |  |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  | MoJ/OPM/CSO/ACC |
| 5.3. The establishment of stakeholder network/ forums to facilitate collaboration and knowledge-sharing around the plan's implementation. |  |  | X |  |  |  | X |  |  |  |  |  | X |  |  |  | X |  |  |  | x |  |  |  | ACC/CSOs/ O/M/As/UN |
| Output 1.3. By 2028, relevant institutions have demonstrated enhanced capacity through improved training programs, improved advocacy for resources allocations, and strengthened collaboration, leading to more effective monitoring, evaluation, and oversight of government activities and expenditures. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity: 6. Capacity Building and Ethics Promotion |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Develop and implement a capacity building program for government officials, civil society organizations, and private sector actors to enhance their understanding and skills in anti-corruption measures, ethical practices, and governance and transparency standards. |  |  | x |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ACC/MoJ/O/M/As/UN/UNODC |
| - Develop Capacity building for enhanced digital forensics, data analytics and forensic Analysis. |  |  |  | x |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ACC/MoJ/O/M/As/UN/UNODC |
| - Support and refine ethics promotion campaigns for awareness raising and promote ethical behaviour among public officials, civil society organizations, and private sector actors, using various communication channels such as social media, print and electronic media, and community outreach programs. |  |  | X | X | X | X | X |  |  |  |  | X | X | X | X | X |  |  |  |  |  |  |  |  | ACC/MoJ/O/M/As/UN/UNODC |
| Outcome 2: By 2028, the ACC has successfully implemented/executed the National Anti-Corruption Strategy and Action Plan. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1 Effective implementation of the National Anti-Corruption Strategy and Action Plan through the establishment of robust monitoring mechanisms, stakeholder engagement, capacity-building initiatives, and the enforcement of anti-corruption measures |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity: 7. Strengthening Anti-Corruption Legislation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7.1. Provide technical assistance and support to strengthen the legal framework for combating corruption, including the revision and development of anti-corruption laws, review whistleblower and witness protection regulations, and procedures. |  |  |  |  | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ACC/MoJ/O/M/As/UN/UNODC |
| 7.2. Enhance the capacity of relevant institutions and stakeholders for effective implementation and enforcement of anti-corruption legislation. |  |  |  | x | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ACC/MoJ/O/M/As/UN/UNODC |
| Activity: 8. Strengthening the oversight and coordination role of the ACC as the secretariat of NACSAP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Develop and implement a comprehensive capacity-building program for the ACC to strengthen its oversight and coordination role as the secretariat of NACSAP, including training on strategic planning, project management, and stakeholder engagement. |  | x |  |  | x |  |  |  |  |  |  | x |  | x |  | x |  | x |  | x |  |  |  |  | ACC/MoJ/O/M/As/UN/UNODC |
| - Review and action a robust monitoring and evaluation framework to assess the performance of NACSAP and its member institutions, providing regular reports to stakeholders and the public on progress towards achieving the objectives of the NACSAP. |  |  | x |  |  | x |  |  |  |  |  |  |  | x |  |  | x |  |  | x |  |  |  |  | ACC/MoJ/O/M/As/UN/UNODC |
| - Procurement of ICT equipment/software /services for Education Awareness. |  |  |  |  | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ACC/UN |
| - Support evaluation of the current NACSAP to inform development of a 3rd NACSAP |  |  |  |  | X | X | X |  |  |  |  | X | X |  |  |  |  |  |  |  |  |  |  |  | ACC/MoJ/O/M/As/UN/UNODC |
| Output 2.2. The ACC has achieved all the objectives outlined in the National Ant-Corruption Strategy and Action Plan by demonstrating its commitment to fighting corruption and promoting accountability and transparency in all sectors of society. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity: 9. Engaging Civil Society and NGOs in Combatting corruption: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9.1. Support the organization of National anti-corruption public dialogue and corruption awareness for youth bodies and political party youth wings at national, regional and local levels. |  |  |  | x |  |  |  |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | ACC/CSOs/Media |
| 9.2. Provide support to Civil Society organisations to exercise their watchdog/awareness raising/consultative/educative function. |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | ACC/CSOs/ Media |
| 9.3. Initiate and administer a Small Grants Program aimed at providing financial support to relevant Civil Society Organizations (CSOs). |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | UNDP/ACC/CSO |
| 10. Project Office Costs (General Operating and Other Costs) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10.1. Project Management, staffing, Quality Assurance, Monitoring, Meetings convened |  |  | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | UNDP |
| 10.2. Goods and Services to support project activities procured and maintained (ICT) | x | x | x | x | x | x | x | x | x |  |  | x | x | x | x | x | x | x | x | x | x | x |  |  | UNDP |
| 10.3. Project Quality Assurance |  |  | x |  |  | x |  |  |  |  |  | x |  | x |  |  | x |  |  | x |  |  |  |  | UNDP/EU |

## Implementation Arrangements

In line with the action document, UNDP will be responsible for overall management of the technical, administrative and financial management of the respective project components. UNDP will primarily provide technical assistance to the Anti-Corruption Commission and carry out budget implementation tasks related to the procurement of goods, services and issuance of grant awards to civil society organizations, following UNDP Namibia operational rules and regulations.

UNDP Namibia, in coordination with the relevant government authorities and partners, will be responsible for the overall implementation of the project. A project manager at UNDP will be recruited to oversee day-to-day operations, monitoring, and reporting. Regular coordination meetings and progress reviews will be conducted to ensure effective implementation of the action. The implementation will entail managing the technical and financial aspects of all project components, including administrative tasks, except for evaluation and audit.

A Project Steering Committee (PSC) will be set up to oversee the overall strategic direction, implementation, and progress of the Action. The PSC will review and discuss the programme implementation progress, identify opportunities, achievements and constraints and adopt amendments if/as needed. The PSC will be chaired by the Anti-Corruption Commission and co-chaired by UNDP. The PSC will include representatives of other key stakeholders (National Planning Commission, Ministry of Finance, Ministry of Justice, Ministry of Mines and Energy, Ministry of Information Communication and Technology, Namibia Revenue Agency and at least 2 representatives from civil society from the environmental and wider democracy/human rights/legal sector) and a representative of the EU Delegation Other representatives of OMAs may be invited on a needs/variable basis. Through the PSC bylaws, the inclusion of gender expertise into the committee will be considered. The PSC shall meet  three times a year.

The day-to-day technical, administrative and financial monitoring of the implementation of this action will be a continuous process, and part of UNDP’s responsibilities. To this aim, UNDP shall establish an internal monitoring system for the action and elaborate regular progress reports (not less than annual) and final reports to the EU.

Grants to Civil Society Organizations

Corruption remains a pervasive issue in Namibia, hindering the country's economic growth and development. To combat this problem, the government and civil society organizations (CSOs) must work together to promote transparency and accountability. Through this action UNDP will support CSOs in Namibia to develop and implement effective corruption prevention initiatives that compliment ongoing intervention in country.

Although the country's Corruption Perceptions Index (CPI) score has improved, it still ranks low compared to other countries in the region. To address this issue, the government has established various institutions and laws, to combat corruption. However more needs to be done to engage citizens and promote transparency. Through supporting CSOs in developing and implementing community-led corruption prevention initiatives the action aims to:

a) Strengthen Capacity of Grassroot institutions: Provide training and capacity-building programs for CSOs to enhance their understanding of corruption prevention strategies and effective project management.

b) Community Engagement: Engage local communities in the fight against corruption through awareness campaigns, public events, and community outreach programs.

c) Collaboration and Networking: Foster collaboration and networking among CSOs, government agencies, and other stakeholders to share best practices and leverage resources towards corruption prevention.

The grants will be initiated over a 24 month period, targeting CSO’s awarding a minimum of two (2) grants and where possible a maximum of three (3) grants to CSOs at a total of approximately fifteen  thousand USD per CSO. The action will develop detailed expression of interest in accordance with the UNDP rules and regulations.

## Human Resources and Project Costs

The effective management of the action will require, human resource expenses which encompass a full-time non-Namibian-Corruption Specialist who will also serve as the overall Project Manager. Moreover, the Direct Implementation Modality costs include the following staff, whose expenses will be apportioned as a percentage over the action duration and their costs are reflected proportionally in the Budget (Annex 2):

Anti-Corruption Specialist: The Specialist will oversee the day to day programme and technical communication as well as implementation and management of the action. The specialist will further prepare regular briefings/progress reports to be shared with the Steering Committee as well as ensure regular communication with the EU.

In addition, the Direct Implementation Modality costs of the support to the project comprise of UNDP staff who will serve the project using a percentage of their costs and will recur over the duration of the agreement as follows:

- Anti-Corruption Specialist/Expert (100% IPSA 11) - will provide project oversight and implementation for the entirety of the project and oversee day-to-day operations, monitoring, and reporting.

- GRICE Portfolio & Programme Analyst (30%) – to ensure alignment with UNDP portfolio approach and synergy with other Portfolio interventions.

- Operations (Communications, HR, M&E, Finance & Procurement) (10%) - will ensure that the end to end process of procurement, logistics and general operations for the project to succeed are optimal.

These costs will be covered in the detailed budget under action 10. Project Office Costs (General Operating and Other Costs) which will incorporate project costs for procurement of necessary equipment, including two laptops mobile devices, along with minimal expenses for office phone services inclusive of general utilities such as electricity. Transportation costs encompass leasing a project vehicle, fuel, email, Office 365 subscription (1 user), ink cartridges, stationery, and a postpaid mobile phone plan for one user to facilitate official travel for project staff.

## Synergies with other Programmes and Initiatives

Within the UNDP Namibia GRICE portfolio, the action will contribute to the accelerated delivery of top-quality programmatic results for the SDGs and in particular SDGs 16/17. The Overall Objective (Impact) of this action aims to substantially reduce corruption and bribery in all their forms particularly in line with the objectives of SDG 16, on Peace, Justice and Strong Institutions.

The UNDP Namibia Sustainable Inclusive Green Growth (SIGG) Portfolio aims to achieve sustainable, inclusive, and green growth in Namibia. This action will contribute to the results of the portfolio by promoting good governance, environmental sustainability, and economic progression, which are integral to achieving the SDGs. The SIGG Portfolio focuses on developing solutions for employment creation, pro-poor income and livelihood development, and environmental management, aligning with Namibia's development priorities and the NDP5. By addressing economic inequality, promoting environmental sustainability, and improving governance, the SIGG Portfolio indirectly contributes to the fight against corruption by fostering transparency, accountability, and equitable economic development.

The UNDP Sustainable Environmental Management, Energy and enhanced Resilience (SEMER) Portfolio focuses on issues such as environmental management, climate resilience, and energy efficiency, aligning with Namibia's development priorities and the NDP5. By addressing economic inequality, promoting environmental sustainability, and improving governance, the SEMER Portfolio indirectly contributes to the fight against corruption by fostering transparency, accountability, and equitable economic development. The SEMER portfolio is structured to provide entry points for solving some of Namibia's environmental challenges, with projects that support the country's environment and climate targets. The portfolio is largely funded through the Green Environment Facility and UNDP Core resources. Interventions in the portfolio include the Benguela Current Large Marine Ecosystem (BCLME) which is  joint initiative by the governments of Angola, Namibia, and South Africa to manage and utilize the marine resources within BCLME programme.

Additionally through the SEMER portfolio UNDP Namibia has a project called "Strengthening Environmental Governance and Improving Health and Safety in Critical Small-Scale Mining Hotspots in Namibia". The project is supported by the Ministry of Mining and Energy (MME) and Sweden's Sida with a goal to assist small-scale gemstone miners in Namibia learn how to mine responsibly. The project considers environmental compliance, heritage laws, and impact assessments which capacitates small-scale miners in first aid, health, and safety guidelines and safeguards. Artisanal and small-scale mining (ASM) is a key source of income for many unemployed people in Namibia, especially those in rural communities and vulnerable groups. Small-scale miners use basic equipment and technology to exploit small mineral deposits that are not economical for large-scale mining operations.

## Sustainability

This action with support of the EU an in partnership with UNDP will contribute to the broader UN Corporation Framework’s objective toward supporting the Government of the Republic of Namibia in achieving its national development priorities and accelerating the achievement of the SDGs by 2030. The UN corporation framework aims to promote sustainable, inclusive, and green growth, good governance, and environmental sustainability.

The project will prioritize sustainability by focusing on capacity building, policy coherence, institutional strengthening, and knowledge transfer, while working towards the integration of anti-corruption measures into national policies, legislation, and practices. The project will also support the establishment of mechanisms for monitoring and evaluating the effectiveness of anti-corruption efforts.

## Sustainability post implementation:

Achieving sustainability through the action will be focused on enhancing anti-corruption efforts which involves addressing financial, institutional, and environmental aspects. The action aims to institutionalize several strategies to promote sustainability in the following dimensions:

Financial Sustainability: Closing the loop on financial loss through corruption provides diversified funding and revenue streams for national and local development. This action will promote financial sustainability by addressing corruption risks in financial decision-making processes and will contribute to the financial sustainability of the action.

Institutional Sustainability: Capacity building investment in anti-corruption institutions, mechanisms, legislation and personnel will advance institutional resilience in curbing corruption. The action will have invested in the development and enhancement of skills, knowledge and accountability and compliance systems necessary for effective corruption prevention, investigation, and enforcement.

Institutionalization of Good Practices: The action will further aim at embedding anti-corruption good practices into the institutional culture and standard operating procedures. By developing and implementing policies and protocols that promote transparency, accountability, and ethical conduct within the organization.

Public Awareness and Advocacy: Foster a culture of accountability and integrity through public awareness campaigns and advocacy programs. Engage with civil society organizations, media, and the public to create a supportive environment for anti-corruption initiatives.

Environmental Sustainability: Integrate environmentally sustainable practices into project operations by undertaking green practices. This includes minimizing paper usage, adopting energy-efficient technologies, and implementing waste reduction measures to contribute to environmental conservation.

Community Engagement: Involve local communities in anti-corruption efforts, emphasizing the link between environmental sustainability and corruption prevention. Community participation fosters a sense of ownership and responsibility for protecting natural resources.

Compliance with Environmental Standards: The Action will contribute to ensure that the project adheres to relevant environmental standards and regulations. Demonstrating a commitment to environmental responsibility enhances the actions credibility and support from stakeholders. By incorporating these strategies, the action will focus on enhancing anti-corruption interventions which contribute to financial stability, institutional resilience, and environmental sustainability, ultimately increasing the likelihood of long-term success in combating corruption.

## Risk Analysis and contingency Plan

The following are key risks associated with the proposed action highlighting relevant mitigation actions:

| Proposed Action | Risk | Mitigation Measure |
| --- | --- | --- |
| Access to Information | - Delay in operationalization of the ATI bill - Unauthorized access to sensitive information by individuals without proper authorization. | - Advocate for implementation of ATI bill - Implement access controls and user permissions based on the principle of least privilege to restrict access to sensitive information only to authorized personnel. |
| Sound Financial and Procurement Management | - Mismanagement of financial resources leading to inefficiency or corruption. | - Conduct regular audits and financial reviews to ensure transparency and accountability in financial transactions and procurement processes. |
| Alignment of Legislation to International Extractive Industry Standards | - Non-compliance with international standards leading to legal issues or reputational damage. | - Develop a roadmap for aligning national legislation with international standards, conduct stakeholder consultations, and establish a monitoring mechanism to ensure compliance. |
| Mechanisms of Allocating Fishing Quotas | - Intransparent distribution of fishing quotas leading to overfishing or depletion of marine resources. | - Implement transparent and equitable mechanisms for allocating fishing quotas, conduct regular social& environmental process assessments of fish stocks, and involve stakeholders in decision-making processes. |
| Strengthening Anti-Corruption Legislation | - Weak enforcement of anti-corruption laws leading to continued corrupt practices. | - Enhance enforcement mechanisms, establish independent anti-corruption bodies, and conduct regular reviews of legislation to address loopholes. |
| Strengthening the oversight and coordination role of the ACC as the secretariat of NACSAP | - Inadequate oversight leading to inefficiencies or lack of coordination in anti-corruption efforts. | - Develop a robust monitoring and evaluation framework, establish clear reporting mechanisms, and provide training to enhance oversight and coordination capabilities. |
| Enhance Monitoring and Evaluation | - Ineffective monitoring leading to the inability to track progress or identify areas for improvement. | - Implement real-time monitoring systems, conduct regular evaluations, and use data-driven insights to make informed decisions and adjustments. |
| Strengthen Stakeholder Engagement | - Lack of stakeholder buy-in leading to resistance or limited support for anti-corruption initiatives. | - Develop a comprehensive stakeholder engagement strategy, involve stakeholders in decision-making processes, and provide regular updates and feedback mechanisms to foster collaboration and participation. |
| Capacity Building and Ethics Promotion | - Insufficient skills or ethical awareness among personnel leading to misconduct or non-compliance. | - Implement capacity-building programs, ethics training, and establish clear guidelines and codes of conduct to promote ethical behaviour and enhance skills. |
| Engaging Civil Society and NGOs in Combatting corruption | - Limited involvement of civil society and NGOs leading to a lack of transparency and accountability. | - Foster partnerships with civil society and NGOs, involve them in anti-corruption initiatives, and provide platforms for collaboration and feedback to enhance transparency and accountability efforts. |

## General overview on Visibility and communication

UNDP will inform the relevant stakeholders of the Action through the EUs support by displaying the EU emblem and brief funding statement as appropriate on all communication materials, online, offline, and on social media,  related to the action and in line with the EU-UN Financial and Administrative Framework Agreement, Annex II. General Conditions and the EU-UN Joint Visibility Guidelines for the EU-UN Actions in the field. .

UNDP will ensure that the EU Contribution is publicised, including in official publications, such as media coverage, official notices and press statements, reports and other publications refereeing to the Action, which shall display in an appropriate way the EU emblem. All press, visibility materials, inclusive of social media posts, and publications relevant and related to the Action will include the EU’s visual identity, written acknowledgement of the EU’s funding, as well as appropriate disclaimers where relevant.

Once they are agreed upon by the EU and the United Nations, the updated version of the Joint Visibility Guidelines for the EU-UN Actions in the field will become the primary reference point to guide the strategic communications under this Action, together with the EU-UN Financial and Administrative Framework Agreement.

## Monitoring and Evaluation

Agreed evaluation and verification missions will be conducted at appropriate intervals to assess the progress and impact of the project. These missions will provide an opportunity to review the implementation, identify challenges, and make necessary adjustments to ensure the achievement of project objectives. The findings and recommendations from these missions will inform project management and decision-making processes.

The Action will utilize the results-based management (RBM) approach to monitor performance and assess results through the existing UNDP corporate reporting systems. Supportive, supervision and quarterly monitoring of the implementation will be conducted by internal and external monitoring teams using existing tools aligned to UNDP Monitoring and Evaluation systems and requirements. Monitoring will integrate the principles of Leave No One Behind, Human Rights Based Approach and gender equality and women’s empowerment. In line with the UN system wide approach, efforts will be made to ensure the following key elements:

- Tracking progress over time to assess whether the action is narrowing the incidence of corruption.

- Promote community based monitoring and participation by a broad section of stakeholders inclusive of CSOs, to assess the extent to which structural and root causes have been address. Efforts will be made to strengthen citizen engagement through enhanced participation of the most underserved and excluded groups.

- Strengthening of data collection and evidence based decision making.

The monitoring and evaluation officers for UNDP, the ACC and relevant line ministries where necessary will systematically collect information about lessons learned, challenges and other external factors relevant to the implementation and performance of the Action and produce quarterly and annual reports. UNDP will also track and monitor assumptions and risks identified in the Action Results Framework and provide remedial action where required.

Reporting against indicators will be disaggregated according to sex and age, and even further (including disability, location urban/rural, group etc.) where useful. Any monitoring and evaluation will be gender-sensitive, assess gender equality results and implementation of rights-based approach working method principles (participation, non-discrimination, accountability and transparency) in terms of implementation of the project and project outcomes. Key stakeholders will be involved in the monitoring process.

The implementing partners which include; Anti-Corruption Commission, Ministry of Mines and Energy, Ministry of Fisheries, Ministry of Finance, Ministry of Information Communication Technology and other relevant ministries, civil society organizations and media fraternity, contributing to data collection, analysis and monitoring. Where the collection of data for specific indicators is outside of the possibilities of the implementing partner, surveys and studies can -to a certain extent- be financed under the regular budget of the action or outside the action, through relevant support measures.

https://www.npc.gov.na/national-plans/national-plans-ndp-5/

http://hppii.gov.na/wp-content/uploads/2021/03/HPP2.pdf

https://www.npc.gov.na/wp-content/uploads/2021/11/vision_2030.pdf

https://www.transparency.org/en/countries/namibia

https://data.worldbank.org/indicator/SL.UEM.TOTL.ZS?locations=NA

https://au.int/en/treaties/african-union-convention-preventing-and-combating-corruption

https://ippr.org.na/publication/human-rights-impacts-of-the-fishrot-scandal/

https://ippr.org.na/publication/human-rights-impacts-of-the-fishrot-scandal/

https://www.transparency.org/en/countries/namibia

https://whatson.unodc.org/whatson/en/featured-human-story-ippr.html

https://acc.gov.na/documents/31390/31530/Updated%2BProposed%2BNACSAP%2BNamibia%2B2021-2025%2B21%2BApril.pdf/fc5b30bf-6d5c-c24a-e586-22ca3b96bd5c

https://www.nid.org.na/projects-activities/zero-tolerance-for-corruption-campaign

The Namibian government is run by 23 ministerial departments, 8 agencies, 3 offices, and 41 parastatals = 75 total (Target =30).

https://popp.undp.org/programme-and-project-management

https://popp.undp.org/programme-and-project-management