Country: Yemen

Country Plan

Project Title: Addressing the climate crisis and human security through NDC planning and implementation.

Sub-title (national) if any: Enhancing Resilience of Agriculture and Food Security in Yemen

Expected UNDAF/CP Outcome(s):	Outcome 1: “By 2025, people in Yemen, especially women, adolescents and girls and those in the most vulnerable and marginalized communities benefit from better, equal and inclusive access to nutritious food, sustainable and resilient livelihoods and environmental stability”.

Expected CPD Output(s): Output 1.3: Natural resources management improved to enhance sustainable agricultural productivity and climate resilience.

Initiation Plan Start/End Dates:    	March 2025 - March 2026

Implementing Partner: United Nations Development Programme: Yemen Country Office (DIM)

Brief Description

The primary need addressed by this project is the urgent requirement for improved water usage efficiency and enhanced food security among vulnerable communities, particularly in the face of climate change. By integrating smart technologies and advanced crop management practices that consider climate change implications, the project seeks to optimize water usage, thereby mitigating the adverse effects of climate variability on agricultural productivity.

The expected outcomes of this project are multifaceted. Firstly, it aims to improve water usage efficiency through the adoption of modern irrigation technologies and innovative crop management strategies. This will directly contribute to strengthening food security for vulnerable communities by ensuring a more reliable and sustainable agricultural output. Secondly, the project seeks to enhance awareness of climate adaptation measures among smallholder farmers, fostering a culture of preparedness and resilience. Ultimately, the project aims to directly target and benefit 500 smallholder farmers, and indirectly benefit 2000 residents and smallholder farmers through broader impacts on community resilience to climate change.

Programme Period:		1 year

Quantum Project Number: 	01003664

Quantum Output ID:

Gender Marker:			GEN-2

Total resources required           	$500,000

Total allocated resources:	_________

- Regular			_________

- Other:

  - Donor (Japan)          $500,000_

Agreed by UNDP:

# Purpose and Expected Output

The ongoing humanitarian crisis in Yemen, conflict, severe economic decline, and collapsing essential public services have taken an enormous toll on the Yemeni population, exacerbating existing vulnerabilities and inequalities. Yemen is currently suffering from the world’s worst food crisis. Out of its 30 million population, 18.6 million people are in need of food assistance, while an estimated 4.5 million people have been internally displaced. The country’s food systems are expected to face an additional strain due to the effects of climate change, risking human security in and of itself, and exacerbating the potential for conflict. Food insecurity is a longstanding phenomenon in Yemen, with the conflict serving to exacerbate underlying issues, vulnerabilities, and exposure. Prior to the war, just 25% of Yemen’s food was produced domestically, a figure that is substantially decreasing in the years following the outbreak of war. Such issues are exacerbated by poor agricultural governance, particularly with regard to qat production, where myopic benefits to elites are prioritised over food provision for the population.

Due to the lack of smart and modern agriculture and irrigation technologies, inadequate water harvesting and storing infrastructure, most farmers lost their 2023 planting season. One-third of households reported a reduced planted area. With the war and past institutional failures, Yemen’s ability to combat water and food insecurity faces major challenges, including inefficient use of water resources in agriculture; over-exploitation of groundwater and the lack of investments in renewable water harvesting options; neglecting traditional terraces; poorly coordinated planning and water allocations; lack of investment in agricultural value chains and market accessibility; inadequate water governance for managing water and related infrastructure, and limited participation of women. There is a need to leverage existing agricultural practices by equipping farmers with climate-smart modern agriculture and irrigation technologies.

The project is closely aligned with pillar 2: Accelerating adaptation in vulnerable and fragile countries and communities, for increased resilience to climate risks and impacts.  Specifically, the project is aligned with the sub-pillar 2.1. Implement adaptation and risk reduction actions, including ecosystem-based adaptation, coastal adaptation, climate-resilient agricultural practices, adaptation in high-mountain ecosystems due to glacier melting, early warning systems, etc. and ensure they are available in fragile settings and to marginalized groups. By focusing on improved water usage efficiency through water efficient irrigation technologies and innovative crop management practices, the project directly tackles the pressing issue of climate variability's impact on agricultural productivity specifically in vulnerable communities. This approach not only mitigates the immediate risks associated with climate change but also promotes long-term sustainability in food production, thereby enhancing food security by ensuring stable and reliable food supplies for vulnerable communities.

Furthermore, the project underscores the urgent need for green and sustainable transformation in agricultural practices. By fostering improved awareness of climate adaptation measures through trainings and enhanced communication with the Agriculture Research and Extension Authorities, it empowers communities to adopt more resilient and eco-friendly methods. This shift towards sustainability is crucial in building a more resilient agricultural sector that can withstand the challenges posed by climate change. The project's focus on strengthening food security and enhancing climate adaptation awareness reflects a comprehensive strategy to address both the immediate and long-term impacts of the climate emergency, ensuring a sustainable and secure future for the targeted communities.

The proposed project is consistent with the Yemen Technical Needs Assessment (TNA), 2022, which identified both water and agriculture as priority adaptation sectors. The project is also aligned with the National Communications reports, including the Third National Communication (TNC) to the UNFCCC, 2018, and the Intended Nationally Determined Contributions (INDC) that flag water resources as the most vulnerable sector with regard to the effects of climate change in Yemen. The proposed action will build on the contemporary water knowledge accumulated from the two most recent water assessments: Water Availability in Yemen and the Strategic Framework: A Holistic Approach to Addressing Water Resources Challenges in Yemen to start a fundamental shift in water projects focusing on developing and augmenting the water infrastructure for enhancing food security through the sustainable harvesting of renewable water resources and allowing groundwater sources to regenerate. Furthermore, it will contribute to reducing conflict causes, as stated in the Water-related Conflict Assessment Report published  by UNDP in 2023. Finally, the proposed action will align with and complement other Japan-funded projects (as indicated above in the Partnership with Japan section) and build on lesson learned from these projects so far.

The project interventions will be implemented in Wadi Tuban area which is highly impacted by climate change affecting agriculture and food security. The project will be contributing to the implementation of the ongoing formulation of the NDC targets, in line with the UNDP Climate Promise 2025, through the human security lens by strengthening the capacity of vulnerable farmers affected by climate change in Wadi Tuban and equipping them with necessary modern smart agriculture and irrigation technologies that will improve their farms’ productivity and reduce water use. Wadi Tuban was selected due to its vast geographical expanse across multiple governorates and its acute vulnerability to climate change, resulting in severe water scarcity, agricultural decline, increased poverty, displacement, and conflict.The key objectives of Yemen's INDC included prioritizing building resilience and adapting to the impacts of climate change. This included measures to enhance water resource management, improve agricultural practices, protect ecosystems, and develop climate-resilient infrastructure.

| Country NDC sector | Country NDC target | Project activity contributing to this target | Alignment with LT-LEDS, as relevant |
| --- | --- | --- | --- |
| Agriculture | Promoting agricultural drought management as well as sustainable crop and livestock management | The project will disseminate and install water-efficient irrigation technologies for farmers in Tuban | Agriculture sector is one of the emitting sectors. Under the LT-LEDS project, a sector plan as well as an investment plan will be developed to contribute to Low emission development and GHG emissions reduction. |
| Agriculture | Livelihood approaches for integrating natural resources management and preservation of sensitive ecosystems | The project will conduct training of small-holder farmers on climate resilient production practices, which will help people understand how they need to adjust their crop calendar and change their planting and harvesting dates in response to changing climate. | Within the national LT-LEDS, sector-specific strategy and action plan will be developed to identify sector-specific challenges, opportunities, and mitigation measures to reduce emissions and promote sustainable practices within the agriculture sector. Integration of climate change agenda into sectoral plans and policies will facilitate adopting cleaner technologies, energy efficiency, or sustainability practices, leading to lower emissions and support future transition efforts. |
| Cross- cutting | Capacity-building and awareness-raising | The project will deploy social and media platforms for disseminating information on climate change adaptation. This involves developing messages, extension materials, video and audio content and weather forecasts that will assist small-holder farmers to adapt to climate change through transfer of technology and weather information. | Capacities of targeted sector stakeholders from farmers community including women will be enhanced, and opportunities for data and information sharing will be established through the MRV system to be an integral part of the climate information system, which will eventually contribute to awareness raising and capacity building. |

# Management Arrangements

To implement the proposed project, UNDP will leverage the existing management team from the project titled “Integrated Water Resources Management to Enhance Resilience of Agriculture (ERA) and Food Security”, funded by BMZ, Germany through KfW. In addition, the Climate Change, Energy and Environment (CCEE) portfolio will provide strategic guidance, oversee implementation, and review progress to ensure the project's successful execution.

A Field Coordinator will be deployed to facilitate coordination of field activities and engagement with key stakeholders, including the Ministry of Irrigation and Agriculture and Fisheries and its affiliated Office of Agriculture and Irrigation, as well as other relevant stakeholders, for the project's implementation. The project will be supported by the dedicated team from the project of “Integrated Water Resources Management to Enhance Resilience of Agriculture (ERA) and Food Security”, including a Project Team Leader, National Project Manager, Water Resources Management Specialist, Monitoring and Evaluation and Reporting Specialist, Project Officer, Civil Engineer, Communication officer and Admin and Finance Associate.

The project team will submit the final narrative report within three months after the completion of project, and the final financial report within one year upon completion of project.

The project will ensure cooperation and consultation with JICA on technical expertise, knowledge exchange and best practices to implement the project’s activities. The lessons learned from the JICA-supported project under the UNDP Yemen portfolio will be sought and applied.

# Results Framework

Intended Outcome as stated in the UNSDCF/Country [or Regional] Programme Results and Resource Framework: Outcome 1: “By 2024, people in Yemen, especially women, adolescents and girls and those in the most vulnerable and marginalized communities benefit from better, equal and inclusive access to nutritious food, sustainable and resilient livelihoods and environmental stability”.

Outcome indicators as stated in the Country Programme [or Regional] Results and Resources Framework, including baseline and targets: Indicator 1.1 Proportion of the population experiencing moderate to severe food insecurity (modified Sustainable Development Goal) (SDG) 2.1.2) Baseline (2021):16.2 million (54%) Target (2024): 13 million (43%)

Applicable Output(s) from the UNDP Strategic Plan: Structural transformation accelerated, particularly green, inclusive and digital transitions

SDGs to which the project will contribute: SDG 13 (climate action), SDG 1 (no poverty), SDG 2 (Zero hunger), SDG 5 (Gender equality), SDG 6 (Clean water)

Project title: Addressing the climate crisis and human security through NDC planning and implementation. Project Number: 01003664

| Core Indicators | Data Source | BASELINE |  | Pillar 1 | Pillar 2 |
| --- | --- | --- | --- | --- | --- |
|  |  | Value | Year | Clean energy, sustainable climate change mitigation practices, and just transition towards net-zero pathways | Accelerating adaptation in vulnerable and fragile countries and communities for increased resilience to climate risks and impacts |
| 1.1 Tonnes of CO2 emissions avoided or reduced |  |  |  |  |  |
| 1.2 Megawatts of renewable or low-emission energy capacity installed, generated or rehabilitated |  |  |  |  |  |
| 1.3 Number of beneficiaries with new access to green/sustainable energy (disaggregated by: male, female, youth (15-24) and indigenous people) |  |  |  |  |  |
| 2.0 Number of direct beneficiaries with increased resilience to climate change (i.e., more resilient physical and natural assets, diversified and strengthened livelihoods and sources of income, new/improved climate information systems) (disaggregated by: male, female, youth (15-24) and indigenous people) |  |  |  |  | X |
| 3.0 Number of green/sustainable jobs created (disaggregated by: male, female, youth (15-24) and indigenous people) |  |  |  |  |  |
| 4.0 Number of people trained/educated/informed through technical transfers, dialogues, workshops, campaigns, and other efforts (disaggregated by: male, female, youth (15-24) and indigenous people) |  |  |  |  | X |
| 5.0 Number of development or sectoral policies/plans/budgets that integrate NDC targets or net-zero goals |  |  |  |  |  |
| Legislation |  |  |  |  |  |
| Just transition efforts or assessments |  |  |  |  |  |
| Development plans or roadmaps |  |  |  |  |  |
| Sectoral policies and plans |  |  |  |  |  |
| National or sectoral budgets |  |  |  |  |  |
| Financial instruments or models |  |  |  |  |  |
| Subsidy reforms |  |  |  |  |  |
| Others (specify) |  |  |  |  |  |
| 6.0 Number of partnerships with Japanese organizations |  |  |  |  |  |
| Private Sector |  |  |  |  |  |
| JICA/University/technical experts |  |  |  |  |  |
| Other |  |  |  |  |  |

# WORK PLAN

Period: 1 year

| EXPECTED OUTPUTS | Indicators | Baseline | Targets | PLANNED ACTIVITIES List activity results and associated actions | PLANNED BUDGET |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Budget Description | Amount |
| Country Output 1 Enhanced Climate Change Resilience for Livelihoods and Food Security Global Output – 2: Accelerating adaptation in vulnerable and fragile countries and communities, for increased resilience to climate risks and impacts. 2.1. Implement adaptation and risk reduction actions, including ecosystem-based adaptation, coastal adaptation, climate-resilient agricultural practices, adaptation in high-mountain ecosystems due to glacier melting, early warning systems, etc. and ensure they are available in fragile settings and to marginalized groups. | 1.1 Number of farmers benefiting directly from smart irrigation technologies in Tuban | 0 | 80 | 1. Activity: 1.1. Define water-efficient irrigation technologies that are appropriate for the Tuban area in consultation with counterparts and farmers. - Action: Kick off meetings with the government authorities - Action: Rapid Mapping for the appropriate water efficient technologies - Action: Consultation meetings with the local authorities and WUAs. - Action: Field assessment for the targeted small farms. - Action: Prioritization of beneficiaries based on socio-economic criteria | Contractual Services | 15,000 |
|  | 1.2 Area where the smart irrigation technologies will strengthen adaptation /climate resilience, in hectare |  | 20 Ha | 2. Activity: 1.2. Implement water-efficient irrigation technologies for farmers in Tuban - Action: Procurement, transport, delivery, and installation of water-efficient irrigation technologies. This also include supplier-led training for the small-holder farmers. | Equipment | 305,000 |
|  | 1.3 Number of farmers engaged in the training program | 0 | 200 | 3. Activity 1.3: Train small-holder farmers on climate-resilient production practices, emphasizing the need to adapt their crop calendars by adjusting planting and harvesting dates in response to changing climate conditions. - Action: Conduct training sessions for the beneficiaries in collaboration with the Agriculture Research and Extension Authority and the Office of Irrigation and Agriculture. | Contractual Services/Responsible Party | 50,000 |
|  | 1.4 Number of residents/farmers who have access to information on climate change adaptation | 0 | 500 small-holder Farmers | 4. Activity 1.4: Develop and disseminate climate change adaptation communication materials among target communities - Action: Establish communication channel between Agriculture Research and Extension Authority, Office of Irrigation and Agriculture and Civil Aviation and Meteorological Authority (CAMA) - Action: Conduct training for Agriculture Research and Extension Authority and Office of Irrigation and Agriculture to develop agrometeorological and climate messages based on meteorological data from CAMA. - Action: Establish communication channel between Agriculture Research and Extension Authority, Office of Irrigation and Agriculture and WUAs to disseminate the agrometeorological and climate information. | Contractual Services | 50,000 |
| SUBTOTAL |  |  |  |  |  | 420,000 |
| DPC |  |  |  | Project management costs include: Personnel Cost - Field coordinator - Audit and Evaluation - Visibility and communication - Direct project cost (including DES/DPC) |  | 38,380 |
|  |  |  |  |  | GMS | 36,670.00 |
|  |  |  |  |  | UN Levy | 4,950.00 |
| TOTAL |  |  |  |  |  | 500,000.00 |

WFP (2023): https://www.wfp.org/emergencies/yemen-emergency;  checked on 24/07/2024.

WFP (2019): Yemen: This is the world's largest food crisis. Rome.

The ongoing NDC formulation is set to be launched in line with the new revision of the NDCs in 2025

The ongoing NDC formulation is set to be launched in line with the new revision of the NDCs in 2025.

Yemen INDC submitted to UNFCCC in 2015, available here

It is recommended that projects use output indicators from the Strategic Plan IRRF, as relevant, in addition to project-specific results indicators. Indicators should be disaggregated by sex or for other targeted groups where relevant.