Project Title: Skills Development for Improved Employability

Project Number:

Implementing Partner: Turkish Employment Agency (İŞKUR)

Start Date: 01.01.2025			End Date: 31.12.2027		PAC Meeting date: 20/12/2024

Brief Description

The project aims to enhance formal employment and employability among vulnerable groups in pilot provinces Türkiye by implementing a comprehensive Applied Training Program (ATP) and complementary soft skills and language training. The ATP encourages regularization, providing both employers and workers with tangible benefits such as secure employment and access to a trained workforce. The project also addresses key barriers like language proficiency and technical skills through tailored training, promoting better integration into the labour market. UNDP plays a central role in coordinating and implementing these initiatives, leveraging its expertise and partnerships with key government bodies such as İŞKUR and private sector stakeholders. This multi-dimensional approach not only supports vulnerable individuals, such as refugees, in transitioning into formal employment but also contributes to a more stable and regulated labour market.

| Contributing Outcome (UNSDCF, CPD, RPD): Outcome #1.3: By 2025, people under the Law on Foreigners and International Protection are supported towards selfreliance. Indicative Output(s) with gender marker: GEN 2 Output 1.1. Displaced populations are equipped with the knowledge and skills to engage in the socioeconomic life of their host community. Output 1.4. Sustainable job opportunities created for displaced populations and host communities. |  | Total resources required: | 59,081,831.48 EUR (UNORE between 01-12 December 2024: 1.0549) (62.035.923,06 USD) |  |
| --- | --- | --- | --- | --- |
|  |  | Total resources allocated: |  |  |
|  |  |  | UNDP TRAC: | N/A |
|  |  |  | Donor (EU): | 62.035.923,06 USD (including GMS) |
|  |  |  | Government: | N/A |
|  |  |  | In-Kind: | N/A |
|  |  | Unfunded: | N/A |  |

| Government | UNDP | Implementing Partner |
| --- | --- | --- |
| The Ministry of Foreign Affairs (MoFA) | Monica Merino Dominguez Resident Representative | Turkish Employment Agency (IŞKUR) |
| Date: | Date: | Date: |

# Development Challenge

Türkiye has been the world’s foremost host of refugees since 2014, currently hosting close to 4 million officially registered refugees.  This number includes approximately 3 million Syrians under temporary protection.  As at mid-2023 more than half of the Syrians under Temporary Protection (SuTPs) and International Protection Status Holders and Applicants (IPSHA) in Türkiye benefit from various forms of social and financial aid, with a substantial portion of this assistance being channelled through the EU-funded programmes. Nevertheless, such humanitarian assistance fulfils only a part of their comprehensive needs, as the imperative for accessible, sustainable livelihood opportunities continues to escalate. Of the nearly two million SuTPs/ IPSHA of working age, it is estimated that around 65%, predominantly males, are employed within the informal sector.  Conversely, a relatively small percentage has secured work permits.  As per the mid-2023 UN Inter-Agency Protection Need Assessment, 91% of SuTPs/ IPSHA respondents were not able to fully cover their monthly expenses despite combining incomes from informal labour, humanitarian aid, and remittances.

In light of these challenges, the urgency to facilitate a transition from reliance on humanitarian programmes to sustainable and decent employment opportunities is paramount.  In the previous phases of the EU Facility for Refugees in Turkey (FRIT 1-2), socio-economic sector projects made important contributions to skills development, entrepreneurship, and economic opportunities. These initiatives were crucial in promoting the self-sufficiency of SuTPs/ IPSHA in Türkiye and residing Turkish citizens, aiming for socio-economic independence. The projects were designed to facilitate easier access to the job market for these groups, both as employees and entrepreneurs. However, evaluations on the programme also identified that despite efforts to increase employability through supply-side interventions like short-term vocational training courses, the programs have not adequately addressed the demand side of the equation. This oversight includes a lack of focus on creating sustainable job opportunities in sectors likely to employ the target groups.  Overall, a more nuanced approach that considers both supply and demand factors, the socio-political context, and the specific challenges of formalizing employment in the Turkish labour market appears to be necessary. This approach should aim to create sustainable job opportunities, and ease bureaucratic processes among others.

Based on these considerations, the proposed action takes into account the programmatic strategies for refugees and host communities in Türkiye, as outlined in the Facility for Refugees in Turkey (FRiT) theory of change, released in February 2022. Parallel with the FRiT’s result chain in the livelihoods priority area, contributing at various levels to achieve the long-term outcomes are envisioned. The facility aims at improved income-generation opportunities for refugees and Turkish citizens in high-refugee concentration provinces as its long-term objective which is to be achieved through increased level of employability of, and enterprise start-up and expansion by refugees and residingTurkish citizens in high-refugee concentration provinces, as well as increased effectiveness of Türkiye in delivering employment support services to refugees in the provinces in question.

The ‘Action Document for socio-economic development support and infrastructure services for refugees and host communities in Türkiye following the February 2023 earthquakes’ dated 20 December 2023 which forms the basis for the proposed project at hand, acknowledges that while cash-based assistance programs like the ESSN are crucial for addressing immediate needs, they might also unintentionally hinder the progression toward sustainable livelihood and employment opportunities. Coupled with the challenges in fully addressing the demand side of the labour market, these factors intensify the difficulties faced by employment support programs. Thus, it becomes essential to develop approaches that comprehensively enhance sustainable livelihoods and employment opportunities, addressing these challenges in a more integrated and effective manner. The EU’s commitment in the same document also highlights a dedicated strategy to alleviate both the immediate and long-term impacts of the disaster to foster socio-economic advancement, rejuvenate infrastructure for both refugees and residing Turkish citizens, and enhance resilience. The proposed project would also address certain measures to accelerate the recovery process, strengthen community resilience, and facilitate the integration of affected individuals, with a focus on delivering tailored assistance to the hardest-hit regions.

The proposed project acknowledges the systemic limitations inherent in the current context and is designed to either circumvent or minimize these challenges. With a focus on the demand side of the labour market, a traditional area of activity for UNDP, the project aims to implement programs that are driven by demand and support expansions in this area across both of its components. Developing a project framework that not only achieves this objective but also prioritizes vulnerable groups as its main beneficiaries was a complex task. However, this challenge was effectively addressed through multi-staged consultative processes involving all stakeholder institutions, incorporating their valuable insights and lessons learned from previous initiatives. This collaborative approach has been instrumental in shaping a project that is both responsive and inclusive in its scope and execution.

The Project aligns with the principles of the European Pillars of Social Rights which highlights decent work framework including international labour standards. Further on, the Project notably contributes to the advancement of Decent Work agenda more recently reaffirmed by the EU Commission through its Communication on Decent Work Worldwide for a Global Just Transition and a Sustainable Recovery. The Document notes that “people working in labour-intensive sectors such as agriculture, fisheries and textiles are particularly affected” by “health- and life-threatening workplaces and suffer from in-work poverty, excessive working hours, discrimination, harassment and violence, including gender-based violence, without the freedom to associate”. The communication also refers to back-than-proposal for a Corporate Sustainability Due Diligence Directive as part of EU’s comprehensive approach aims at effective promotion of decent work for all.

In Türkiye, the economic circumstances of refugees, especially after the 2023 earthquakes and the ongoing impacts of the COVID-19 pandemic, necessitate a targeted and multifaceted intervention. A significant portion of the refugee population, engaged primarily in the informal sector, faces precarious working conditions. This situation is rooted in numerous challenges such as capacity-related issues faced by the employers in following formal work permit procedures and the relative ease of entry into the informal sector. Moreover, the lack of employable skills among refugees exacerbates their economic vulnerability, often leading to underemployment in unstable and low-paying jobs.

Building upon the EU’s strategic focus, this initiative is set to fortify income-generating opportunities by improving employability. The project will advance this goal through the ATP, harnessing İŞKUR’s proven experience in administering similar programmes. ATP’s success will be facilitated through complementary interventions, such as language/soft skills trainings and outreach activities, developed based on UNDP and İŞKUR’s experience in tailored programmes to bridge skill gaps in local labour markets.

The Ministry of Labour and Social Security (MoLSS) in Türkiye, being the principal authority overseeing labor market regulation and support, is dedicated to fostering balanced, registered, and sustainable employment opportunities for SuTP, IPSHA, and residing Turkish citizens. This commitment aligns with the broader objective of reducing reliance on social assistance and facilitating the transition to sustainable employment avenues. Furthermore, the proposed project aligns with the supports strategic plans and priorities of the Ministry. MoLSS Strategic Plan defines labor market integration of temporary protection beneficiaries as one of the principal action areas for the Ministry in terms of policy development and implementation.

At a higher level, the 12th Development Plan of Türkiye emphasizes the need for socio-cultural integration of migrants through initiatives like language and informative programs,  vocational referrals for young SuTPs. In response to the February 2023 earthquakes, which inflicted widespread infrastructural damage and social upheaval, including amongst the refugee community, the project aligns with the Türkiye Earthquakes Recovery and Reconstruction Assessment (TERRA)  and the recovery vision that it proposes.  Proposed project supports this vision by including provinces affected by the disaster among its target provinces. Economically, it aligns with the vision of reinvigorating regional economies, supporting local enterprises, and fostering skilled labour retention. Overall, the project responds directly to the current socio-economic challenges in Türkiye, offering a comprehensive approach to recovery and sustainable development. By focusing on skill development, and aligning with national recovery plans, the project aims to make a significant impact in the lives of refugees and host communities in the targeted regions. This holistic approach ensures the Project’s relevance to key strategic objectives and its potential for impactful contributions in these crucial sectors.

# Strategy

In Türkiye, a significant portion of the 3 million SuTP, roughly two-thirds, do not have financial independence despite being at the working age. This is due to certain key challenges including limited proficiency in the Turkish language, which is compounded by a generally low level of formal education. Additionally, many lack the necessary vocational and technical skills that are crucial in the job market. These issues are further exacerbated by a lack of knowledge regarding job searching and securing employment. Moreover, official restrictions and negative perceptions from potential employers serve as significant barriers to their employment in Türkiye.

The Project is designed to address these challenges and enhance the economic resilience and independence of SuTPs/ IPSHA in Türkiye, as well as residing Turkish citizens. The aim of the project is to facilitate sustainable livelihood opportunities for these targeted populations through better employability, job opportunities and working conditions, both in urban and rural settings.

Key outcomes sought include the increased employability of the target groups in specific urban and rural areas, and improvement of institutional effectiveness in delivering employment support services. To achieve these outcomes, various strategies are adopted. These include providing employability, capacity development and support services, enterprise development support, strengthening the capacity of relevant institutions, and increasing the awareness and capacity of the private sector in promoting employability and decent work conditions for the target groups.

The project is structured to enhance the employability of beneficiaries in the labour market, particularly to facilitate their transition from informal to formal employment. The main challenge is that both employers and workers often avoid regularizing employment in compliance with national laws for various reasons. Employers are hesitant to regularize SuTP/IPSHA workers due to the additional procedures, criteria, and costs associated with obtaining work permits. Often, they lack the necessary information or time to navigate these challenges. On the other side, the workers themselves usually don't pursue regularization. They lack information about the process and fear losing social support benefits for their families and themselves once they become regular workers.

To address these challenges, the project will implement several key interventions:

Incentivizing Regularization: A pivotal element of the project is to encourage regularization among the workforces. This is primarily achieved following the ATP, in the employment phase. The ATP is designed to be an attractive proposition for both employers and workers, showing the tangible benefits of formal employment. For employers, this means access to a trained and formal workforce, and for workers, it translates to secure employment with legal protections. A concerted effort will be directed towards enrolling job seekers from target groups in these programs. By doing so, the project intends to transition these individuals from unemployment or informal employment into the formal employment, thus ensuring they benefit from official labor protections and rights. This transition not only aids the workers but also contributes to a more regulated and stable labor market.

Improving Employability: Main goal of the project is the enhancement of employability among vulnerable groups. Recognizing that language barriers, basic education, and technical skills are key impediments to labor market integration, the project will implement comprehensive training programs. These programs are not just limited to language proficiency, particularly Turkish, which is crucial for integration in Türkiye, but also encompass basic educational skills and technical training. These include fundamental workplace skills, basic human rights, essential aspects of employment law, career development strategies, effective resume writing, understanding and promoting gender equality in the workplace, entrepreneurship fundamentals including key laws and regulations, and critical knowledge on occupational health and safety. By covering such a broad spectrum of subjects, the project aims to not only improve language proficiency and technical abilities but also to foster a well-rounded understanding of professional environments and individual rights within them. This approach is geared towards smoothing the transition of these groups into the labor market, ensuring they are well-prepared and competitive in Türkiye's job landscape.

Through these interventions, the project aims to reduce informal employment, improve working and living conditions, and enhance the economic resilience and independence of the targeted groups in Türkiye. It is assumed that the training and support provided will be adequate for beneficiaries to secure and retain meaningful employment. The health of the Turkish economy is expected to either remain stable or improve, facilitating job creation and enterprise success. The official policies regarding the integration of SuTPs/IPSHA to the local labor market are expected not to deteriorate, despite the recent discussions and policies promoted for safe return by Presidency for Migration Management (PMM). Additionally, the social acceptance of the target groups, especially refugees, is presumed to remain stable, ensuring willingness from employers in certain sectors such as textile or retail sectors to hire them.

Building on these foundational goals, the project strategically aims to navigate and mitigate the complexities that often act as barriers to formal employment. Recognizing that certain factors, such as the potential loss of social assistance benefits, can disincentivize individuals from seeking formal employment, this multifaceted intervention is designed to create an environment where the transition to formal work is a seamless and less daunting shift for beneficiaries, as well as the employers.

The methodology of the project is grounded in a multi-dimensional implementation strategy, aimed at achieving effective and sustainable outcomes in labour market integration. Central to this approach is the collaboration of highly skilled and experienced governmental and international entities in this domain, with a focus on fostering synergies among them. A pivotal aspect of the approach is the integration of lessons learned from previous initiatives, ensuring an informed and effective implementation strategy. Underpinning this comprehensive approach, the United Nations Development Programme (UNDP) holds the overarching responsibility for the implementation of the entire project, ensuring consistency and coherence across all activities. In terms of coordination, UNDP will act as the principal implementing body for the entire project, drawing on its vast experience in development areas. The Directorate General of International Labour Force (DGILF) will serve as the main coordinating body from the government's side, ensuring alignment with national policies and strategies.

The project is structured into two distinct components, each with a specific area of focus. The first component is spearheaded by İŞKUR, Türkiye's specialized institution for labour force programmes, in partnership with UNDP. This segment aims to implement an adapted and enhanced version of İŞKUR’s ATP with complementary trainings and establish connections with private sector entities. Leveraging UNDP’s extensive experience and established relations with private sector stakeholders, including major chambers and umbrella organisations, the component will also focus on increasing awareness about ATP to support it with suitable beneficiaries on demand and supply side, while also gathering valuable feedback for ongoing programme enhancement. In developing and executing soft skills and language training to support ATP, UNDP will adapt and utilise curricula and systems established in its previous projects, ensuring a tailored and effective learning experience for the beneficiaries.

İŞKUR possesses significant experience in implementing on the job trainings as part of its nationwide core responsibilities, ATP programs developed within the framework of the ISDEP 1 and ISDEP 2 Projects, modelled based on-the-job training programs. ATP is governed by its own regulations and rules, which have been adapted and codified in an implementation guideline to suit the project context.

This implementation guideline will also undergo revision for the planned project, if necessary, reflecting the lessons learned and any legislative changes. While adhering to the core rules and restrictions of ATP programs in pilot provinces, the practice of adapting the programme to the context of international protection will be continued to the extent possible, ensuring that the ATP remains relevant and effective in addressing the unique challenges faced by refugees and residing Turkish citizens in Türkiye.

In addition to overall management of the project, UNDP will play a pivotal role in directly implementing sub-components that complement the İŞKUR’s ATP. UNDP brings to the table a wealth of experience in conducting skills and language training for large groups of beneficiaries. A notable example of this expertise is the 'Turkey Resilience Project in Response to the Syria Crisis,' recently funded by EU MADAD, where similar training programs were successfully executed for large groups of beneficiaries.2 In this project, UNDP plans to leverage this experience and the systems developed in coordination with the Ministry of National Education (MoNE) to enhance the employability of ATP beneficiaries and potential participants.

The language training program adopts a blended learning approach, combining online and classroom instruction. This method significantly reduces classroom hours from the standard 160 for A2 level and 320 for B1 level in the Turkish lifelong learning system to just 90 hours for each level. Courses are structured to be completed over 10 weeks, with classes held for 3 days each week, 3 hours per day, and include a break day for online study. The flipped classroom model transforms the teacher's role into a guide for learning. This approach aligns with adult learning principles, emphasizing self-motivation and independent study. Trainees are expected to engage with online materials in their own time, using classroom hours to reinforce their learning. The course content, designed in accordance with the Common European Framework Reference (CEFR), includes interactive elements like videos, animations, and texts, accessible asynchronously via smart devices. This flexibility allows trainees to study at their convenience, download materials, and submit completed activities. Additionally, the content is tailored with sector-specific terminology, supporting trainees in effectively adapting to workplace environments. Course content will be revised to be adapted to vocational language. Pre-course, in-course and post-course content will be revised for at least three sectors. Beneficiaries will have exposure to the similar terminology in workplace and courses simultaneously to support the adaptation. Limited in class time and offline usage of the pre and post course content allows women to organize their time to participate easier. Methodology used to optimize the selection of public education centres will include formal information of number of SuTPs/IPSHA, number of beneficiaries that each PEC served in 2021 – 2023 and data of potential ATP beneficiaries taken from İŞKUR according to İSDEP 1 and 2 projects. The flexibility of classroom usage modality of the PECs will enable to deliver the lectures in most efficient spaces in means of accessibility since PEC has the right and capacity to deliver the courses in any place within its responsible neighbourhood. Blended modality of the courses will enable to deliver them out of working hours which makes accessible for employees.

Based on insights gained from ISDEP 1 and ISDEP 2 projects, the complementary trainings will be structured to avoid impeding the ATP process. Recognizing that mandatory training as a prerequisite for ATP can disrupt the sequencing and flow of the ATP, these trainings will instead be optional and scheduled outside of regular working hours, including evenings and weekends. Only the basic soft skills training for all participants will be mandatory and will be delivered through the local offices in the project provinces. The training content and the learning platform of the local offices will be enhanced through the Project, which will be operational after the project lifetime as well. This approach ensures better sustainability and minimizes the risk of conflicts with working hours and adopts a blended format of online and in-person sessions to maximize accessibility and convenience for participants.

Moreover, the language training programmes will be open not only to current ATP beneficiaries but also to potential beneficiaries, with specific criteria for participation to be developed during the project's inception phase. This strategy is intended to amplify the impact of the trainings, contributing to the success of future ATP cycles. Furthermore, the trainings will extend to employees of private sector actors engaged through the Project's outreach programme. Thus, employees in need of soft skills or language training will also benefit from the established complementary training mechanism, ensuring a broader impact and support for workforce development in the private sector. This comprehensive approach underscores UNDP's commitment to enhancing workforce capabilities and supports the overarching goal of fostering sustainable labour market integration in Türkiye. The implementation of the ATP system will include diligent follow-up through regular monitoring at both provincial and central levels. This monitoring will be conducted through the inherent monitoring system of İŞKUR programmes, complemented specifically by the Project Team (PT). In essence, the ATP component will be operationalized based on the structure outlined in the chart below:

In conclusion, the project's methodology is characterised by a strategic combination of expertise, collaboration, and experience-driven insights. This approach is designed to ensure not only the successful implementation of the project but also its long-term sustainability and impact in the field of labour market integration.

#### Selection of Project Provinces

The pilot provinces for the project were selected through a meticulous process, considering a multitude of factors to ensure the project’s effectiveness and relevance. The Project centres on ATPs and supplementary training to aid in labour market integration, a preliminary list of provinces has been identified, including İstanbul, Gaziantep, Şanlıurfa, Adana, Mersin, Bursa, İzmir, Kahramanmaraş, Sakarya, Hatay and Mardin. The final selection of project provinces will be refined during the inception period of the Project. The goal is to finalize 7 provinces. This approach is designed to provide focused and effective implementation in the most suitable regions for the target group.

The selection criteria were comprehensive, including preliminary analysis of the target group population and profile in each province to ensure the interventions meet their specific needs, provincial production values, number of available job places, presence of active private sector entities, and local labour market needs aiming to align the project with existing economic opportunities. The capacity for local implementation was also evaluated to guarantee that the chosen provinces could support and sustain the project activities effectively. The impact of the February 2023 earthquakes was another factor, especially in selecting regions where the project could contribute to recovery and resilience. The social dynamics and history of previous project activities, such as those under FRIT 1 and 2, were also factored into the decision-making process.

The selection of pilot provinces was a collaborative effort involving UNDP, İŞKUR and DGILF.  For the first component in particular, the analysis of İŞKUR data played a crucial role, enabling the identification of provinces with the greatest potential. This analysis was an integral part of the preliminary selection process, providing key insights into the demographic and labour demand-related aspects in the provinces. The data reviewed by İŞKUR offered a comprehensive view of each province's unique characteristics, informing the decision-making process and ensuring a targeted and effective implementation strategy.

It's important to note that İstanbul, Gaziantep, Şanlıurfa, Adana, Bursa and İzmir are also included in the ISDEP 2 Project. This overlap has been carefully considered in developing the implementation timeline for the current project to avoid any potential duplications of effort. This strategic planning ensures that the new project complements and builds upon the work already done under ISDEP 2, enhancing the overall impact and efficiency of both projects in these provinces.

Gender Mainstreaming

In alignment with the EU Gender Equality Strategy (2020-2025) (particularly towards “closing gender gaps in the labour market” under priority 2 “thriving in a gender-equal economy”) and UNDP's Gender Equality Strategy for 2022-2025 (specifically with the priority for gender equal and sustainable economies), the Project is dedicated to promoting gender equality and the empowerment of women within its framework. This commitment aligns with SDG 5 - Gender Equality and with the strategic objectives of the 12th National Development Plan (NDP), which emphasizes the empowerment of women in employment and labour markets within the framework of a strong approach towards equal opportunities for men and women.

In the newly announced Women’s Empowerment Strategy Document and Action Plan (2024-28), Activity 2.1 outlines the priority of enhancing women’s participation in on-the-job training programs to facilitate their access to decent employment opportunities: “Efforts will be made to ensure that women, especially NEET young women, benefit more from vocational training courses, on-the-job training programs, and counselling activities aimed at acquiring skills tailored to the evolving needs of the labour market, thereby enhancing their access to dignified job opportunities.”

Key strategies for gender mainstreaming will include equitable participation and leadership, gender balance in managing bodies, decision-making positions, and activities. This includes ensuring that women have equal opportunities to participate in training programs, employment support initiatives, and business development activities. Activities and programs will be designed to address the specific needs of women, particularly those who require specific policies. This involves creating safe and inclusive training environments and providing resources that are tailored to the unique challenges faced by women in the labour market. Participatory assessment exercises to be organized with women will help capture their expectations and preferences on the scope and delivery methods of the employment support programmes and serve as the main mechanism to identify and incorporate the needs and demands of women and increase their representation in the activities.

The strategy for gender mainstreaming will prioritize the development of tailored solutions to address the differential needs and pre-existing inequalities between men and women in the labor market. This involves moving beyond simply integrating women into generic activities and focusing on designing targeted interventions that directly respond to the unique barriers and challenges women face.

In order to outline this approach, some responses are planned as follow:

o	A Participatory Needs Assessments will be conducted to gather women’s expectations, preferences, and challenges. Based on the results of this participatory exercise, the scope, delivery methods, and content of employment support programs will be shaped. By doing it, women’s voices will be placed in the planning and decision-making process.

o	Gender-inclusive communication and outreach will be the centre of the gender mainstreaming policy. Gender-sensitive language will be used in announcements to encourage women's participation to the courses.

Also visuals which are used for announcement of the ATP will be ensured to reflect gender inclusivity and diversity.

o	Tailor-made Training Program will be conducted to respond the women’s specific needs, such as flexible schedules, caregiving responsibilities, or limited access to resources. Training modules will be developed or updated accordingly. Additionally, soft skills trainings will give a chance to beneficiary women to widen economic opportunities, focusing on both traditional and non-traditional sectors.

o	Safe, inclusive and gender responsive environments will be created to establish training and work environments free from harassment and gender-based discrimination. Some initiatives are planned to provide such as childcare support in the workplaces and PECs, safe transportation options –if the companies included in the program have this service-, or women-only spaces (dressing room, breastfeeding room), to encourage participation.

o	Women's decision-making and representation will be actively promoted to achieve gender balance within the leadership structures of activities. Women will be encouraged to apply to positions with leadership roles.

o	Specific policies to support women’s economic participation, particularly for those facing additional vulnerabilities (refugee women, women with disabilities, single mother) will be developed and lobbying activities will take place for the greater policy integration to reduce structural inequalities, such as addressing wage gaps or ensuring equal rights in employment.

o	Program evaluations will include gender-disaggregated data to assess effectiveness in reducing inequalities.

o	Engaging men in gender equality by organizing fatherhood information sessions is crucial for shifting societal norms and fostering shared responsibilities in both households and workplaces.

o	Formation of small support groups (e.g., buddy systems of 2-3 women) will be facilitated among training participants to promote engagement, continuity, and mutual encouragement.

o	Procurement processes will prioritize gender-responsive principles, assessing suppliers on their commitment to gender equality and ensuring equipment and renovations meet the needs of all users. Renovations will include women-friendly designs, such as proper lighting and safety features, while staff will be trained to implement gender-responsive practices effectively.

o	Recruitment processes will integrate UNDP's commitment to gender equality by including specific language in job descriptions that requires candidates to demonstrate experience or knowledge in gender-sensitive practices. Policies will emphasize gender inclusivity, ensuring equal opportunities at every stage of hiring, from advertising to final selection. To promote fairness and minimize unconscious biases, interview and selection panels will be diverse and gender-balanced.

o	Women-specific sessions will highlight the benefits of social security, such as health insurance and maternity leave. Tailored materials will address common misconceptions, and accessible communication channels, like women’s organizations and social media, will be used to spread the message. Awareness workshops for employers will promote gender-inclusive workplaces, while partnerships with NGOs and labor organizations will ensure effective outreach to diverse women’s groups.

o	The project will conduct awareness-raising activities during training sessions (ATP, soft skills trainings, Turkish language trainings), emphasizing key gender-related themes on important days such as International Women’s Day, International Day for the Elimination of Violence against Women. Additionally, informative brochures and resources on gender equality and women’s empowerment will be prepared and shared with participants. These efforts aim to foster a deeper understanding of gender issues and empower individuals to advocate for equality in both personal and professional settings.

The project will ensure the collection and analysis of gender-focused and gender-disaggregated data. This data will inform the project's approach and ensure that interventions are effectively addressing gender disparities. The project will include specific measures to raise awareness among beneficiaries and stakeholders about the importance of gender equality in the labour market. This will involve activities focused on understanding and addressing gender-based challenges.

Through these strategies, the Project aims to contribute significantly to the advancement of gender equality, ensuring that both women and men benefit equally from the project’s initiatives and opportunities.

To mitigate barriers faced by women, the project will set targets for women's engagement across all support programs, integrate gender-specific needs into program design, conduct gender-responsive participatory assessments, data collection and analysis, and provide capacity-building trainings to partners and stakeholders. Through these measures, the project aims to significantly advance gender equality and ensure equal opportunities for both women and men.

Equal Opportunities

The Project’s attention to the advancement of decent work agenda, as laid out by the International Labour Organization, promotes the rights of the refugees and of the members of the host communities. This is integral to reducing inequalities among the target group affected by a number of vulnerabilities in a sustainable way.

Under the Project’s awareness-raising activities, including training activities for workers, outreach to employers, and joint monitoring visits to the workplaces, information on concepts such as decent work and international labour standards will be provided through the ILO frameworks, UN Guiding Principles on Business and Human Rights as well as European Pillars of Social Rights, EU Commission’s Communication on Decent Work Worldwide and Corporate Sustainability Due Diligence Directive.

Through inter-active workshops and informative materials/platforms, workers will be empowered in raising their knowledge on the rights, remedy routes, administrative procedures including obtaining of work permits and new regulations in the field in accordance with the needs of the right holders.

The principles of transparency, inclusiveness, and non-discrimination will be applied across all activities and at every stage of the Project’s implementation. While designing the training modules and materials the needs of people with disabilities including those who are visually impaired and hearing-impaired will be included. In some of the trainings, sign language services will be provided.

Sustainable Development Goals (SDGs),Leaving no One behind and Other Global and Regional Frameworks

Although not strictly a humanitarian programme given its medium-term approach, the programme will maintain strong adherence of the nine quality criteria of core humanitarian standards, as an appropriate, relevant, timely, and effective intervention to one of the main challenges hampering the social inclusion of the furthest behind refugee community members and other vulnerable groups. UNDP will ensure a rights-based approach in the programming and facilitate implementation by partners for effective inclusiveness, responsiveness and accountability, with a special focus on the furthest behind people and places.

The Project’s actions are also aligned with the 2030 Agenda for Sustainable Development, contributing significantly to several Sustainable Development Goals (SDGs). These include ensuring inclusive and quality education (SDG 4), promoting gender equality (SDG 5), fostering sustainable economic growth and decent work (SDG 8).

Moreover, it supports two key objectives of the Global Compact on Refugees: alleviating the burdens on host nations and empowering refugee self-sufficiency.

Regionally, the Regional Refugee and Resilience Plan (3RP) Regional Strategic Overview 2023 and, more specifically, the Turkey Country Chapter serve as the guiding framework for initiatives supporting the Turkish refugee response from the donor side. Among 3RP's strategic objectives is the expansion of livelihood and job opportunities for SuTP/IPSHA and residing Turkish citizens, which directly aligns with the objectives of the Project at hand.

# Results and Partnerships

Expected Results

The primary aim of the Project is improved resilience of vulnerable populations, including SuTPs/IPSHA and residing Turkish citizens in order to reduce dependency on ESSN and other social assistance mechanisms, promotion of self-sufficiency, and fostering economic independence.

Specific objective is set to achieve this overarching goal:

1. Increased level of employability of refugees and residing Turkish citizens in the non-agriculture sectors

The ATP is established as a key component in achieving this objective. The following key outputs are determined in pursuit of this objective:

Output 1.1: Employability of beneficiaries consisting of SuTPs/IPSHA and residing Turkish citizens is improved

Output 1.2: ISKUR and DGILF’s training management capacity is strengthened.

Output 1.3: Beneficiaries are equipped with the required soft skills and Turkish language capabilities.

In conclusion, the project is characterized by a comprehensive approach, addressing the socio-economic challenges of vulnerable populations in Türkiye, targeting urban development through a strategic and multifaceted methodology.

Component 0 – Inception

During the 4-month Inception Phase, the following preparatory activities will be realized:

Act. 0.1. Establishment of the project implementation team and the project office: Assembling a dedicated team and setting up a central office to coordinate and manage all project activities effectively.

Act. 0.2. Kick-off meeting: An initial gathering of key project stakeholders and project team members to discuss the project's objectives, expectations, roles, and the roadmap ahead.

Act. 0.3. Launch event: A formal event to publicly announce the commencement of the project, aimed at raising awareness and garnering support from relevant communities and stakeholders. Subject to sensitivities at the time, the event is planned to be a high-profile launch with the participation of national and international stakeholders and partners, representatives from the line ministries, and the private sector.

Act. 0.4. Inception report submission: The submission of an initial report detailing the project’s framework, planned activities, expected outcomes, and preliminary assessments conducted at the project’s onset in line with contractual obligations.

Component 1

Employment support through Private Sector Driven Applied Training Program (ATP):

In a bid to strengthen the resilience of vulnerable populations in Türkiye, including SuTP/IPSHA and residing Turkish citizens, the Project plans to support the vulnerable groups and businesses through complementary mechanisms. One of the cornerstones of the Project is the provision of employment support via a structured and private sector influenced ATP based on the active labour programmes implemented by İŞKUR.

This endeavour begins with providing consultancy services to 12,000 beneficiaries by İŞKUR, at least half of whom belong to SuTPs/IPSHA groups and priority will be given to (former) ESSN beneficiaries as much as possible. This is complemented by the provision of Turkish language trainings through Public Education Centes, and soft skills trainings through İŞKUR’s local offices, the capacity of which will be enhanced through the Project activities. The soft skills training programme will be developed and implemented by UNDP and İŞKUR, and the language trainings will be developed and delivered by UNDP through cooperation with the Ministry of National Education (MoNE).

İŞKUR local offices are intensive job and vocational counselling programs which are designed to provide job search motivation and methodological support to groups requiring special policies in the labour market, such as women, youth, people with disabilities, and the long-term unemployed. The primary objective of local offices is to re-motivate job seekers who have lost hope of finding employment and to provide them with the necessary methodological support. Each local office is led by a job and vocational counsellor who ensures that members develop the skills and motivation needed to independently search for and secure employment. As part of the training, job and vocational counsellors receive education and training on how to support groups requiring basic soft skills. This includes resume preparation through individual, peer, and group work, understanding the relationship between professional competencies and job analysis, and providing a counselling approach tailored to these groups. In addition to this foundational training, advanced soft skills training is organized to further enhance the qualifications of the counsellors involved in the project. Soft skills courses will help all beneficiaries understand their rights and responsibilities, promoting labour peace. These courses will also address gender equality and entrepreneurship, aiding beneficiaries in career planning and boosting their self-esteem through increased awareness. Since all trainings will be conducted online, beneficiaries can take these courses outside of working hours, accommodating their schedules. The course content and curricula that will be developed will be uploaded to İŞKUR's Learning Management System (LMS). The LMS will be accessible not only to the İŞKUR local offices involved in the project but also to İŞKUR local offices across Türkiye. As the training will be standardized, İŞKUR will have the ability to certify trainees upon course completion. Certificates will be issued online, with records maintained on İŞKUR’s LMS servers. Additionally, İŞKUR will have the option to transfer the certificates to the e-government system in collaboration with the Continuous Education Centre of Anadolu University.

The programmes under the Project scope are aimed at facilitating the integration of beneficiaries, especially SuTPs/IPSHA, into the Turkish work ecosystem seamlessly. Through the ATP, there will be an active thrust towards integrating the beneficiaries into sectors that have a substantial demand for labour. As a practical step, support for work permit procedures will be extended to a portion of the SuTPs/IPSHA beneficiaries.

With agreement of all parties an alternative program may be implemented beyond the ATP or a new program may be initiated to enhance the project's effectiveness. The mentioned program is planned to be determined during the Inception Phase. It will then be detailed in the Inception Report and submitted to the EU for approval, provided that the proposed program aligns with the objectives, targets, and the Financing Decision.

Additionally, in order to ensure private sector involvement and integration of private sector demands into the design and implementation of the programme, the main relevant private sector actors will be mapped at each pilot province and covered through an outreach and information programme by UNDP whereby they will be referred to the ATP and their inputs will be received, analysed and integrated into the implementation of the programme. The outreach programme will be designed and implemented in coordination by UNDP with the DGILF and İŞKUR.

UNDP will leverage its longstanding cooperation with private sector umbrella organizations, including Chambers of Commerce and Industries at regional and national levels. Lastly, to ensure the smooth rollout and oversight of these activities, DGILF and İŞKUR will receive capacity support, streamlining project coordination, monitoring, data management, and communication.

The outputs of this component are planned to be delivered through the specific activities below:

Act. 1.1. Revision of ATP digital system and implementing guidelines (Outputs 1.1., 1.2. and 1.3.): An update of the digital system and the implementing guidelines for the Applied Training Program (ATP) will be carried out based on the criteria and specifications determined for the Project and the lessons learned from the ISDEP 2 Project. The ATP programme under the project adheres to specific criteria and procedures that must be uniformly followed across all pilot provinces. To ensure consistency and clarity, implementing guidelines that include detailed instructions for both central and provincial levels will be developed and revised by ISKUR during the project's implementation. The ISDEP 2 guidelines were recently updated, according to information from İŞKUR. Consequently, a revision of the proposed project will also be conducted once the implementing procedures are fully developed. This revision will incorporate the lessons learned from the ISDEP 2 project, ensuring that the ATP programme is effectively tailored to meet the project's objectives and standards.

Act. 1.2. ATP implementation (Outputs 1.1., 1.2. and 1.3.): Placement of 12,000 beneficiaries (at least 6,000 SuTPs/IPSHA) in ATP to support their integration into labour-absorptive sectors. Implementation of the ATP will involve placing 12,000 beneficiaries in training programs aligned with labour market demands, supporting their integration into suitable employment sectors.

Act. 1.2.1. Counselling to potential beneficiaries by İŞKUR: Provision of consultancy services to 12,000 beneficiaries (at least 6,000 SuTPs/IPSHA primarily ESSN beneficiaries) by job and vocational counsellors.  İŞKUR’s vocational consultants will provide consultancy services to 12,000 beneficiaries who applied to İŞKUR in the 7 project provinces, offering career and vocational guidance to assist them in navigating the job market, informing them on the ATPs and referring them to UNDP for the complementary training activities.

Act. 1.2.2. Matching and conduct of ATPs: Beneficiaries will be matched with appropriate employers, ensuring alignment with their skills and job market needs. The suitable beneficiaries will be placed to the ATPs through an on-the-job basis for durations up to 6 months to 8 months (if the ATPs organized in dangerous and highly dangerous occupations) depending on the specifications of each vocation. Beneficiaries’ salary costs (at the minimum wage level) will be covered by the Project during the ATP.

Act. 1.2.3. Monitoring visits and evaluations: Regular monitoring visits and evaluations of the training programs will be conducted by İŞKUR and UNDP and DGILF to assess effectiveness and make necessary adjustments. 4 field visits annually to each pilot province are planned to be realised with the participation of 8 PT members and with the duration of 3 days. Following each visit, a monitoring report will be developed by the PT, the findings of which and changes made based on the findings will be incorporated in the project progress reports.

Act. 1.3. Turkish language courses to SuTPs/ IPSHA beneficiaries (Outputs 1.2. and 1.3.): Turkish language training for at least 6,000 SuTPs/IPSHA (Outputs 1.1 and 1.2) will be provided to facilitate their integration into the Turkish labour market. The trainings will be on a voluntary basis for the beneficiaries and potential beneficiaries of the ATP and will be delivered through the training system developed by UNDP in cooperation with the Ministry of National Education in a previous project (Turkish Resilience Project) funded by EU.

Act. 1.3.1. Development of curriculum including tests: A comprehensive curriculum for Turkish language instruction, including proficiency tests to be applied at the beginning and the end of the trainings, will be developed to ensure the courses meet the specific needs of the beneficiaries. Anadolu University (AU) will be cooperated to develop online content, revise the content, and support the platform and its digital infrastructure. UNDP will sign a responsible party agreement with the AU to deliver the services. AU is the formal online learning authority in formal and informal education for Türkiye. AU also developed and supported the platform and content for previous courses in several projects including TRP.

Act. 1.3.2. Delivery of Turkish language courses: The Turkish language courses, as per the developed curriculum, will be delivered to the beneficiaries, enhancing their language skills essential for the workplace. The success of the trainings will be measured through the pre-and post-tests. The trainings will be delivered through the hybrid training platform developed by UNDP under earlier projects, ensuring value for money, higher attendance, and prompt delivery. Courses will be delivered by MoNE and will ensure the formal language level standards according to the Common European Framework of Reference for Languages. PTT will serve as an intermediary and provide banking services and access to the personal data of beneficiaries for data verification as a semi-public institution. UNDP, Directorate General of Lifelong Learning of MoNE, and Banking Services of T.C. Post and Telegraph Organization (PTT) will sign a MoU to deliver the courses, to certify the beneficiaries formally, and to transfer stipends of beneficiaries due to regulations of MoNE. Courses will be opened in pilot provinces by Public Education Centres (PEC).

Courses will be delivered in a blended education modality. The modality includes online activities and face-to-face courses simultaneously. The digital infrastructure of the selected PECs will be supported.  Trainers who will deliver the courses will be trained to educate in blended modality, flipped classroom method, and to use the learning management system. The beneficiaries will receive stipends due to the number of face-to-face courses they attend. The amount and conditions of stipends are annually declared by MoNE. The amount is declared through a formal letter to all the parties organizing training programs in Türkiye. The stipend amounts are calculated based on the number of face-to-face class hours. The participants of language trainings might either be ATP beneficiaries and/or job seekers.

Act. 1.4. Soft-skills trainings to beneficiaries (Outputs 1.2. and 1.3.): Soft skills development training for 12,000 beneficiaries (at least 6,000 SuTPs/IPSHA) (Outputs 1.1 -3) Soft skills development training will be provided to 12,000 beneficiaries, focusing on skills crucial for better employment and workplace success. The trainings, especially for the SuTPs/IPSHA beneficiaries will include information on the protection of rights and access to services by target groups. The programme will consist of 2 parts, a compulsory basic training for all ATP participants that will take place ideally before the ATP and an extended training optional for ATP beneficiaries who completed the basic training will be provided during ATP.

All soft skill courses will be delivered online and managed through a learning management system (LMS). The courses will be designed to be downloadable to mobile phones and can be accessed offline. The system will upload completed modules to the LMS for feedback. Courses will be designed in modular modality. Beneficiaries will organize their free time to complete the course modules step by step. All content will be downloadable, and the beneficiary will be able to finish the modules when it is downloaded. The content will be designed to use the minimum capacity of the mobile phone service with a minimum usage of an internet connection. Soft skills trainings will be delivered through the İŞKUR local offices, and the technical capacities and training content will be supported through the Project. Soft skill training courses will be delivered online through a learning management system which is integrated in the existing online system of İŞKUR. JVCs will act as facilitators and observers for the online training programme. Supported digital infrastructure of the İŞKUR training system will serve nationwide parallel to project implementation. İŞKUR will have the opportunity of providing the abovementioned courses and extra programmes through the system. The system will also allow İŞKUR to have a formal certification system.

Act. 1.4.1. Development of training content/specifications and platform: Training content and specifications for soft skills development will be created and tailored to the needs and challenges faced by the beneficiaries in the labour market. The distance learning platform of İŞKUR local offices will be supported for proper delivery of trainings. Adult Language Courses designed and implemented in TRP project between 2018 and 2021 will be the base of the platform and the content. Courses will be delivered in blended learning modality as delivered in several UNDP projects including TRP Component 3: Adult Language Learning and Increasing Employability for Syrian Refugees and Turkish Host Communities in the Renewable Energy Sector funded by the Republic of Korea. Pre-course, in-course and post-course content will be revised according to vocational Turkish for at least three sectors. Digital infrastructure can be used by İŞKUR after the completion of the Project and will be supported by developers for at least three years after the completion of the project.

Act. 1.4.2. Delivery of basic soft-skills trainings: The soft-skills training programs, as per the developed content and delivery modality, will be conducted, emphasizing work culture, communication, teamwork, procedures, rights and obligations, and other essential soft skills.

Act. 1.4.3. Delivery of extended soft skills trainings: An extended trainings will be available for Turkish nationals who have completed the basic training. The extended training will be voluntary. Extended courses will comprise advanced content of the basic soft skill courses for the employees and ATP beneficiaries who aim to improve themselves in specific areas among the given courses. Content of the courses will be produced with contribution of specialists elected among academicians, İŞKUR personnel, and the UNDP team. Each course will focus on detailed learning targets for the self-development of the beneficiary. Extended training courses aim to support the beneficiaries to set self-career paths as employees, employers or entrepreneurs. These courses will also allow the beneficiaries to have detailed background information about labor laws, regulations, and general legal trading systems.

Act. 1.5. Work permit support for SuTPs/ IPSHA beneficiaries (Output 1.1.): Provision of support to the companies as an incentive to facilitate work permit procedures of 1,800 SuTPs/IPSHA engaged in ATP, including associated costs. (Outputs 1.1 and 1.2.) Support will be provided for the work permit procedures for 1,800 SuTPs/IPSHA engaged in ATP, including guidance in completing the procedures and handling associated costs, to facilitate their legal employment.

Act. 1.5.1. Development of selection criteria and support procedure: Criterion and methodology for choosing, from the ATP beneficiaries, the employers, and workers who require procedural and financial assistance in obtaining work permits will be established, ensuring a fair and efficient process.

Act. 1.5.2. Delivery of work permit support: The actual process of providing work permit support to the beneficiaries selected by employers after completion of ATPs, will be carried out, aiding in their regularization in the Turkish labour market.

Act. 1.6. Business engagement and outreach for ATP (Output 1.1.): The activity involves the identification and outreach to employers who could potentially benefit from the ATP (Outputs 1.1). It is centred around creating a comprehensive list of potential companies, focusing on sectors that align with the skillsets offered through the ATP. The activity includes a structured approach to engaging these businesses, providing detailed information on the ATP system and its advantages. Key aspects of this engagement include highlighting how participation in ATP can enhance their workforce, contribute to skill development, and potentially lead to improved productivity and innovation within their operations. Additionally, this activity will emphasize the social and economic benefits of employing individuals from the target groups, thereby fostering inclusive employment practices.

Act. 1.6.1. Development of outreach strategy/materials: The outreach strategy will encompass various communication methods, to ensure effective dissemination of information and engagement with the business community. This activity aims to build strong partnerships between governing body of the Project and the employers, facilitating mutually beneficial outcomes and contributing to the overall objectives of socio-economic inclusion and resilience enhancement.

Act. 1.6.2. Mapping of outreach targets in project provinces: Potential companies in the project provinces will be identified and mapped as targets for outreach and engagement.

Act. 1.6.3. Outreach missions and dissemination of information: Outreach visits will be conducted in cooperation with local İŞKUR provincial directorates to engage with the identified businesses, disseminating information and encouraging participation in the ATP.

Act. 1.7. Institutional support for facilitation of ATP: Operational support to İŞKUR (including provincial directorates responsible for the implementation) and DGILF for project implementation and coordination, human resources, monitoring and evaluation, data management and analytics, and communication activities (Outputs 1.1-3)

1.7.1. Service vehicles will be rented and utilized to facilitate the execution of project activities across pilot provinces. These vehicles are deemed essential for ensuring mobility and effective on-ground implementation, especially in regions where access and outreach might be challenging. The vehicles will be utilised by the İŞKUR staff in the targeted provinces.

1.7.2. Renovations of field offices and HQs will be undertaken, particularly focusing on provinces that were not covered in the earlier phases of the project. Special attention will be given to cities where provincial capacities have been impacted by the earthquake.

1.7.3. Software, hardware, and consumables procurement and delivery are critical for maintaining and adapting İŞKUR and DGILF’s information technology platforms. This support is necessary to handle the increased demands of the project, including managing extensive data, analytics, and communication needs. This step will ensure that İŞKUR and DGILF’s systems are robust, responsive, and capable of supporting the project's technological requirements.

1.7.4. 8 workshops with the participation of Project stakeholders and HQ as well as Project Implementing Units: To ensure the smooth, efficient, and effective implementation of the ATP and work permit assessment and issuance processes, 5 İŞKUR and 3 DGILF workshops will be conducted, bringing together implementing actors from the local offices and headquarters. These workshops are designed to foster a cohesive approach to the ATP program by the provincial İŞKUR directorates and central authorities. They will focus on facilitating knowledge exchange and collaborative strategy development. Additionally, these sessions will be instrumental in analysing lessons learned and formulating solutions to any challenges encountered in the field, thereby refining, and improving the overall effectiveness of the ATP implementation process.

1.7.5. 2 Study visits on migration management applications good practices in the EU and attendance to ILO training: 2 study visits will be organized with the participation of 8 ISKUR staff to explore good practices in labour market integration in the migration management context within the EU. These visits are intended to gather insights and best practices that can be applied to enhance the effectiveness of the proposed project. In addition, 4 İŞKUR staff and 4 DGILF staff responsible for the development and implementation of the ATPs and implementation of the Project will attend the training programme of the International Training Centre of International Labour Organization (ILO) or other relevant international organizations. Content, specifications and the draft agendas of the study tours and international training programmes will be shared with the EUD in advance.

Target groups and final beneficiaries:

•	SuTPs, IPSHA and residing Turkish Citizens: These are the identified main target groups of the project as they face challenges in securing stable employment due to factors such as language barriers, lack of knowledge and qualifications, and limited understanding of the Turkish labor market. The Project will address these needs by providing trainings, vocational skills development, and job placement assistance through programs like the ATP. This holistic approach aims to enhance their employability and facilitate their integration into the labor market.

•	Government institutions involved in policy making and providing socio-economic inclusion services in terms of capacity development/adaptation; Ministry of Labor and Social Security (MoLSS)-Directorate General of International Labor Force (DGILF), Turkish Employment Agency (ISKUR): These institutions play a crucial role in implementing socio-economic inclusion strategies. However, they may face constraints in terms of capacity and resource availability. The project will support these institutions in capacity development and adaptation, enhancing their effectiveness in delivering services and coordinating various aspects of the project.

•	The coordination role of the Presidency for Migration Management (PMM) is crucial for ensuring alignment between the Project and Türkiye’s national refugee response and migration policies, especially considering challenges such as limited local capacities and the necessity for harmonization with existing governmental mechanisms.

Resources Required to Achieve the Expected Results

The project will be financed by the European Union (62.035.923,06 USD). The technical cooperation model applied by the UNDP in collaboration with the local implementing partners will be maintained in the implementation of the current project (i.e. National Implementing Model with full Country Office support).

In this regard, through Preperdness, Response and Resilience Portfolio, UNDP will provide contribution both in programmatic areas and project implementation areas (operation) in the light of the experiences gained through projects already implemented/being implemented by UNDP through the following items in accordance with its corporate competencies and operation model:

- Provision of qualified individual and/or corporate expertise support, access to national and international knowledge and cooperation networks

- Transferring field level implementation experience into the project gained in other countries where UNDP operates,

- Using the analysis and planning tools developed/supported by UNDP within local/regional development areas in planning, implementation and monitoring of project activities,

- Human resources management, financial management, procurement, monitoring, and evaluation etc. and provision of services and procurement of goods provided in UNDP’s corporate operation model, and

- Fund raising for the next phases of the project.

By its mandate, UNDP does not provide direct financial resources for the projects. Among others, UNDP’s main corporate competency areas rather include provision of synergies and cooperation among projects, enabling and facilitating access to financial resources/schemes for qualified project ideas and management of fund-raising processes. In this sense, the project will benefit from the lessons learned and key project outputs derived from different completed and/or on-going projects of UNDP.

Required human resources for the project is determined as a Project Team consisting of Project Manager, Project Associate, Project Assistant, Field Coordinators based in 7 Project provinces, including local short-term consultants, technical Advisor. Moreover, local financial experts, IT experts, Project consultants of IŞKUR will be in charge of implementing the project’s activities. In addition to human resources, equipment and furniture, hardware and software, communication and audio-visual equipment, IT equipment are determined to be needed during the Project. Rental and maintenance premises and other support services provided by operations and program staff are required within the scope of the Project.

Partnerships

Within the scope of the Project, UNDP will collaborate with the ISKUR, and DGILF along with a broad range of local, regional and national stakeholders.

UNDP will be responsible for the implementation of the Project and the use of the funds under a Contribution Agreement signed with the EUD. UNDP is expected to ensure the achievement of the Project’s expected results as presented in this DoA and under the conditions stipulated in the General and Special Conditions of the Agreement.

ISKUR has a leading role and mandate on job placement through matching employers and employees and on-the-job training in Türkiye. ISKUR will be the main implementing partner and beneficiary of the Project for the achievement of Specific Objective 1 and the implementation of the activities under Output 1. It is also expected that ISKUR will mobilize its human resources and facilities at the provincial and district levels in selected pilot provinces for the successful implementation of the Project.

As main implementing partners of the Project, ISKUR will be closely involved in implementing this Project in cooperation with the UNDP and will be responsible for, among others;

  - Contributing to the initiating of the Project and further carrying out all activities in line with the Project work plan;

  - Following and monitoring the proper implementation of activities of the Project and review the reporting to the Project   Board(PB);

  - Mobilizing and coordinating other institutions involved in the Project;

  - Ensuring proper participation and representation of relevant Turkish institutions in activities organized within the Project;

  - Reviewing and approving, in a timely manner, the Project outputs.

DGILF is a leading institution in Türkiye’s governance and regulation of labour migration and is responsible for issuing work permits to ensure the inclusion of international workers in the Turkish labour market; providing technical and administrative support to migrants to help navigate government regulations; and leading inter-agency coordination on labour migration issues. In this regard, DGILF will be responsible for facilitating the work permit and work permit exemptions for the beneficiaries of the Project; and the Project will support the DG through the strengthening of the work permit automation system to serve for the development of international labour force policies in Türkiye. In addition, DGILF will also lead and guide the Project Team and partners to have a coordinated response for employment and particularly promote a skilled, trained, and adaptable workforce as well as labour market that is responsive to economic changes to achieve the objectives of the Project.

Presidency for Migration Management (PMM) is the organization responsible for migration management in Türkiye (including visas, residence permits, asylum applications, deportation, readmission, integration, etc.), and is mandated by law to approve and coordinate all projects related to migration implemented in the country by any institution. It is the secretariat of the Migration Board, which is chaired by the Minister of Interior and comprised of the Deputy Ministers from all the line ministries as the main inter-institutional coordination mechanism with regard to migration policy development. In this regard, PMM will ensure alignment between the Project and Türkiye's national refugee response and migration policies, especially considering challenges such as limited local capacities and the necessity for harmonization with existing governmental mechanisms. In addition, as it is the leading institution as regards the expenditure of EU funds in the area of migration management, PMM will be offering guidance and expertise to strengthen the Project’s relevance and impact within the existing governmental framework and providing guidance for the implementation and further improving and strengthening the Project’s expected results.

Social Security Institution (SGK) and KOSGEB (Small and Medium-Sized Enterprises Development and Support Administration) will also be invited to the relevant meetings.

EUD as representative of the EU, will contribute to the implementation of this project in the following aspects:

Follow and monitor activities and deliveries as well as the evaluation for this programme;

Participate in the PB meetings;

Attend and represent the EU in activities and other actions during the implementation of the project;

Provide advice and guidance for the purposes of improving and strengthening further the project’s expected results.

Risks and Assumptions

The main assumptions for the success of the overall Action and its implementation are:

- The political and security situation in Türkiye remains stable, ensuring uninterrupted implementation of the project activities

- The regulatory framework for work permit exemptions remains supportive, allowing smooth issuance of work permit exemption certificates for migrant workers.

- Private sector in pilot provinces has the capacity and willingness to absorb new employees.

- Support provided leads to sustainable business practices and employment creation.

- IŞKUR sustains ATP modality for SuTP/IPSHA.

- Training programs are relevant and effective in leading to employment.

- Training and consultancy services are aligned with market needs.

- Interventions effectively improve working conditions and quality of life for SMAWs.

Identified risks and mitigation measures for smooth implementation of the project are listed in Annex-  ‘’Project Risk Register’’.

Stakeholder Engagement

Target groups and final beneficiaries of the project are as follows:

SuTPs,  IPSHA, and residing Turkish Citizens: These are the identified main target groups of the project as they face challenges in securing stable employment due to factors such as language barriers, lack of knowledge and qualifications, and limited understanding of the Turkish labour market. The Project will address these needs by providing trainings, vocational skills development, and job placement assistance through programs like the ATP. This holistic approach aims to enhance their employability and facilitate their integration into the labour market.

Government institutions involved in policy-making and providing socio-economic inclusion services in terms of capacity development/adaptation; DGILF, IŞKUR: These institutions play a crucial role in implementing socio-economic inclusion strategies. However, they may face constraints in terms of capacity and resource availability. The project will support these institutions in capacity development and adaptation, enhancing their effectiveness in delivering services and coordinating various aspects of the project. The coordination role of the Presidency for Migration Management is crucial for ensuring alignment between the Project and Türkiye's national refugee response and migration policies, especially considering challenges such as limited local capacities and the necessity for harmonization with existing governmental mechanisms.

Stakeholder engagement plan for smooth implementation of the project is proposed in Annex-  ‘’Stakeholder Engagement Plan’’.

South-South and Triangular Cooperation (SSC/TrC)

N/A

Digital Solutions

Within the scope of the project, the soft skill and language courses will be offered to the beneficiaries via digital tools. Accordingly, the Project will provide a strong contribution to government institutions’, namely MoNe and IŞKUR, digital capacities. The course content and the Learning Management Systems will be produced by Anadolu Univarsity and transferred to those government institutions. Due to UNDP’s global work, a formal approach to the data lifecyle must be adapted within the Project. According to the data Principles that every project must adhere to, the project will safeguard personal data, uphold the highest ethical standards and manage data responsibly. The information of beneficiaries using the system will be stored within the system and not shared with any other parties without user consent.

The critical risks with data collection such as security issues and vulnerabilities that leak data to malicious third parties, collecting unnecessary personal data that is used, oversharing collected data with authorised third parties, breaking local privacy laws in the country, will be reminded to the responsible parties for these digital tools.

The parties will be clear towards the beneficiaries about who owns the data, who can access and manage it, what it can and cannot be used for, where, how, and with whom it will be shared, how it will be collected continuously. Specific consent will be get from the users and they will allowed to request to delete their data entirely.

Knowledge

Within the scope of the Project, first, a Turkish language course curriculum will be produced including tests to enable Turkish language training of the beneficiaries. Similarly, soft skills trainings content and platform will be developed. In addition, the mapping of outreach targets in the project provinces will contribute the current knowledge.

The other important contributions of the Project to the current knowledge will be the 8 workshops with the participation of migration related departments of local offices and HQ. The fruitful results from the workshops will be comprehensively reported. Similarly, 2 study visits on migration management applications good practices in the EU and ILO training will also contribute to the existing knowledge.

In addition to the above-mentioned resources, the regular progress reports and implemented activities will take a snapshot of the situation in Türkiye with gaps and opportunities also will be providing relevant recommendations for improvement. Project closure events and management meetings will also tools for production of knowledge.

The publications, knowledge and visibility materials produced will also be shared with UNDP’s relevant global teams and units as well as during relevant local, national, and international events around displacement.

The overall objective is to ensure due visibility of the project including on EU’s financial support and communicate the project’s objective, progress, and achievements to raise awareness of the benefits of improving employability and economic resilience of vulnerable populations, and supporting urban and rural development by creating sustainable employment opportunities for SuTPs, IPSHA and residing Turkish citizens. This will be ensured by:

•	Informing Target Groups and General Public: Keep the target groups and general public informed about project activities and achievements.

•	Ensuring Donor and Partner Visibility: Highlight roles and contributions of the EU Delegation, Ministry of Labour and Social Security - DGILF, and ISKUR, by working in close collaboration with them.

•	Positive Impact Communication: Show the project's positive impact on SuTPs, IPSHA, residing Turkish citizens, businesses, and government institutions providing socio-economic inclusion services in terms of capacity development/adaptation.

•	Creating Impactful Success Stories: Share stories that highlight the initiative's role in improving economic resilience, and working and living conditions of vulnerable populations, and supporting businesses by helping them to employ qualified and trained personnel.

•	Media Coverage: Ensure wide and impactful media coverage through press releases and interviews, focusing on increased employability, enhanced employment opportunities, and improvement of institutional effectiveness in delivering employment support services.

•	Contribution to Earthquake Recovery: Highlight contributions to Türkiye’s sustainable development, resilience, and recovery after the February 2023 earthquakes through the creation of sustainable employment opportunities.

•	Women’s Empowerment: Emphasize the project’s contributions to women's empowerment and economic resilience.

The communication and visibility activities will aim to showcase the positive results and impact of the project, by showing clearly how this initiative changes individuals’ and their families’ lives for the better. It will be important to show how this initiative increases the social and economic resilience of both individuals who have been left behind, and businesses in Türkiye. The communications activities will demonstrate how this project meets the needs and help overcome the challenges faced by both vulnerable populations and businesses on the way to decent jobs and sustainable development. It is important to show how the Project increases Türkiye’s strength and resilience and contributes to sharing the responsibility of hosting refugees, in other words, how Türkiye benefits from the Project.

Using impactful interviews with beneficiaries and all stakeholders involved, making local voices heard, sharing important figures to show the progress and impact, creating before and after stories, visualizing before and after situations will be useful.

When communicating about the project, it will be important to consider political and social sensitivities regarding refugees in Türkiye, always closely follow the developments, stay updated, and proceed prudently.

Along with the UNDP Communications Team, a dedicated Communications Officer will also be mobilized for the project at UNDP Türkiye.

In the implementation of the communication and visibility actions under the above objectives:

All necessary measures will be taken to ensure the promotion of the contribution of the EU-Türkiye financial cooperation for this Project and all initiatives under that as part of Instrument for Pre-Accession Assistance (IPA). The Budget of the Project includes the allocation of budget for actions related to visibility and communication. All related actions will be carried out in accordance with the General Conditions (Annex II - General Conditions for Contribution Agreements, Article 7).

These actions will follow the “Joint Visibility Guidelines for EC-UN Actions in the Field” at http://eeas.europa.eu/archives/delegations/rome/documents/eu_united_nations/ec_un_joint_visibility_guidelines_en.pdf as well as the visibility guidelines of the EU Delegation to Türkiye at

https://www.eeas.europa.eu/delegations/t%C3%BCrkiye/visibility-guidelines-clarification-2022-guidelines-communicating-and-raising-eu-visibility_en

The new EU-Türkiye cooperation logo should be used. The logo should be accompanied by the following text in English/Turkish:

This project is funded by the European Union.

All the project-funded materials will bear the new EU-Türkiye cooperation logo, along with the logos of UNDP, DGILF, ISKUR where appropriate.

All photos and films taken throughout the course of the project will be used in publications, websites, social media, etc. Images will be open to the use of the EU Delegation on its social media, publications, etc. Form of consent will be received from the people for using of their images. All personal information of participants including pictures of groups will be handled according to UNDP Personal Data Protection and Privacy Policy. Throughout the implementation of the project, communication and visibility activities will also be in line with the UNDP Information Classification and Handling Policy.

All equipment, if applicable, shall have a solidly fixed and durable label, as appropriate for each piece of equipment, with the EU-Türkiye cooperation logo. Confirmation must be sought from the MoLSS- DGILF, ISKUR, MoAF, and EUD regarding the visibility items. The UNDP will consult the EUD for visibility-related actions which will be implemented in accordance with Article 11 of the Financial Administrative Framework Agreement between EU-UN and the General Conditions of the EU-UNDP Contribution Agreement. The entire visibility actions will be discussed and reviewed in detail during the Inception Period.

In specific terms, the visibility-related activities will be carried out during the lifetime of the Project, as detailed further below.

The visibility materials to be produced within the scope of the Project will be shared with the relevant department at the EUD 10 days before their production.

Target groups are defined in this document under relevant sections in detail and specific terms, the following visibility-related activities will be carried out during the lifetime of the Project at hand, which can be found in the detailed Communication and Visibility section here below:

Activities and tools

•	Press releases and news pieces: Issue impact-oriented press releases and news pieces at key milestones.

•	Short videos: Produce at least 10 human story videos highlighting the project’s impact complemented by written stories.

•	Social media presence: Use UNDP Türkiye’s social media accounts to disseminate project successes and messages. (UNDP Türkiye has more than 41K followers on Twitter, more than 35K followers on Instagram, more than 44K followers on LinkedIn, and more than 32K followers on Facebook.) Dissemination of messages through UNDP Eurasia and UNDP HQ accounts will be ensured for wider outreach to the international audience.

•	Printed materials: Design, print, and distribute brochures, posters, and leaflets, ensuring online versions are available on the UNDP Türkiye’s website. All publications will be printed in recycled/recyclable materials whenever possible.

•	Visibility materials: Produce theme-based flyers, brochures, info-sheets, and promotional materials from environmentally friendly materials. Also, branding materials will be designed and produced to be used in events.

•	Field visits: Organize high-level project field visits for national and international media representatives and journalists. EU participation in these visits will be ensured by providing notification at least one month in advance.

•	Launch and closure events: Hold high-profile launch and closure events to inform stakeholders and the public about the project’s activities and impact. Press release will be disseminated after the events.

The outcomes of the above-mentioned activities will be reported, including metrics such as the number of participants, media coverage, and social media performance (e.g., engagement, number of likes, etc.).

Key messages

•	Sustainable Livelihood Opportunities: Emphasize the socio-economic development promoted by creating sustainable livelihood opportunities for refugees and residing Turkish citizens.

•	Employability in Earthquake-Affected Provinces: Highlight the role of employability in accelerating recovery and strengthening community resilience.

•	Women’s Economic Resilience: Focus on training, vocational skills development, and job placement assistance for women.

•	Social Cohesion: Stress the importance of improving working and living conditions for social cohesion.

•	Community Welfare: Promote the idea of connecting communities through sustainable employment opportunities and decent jobs.

Sustainability and Scaling Up

The project is designed to optimize multiplier effects and ensure sustainability of impact beyond its completion. These effects manifest in various ways. Firstly, targeted training programs will significantly enhance the employability of participants, which is expected to lead to higher employment rates and stimulate local economies. Another element is the project's engagement with the private sector. By fostering collaborations and networking, the project enhances job placement opportunities and establishes long-term industry relationships. This engagement benefits both employers and the workforce, creating a more dynamic and responsive labor market. In addition to these direct impacts, the project focuses on strengthening the capabilities of businesses, and governmental institutions. This institutional capacity building enhances service delivery and efficiency, contributing to the broader goals of economic and social development. This aspect aims to extend the impact of the project and offers valuable insights for future initiatives. Promoting social inclusion is another key aspect of the project. Through an inclusive approach that integrates diverse groups into the labor market the project aims to support cohesive and resilient communities. This approach not only focuses on immediate labor market needs but also fosters long-term social cohesion.

The Project is aware of the significant sustainability challenges inherent in job creation and labor market integration, as highlighted by previous interventions in this domain. To address these challenges, sustainability is embedded as a primary consideration in the design of project activities. This approach involves engaging actors from both the supply and demand sides of the labor market and developing policy tools to guide future interventions and implementations.

Central to the project are the ATPs incorporate strategies to actively involve sector actors in their design and implementation. This engagement is crucial for ensuring that the programs are aligned with the current needs and trends of the labor market. This will primarily equip the beneficiary groups with skills and capacities that are beneficial for working in specific sectors and finding jobs and integrating into the socio-economic life of Türkiye in general. Within the scope of the Project, outreach programs and market assessments are instrumental in securing employer interest and ensuring that the implementation is targeted and well-informed. This approach ensures that the training provided is relevant and directly contributes to the effective integration of participants into the labor market.

To ensure the sustainability of the project, the monitoring of employed project beneficiaries through the ATPs will be systematically conducted by İŞKUR and UNDP. İŞKUR collects periodic information on the employment status and program participation of each beneficiary registered in or having completed the program. This ensures that the project's impact on employment is continuously assessed, and that the sustainability of employment outcomes is maintained. Monitoring on the project beneficiaries and their employment status will continue following the project completion and the findings will be included in the final report of the Project. The outreach program will be designed based on the findings from the analysis of ISDEP 2 Project and inputs of chambers in the pilot areas with a view to identify the potential targets with the highest probability of employing the target groups. A 30% of retention rate is also adopted in relation to beneficiaries with continued employment following the completion of the ATP program which will be supported through the agreements İŞKUR will have with the ATP participant businesses.

Another important aspect of this sustainability effort is the delivery of soft skills training through İŞKUR local offices. The project support will enable İŞKUR to revise and adapt their training modules to meet the specific requirements of the project. Additionally, the project will assist in enhancing İŞKUR's distance learning platform. This improvement is not just for the duration of the project; it's an investment in İŞKUR's long-term capability. Post-project, the enhanced distance learning platform will remain an asset for İŞKUR, facilitating ongoing and future training initiatives so that the benefits of the project extend beyond its immediate timeframe, contributing to lasting change.

In summary, the project's sustainability strategy is multi-faceted, involving direct engagement with labor market actors, support to businesses for long-term job creation, and the development of policy tools informed by on-ground experiences and needs assessments. This comprehensive approach is designed to ensure that the project's outcomes are sustainable and that the lessons learned can be applied to future interventions, contributing to ongoing progress in the field of labor market integration.

# Project Management

Cost Efficiency and Effectiveness

The Project will build on existing national and local structures and capacities in Türkiye especially those of the MoLSS and İŞKUR in project implementation provinces. This will enable the project implementation unit to have an efficiency in project management in terms of cost efficiency and effectiveness. Moreover, UNDP will adopt a programmatic approach whereas staffing will be made to serve for and to be costed to more than one project where possible. The Project will be a continuation of ISDEP II Project of IŞKUR and will built of the previous system, which contributes the cost efficiency and effectiveness with its existing structure and knowledge.

The project will be implemented as part of UNDP’s Preperdness, Response and Resilience programme Portfolio and will thereby leverage on existing management and staff capacities, especially on operations such as procurement/finance/HR(administration, as well as projects funded under the programme by other donors. This includes, for instance, projects focusing on the facilitation of employability, funded by the Republic of Korea respectively. The project will also build on existing experience on the language training and previous livelihood projects of UNDP. Following a programmatic approach will also be relevant for procurement and other administrative issues, increasing cost efficiency of the project.

The current project is based on UNDP’s resilience-based development approach, which has been UNDP’s flagship response in several countries affected by the Syria crisis, including Jordan, Lebanon, and Iraq. UNDP Türkiye works in close partnership with its partner offices in those countries to share lessons learned.

In addition to the overall management of the project, UNDP will play a pivotal role in directly implementing sub-components that complement the İŞKUR’s ATP. UNDP brings to the table a wealth of experience in conducting skills and language training for large groups of beneficiaries. A notable example of this expertise is the 'Turkey Resilience Project in Response to the Syria Crisis,' recently funded by EU MADAD, where similar training programs were successfully executed for large groups of beneficiaries. In this project, UNDP plans to leverage this experience and the systems developed in coordination with the Ministry of National Education (MoNE) to enhance the employability of ATP beneficiaries and potential participants.

Project Management

The UNDP will establish a Project Team (PT), which will work in close cooperation with the beneficiary and implementing partners. The PT will be headed by the UNDP Programme Manager (UNDP Livelihood Projects Coordinator).

The PT responsibilities include:

•	Maintaining liaison with relevant authorities to determine what the immediate and mid-term priorities of the Project are including the preparation of plans to address these priorities;

•	Managing Project activities to ensure that immediate and mid-term priorities are within the scope of the Project;

•	Acting as the secretariat for the Project Board (PB).

In addition to the PT, depending on the nature of the work and complexity, several technical and administrative roles and services are covered by the UNDP Country Office and are cost-shared within the office. Based on the needs of the Project and the projected inputs, the relevant positions are included, on a pro-rata basis, as direct costs to the Project. The time allocation is based on the existing workflow in the UNDP office and is pro-rated to the scale of the budget and the scope of the Project requiring different time inputs from different positions:UNDP will deploy its in-house experience (i.e. relevant programme and operations staff) as well as mobilize other capacities in the form of National Personnel Service agreements and individual contracts. For this project, UNDP will avail the capacities of a Project Manager and relevant administrative and operational support staff, with oversight of the Project’s UNDP Programme Manager (UNDP Livelihood Projects Coordinator).

UNDP will provide direct country office support services (including for the functions of procurement, human resources, administrative services, communication, office space), and direct project costing will apply in line with UNDP’s cost recovery policy. Financial transactions and financial statements shall be subject to internal and external auditing procedures laid down in the Rules and Regulations of UNDP, whereby the cost of audit will be charged against the relevant budget line in project budget.

Using programme and country office staff allows UNDP to build on the existing mechanisms and exploit synergies with other ongoing projects, leading to increased efficiencies in project and budget management and procurement. The direct cost of such support will be included in the project budget and pro-rated as per UNDP’s regulations.

Project Management Unit

Key personnel involved in the program

| Project Team & Task Team members | Delivery Enabling Services |
| --- | --- |
| Programme Manager/Analyst | The Programme Manager/Analyst will be employed for the project implementation period of 36 months. The Programme Manager/Analyst is responsible for the overall management of the Project which is a part of the UNDP programme within the thematic/sectoral areas assigned. The Programme Manager /Analyst analyses political, social, and economic trends; leads formulation, management, and evaluation of programme activities within his/her portfolio; and provides policy advice services. The Programme Manager/Analyst supervises and leads the programme staff and coordinates activities of the projects’ staff. The Programme Manager/Analyst works in close collaboration with the UNDP Programme and Operations teams, technical advisors/experts, external specialists, government officials and partners, donors, and civil society to ensure successful implementation of the UNDP programme. |
| Project Manager | The Project Manager will be employed for the project implementation duration of 36 months. S/he will be reporting to the Programme Manager /Analyst and in charge of managing, coordinating, and supervising project implementation for Component 1 to ensure the overall project relevance and performance. S/he’ll ensure proper execution of all administrative activities associated with project implementation. S/he will provide technical support to the implementing partners and act as a liaison between UNDP and the partners; ensure project reports capture results, lessons learned and good practices for possible wider application. S/he will also monitor project risks, including social and environmental risks, initially identified and submit new risks to appropriate project governing bodies for consideration and decision on possible actions. |
| Procurement Officer | The Procurement Officer will be employed for the project implementation duration of 36 months and responsible for implementing operational strategies, managing procurement processes, and utilizing sourcing strategies and e-procurement tools to ensure compliance with UN/UNDP rules and regulations. S/he will develop and implement internal SOPs, conduct cost-saving analysis, and manage the entire procurement lifecycle, including tendering, contractor management, and risk assessment. The role involves preparing procurement plans, developing terms of references, and conducting procurement processes for various projects. S/he will provide guidance on contract management, implement harmonized procurement services, and contribute to corporate reporting and audits. |
| Finance Officer | The Finance Officer will be employed for the project implementation period of 36 months. Under the supervision of Programme Manager, s/he will be responsible for providing support for implementation of asset management, ensuring proper recording and transfer of assets in a timely manner; monitoring and alerting the due times of contracts, ensuring timely support is provided to contract management, timely amendments (when needed) etc., providing support for performing and closely monitoring direct cash transfer transactions and assist in the preparation of required documentation. S/he’ll be responsible for the accuracy of account codes red into UNDP’s corporate management systems and the clearance processes of the invoices before submission for payment. S/he’ll serve as the focal point of the management of payments through Request for Direct Payment (RDP), Responsible Party Agreement (RPA), and other contract modalities of UNDP. S/he will be the focal point for any type of audits required. S/he’ll also have duties of keeping records, collecting necessary forms, assisting development of project budgets, performing regular reviews of project budgets, and flagging errors and anomalies, and foreseeing necessary revisions. |
| M&E Officer | The M&E Officer will be employed for the project implementation period of 36 months. S/he will be responsible for supporting the assessment of the overall project’s progress, ensuring that the project is on track to deliver the agreed outcomes, and producing recommendations for any necessary adjustments. The M&E Officer will work in close coordination with the Programme Manager, Project Manager, and M&E Analyst of the UNDP CO. S/he will support the project team by undertaking data analysis to generate information for regular reporting and knowledge sharing, identifying, and summarizing good practices and lessons learned from the overall project, and delivering presentations to relevant coordination forums. This will ensure the timely and quality submission of reports, highlighting progress, documenting impact, identifying gaps, and recommending corrective measures. |
| Communication Officer | Main responsibility of the Communication Specialist is to design and implement the communication actions of the Project as well as development of communication and visibility materials in line with the agreements and as per the Communication and Visibility plan of the Action. He/she will work closely with the UNDP communication unit. Substance of communication will be cleared by the UNDP communication unit for corporate compliance, alignment with EU, UNDP and İŞKUR visibility requirements and country context. |
| Project Associate | The Project Associate will be employed for the project implementation duration of 36 months. Project Associate will support the project team to ensure effective project planning and implementation. S/he is expected to compile and summarize information and data for the formulation of project work plans, draft annual/quarterly budgets, proposals on implementation arrangements, and other specific project-related topics or issues. S/he will also provide comprehensive support in all aspects of project implementation in accordance with the project document, annual work plans, and other agreements between UNDP and responsible partners. Additionally, s/he will ensure the quality of delivery by consultants, beneficiaries, and contracted companies, and communicate findings. They will be responsible for ensuring compliance with project business processes, including UNDP Project Operational Policies and Procedures (POPP) and UNDP Standard Operating Procedures (SOP). Furthermore, s/he will provide administrative and logistical support to ensure successful project delivery, which includes organizing/coordinating project events and selecting appropriate venues, coordinating project procurement procedures, maintaining project records and files, recruiting project team members, and supporting contracting activities. |
| Project Assistant | The Project Assistant will be employed for the project implementation duration of 36 months. Project Assistant will support the project team to ensure effective project planning and implementation. S/he will assist in compiling and summarizing information and data for the formulation of project work plans, and in consultation with the project team, draft annual/quarterly budgets, proposals on implementation arrangements, and other specific project-related topics or issues. S/he will support project implementation in accordance with the project documents, annual work plans, and other agreements between UNDP and responsible partners. S/he will review project documents for completeness and compliance with relevant rules and procedures, identifying inconsistencies for referral to the supervisor. S/he will compile, summarize, and present basic information/data on specific projects and related topics or issues. Additionally, s/he will provide administrative and logistical support to ensure successful project delivery, which includes organizing/coordinating project events, procurement and finance-related activities, contract management, recruitment, and coordination of field visits and project-related missions. The Project Assistant will also be responsible for drafting correspondence and documents, supporting the finalization of administrative correspondence, handling telephone inquiries, fax, post, and e-mail transmissions, and coordinating appointments. S/he will provide interpretation during project-related meetings and events and translate documents from English to Turkish or from Turkish to English as needed. |
| Provincial Coordinator/Associates (x7) | The provincial coordinators will be employed for the project implementation duration of 36 months in each province. Under the supervision of the Project Manager (if the project province covers both components, then the coordinator will also report to the Programme Manager in a matrix structure), the provincial coordinators will be responsible for the coordination of project activities at the field level, as well as liaison with provincial, regional, national, and international stakeholders at the institutional level. They will oversee regular communication and coordination with local partners, project counterparts, stakeholders, and beneficiaries, and will develop and maintain effective mechanisms for integrating and responding to their feedback and insights. They will collect, analyse, and present information for monitoring and evaluation of project implementation against project targets, as well as for audit purposes. Additionally, they will identify gaps in implementation and provide support in bridging those gaps in consultation with their supervisor and partners. The coordinators will also assist in organizing field and study visits, missions, workshops, roundtables, and conferences within the project. |
| Provincial Project Assistants (x3) | The Provincial Project Assistants will be employed for the project implementation duration of 36 months in the provinces where the two Components will be implemented. The overall duty of the Provincial Project Assistants is assistance to the Provincial Coordinators and administrative support. In addition to their daily routine, the Provincial Project Assistants will also fulfil the tasks to be assigned by supervisors. In addition to the PT, depending on the nature of the work and complexity, several technical and administrative roles and services are covered by the UNDP Country Office and are cost-shared within the office. Based on the needs of the action and the projected inputs, the following positions are included, on a pro-rata basis, as direct costs to the Action. The time allocation is based on the existing workflow in the UNDP office and is pro-rated to the scale of the budget and the scope of the action requiring different time inputs from different positions. |

# Results Framework

Intended Outcome as stated in the UNSDCF/Country [or Regional] Programme Results and Resource Framework: Outcome #1.3: By 2025, people under the Law on Foreigners and International Protection are supported towards selfreliance.

Outcome indicators as stated in the Country Programme [or Regional] Results and Resources Framework, including baseline and targets: Output 1.1. Displaced populations are equipped with the knowledge and skills to engage in the socioeconomic life of their host community. Number of people benefiting from jobs and improved livelihoods in crisis or post-crisis settings, disaggregated by sex Baseline (2021): 68,969 Target (2025): 76,169 Output 1.4. Sustainable job opportunities created for displaced populations and host communities. Number of interventions to increase labour absorption capacity of businesses to accommodate displaced populations Baseline (2021): 17 Target (2025): 29

Applicable Output(s) from the UNDP Strategic Plan: Output 3.4 Integrated development solutions implemented to address the drivers of irregular and forced migration, enhance the resilience of migrants, forcibly displaced and host communities, and expand the benefits of human mobility

Project title and Quantum Project Number: Skills Development for Improved Employability

| EXPECTED OUTPUTS | OUTPUT INDICATORS | DATA SOURCE | BASELINE |  | ## TARGETS (by frequency of data collection) |  |  |  | ## DATA COLLECTION METHODS & RISKS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Value | Year | Year 1 | Year 2 | Year 3 | ## FINAL |  |
| Output 1 Employability of beneficiaries’ consisting of SuTPs/ IPSHA and residing Turkish citizens is improved through consultancy and training services and ATP | - Number of beneficiaries (SuTPs/IPSHA and Turkish citizens) who completed ATP. | ISKUR employment records/database. | 30,566 | 2023 | 2,000 | 5,000 | 5,000 | 12,000 (At least 6,000 SuTP’s/IPSHA) At least 25% Female (3,000) | The risk of the private sector in pilot provinces not having the capacity and willingness to absorb new employees. The risk that ATP does not effectively match beneficiaries with suitable employment opportunities. The risk that refugees and residing Turkish citizens are not willing and able to participate in the training programs and employment opportunities offered. |
|  | 1.2 Number of beneficiaries supported to obtain work permit | DGILF records | 721 | 2023 | 300 | 750 | 750 | 1,800 | The risk that refugees and residing Turkish citizens are not willing and able to participate in the training programs and employment opportunities offered. |
| Output 2 ISKUR and DGILF’s training management capacity strengthened | 2.1 Distance Learning Management System for ISKUR developed and operationalised. | Project Monitoring Reports | No | 2023 | Yes |  |  | Yes | The risk that training contents does not address skills needs and participant profile. The risk that training model conflicts with employer expectations and work hours. The risk that training services are not aligned with market needs. Pre- and post-test for TOT and facilitator trainings |
|  | 2.2 Number of ISKUR and MONE staff trained as facilitators/trainers | Project M&E tools and systems | 0 | 2023 | 42 |  |  | 42 |  |
|  | 2.3 Number of course content packages adapted and delivered for Turkish Language Courses and soft skills trainings | LMS database, MoNE database system | 0 | 2023 | 10 |  |  | 10 |  |
|  | 2.4 Number of ‘person training days’ provided to language course trainers and İŞKUR’ local office facilitators | Pre- and post-test for ToT and facilitator trainings | 0 | 2023 | 20 | 200 | 200 | 420 |  |
|  | 2.5 Number of workshops conducted for İŞKUR and DGILF Personnel | LMS database, MoNE database system | 0 | 2023 | 2 | 3 | 3 | 8 |  |
|  | 2.6 Number of institutions continuously supported with equipment, vehicles and renovation | LMS database, MoNE database system | 0 | 2023 |  |  | 2 | 2 |  |
| Output 3 ISKUR and DGIL’s training management capacity strengthened | 3.1 Number of beneficiaries who completed soft skills trainings | Project monitoring reports, Project M&E tools and systems | 0 | 2023 | 2,000 | 5,000 | 5,000 | 12,000 (at least 6000 SuTP/IPSA, 25% female) | Pre- and post-test for TOT and facilitator trainings The risk that refugees and residing Turkish citizens are not willing and able to participate in the training programs and employment opportunities offered |
|  | 3.2 Number of beneficiaries who completed extended soft skills trainings | LMS database, MoNE database system | 0 | 2023 | 1,000 | 2,500 | 2,500 | 6,000 (25% female) |  |
|  | 3.3 Number of adult SuTPs/IPSHA beneficiaries who completed one or more Turkish Language Courses | LMS database, MoNE database system | 0 | 2023 | 1,000 | 2,500 | 2,500 | 6,000 (25% female) |  |

# Monitoring And Evaluation

In accordance with UNDP’s programming policies and procedures, the project will be monitored through the following monitoring and evaluation plans: [Note: monitoring and evaluation plans should be adapted to project context, as needed]

Monitoring Plan

| Monitoring Activity | Purpose | Frequency | Expected Action | Partners (if joint) |
| --- | --- | --- | --- | --- |
| Track results progress | Progress data against the results indicators in the RRF will be collected and analysed to assess the progress of the project in achieving the agreed outputs. | Quarterly or in the frequency required for each indicator. | Slower than expected progress will be addressed by project management. | N/A |
| Monitor and Manage Risk | Identify specific risks that may threaten achievement of intended results. Identify and monitor risk management actions using a risk log. This includes monitoring measures and plans that may have been required as per UNDP’s Social and Environmental Standards. Audits will be conducted in accordance with UNDP’s audit policy to manage financial risk. | At least annually | Risks are identified by project management and actions are taken to manage risk. The risk log is actively maintained to keep track of identified risks and actions taken. | N/A |
| Learn | Knowledge, good practices and lessons will be captured regularly, as well as actively sourced from other projects and partners and integrated back into the project. | At least annually | Relevant lessons are captured by the project team and used to inform management decisions. | N/A |
| Annual Project Quality Assurance | The quality of the project will be assessed against UNDP’s quality standards to identify project strengths and weaknesses and to inform management decision making to improve the project. | At design and appraisal, implementation (every two years) and closure stages | Areas of strength and weakness will be reviewed by project management and used to inform decisions to improve project performance. | N/A |
| Review and Make Course Corrections | Internal review of data and evidence from all monitoring actions to inform decision making. | Every two months | Performance data, risks, lessons and quality will be discussed by the project board and used to make course corrections. | N/A |
| Project Report | A progress report will be presented to the Project Board and key stakeholders, consisting of progress data showing the results achieved against pre-defined annual targets at the output level, the annual project quality rating summary, an updated risk long with mitigation measures, and any evaluation or review reports prepared over the period. | Annually |  | N/A |
| Project Review (Project Board) | The project’s governance mechanism (i.e., project board) will hold regular project reviews to assess the performance of the project and review the Multi-Year Work Plan to ensure realistic budgeting over the life of the project. In the project’s final year, the Project Board shall hold an end-of project review to capture lessons learned and discuss opportunities for scaling up and to socialize project results and lessons learned with relevant audiences. | Every two months | Any quality concerns or slower than expected progress should be discussed by the project board and management actions agreed to address the issues identified. | N/A |

Evaluation Plan

| Evaluation Title | Partners (if joint) | Related Strategic Plan Output | UNSDCF/CPD Outcome | Planned Completion Date | Key Evaluation Stakeholders | Cost and Source of Funding |
| --- | --- | --- | --- | --- | --- | --- |
| Final Evaluation | N/A | Output 3.4 Integrated development solutions implemented to address the drivers of irregular and forced migration, enhance the resilience of migrants, forcibly displaced and host | Outcome #1.3: By 2025, people under the Law on Foreigners and International Protection are supported towards selfreliance. | 31.12.2027 | EUD, İŞKUR, DGILF | 62.035.923,06 USD |

# Multi-Year Work Plan

| EXPECTED OUTPUTS | PLANNED ACTIVITIES | Planned Budget by Year |  |  | RESPONSIBLE PARTY |  | PLANNED BUDGET |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Y1 | Y2 | Y3 |  | Funding Source |  | Budget Description | Amount |
| Output 1: Employability of beneficiaries’ consisting of SuTPs/ IPSHA and residing Turkish citizens is improved through consultancy and training services and ATP Gender marker: GEN 2 | 1.1 Revision of ATP digital system and implementing guidelines | $756,000 | $ 0 | $ 0 | UNDP | EU |  | 72800 Information Technology Equipment | $756,000 |
|  | 1.2 ATP implementation | $745,500 | $21,992,250 | $21,992,250 | UNDP & ISKUR | EU |  | 71800 Contractual Services – IP | $44,730,000.00 |
|  | 1.3 Work permit support for SuTPs/ IPSHA beneficiaries | $7.302.75 | $127,798.13 | $127,798.13 | UNDP & ISKUR | EU |  | 71800 Contractual Services – IP | $262,899.00 |
|  | 1.4 Business engagement and outreach for ATP | $14,053.20 | $66,752.70 | $66,752.70 | UNDP | EU |  | 72400 Communication & Audio Visual Equipment | $147,558.60 |
| Output 2: ISKUR and DGILF’s training management capacity strengthened. Gender marker: GEN 2 | 2.1 Institutional support for facilitation of ATP | $1,162,052.83 | $1,692,445.41 | $1,692,445.41 | UNDP | EU |  | 72800 Information Technology Equipment | $4,546,943.65 |
|  |  | $435,750.00 | - | - | UNDP | EU |  | 72200 Equipment and Furniture | $435,750.00 |
| Output 3: Beneficiaries are equipped with the required soft skills and Turkish language capabilities for improved employability. Gender marker: GEN 2 | 3.1 Turkish language courses to SuTP/ IPSHA beneficiaries | $1,212,603.00 | $1,287,168.75 | $1,287,168.75 | UNDP & MoNE | EU |  | 71800 Contractual Services – IP | $3,786,940.50 |
|  | 3.2 Soft-skills trainings to beneficiaries | $841,312.50 | $335,343.75 | $335,343.75 | UNDP & ANADOLU UNIVERSITY | EU |  | 71800 Contractual Services – IP | $1,512,000.00 |
| Output 4: UNDP Arrangements Gender Marker: GEN2 | 4.1. Evaluation | $0 | $0 | $52,500.00 | UNDP | EU |  | 74100 Professional Services | $52,500.00 |
|  | 4.2. HR (Salary, DSA, IC Contracts) | $733,265.40 | $709,860.90 | $709,860.90 | UNDP | EU |  | 71400 Contractual Services - Individuals | $2,152,987.20 |
|  | 4.3. All Travels | $42,052.50 | $110,355.00 | $110,355.00 | UNDP | EU |  | 71600 Travel | $262,762.50 |
|  | 4.4. Equipment and Supplies | $127,528.77 | $15,750.00 | $15,750.00 | UNDP | EU |  | 72200 Equipment and Furniture | $159,028.77 |
|  | 4.5. Local Office | $25,200.00 | $44,100.00 | $44,100.00 | UNDP | EU |  | 73100 Rental & Maintenance - Premises | $113,400.00 |
|  | 4.6. Launch/Workshops/Closing etc. | $80,200.09 | $270,772.86 | $297,022.86 | UNDP | EU |  | 75700 Training, Workshop, Conference | $647,995.80 |
|  | 4.7. Visibility | $6,111.00 | $25,399.50 | $25,399.50 | UNDP | EU |  | 74200 Audio Visual & Print Prod. Costs | $56,910.00 |
|  | 4.8. Other (All Supporting Activities) | $8,400.00 | $8,925.00 | $8,925.00 | UNDP | EU |  | 72100 Contractual Services - Companies | $26,250.00 |
| Subtotal Direct Eligible Cost |  | $6,197,332.01 | $26,713,172.01 | $26,739,422.00 |  |  |  |  | $59,649,926.02 |
| General Management Support (%4) |  | $247,893.28 | $1,068,526.88 | $1,069,576.88 |  |  |  |  | $2,385,997.04 |
| Total Project Budget |  | $6,445,225.29 | $27,781,698.89 | $27,808,998.88 |  |  |  |  | $62,035,923.06 |

# Governance and Management Arrangements

Figure: Project Management Structure

Project Board

End Recipient

Turkish Employment Agency (ISKUR) & Directorate General of International Labor Force (DGILF)

Contracting Authority

EUD

Organization

UNDP Türkiye CO

Natural Members of PB

PSB*, MFA* Stakeholders

PMM, MoLSS

Project Technical Management Team

- ISKUR

- UNDP

- DGILF

Project Management Structure

Project Implementation Team

Programme Manager/Analyst (UNDP Livelihood Projects Coordinator)

Project Manager

Procurement Officer

Finance Officer

M&E Officer

Communication Officer

Project Associate

Project Assistant

Provincial Coordinator/Associate

Provincial Coordinator/Associate

Provincial Coordinator/Associate

Assistant Resident Representative (Programme)

UNDP Quality Assurance Team

HR Administrator

Human Rights and Decent Work Specialist

Procurement Analyst

Programme Finance Administrator

Gender Analyst

Comms Specialist

Administrative Associate

ICT Analyst

Programme Support Center Associates

Travel and Security Associate

Partnership and Quality Assurance

Project Board

End Recipient

Turkish Employment Agency (ISKUR) & Directorate General of International Labor Force (DGILF)

Contracting Authority

EUD

Organization

UNDP Türkiye CO

Natural Members of PB

PSB*, MFA* Stakeholders

PMM, MoLSS

Project Technical Management Team

- ISKUR

- UNDP

- DGILF

Project Management Structure

Project Implementation Team

Programme Manager/Analyst (UNDP Livelihood Projects Coordinator)

Project Manager

Procurement Officer

Finance Officer

M&E Officer

Communication Officer

Project Associate

Project Assistant

Provincial Coordinator/Associate

Provincial Coordinator/Associate

Provincial Coordinator/Associate

Assistant Resident Representative (Programme)

UNDP Quality Assurance Team

HR Administrator

Human Rights and Decent Work Specialist

Procurement Analyst

Programme Finance Administrator

Gender Analyst

Comms Specialist

Administrative Associate

ICT Analyst

Programme Support Center Associates

Travel and Security Associate

Partnership and Quality Assurance

This project will be implemented through a national implementation modality (NIM), with Turkish Labor Institution (İŞKUR) as the implementing partner. UNDP’s rules and regulations for program management will apply throughout the project and UNDP will also provide direct project management support including procurement, financial management and strategic support.

The Project Support role provides administration, management and technical support to the Project Manager as required by the needs of the Project Manager. The provision of any Project Support on a formal basis is optional.  In most projects, project support includes HR, procurement and PSC (Program Service Center) services.

A Project Board (PB, also called Project Steering Committee) with representation from İŞKUR, Presidency of Strategy Budget, Ministry of Foreign Affairs, Ministry of Labor and Social Security, Presidency of Migration Management, EUD and UNDP will be set up to guide and oversee the implementation of the project. The PB will jointly decide on the critical aspects of the project, including possible synergies with other ongoing initiatives in the region. PB will also be monitoring the results achieved with the project.

The Donor, which is the EUD, becomes a natural member of the Project Board. In addition to the donor of the Project, the Presidency of the Republic of Türkiye, the Presidency of Strategy and Budget (PSB) & Ministry of Foreign Affairs are also natural members of the Project Board. PSB is the Government coordinating agency of the UNDP in Türkiye and ensures that all UNDP programs are designed/implemented in line with national priorities. Ministry of Foreign Affairs gives final approval to all UNDP implemented projects, hence has an overall oversight function under each project.

In case consensus cannot be reached within the Board, the UNDP Resident Representative (or their designate) will mediate to find consensus and, if this cannot be found, will take the final decision to ensure project implementation is not unduly delayed.

The Project Board will:

When project is initiated:

•	Provide general, high-level, strategic oversight to the project activities including financial oversight

•	Agree on the Project Manager responsibilities, as well as the responsibilities of the other members of the Project team

•	Delegate any Project Assurance function as appropriate.

•	Review and appraise detailed Project Plans and AWP, including the risk log and the monitoring and communication plan.

During the implementation / running of the project, specific roles of the PB will include:

•	Provide project and policy implementation oversight

•	Provide overall guidance and direction to the project, ensuring it remains within specified constraints

•	Approve annual work plans and budgets; and based on the approved annual work plans (AWP) authorize any major deviation from the approved work plans and budgets.

•	Conduct meetings every two months and provide direction and recommendations to ensure agreed deliverables are produced satisfactorily according to plans.

•	Approve changes and amendments to the existing project document

•	Consider recommendations from the Technical Working Group (if any).

•	Monitor progressive achievement of project objectives and provide guidance on long term sustainability of the project’s achievements

•	Provide high-level quality assurance for project results and input and advice to on-going risk analysis.

•	Undertake mobilization of funding for the project and consider funding for emerging issues.

•	Invite representatives of other project beneficiaries to inform on their specific activities and needs.

•	Provide overall guidance and direction to the project.

•	Address project issues as raised by the Project Manager

•	Provide guidance and agree on possible management actions to address specific risks.

•	Agree on Project Manager’s tolerances within the AWP.

•	Conduct regular meetings to review the Project Annual Progress Report and provide direction and recommendations to ensure that the agreed deliverables are produced satisfactorily according to plans.

•	Review Combined Delivery Reports (CDR) prior to certification by the Implementing Partner.

•	Appraise the Project Annual Review Report, make recommendations for the next AWP, and inform the Outcome Board about the results of the review.

•	Provide ad-hoc direction and advice for exception situations when project manager’s tolerances are exceeded.

•	Assess and decide on project changes through revisions.

When the project is being closed:

•	Review and approve the Final Project Review Report, including lessons learned.

•	Commission project evaluation when required.

•	Assure that all Project deliverables have been produced satisfactorily.

•	Review and approve the Final Project Review Report, including Lessons-learned.

•	Make recommendations for follow-on actions to be submitted to the Outcome Board.

•	Commission project evaluation if it is required.

•	Notify operational completion of the project to the Outcome Board

The PB will meet every two montrhs throughout project period.

The implementing partner (IP), which is İŞKUR for this project, will ultimately be responsible for the project implementation and will be supported by UNDP in terms of technical implementation. The IP’s role is to ensure that the project is focused throughout its life cycle on achieving its objectives and delivering outputs that will contribute to higher level outcomes. The main responsibilities of İŞKUR are as follows;

•	to ensure that there is a coherent management organization structure and logical set of plans,

•	to set tolerances in the AWP and other plans as required for the Project Manager,

•	to monitor and control the progress of the project at a strategic level,

•	to ensure that risks are being tracked and mitigated as effectively as possible,

•	to brief relevant stakeholders about project’s progress, and

•	to organize and chair Project Board meetings.

Senior Supplier (UNDP)

The Senior Supplier represents the interests of the parties which provide funding and/or technical expertise to the development project/initiation plan. The Senior Supplier’s primary function within the Project Board is to provide guidance regarding the technical feasibility of the initiation plan. The Senior Supplier role must have the authority to commit to or acquire supplier resources required. If necessary, more than one person may be required for this role.

Specific Responsibilities (as part of the above responsibilities for the Project Board)

•	Make sure that progress toward the outputs remains consistent from the supplier’s perspective.

•	Promote and maintain focus on the expected output(s) from the point of view of supplier management.

•	Ensure that the supplier resources required for the initiation plan are made available.

•	Contribute supplier opinions on Project Board decisions on whether to implement recommendations on proposed changes.

•	Arbitrate on and ensure the resolution of any supplier priority or resource conflicts.

Implementation Partners

The implementation partners will be ISKUR and UNDP and will be responsible for, among others, contributing to the initiating of the Project and further carrying out all activities in line with the Project work plan, following and monitoring the proper implementation of activities of the Project and review the reporting to the Project Steering Committee (PSC), mobilizing and coordinating other institutions involved in the Project, ensuring proper participation and representation of relevant Turkish institutions in activities organized within the Project, reviewing and approving, in a timely manner, the Project outputs.

Project Assurance

The Project Assurance role supports the Project Board by carrying out objective and independent project oversight and monitoring functions. This role ensures appropriate project management milestones are managed and completed.

Project Assurance has to be independent of the Project Manager; therefore, the Project Board cannot delegate any of its assurance responsibilities to the Project Manager. At UNDP Project Assurance function belongs to ARR/P, Portfolio Manager, M&E and KM Analyst and M&E Advisor Portfolio with a clear mandate for oversight and monitoring functions.

Project assurance can also include key staff in Beneficiary institutions that have a stake in the quality execution of the project. However, project assurance function cannot be assumed by Senior Executive since assurance function is to be carried out by an impartial party.

The Project will be led by a project manager who will be responsible for the day-to-day management of project implementation including administration and project finance. The Project Manager will be responsible for overall team management and supervision in both Ankara and field locations. The Project Manager will be the first responsible for project level reporting and support project specific donor engagement. Project Managers are also focal points for respective national level Government implementing partner.

Project’s day-to-day implementation will be carried out by the Project team as well as UNDP staff providing direct project support.

UNDP has received total budget 59,081,831.48 EUR from the donor, European Union, and will be responsible of making payments according to the needs of project activities (as outlined in budget section). UNDP will also provide direct project implementation support for procurement, contract management and budget/financial management as well as content. UNDP’s direct costs will be charged in line with its rules and regulations, as outlined in the project document and budget. Financial transactions and financial statements shall be subject to the internal and external auditing procedures laid down in the Regulations and Rules of UNDP.

# Legal Context

Türkiye is a signatory of a basic agreement to govern the United Nations Development Programme’s (UNDP) assistance to the country, being the provisions of the Revised Standard Agreement signed between the Government and the Technical Assistance Board, which is one of the predecessor entities of UNDP (the “Basic Agreement”) on 21 October 1965.

In this regard, the project document shall be the instrument envisaged and defined in the Supplemental Provisions,(https://popp.undp.org/_layouts/15/WopiFrame.aspx?sourcedoc=/UNDP_POPP_DOCUMENT_LIBRARY/Public/FRM_Pipeline%20and%20Revenue%20Management_Annexure%208%20-%20SBAA_Standard%20Annex%20to%20Project%20Document.doc&action=default&DefaultItemOpen=1) to the Project Document, attached hereto and forming an integral part hereof, as “the Project Document”.

This project will be implemented by Turkish Employment Agency (“Implementing Partner”) in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

# Risk Management

Government Entity (NIM)

- Consistent with the Article III of the SBAA [or the Supplemental Provisions to the Project Document], the responsibility for the safety and security of the Implementing Partner and its personnel and property, and of UNDP’s property in the Implementing Partner’s custody, rests with the Implementing Partner.  To this end, the Implementing Partner shall:

- put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

- assume all risks and liabilities related to the Implementing Partner’s security, and the full implementation of the security plan.

- UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the Implementing Partner’s obligations under this Project Document.

- The Implementing Partner agrees to undertake all reasonable efforts to ensure that no UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism, that the recipients of any amounts provided by UNDP hereunder do not appear on the United Nations Security Council Consolidated Sanctions List, and that no UNDP funds received pursuant to the Project Document are used for money laundering activities. The United Nations Security Council Consolidated Sanctions List can be accessed via https://www.un.org/securitycouncil/content/un-sc-consolidated-list.

- The Implementing Partner acknowledges and agrees that UNDP will not tolerate sexual harassment and sexual exploitation and abuse of anyone by the Implementing Partner, and each of its responsible parties, their respective sub-recipients and other entities involved in Project implementation, either as contractors or subcontractors and their personnel, and any individuals performing services for them under the Project Document.

(a) In the implementation of the activities under this Project Document, the Implementing Partner, and each of its sub-parties referred to above, shall comply with the standards of conduct set forth in the Secretary General’s Bulletin ST/SGB/2003/13 of 9 October 2003, concerning “Special measures for protection from sexual exploitation and sexual abuse” (“SEA”).

(b) Moreover, and without limitation to the application of other regulations, rules, policies and procedures bearing upon the performance of the activities under this Project Document, in the implementation of activities, the Implementing Partner, and each of its sub-parties referred to above, shall not engage in any form of sexual harassment (“SH”). SH is defined as any unwelcome conduct of a sexual nature that might reasonably be expected or be perceived to cause offense or humiliation, when such conduct interferes with work, is made a condition of employment or creates an intimidating, hostile or offensive work environment. SH may occur in the workplace or in connection with work. While typically involving a pattern of conduct, SH may take the form of a single incident. In assessing the reasonableness of expectations or perceptions, the perspective of the person who is the target of the conduct shall be considered.

- a) In the performance of the activities under this Project Document, the Implementing Partner shall (with respect to its own activities), and shall require from its sub-parties referred to in paragraph 4 (with respect to their activities) that they, have minimum standards and procedures in place, or a plan to develop and/or improve such standards and procedures in order to be able to take effective preventive and investigative action. These should include: policies on sexual harassment and sexual exploitation and abuse; policies on whistleblowing/protection against retaliation; and complaints, disciplinary and investigative mechanisms. In line with this, the Implementing Partner will and will require that such sub-parties will take all appropriate measures to:

  - Prevent its employees, agents or any other persons engaged to perform any services under this Project Document, from engaging in SH or SEA;

  - Offer employees and associated personnel training on prevention and response to SH and SEA, where the Implementing Partner and its sub-parties referred to in paragraph 4 have not put in place its own training regarding the prevention of SH and SEA, the Implementing Partner and its sub-parties may use the training material available at UNDP;

  - Report and monitor allegations of SH and SEA of which the Implementing Partner and its sub-parties referred to in paragraph 4 have been informed or have otherwise become aware, and status thereof;

  - Refer victims/survivors of SH and SEA to safe and confidential victim assistance; and

  - Promptly and confidentially record and investigate any allegations credible enough to warrant an investigation of SH or SEA. The Implementing Partner shall advise UNDP of any such allegations received and investigations being conducted by itself or any of its sub-parties referred to in paragraph 4 with respect to their activities under the Project Document, and shall keep UNDP informed during the investigation by it or any of such sub-parties, to the extent that such notification (i) does not jeopardize the conduct of the investigation, including but not limited to the safety or security of persons, and/or (ii) is not in contravention of any laws applicable to it. Following the investigation, the Implementing Partner shall advise UNDP of any actions taken by it or any of the other entities further to the investigation.

b) The Implementing Partner shall establish that it has complied with the foregoing, to the satisfaction of UNDP, when requested by UNDP or any party acting on its behalf to provide such confirmation. Failure of the Implementing Partner, and each of its sub-parties referred to in paragraph 4, to comply of the foregoing, as determined by UNDP, shall be considered grounds for suspension or termination of the Project.

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

- The Implementing Partner shall: (a) conduct project and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

- All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any programme or project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

- The Implementing Partner will take appropriate steps to prevent misuse of funds, fraud or corruption, by its officials, consultants, responsible parties, subcontractors and sub-recipients in implementing the project or using UNDP funds.

- In the implementation of the activities under this Project Document, UNDP places reasonable reliance upon the Implementing Partner for it to apply its laws, regulations and processes, and applicable international laws regarding anti money laundering and countering the financing of terrorism, to ensure consistency with the principles of then in force the UNDP Anti-Money Laundering and Countering the Financing of Terrorism Policy.

- The Implementing Partner will ensure that its financial management, anti-corruption, anti-fraud and anti money laundering and countering the financing of terrorism policies are in place and enforced for all funding received from or through UNDP.

- The requirements of the following documents, then in force at the time of signature of the Project Document, apply to the Implementing Partner: (a) UNDP Policy on Fraud and other Corrupt Practices and (b) UNDP Office of Audit and Investigations Investigation Guidelines. The Implementing Partner agrees to the requirements of the above documents, which are an integral part of this Project Document and are available online at www.undp.org.

- In the event that an investigation is required, UNDP has the obligation to conduct investigations relating to any aspect of UNDP projects and programmes in accordance with UNDP’s regulations, rules, policies and procedures. The Implementing Partner shall provide its full cooperation, including making available personnel, relevant documentation, and granting access to the Implementing Partner’s (and its consultants’, responsible parties’, subcontractors’ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with the Implementing Partner to find a solution.

- The signatories to this Project Document will promptly inform one another in case of any incidence of inappropriate use of funds, credible allegation of fraud or corruption or other financial irregularities with due confidentiality.

Where the Implementing Partner becomes aware that a UNDP project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption, the Implementing Partner will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). The Implementing Partner shall provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

- The Implementing Partner agrees that, where applicable, donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities which are the subject of this Project Document, may seek recourse to the Implementing Partner for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud, corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Note:  The term “Project Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Project Document, including those with responsible parties, subcontractors, and sub-recipients.

- Each contract issued by the Implementing Partner in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from the Implementing Partner shall cooperate with any and all investigations and post-payment audits.

- Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the project, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

- The Implementing Partner shall ensure that all of its obligations set forth under this section entitled “Risk Management” are passed on to each responsible party, subcontractor and sub-recipient and that all the clauses under this section entitled “Risk Management Standard Clauses” are included, mutatis mutandis, in all sub-contracts or sub-agreements entered into further to this Project Document.

# ANNEXES

# Social and Environmental Screening Template

# UNDP Social and Environmental Screening Template (v. July 2022)

The completed template, which constitutes the Social and Environmental Screening Report, must be included as an annex to the Project Document at the design stage. Note: this template will be converted into an online tool. The online version will guide users through the process and will embed relevant guidance.

### Project Information

| Project Information |  |
| --- | --- |
| 1. Project Title | Skills Development for Improved Employability |
| 2. Project Number (i.e. Quantum project ID, PIMS+) |  |
| 3. Location (Global/Region/Country) | Country - Pilot Provinces in Türkiye (İstanbul, Gaziantep, Şanlıurfa, Adana, Mersin, Bursa, İzmir, Kahramanmaraş, Sakarya, Hatay, Mardin, and Konya) |
| 4. Project stage (Design or Implementation) | Design |
| 5. Date | 26.11.2024 |

Part A. Integrating Programming Principles to Strengthen Social and Environmental Sustainability

QUESTION 1: How Does the Project Integrate the Programming Principles in Order to Strengthen Social and Environmental Sustainability?

Briefly describe in the space below how the project mainstreams the human rights-based approach

Although not strictly a humanitarian programme given its medium-term approach, the project will offer services to SuTP/IPSHA in Türkiye and will maintain strong adherence to the nine quality criteria of core humanitarian standards, as an appropriate, relevant, timely, and effective intervention to one of the main challenges hampering the social inclusion of refugee community members and other vulnerable groups. UNDP will ensure a rights-based approach in the programming and facilitate implementation by partners for effective inclusiveness, responsiveness, and accountability, with a special focus on the most vulnerable population. One of the main targets of the Project is contributing decent work through legalization of labor status of target groups. Moreover, it supports two key objectives of the Global Compact on Refugees: alleviating the burdens on host nations and empowering refugee self-sufficiency. Regionally, the Regional Refugee and Resilience Plan (3RP) Regional Strategic Overview 2023 and, more specifically, the Türkiye Country Chapter serve as the guiding framework for initiatives supporting the Turkish refugee response from the donor side. Among 3RP's strategic objectives is the expansion of livelihood and job opportunities for SuTP/IPSHA and residing Turkish citizens, which directly aligns with the objectives of the Project at hand. The Project’s actions are also aligned with the 2030 Agenda for Sustainable Development, contributing significantly to several Sustainable Development Goals (SDGs). These include ensuring inclusive and quality education (SDG 4), promoting gender equality (SDG 5), fostering sustainable economic growth and decent work (SDG 8).

Briefly describe in the space below how the project is likely to improve gender equality and women’s empowerment

There are existing inequalities that lead to limited participation of women in labor market. The project that focuses on promoting gender equality and the empowerment of women, aligning with key international strategies like the EU Gender Equality Strategy (2020-2025), UNDP's Gender Equality Strategy (2022-2025), and the UN’s SDG 5. It also supports the objectives of Türkiye's 12th National Development Plan, which emphasizes women's empowerment in the labor market. The project aims to enhance women's participation in the workforce, particularly by improving their access to vocational training and on-the-job training, especially for NEET (Not in Education, Employment, or Training) young women. The Women’s Empowerment Strategy Document (2024-2028) prioritizes vocational training and skill-building as key pathways to dignified employment opportunities for women. The project aims to significantly improve gender equality and women’s empowerment by embedding gender-sensitive strategies and practices throughout its design and implementation. Key strategies for gender mainstreaming include ensuring equal participation of women in training, employment support, and business development activities. The project will provide safe and inclusive training environments tailored to address the specific needs of women, including resources designed to overcome barriers they face in the labor market. Participatory assessments will capture women’s preferences and challenges, ensuring program designs are responsive to their unique needs. Gender-disaggregated data will be collected and analyzed to guide interventions and address existing inequalities effectively. Awareness-raising activities will emphasize the importance of gender equality in the labor market, targeting both beneficiaries and stakeholders to foster inclusive practices. To mitigate risks, such as low female participation in ATPs, the project leverages regulatory changes and sets specific targets for female engagement. Gender-specific needs will be integrated into program designs, with gender-responsive assessments and capacity-building initiatives for partners (ISKUR & DGILF) enhancing inclusivity. Recruitment processes incorporate gender criteria within Terms of Reference, and diverse, gender-balanced selection panels work to eliminate unconscious biases. Communication strategies, including the use of gender-inclusive language and targeted outreach through community-based networks, ensure accessibility and engagement. Training programs are designed with a gender-responsive lens, featuring modules on women-friendly workplace practices and empowerment. Support systems, such as buddy groups and child-friendly spaces, enable active participation by women with caregiving responsibilities. Efforts to engage men through fatherhood training and work-life balance workshops foster shared responsibilities and challenge traditional norms. Infrastructure and procurement processes align with gender-responsive principles, prioritizing safety and inclusivity. Tailored training modules address structural barriers, empowering women to enter and thrive in the workforce. Institutional partnerships and workshops further amplify outreach, advocating for registered employment and equitable policies. By integrating these comprehensive measures, the project ensures that women and men benefit equally, fostering sustainable gender equality and empowerment at all levels.

Briefly describe in the space below how the project mainstreams sustainability and resilience

Through increasing capacities of the institutions, in terms of software and hardware, the Project will contribute the sustainability of the actions in the future. Corporate knowledge on working with vulnerable groups will also promote the further solutions to the issue. The Project is designed to address challenges and enhance the economic resilience and independence of vulnerable populations in Türkiye, which include SuTPs/ IPSHA in Türkiye, and residing Turkish citizens. The aim of the project is to facilitate sustainable livelihood opportunities for these targeted populations through better employability, job opportunities, and working conditions. It is assumed that the training and support provided will be adequate for beneficiaries to secure and retain meaningful employment. The current state of the Turkish economy is expected to either remain stable or improve, facilitating job creation and enterprise success. The official policies regarding the integration of SuTPs/IPSHA to the local labour market are expected not to deteriorate, despite the recent discussions and policies promoted for safe return by PMM. Additionally, the social acceptance of the target groups, especially refugees, is presumed to remain stable, ensuring willingness from employers in certain sectors like textile or retail sectors to hire them.

Briefly describe in the space below how the project strengthens accountability to stakeholders

The project strengthens accountability to stakeholders through an inclusive and transparent implementation framework that actively engages beneficiaries, local authorities, and implementing partners. Regular consultations, feedback mechanisms, and participatory approaches enable stakeholders, including vulnerable groups, to contribute to decision-making and project design. İŞKUR and UNDP implement robust monitoring and evaluation processes, including data management and analytics, to track progress and outcomes, ensuring alignment with agreed objectives. Reporting mechanisms provide timely updates to stakeholders, including the EU, ensuring compliance with contractual obligations. This integrated approach fosters trust, ownership, and mutual accountability among all parties involved, reinforcing the project's credibility and effectiveness. Target groups and beneficiaries of the Project will close contact with field staff of the Project, those will be a part of UNDP Project Team and some of them are IŞKUR job and occupational consultants. This close contact will enable them to raise their concerns and/or grievances easily.

Part B. Identifying and Managing Social and Environmental Risks

| QUESTION 2: What are the Potential Social and Environmental Risks? Note: Complete SESP Attachment 1 before responding to Question 2. | QUESTION 3: What is the level of significance of the potential social and environmental risks? Note: Respond to Questions 4 and 5below before proceeding to Question 5 |  |  |  | QUESTION 6: Describe the assessment and management measures for each risk rated Moderate, Substantial or High |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Description (broken down by event, cause, impact) | Impact and Likelihood (1-5) | Significance (Low, Moderate Substantial, High) | Comments (optional) |  | Description of assessment and management measures for risks rated as Moderate, Substantial or High |  |  |
| There is a risk that ATP participants may become injured or harmed during applied/on-the-job due to lack of awareness on and improper enforcement of occupational health and safety measures which might result in cancellation/delays in project activities, filing of lawsuits against project partners, and reputational risks for UNDP. | I = 3 L = 1 | Low |  |  | UNDP will ensure incorporation of UNDP SES standards and compliance with national legislation on occupational health and safety in the design and implementation of works contracts by ensuring employers and employees are informed on potential OHS risks and measures with all necessary measures taken to minimize OHS risks at the work places. |  |  |
| There is a risk that low interest of female participants in ATPs due to the biased traditional gender roles which may result in low participation of women the programme | I= 3 L=2 | Moderate |  |  | Through recent regulatory changes, such as including the retail sector in ATP eligibility, may help improve gender balance and provide more opportunities for women. To overcome barriers, the project will set targets for female engagement, integrate gender-specific needs into program design, and provide gender-responsive assessments and capacity-building for stakeholders. |  |  |
|  | QUESTION 4: What is the overall project risk categorization? |  |  |  |  |  |  |
|  | Low Risk |  |  | X |  |  |  |
|  | Moderate Risk |  |  | ☐ |  |  |  |
|  | Substantial Risk |  |  | ☐ |  |  |  |
|  | High Risk |  |  | ☐ |  |  |  |
|  | QUESTION 5: Based on the identified risks and risk categorization, what requirements of the SES are triggered? (check all that apply) |  |  |  |  |  |  |
|  | Question only required for Moderate, Substantial and High Risk projects |  |  |  |  |  |  |
|  | Is assessment required? (check if “yes”) |  |  | ☐ |  |  | Status? (completed, planned) |
|  | if yes, indicate overall type and status |  |  |  | ☐ | Targeted assessment(s) |  |
|  |  |  |  |  | ☐ | ESIA (Environmental and Social Impact Assessment) |  |
|  |  |  |  |  | ☐ | SESA (Strategic Environmental and Social Assessment) |  |
|  | Are management plans required? (check if “yes) |  |  | ☐ |  |  |  |
|  | If yes, indicate overall type |  |  |  | ☐ | Targeted management plans (e.g. Gender Action Plan, Emergency Response Plan, Waste Management Plan, others) |  |

|  |  |  | ☐ | ESMP (Environmental and Social Management Plan which may include range of targeted plans) |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | ☐ | ESMF (Environmental and Social Management Framework) |  |
|  | Based on identified risks, which Principles/Project- level Standards triggered? |  | Comments (not required) |  |  |
|  | Overarching Principle: Leave No One Behind |  |  |  |  |
|  | Human Rights | X |  |  |  |
|  | Gender Equality and Women’s Empowerment | ☐ |  |  |  |
|  | Accountability | ☐ |  |  |  |
|  | 1. Biodiversity Conservation and Sustainable Natural Resource Management | ☐ |  |  |  |
|  | 2. Climate Change and Disaster Risks | ☐ |  |  |  |
|  | 3. Community Health, Safety and Security | ☐ |  |  |  |
|  | 4. Cultural Heritage | ☐ |  |  |  |
|  | 5. Displacement and Resettlement | ☐ |  |  |  |
|  | 6. Indigenous Peoples | ☐ |  |  |  |
|  | 7. Labour and Working Conditions | X |  |  |  |
|  | 8. Pollution Prevention and Resource Efficiency | ☐ |  |  |  |

Final Sign Off

Final Screening at the design-stage is not complete until the following signatures are included

| Signature | Date | Description |
| --- | --- | --- |
| QA Assessor Berkin Erol M&E Officer |  | UNDP staff member responsible for the project, typically a UNDP Programme Officer. Final signature confirms they have “checked” to ensure that the SESP is adequately conducted. |
| QA Approver Nurettin Cemil Gökpınar M&E and Knowledge Management Analyst |  | UNDP senior manager, typically the UNDP Deputy Country Director (DCD), Country Director (CD), Deputy Resident Representative (DRR), or Resident Representative (RR). The QA Approver cannot also be the QA Assessor. Final signature confirms they have “cleared” the SESP prior to submittal to the PAC. |
| PAC Chair Mustafa Ali Yurdupak ARR (Programme) |  | UNDP chair of the PAC. In some cases PAC Chair may also be the QA Approver. Final signature confirms that the SESP was considered as part of the project appraisal and considered in recommendations of the PAC. |

#### SESP Attachment 1. Social and Environmental Risk Screening Checklist

| Checklist Potential Social and Environmental Risks |  |  |
| --- | --- | --- |
| INSTRUCTIONS: The risk screening checklist will assist in answering Questions 2-6 of the Screening Template. Answers to the checklist questions help to (1) identify potential risks, (2) determine the overall risk categorization of the project, and (3) determine required level of assessment and management measures. Refer to the SES toolkit for further guidance on addressing screening questions. |  |  |
| Overarching Principle: Leave No One Behind Human Rights |  | Answer (Yes/No) |
| P.1 | Have local communities or individuals raised human rights concerns regarding the project (e.g. during the stakeholder engagement process, grievance processes, public statements)? | No |
| P.2 | Is there a risk that duty-bearers (e.g. government agencies) do not have the capacity to meet their obligations in the project? | No |
| P.3 | Is there a risk that rights-holders (e.g. project-affected persons) do not have the capacity to claim their rights? | No |
| Would the project potentially involve or lead to: |  |  |
| P.4 | adverse impacts on enjoyment of the human rights (civil, political, economic, social or cultural) of the affected population and particularly of marginalized groups? | No |
| P.5 | inequitable or discriminatory impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups, including persons with disabilities? 16 | No |
| P.6 | restrictions in availability, quality of and/or access to resources or basic services, in particular to marginalized individuals or groups, including persons with disabilities? | Yes |
| P.7 | exacerbation of conflicts among and/or the risk of violence to project-affected communities and individuals? | No |
| Gender Equality and Women’s Empowerment |  |  |
| P.8 | Have women’s groups/leaders raised gender equality concerns regarding the project, (e.g. during the stakeholder engagement process, grievance processes, public statements)? | No |
| Would the project potentially involve or lead to: |  |  |
| P.9 | adverse impacts on gender equality and/or the situation of women and girls? | No |
| P.10 reproducing discriminations against women based on gender, especially regarding participation in design and implementation or access to opportunities and benefits? |  | No |
| P.11 limitations on women’s ability to use, develop and protect natural resources, taking into account different roles and positions of women and men in accessing environmental goods and services? For example, activities that could lead to natural resources degradation or depletion in communities who depend on these resources for their livelihoods and well being |  | No |
| P.12 exacerbation of risks of gender-based violence? For example, through the influx of workers to a community, changes in community and household power dynamics, increased exposure to unsafe public places and/or transport, etc. |  | No |

16 Prohibited grounds of discrimination include race, ethnicity, sex, age, language, disability, sexual orientation, gender identity, religion, political or other opinion, national or social or geographical origin, property, birth or other status including as an indigenous person or as a member of a minority. References to “women and men” or similar is understood to include women and men, boys and girls, and other groups discriminated against based on their gender identities, such as transgender and transsexual people.

| Sustainability and Resilience: Screening questions regarding risks associated with sustainability and resilience are encompassed by the Standard-specific questions below |  |
| --- | --- |
| Accountability |  |
| Would the project potentially involve or lead to: |  |
| P.13 exclusion of any potentially affected stakeholders, in particular marginalized groups and excluded individuals (including persons with disabilities), from fully participating in decisions that may affect them? | No |
| P.14 grievances or objections from potentially affected stakeholders? | No |
| P.15 risks of retaliation or reprisals against stakeholders who express concerns or grievances, or who seek to participate in or to obtain information on the project? | No |
| Project-Level Standards |  |
| Standard 1: Biodiversity Conservation and Sustainable Natural Resource Management |  |
| Would the project potentially involve or lead to: |  |
| 1.1 adverse impacts to habitats (e.g. modified, natural, and critical habitats) and/or ecosystems and ecosystem services? For example, through habitat loss, conversion or degradation, fragmentation, hydrological changes | No |
| 1.2 activities within or adjacent to critical habitats and/or environmentally sensitive areas, including (but not limited to) legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities? | No |
| 1.3 changes to the use of lands and resources that may have adverse impacts on habitats, ecosystems, and/or livelihoods? (Note: if restrictions and/or limitations of access to lands would apply, refer to Standard 5) | No |
| 1.4 risks to endangered species (e.g. reduction, encroachment on habitat)? | No |
| 1.5 exacerbation of illegal wildlife trade? | No |
| 1.6 introduction of invasive alien species? | No |
| 1.7 adverse impacts on soils? | No |
| 1.8 harvesting of natural forests, plantation development, or reforestation? | No |
| 1.9 significant agricultural production? | No |
| 1.10 animal husbandry or harvesting of fish populations or other aquatic species? | No |
| 1.11 significant extraction, diversion or containment of surface or ground water? For example, construction of dams, reservoirs, river basin developments, groundwater extraction | No |
| 1.12 handling or utilization of genetically modified organisms/living modified organisms?17 | No |
| 1.13 utilization of genetic resources? (e.g. collection and/or harvesting, commercial development)18 | No |
| 1.14 adverse transboundary or global environmental concerns? | No |
| Standard 2: Climate Change and Disaster Risks |  |
| Would the project potentially involve or lead to: |  |

17 See the Convention on Biological Diversity and its Cartagena Protocol on Biosafety.

18 See the Convention on Biological Diversity and its Nagoya Protocol on access and benefit sharing from use of genetic resources.

| 2.1 areas subject to hazards such as earthquakes, floods, landslides, severe winds, storm surges, tsunami or volcanic eruptions? | No |
| --- | --- |
| 2.2 outputs and outcomes sensitive or vulnerable to potential impacts of climate change or disasters? For example, through increased precipitation, drought, temperature, salinity, extreme events, earthquakes | No |
| 2.3 increases in vulnerability to climate change impacts or disaster risks now or in the future (also known as maladaptive or negative coping practices)? For example, changes to land use planning may encourage further development of floodplains, potentially increasing the population’s vulnerability to climate change, specifically flooding | No |
| 2.4 increases of greenhouse gas emissions, black carbon emissions or other drivers of climate change? | No |
| Standard 3: Community Health, Safety and Security |  |
| Would the project potentially involve or lead to: |  |
| 3.1 construction and/or infrastructure development (e.g. roads, buildings, dams)? (Note: the GEF does not finance projects that would involve the construction or rehabilitation of large or complex dams) | No |
| 3.2 air pollution, noise, vibration, traffic, injuries, physical hazards, poor surface water quality due to runoff, erosion, sanitation? | No |
| 3.3 harm or losses due to failure of structural elements of the project (e.g. collapse of buildings or infrastructure)? | No |
| 3.4 risks of water-borne or other vector-borne diseases (e.g. temporary breeding habitats), communicable and noncommunicable diseases, nutritional disorders, mental health? | No |
| 3.5 transport, storage, and use and/or disposal of hazardous or dangerous materials (e.g. explosives, fuel and other chemicals during construction and operation)? | No |
| 3.6 adverse impacts on ecosystems and ecosystem services relevant to communities’ health (e.g. food, surface water purification, natural buffers from flooding)? | No |
| 3.7 influx of project workers to project areas? | No |
| 3.8 engagement of security personnel to protect facilities and property or to support project activities? | No |
| Standard 4: Cultural Heritage |  |
| Would the project potentially involve or lead to: | No |
| 4.1 activities adjacent to or within a Cultural Heritage site? | No |
| 4.2 significant excavations, demolitions, movement of earth, flooding or other environmental changes? | No |
| 4.3 adverse impacts to sites, structures, or objects with historical, cultural, artistic, traditional or religious values or intangible forms of culture (e.g. knowledge, innovations, practices)? (Note: projects intended to protect and conserve Cultural Heritage may also have inadvertent adverse impacts) | No |
| 4.4 alterations to landscapes and natural features with cultural significance? | No |
| 4.5 utilization of tangible and/or intangible forms (e.g. practices, traditional knowledge) of Cultural Heritage for commercial or other purposes? | No |
| Standard 5: Displacement and Resettlement |  |
| Would the project potentially involve or lead to: |  |
| 5.1 temporary or permanent and full or partial physical displacement (including people without legally recognizable claims to land)? | No |
| 5.2 economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation)? | No |
| 5.3 risk of forced evictions?19 | No |
| 5.4 impacts on or changes to land tenure arrangements and/or community based property rights/customary rights to land, territories and/or resources? | No |
| Standard 6: Indigenous Peoples |  |
| Would the project potentially involve or lead to: |  |
| 6.1 areas where indigenous peoples are present (including project area of influence)? | No |
| 6.2 activities located on lands and territories claimed by indigenous peoples? | No |
| 6.3 impacts (positive or negative) to the human rights, lands, natural resources, territories, and traditional livelihoods of indigenous peoples (regardless of whether indigenous peoples possess the legal titles to such areas, whether the project is located within or outside of the lands and territories inhabited by the affected peoples, or whether the indigenous peoples are recognized as indigenous peoples by the country in question)? If the answer to screening question 6.3 is “yes”, then Standard 6 requirements apply, and the potential significance of risks related to impacts on indigenous peoples must be Moderate or above. * | No |
| 6.4 the absence of culturally appropriate consultations carried out with the objective of achieving FPIC on matters that may affect the rights and interests, lands, resources, territories and traditional livelihoods of the indigenous peoples concerned? | No |
| 6.5 the utilization and/or commercial development of natural resources on lands and territories claimed by indigenous peoples? | No |
| 6.6 forced eviction or the whole or partial physical or economic displacement of indigenous peoples, including through access restrictions to lands, territories, and resources? Consider, and where appropriate ensure, consistency with the answers under Standard 5 above | No |
| 6.7 adverse impacts on the development priorities of indigenous peoples as defined by them? |  |
| 6.8 risks to the physical and cultural survival of indigenous peoples? | No |
| 6.9 impacts on the Cultural Heritage of indigenous peoples, including through the commercialization or use of their traditional knowledge and practices? Consider, and where appropriate ensure, consistency with the answers under Standard 4 above. | No |
| Standard 7: Labour and Working Conditions |  |
| Would the project potentially involve or lead to: (note: applies to project and contractor workers) |  |
| 7.1 working conditions that do not meet national labour laws and international commitments? | No |
| 7.2 working conditions that may deny freedom of association and collective bargaining? | No |

| 7.3 use of child labour? | No |
| --- | --- |
| 7.4 use of forced labour? | No |
| 7.5 discriminatory working conditions and/or lack of equal opportunity? | No |
| 7.6 occupational health and safety risks due to physical, chemical, biological and psychosocial hazards (including violence and harassment) throughout the project life-cycle? | Yes |

| Standard 8: Pollution Prevention and Resource Efficiency |  |
| --- | --- |
| Would the project potentially involve or lead to: |  |
| 8.1 the release of pollutants to the environment due to routine or non-routine circumstances with the potential for adverse local, regional, and/or transboundary impacts? | No |
| 8.2 the generation of waste (both hazardous and non-hazardous)? | No |
| 8.3 the manufacture, trade, release, and/or use of hazardous materials and/or chemicals? | No |
| 8.4 the use of chemicals or materials subject to international bans or phase-outs? For example, DDT, PCBs and other chemicals listed in international conventions such as the Montreal Protocol, Minamata Convention, Basel Convention, Rotterdam Convention, Stockholm Convention | No |
| 8.5 the application of pesticides that may have a negative effect on the environment or human health? | No |
| 8.6 significant consumption of raw materials, energy, and/or water? | No |

Risk Analysis

| Project Title: Skills Development for Improved Employability | Project Number: | Date: Click or tap to enter a date. |
| --- | --- | --- |

| # | Event | Cause | Impact(s) | Risk Category and Sub-category (including Risk Appetite) | Impact, Likelihood & Risk Level (see Annex 3 Risk Matrix) | Risk Valid From/To | Risk Owner (individual accountable for managing the risk) | Risk Treatment and Treatment Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | There is a risk that policy and legislative changes regarding the status of SuTPs/IPSHA may occur | As a result of political orientation of the government | Which will result in invalidation of Project’s employment support modality | 6. REGULATORY (6.1. Changes in the regulatory framework within the country of operation) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 1 - Not likely Impact: 4 - Extensive Risk level: LOW (equates to a risk appetite of CAUTIOUS) | From: 01.Jan.2025 To: 31.Dec.2027 | Project Manager | Risk Treatment 1.1: Establish a monitoring system to track policy changes. Regularly communicate with government stakeholders to stay updated and adapt project plans proactively. Risk Treatment Owner: Project Manager |
|  |  |  |  |  |  |  |  | Risk Treatment 1.2. If significant changes occur, the Project Steering Committee will be engaged for prompt intervention and strategizing alternative approaches. Risk Treatment Owner: Project Manager |
|  |  |  |  |  |  |  |  | Risk Treatment 1.3. If the policy change signal occurs, the signal will be escalated to the Steering Committee, the Project structure should be revised by the PSC. Risk Treatment Owner: Project Manager |
|  |  |  |  |  |  |  |  | Risk Treatment 1.4. A monitoring system to track any changes in work permit conditions will be established. Risk Treatment Owner: Project Manager |
|  |  |  |  |  |  |  |  | Risk treatment 1.5. Engagement with legal experts and government officials will be established for insights and updates. In case of changes, adaption of the project structure to comply with new legal requirements, ensuring minimal disruption will be made if possible. If necessary, the issue will be escalated to the Project Steering Committee. Risk Treatment Owner: Project Manager |
| 2 | There is a risk that DGILF may increase the fee for SuTP/IPSHA work permits | As a result of changes in institutional policy | Which will result in additional cost in the Project budget | 6. REGULATORY (6.1. Changes in the regulatory framework within the country of operation) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 1 - Not likely Impact: 4 - Extensive Risk level: LOW (equates to a risk appetite of CAUTIOUS) | From: 01.Jan.2025 To: 31.Dec.2027 | Project Manager | Risk Treatment 2.1: Financial structure will be regularly reviewed considering potential changes in costs. Engagement will be done through the Project Steering Committee for financial planning and adjustments if required. Risk Treatment Owner: Project Manager |
|  |  |  |  |  |  |  |  | Risk Treatment 2.2: If the policy change signal occurs, the signal will be escalated to the Steering Committee, the Project structure will be revised by PSC Risk Treatment Owner: Project Manager |
| 3 | There is a risk that monetary policy-induced adverse macro economic conditions may emerge | As a result of national and global political and economic developments | Which will impact in exchange rate induced additional costs undermining beneficiary targets of the Project. | 2. FINANCIAL (2.2. Value for money) - UNDP Risk Appetite: MINIMAL TO CAUTIOUS | Likelihood: 3 - Moderately likely Impact: 3 - Intermediate Risk level: MODERATE (equates to a risk appetite of EXPLORATORY) | From: 01.Jan.2025 To: 31.Dec.2027 | Project Manager | Risk Treatment 3.1: UNDP will regularly monitor economic indicators and assess potential impacts on the project’s financial and operational aspects. Risk Treatment Owner: Project Manager |
|  |  |  |  |  |  |  |  | Risk Treatment 3.2: Effective communication will be maintained with government stakeholders and engagement with the Project Steering Committee for timely financial planning and adjustments will be done. Risk Treatment Owner: Project Manager |
|  |  |  |  |  |  |  |  | Risk Treatment 3.3: When deemed necessary, development of contingency plans to adapt project activities and budgets in response to economic fluctuations, ensuring the continuity and effectiveness of the project despite economic challenges will be conducted. Risk Treatment Owner: Project Manager |
| 4 | There is a risk that targeted employers for ATP implementation may not be interested in participating the ATP | As a result of lack of awareness about project benefits and incentives and potential anti-refugee sentiments | Which will result in limited achievement of project targets in a timely manner. | 4ORGANIZATIONAL (4.3.Implementation Arrangements) – UNDP Risk Appetite: | Likelihood: 2-Low Likely Impact: 4-Extensive Risk level: Moderate (equates to a risk appetite of EXPLORATORY) | From: 01.Jan.2025 To: 31.Dec.2027 | Project Manager | Risk Treatment 4.1: Conduct continuous monitoring of social sentiments. Implement sensitive and tailored communication and visibility activities to promote understanding and cooperation. Risk Treatment Owner: Project Manager |
|  |  |  |  |  |  |  |  | Risk Treatment 4.2: Disseminate comprehensive project information in terms of especially incentive mechanism and 50% criteria of ethnicity, meaning 50% of the target group will be SuTP/IPSHA and 50% will be Turkish citizens. Risk Treatment Owner: Project Manager |
|  |  |  |  |  |  |  |  | Risk Treatment 4.3: The stakeholders will be aware of their responsibilities in terms of generating interest on the issue through Stakeholder Engagement Plan. Risk Treatment Owner: Project Manager |
| 5 | There is a risk that existing benefits provided by other socioeconomic assistance programmes may discourage targeted SuTP/IPSHA from participating in ATP | As a result of being deprived of alternative benefits | Which will result in low interest in participation in ATP. | 4ORGANIZATIONAL (4.3.Implementation Arrangements) – UNDP Risk Appetite: | Likelihood: 2-Low Likely Impact: 2-Minor Risk level: Low (equates to a risk appetite of EXPLORATORY) | From: 01.Jan.2025 To: 31.Dec.2027 | Project Manager | Risk Treatment 5.1: Implement an effective outreach strategy to boost interest in ATP and training programmes. Regularly gather feedback from target groups to understand their needs and interests, adapting programs accordingly. Foster partnerships with private sector actors to enhance the attractiveness and relevance of these programmes. Design and implement a new programme that addresses the weaknesses of ATP. Risk Treatment Owner: Project Manager |
|  |  |  |  |  |  |  |  | Risk Treatment 5.2: Implement sensitive and tailored communication and visibility activities to promote understanding and cooperation Risk Treatment Owner: Project Manager |
|  |  |  |  |  |  |  |  | Risk Treatment 5.3: Disseminate comprehensive project information in terms of especially incentive mechanism and advantages of ATP such as skills development Risk Treatment Owner: Project Manager |
|  |  |  |  |  |  |  |  | Risk Treatment 5.4: Outreach activities through meeting the employers face-to-face and inform them about the programme, ease their paper work through dedicated teams in the filed. Risk Treatment Owner: Project Manager |
| 6 | There is a risk that ATP participants may become injured or harmed during applied/on-the-job trainings | As a result of lack of awareness on and improper enforcement of occupational health and safety measures | which might result in cancellation/delays in project activities, filing of lawsuits against project partners, and reputational risks for UNDP. | 1. SOCIAL AND ENVIRONMENTAL (1.10. Labor and Working Conditions - UNDP Risk Appetite: CAUTIOUS | Likelihood: 1-Not Likely Impact: 3-Intermediate Risk level: MODERATE (equates to a risk appetite of EXPLORATORY) | From: 01.Jan.2025 To: 31.Dec.2027 | Project Manager | Risk Treatment 6.1: UNDP will ensure incorporation of UNDP SES standards and compliance with national legislation on occupational health and safety in the design and implementation of works contracts by ensuring employers and employees are informed on potential OHS risks and measures with all necessary measures taken to minimize OHS risks at the work places. Risk Treatment Owner: Project Manager |
| 7 | There is a risk that low interest of female participants in ATPs | Due to the biased traditional gender roles | Which may impact in low participation of women to the programme | 1.SOCIAL AND ENVIRONMENTAL 1.3. Human Rights UNDP Risk Appetite: CAUTIOUS | Likelihood: 2-Low Likelihood Impact: 3-Intermediate Risk level: MODERATE (equates to a risk appetite of EXPLORATORY) | From: 01.Jan.2025 To: 31.Dec.2027 | Project Manager | Through recent regulatory changes, such as including the retail sector in ATP eligibility, may help improve gender balance and provide more opportunities for women. To overcome barriers, the project will set targets for female engagement, integrate gender-specific needs into program design, and provide gender-responsive assessments and capacity-building for stakeholders. |

Standard Letter of Agreement for Provision of Services Provided by UNDP

This Annex ensures that information provided through the attachments of “Standard Letter of Agreement Between the United Nations Development Programme and Republic of Türkiye Ministry Of Foreign Affairs to carry out activities when UNDP provides support services to the “Skills Development for Improved Employability ” are contained in the Project Document.

In view of above and in the context of “Standard Letter of Agreement signed on 22 January 2002 between the Turkish Government and the UNDP is ratified by the decision of Council of Ministries No. 2003/6090 dated 22 August 2003”;

i)   The manner and the method of cost recovery by UNDP Country Office in providing the support services is stated in the project document “Heading VII - Multi-year Workplan” in line with UNDP’s Executive Board approved Cost Recovery Policy.

ii)   The results to be achieved and works to be performed by the Implementing Partner and inputs to be provided in the context of “Description of Activities” are available in the Project Document.

iii)  Information concerning “Outputs, Planned Activities, Timeframe, Planned Budget, Schedule of Payments (to be further agreed in the Project Board)” is provided in the Project Document.

iv)  Model UNDP Expenditure Report is presented as below:

Period _______

| EXPECTED CP OUTPUTS ### and indicators including annual targets | PLANNED ACTIVITIES List all activities to be undertaken during the year towards stated outputs | Planned Budget |  | Payments and Expenditures |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Budget Description | Amount | Payments received | Expenditures | Balance |
|  |  | ### Total |  |  |  |  |

UNDP TURKIYE CO

TERMS OF REFERENCE FOR PROJECT BOARD

The Project Board is the group responsible for making, by consensus, management decisions for a development project when guidance is required by the Project Manager (PM), including recommendation for UNDP/Implementing Partner approval of plans and revisions.  The Project Board is chaired by the Senior Executive (Implementing Partners) or co-chaired by UNDP.  It depends on the arrangements agreed with all parties and the Donor in design stage of the Project.  From UNDP side, the Deputy Resident Representative DRR chairs the PB meetings.  Presidency of Republic of Türkiye Strategy and Budget Office (PSB) & Ministry of Foreign Affairs (MFA) are natural members of each Project Board.

In order to ensure UNDP’s ultimate accountability, Project Board decisions should be made in accordance to standards that shall ensure best value for money, fairness, integrity transparency and effective international competition. Reviews by this group are made at designated decision points during the running of the development project, or as necessary when raised by the PM.

Based on the approved annual work plan (AWP), the Project Board may review and approve the annual plans when required and authorizes any major deviation from these agreed quarterly plans. It is the authority that signs off the completion of each annual plan as well as authorizes the start of the next annual plan. It ensures that required resources are committed and arbitrates on any conflicts within the development project or negotiates a solution to any problems between the PM and external bodies. In addition, it approves the appointment and responsibilities of the PM and any delegation of its Project Assurance responsibilities.

The Project Board must meet one time annually at a minimum. It is recommended that the timing of board meetings be agreed upon in advance and corresponds to key project reporting or work planning milestones. This Project Board will meet 6 times annually according to this provisional schedule.

Specific responsibilities of the Project Board:

- Provide overall guidance and direction to the project, ensuring it remains within any specified constraints, and promote gender equality and social inclusion (LNOB) in the project implementation;

- Review project performance based on monitoring, evaluation and reporting, including standard quality assurance checks, progress reports, risk logs, spot checks/audit reports and the combined delivery report;

- Address any high-level project issues as raised by the project manager and project assurance;

- Provide guidance on emerging and/or pressing project risks and agree on possible mitigation and management actions to address specific risks (including ensuring compliance with UNDP’s Social and Environmental Standards, Fraud/corruption, Sexual Exploitation and Abuse and Sexual Harassment);

- Agree or decide on project manager’s tolerances as required, within the parameters set by UNDP (Manage Change in the PPM) and the donor, and provide direction and decisions for exceptional situations when the project manager’s tolerances are exceeded;

- Advise on major and minor amendments to the project within the parameters set by UNDP and the donor;

- Agree or decide on a project suspension or cancellation, if required; (note that for GEF and GCF projects it is UNDP that decides to suspend or cancel and project and the [Project Board or Project Steering Committee] is informed/consulted only).

- Provide high-level direction and recommendations to the project management unit to ensure that the agreed deliverables are produced satisfactorily according to plans.

- Receive and address project level grievance, including overseeing whatever specific compliance and stakeholder response (or grievance) mechanisms have been put in place so that individuals and communities potentially affected by the project have access to effective mechanisms and procedures for raising concerns about the social and environmental performance of the project.

- Engage in the low value grant selection process where there is no Grant Selection Committee, as guided by the Low Value Grants – UNDP Operational Guide.

Additional responsibilities of the Project Board can include, but are not limited to, the following:

- Ensure coordination between the various donors and government-funded projects and programmes;

- Report to relevant inter-ministerial bodies or higher-level oversight bodies;

- Ensure coordination with multiple government agencies and their participation in project activities;

- Track and monitor co-financing for this project;

- Appraise the annual project implementation report, including the quality assessment rating report;

- Ensure commitment of human resources to support project implementation, arbitrating any issues within the project;

- Act as an informal consultation mechanism for stakeholders;

- Approve the Project Inception Report, Mid-term Review and Terminal Evaluation reports and corresponding management responses;

- Review the final project report package during an end-of-project review meeting to discuss lessons learned and opportunities for scaling up;

- Providing guidance or reporting protocols to technical committees or sub-bodies reporting to the Board (if applicable);

Senior Executive (Executing/Implementing Partner)

The Executive is ultimately responsible for the project implementation, supported by the Senior Supplier. The Executive’s role is to ensure that the development project is focused throughout its life cycle on achieving its objectives and delivering outputs that will contribute to higher level outcomes. The Executive must ensure that the project gives value for money, ensuring a cost-conscious approach to the project, balancing the demands of supplier.

Specific Responsibilities (as part of the above responsibilities for the Project Board)

- Ensure that there is a coherent management organisation structure and logical set of plans

- Set tolerances in the AWP and other plans as required for the Project Manager

- Monitor and control the progress of the development project at a strategic level

- Ensure that risks are being tracked and mitigated as effectively as possible

- Brief relevant stakeholders about development project’s progress

- Organise and chair Project Board meetings

The Executive is responsible for overall assurance of the development project as described below.  If the project document warrants it, the Executive may delegate some responsibility for the project assurance functions.

Senior Beneficiary

This role requires representing the interests of the institution who will ultimately benefit from the project. The Senior Beneficiary’s primary function within the Board will be to ensure the realization of project results from the perspective of project beneficiaries. This role will rest with the other institutions (key national governmental and non-governmental agencies, and appropriate local level representatives) represented on the Project Board, who are stakeholders in the project.

Senior Supplier (UNDP)

The Senior Supplier represents the interests of the parties which provide funding and/or technical expertise to the development project. The Senior Supplier’s primary function within the Project Board is to provide guidance regarding the technical feasibility of the development project.  The Senior Supplier role must have the authority to commit or acquire supplier resources required. If necessary, more than one person may be required for this role.

Specific Responsibilities (as part of the above responsibilities for the Project Board)

- Make sure that progress towards the outputs remains consistent from the supplier perspective

- Promote and maintain focus on the expected output(s) from the point of view of supplier management

- Ensure that the supplier resources required for the project are made available

- Contribute supplier opinions on Project Board decisions on whether to implement recommendations on proposed changes

- Arbitrate on, and ensure resolution of, any supplier priority or resource conflicts

Donor

The Donor which is funding the project becomes a natural member of the Project Board.

Presidency of Republic of Türkiye Strategy and Budget Office (SBO) & Ministry of Foreign Affairs

These two offices are natural members of each Project Board.

SBO is the Government coordinating agency of the UNDP in Türkiye and ensures that all UNDP programmes are designed/implemented in line with National priorities.

Ministry of Foreign Affairs gives final approval to all UNDP implemented projects, hence has an overall oversight function under each project.

Project Assurance

The Project Assurance role supports the Project Board by carrying out objective and independent project oversight and monitoring functions. This role ensures appropriate project management milestones are managed and completed.

Project Assurance has to be independent of the Project Manager; therefore, the Project Board cannot delegate any of its assurance responsibilities to the Project Manager. At UNDP Project Assurance function belongs to DRR, Portfolio Manager and M&E and KM Analyst with a clear mandate for oversight and monitoring functions.

Project assurance can also include key staff in Beneficiary institutions that have a stake in the quality execution of the project. However, project assurance function cannot be assumed by Senior Executive since assurance function is to be carried out by an impartial party.

Project Management Unit

A Project Management Unit (PMU) will be established comprising permanent staff including:  Project Manager (PM) and any other support staff appointed for successful completion of this project i.e. Project Associate, Project Finance and Procurement Officer, Portfolio Administrator as well as Project Support Unit. The PMU will assist Senior Executive in performing its role as implementing partner. PMI also includes any technical expert/consultant hired for the successful implementation of the project. PM will be responsible from close surveillance of performance of technical experts if any. The PMU also includes any technical teams in pilot provinces which report directly to PM.

i.Project Manager

The Project Manager has the authority to run the project on a day-to-day basis on behalf of the Implementing Partner within the constraints laid down by the Board. The Project Manager’s prime responsibility is to ensure that the project produces the results specified in the project document, to the required standard of quality and within the specified constraints of time and cost. The PM will be recruited in accordance with UNDP regulations and will be based in Ankara. S/he will report to the relevant UNDP Portfolio Manager. The PM will be responsible for overall project coordination and implementation, consolidation of work plans and project papers, preparation of quarterly progress reports, reporting to the project supervisory bodies, and supervising the work of the project experts and other project staff. The PM will also closely coordinate project activities with relevant Government institutions (if applicable) and hold regular consultations with other project stakeholders and partners. Under the direct supervision of the PM, the Project Associate will be responsible for administrative issues while Project Finance and Procurement Officer will be responsible for financial issues and will get support from UNDPCO administration.

ii.Project Support

Overall responsibilities:  The Project Support role provides administration, management and technical support to the Project Manager as required by the needs of the Project Manager. The provision of any Project Support on a formal basis is optional.  In most projects, project support includes HR, procurement and PSC (Program Service Center) services

Capacity Assessment: Results of capacity assessments of Implementing Partner (including Partner Capacity Assessment Tool (PCAT) and HACT Micro Assessment)

Please see the Guideline “Embedding Digital in Project Design”.

UNDP publishes its project information (indicators, baselines, targets and results) to meet the International Aid Transparency Initiative (IATI) standards.  Make sure that indicators are S.M.A.R.T. (Specific, Measurable, Attainable, Relevant and Time-bound), provide accurate baselines and targets underpinned by reliable evidence and data, and avoid acronyms so that external audience clearly understand the results of the project.

It is recommended that projects use output indicators from the Strategic Plan IRRF, as relevant, in addition to project-specific results indicators. Indicators should be disaggregated by sex or for other targeted groups where relevant.

Optional, if needed

19 Forced eviction is defined here as the permanent or temporary removal against their will of individuals, families or communities from the homes and/or land which they occupy, without the provision of, and access to, appropriate forms of legal or other protection. Forced evictions constitute gross violations of a range of internationally recognized human rights.

Note: revised July 2022 modifying presumption of risk significance from Substantial or higher to Moderate or higher.

The responsibilities of the board in this regard should follow UNDP’s Social and Environmental Standards (SES) as codified in the PPM. It should be noted that while a project board can play a role in addressing or assisting with the compliance and stakeholder response (or grievance) mechanisms put in in place for a given project (as part of their quality assurance and oversight function), this will be in addition to and does not substitute for UNDP’s core responsibility to ensure compliance with the SES throughout the project management cycle as part of UNDP’s Programming Quality Assurance system.