Country: NIGERIA

Initiation Plan

Project Title:	UNDP/UN Joint Team on AIDS support to Grant cycle

Expected UNSDCF/CPD Outcome(s)	:	Outcome 1: Establishing a response mechanism for human rights violations for key populations. 2. Incubating the newly revamped Key Population Secretariat.

Expected CPD Output(s)	:	Collaborate with national stakeholders to establish an emergency response mechanism to address violations and arrests of Key Populations and strengthen the institutional capacity of the newly revamped Key Population Secretariat.

Output 1: Establishing an emergency response mechanism for violations.

OUTPUT 2: Review of Environment for Human Rights and support for the domestication of the Anti-Stigma Act in States

OUTPUT 3: Strengthened Organizational Capacity and Improved Programmatic Capacity

Initiation Plan Start/End Dates:	15 JAN 2025.- 23 DEC 2025.

Programme Period:		______________

Quantum Project Number:	______________

Quantum Output Number:	______________

Gender Marker:			______________

Implementing Partner:                       001981

G

Total resources required           	_________

Total allocated resources:	_________

- Regular			_________

- Other:

  - Donor		_________

  - Donor		_________

  - Government	_________

Unfunded budget:		_________

In-kind Contributions		_________

Brief Description

This document proposes actions to be undertaken by UNDP, and the Joint UN Team on AIDS

(UNJTA) to facilitate and support the implementation of the Global Fund Grant Cycle 7(GC7) grants in Nigeria. The proposed interventions leverage the expertise and experience of UNDP and multiple UN agencies related to convening, normative guidance, technical assistance, advocacy, communication, strategic information, organizational development, knowledge management, and coordinated effort. Thereby streamlining resources and enhancing in-country capacity, at national and sub-national levels.

However, previous grants and the general response continue to suffer delayed implementation, and follow-through on agreed consensus on program plans; leading to a major disconnect between intended program outcomes and actual results.

This proposal seeks to address this gap by bringing together the implementation stakeholders in the GC7 and supporting the government of Nigeria to articulate the programmatic gaps and distil the different workstreams to the capacities and responsibilities of all actors involved in the implementation of the grant.

UNDP and the UNJTA shall be prioritizing in this GC7 which requires its unique strengths in serving. as a catalyst in key problems identified by the Global Fund country team.

Agreed by UNDP

# Purpose and Expected Output

Purpose

Establishing a response mechanism for human rights violations for key populations. To review, document, and learn from the incidence of harassment and arrests by law enforcement, against the KP community and how they have been managed from 2014 to 2024. Includes review of how relevant laws (including Anti-Torture Act, Violence Against Persons Prohibition Act, etc) have or have not been applied as well as the role of secondary actors such as the ACJMC in documented Materials.

Support the accelerated implementation of Gender, Human Rights, and Community system-strengthening activities funded under the grants.

Different stakeholders within the GC7 have been assigned different roles and responsibilities in the national effort to address gender and human rights issues and strengthen community systems to support HTM service delivery. The UNJTA will support the government of Nigeria in convening these stakeholders, articulating common response frameworks that combine their individual efforts, and driving collaborative implementation efforts. Establishing an emergency response mechanism for violations. Frequent arrests of KPs in service delivery and other social contexts threaten service uptake within the community. The responses to these arrests have been incoherent, and duplicative, often complicating engagement with law enforcement and eventual outcomes for the community. In addition, KP communities are not adequately organized to operate in high-risk environments and respond to these issues.

GHR programmes currently led by NACA target law enforcement agents to affirm the rights of KPs, with some efforts now being led by the NHRC. On the field, implementing partners and civil society actors are supporting and mobilizing efforts to respond to violations.

The UNJTA will support the government of Nigeria to catalog all relevant stakeholders and subsequently convene these stakeholders to articulate an emergency response mechanism with clear roles and responsibilities for all actors at national and state levels. It will also help to facilitate engagement between the KP community and collaboration with government agencies to reduce the incidence of human rights violations. Key interventions here will include •

A situation analysis to review the incidence of harassment and arrests by law enforcement, against the KP community and how they have been managed in the last five years. This will include stakeholder mapping of actors on both sides at sub-national, national, and international levels. It will also include the identification and awareness creation of relevant laws and policies on gender, human rights, and justice for KPs.

Based on the findings of the situation analysis, support the Nigerian Ministry of Justice to mobilize stakeholders for the set up a rapid response mechanism and to develop a national rights violation reporting and response system with clear roles and responsibilities for stakeholders and communication channels.

At the primary level, support stakeholders to set up state-level response pathways for dealing with wrongful arrests and prosecution of KP. Considering the global scope of some of the stakeholders, these pathways will reflect state-level coordination, and its integration with national and international frameworks.

An assessment of the legal environment will be conducted and the UNJT will facilitate engagement between the national and state assemblies to domesticate Human Rights laws in each state.

Support the sensitization, training, and mobilization of other secondary-level response actors like the Administration of Criminal Justice Committee (ACJMC), which has the mandate of the Attorney-General of the Federation to strengthen the implementation of the Administration of the Criminal Justice Act (ACJA, 2015) (add reference) by monitoring compliance with the critical. essential, and unifying elements of the Act with focus on pre-trial processes, trial proceedings, case management processes and timeframes, and institutional frameworks for sustainable reform

Expected Output

Incubating the newly revamped KPHRN (Key Population Secretariat)

The newly revamped Key Populations Health Rights Network (KPHRN) is expected to lead engagements with national HTM program stakeholders on behalf of the KP community and several actors have proposed to help them build their organizational capacity and set-up operational systems for accountability. Key deliverables in the network's operational plan have been costed and to be funded through the IHVN grant. Other support channels may exist in the NACA grant, through the National Human Rights Commission and the Network of PLHIV (NEPWHAN)-led interventions.

The UNJTA intends to support the network to map and access available stakeholders' support aligned to their deliverables at national and sub-national levels and help the network leadership achieve their work plan objectives.

Other key Expected outputs include: •	Work with other stakeholders to train network leaders at national and state levels on leadership, advocacy, policy influencing, and strategic engagement with partners and government.

Support network leaders to members in 36+1 states on human rights within Nigeria's legal framework, operating in high-risk environments and engaging with the established response mechanisms for protection from violation and harassment.

Support network leaders to engage with the National Data Situation Room and existing National Emergency and referral pathways like National GBV Gender Based Violence) and the Toll-Free Helpline at the NHRC.

Facilitate the periodic engagement of network leaders and community members with national and state-level stakeholders in the national response mechanisms for the protection of KPs against violation and harassment.

# Management Arrangements

The project will be implemented by UNDP using a direct implementation modality. The UNDP’s Gender Unit will have the overall project management responsibility including planning, implementation, and coordination with relevant stakeholders. The team will leverage partnerships with relevant Government Ministries, Departments, and Agencies as well as the private sector to ensure effective feedback, collaboration, and strong political buy-in. UNDP will collaborate with UNAIDS to drive the implementation of the project, while private-sector partnerships will be leveraged to implement other components.

The Project will be coordinated by the Programme Manager, with technical support from UNDP’s regional Gender team and from program officers across country office units such as the digital and innovation hub, and the programme management and support unit, to ensure a smooth flow of operations and effective communication.

| Title and Function | Function |
| --- | --- |
| Project Manager | to coordinate the day-to-day implementation of the project |
| Project Associate | to provide programme support to Project Manager on the project implementation |
| Admin/ Finance Associate | to initiate payment, process vouchers, etc. for project |
| Procurement Analyst | to support procurement activities of the project |
| Monitoring, Evaluation Analyst | to undertake monitoring visits and organize partners meetings etc.in relation to the project |
| Communication and Visibility Analyst | to prepare, promote and publish communication and visibility activities in electronic and social media highlighting project activities |

# Monitoring

In accordance with UNDP’s programming policies and procedures, the project will be monitored through the following monitoring plan:

Monitoring Plan

| Monitoring Activity | Purpose | Frequency | Expected Action | Partners (if joint) | Cost (if any) |
| --- | --- | --- | --- | --- | --- |
| Track results progress | Progress data against the results indicators in the RRF will be collected and analysed to assess the progress of the project in achieving the agreed outputs. | Quarterly, or in the frequency required for each indicator. | Slower than expected progress will be addressed by project management. |  |  |
| Monitor and Manage Risk | Identify specific risks that may threaten achievement of intended results. Identify and monitor risk management actions using a risk log. This includes monitoring measures and plans that may have been required as per UNDP’s Social and Environmental Standards. Audits will be conducted in accordance with UNDP’s audit policy to manage financial risk. | Quarterly | Risks are identified by project management and actions are taken to manage risk. The risk log is actively maintained to keep track of identified risks and actions taken. |  |  |
| Learn | Knowledge, good practices and lessons will be captured regularly, as well as actively sourced from other projects and partners and integrated back into the project. | At least annually | Relevant lessons are captured by the project team and used to inform management decisions. |  |  |
| Review and Make Course Corrections | Internal review of data and evidence from all monitoring actions to inform decision making. | At least annually | Performance data, risks, lessons and quality will be discussed by the project board and used to make course corrections. |  |  |
| Project Report | A progress report will be presented to the Project Board and key stakeholders, consisting of progress data showing the results achieved against pre-defined annual targets at the output level, the annual project quality rating summary, an updated risk long with mitigation measures, and review reports prepared over the period. | Annually, and at the end of the project (final report) |  |  |  |

# WORK PLAN

Period:

| EXPECTED OUTPUTS And baseline, indicators including annual targets | PLANNED ACTIVITIES List activity results and associated actions | TIMEFRAME |  |  |  |  |  | RESPONSIBLE PARTY | PLANNED BUDGET |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 |  | Funding Source | Budget Description | Amount |
| Output 1 Establishing an emergency response mechanism for violations Baseline: Response Protocol Indicators: Situation analysis of Key Population harassment and arrest to inform programme action developed. Targets: Primary Targets Related CP Enhanced Accountability | Activity 1.1 A situation analysis of KP harassment and arrest to inform programme action including visits to 6 states. |  |  |  |  |  |  | UNDP | UNDP |  | $198,881.00 $46,450.00 |
|  | 1.2 A situation analysis of KP harassment and arrest to inform programme action - Discuss findings and recommendations at the national level. |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | $1,800.00 |
|  | 1.3 A situation analysis of KP harassment and arrest to inform program action - Discuss and share findings and recommendations at the state level. level to discuss and share findings at the state level. |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | $21,750.00 $30,000.00 $40,000.00 $25,281.00 $1,200.00 $32,400.00 |
|  | 1.4 Establishing an emergency response mechanism for violations |  |  |  |  |  |  |  |  |  |  |
|  | 1.5 Training of KP- TA to develop modules. |  |  |  |  |  |  |  |  |  |  |
|  | 1.6 Training of KP- Training of trainers |  |  |  |  |  |  |  |  |  |  |
|  | 1.7 Support mobilization of Administration of Criminal Justice Committee (ACIMC) - Sensitization and training |  |  |  |  |  |  |  |  |  |  |
|  | 1.8 Support mobilization of Administration of Criminal Justice Committee (ACJMC) - Monitoring visits: DSA and travel |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 2 Review of Environment for Human Rights and support for the domestication of the Anti-Stigma Act in States. Baseline: Legal Framework Indicators: Number of laws and policies reviewed and assessed for compliance with human rights standards: Targets: Legal Environment Related CP outcome | Activity 2.1 Complete Legal Environment Assessment 2025 |  |  |  |  |  |  | UNDP | UNDP |  | $155,000.00 $45,000.00 $110,000.00 $162,644.00 $18,800.00 $1,200.00 $142,644.00 |
|  | 2.2 Domestication of critical human rights legislation in 36+ 1 states |  |  |  |  |  |  |  |  |  |  |
|  | Activity 3.1 Train network leaders at national and state level TA Develop training modules. |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 3 Strengthened Organizational Capacity Improved Programmatic Capacity Indicators: Organization Capacity Programme Capacity Organization Targets: Capacity Programmatic Target Related CP outcome: |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.2 Train network leaders at national level - Conduct the training. |  |  |  |  |  |  |  |  |  |  |
|  | 3.3 Position (NOC) in UNDP |  |  |  |  |  |  |  |  |  |  |
| Total programmable Amount including direct cost | $264,922.00 | $55,540.00 |  |  |  |  |  |  |  | $258,540.00 | $519,069.00 |
| Indirect Support Cost 7% | $14,345.00 | $18,102.00 |  |  |  |  |  |  |  | $3,888.00 | $36,335.00 |
| Grand Total | $219,267.00 | $276,709.00 |  |  |  |  |  |  |  | $59,428.00 | $555,404.00 |

Maximum 18 months