Funding Windows Proposal Template

Country/Context*: Multicountry initiative with country components in Kenya, Senegal, Somalia, Mongolia, Sri Lanka and an overall cross-country coordination component

Operational Overview

Proposal Title*:	Promoting Participation Pathways for Human Development - 3P4D

Funding Windows (FWs) resources will support (please check one) *:

☐  An ongoing output within an existing Prodoc

☒  A new output within an existing Prodoc

☐  A new Prodoc (please provide estimated PAC date)

Linked SDG Goal(s) and Target(s):

SDG 16: Peace, Justice and Strong Institutions

- Target 16.7. Ensure responsive, inclusive, participatory and representative decision-making at all levels.

- Target 16.10:  Ensure public access to information and protect fundamental freedoms, in accordance with national legislation and international agreements

SDG 10: Reduced Inequalities

  - Target 10.2: Empower and promote the social, economic, and political inclusion of all, irrespective of age, gender, disability, race, ethnicity, origin, religion, or economic or other status.

SDG 5: Achieve gender equality and empower all women and girls

- Target 5.5. Ensure women’s full and effective participation and equal opportunities for leadership at all levels of decision-making in political, economic and public life.

SDG 17: Partnerships for the Goals

- Target 17.17: Encourage and promote effective public, public-private, and civil society partnerships, building on the experience and resourcing strategies of partnerships.

Linked SP Moonshot(s):

Helping 100 million people to escape multidimensional poverty.

Support 800 million people to participate in elections, many for the first time

Linked Strategic Plan Output*:

2.2. Civic space and access to justice expanded, racism and discrimination addressed, and rule of law, human rights and equity strengthened.

2.3 Responsive governance systems and local governance strengthened for socio economic opportunity, inclusive basic service delivery, community security, and peacebuilding

2.4. Democratic institutions and processes strengthened for an inclusive and open public sphere with expanded public engagement.

3.2 Capacities for conflict prevention and peacebuilding strengthened at regional, national and sub-national level and across borders

6.2. Women’s leadership and participation advanced through implementing affirmative measures, strengthening institutions and civil society, and addressing structural barriers, in order to advance gender equality, including in crisis contexts.

Linked Strategic Plan Indicator*:

2.2.1 Number of countries with institutions, systems, or stakeholders with capacities to support fulfilment of nationally and internationally ratified human rights obligations;

2.2.2 Number of countries that have targeted systems with strengthened capacities to:  a) address discrimination; b) address racism; c) expand civic space;

2.3.2 Number of new measures that improved agility and responsiveness of local governance institutions for: a) basic service delivery; b) prevention;

2.4.5 number of regional, national and sub-national initiatives, policies, and strategies to protect and promote: a) civil society to function in the public sphere and contribute to sustainable development; b) inclusive spaces, mechanisms and capacities for public dialogue; and c) access to reliable information on issues of public concern;

3.2.3 Number of countries that have endorsed a youth, peace and security framework;

6.2.2 Number of partnerships with women-led civil society organizations and other bodies and networks to advance women’s leadership and participation and gender equality.

Linked Flagship target: 5 countries with institutionalized mechanisms for civic engagement and public dialogue, multistakeholder alliances to strengthen civic space and youth participation

Linked CPD Output(s) *:

Linked to Global Programme Governance for People and the Planet (G4PP):

Output 2.1 Support an open public sphere and informed civic engagement

Output 2.2 Promote inclusion in public decision-making

Expected FW funding duration*:	 18 months

Global/CO Project Lead/Focal Point*: Emanuele	Sapienza, Global Lead, Open and Inclusive Public Sphere

Technical Accompaniment and Endorsement

Names and expertise of the experts who have contributed to this proposal:

- Gender*:			Jesus Sanchez Mugica; Joanna Hill

- M&E/RBM*:			Pascal Mukanya Mufuta

- Youth:				Pauline Deneufbourg; Kiri Ginnerup

- Environment/Climate:

- Other Technical expertise*:	Raquel Leandro (RBA); Christella Igiraneza (RBA); Beniam Gebrezghi (RBAP); Martti Karttunen (UNDP RBAS); Dragan Popovic (UNDP Somalia); Maha Abusamra (UNDP Somalia); Jane Serwanga (UNDP Kenya); Zainab Ali (UNDP Kenya); Ibrahima Amadou Niang (UNDP Senegal); Barkhas Losolsuren (UNDP Mongolia); Malin Herwig (UNDP Sri Lanka)

- Global/Regional Hub thematic lead*:	Nirina Kiplagat, Governance and Peacebuilding Coordinator, RSCA

- RB advisor/country desk*:         Doina Ghimici, Bangkok Regional Hub; Francis Mbilima (RBA), Abdullah Alkulaib (RBA)

Department ID: 	29107

Quantum Project Award: 904443

Project/Output ID(s):	01002305

Gender Marker*:	GEN 3

Total resources required*:	2,400,000 USD

Total allocated resources: Click or tap here to enter text

- Regular:	Click or tap here to enter text

- Other:

  - Funding Windows*:	 2,400,000 USD

  - Government:	Click or tap here to enter text

  - Other donor(s):	Click or tap here to enter text

Unfunded budget: 	Click or tap here to enter text

In-kind contributions: 	Click or tap here to enter text

* required fields

Brief Description (200-250 words)

The project “Promoting Participation Pathways for Human Development – 3P4D” under the Civic Space Flagship of the GPCR Funding Window will support five COs – Kenya, Mongolia, Senegal, Somalia, and Sri Lanka – in promoting structural reforms aimed at fostering an enabling environment for people's participation in public life. These reforms will focus on an appropriate combination of the following elements:

- Regulatory frameworks for civic space. Legal and administrative provisions regulating the exercise of the freedoms of expression, association and peaceful assembly, as well as the protection of human rights defenders.

- Citizen participation infrastructure. The concrete mechanisms and processes that allow for people's participation in different aspects of public life, such as procedures enabling citizen input into policymaking.

- Civil society strengthening infrastructure. Mechanisms to strengthen the capacity of civil society organizations, including by strengthening their financial viability either through public investment (e.g. via social innovation funds) or private capital (via innovative financing solutions).

To promote the meaningful and equal participation of all members of society without discrimination, the project will adopt a strong gender equality lens with a focus on women’s participation, leadership and decision-making. The initiative streamlines, across all its outputs, gender equality principles – and it comprises one key output that is fully dedicated to women’s empowerment.

In addition, the project will systematically address the issue of young people’s inclusion in public life – including, where applicable, the Youth, Peace and Security Agenda – with at least one result per country specifically contributing to advancing young people’s leadership and participation in public life, including by providing support to youth-led organizations.

Allocation Proposal

# Development Challenge (1/2 page)

Around the world, governance systems are facing significant levels of strain with growing disenchantment with public institutions and an increasing number and intensity of protest events in all regions. In many cases, people’s expressions of dissatisfaction have been met with repressive responses, often resulting in heightened internal tensions and deepening instability, including at the international level. At the same time, the quality of public debate has been deteriorating.

As articulated by the United-Nations Secretary-General, there is “a growing disconnect between people and the institutions that serve them, with many feeling left behind and no longer confident that the system is working for them, an increase in social movements and protests and an ever-deeper crisis of trust fomented by a loss of shared truth and understanding.” The Secretary General points to “a frayed social contract” at the heart of these challenges, and stresses therefore the need for “a renewed social contract, anchored in human rights”.

To lay the foundations for stronger social contracts, it is crucial to improve the quality of the public sphere, understood as the complex network of spaces in which the social contract is envisioned, negotiated and continuously reevaluated. In particular, it is critical to ensure that the public sphere is open and inclusive, allowing for the meaningful and equal participation of all members of society.

Participation is a human right. People should be able to engage in the public sphere and shape the destiny of their communities and decisions that affect them as citizens not only as voters or holders of elective office but also in a multitude of other ways, such as by “exerting influence through public debate and dialogue with their representatives or through their capacity to organize themselves”.

But participation also has tangible benefits for preventing conflict and sustaining peace in the long term. In fact, a significant amount of evidence shows that countries with more open and inclusive citizen engagement in public life are better equipped to constructively deal with social tensions before they are mobilized into violence.

Yet, worldwide, civic space is shrinking, undermining human rights, democracy, and peace. Virtually all of the indicators measuring civil society organizations’ ability to operate in the Varieties of Democracy dataset have worsened since 2010, and, according to the CIVICUS Monitor, as of 2023, over two thirds of the world population (70.1 percent) live in a country that is characterized by a repressed or closed civic space (the highest percentage since the Monitor was launched). Repressive laws are spreading, with increased restrictions on freedoms to express, participate, assemble and associate. Never have so many political activists and human rights defenders, including many young people, been harassed, threatened, detained or killed for raising their voice and mobilizing their communities.

In the context of the shrinking civic space, coupled with a global backlash against women’s rights and gender equality, women are disproportionately affected, experiencing compounded discrimination, marginalization and additional barriers of participation. Women’s organizations play a pivotal role in advancing gender equality and realizing the 2030 Agenda but face additional and gender-specific obstacles, risks and violations and women human right defenders (WHRDs) are often specifically targeted. Hence, it is necessary to place gender equality and women’s meaningful participation front and center to promote equal participation in the public sphere.

While young people are strikingly creative in sustaining peace and in bridging divides within and between communities, many young people continue to encounter barriers when trying to engage in political and civic activities. The third report of the Secretary General on Youth, Peace and Security (March 2024) recognizes that, while the institutionalization of the agenda has gained notable momentum, with significant advancements at the national, regional and global levels, more remains to be done to fully institutionalize the agenda at all levels, including allocating adequate resources and capacities at all levels. Without conscious efforts to ensure the safe and meaningful participation of young people in decision-making and electoral processes and foster youth civic engagement, the status quo will continue.

While the context-specific challenges and opportunities related to these global challenges vary, each country has been identified to have a political window of opportunity to bring about positive structural change towards a more enabling environment for civic engagement. As such and across the country contexts, there is in one way or another a window of opportunity and political will to strengthen civic space with concrete entry points which would benefit from UNDP’s technical and convening support. For instance, in Kenya, the commencement of The Public Benefits Organization (PBO) Act (of 2013) in May 2024 offers a timely pathway to strengthen civic space for Public Benefit Organizations (PBOs) by offering a robust legal and operational framework, while the recent historic ‘Gen Z protests’ has sparked momentum and demand for strengthening youth inclusion and participation. In Mongolia, two civic space commitments on Ensuring Media Freedom and Freedom of Expression and Support Civil Society and Freedom of Association under their OGP Action Plan have recently been adopted while the August 2024 Independent OGP Action Plan Review also offers concrete entry points and recommendations to pilot new initiatives making legislative or policy decisions participatory, inclusive and human-centric, in particular for women and young people. In Senegal, there is a window of opportunity to support the passing of the Freedom of Information (FOI) Act, which was drafted and submitted to the Supreme Court for validation in recent years as well as to support the ongoing process of developing Senegal’s National Action Plan (NAP) on YPS. In Somalia, the ongoing discussion on the National Transformation Plan as well as the UN Security Council Resolution 2753, from 30 October 2024, referring to the transition of UNSOM to UNTMI, offer concrete and timely entry points to strengthen inclusive civic engagement, strengthening women and young people’s inclusion and participation. Finally, in Sri Lanka, the context of the newly elected Parliament (elections held on November 14, 2024), is a unique and timely opportunity to strengthen more participatory and inclusive civil society spaces at national and subnational levels, enabling young people and women to participate meaningfully in national and subnational decision-making processes and enhancing accountability and trust between communities and public institutions and mechanisms in the country. In each of the country contexts, the detailed workplan will provide more in-depth analysis of these challenges, opportunities and entry points, informing the concrete interventions and activities.

# Strategy (1/2 page)

More equitable and resilient social contracts will require an open and inclusive public sphere which allows for the meaningful participation of all citizens without discrimination. In turn, the creation of genuine opportunities for citizen participation is premised on a number of conditions which include: enabling normative frameworks based on the full recognition of the freedoms of expression, association and peaceful assembly; adequate venues for participation and dialogue (among citizens and between citizens and the state); and a vibrant organized civil society with capacity for economic independence and sustainability.

The project “Promoting Participation Pathways for Human Development – 3P4D” will support five countries – Kenya, Mongolia, Senegal, Somalia and Sri Lanka – in promoting context-appropriate structural reforms aimed at enhancing an enabling environment for people's participation in public life. The specific reforms to be promoted in each country will depend on country-specific opportunities and challenges and may vary significantly. However, each of the project country components will address at least two of the following elements as programming entry points and drivers of change:

  - Regulatory frameworks for civic space: Legal and administrative provisions regulating the exercise of the freedoms of expression, association and peaceful assembly, as well as the protection of human rights defenders.

  - Citizen participation infrastructure: The concrete mechanisms and processes that allow for people's participation in different aspects of public life, such as procedures enabling citizen input into policymaking.

  - Civil society strengthening infrastructure: Mechanisms to strengthen the capacity of civil society organizations, including women and young people’s organizations, also through public investment (e.g. via social innovation funds) or private capital (via innovative financing solutions).

The project will be based on the principles of conflict-sensitivity and Leaving No One Behind, with a strong focus on non-discrimination and ensuring the inclusion of all members of society, including women, young people, persons with disabilities, indigenous peoples, LGBTI+ people, ethnic minorities, migrants, refugees and displaced people.

To promote women’s participation and leadership, the project will include a strong gender equality and women empowerment lens by streamlining, across all its outputs, gender equality principles, as well as comprising one key output that is fully dedicated to the promotion of gender equality. The project will support and provide platforms for women's CSOs to influence policymaking, while strengthening the capacity of women and women's organizations to engage in various aspects of public life and enhance gender-responsive governance. In addition, the project will support citizen participation mechanisms that are gender-responsive by considering women’s specific needs and priorities. Moreover, the project will integrate gender equality into regulatory frameworks to address the backlash against women’s rights and gender equality.

In addition, the project will systematically address the issue of young people’s inclusion and participation in public life – in line, where appropriate, with the Youth, Peace and Security Agenda – with at least one result per country specifically advancing young people’s leadership and participation. The project builds on the recommendation to ensure the safe and meaningful participation of young people and will facilitate and support innovative platforms for youth engagement and intergenerational dialogues, as well as partnership with young individuals and youth organizations.

In addition, the project will seek to maximize the potential of digital solutions as enablers of inclusion and public participation, in particular to support the empowerment and contribution of women and young people to policy making and to amplify women’s and young people’s voices.

To summarize, the basic theory of the change of the project is as follows:

IF

- An enabling overall environment for civic engagement is realized through:

  - Alignment of relevant regulatory frameworks with international human rights standards related to the freedoms of expression, association and peaceful assembly; and/or

  - Establishment of effective and inclusive operational mechanisms for civic engagement and public dialogue;

AND

- Organized civil society's capacity to catalyze collective action for voice and accountability is strengthened, with a special focus on:

  - The capacity of women’s organizations to engage in different aspects of public life; and

  - The capacity of young people and youth-led organizations to engage in different aspects of public life;

THEN

A broader spectrum of voices will be heard in the public sphere, laying the foundation for a more equitable and resilient social contract;

AND THEN, AS A FURTHER RESULT

Societies will be better equipped to constructively deal with social tensions before they are mobilized into violence.

As such, the project will advance key UN global agendas, including the Secretary-General’s “Our Common Agenda” report (September 2021), as well as the “Call to Action for Human Rights” (February 2020) and the “New Agenda for Peace” (July 2023). The project will also support the implementation of recommendations from the third report of the Secretary-General on Youth, Peace and Security (March 2024) as well as commitments from the Pact for the Future, the Global Digital Compact and the Declaration on Future Generations (September 2024).

Further, the project is closely aligned with UNDP’s Strategic Plan 2022-2025 which highlights “an inclusive and open public sphere with expanded public engagement” as one of the key outputs under its Governance Signature Solution (Output 2.4) - particularly indicator 2.4.5 which focuses on: “number of regional, national and sub-national initiatives, policies, and strategies to protect and promote: i) civil society to function in the public sphere and contribute to sustainable development; ii) inclusive spaces, mechanisms and capacities for public dialogue; and iii) access to reliable information on issues of public concern.”

Importantly, the 3P4D Initiative is designed to achieve policy scale-up effects, building on UNDP’s unique ability to leverage local and national action for global impact. Specifically, the multi-country approach will combine national-level context-specific interventions, with exchange of experiences among participating countries and the generations of scalable learning and approaches, which could be later applied by other Country Offices.

For this reason, a dedicated output is included in the project result framework with a focus on providing evidence of what works and what does not and producing insights into the most technically sound and politically viable approaches to nurturing civic space. These insights and lessons learnt will be socialized through appropriate communication strategies to regional and/or global audiences for further positioning and knowledge generation as a strategic (global) objective.

# Results and Partnerships (1.5-2 pages)

Expected Results

At the aggregate level, the project will deliver the following results:

- An enabling environment for civic engagement is promoted through:

  - Alignment of relevant regulatory frameworks with international human rights standards related to the freedoms of expression, association and peaceful assembly; and/or

  - Design and roll-out of relevant operational mechanisms for effective and inclusive civic engagement and public dialogue.

- Mechanisms to strengthen the capacity of civil society organizations, including their economic viability, are established, with a special focus on:

  - Strengthening the capacity of women’s organizations to engage in different aspects of public life; and

  - Strengthening the capacity of young people and youth-led organizations to engage in different aspects of public life.

- Relevant insights and approaches based on country-level interventions are identified and documented in order to inform global knowledge management for policy development.

These changes will be the combined result of country-level interventions summarized below.

Kenya

In Kenya, the project will support the operationalization of the Public Benefits Organization (PBO) Act (2013) by supporting the development of the PBO Act regulations. These regulations will create a structured, transparent, and effective framework to guide both civil society actors and the PBO Regulatory Authority. In addition, the project will support the participation in the operationalization of the Act of PBOs in four counties – Kitui, Kilifi, Kwale and Turkana, while also supporting the registration of women's organizations and youth-led organizations as PBOs in the target counties. Further, the project will provide technical assistance in developing a clear and inclusive normative framework for public engagement at all levels, including gender and youth-responsive components that take into account women’s and young people’s specific needs and priorities. Ongoing efforts leveraging digital solutions to promote youth-led social accountability will be further boosted and national intergenerational dialogue sessions will be facilitated with a focus on strengthening the role of women in public life.

Senegal

In Senegal, the project will support the passing of a Freedom of Information (FOI) Act Bill – which is one of the commitments under Senegal’s Open Government Partnership (OGP) National Action Plan – through advocacy efforts and stakeholder alliances. The advocacy efforts and stakeholder alliances will be informed by women's organizations priorities and needs. This will in turn contribute to enhancing citizen-led accountability and improved public debate. In addition, the project will support the establishment of a CSO platform to provide public oversight of government commitments and to facilitate public participation in policy formulation. The initiative will accompany and facilitate a participatory process aimed at developing a National Action Plan on Youth, Peace and Security as part of its efforts to advance youth leadership towards social cohesion. Further, the project will strengthen the capacity and economic viability of women’s organizations in Casamance through a combination of seed funding and assistance in the design and roll-out of crowdfunding campaigns.

Somalia

In Somalia, the project intends to contribute to inclusive state-building by providing platforms for all groups in society, particularly young people and women to engage in relevant political, peacebuilding and social development processes. The overall approach will be to initiate community spaces (TRACK 3 processes) aiming to (i) contribute to resolving long-standing community conflicts, which are based on climate security and natural resources management and (ii) secure inclusive citizen participation in relevant initiatives underway in Somalia, linked to the development of the National Transformation Plan (NTP) as well as the UNSCR2753 (from 30 October 2024), referring to the transition of UNSOM to UNTMIS. Furthermore, the project will create platforms for dialogue between the legislatures and constitutional review bodies, young people and women, and by supporting the Federal Parliament to develop gender-responsive mechanisms for continuous engagement with citizens in the legislative processes. In addition, the project will build the capacity of women and youth insider mediators to mediate community-level conflicts and to enhance positive perceptions of women and youth as leaders, as well as targeting religious leaders as change agents.

Mongolia

The project will advocate for changes in legislation, procedures, and implementation approaches to make policymaking more inclusive and participatory. With the support of the UNDP Accelerator Lab, it will carry out an ecosystem-level analysis of participation practice assessing what it takes to make legislative and policy decisions more participatory. Selected thematic areas – to be identified in collaboration with youth and women’s civil society organizations – may serve as case studies. This exercise will lead to the identification of potential participation “accelerators” which will be piloted, building capacity among policymakers, CSOs, and professional groups for inclusive policy co-creation. Based on these pilots, the project will formulate relevant recommendations on improving gender- and youth-responsive citizen participation on policymaking in Mongolia. These recommendations will consider and incorporate as appropriate, commitments from the OGP National Action Plan and insights from the August 2024 independent NAP review.

Sri Lanka

In Sri Lanka, the project will build on ongoing efforts within the Sri Lanka parliament and recently concluded UNDP project on strengthening local government capacities for inclusive development with a strong emphasis on connecting engagement spaces at the national and sub-national level. More specifically, the project will strengthen public engagement in the sectoral oversight committees and financial oversight committees of Parliament; and optimize the work of the Parliament Public Outreach and Media departments through the development of tools and a public engagement strategy which will help establish a comprehensive framework for citizen participation in legislative impact assessment processes (pre- and post-enactment). It will also support the strengthening of the Right to Information Commission to enhance public oversight and knowledge on parliamentary oversight functions and access to information. An online citizen engagement platform will also be developed to facilitate dialogue between the parliament and the general public enabling a participatory and consultative environment for public engagement in policymaking. In addition, the project will support the creation of a network of civil society organizations, including through the revival of the Youth Peace and Security Coalitions, to advance dialogue on regulatory framework for civic engagement. Further, the project will develop and strengthen mentorship initiatives and an overarching network of young and seasoned women leaders, creating a supportive ecosystem for women aspiring to enter politics and equip them with skills and resources.

While each country component will deliver results that are relevant and specific to the country, the project is designed to deliver more than the sum of its parts as it will promote knowledge- and experience sharing and collaboration across country components, distill country insights into global knowledge products and leverage country interventions into global partnerships. As such, the 3P4D initiative is expected to provide evidence of what works and what does not, generating insights into the most technically sound and politically viable approaches to nurturing civic space, which can be showcased to regional and/or global audiences for further positioning and knowledge generation as a strategic (global) objective.

Resources Required to Achieve the Expected Results

The series of interventions to be rolled out through this initiative will require seed investments - particularly in the form of technical assistance (through local, regional or global teams); capacity building activities; procurement; advocacy/communications and travel. The introduction of new approaches and tools will require a significant component of technical leadership not only to provide know-how, but to strongly advocate for novel approaches and tools among key partners, and to build trust among key stakeholders. The intent is to ensure both high quality technical inputs, to enable the generation of new knowledge at corporate level, to be showcased in global platforms and to also help the eventual development of ‘products’ that can potentially leverage future resources for further investments and scale-up. In addition, as per the ToC pathway laid out above, investments to strengthen civil society infrastructure and capacities, including economic viability, plays a pivotal role when nurturing civic engagement.

Further, project will build on existing programmes and partnerships, such as the Amkeni Wakenya project in Kenya, the State building and Reconciliation Support Programme and Constitutional Support Programme in Somalia, the SDG 16 Portfolio in Sri Lanka, and the Accelerator Lab in Mongolia and Senegal, to ensure synergies and support the in implementation of activities.

Please also list any additional co-funding sources – existing or expected – in the table below that will complement this FWs allocation.

| Co-Funding source(s) | Amount (USD) | Existing or expected? | Additional information (duration of co-funding, specific thematic area, etc.) |
| --- | --- | --- | --- |
| Somalia - Somalia Joint Fund Statebuilding and Reconciliation Support Programme (SRSP) Support to Democratization and Achieving Social Contract Through Inclusive Constitutional Review Process in Somalia | 474,000 1,391,291 | 114,700 – existing; 359,300 expected 468,620.58 existing; 922,670.40 expected. | The project lasts until 31 December 2027, covering the key state-building and reconciliation processes. The project lasts until 31 December 2026, covering completion of the constitutional review process and harmonization of constitutional framework |
| Kenya Irish Aid ((Empowering Youth Voices) EU/UNODC (Amkeni Wakenya) EU/UNODC (Amkeni Wakenya) Embassy of the Kingdom of the Netherlands (Amkeni Wakenya) | 88,000 100,000 293,500 10,000 | Existing Expected Existing Existing | Funding for youth engagement/ public participation- Ending January 2025 Funding for youth engagement/ public participation-Expected February 2025 Funding for advocacy & operationalization of PBO ACT- Ending 2027 Funding for PBO strategic plan implementation- Ending 2026 |
| Mongolia KOICA (Gender equality and women's political empowerment project) EU (Change of agents: youth and media for responsible business practices) | 10,000 5,000 | Expected Existing | Engagement of women from sub-national/local assemblies in late 2025 and 2026 Engagement of young people from sub-national/local areas in 2025 and 2026 |

Partnerships

The project will leverage partnerships with a wide spectrum of governance institutions and civil society platforms that are key to the realization of an open and inclusive public sphere. Here, UNDP will tap into long-standing relationships of trust with public authorities and extensive partnerships with local civil society organizations, including women’s organizations and women-led and youth-led civil society organizations and leverage its convening capacity at the local level.

On the global level, the project will be able to leverage global partnerships with members of the UN Task Team on Civic Space (especially OHCHR, but also UN Women and UNESCO) as well as members of the OECD DAC Community of Practice on Civil Society and other partners and networks in the area of democratic innovation (including for example the Open Government Partnership) and youth participation (including for instance the Global Coalition on Youth, Peace and Security) to support COs in the design and implementation of impactful interventions and extracting and building on the lessons learned throughout the project.

Similarly, the project will leverage partnerships and joint and inter-agency work with other UN agencies, strengthening coherence and coordination on the ground. These concrete partnerships and joint activities will build on the already existing work and partnerships on the country level, including where relevant with UN Women, OHCHR (and Human Rights officers where appropriate), UNESCO, and other UN partners. For instance, UNDP is working together with UNFPA and UN Women to support the process on the NAP on YPS in Senegal, while the support to the transformative processes underway in Somalia is indeed a joint UN one.

On the national level, the project will also foster collaboration with key national and sub-national partners – such as the Federal Government of Somalia (FGS) and Federal Member States’ (FMS) governments and the Federal Parliament as well as local authorities in Somalia, the parliament and the National Human Rights Commission and the Ministry of Justice and Home Affairs in Mongolia, the Youth Ministry, local governments authorities and the parliament in Senegal, the Parliament and local government authorities in Sri Lanka and National and County Governments and relevant State Departments in Kenya. Crucially, the project will also foster co-creation and partnerships with civil society, prioritizing partnerships with women- and youth-led organizations, networks and coalitions, across all five country offices. As such the project will promote not only women’s and young people’s participation but also their leadership by prioritizing partnerships with youth-led and women’s and women-led organizations and strengthening their capacities.

Communications and Advocacy

Using the learning and communications component in this proposal, the project aims to develop a series of communication pieces showcasing the result of the interventions. The pieces will highlight lessons learned and best practices, discuss challenges, and explore future opportunities for further replication and scale up. A special focus will be given to gender- and youth-related results, and in line with the project’s objectives on women’s and young people’s participation and inclusion, women and young people will be also involved in the collection of data and stock taking of lessons learnt from the five countries.

The initiative will leverage social media platforms to share compelling stories, infographics, videos, and updates on progress and impact.

The project will ensure recognition and visibility for the Funding Window (and its donors) during events, in communication pieces, and in knowledge products, adhering to the visibility guidance of the Funding Window Management Team.

To this end, resources for Monitoring, Evaluation and Learning will be leveraged to support the documentation of lessons learned, experiences and human-interest stories– which will feature in communications and advocacy campaigns.

Risks and Assumptions

Specify the key risks that can threaten achieving results and describe how risks will be mitigated.

While the previously described theory of change outlines the programming entry points, the concrete programme activities in each country will necessarily be informed by context-specific analyses of barriers and enablers, allowing for flexibility and agility. Of course, there are a variety of other factors, with likelihood and risks levels varying from country to country, in country and beyond that may affect the overall outcomes, which will be addressed through careful analysis and adaptive approaches to programme management.

| Risk type | Risk description | Risk assessment (Impact, Likelihood & Risk Level) | Mitigation measures |
| --- | --- | --- | --- |
| Political risk | Changing political environments and national priorities create delays, undermine, or compromise intended activities. The originally identified window of opportunity closes due to changes in political circumstances. | Impact: High Likelihood: Medium Risk Level: Medium | - The multistakeholder alliances to be convened by the project are designed to maximize the resilience of the initiatives by securing support across sectors and, where possible, political orientations. - Regular review and analysis of the operating environment and development of contingency plans - Create a flexible, quality programme framework that will allow for adaptive implementation at country level. - Maintain constant inclusive dialogue and exchanges on initiative and specific required country support. - Realignment of activities to ensure they are fit-for-purpose to the situation on the ground |
| Sustainability risk | Efforts to mobilize resources for the implementation of the roadmap beyond the project do not succeed. | Impact: Moderate Likelihood: Moderate Risk level: Medium | - The project will be designed to deliver at least a “minimum viable product” – i.e. a transformation that would represent a meaningful and self-sustaining step forward even in the absence of further follow-up. |
| Protection risk | Civil society actors are exposed to intimidation or reprisals as a result of their involvement in the project. | Impact: High Likelihood: Medium Risk level: Medium | - Appropriate preventive and, if needed, remedial action is taken in line with the recommendations of the SG’s report “Cooperation with the United Nations, its representatives and mechanisms in the field of human rights”. - Ensure specific protection needs, including those in relation to digital threats, for women. - Ensure specific protection needs, including those in relation to digital threats, for young people. - Ensure specific protection for groups facing cultural and historical exclusion and stigma e.g. PwD, LGBTI+ groups. - Ensure that all project staff are aware of and responsible for protection needs, including those related to digital threats and data security, and utilize staff and participants’ knowledge of the security situation. |
| Implementation | Resistance to change ingrained traditional roles and norms may limit the scope of impact. | Impact: High Likelihood: Medium Risk Level: Medium | - Identify and work with trusted women’s organizations and women-led local organizations/networks and build synergies with existing women’s empowerment projects. - Build on analytical work led by women economists and researchers to ensure evidence-based approaches and impact. - Ensure safe and gender-sensitive spaces for women’s participation. - Move beyond gender mainstreaming by prioritizing women’s leadership. - Tailor activities and approaches to different contexts and target groups, ensure synergies with ongoing efforts by UNDP and others, and adjust ambition levels accordingly. |
| Implementation | Deep-rooted socio-cultural barriers limit ability to meaningfully include young people in the project. | Impact: High Likelihood: Medium Risk level: Medium | - The project will focus on facilitating intergenerational dialogue, emphasizing mutual understanding, knowledge sharing and best practices for meaningful youth engagement and civic participation. - Ensure safe and gender-sensitive spaces for young people’s inclusion and participation. - Tailor activities and approaches to different contexts, ensure synergies with ongoing efforts by UNDP and others, and adjust ambition levels accordingly. - Identify and work with trusted local organizations that have existing relationships with youth. |
| Project design | Lack of interest and/or capacity at country level to engage in co-creation and implementation. | Impact: High Likelihood: Low Risk Level: Medium | - Incubate interest from select country level partners by engaging them in the design of implementation of activities. - Provide technical accompaniment to UNDP Country Offices and national partners to enable them to be active participants in the incubation of ideas and approaches. - Showcase UNDP tools such as iParticipate during events including institutions and government officials. |
| Reputational | Corruption or fraud by programme implementing partners | Impact: Moderate Likelihood: Moderate Risk Level: Medium | - Use of due diligence in partner selection and apply UNDP’s own procurement Standard Operating Procedures and protocols. - Ensure that implementing partners are informed of UNDP policies related to fraud and corruption. |

Assumptions

- No significant deterioration of the security situation in the pilot countries will take place during the period of implementation.

- Activities will not need to be reprioritized or postponed as a result of major natural disasters.

- The five countries will not face a major political crisis that disrupts the ability of UNDP/UN to smoothly operate in the country.

- No major public health crisis will disrupt the ability of field personnel and CO staff to travel and to engage with relevant stakeholders in the countries.

Stakeholder and Beneficiary Engagement

As the major objectives of this initiative is to contribute to a more enabling environment for people's participation in public life, a participatory approach with citizens and organized civil society as well as partnerships with public authorities is central. On the civil society side, women and young people are among the key stakeholders, not only as beneficiaries but also as partners in the implementation and monitoring of the project. Further, a multilevel governance approach will be adopted in the project, recognizing the importance of the localization agenda and the role of subnational governments as potential leaders in promoting civic engagement and as laboratories of democratic innovation.

Primary stakeholders include:

Civil society organizations. The initiative will engage directly with civil society organizations, ensuring a co-creation approach, with a particular focus on partnerships with women- and youth-led organizations.

- Youth and youth-led organizations: Partnerships with young individuals and youth organizations to promote young people’s participation and implementation of the Youth, Peace and Security (YPS) agenda will be a key priority for the project.

- Women’s organizations: Similarly, partnerships with women's organizations will be key for the project across all country components, with additional standalone activities focusing on women’s leadership and participation.

Governance institutions. UNDP through its existing governance programming at both national and regional levels has pre-existing relationships with governance institutions at national and sub-national levels in beneficiary countries. Engagement of these organizations is expected to take place on an as-needed basis building on existing programmes of engagement and the local context of intervention. This approach reduces the risk of gaps or overlaps in engagement at this level. In addition, the project will also leverage partnerships and linkages with regional and other across-country organizations where appropriate.

Academic and research organizations. The implementation of the project will also call for engagement with academic and research organizations that can support capacity building and knowledge generation in various areas under this initiative. The project will leverage global partnerships with researchers and practitioners in the area of democratic innovation (e.g. through the OECD Innovative Citizen Participation Network) to support COs in the design and implementation of impactful interventions, while also partnering with independent think tanks at the local level.

South-South and Triangular Cooperation (SSC/TrC)

In line with UNDP’s corporate strategy on South-South Cooperation and Triangular Cooperation, this project will promote SSC/TrC to facilitate the exchange of knowledge, expertise, and best practices between countries which will be documented and disseminated as parts of the monitoring and learning and communications efforts, e.g. through knowledge products, Community of Practice webinars, and reports as well as through social media posts. Owing to the implementation of the project in five different country offices, and the global oversight role, the exchange of experiences across countries (including countries not included in the project) is uniquely positioned to facilitate South-South dialogue and cooperation on the promotion of open and inclusive governance arrangements.

Sustainability and Scaling Up

The project will be encouraging COs to take a portfolio approach building on specific guidance provided in the document “Promoting an Open and Inclusive Public Sphere. Programmatic Options” (ref. sections 2.1 “Priority areas for programming: A menu of options” and “Priority Area 1: Nurturing Spaces for Civic Engagement”. The modular approach will ensure both the delivery of results within the 2024-25 framework and the country-level scalability of the initiative.

While the specific context of each country varies significantly, they have all been identified to have a window of opportunity to bring about positive structural change towards a more enabling environment for civic engagement. The underlying Theory of Change outlines a high-level pathway that goes beyond the 18-month duration of this initiative - as it is built on the premise that the proof of concept, if successful, can carry positive effects beyond the end of the project. Additionally, the project will document and disseminate knowledge and best practices to sustain its impact and inform UNDP’s efforts in nurturing civic spaces.

This approach is expected to create further opportunities for collaboration with development partners and donors focused on promoting an open and inclusive public sphere, governance and capacity building, including related to women and youth, potentially attracting additional resources. However, as noted in the risk section above, the project will be designed to deliver at least a “minimum viable product” – i.e. a transformation that would represent a meaningful and self-sustaining step forward even in the absence of further follow-up.

Digitalization will be a key component and enabler of the project in terms of: 1) how digital solutions can boost citizen participation but also; 2) how inclusive citizen participation can contribute to a more effective and legitimate governance of digitalization. Internal partnerships – for instance with the Chief Digital Office – as well as external ones – with both civil society actors and the private sector – will contribute to strengthening the digital dimension of the project.

# Management and Governance Arrangements, and Accountability (1/2 page)

**Implementation of Funding Windows resources must adhere to the established corporate policies and procedures as prescribed in the POPP. The UNDP Resident Representative will be held accountable for the effective and prudent use of the funds allocated to your office, including following the Social and Environmental Screening Procedure.**

Funds under this project will be sent to the five Country Offices implementing activities under this initiative at the national level. Each Country Office will be responsible for managing the results and the financial resources that they receive.  Funds for global technical accompaniment will be sent to the Global Project Governance for People and Planet (G4PP) to support overall substantive oversight of the project and aggregated results reporting. A new output will be created under the Global Project dedicated to this initiative.

The project is implemented through a Direct Implementation Modality (DIM). Under DIM, UNDP bears full responsibility and accountability to manage the Project, achieve project outputs and ensure the efficient use of funds. UNDP is accountable to funding partners for disbursement of funds and achievement of the Project objective, according to approved work plans. UNDP is responsible for the following functions: (i) coordinating activities to ensure the delivery of agreed outputs; (ii) certifying expenditures in line with approved budgets and work-plans; (iii) facilitating, monitoring and reporting on the procurement of inputs and delivery of outputs; (iv) approval of Terms of Reference for consultants and tender documents for sub-contracted inputs; and (vi) reporting on project delivery and impact.

Financial audits of DIM projects are conducted by UNDP’s Office of Audit and Investigation (OAI) as part of the 2008 Accountability Framework and Oversight Policy. The audit schedule is issued by OAI each fiscal year and completed audits statements are posted to www.undp.org/accountability following completion.

This project operates as a decentralized project, leveraging UNDP’s existing global network of regional and country offices. Project management will be decentralized among the country offices implementing activities. Appropriate arrangements will be made at the country level for effective oversight and implementation of the initiative. The Country Office will appoint a project Focal Point for streamlined communication and collaboration with the global team.

The Governance team in BPPS will manage the funds for technical accompaniment, strategic knowledge management and high-level communications and advocacy events allocated to G4PP. Such strategic interventions will be managed through a consultative process with the COs – which will benefit from greater economies of scale (avoiding duplicative and overlapping efforts), and will help to strengthen the technical interface between HQs-ROs-COs (‘working as one’) while leveraging a decentralized delivery model.

The Governance team in BPPS will provide substantive oversight of the project and support with the reporting of aggregated results. Consultants and/or staff supporting implementation of the Project shall be variously situated, making use of UNDP cost-recovery modalities where necessary. This arrangement minimizes operational (platform) costs and facilitates flexibility and best value for money.

Management arrangements and oversight mechanisms are established to foster alignment with national processes while ensuring accountability for activities, results and the use of resources. The Country Office is responsible for the overall financial and administrative management of the Project. In addition, each CO will count on the necessary governance, gender, youth, digitalization, inclusion, or other necessary expertise for implementing the activities and ensure the technical soundness of deliverables associated with the implementation. The resources will also be used for contracting and procuring goods and services required for the implementation of the activities. CO will leverage existing programming, partnerships, and resources at the national, regional and global levels to advance the results envisioned in this proposal.

Technical accompaniment will be provided to CO to support the implementation of the activities as per the workplan. Strategic communication, learning and advocacy activities will be managed globally to capitalize on synergies and economies of scale (e.g. communication products and events that benefit visibility and learning for all five pilot countries) and to facilitate positioning of the multi-country initiative in global platforms.

Regular meetings will be organized on a periodic basis between CO colleagues involved in project implementation, regional colleagues and the global team, with the goal of jointly reviewing progress and emerging challenges, facilitating connections between ongoing work at country level and work in other countries (within or outside 3P4D), and documenting learning as the project responds to evolving circumstances.

Implementation of Funding Windows resources will adhere to the established corporate policies and procedures as prescribed in the POPP. For the management of country-level activities, the COs will be held accountable for the effective and prudent use of the funds allocated to the respective office, including following the Social and Environmental Screening Procedures.

# Monitoring and Learning (1/2 page)

Monitoring

This flagship initiative will be monitored using a two-tier approach: at the country level, designated CO focal points will be responsible to ensure relevant monitoring activities are implemented in a timely manner, and that accompanying progress and final reports are completed as per planned schedule; at the global level, the BPPS/Open and Inclusive Public Sphere team will be monitoring the project to inform corporate knowledge management and to ensure the achievement of high level impact.

At the inception of the project, Country Offices will develop an appropriately detailed workplan in consultation with the regional and global team, based on the intervention areas and expected results highlighted in this project document. The workplan will include relevant measures of success for the country intervention, together with the corresponding baseline information and plans to monitor corresponding indicators (M&E plan). The workplan will be reviewed and updated, if needed, after 6 and 12 months. Regular meetings (“pulse checks”) will be held with an agreed periodicity with the participation of relevant CO, regional and global colleagues to discuss progress, emerging insights, technical support needs and partnership opportunities.

| Monitoring Activity | Frequency/Timeline | Responsible Party | Notes |
| --- | --- | --- | --- |
| Workplan | At project inception. To be revised (if needed) after 6 and 12 months | COs with regional and global team support | The workplan will include relevant measures of success together with the corresponding baseline information and plans to monitor corresponding indicators. |
| Six-monthly ‘two-pager’ reports | At the start of quarter 3 quarter 5 of implementation | COs | Such reports will highlight key progress achieved to date – and potentially showcase emerging lessons learned or results that can be communicated/ disseminated through various means, including through social media platforms and in communications with FW contributing partners |
| FW Annual Reports | January 2026 and January 2027 | Global team in consultation with regional teams and with inputs from COs | As per FW requirements. The reports will be reviewed and aggregated by the BPPS/Governance/Open and Inclusive Public Sphere, with a view to demonstrating high level impact of the initiative. |
| Quantum Logs (Risks, Issues), Project Quality Assurance As per POPP requirements | As per POPP requirements | Global team, COs |  |
| ROAR/Results Oriented Annual Report (as per POPP requirements) | Annually | Global team, COs |  |
| Updates to UNDP Transparency Dashboard As per standard corporate practice | Annually | Global team, COs |  |
| Pulse checks | Periodicity to be agreed (not less than once a quarter) | CO, regional and global team | Periodic Pulse Checks to discuss progress, emerging insights, technical support needs and partnership opportunities. Relevant experts from BPPS, Crisis Bureaux, DCO and other relevant UNDP teams will be brought on board needed Addition ad hoc calls will be arranged on a need basis. |

**Annual reports for the FWs are collected from country offices in January for the previous calendar year. All country offices will need to respond to a set of questions to help the FWs aggregate results across all allocations and create narrative around the impact of our investments for our partners. Continuous monitoring throughout the year – including following up on completed activities to gather evidence and assess their lasting impact – will make the process of annual reporting smoother and more efficient. **

Learning

The project will contribute to UNDP learning by providing evidence of what works and what does not, generating insights into the most technically sound and politically viable approaches to nurturing civic space. The documentation of these insights (through technical accompaniment) will contribute to global scalability as the insights from project implementation will be leveraged to promote regional learning and strengthen regional programming, including through collaboration with relevant regional and subregional institutions. In addition, the project will also promote peer-to-peer learning and the exchange of experiences between COs. To further facilitate learning and collaboration, the project will organize appropriate discussion spaces with partners, providing opportunities for sharing lessons, discussing challenges, and exploring future opportunities for further replication and scale up.

Distribution of the FWs allocations

| Country/Region/Global | Dept ID | Amount (USD) |
| --- | --- | --- |
| Senegal | B0370 | 436,098 |
| Kenya | B0342 | 436,098 |
| Somalia | B0468 | 436,098 |
| Sri Lanka | B0434 | 436,098 |
| Mongolia | B0418 | 436,098 |
| BPPS (incl. TA) | B0291 | 219,510 |
| Total |  | 2,400,000 |

# WORK PLAN

If resources will be used beyond one calendar year, please use the resource framework in the project document template.

**According to the UNDP Gender Equality Strategy 2022-2025 global, regional and country office programmes and projects will identify, at their design stage, at least one stand-alone gender-specific component (GEN3 output of project document) with at least of 15 percent of the total resources of the initiative allocated to this component. For more information, please refer to the updated Funding Windows Gender Marker Guidance Note.**

Period January 2025-August 2026

| EXPECTED OUTPUTS And indicators, baselines, and annual targets |  |  | PLANNED ACTIVITIES List activity and associated actions |  |  | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | RESPONSIBLE PARTY | Funding source | Specific Budget Description 13 | Amount (USD) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Output 1. An enabling environment for civic engagement is promoted, through: 1.1 Alignment of relevant regulatory frameworks with international human rights standards related to the freedoms of expression, association and peaceful assembly; 1.2 Design and roll-out of relevant operational mechanisms for effective and inclusive civic engagement and public dialogue. Indicator 1.1 (IRRF 2.4.5) number of regional, national and sub-national initiatives, policies, and strategies to protect and promote: a) civil society to function in the public sphere and contribute to sustainable development; b) inclusive spaces, mechanisms and capacities for public dialogue; and c) access to reliable information on issues of public concern Baseline: 0 Target: 5 Indicator 1.2 (IRRF 2.2.1) Number of countries with institutions, systems, or stakeholders with capacities to support fulfilment of nationally and internationally ratified human rights obligations: Baseline: 0 Target: 5 Indicator 1.3 (IRRF 2.2.2) Number of countries that have targeted systems with strengthened capacities to: a) address discrimination against women ; b) address racism; c) expand civic space Baseline: 0 Target: 5 Indicator 1.4 (IRRF 2.3.2) Number of new measures that improved agility and responsiveness of local governance institutions for: a) basic service delivery; b) prevention Baseline: 0 Target: 5 |  |  | Activity 1.1.1 Kenya. Provide support to the process of developing the PBO Act regulations and participation of PBOs in the 4 target counties – Turkana, Kitui, Kilifi, and Kwale Actions: - Development of simplified version of the PBO Act, the PBO Act regulations and IEC materials - Support the establishment of self-regulatory frameworks for women and youth focused PBOs in the four target counties Activity 1.1.2 Kenya: Support civic engagement framework and civic engagement platforms Actions - Assistance to developing clear, inclusive guidelines and legislative framework for public engagement and inclusion and participation of women and youth at all government levels - Support timely access to information and civic education on proposed amendments/ guidelines on public participation framework by duty bearers and right holders, with special focus on women and young people. |  |  | A1, A2,A3,A5 | A1-A4 | A1-A4 | A1-A5 | A1-A5 | A1-A5 | UNDP Kenya | FW | Consultancy(ies) Workshops and training events Grants Workshops, trainings and advocacy events: Workshops and training events: Technical Expertise (consultancies/NPSAS/IPSAS): Consultancy Technical Expertise (consultancies, NPSAS, IPSAS): Workshops, trainings, advocacy events: Consultancies Procurement supplies Travel: | 12,500 38,769 40,000 95,846 40,000 4,000 4,000 22,000 43,000 25,000 20,000 5,000 |
|  |  |  | Activity 1.2.1 Senegal. Support the passing of a Freedom of Information (FOI) Act Actions - Baseline study on the state of Freedom of Information bill and how it aligns with AU model law, lessons learnt, limitations and recommendations – with a focus on women and youth. - Support the establishment of a Civil Society – Parliament working group on the Freedom of Information Bill, with a special focus on inclusion of women and youth CSOs. - Advocacy campaign (online and offline) for the passing of the Freedom of Information Act in collaboration with OGP CSO Senegal group - Building a media alliance for freedom of information which will support advocacy efforts of civil society, with special focus on women and young journalists and gender and youth sensitive reporting. Activity 1.2.2. Senegal. Support citizen-led public oversight and participation, incl. for women and youth Actions. - Conduct baseline study and mapping on the state of citizens’ – including women and youth - participation in transparency and accountability processes in Senegal. - Establish a CSO platform - Develop indicators to monitor budgetary processes, transparency and accountability in Senegal - Adopt UNDP iParticipate tool for public oversight in Senegal, ensuring young people’s and women’s participation - Produce public oversight monitoring reports - 6. Organize multistakeholder dialogue platforms between CSOs, media and government official around release of monitoring reports. |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Activity 1.3.1 Somalia. Create a platform for engagement between the legislatures and constitutional review bodies and citizens, incl. Women and youth Actions: - Organize consultations on the constitutional review process engaging youth and women and other disadvantaged groups - Support Federal Parliament to develop platforms for continuous engagement with citizens, incl. women and youth, in the legislative processes |  |  |  |  |  |  |  |  |  |  | Technical Expertise (NPSA/IUNV/FTA): Workshops, trainings and advocacy events: Low value grants Travel Monitoring and learning: Communications | 71,829.4 64,222.29 10,000 2,297.5 7,568 3000 |
|  |  |  | Activity 1.4.1 Sri Lanka. Support citizen-led accountability and transparency in policy- and law making and reporting processes Actions: - Strengthen public engagement in the sectoral oversight committees and financial oversight committees of the Parliament including the gender responsive capacitating of youth representatives of the committees. - Development of an Online Citizen Engagement Platform to provide public input from citizens, incl. women and youth, to committees and works of the Parliament. - Optimize the work of the Parliament Public Outreach and Media departments through the development of a public engagement strategy, cantered on the open parliament concept, with a focus on engaging youth. - Support establishment of a comprehensive legislative impact assessment process, whilst enabling public consultations in law, policy-making, and related discussions and reviews encompassing full pre- and post-enactment scrutiny of legislation. |  |  |  |  |  |  |  |  |  |  | Consultancies Technical Expertise (NPSA/IUNV/FTA) Travel: Workshops, trainings and advocacy events Procurement supplies: Monitoring and learning: Communications | : 124,000 18,826 6,642 40,000 14,000 7,000 3000 |
|  |  |  | Activity 1.5.1 Mongolia. Identify and pilot participation ‘accelerators’ and provide recommendations on improving gender- and youth responsive citizen participation in policymaking Actions: - Ecosystem-level analysis of participation practice in Mongolia carried out in collaboration with youth and women’s civil society organizations and other partners - Situational analyses and studies - Potential participation “accelerators” identified and piloted - Pilots for legislative, procedural and implementations changes - Policy recommendations on improving gender- and youth responsive citizen participation in policy making in Mongolia formulated |  |  |  |  |  |  |  |  |  |  | Technical Expertise (NPSA/IUNV/FTA) Consultancies Workshops, trainings and advocacy events | 40,000 60,000 102,000 |
|  |  |  | Subtotal Output 1 |  |  |  |  |  |  |  |  |  |  |  | 924,500.19 |
| Output 2. The capacity of civil society to engage in different aspects of public life is strengthened, with a special focus on: 2.1 Strengthening the capacity of women’s organizations to engage in different aspects of public life; 2.2 Strengthening the capacity of young people and youth-led organizations to engage in different aspects of public life. Indicator 2.1. (IRRF 6.2.2) Number of partnerships with women-led civil society organizations and other bodies and networks to advance women’s leadership and participation and gender equality Baseline: 0 Target: 5 Indicator 2.2. (IRRF 3.2.3) Number of countries that have endorsed a youth, peace and security framework Baseline: 0 Target: 1 Related Global Programme Output (G4PP): Gender Marker: 3 |  |  | Activity 2.1.1 Kenya. Strengthen capacity towards sustainability for women and youth focused organizations and provide platforms for engagement Actions: - Facilitate national intergenerational dialogue sessions to strengthen the role of women in public participation - Co-creation and application of an interactive digital platform for youth and citizens in general to engage with government proposals, track development commitments, monitor and evaluate youth engagement levels and the platform's impact on transparency and accountability in partnership with the UNDP YSB. - Enhance capacity towards sustainability for women and youth focused organizations in the four target counties - Capacity-building support to youth-focused organisations towards registration as PBOs and ensuring compliance with the PBO Act Provisions - Capacity-building support to women-focused organisations towards registration as PBOs and ensuring compliance with the PBO Act Provisions |  |  |  |  |  |  |  |  |  |  | Workshops, trainings and advocacy events Consultancies Grants Monitoring and learning: Communications Workshops, trainings, and advocacy events: Workshops, trainings and advocacy events: | 35,715 49,323 50,000 4,568 3,000 19,385 30,462 . |
|  |  |  | Activity 2.2.1 Senegal. Women-led CSOs are trained to launch crowdfunding campaigns and equipped with social entrepreneurship skills and supported with seed funding Actions: - Crowdfunding academies for CSOs led by women to develop a communication strategy, visual and textual elements, and building partners network which will enable them to launch their crowdfunding campaign. - Develop a social entrepreneurship toolkit and conduct a training of trainers for women CSO leaders. - Provide seed funding to selected women CSOs to start social entrepreneurship projects Activity 2.2.2 Senegal. Support the process of developing a NAP on YPS - Youth responsive conflict analysis and mapping of key actors - Training of youth community leaders in Southern Senegal on Youth, Peace and Security - Establishment of a Drafting Committee for the YPS national action plan (NAP) and the ToRs and institutional design for the YPS secretariat to be hosted by the Ministry of Youth - Multi stakeholders’ consultations on the draft YPS NAP - Launch of the Senegal YPS NAP |  |  |  |  |  |  |  |  |  |  | Workshops, trainings. Advocacy events Consultancies Grants: Technical Expertise (consultancies, NPSAS, IPSAS) Workshops, trainings, advocacy events: Monitoring and learning: Communication | 36,000 11,568 60,000 23,000 62,000 20,000 4,000 |
|  |  |  | Activity 2.3.1 Somalia. Ensure and expand space for participation of women and youth in political, decision making and societal processes at the community and higher levels Actions: - Organize inclusive consultations on the constitutional review process and other state building matters and ensure women and youth participation and engagement - Initiate low value grants scheme engaging women and youth organizations and networks to advocate for the inclusion and engagement of women and youth in gender responsive state building processes Activity 2.3.2. Somalia. Building capacity of women and youth inside mediators to mediate conflicts at the community level Actions: - Train and empower youth and women insider mediators - Initiate community reconciliation process addressing longstanding grievances in regions, identified in collaboration with the government. - Organize gender and youth- responsive peacebuilding activities focusing on youth and women’s perspectives |  |  |  |  |  |  |  |  |  |  | Workshops, trainings and advocacy events Low value grants: Travel: Technical expertise (NPSAS/IUNV/FTA): Workshops, trainings, advocacy events: Low value grants: Travel: | 50,228.11 20,000 2,016.83 76,874.4 50,031.12 20,000 1500 |
|  |  |  | Activity 2.4.1. Sri Lanka. Strengthening civil society, incl. women and youth capacities to engage in national and sub-national policy and decision –making processes, and to advocate for institutional accountability and transparency Actions: - Support the creation of a civil society consortium at the subnational level to advocate for and inform the national budget, including the location of the SDG budget analysis, policies, and legislation reflecting community needs, incl. for women and youth. - Strengthen civil society’s, incl. women and youth, capacities for monitoring the implementation of the citizen’s charter, environmental impact assessments (EIA) and the national action plan on anti-corruption and providing periodic feedback. Action 2.4.2 Sri Lanka. Promote mentorship and peer-to-peer support amongst emerging and seasoned women leaders, including overarching platform to sustain their participation in politics - Mentorship activities with the Women Parliamentarians Caucus and the Women Councilors Network - Capacity building activities for younger women, building on analytical work led by women economists and researchers consortium - Launch ecosystem/support network for young women aspiring to enter politics, with peer-to-peer support and mentorship between emerging and seasoned women leaders |  |  |  |  |  |  |  |  |  |  | Workshops, trainings and advocacy events: Technical expertise (NPSAS/IUNV/FTA): Consultancies Travel: Workshops, trainings and advocacy events Consultancies | 12,568 47,365 50,000 3,000 23,167 30,000 |
|  |  |  | Activity 2.5.1 Mongolia. Strengthen women’s participation in policy/development. Actions. - Engaging women in co-creation and piloting of participation accelerators - Identify women participants from different backgrounds, sectors, and locations whose interests may be affected by the issue/selected topic/s, for equal participation - Organize sessions for women to discuss the issue/topic/s both substantively and procedurally and from gender perspective, as part of the participation pilots, using relevant tools. - Share/report the findings and recommendations to the main stakeholder group Activity 2.5.2 Mongolia. Support youth’s engagement and leadership through the Youth Parliament and youth-led media engagement. Actions: - Identify young participants from different backgrounds, sectors, and locations for equal participation - Put the selected issue/topic/s on the agenda of youth Parliament - Design youth Parliament sessions so that the issue/topic/s are discussed both substantively and procedurally, in order to identify participation accelerators - Share/report the findings and recommendations to the main stakeholder group - Expand media exposure of youth participation initiatives through youth-led media activities - Lessons learned report on youth as change agents |  |  |  |  |  |  |  |  |  |  | Workshops, trainings and advocacy events: Monitoring and learning: Workshops, trainings and advocacy events: Consultancies: Communications: | 60,000 3,785 80,000 30,000 3,784 |
|  |  |  | Subtotal Output 2 |  |  |  |  |  |  |  |  |  |  |  | 973,340.46 GEN3 output must be minimum 15% of allocation |
| Output 3. Relevant insights and approaches based on country-level interventions are identified and documented in order to inform global knowledge management for policy scale-up. Indicator 1.1. Number of countries that express interest to roll-out approached tested in pilots Baseline: 0 Target: 5 Indicator 2.2. Number of partners expressing interest to partner on an Open, Public Sphere, following communication products Baseline: 0 Target: 3 Related Global Programme Output (G4PP): Gender Marker: 2 |  |  | Activity 3.1.1 Strategic Guidance, Oversight and Stock-taking: Draw and Disseminate Lessons from country-contexts to inform global knowledge management for policy scale up Actions - Provide technical support to COs for youth inclusive and gender sensitive analysis and implementation of activities. - Provide technical support to COs to develop knowledge products, including specific lessons learned and briefs on women inclusion and participation, and communication/dissemination of lessons learned, at regional/global levels. - Codification and global dissemination of knowledge products from pilot experiences - Global communication products with key learnings - Organization of discussion spaces with partners, youth led organizations, and women's organizations, providing opportunities for sharing lessons, discussing challenges, and exploring future opportunities for further replication and scale up. |  |  |  |  |  |  |  |  |  | Governance/BPPS/Open, Inclusive, Public Sphere | Technical Expertise (IPSAs/NPSAs, consultancies, UNVs, etc.) Workshops, trainings and advocacy events, communications products: Travel: | 41,507 29,707 21,787 |
|  |  |  | Subtotal output 3 |  |  |  |  |  |  |  |  |  |  |  | 93,001 |
| Technical Accompaniment |  |  | Technical Expertise (IPSAs/NPSAs, consultancies, UNVs, etc.) - Workshops/ co-creation events (with COs, Regional Offices) and advocacy/sensitization events (with external partners- contributing partners, IFIs, UN agencies, etc.) - Contractual services (specialized research, consulting firms) - Travel (engagement with Regional Offices, COs; contributing partners, IFIs; South-south engagements) |  |  |  |  |  |  |  |  |  |  |  | 112,149 |
| Project Management Costs (Cross-Output) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 140,000 |
| General Management Support (7%) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 157,009.4 |
|  |  | TOTAL: |  |  |  |  |  |  |  |  |  |  |  |  | 2,400,000 |

All proposals should align to at least one SP output and related indicator and include those in the workplan/result-framework below to show contribution to the SP IRRF. The linkage to the SP Output and indicator should also be reflected in Quantum.

See, e.g., the results of the 2023 Edelman Trust Barometer and Brannen, S. J., Haig, C. S., & Schmidt, K. (2020). The age of mass protests. Understanding an escalating global trend.

See, e.g., Boese, V. A., et al. (2022). Autocratization Changing Nature? Democracy Report 2022. Varieties of Democracy Institute (V-Dem).

United Nations. (2021). ‘Our Common Agenda: Report of the Secretary General.

As established in the Universal Declaration of Human Rights, the International Covenant on Civil and Political Rights, and several other international and regional human rights legal instruments

As clarified in the UN Human Rights Committee’s General Comment No. 25

United Nations and World Bank. (2018). Pathways for peace: Inclusive approaches to preventing violent conflict;

UNU-WIDER. (2023) Towards peace, decent work, and greater equality: Research evidence for transforming economies, states, and societies. Helsinki: UNU-WIDER.

OHCHR. Women human rights defenders. OHCHR and women’s human rights and gender equality.

opengovpartnership.org/members/mongolia/commitments/mn0060/

opengovpartnership.org/members/mongolia/commitments/mn0059/

OGP Independent Reporting Mechanism Action Plan Review: Mongolia 2023-2027: https://www.opengovpartnership.org/wp-content/uploads/2024/08/Mongolia_Action-Plan-Review_2023%E2%80%932027_EN.pdf

As per UNDP’s Enterprise Risk Management Policy

In the below, the aggregated risk assessment is noted, yet likelihood and risk levels will vary from country to country. For instance, the political risk is seen as high in Somalia but low in Senegal. As noted, such risks will be addressed through careful analysis and adaptive approaches to programme management, in each context.

Cost definitions and classifications for programme and development effectiveness costs to be charged to the project are defined in the Executive Board decision DP/2010/32

Changes to a budget affecting the scope (outputs), completion date, or total estimated costs require a formal budget revision that must be signed by the project board. In other cases, the UNDP programme manager alone may sign the revision provided the other signatories have no objection. This procedure may be applied for example when the purpose of the revision is only to re-phase activities among years.

Costs associated with the management of the initiative at the country level - across the programme countries, at approximately, at approximately 7% of programmable budget. This is to ensure responsibility for the overall design, management, implementation, monitoring and reporting of the project at country level - and adequate coordination with HQs/Regional Hubs.