Project Final Report

Project/intervention title:  UN-to-UN Contribution Agreement for Joint Support to the Second Phase of the Land Degradation Neutrality Target Setting Process (LDN TSP 2.0) in Jordan

Partners: Ministry of Environment (MoEnv)

Agreement Expiration Date :  23rd December 2025

Date submitted:  18 April, 2026

Total Agreement Budget: $26,000

- Nature of Activities

The activities under this agreement focused on providing technical support to the Government of Jordan to advance the second phase of the voluntary Land Degradation Neutrality Target Setting Process (LDN TSP 2.0), with a specific emphasis on integrating gender considerations into land degradation planning and implementation.

The intervention supported the design and execution of a national gender assessment, ensuring that LDN targets, measures, and future programmes are gender-responsive and aligned with international commitments. The activities included:

- Providing technical support to Jordan’s Land Degradation Neutrality (LDN) target-setting process and its implementation;

- Facilitating intersectoral coordination and stakeholder engagement in land degradation monitoring and planning;

- Strengthening national capacities and supporting the integration of gender considerations into LDN policy and reporting processes.

# Achievements

Activity 1: Multi-Stakeholder Consultations for Revising National LDN Targets – Completed As part of the LDN TSP 2.0 process, a two-day national consultation workshop was held in 28-29 May 2025 at the Hilton Hotel in the Dead Sea, convening all relevant stakeholders, including members of the national taskforce, technical working groups, government entities, civil society, and academic representatives. The workshop served as a key milestone in advancing the revision of Jordan’s LDN targets. It provided a structured platform to: - Review and discuss updated land degradation data and assessments - Facilitate technical exchanges across sectors - Refine and validate proposed revisions to national LDN targets - Strengthen alignment with national priorities related to land use, biodiversity, and climate resilience The consultations enabled inclusive, cross-sectoral dialogue and ensured that the revised LDN targets reflect both technical rigor and national ownership. The workshop also reinforced coordination mechanisms among stakeholders, supporting a more integrated approach to land degradation monitoring and planning in Jordan. Activity 2: National Gender Assessment and Mainstreaming into LDN Targets – Completed Under this activity, a national gender consultant was successfully recruited to conduct a comprehensive gender assessment within the context of land degradation in Jordan. The consultant carried out a series of targeted consultations with civil society organizations (CSOs), national partners, and relevant stakeholders, aiming to: - Identify gender-specific challenges and gaps in land use and resource access - Assess participation and decision-making dynamics in land governance - Gather stakeholder insights to inform gender-responsive LDN targets and interventions The assessment process culminated in a one-day national validation workshop held on the 13th of October, 2025 at the Signia by Hilton hotel , where key findings and recommendations were presented and discussed with stakeholders. The workshop provided a platform to validate results, refine recommendations, and build consensus on integrating gender considerations into LDN policy and implementation.

# Implementation Challenges

This intervention experienced some delays in implementation and overall workflow due to: - Coordination and procedural delays with the Ministry of Environment - Challenges in ensuring sufficient stakeholder participation, particularly for the gender validation workshop These delays impacted the timeline but did not affect the overall delivery of key outputs, which were successfully completed.

# Stakeholder Engagement

The project was implemented by the United Nations Development Programme (UNDP) in close coordination with: - The Ministry of Environment (UNCCD national focal point) - The Global Mechanism of the UNCCD - Relevant national stakeholders and sectoral institutions UNDP provided technical leadership, coordination, and quality assurance, ensuring alignment with its standards and procedures, while facilitating inclusive stakeholder engagement throughout the process.

# Lessons Learned

Key lessons from implementation include: - Early and continuous stakeholder engagement is critical for ownership and validation - Integrating gender into technical processes requires targeted expertise and dedicated analysis - Alignment with ongoing national processes (LDN, NDC, biodiversity) enhances efficiency and impact - Capacity-building should accompany analytical outputs to ensure sustainability

# Sustainability and Next Steps

The results of this intervention provide a strong foundation for: - Integrating gender considerations into LDN implementation frameworks and national land-use planning processes - Informing future climate, biodiversity, and sustainable land management programmes - Supporting the development of transformative, gender-responsive investment projects aligned with LDN priorities Further efforts are recommended to: - Institutionalize gender-responsive approaches within national LDN enabling environments and policy frameworks - Continue targeted capacity-building for relevant national and sub-national stakeholders - Ensure the systematic uptake of recommendations in future project design, planning processes, and investment programming

# Attachment: National Gender Assessment: The Voluntary Land Degradation Neutrality Target Setting Process (LDN TSP 2.0) of Jordan.

Signature: Rana S. Saleh

OiC, Team Leader of the Sustainable Green Pathways and Inclusive Growth Pillar, UNDP