PROGRAMME DOCUMENT

Ukraine

Project Title: Inclusive Recovery Support for Resilience and Human Security in Ukraine

Project Number: 01003977

Implementing Partner: UNDP (DIM)

Start Date: 31 March 2025		End Date: 31 March 2026             PAC Meeting date: 19 February 2025

Brief Description

Since the full-scale military aggression by Russian forces in February 2022 (hereafter, the “War”), Ukraine has been facing unprecedented destruction and displacement, and continued threats to human security--- thousands of women, men, and children have lost their lives, critical life-line infrastructures have been destroyed, and millions of people have been forced to leave their homes. The degree of destruction and damages has been unprecedented, profoundly affecting every aspect of Ukrainian society and economy, while casting a long shadow over global peace and security, including stability in East Asia. Without immediate and synergized efforts for three pillars of Human Security---protection, empowerment, and solidarity---to capacitate the nation and people of Ukraine to be resilient against the cumulating negative impacts of the War, Ukraine will soon face risks of succumbing to the cumulative and escalating impacts of the ongoing war, potentially leading to irrecoverable loss. This project aims to stimulate urgent recovery and strengthen resilience against the widespread death, destruction, displacement, and suffering caused by the war in Ukraine, for promoting Human Security in Ukraine. The project will undertake multi-sectoral and integrated immediate actions against interconnected and multidimensional threats that Ukraine is currently facing. The project will promote rapid recovery from the devastation of war by comprehensively implementing the urgently required interventions, which include: the restoration of basic infrastructure (electricity, water, public facilities, etc.), enhancement of a safe living environment through clearance of mines and explosive remnants of war (ERW) and debris management and recycling, promotion of economic recovery with support for agricultural industries and small and medium-sized enterprises and social reintegration of war victims and veterans, strengthening of capacity and functions related to the implementation of anti-corruption policies, expansion of legal services to war victims and socially vulnerable people, and strengthening of governance in the formulation and implementation of reconstruction plans by the Ukrainian at the national and local levels. To maximise positive results on transformational recovery, the project interventions will focus on the 6 priority thematic areas for the project outputs, which are: Output 1: Critical infrastructure for basic services Output 2: Debris management and recycling Output 3: Mine action and war victim assistance Output 4: Economic recovery Output 5: Government recovery coordination Output 6: Access to justice and human rights

| Contributing CPD Outcomes: CPD Outcome 1: Peace, Justice, and Strong Institutions CPD Outcome 2: Inclusive Economic Growth CPD Outcome 3: Environment Indicative Output(s) with gender marker Gender marker: GEN 2 |  | Total resources required: | US$29,316,546 |  |
| --- | --- | --- | --- | --- |
|  |  | Total resources allocated: | Gov of Japan: | 29,316,546 |
|  |  |  | Other: | 0 |
|  |  |  | Unfunded: | 0 |
|  |  | Total Programme Budget | US$29,316,546 |  |

Agreed by (signatures):

Date:

# Background

1-1. Situation Analysis

The escalation of the war in Ukraine began on 24 February 2022 and has been causing heavy shelling and fighting with an estimated 5.1 million people driven from their homes and internally displaced while more than 8.1 million people crossed into neighbouring countries in the region including Poland, Hungary, Moldova and other countries across Europe.

As the map below shows, the damages sustained by the War have greatly increased in 2023, especially in Donetska, Kharkivska, Luhanska, Zaporizka, Khersonska, Zhytomyrska, Odeska and Kyivska oblasts. Ukraine Rapid Damage and Needs Assessment: February 2022-2023 (RDNA3, published in Feb. 2024) reveals that Ukraine's reconstruction and recovery cost has grown to US $486 billion. As the War is expected to prolong, the cost of reconstruction and recovery will stretch both public and private funds over a decade.

| Map 1&2: Extent of damage by region as of February 2023 (left) and December 31, 2023 (right) |  |
| --- | --- |

Leveraging Japan’s extensive expertise and extensive Japan-UNDP partnership for recovery and Humanitarian-Development-Peace nexus in crisis situations, integrated urgent and immediate multi-sectoral support is indispensable to respond to the growing damages in volatile and unpredictable situations caused by the prolonged War in Ukraine, as summarized below:

1-2. Justifications

1) Urgency – the reason why the project should be launched during the GoJ’s FY 2024 (until March 2025)

As of November 19, 2024, Ukraine marks 1,000 days since Russia’s invasion, and the needs for emergency assistance and immediate recovery persist. Ukrainian people continue to struggle with limited access to basic services, lost livelihoods and an uncertain future, as described below. Over 14.6 million people are in need of humanitarian assistance, exacerbated by ongoing conflict and limited access to essential services. Russia has increased missile strikes on Ukrainian infrastructure, leading to widespread civilian casualties and damage to essential services. The urgent support to the recovery and reconstruction of the country is critical to alleviating people’s suffering, particularly during hot summer and cold winter months. If such emergency assistance is not provided, the impacts of the War will not be mitigated, and Ukraine's society and economy will weaken, leading to the country suffering from a devastating situation for a long period of time. Furthermore, if this were to happen, the international order would no longer be able to be maintained, which could pose a threat to the stability of the East Asian region and, ultimately, to world peace. Japan’s swift and decisive funding is essential to prevent a compound crisis that could further undermine Ukraine’s recovery and jeopardize global peace, including stability in East Asia.

Critical infrastructure for basic services : UNDP’s Energy Damage Assessment report (June 2023) indicates that the Ukrainian energy system remains extremely vulnerable and continues to operate in emergency mode with a reduced and limited safety margin, grappling with damages that have exceeded $10 billion. Power generation capacity has been reduced to over 50% of its pre-2022 levels. With support from the Government of Japan (GoJ) and other partners, UNDP has been supporting the restoration of the high-voltage energy grid to ensure the uninterrupted supply of electricity, water, and heating -- directly benefiting over 6 million people. However, resumed and intensified attacks in March 2024 have targeted transmission capacities, such as substations and autotransformers, and energy generation facilities, both state/municipally owned and private, in all major cities. Attacks targeting infrastructure have been continuing and causing devastating damages not only in energy sector, but also distorting heating, water supply, sewage services, as well as economic activities. Therefore, it is extremely critical to undertake immediate action for restoring damaged infrastructure to meet urgent needs in energy and key utility sectors.

Debris management and recycling: The War in Ukraine has resulted in significant destruction of residential buildings. With over 10 percent of the total housing stock either damaged or destroyed and close to 2 million households affected, housing continues to be one of the most impacted sectors. As of December 31, 2023, the total cost of damage to the housing sector is estimated to be US$55.9 billion, according to RDNA3 report.   As of January 2024, the Kyiv School of Economics reported that the Russian invasion had damaged or destroyed about 250,000 housing facilities. The educational sector has also suffered heavily, with more than 3,800 educational facilities damaged or destroyed, including approx. 1,900 secondary schools, approx. 1,300 preschools, and 586 higher education institutions. Additionally, the health sector has been significantly impacted, with 358 hospitals, 426 clinics destroyed or damaged. The scale of destruction extends to over 1,222,600 private (individual) buildings, 27,000 multi-story buildings and 530 dormitories, figures that continue to climb. Damage to infrastructure and total losses to gross domestic product have already reached $157.2 billion. The widespread presence of debris and damaged infrastructure are severely impeding the return of residents as well as posing a risk to human health from such hazards as asbestos, hazardous waste and unstable buildings. Due to the damaged infrastructure, chemicals and hazardous substances are also leaking into the natural environment, impacting on land, water, and air resources. These challenges underscore the urgent need for comprehensive recovery efforts address both immediate needs and long-term consequences.

Mine action and war victim assistance: As of 2024, Ukraine remains one of the most heavily mine-contaminated countries in the world. The conflict has resulted in approximately 174,000 square kilometers of the country, nearly 29% of its total area, being contaminated with landmines and unexploded ordnance​. The widespread presence of debris and damaged buildings/infrastructure are severely impeding the return of residents, economic activities, as well as posing a risk to human health from hazards including asbestos, hazardous waste and unstable buildings. This leads to negative environmental impacts on land, water, and air resources. With the support from the GoJ and other partners, UNDP has been assisting Ukraine's emergency services to remove over half a million landmines and pieces of unexploded ordnance. Through integrated debris treatment protocol for EO clearance and hazardous materials management, UNDP with support from Japan has removed approximately 190,000 m3 of construction debris at 1,000 locations, including private houses, public facilities, educational institutions and dismantled 883 damaged buildings, benefiting approximately 1,700 people in need. This, however, is a fraction of the debris accumulated and the volume of debris has been increasing due to continuous fighting and shelling. Urgent actions are required to promote safe living environments for all, including IDPs and returnees. UNDP also safely removed over 2,100 m³ of hazardous waste, including 1,500 m³ of asbestos-containing materials.

Ukraine is indeed the world’s most potentially explosive ordnance-contaminated country, with nearly 6 million citizens living under the constant threat of explosive remnants of war. As of early 2024, approximately 3 million people in Ukraine were living with disabilities, up from around 2.7 million before the full-scale invasion, underscoring the urgent need for comprehensive rehabilitation and support programme, including to socio-economic integration. According to the UN Human Rights Monitoring Mission in Ukraine has verified 30,457 civilian casualties during two years since 24 February 2022, including 10,582 killed and 19,875 injured, with the actual numbers likely to be significantly higher.  To assist the EO and war-affected population UNDP with support from the GoJ has developed and is implementing the Victim Assistance Model in Mine Action in Ukraine.

Economic recovery: According to RDNA3, the War has continued to cause significant damage to Ukraine’s economy. Poverty surged from 5.5% in 2021 to 24.1% in 2022 based on the poverty line of US$6.85 per person per day. Employment in 2022 was 15.5% (2.4 million jobs) below the pre-war levels as reported by the International Labour Organization (ILO). Though the economy started recovering from the 2022 shock, growth remains weak and businesses face resource constraints and war risks. Small businesses remain vital for economic activity and employment in Ukraine with 99.98% of businesses classified as small and medium enterprises (SMEs). Micro-, small and medium-sized enterprises (MSMEs) employ 82% of the total labour force (employees, sole proprietors and working shareholders) and provide 73.8% of jobs in the employment market. Due to the War, businesses in Ukraine have faced substantial losses with about 50% of enterprises operating at only 10-60% of pre-war capacity. In the second quarter of 2023, around 50% of MSMEs operated with some restrictions, and 10% had not resumed operations. Access to financing has become a major issue for MSMEs since the War began. According to a UNDP study in October 2022, 46% of interviewed MSMEs had never used external financing. The UNDP is supporting the government's efforts to help businesses stay afloat and thrive. To mitigate displacement and disruptions in production capacities and value chains, the UNDP has provided a range of targeted livelihoods support, from small grants to training for women-led businesses, benefiting 20,000 MSMEs. As more and more areas in Ukraine regain minimum security, such as Kyiv and its surrounding oblasts, it is critical to swiftly revive the local economy to support a steady recovery.

Government Recovery Coordination: Despite the ongoing full-scale war, the Government of Ukraine (GoU) has demonstrated extraordinary capacity in leading and coordinating all crisis response efforts, ensuring sustained public service provision while organising the efforts to restore the country. Ukraine continues operating under martial law. International partners and civil society continue supporting the government’s efforts to build resilience, consolidate democratic reforms, and foster EU integration. However, critical components necessary for recovery are not fully in place, such as clear tools for internal and external oversight and mechanisms for effectively engaging civil society and local communities and continuing to promote gender equality which will contribute to higher productivity and better financial performance. Local authorities have uneven capacities to address recovery challenges, which vary based on how severely communities have been affected by the war, and many lack experience with infrastructure projects. Although civil society actors have been deeply involved in reconstruction and relief efforts since the War’s start, many feel not fully involved in planning and delivering the recovery. Moving forward involving more international partners further coordinating their efforts, the Government urgently needs to develop mechanisms for increased transparency, accountability, and participatory approaches in the recovery and reconstruction processes to build public trust and ensure efficiency.

Access to Justice, Human Rights: According to a Two-Year Update by OHCHR on the protection of civilians, it is recorded that since 24 February 2022, conflict-related violence in Ukraine has killed at least 12,605 civilians and injured 29,178 (41,783 total civilian casualties). This number includes 2,523 child casualties. Of the adults, men were disproportionally affected, accounting for 60 per cent of the casualties. The number of victims is growing by the day, by 11 February 2025 the Prosecutor General’s Office has recorded 155,885 war crimes, including 20,674 crimes against national security committed during the full-scale invasion by the Russian Federation. In total 599 children have been killed. In parallel with the ongoing humanitarian crises, another critical challenge relates to the investigation of human rights and international humanitarian law violations, including conflict-related sexual violence (CRSV), and the provision of effective support to survivors and people affected by these violations. The Independent International Commission of Inquiry on Ukraine has found that an array of war crimes, violations of human rights and international humanitarian law have been committed in Ukraine.  In such a context, proper and impartial documentation and evidence collection on war crimes, along with regular monitoring of these and other conflict-related human rights violations, including for the damaged and lost property, is crucial to ensure further access to justice, remedies for victims/survivors, and accountability.

2) Necessity – the reason why the project should be financed especially by the GoJ

Without urgent intervention, the emerging human security crises will significantly derail Ukraine's development trajectory and drastically increase human suffering.

Japan is the leading donor in recovery support in Ukraine to the UN system, contributing the largest funding (US$208 million for 2023) to the UN system for recovery, while UNDP is the lead UN agency for recovery in Ukraine and has received the largest contribution from Japan for recovery supports among UN agencies in Ukraine. This represents a significant partnership between UNDP and Japan for recovery in Ukraine, and combined efforts by Japan and UNDP to promote multi-sectoral recovery under this project is expected to contribute to Japan’s diplomatic, financial, humanitarian and recovery support to Ukraine.

Donor Support for UN Recovery Efforts in 2023

The effects of the war are also threatening global peace and stability, casting a shadow over the future stability of East Asia. As a major regional power, Japan has an obligation to contribute to support Ukraine from the perspective of preventing instability in East Asia.

Critical infrastructure for basic services: UNDP, with funding from Japan, secured stable energy supplies for 6 million people in Ukraine by supplying and transporting complex critical equipment, such as high-voltage autotransformers and gas turbines, and Japan is widely recognized as a leading donor for the energy sector. Building on UNDP’s experience in the swift provision of large infrastructure equipment, Japan’s fund for this project will safeguard families from the risks of unsafe water sources, potential sewage backups, and the dangers of resorting to hazardous heating methods under Output 1.

Debris management and recycling: The project, particularly Output 2 on Debris management and recycling, will leverage Japan's unique reconstruction expertise, gained through overcoming natural hazards such as the Great Hanshin-Awaji Earthquake in 1995 and the Great East Japan Earthquake in 2011. Japan is a unique country with dual characteristics of earthquake-prone country and advanced technology. With this rare positioning, Japan should use its knowledge and best practices gained from past disasters to support Ukraine.

Mine action and war victim assistance: Japan’s leadership in the field of mine action is well established, and its upcoming roles - host of the international Ukraine Mine Action Conference in 2025 and presiding over the 22nd Meeting of States Parties to the Anti-Personnel Mine Ban Convention in Geneva- highlight its global commitment to this critical issue. The project, especially Output 3 on Mine Action and War Victim Assistance, presents a unique opportunity to showcase and enhance the visibility of the GoJ's contributions. Furthermore, Japan possesses a sound experience and expertise in mine action through its experience in Cambodia. Supporting Ukraine through such established experience is requested by international community.

Economic Recovery: Following the Japan-Ukraine Conference for Promotion of Economic Growth and Reconstruction in February 2024, the project will continue to promote economic recovery and growth in Ukraine under Output 4. This will involve active participation from the Japanese private sector and close collaboration with JETRO, which opened an office in Kyiv in 2024 to expand business ties and trade between Ukraine and Japan, further aiding Ukraine's economic stability and growth. In addition, Japan’s contribution to the area of Ukrainian economic recovery will be a foundation on which Japanese companies develop in Ukraine. This dual benefit – revitalizing Ukraine’s economy whole creating opportunities for foreign investment by Japanese businesses – underscores the importance of Japan’s continued active participation and leadership in this area.

Government Recovery Coordination: Japan has been promoting transparency and anti-corruption in the recovery process in Ukraine, leading the G7 Anti-Corruption Task Force (ACT) for Ukraine, which was established in the G7 Justice Ministerial Forum in 2023. UNDP is a member of the ACT and conducted the actor-mapping study for anti-corruption in Ukraine. Follow-up actions based on the findings of the study will ensure a responsive, transparent, and accountable recovery process under Output 5.

Access to Justice and Human Rights: UNDP has demonstrated strong tripartite collaboration among UNDP, the GoU, and the GoJ. This includes a recent successful study tour for the National Police of Ukraine, hosted by the National Police Agency of Japan, which improved Ukrainian experts’ forensic practices, learning from Japan’s experiences in the Tohoku earthquake and tsunami. The continuous partnership will fortify the sustainability of the increased capacity of the police and justice sectors under Output 6 in this project. As Japan plans to augment its support to Ukraine in the area of Justice and Human Rights, supporting Ukraine through UNDP will result in expanding the base of knowledge and expertise for Japan in this area.

3) Unpredictability – the reason why the background of the project was not foreseen during previous GoJ’s FY (until March 2025)

The extensive degree of the damages caused by the War and targeted attacks on critical infrastructure across Ukraine have not been fully foreseen at the time of the budget formulation period of FY 2024. As of July 2024, the GoU estimates that over 2,000 missiles and drones, along with continuous shelling and grenades, have targeted the country’s energy infrastructure. Among these, more than 150 missiles have hit large energy facilities. The electricity sector has suffered significantly, with the generation capacity decreasing from 37.6 GW to approximately 17 GW as of May 2024 due to attacks by Russian missiles or drones, in addition to frequent destruction of health and education facilities and other basic infrastructures. Such ever-growing damages to critical infrastructure lead to the disruption of basic services and risks, including security due to lack of street lighting, disrupted education for children, limited mobility of elderly and people with disabilities, health safety concerns as well as economic productivity. The total level of destruction in the future remains highly uncertain.

4) Unsubstitutability – the reason why there is no other means but GoJ’s support to achieve the project goal

Japan’s support is indispensable to the success of this project due to its unparalleled expertise and longstanding commitment to advancing Human Security and HDP nexus. The GoJ has consistently been a global leader in addressing complex crises through integrated, multi-sectoral approaches that bridge immediate humanitarian needs with sustainable development outcomes. Currently, available external funding largely focuses on humanitarian needs. The JSB is a sole and unique funding source for enabling UNDP to work on the HDP nexus to create multi-sector, comprehensive, and integrated solutions to address humanitarian emergencies with sustainability at the core for the challenges to the survival, livelihood and dignity of the people in Ukraine. In particular, the GoJ has been a prominent world leader in promoting human security and the HDP nexus, and the support from the GoJ will exert high impacts to tackle both the root causes of vulnerabilities and the negative consequences of the crises, shifting towards resilience-based programming and longer-term transformational development solutions. Considering the highly unpredictable nature of the situation in Ukraine, it is imperative that the immediate interventions that are so urgently needed are managed in a way that reduces the vulnerability as well as the potential escalation of humanitarian suffering. The GoJ’s involvement in this project will not only ensure effective implementation but also set a global benchmark for integrated recovery efforts, reinforcing Japan’s leadership on the international stage.

In Ukraine, the GoJ has been providing tremendous assistance through UNDP with the following 5 projects: 1. Emergency Grant Aid Project (US$ 4.5 million) for Mine Action and Debris Management; 2. 2022 JSB Project (US$ 94.9 million) “Promotion of human security in Ukraine through responding to the multidimensional crisis caused by the war”, 3. Regular Budget Project (US$ 70 million) “Support to Critical Energy Infrastructure Restoration and Immediate Provision of Energy Equipment in Ukraine”, 4. 2021 JSB Global Project “Human Rights Due Diligence in Global Supply Chains: Leveraging the UN Guiding Principles on Business and Human Rights for a Just Recovery” (US$ 300,000), and 5. 2023 JSB Project (US$ 71.6 million) “Transformational Recovery for Human Security in Ukraine.”

This project is part of the Ukraine Humanitarian Response Plan 2024. The project will contribute to the work of Education, Food Security and Livelihoods, Health, General Protection, CP, Gender-Based Violence, Mine Action, Shelter and Non-Food Items, Water, Sanitation and Hygiene under the HRP 2024.

# Strategy

2-1. Objectives of the Project

Since the full-scale military aggression by Russian forces in February 2022 (hereafter, the “War”), Ukraine has been facing unprecedented threats to human security--- thousands of women, men, and children have lost their lives, critical infrastructures have been destroyed, and millions of people have been forced to leave their homes. The degree of destruction and damages have been widespread and creating detrimental impacts of all aspects of the Ukrainian society and economy, dropping shadows to global peace and security including East Asia. Without immediate and synergized efforts for three elements of Human Security---protection, empowerment, and solidarity--- to capacitate the nation and people of Ukraine to be resilient against the cumulating negative impacts of the War, Ukraine will soon face catastrophic effects created by the War.

This project aims to stimulate urgent recovery and strengthen resilience against widespread death, destruction, displacement, and suffering caused by the war in Ukraine and promote Human Security in Ukraine by undertaking consorted immediate actions against interconnected and multidimensional threats that Ukraine is currently facing.

2-2. Theory of Change

This project intends to offer a practical framework to implement comprehensive and multidimensional interventions to enhance Human Security for protection, empowerment, and solidarity for swift and sound recovery in Ukraine, based on the three principles of Human Security, which are, i) freedom from fear (threats to the safety of people); ii) freedom from want (threats to basic needs); and iii) freedom to live in dignity (access to livelihoods and opportunities).

The theory of change of this project is shown below, depicting a conceptual framework how to advance human security in Ukraine through swift and robust recovery in line with the Country Programme Document (CPD) for UNDP Ukraine for 2025-2029.

2-3. Outlines of the Project

The complex nature of the compounded crises in Ukraine requires a holistic, multi-sectoral perspective, going beyond sectoral terms and covering the whole population affected by the crisis, living in a specific geographic area in need of multi-sectoral support by working with multiple stakeholders. Therefore, the proposed project is designed with an area-based programming methodology with a build-back better approach to implement integrated and multi-sector interventions in six essential thematic areas to address the root causes of vulnerabilities and prevention against the emerging risks and threats derived from the ongoing conflict in the country.

The project will promote a rapid recovery from the devastation of war by comprehensively implementing the urgently required interventions, which include: restoration of basic infrastructure (electricity, water, public facilities, etc.), enhancement of a safe living environment through clearance of mines and  explosive remnants of war (ERW) and debris management, promotion of economic recovery with support for agricultural industries and small and medium-sized enterprises and social reintegration of war victims and veterans, strengthening of capacity and functions related to the implementation of anti-corruption policies, expansion of judicial services to war victims and socially vulnerable people, and strengthening of governance in the formulation and implementation of reconstruction plans by the Ukrainian at the national and local levels. This project will focus on the areas where the damage from war has significantly increased this year (such as Kharkiv) as well as the locations where the impacts by the War are placing serious negative socio-economic consequence and immediate support for social reintegration and economic recovery is required, such as the Western region (for example, Lviv.).

To maximise positive results on transformational recovery, the project interventions will focus on the following 6 priority thematic areas as the project outputs, based on the three principles of human security, namely, i) freedom from fear (threats to the safety of people); ii) freedom from want (threats to basic needs); and iii) freedom to live in dignity (access to services and opportunities). Details for each output are explained in Section III.

Output 1: Critical infrastructure for basic services

Output 2: Debris management and recycling

Output 3: Mine action and war victim assistance

Output 4: Economic recovery

Output 5: Government recovery coordination

Output 6: Access to Justice and Human Rights

2-4. Target locations and beneficiaries

The project plans to apply an area-based approach on a pilot basis and select the target areas at the oblast level out of the following three zonal categories, which share similar socio-economic contexts. The project plans to select at least 2 oblasts (states) out of the following three zonal categories, based on: i) severity of war damages; ii) exigency of needs for a large population; iii) accessibility to the locations in compliance with UN security standards; iv) government priorities and willingness of the government authority and community to support the project activities;  v) existence of social tensions or threats to the social fabric; and vi) opportunity to anchor project action with ongoing UNDP implemented initiatives at subnational level with the aim to achieve a multiplier and catalytic effect towards the recovery of the selected areas.

- “Recovery” zones where the Government of Ukraine regained control with high levels of reconstruction and recovery needs (such as Kyiv, Chernihiv, Sumy, and Dnipro oblasts)

- “Crisis” zones where the Government of Ukraine has restored a certain level of control in the areas but are still subject to ongoing active hostilities or in close proximity to the hostility areas, or the transit areas (such as Donetsk, Kherson, Kharkiv, Luhansk, Mykolaiv and Zaporizhzhia oblasts)

- “Hosting” zones that are not directly affected by the active fighting but facing severe negative consequences of the war, such as declined local economy or influx of the IDPs with some damages (such as Chernivtsi, Ivano-Frankivsk, Khmelnytskyi, Kirovohrad, Lviv, Odesa, Poltava, Ternopil, Vinnytsia, Volyn, Zakarpattia and Zhytomyr oblasts)

The total beneficiary number of this project through the proposed support described below in these 2 oblasts is expected to be approx. 1,527,000 people, out of which 804,500 are expected to be women.

2-5. Area-Based Approach for Human Security

Through its sub-national presence UNDP has long-standing partnerships with extensive networks of civil society organizations that are mobilized as entry points to target and deliver support to vulnerable groups, assist with local service provision, and strengthen the social fabric as it comes under increasing and protracted strain.

With the adoption of a new Country Programme Document for Ukraine, 2025-2029, UNDP has built on the success of its sub-national programming since February 2022 and designed a new area-based recovery and development framework focused on Reconstruction, Returns, Resilience, and Reforms (R4).  Over the course of the CPD cycle in 2025-2029, all UNDP work at sub-national level will be aligned to the R4 Framework aimed at addressing the complex recovery and development challenges in Ukraine.  UNDP will focus the sub-national interventions of this proposal in two oblasts and will work with national regional and municipality authorities to select multi-sectoral interventions across the outputs will be linked.  The subnational area-based interventions will be designed through participatory and inclusive consultation methodologies and will be multi-sectoral, linking immediate/short-term needs with transformational “build-back-better” approaches.

Building on such UNDP’s experiences, the area-based approach under this project is designed to ensure people-centered, comprehensive, inclusive and context-specific interventions. As described in the chart below, the proposed project will aim to generate catalytic and synergistic effects to maximize the coverage of positive impacts within the target areas and beyond by integrating multi-facet needs of human security in the complex nature of the compounded crises in Ukraine and encompassing all vulnerable populations in Ukraine, including Internally Displaced Person (IDPs), mine/war victims, veterans, people with disabilities, and returned refugees and among others. The area-based approach will enable the project to address a holistic, multi-sectoral perspectives beyond sectoral terms and cover the whole population affected by the crisis, living in a specific geographic area in need of multi-sectoral support by working with multiple stakeholders and strong synergies among different interventions. Furthermore, the context and dynamics of the communities significantly vary in different geographical areas in Ukraine, such as recovery, crisis, hosting as well as military action settings. The area-based approach can offer a suitable and practical programming framework for tailoring multi-sectoral support to specific localized needs of the targeted geographical areas.

Based on the needs, context, and future risks and vulnerabilities that people are facing, at least 2 oblasts will be selected as target geographical areas for multi-sectoral interventions. The interventions under each output to respond to the identified priority needs in the respective oblasts will be designed with participatory and inclusive consultation methodologies. Interventions to respond to the inter-related and multi-sectoral needs should be also identified, linking immediate/short-term needs with transformational impacts with a “build-back-better” approach for human security with the prevention-oriented, protection and empowerment focuses.

2-6. SDGs Targets

The interventions of this proposed project focus on addressing the multi-sectoral and inter-twined factors to achieve the SDGs listed below. It should be noted that the activities under each output are expected to exert multiplier effects, bringing conducive conditions for the SDGs targeted under other outcomes and beyond the listed SDGs. In particular, gender equality and women empowerment (SDG 5) will be mainstreamed under each output.

| Output | Related SDGs |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Output 1 (Infra.) |  |  |  |  |  |  |  |  |  |  |
| Output 2 (Debris) |  |  |  |  |  |  |  |  |  |  |
| Output 3 (Mine & War Victim) |  |  |  |  |  |  |  |  |  |  |
| Output 4 (Econ.) |  |  |  |  |  |  |  |  |  |  |
| Output 5 (Recovery Coord.) |  |  |  |  |  |  |  |  |  |  |
| Output 6 (A2J/HR) |  |  |  |  |  |  |  |  |  |  |

2-7. Inter-Output Synergies and Cross-Cutting Issues

Support for Gender in Crisis Situations: The project interventions under each output will address the 10-Point Action Agenda: Advancing Gender Equality in Crisis Settings (10PAA) as illustrated below:

| 10-Point Action Agenda Points | Output 1 (Infra.) | Output 2 (Debris) | Output 3 (Mine & War Victims) | Output 4 (Econ.) | Output 5 (Recovery Coord.) | Output 6 (A2J/HR) |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Stop the brutal trends in conflict-related sexual violence and the pervasiveness of gender-based violence in crisis |  |  |  |  |  |  |
| 2. Claim women’s agency as leaders of peace processes and political institutions: Women must be at the table |  |  |  |  |  |  |
| 3. Ensure women’s access to justice and security and their full rights as citizens |  |  |  |  |  |  |
| 4. Promote the participation and leadership of women and women’s organizations in crisis and recovery |  |  |  |  |  |  |
| 5. Value women’s unique knowledge and capacities in resilience-building, risk reduction and climate action |  |  |  |  |  |  |
| 6. Promote transformative and gender-responsive livelihoods and economic recovery |  |  |  |  |  |  |
| 7. Transform government to deliver equally for all |  |  |  |  |  |  |
| 8. Work with men and boys to challenge violent masculinities |  |  |  |  |  |  |
| 9. Prioritize gender data in analysis of risk, crisis and conflict: Data is not a choice anymore |  |  |  |  |  |  |
| 10. Increase funding for gender equality and women’s empowerment: Get the numbers right |  |  |  |  |  |  |

Furthermore, throughout this project, four pillars of Women, Peace and Security (WPS) on Prevention, Participation, Protection and Relief & Recovery will be addressed. The project will ensure women's participation and leadership in needs identification and determining the relief and recovery activity strategies by involving women in decision-making processes with leadership roles and leveraging women's unique perspectives and contributions. The activities will focus on building the capacity of female peace and security actors and providing multi-sectoral support for protecting women and girls from all forms of sexual and gender-based violence, particularly through Output 3: Mine Action & War Victims Assistance and 6: Access to Justice and Human Rights. The project also supports the Government of Ukraine in ensuring the participation of women and gender equality in decision-making in the government recovery plan and its operationalization process under Output 5: Government Recovery Coordination.

Public-Private Partnership (PPP): Building on the partnership with JETRO and UNDP’s expertise in MSME promotion in Ukraine, the project will serve as an impetus and a convenor to identify PPP opportunities and implement PPP initiatives under Output 4: Economic Recovery, while other outputs will also actively explore PPP collaboration to adopt innovation and top-notch technologies from Japanese and other foreign businesses and entrepreneurs, such as green energy under Output 1: Critical Infrastructure, Output 2: Debris Management and Recycle, and Output 3: Mine Action & War Victims Assistance.

Inclusive Society for Recovery: While there has been a strong sense of solidarity in Ukraine, the prolonged War has led to the emergence of potential new dividing lines and social groups with different experiences of the war, leading to diversified views on the recovery needs and priorities. However, as the concept of Human Security rightly indicates, solidarity is an integral part of promoting sound and swift recovery and building resilience. The project will adopt a “whole-society” approach to involve all segments of society decision-making and activity implementation, while providing specific support to ensure participatory methodologies for GoU’s recovery planning, ensuring continued attention and support to dialogue efforts mitigating potential social tensions, preventing disinformation and promoting transparency and accountability of the recovery process under Output 5: Government Recovery Coordination as well as advance social and economic inclusiveness of the war-affected populations, including youth, persons with disabilities and veterans under Output 3: Mine Action & War Victims Assistance.

# Results and Partnerships

3-1. Expected Results

The project will implement the interventions described below, aiming at effectively responding to the critical needs described above, for advancing Human Security through promoting recovery and resilience in Ukraine.

Output 1: Critical infrastructures and facilities restored to meet immediate needs to provide essential public services to prompt recovery and resilience

- Estimated number of beneficiaries: 500,000 (At least 50% women)

- Key counterparts: Ministry of Infrastructure, Ministry of Energy, Relevant Line Ministries, State-owned Energy Enterprises, Municipal authorities

Under this Output, UNDP will continue to support restoration of infrastructure in the energy sector, focusing on infrastructure support for energy generation and transmission to ensure the functioning of basic utilities in war-affected areas, such as heating, water, and sewage.  In particular, building on past experiences, the project will continue to enhance energy supply reliability with an approach to build-back better and greener through the establishment of decentralized, flexible and resilient energy system as well as other infrastructure that provide essential basic services to all. The findings from UNDP’s study on women in the energy sector will be integrated in design and implementation of the activities.

Planning and selection of the infrastructure facilities to be restored will be linked with the local recovery planning process supported under Output 5. In case imminent needs are identified in the targeted geographical areas, the restoration support under this Output may be extended to cover other critical infrastructures.

The results described above, the project will implement the following activities:

Activity 1.1: Formulate a critical infrastructure restoration plan for the target community, identifying the essential needs of different groups of the population, including women, girls, boys and vulnerable people, for universal access to basic services and critical utilities and innovative technologies for build-back better and greener recovery.

Activity 1.2: Rehabilitate or construct key infrastructures and provide necessary equipment for energy, critical utilities (e.g., water, heating, sewage) and other public services

Activity 1.3: Provide technical and quality assurance support to the construction and maintenance of infrastructures and installation of the equipment.

Output 2: Debris management system in Ukraine improved through the safe removal and recycling of debris and environmentally-sound management of hazardous waste and materials.

- Estimated number of beneficiaries: 500,000 (at least 50% women)

- Key counterparts:  Ministry for Communities and Territories Development, Ministry of Environmental Protection and Natural Resources, Ministry of Health, Oblast Military Administrations, Environmental Recycling Association of Ukraine, Territorial Community Administrations and City authorities

Under this output, UNDP will continue enhancing the capacities of local authorities to clear debris and safely demolish dangerous structures to enable rehabilitation and reconstruction of housing and public socio-economic facilities. The output also focuses on early recovery through collection, separation, transport, recycling and safe disposal of debris and hazardous waste by providing necessary equipment, reviewing the regulatory frameworks, and developing sustainable business models besides digital tools to support in debris assessment based on the achievements since the escalation of the War in 2022.

The project will conduct debris assessments in targeted oblasts and develop a GIS/MIS database to estimate debris volumes, track progress, and align with regulatory frameworks. This will support the government in updating the legal framework and prioritizing debris removal for structures with potential for reconstruction.

Removal of debris and damaged structures will be carried out, piloting UNDP’s Standard Operation Procedure that was developed based on its experiences. Safety of the work sites will be secured by conducting Non-Technical Survey (NTS) on explosive materials under Output 3 and providing necessary technical assistance on hazardous materials through Activity 2.4. Selection of the sites for debris removal and building demolition will be prioritised for the facilities that have already have a plan for reconstruction or future use and determined through consultation of the local authorities and communities.

Under this Output, capacity of   national and local authorities will be strengthened for safe and efficient management of debris by developing a long-term debris management strategy, reviewing the regulatory framework, and providing necessary equipment. Recycling initiatives will focus on supporting crushing operations, testing recycled materials for reuse, and ensuring compliance with national standards with technical assistance to local authorities and development of local market’s recycling capabilities. For   enhancing safe management of hazardous materials, such as asbestos, the project will improve testing capacity of the designated institutions by providing equipment, developing an environmentally-sound management practice and expand awareness campaigns for construction workers and households.

All stages of debris management will incorporate gender considerations to ensure equitable benefits for women, men, and marginalized groups. This includes collecting gender-disaggregated data, invite local government to engage women in decision-making and debris removal priorities, empowering them through roles in awareness campaigns, sorting, and recycling. Safety measures, such as PPE designed for diverse needs, and prioritizing debris removal for female-headed households, will be implemented. Collaboration with local women's organizations will guide gender-sensitive actions, supported by indicators to monitor progress and ensure accountability.

The results described above, the project will implement the following activities:

Activity 2.1: Conduct debris assessments, develop a GIS/MIS database to estimate volumes and capture progress and implement debris removal and demolition work

Activity 2.2: Strengthen the capacity of national/sub-national/local authorities in sustainable management of debris, recycling, and hazardous materials by reviewing regulations, developing relevant policies and guidelines and providing necessary equipment for operationalization

Activity 2.3: Promote debris recycling by piloting a recycling process, including carrying out crushing operations, testing recycled materials, and developing national standards for demolition management and reuse in Ukraine

Activity 2.4: Strengthen the capacity of government authorities for hazardous materials management, particularly on asbestos, by developing technical guidelines, providing equipment, and conducing awareness campaigns in partnership with women’s CSOs.

Output 3: Capacities of mine action authorities, local communities, and service providers expanded to protect the population affected by war, including veterans, and secure a safe environment for people’s living and socio-economic activities

- Estimated number of beneficiaries: 117,000 (50% women)

- Key counterparts: State Emergency Service of Ukraine (SESU), Ministry of Internal Affairs, Ministry of Social Policy and local authorities, CSOs

This output aligns with UNDP’s broader early recovery efforts in Ukraine by addressing the impacts of war through damage assessments, environmental evaluations, facilitation of explosive ordnance (EO) survey and clearance and enabling risk managed debris removal and demolition. These efforts establish early access for humanitarian actors while supporting recovery in war-affected areas.

The project will prioritize NTS on sites critical to rebuilding communities, including private housing, schools, hospitals, government facilities, and public infrastructure.  It will also target agricultural lands and water resources in two key oblasts. This enables risk managed access for debris removal and paves the way for reconstruction and recovery efforts. The NTS will also be conducted for the sites selected for removal of debris and dangerous structures that are implemented under Output 2.

To increase the awareness of affected communities, the project will deliver tailored EO risk education to at-risk populations, addressing their specific vulnerabilities. This activity focuses on raising awareness among women, men, girls, and boys in areas near NTS sites and promoting behavioural change to reduce risk. UNDP will conduct EORE targeted at debris management staff.

The project will enhance national mine action policies and build institutional capacity through bilateral and triangular cooperation and knowledge exchange with mine-affected states and Japanese institutions. This includes policy advice, technical training, and equipping national institutions to align where practical with International Mine Action Standards (IMAS) and assist sustainable progress in mine action.

Victim assistance as integral part of mine action output will be focused on enhancement of capacities of the national and local authorities in the provision of victim assistance in the mine- and war-affected communities, and strengthening the capacity of local professionals to ensure medical, psychological, social and livelihood supports in accordance with the International Mine Action Standards (IMAS).

The results described above, the project will implement the following activities:

Activity 3.1: Conduct Non-Technical Survey (NTS) on sites identified for debris removal (e.g., private housing, schools, hospitals, government facilities, public/social infrastructure) and agricultural lands, water beds and water resource infrastructure in 2 targeted oblasts.

Activity 3.2: Conduct targeted Explosive Ordnance Risk Education (EORE) for affected and at-risk communities in and around sites were explosive ordnance (EO) is confirmed. Targeted EORE will also be conducted for debris management site staff.

Activity 3.3: Strengthen mine action policy and build national institutional capacity through bilateral and triangular cooperation, knowledge exchange with mine-affected states and Japanese institutions, and targeted support.

Activity 3.4: Strengthen policy framework and practice for community-based social services, health, inclusive education, physical and mental rehabilitation, assistive technology services for war-affected populations, including persons with disabilities and veterans within the framework of Victims Assistance, by providing policy advice, equipment and capacity building support for national and sub-national government authorities and civil society organizations.

Output 4: Economic recovery in the targeted regions and key sectors promoted by fostering self-employment and entrepreneurship, enhancing employment of the war affected population and improving business enabling environment

- Estimated number of beneficiaries: 10,000 (At least 60% women)

- Key government counterparts:  Ministry of Economy, Ministry of Digital Transformation, Ministry of Education and Science, State Employment Service, State Regulatory Service, Entrepreneurship and Export Promotion Office, business support organizations (including women-led)

This output addresses the economic dimension of human security by improving access of the war-affected populations to livelihoods and income generation opportunities. It will respond to this challenge by supporting jobs creation and employment for the war-affected populations with a three-pronged approach:

- Direct support to self-employed, entrepreneurs and MSMEs to strengthen their capacity to generate livelihoods and create jobs

- Strengthening inclusive employment to enable access to dignified jobs, livelihoods and income opportunities for the broad groups of the war-affected populations, prioritizing the needs of the most vulnerable and leaving no one behind

- Improving conditions and enabling environment for entrepreneurs and MSMEs to ensure efficiency and multiplier effect of the project interventions to enhance economic recovery and security

The funnel approach applied to support self-employed, entrepreneurs and MSMEs combines training and capacity building for large numbers of entrepreneurs, targeted individual advisory and consulting support to the most engaged and motivated as well as financial support to avail additional resources for starting and growing businesses. War-affected self-employed and entrepreneurs will benefit from a selection of sustainable business models that prioritize social entrepreneurship, green, circular, sharing, and care economy solutions, made available through free-of-charge franchises in targeted value chains.

The output will focus on expanding employment opportunities, promoting inclusiveness, and ensuring the relevance of workforce training in target areas. It aims to unlock the additional potential of vulnerable groups, particularly persons with disabilities (PwDs), veterans, and other segments of the local population often underrepresented in the labor market. By enhancing the quality of professional education, the output seeks to strengthen the supply side of the labor market and foster partnerships between employers, vocational education and training (VET) institutions, and the State Employment Service to support the creation of new jobs. Additionally, the output will aim to enhance the capacities and capabilities of the VET system, the employer community, and the State Employment Service to provide inclusive training processes, employment conditions, and consulting services, respectively. This will be achieved through specialized training for VET trainers, awareness-raising initiatives, and the provision of specialized equipment to facilitate an inclusive training and working environment at training centers and workplaces.

The output will improve conditions and enabling environment for the war-affected entrepreneurs and MSMEs through the three main enablers:

- Enhanced access to business development services by strengthening business support ecosystem including the networks of business support centers from entrepreneurship support points at community level to resilient business hubs at regional level

- Improved market access facilitated through a series of dedicated local, national and international events, including trade shows and business forums

- Evidence-based and inclusive policy development cycles initiated at the national and local level to ensure participatory approach and alignment of national and local priorities of the economic recovery policies defining the conditions and enabling environment for entrepreneurs and MSMEs

Based on the results of the value chains mapping in each of targeted oblast the output will prioritize specific value chains with the highest potential for livelihood generation, job creation, contribution to reconstruction, internationalization, green and digital transformation, inclusivity and women economic empowerment in a particular oblast. Further targeting under the output will prioritize the needs of war-victims and vulnerable groups of the war-affected populations.

An area-based approach will be applied to address the crisis and recovery conditions in each targeted oblast. Tailoring innovative solutions to the specific needs of each oblast will allow for a more targeted, effective, people-centred, comprehensive, inclusive and context-specific interventions to ensure integration of multi-facet needs of economic recovery and inclusion of all war-affected populations, including women, youth, people with disabilities, IDPs and veterans.

The results described above the project will implement the following activities:

Activity 4.1: Support war-affected self-employed and entrepreneurs to start-up and develop businesses by providing capacity building, advisory and financial support to develop and pilot sustainable and competitive business models in the key value chains of the targeted oblasts.

Activity 4.2: Foster inclusive employment for the war-affected women and men, including veterans and people with disabilities, in targeted sectors by improving training infrastructure, delivering up/re-skilling training and strengthening employment facilitation mechanisms in partnership with labor market actors: professional training service providers, employers, and State Employment Service.

Activity 4.3: Improve conditions and enabling environment for entrepreneurs and MSMEs by strengthening business-support ecosystem, advancing market access and enhancing policy frameworks, prioritizing the needs of war-victims and vulnerable groups of the war-affected populations.

Output 5: Integrity, transparency, and accountability of government mechanisms and processes for crisis management and inclusive recovery strengthened at both national and sub-national levels, empowering citizen participation and engagement, including vulnerable groups, youth, veterans, and women.

- Estimated number of beneficiaries: 300,000 (60% women)

- Key counterparts:  Secretariat of the Cabinet of Ministers of Ukraine, Ministry of Communities and Territories Development of Ukraine, Ministry of Digital Transformation, Ministry of Foreign Affairs, Ministry of Culture and Strategic Communications, Ministry of Social Policy, Ministry of Economy, Ministry of Youth and Sports, Ministry of National Unity of Ukraine, regional administrations, local communities, civil society organizations, including women’s organizations and other relevant institutions.

UNDP will continue its systemic support to the Government of Ukraine and sub-national authorities in strengthening institutional capacity in developing and implementing regional recovery and development planning and policies, considering multi-level governance as a cornerstone of the country’s resilience and recovery efforts. Under this Output, UNDP will further support the Government in enhancing multi-level governance collaboration and policy dialogue in the recovery and regional development process. This Output aims   to ensure that national recovery and regional development priorities are effectively integrated into regional and local policies, decisions, and projects. Tailored expert and capacity-development support will strengthen institutional capacities, enabling subnational authorities to utilize recovery funds in a transparent and accountable manner and implement inclusive, people-centered policies and projects. These efforts will address the needs of diverse groups, including people of different ages, genders, and abilities, as well as internally displaced persons (IDPs) and veterans. The project will upscale the work on youth engagement in the recovery process through VidNova programme and other national and local mechanisms.

Additionally, support will be provided to enhance the government's strategic planning capacity at both national and sub-national levels, ensuring alignment with the Sustainable Development Goals and fostering effective coordination of international technical assistance. This support will be in line with institutional reforms, as prioritized by the Government, including the public administration reform, digital transformation and decentralization agenda. The activities under this Output will focus on advancing policies and mechanisms, delivering targeted capacity-building initiatives, promoting digital solutions, and fostering inclusive engagement among stakeholders. This comprehensive, multi-level governance approach will drive sustainable development and improve institutional effectiveness across all levels of government.

The project will aim at mitigating corruption risks in Ukraine’s recovery processes through a multifaceted approach: (a) at the national level, it will focus on developing evidence-based, comprehensive policy papers, recommendations, and guidelines to enhance transparency and accountability throughout the recovery and reconstruction efforts; and (b) at both national and local levels, the project will build the capacities of anti-corruption commissioners and other stakeholders, including civil servants, business representatives, journalists, and youth, fostering a culture of integrity and accountability.

This Output  will also focus on strengthening informational resilience and enhancing the capacity to counter disinformation across Ukraine by developing evidence-based policies, strategies, and recommendations aligned with international best practices, enhancing government officials’ strategic communication skills, and empowering civil society, particularly in targeted oblasts, to strengthen information resilience, build trust between population and government and empower communities, focusing on women-led initiatives and vulnerable groups.

To achieve the results described above, the project will implement the following activities:

Activity 5.1: Support the Government and sub-national authorities in enhancing crisis response, multi-level governance collaboration, and institutional capacity to integrate national recovery and regional development priorities into local policies, decisions, and projects.

Activity 5.2: Strengthen the capacities of the government at both national and subnational levels in institutional effectiveness, strategic planning, policy development, and coordination in line with the SDGs.

Activity 5.3: Enhance integrity, transparency, and accountability and support anti-corruption initiatives in Ukraine’s recovery and development processes.

Activity 5.4: Strengthen informational resilience, and unity of the government and population with enhancing capacities to counter disinformation, improve media literacy levels, and bolster and strategic communications.

Output 6: Accessibility, inclusiveness and accountability of justice system and human rights protection mechanisms with enhanced capacities to apply people-centered, gender sensitive approach increased ensuring better protection and support to all people, with a focus on war affected and vulnerable groups.

- Estimated number of beneficiaries: 100,000 (60% women)

- Key counterparts: General Prosecutor Office, Ombudsperson’s Office, Free Legal Aid Coordination Center under the Ministry of Justice, Ministry of Internal Affairs, National Police, civil society organizations, including women’s organizations and other relevant institutions.

This Output will be implemented under the overall UNDPs work to enhance human rights and access to justice. With UNDP’s comparative advantages with the expertise and established multistakeholder partnerships in these areas, the activities under this Output will aim at responding to the need to uphold justice, rule of the law and human rights in the war time. At the same time, the project will support the broader and long-term reform and development trajectories, including integration of “Heightened Human Rights Due Diligence” principles, promotion of transparency and accountability of justice institutions and law enforcement bodies. Such approach is aimed to strengthen capacities of the national justice actors to address urgent needs of affected people in a human-centred manner, fitting the Ukrainian context now and having a transformative effect for the country’s long-term determinations.

The activities are designed to ensure the provision of legal support to all, including the vulnerable population and respond to the additional legal and justice needs caused by the war, such as the war crime and human rights violation in the war actions. Recognizing the unprecedented scale of victimization and trauma caused by the war, the initiative prioritizes ensuring that support systems are accessible, inclusive, and responsive to the unique challenges faced by those affected. To achieve this, a human-centered approach is embedded throughout, focusing on the needs of victims as individuals rather than solely as witnesses or sources of evidence. Building on the training already developed and delivered for prosecutors and investigators, this project will extend these efforts to legal service providers, equipping them with the necessary knowledge and skills to deliver victim-centered and trauma-informed services. By fostering an understanding that victims have rights—including the right to withhold their experiences—and by aligning interventions with professional standards and victim-centered principles, the initiative ensures that every interaction strengthens trust, dignity, and recovery.

The support under this Output will also enhance access to justice and human rights protection that promotes   enabling and people-centred settings both in time of the current conflict and in its aftermath, and to support development and operationalization of transitional justice mechanisms of prosecution for war crimes and reparations, in line with international standards. Specifically, the project will help to operationalise standards of investigation of war crimes (investigation of CRSV, civilian killings, destroy of civilian infrastructure) to ensure proper investigation of war crimes and restoring justice for victims.

As well under this Output a comprehensive nationwide monitoring of judiciary actors will be conducted in partnership with the Ombudsperson's Office, which holds a supervisory mandate, and civic activists at both local and national levels. The monitoring will assess key aspects of transparency and accountability of courts such as the accessibility and openness of information on judicial websites and the transparency of judicial hearings. Identified gaps and challenges will be analyzed to inform the development of complex, targeted solutions. These solutions will be piloted in selected institutions, with the aim of refining and scaling them for broader application. Additionally, actionable recommendations will be formulated and widely disseminated to foster improved judicial accessibility and transparency across the system.

To achieve the results described above, the project will implement the following activities:

Activity 6.1: Develop capacities of justice system actors and legal service providers for enabling full and people-centred access to justice and human rights protection instruments to provide justice services in an effective, inclusive, non-discriminatory manner.

Activity 6.2: Enhance the national justice mechanisms for enabling the removal of barriers for survivors of war crimes, including CRSV, to come out and report crimes, get access to support and safe justice systems through strengthening capacity of prosecutors, investigators, police officers and legal service providers at sub-national level.

Activity 6.3: Increase transparency and accountability of justice system with ensuring openness and accessibility to public information and open data in judiciary.

3-2. Partnerships

Partnerships with Japanese Actors and Visibility

UNDP will build on its presence and broad partnerships it has sub-nationally, nationally, regionally and internationally to further enhance the impact of the project. At the country level, leveraging its strong and extensive local presence (Country Office and 6 field offices) and its network with the government and other stakeholders, UNDP will work in close collaboration with line ministries to ensure that government authorities own and lead the entire implementation process and its achievements, so as to ensure the sustainability of the project impact. Close collaboration at the subnational level with public authorities, state/municipality enterprises, and community representatives has been supporting/will support the co-designing and effective implementation of the project, allowing to jointly identify the context-specific priorities for the needs and detect potentially problematic implementation concerns at an early stage. UNDP will also look for collaboration opportunities with other UN agencies to advance Human Security through Humanitarian-Development-Peace nexus.

UNDP will further expand its partnership with Japanese organizations. UNDP Ukraine will explore every opportunity to collaborate Japanese government, JICA, Japanese NGOs, and Japanese private sector. In particular, JICA reopened their office in Ukraine in November 2023, and UNDP closely collaborated with JICA under JSB FY2022 and JSB FY2023 projects such as in a handover ceremony of energy infrastructure equipment held in Kyiv in November 2024, in which Japan’s support to Ukraine through JICA and UNDP was acknowledged under the attendance of the Minister of Energy of Ukraine and the Minister for Foreign Affairs of Japan. UNDP expects to further expand its partnership with JICA at national and subnational levels. Furthermore, UNDP plans to strengthen partnership with the Japanese businesses and the private sector to promote economic revitalization in Ukraine particularly under Output 4. This will be mainly made in cooperation with JETRO which opened a new office in Kyiv in October 2024. In February 2022, on the occasion of the Japan-Conference for Economic Growth and Reconstruction in Tokyo, UNDP and JETRO signed a Statement of Intent to collaborate for economic recovery by connecting Japanese and Ukrainian businesses. This resulted in several collaborations under the framework of JSB FY2023, and a high-level dialogue between the two organization to discuss further collaboration.

To maintain and further expand the partnership with the Japanese actors, UNDP will give attention to involve Japanese-national staff in project implementation within the rules and regulations of UNDP, while UNDP Tokyo Representative Office will provide liaison support with the Ministry of Foreign Affairs of Japan and JICA Headquarters in Tokyo as well as Japanese NGOs and private sector, including Japanese businesses, Keidanren and Japan External Trade Organization (JETRO).

Building on the partnerships formed through implementations of activities under the JSB FY2022 and FY2023 with relevant Japanese Ministries and Agencies, such as the Ministry of Justice (MoJ), Ministry of Economy, Trade and Industry (METI), Reconstruction Agency, and National Police Agency of Japan, UNDP will pursue to further develop these partnerships to jointly implement the Anti-Corruption Taskforce for Ukraine and the other G7 initiatives.

UNDP may also look for new partnership opportunities in engaging with Japanese local governments which have the sister-city relationships (e.g., Odesa-Yokohama) to deepen citizen friendship between the two countries. The signing of the State of Intent (SoI) between the City of Yokohama and UNDP in July 2024 on collaboration in reconstruction in Odesa and its surrounding is an example of such commitment. Utilizing its strong field presence, UNDP can provide advisory support on the local situations and needs in Ukraine for Japanese NGOs and the private companies. Furthermore, UNDP will explore a possibility to engage with Japanese companies within the rules and regulations of UNDP.  UNDP will inform the Japanese Embassy when a Japanese company is selected as a vender/service provider for project activities.

In accordance with the guidelines of Japan-UNDP Partnership Fund, UNDP will make their utmost effort to publicize the partnership between Japan and UNDP for this project. In the past years, UNDP have established solid relationships with Ukrainian and Japanese media and secured wide coverage. Building on these, UNDP will undertake comprehensive measures to ensure Japan’s visibility, which include:

- Ensuring posting Japan’s logo on the reports, publications and other publicity materials, such as signboards and T-shirts that the beneficiaries wear during activity implementation.

- Issuing press releases which highlight the Japanese contribution and produce Public Information materials and brochures on Japan’s contribution.

- Producing and posting web-articles on UNDP web-page on the activities supported by Japan’s contribution. Key web-articles and press releases are to be translated into Japanese and they will be posted on the UNDP Tokyo website.

- Producing and posting photos and videos of the activities/events funded by Japan, with placement of Japan’s logo.

- Utilizing the social media such as Facebook, X, Flickr, LinkedIn, and Instagram of UNDP in Ukraine, disseminating information on the activities supported by Japan.  UNDP will ensure to mention that the activities are funded by Japan.

- Conducting publicity events with the Japanese Government, benchmarking the key accomplishment of activities, such as agreement signing ceremonies, launch/completion ceremonies of the particular activities, and major conferences related to the project activities. UNDP will inform the Japanese Government of these occasions in advance and facilitate their participation in the event.

- Making sure to mention Japan’s contribution when UNDP is delivering speeches in the ceremonial/public events.

- Making arrangements to maximise media coverage of the events related to Japan’s assistance.

- Preparing communications materials in three languages (English, Ukrainian, and Japanese), such as videos and press releases, to extend the reach to cover a wide range of audiences.

The activities of visibility, media communications, and public relations will be carried out by two national communications staff and a Japanese staff in close collaboration with Japanese experts in UNDP Tokyo Representative Office (TRO) and communication staff for each output of the project, under the overall guidance of the Programme Manager and Communication Unit in Ukraine CO. The budget for communications and visibility is included in the budget line: “Programme Management (incl. DPC).”

Stakeholder Engagement

Further to the partnership approach described, the implementation of the project will be highly participatory and will be overseen by a project board. The direct beneficiaries will be engaged based on their willingness and commitment to contribute to the project results on a non-monetary basis. Training courses, workshops and seminars and other activities of the project will pay attention to ensuring access and involvement in project activities by both women and men and considering gender in studies and recommendations prepared by the project. From its onset, the project will promote ownership by the targeted local authorities and communities.

South-South and Triangular Cooperation (SSC/TrC)

The project will make efforts to ensure that the support to address the multidimensional crisis in Ukraine under the human security dimensions are leveraged by the best-practiced UNDP programmes in the regional and global context. For instance, Membership of the Ukrainian Parliament Commissioner for Human Rights in the Global Alliance of National Human Rights Institutions (GANHRI) as well as in the European equivalent, ENNHRI, opens the door to wide cooperation with other NHRIs in the region and all over the world. This cooperation became even more important and valuable in war realm opening door to exchange of experience and common advocacy. These fora were already used by the Ombudsperson to present and elaborate upon the Kyiv Declaration on the role of NHRIs in conflict and post-conflict environments as well as on combating trafficking in humans. Such cooperation enables the UNDP to exchange experience and best practices with other NHRIs from the countries which experienced conflict and post-conflict situations (Moldova, Armenia, Georgia, Western Balkans, etc.). The project will also support documentation and sharing of experiences from other countries in the region and globally on developing digital databases and tools, including direct exchanges through key project capacity building activities.

Knowledge

Various trainings and other forms of knowledge transfer conducted under this project, which include producing training curricula and training toolkits, promoting continuous educational use by relevant professional development and education institutions (such as Prosecutors Training Center and others). Analyses and thematic professional guidance produced by experts, recommendations (related to policies, institutional development, legislation, etc.) will be made available to direct beneficiaries, depending on topics and as agreed with relevant institutions and beneficiaries, to limited or broader expert public, or to the public at large. A variety of information materials (such as leaflets, info kits, online content) produced for purpose of awareness raising and facilitation of access to justice will be disseminated to large categories of indirect beneficiaries or specific groups (e.g. victims of specific crimes and human rights violations). Lessons learned and best practices will be digested in thematic reports or compiled and shared otherwise.  A repository of knowledge products will be maintained by the project staff.

Sustainability and Scaling Up

The Project’s sustainability and exit strategy is built into the Project’s approaches and activities. However, before the end of the Project, UNDP will undertake a review of its overall strategy, with a view to developing a detailed plan for transition and exist. The exit strategy will also be informed by the findings of the Project evaluation. The key elements of sustainability and exit strategy include the following:

- The Project invests in strengthening institutional capacities across the different components of the project that would take the areas of work forward in each Output. The strengthened institutional capacity and mechanisms will remain in place after the project’s end. Furthermore, these achievements will build resilience at individual, community, and national levels as well as create a pool of knowledge within institutions that could be further disseminated through peer-to-peer knowledge transfer and applied in future. The project approach to foster inclusivity and solidarity will ensure long-lasting impacts for recovery and peace, including non-discriminative and efficient access to justice, assistance, and remedies for human rights violations for the citizens. Hence, the main elements of the project are centred around strengthening the institutions’ knowledge and technical capacities to fulfil the mandate of the government authorities and ensure access to basic services and justice. In that sense, the training and capacity building of relevant government institutions and development of methodologies to provide their services and support to the people of Ukraine with enhanced efficiency and accountability under their designated mandate to sustain the results of the project beyond its end.

- The project will facilitate partnerships to support sustainability of relevant activities. For example, cooperation between line Ministries, private sector, academia, CSOs to enhance the energy security, food security, quality standards, community security and peaceful coexistence.

# Project Management

Cost Efficiency and Effectiveness

Cost efficiency and effectiveness in the programme management will be achieved through adherence to the UNDP Programme and Operations Policies and Procedures (POPP) and reviewed regularly through the governance mechanism of the UNDP Country Programme for Ukraine. In addition, there are specific measures for ensuring cost-efficient use of resources through using a portfolio management approach. This approach by UNDP Ukraine deployed by its three portfolios – Democratic Governance, Inclusive Development, Recovery and Peacebuilding, and Environment and Energy - ensures synergies and leverages activities and partnerships among several initiatives and projects that are implemented through the Portfolios by UNDP Ukraine. The strategy of this project is to deliver maximum results with the available resources through ensuring the design is based on good practices and lessons learned, that activities are specific and clearly linked to the expected outputs, and that there is a sound results management and monitoring framework in place with SMART indicators. The project aims to balance cost efficient implementation and best value for money with quality delivery and effectiveness of activities.

As proven in the past programme delivery performance, UNDP Ukraine has established arrangements and measures not only to ensure smooth implementation of the activities but also to flexibly adjust the planned activities to meet unexpected needs under highly uncertain and volatile situations by adopting special measures granted to the country office, undertaking close monitoring and follow-up actions and networking with the relevant stakeholders to coin a solution. Leveraging these experiences and established mechanisms, UNDP Ukraine will continue its effort to improve efficiency and effectiveness of the project activities.

On the financial side, UNDP Ukraine will prepare a financial report at the end of the project, which will constitute the official report of project expenditures for a given period. For any balance at the end of the project, the UNDP Ukraine shall consult with the local Embassy of Japan on its use. The interest income should be treated in accordance with the Japan-UNDP agreement on Arrangement for the Interest Income derived from Japan-UNDP Partnership Fund. UNDP Ukraine will inform and seek approval from the Japanese Government in case the actual budget expenses go beyond the 20% variance of the planned budget at the Output level.

Project Management

This project will be implemented under the framework of UNDP Country Program Document for Ukraine, applying the Direct Implementation (DIM) modality, where UNDP Ukraine will act as the Implementing Partner. Implementation of the project complies with policies, procedures and practices of the United Nations Development Programme in accordance with UNDP’s Programme and Operations Policies and Procedures (POPP) as well as social and environmental sustainability through application of the UNDP Social and Environmental Standards.

The programme implementation team will consist of the experts and specialists for the respective technical areas as well as project and office operations, including M&E and communications, led by senior-level Programme Manager, who is a Japanese national. To ensure effective liaison and close communications with the Government of Japan and UNDP Headquarters, the project deploys two Japanese national specialists in UNDP Tokyo Representative Office (TRO) and UNDP Crisis Bureau (CB).

The programme implementation team will also benefit from wider support services of the Operations Team of UNDP Ukraine, including Procurement, Human Resources and other operational aspects. Furthermore, the implementation programme team will have the technical support of the UNDP GPN. This support will focus on providing technical assistance to the project through GPN ExRoster by deploying Immediate capacity needed for the implementation of the project activities in areas of analysis, capacity development, monitoring and evaluation. The GPN capacity will also be leveraged to support complex studies ensuring timely and efficient delivery of these activities. The programme implementation team will also coordinate with the UNDP’s Istanbul Regional Hub (IRH), contributing to and benefitting from exchanges and sharing of experience and expertise within UNDP’s regional support.

# Results Framework

Intended Outcome as stated in the United Nations in Ukraine Cooperation Framework 2025-2029 #4: Peace, Justice and Strong Institutions. By 2029 society is more inclusive and cohesive with active civic space and more effective, accountable institutions that enable reform and recovery and safeguard rule of law, human rights, and gender equality #2: By 2029, people benefit from a strong economic recovery and decent work, with inclusive labour force participation, increased productivity and reduced regional disparities #3: By 2029, people benefit from inclusive and sustainable management of natural resources, responding to major climate and environmental challenges.

Outcome indicators as stated in the Country Programme Results and Resources Framework, including baseline and targets: Project Output 1: Critical infrastructure for basic services CPD Output 3.3: State institutions have strengthened capacities to affect an energy transformation in a gender-responsive way. CPD Output Indicator: Number of people benefiting from rehabilitated/improved critical infrastructure (inc. energy, heat, water/sewerage systems) for recovery in crisis or post-crisis settings. Baseline (2024)/Target (2029): - Female: 0/1,000,000 - Male: 0/2,000,000 - Sex-disaggregated data unavailable: 500,000/2,000,000 - Young people: 0/100,000 - PWD: 0/1,000 - IDPs: 0/10,000 Project Output 2: Debris management and recycling CPD Output 3.3: State institutions have strengthened capacities to affect an energy transformation in a gender-responsive way. CPD Output Indicator: M3 of waste removed per category: Baseline (2024)/Target (2029): - Debris: 102,093m3/400,000m3 - Hazardous: 0/20,000m3 - Household: 0/1,000,000m3 Project Output 3: Mine action and war victim assistance CPD Output 1.4: Authorities and communities have increased capacities to enhance inclusive human capital and social fabric CPD Output 2.1: Authorities and communities increase their capacities to advance economic recovery are underpinned by gender-responsive infrastructure rehabilitation and mine action. CPD Output Indicator: IRRF 1.3.1 Number of people accessing public and social services. Baseline (2024): Total: 90,213 Target (2029): Total: 170,000 (50% women) CPD Output Indicator: Square meters of land released through non-technical survey/technical survey and mine clearance (m2) Baseline (2024): 490,000 m2 Target (2029): 7,840,000 m2

Project Output 4: Economic recovery CPD Output 2.1: Authorities and communities increase their capacities to advance economic recovery are underpinned by gender-responsive infrastructure rehabilitation and mine action. CPD Output 2.2 State and civil society institutions have strengthened capacities to enhance an enabling environment and regulatory framework to expand economic opportunities, access to finance and green economic growth. CPD Output Indicator: Number of people benefitting from jobs and improved livelihoods in crisis or post-crisis settings. Baseline (2024): 160,000 Target (2029): 360,000 CPD Output Indicator: Number of professional, technical and vocational education and training institutions with improved capacity to deliver training and assessments with UNDP support, with a focus on women, young people, veterans, persons with disabilities, IDPs, returnees, minorities, the Roma community and other vulnerable groups. Baseline: 142 Target (2029): 300 Project Output 5: Government recovery coordination CPD Output: 1.1: National and subnational institutions have strengthened capacities on recovery and development processes, including planning, implementation, coordination, aid effectiveness, and monitoring and evaluation. CPD Output Indicator: Number of institutions with gender-responsive resilient recovery and development strategies or plans in crisis and post-crisis settings, including stabilization and mine action, informed by joint assessments. Baseline: National (2024): 1 Subnational (2024): 10 Target: National (2029): 2 Subnational (2024): 30 CPD Output 1.3 State institutions and civil society organizations have increased capacities to prevent and address corruption and promote participation, transparency and accountability. CPD Output Indicator: Number of institutions with strengthened accountability (including social accountability), prevent and mitigate corruption risks, and integrate anti-corruption in the management of public funds, service delivery and other sectors. Baseline (2024): 121 Target (2029): 550 Project Output 6: Access to Justice and Human Rights CPD Output 1.2: Effective, impartial and transparent institutions ensure access to justice, rule of law and promotion and protection of human rights, including in the context of war. CPD Output Indicator: Number of people supported, who have increased access to justice and legal aid. Baseline (2024): Female:141,415 Male: 89,070 Target (2029): Female: 700,000 Male: 430,000

Applicable Output(s) from the UNDP Strategic Plan: 1.3 Access to basic services and financial and non-financial assets and services improved to support productive capacities for sustainable livelihoods and jobs to achieve prosperity 3.3 Risk informed and gender-responsive recovery solutions, including stabilization efforts and mine action, implemented at regional, national and sub-national levels And full alignment with UNDP Resilience and Recovery Programme/Framework and 4R Strategies

| EXPECTED OUTPUTS | OUTPUT INDICATORS | DATA SOURCE | BASELINE (Emergency grant aid project, JSB 2022, and temporary achievement of ongoing JSB 2023) |  |  | ## TARGETS | ## DATA COLLECTION METHODS & RISKS |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Value | Year |  | ## FINAL |  |  |
| Output 1 Critical infrastructures and facilities restored to meet immediate needs to provide essential public services to prompt recovery and resilience | 1.1 Number of assessment/analysis report conducted to identify essential needs | UNDP Report/ Survey | 0 | 2024 |  | 1 | Data collection based on project records Minimal risks |  |
|  | 1.2 Number of communities municipalities benefited from rehabilitated infrastructure | UNDP Report/ Survey | 57 | 2024 |  | 61 (4 in addition to the baseline) | Data collection based on project records Minimal risks |  |
|  | 1.3 Number of infrastructures benefitting from repair and maintenance of technical Supports | UNDP Report/ Survey | 14 | 2024 |  | 16 (2 in addition to the baseline) | Data collection based on project records Minimal risks |  |
| Output 2 Debris management system in Ukraine improved through the safe removal and recycling of debris and environmentally-sound management of hazardous waste and materials | 2.1 Total tons of debris surveyed and removed | UNDP Report/ Survey | 264,503 | 2024 |  | 364,503 (100,000 in addition to the baseline) | Data collection based on project records Minimal risks |  |
|  | 2.2 Number of sites demolished and removed | UNDP Report/ Survey | 2,040 | 2024 |  | 2,240 (200 in addition to the baseline) | Data collection based on project records Minimal risks |  |
|  | 2.3 Number of communities benefited by debris removal activities (including provision of equipment for debris recycling/waste management activities, etc.) | UNDP Report/ Survey | 13 | 2024 |  | 21 (8 in addition to the baseline) | Data collection based on project records Minimal risks |  |
|  | 2.4 Number of storages and recycle sites prepared | UNDP Report/ Survey | 0 | 2024 |  | 3 | Data collection based on project records Minimal risks |  |
|  | 2.5 Total tons of concrete debris recycled/crushed and tested for the reuse purposed | UNDP Report/ Survey | 0 | 2024 |  | 50,000 | Data collection based on project records Minimal risks |  |
|  | 2.6 Number of people reached out by awareness campaigns on asbestos containing materials | UNDP Report/ Survey | 0 | 2024 |  | 2,000,000 (at least 50% women) | Data collection based on project records Minimal risks |  |
|  | 2.7 Proportion (%) of women employed in debris management role | UNDP Report/ Survey | 5% | 2024 |  | 20% | Data collection based on project records Minimal risks |  |
| Output 3 Capacities of mine action authorities, local communities, and service providers expanded to protect the population affected by war, including veterans, and secure a safe environment for people’s living and socio-economic activities | 3.1 Number of the locations which are NTS/EO surveyed and if necessary, cleared from EO | UNDP Report/ Survey | 1,227 | 2024 |  | 2,227 (1,000 in addition to the baseline) | Data collection based on project records Minimal risks |  |
|  | 3.2 Number of direct beneficiaries of EORE sessions | UNDP Report/ Survey | 1,310 | 2024 |  | 6,310 (5,000 in addition to the baseline-at least 50% women) | Data collection based on project records Minimal risks |  |
|  | 3.3 Number of local Mine Action actors (organizations/companies etc) that benefitted from capacity building (professional orgs, dealing with Mine action) | UNDP Report/ Survey | 0 | 2024 |  | 4 | Data collection based on project records Minimal risks |  |
|  | 3.4 Number of trained persons on war victim assistance | UNDP Report/ Survey | 3,307 | 2024 |  | 3,607 (300 in addition to the baseline-at least 50% women) | Data collection based on project records Minimal risks |  |
|  | 3.5 Number of persons who receive direct services related to war victim assistance | UNDP Report/ Survey | 6,815 | 2024 |  | 8,115 (1,300 in addition to baseline) *No gender target set as this will be provided on needs-basis. | Data collection based on project records Minimal risks |  |
|  | 3.6 Population in select communities with enhanced services on war victim assistance | UNDP Report/ community’ data | 0 | 2024 |  | 10,000 | Data collection based on project records Minimal risks |  |
|  | 3.7 Number of communities with enhanced services on war victim assistance | UNDP Report/ Survey | 37 | 2024 |  | 41 (4 in addition to the baseline) | Data collection based on project records Minimal risks |  |
|  | 3.8 Number of persons with raised awareness on services and support programmes within war victim assistance | UNDP Report/ Survey | 3,170,051 | 2024 |  | 3,270,051 (100,000 in addition to the baseline-at least 50% women) | Data collection based on project records Minimal risks |  |
| Output 4 Economic recovery in the targeted regions and key sectors promoted by fostering self-employment and entrepreneurship, enhancing employment of the war affected population and improving business enabling environment | 4.1 Number of self-employed and entrepreneurs supported in starting up and/or developing businesses | UNDP Report/ Survey | 273 | 2024 | 1,273 (1,000 in addition to the baseline-at least 60% women) |  | Data collection based on project records Minimal risks |  |  |
|  | 4.2 Number of women and men with improved employability | UNDP Report/ Survey | 444 | 2024 | 3,444 (3,000 in addition to baseline, at least 60% women) |  | Data collection based on project records Minimal risks |  |  |
|  | 4.3 Number of MSMEs benefiting from enhanced enabling environment and market access | UNDP Report/ Survey | 0 | 2024 | 2,000 (at least 30% woman led businesses) |  | Data collection based on project records Minimal risks |
| Output 5 Integrity, transparency, and accountability of government mechanisms and processes for crisis management and inclusive recovery strengthened at both national and sub-national levels, empowering citizen participation and engagement, including vulnerable groups, youth, veterans, and women | 5.1. Number of national and sub-national authorities that embed crisis management and recovery coordination expertise, including anti-corruption measures | UNDP Report/ Survey | 9 at national level 0 at regional level 38 at local level | 2024 | 9 at national level (target: 3 entities already counted in the baseline) 2 at regional level 38 at local level (target: 8 communities already counted in the baseline) |  | Data collection based on project records Minimal risks |  |
|  | 5.2 Number of policy papers, research studies, recommendations, and guidelines developed | UNDP Report/ Survey | 22 | 2024 |  | 26 (4 in addition to the baseline) | Data collection based on project records Minimal risks |  |
|  | 5.3. Number of public servants (men and women) at national and sub-national levels with improved capacity on countering disinformation, anti-corruption, strategic planning and project cycle management | UNDP Report/ Survey | 1,440 | 2024 |  | 1,840 (400 in addition to the baseline-at least 40% women) | Data collection based on project records Minimal risks |  |
| Output 6 Accessibility, inclusiveness and accountability of justice system and human rights protection mechanisms with enhanced capacities to apply people-centered, gender sensitive approach increased ensuring better protection and support to all people, with a focus on war affected and vulnerable groups | 6.1.1. Number of people serviced by legal service providers trained by the project 6.1.2 Number of trained legal services providers | UNDP Report/ Survey | 6.1.1: 352,118 6.1.2: 2,052 |  |  | 6.1.1: 452,118 (100,000 in addition to the baseline-at least 60% women) 6.1.2: 2,252 (200 in addition to the baseline-at least 60% women) | Data collection based on FLAS’s NHRI’s and CSOs’ records Minimal risks |  |
|  | 6.2 Number of trained prosecutors and investigators | UNDP Report/ Survey | 537 | 2024 |  | 637 (100 in addition to the baseline-at least 40% women) | Data collection based on project records Minimal risks |  |
|  | 6.3 Number courts monitored and provided with recommendations on increasing accountability and transparency | UNDP Report/ Survey | 0 | 2024 |  | 80 | Data collection based on project records Minimal risks |  |

# Monitoring And Evaluation

Monitoring Plan

| Monitoring Activity | Purpose | Frequency | Expected Action |
| --- | --- | --- | --- |
| Track results progress | Progress data against the results indicators in the RRF will be collected and analysed to assess the progress of the project in achieving the agreed outputs. | Quarterly, or in the frequency required for each indicator. | Slower than expected progress will be addressed by project management. |
| Monitor and Manage Risk | Identify specific risks that may threaten achievement of intended results. Identify and monitor risk management actions using a risk log. This includes monitoring measures and plans that may have been required as per UNDP’s Social and Environmental Standards. Audits will be conducted in accordance with UNDP’s audit policy to manage financial risk. | Quarterly | Risks are identified by project management and actions are taken to manage risk. The risk log is actively maintained to keep track of identified risks and actions taken. |
| Learn | Knowledge, good practices and lessons will be captured regularly, as well as actively sourced from other projects and partners and integrated back into the project. | At least annually | Relevant lessons are captured by the project team and used to inform management decisions. |
| Project Quality Assurance (QA) | The quality of the project will be assessed against UNDP’s quality standards to identify project strengths and weaknesses and to inform management decision making to improve the project. | Design and Appraisal QA (at the project kick-off) Closure QA (at operational closure of the project) | Areas of strength and weakness will be reviewed by project management and used to inform decisions to improve project performance. |
| Review and Make Course Corrections | Internal review of data and evidence from all monitoring actions to inform decision making. | At least annually | Performance data, risks, lessons and quality will be discussed by the project board and used to make course corrections. |
| Project Report | A progress report will be presented to the Project Board and key stakeholders, consisting of progress data showing the results achieved against pre-defined annual targets at the output level, the annual project quality rating summary, an updated risk long with mitigation measures, and any evaluation or review reports prepared over the period. | Annually, and at the end of the project (final report) | The donor partner and the key stakeholders will be informed about the progress of the project activities, challenge, and lessons learnt. |
| Project Review (Project Board) | The project’s governance mechanism (i.e., project board) will hold regular project reviews to assess the performance of the project and review the Annual Work Plan to ensure realistic budgeting over the life of the project. In the project’s final year, the Project Board shall hold an end-of project review to capture lessons learned and discuss opportunities for scaling up and to socialize project results and lessons learned with relevant audiences. | Mid-term and End of Project Duration | Any quality concerns or slower than expected progress should be discussed either through the stakeholder meetings or by the project board and management actions agreed to address the issues identified. |

# Multi-Year Work Plan & Budget

| EXPECTED OUTPUTS | PLANNED ACTIVITIES | Activity Timeframe |  |  |  | RESPONSIBLE PARTIES | PLANNED BUDGET (Mar 2025-Mar 2026) |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | US$ Amount |
| Output 1: Critical infrastructures and facilities restored to meet immediate needs to provide essential public services to prompt recovery and resilience Gender Marker: 2 | 1.1. Formulate a critical infrastructure restoration plan for the target community | X |  |  |  | Ministry of Infrastructure, Relevant Line Ministries, Ministry of Energy, State Energy Enterprises, Municipal authorities | 100,000 |
|  | 1.2. Rehabilitate/construct key infrastructures and provide necessary equipment for energy, critical utilities and other public services |  | X | X | X |  | 7,600,000 |
|  | 1.3 Provide technical and quality assurance support to the construction and maintenance of infrastructures and installation of the equipment. | X | X | X | X |  | 300,000 |
|  | Sub-Total for Output 1 |  |  |  |  |  | 8,000,000 |
| Output 2: Debris management system in Ukraine improved through debris, waste and environmentally hazardous materials removal, safe demolition of dangerous damaged structures, technical support to local authorities, development of local market for recycling capabilities, and raising awareness of hazardous material treatment. Gender Marker: 2 | 2.1. Conduct debris assessments, develop a GIS/MIS database to estimate volumes and capture progress and implement debris removal and demolition work | X |  | X | X | Ministry for Communities and Territories Development, Ministry of Environmental Protection and Natural Resources, Ministry of Health, Oblast Military Administrations, Environmental Recycling Association of Ukraine, Territorial Community Administrations and City authorities | 2,220,000 |
|  | 2.2 Strengthen the capacity of national/sub-national/local authorities in sustainable management of debris, recycling, and hazardous materials |  |  | X | X |  | 840,000 |
|  | 2.3 Promote debris recycling by piloting a recycling process, incl. carrying out crushing operations, testing recycled materials, and developing national standards for demolition management and reuse in Ukraine |  |  | X | X |  | 1,440,000 |
|  | 2.4 Strengthen the capacity of government authorities for hazardous materials management, particularly on asbestos, by developing technical guidelines, providing equipment, and conducing awareness campaigns in partnership with women’s CSOs. | X |  | X | X |  | 500,000 |
|  | Sub-Total for Output 2 |  |  |  |  |  | 5,000,000 |

| EXPECTED OUTPUTS | PLANNED ACTIVITIES | Activity Timeframe |  |  |  | RESPONSIBLE PARTIES |  | PLANNED BUDGET (Mar 2025-Mar 2026) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  |  | US$ Amount |
| Output 3: Capacities of mine action authorities, local communities, and service providers expanded to protect the population affected by war, including veterans, and secure a safe environment for people’s living and socio-economic activities Gender Marker: 2 | 3.1: Conduct Non-Technical Survey (NTS) in 2 targeted oblasts. |  | X | X | X | Ministry of Economy of Ukraine, National Mine Action Authority, State Emergency Service of Ukraine (SESU) and local authorities | 1,000,000 |  |
|  | 3.2: Conduct EORE for affected and at-risk communities and around sites. |  | X | X | X |  | 450,000 |  |
|  | 3.3: Strengthen mine action policy and build national institutional capacity through bilateral and triangular cooperation, knowledge exchange |  |  | X |  |  | 50,000 |  |
|  | 3.4: Strengthen policy framework and practice for community-based social services, health, inclusive education, physical and mental rehabilitation, assistive technology services for war-affected populations, including persons with disabilities and veterans within the framework of Victims Assistance | X | X | X | X | Ministryy of Social Policy, Ministry of Internal Affairs. State Emergency Service of Ukraine (SESU). Local authorities. CSOs | 1,500,000 |  |
|  | Sub-Total for Output 3 |  |  |  |  |  | 3,000,000 |  |
| Output 4: Economic recovery in the targeted regions and key sectors promoted by fostering self-employment and entrepreneurship, enhancing employment of the war affected population and improving business enabling environment Gender Marker: 2 | 4.1: Support war-affected self-employed and entrepreneurs to start-up and develop businesses in the key value chains of the targeted oblasts. | X | X | X | X | Ministry of Economy, Ministry of Digital Transformation, Ministry of Education and Science, Ministry of Restoration, State Employment Service, State Regulatory Service, Entrepreneurship and Export Promotion Office | 1,180,000 |  |
|  | 4.2: Foster inclusive employment for the war-affected women and men, including veterans and people with disabilities, in targeted sectors | X | X | X | X |  | 1,020,000 |  |
|  | 4.3: Improve conditions and enabling environment for entrepreneurs and MSMEs by strengthening business-support ecosystem, advancing market access and enhancing policy frameworks | X | X | X | X |  | 1,800,000 |  |
|  | Sub-Total for Output 4 |  |  |  |  |  | 4,000,000 |  |

| EXPECTED OUTPUTS | PLANNED ACTIVITIES | Activity Timeframe |  |  |  |  |  | RESPONSIBLE PARTIES |  | PLANNED BUDGET (Mar 2025-Mar 2026) |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 |  | Q4 |  |  |  |  | US$ Amount |
| Output 5: Integrity, transparency, and accountability of government mechanisms and processes for crisis management and inclusive recovery strengthened at both national and sub-national levels, empowering citizen participation and engagement, including vulnerable groups, youth, veterans, and women. Gender Marker: 2 | 5.1: Support the Government and sub-national authorities in enhancing crisis response, multi-level governance collaboration, and institutional capacity | X | X | X |  | X |  | Secretariat of the Cabinet of Ministers of Ukraine, Ministry of Communities and Territories Development of Ukraine, Ministry of Digital Transformation, Ministry of Foreign Affairs, Ministry of Culture and Strategic Communications, Ministry of Social Policy, Ministry of Economy, Ministry of Youth and Sports, regional administrations, local communities, civil society organizations, including women’s organizations and other relevant institutions. |  | 783,700 |  |
|  | 5.2: Strengthen the capacities of the government at both national and subnational levels in institutional effectiveness, strategic planning, policy development, and coordination | X | X | X |  | X |  |  |  | 257,500 |  |
|  | 5.3: Enhance integrity, transparency, and accountability and support anti-corruption initiatives in Ukraine’s recovery and development processes. | X | X | X |  | X |  |  |  | 401,800 |  |
|  | 5.4 Strengthen informational resilience, and unity of the government and population with enhancing capacities for disinformation, media literacy, and strategic communications | X | X | X |  | X |  |  |  | 557,000 |  |
|  | Sub-Total for Output 5 |  |  |  |  |  |  |  |  | 2,000,000 |  |
| Output 6: Accessibility, inclusiveness and accountability of justice system and human rights protection mechanisms with enhanced capacities to apply people-centered, gender sensitive approach increased ensuring better protection and support to all people, with a focus on war affected and vulnerable groups. Gender Marker: 2 | 6.1 Develop capacities of justice system actors and legal service providers for enabling full and people-centred access to justice and human rights protection instruments to provide justice services in an effective, inclusive, non-discriminatory manner. | X | X | X |  | X |  | General Prosecutor Office, Ombudsperson’s Office, Free Legal Aid Coordination Center under the Ministry of Justice, Ministry of Internal Affairs, National Police, civil society organizations, including women’s organizations and other relevant institutions. |  | 568,260 |  |

|  | 6.2 Enhance the national justice mechanisms for enabling the removal of barriers for survivors of war crimes, including CRSV through strengthening capacity of prosecutors, investigators, police officers and legal service providers at sub-national level. | X | X | X |  | X |  |  | 681,740 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 6.3 Increase transparency and accountability of justice system with ensuring openness and accessibility to public information and open data in judiciary. |  | X | X |  | X |  |  | 250,000 |
|  | Sub-Total for Output 6 |  |  |  |  |  |  |  | 1,500,000 |
| Programme Management (incl. DPC) |  |  |  |  |  |  |  |  | 3,644,950 |
| General Management Support (8%) |  |  |  |  |  |  |  |  | 2,171,596 |
| TOTAL |  |  |  |  |  |  |  |  | 29,316,546 |

*1% RCO Levy will not be applied due to the humanitarian nature of the project.

# Governance and Management Arrangements

The Project will be governed by the Project Board (PB), which will be responsible for making decisions, in particular when guidance is required by the Project Manager (PM). The Board will play a critical role in project monitoring and evaluations by assuring the quality of these processes and associated products, and by using evaluations for improving performance, accountability and learning. The PB will ensure that required resources are committed. It will also arbitrate on any conflicts within the project and negotiate solutions to any problems with external bodies. The PB meetings are to be organized at least in the mid-term and at the end of the project duration, or to be convened upon necessity. The PB shall be make its decisions in accordance with international standards that shall ensure management for development results, best value for money, fairness, integrity, transparency, and effective international competition. Members of the PB will consist of key national/local government representatives, UNDP senior official, Project Management Team, the donor (i.e., Government of Japan) as well as representative from Civil Society Organization (CSO) and other relevant stakeholders, if necessary.  Potential members of the PB will be reviewed and recommended for approval during the Local Project Appraisal Committee (LPAC) meeting. New members or ad-hoc participants can be invited to the PB upon the decision of the Board.

To ensure that the Board will remain sufficiently lean to facilitate its effective operation, the PB will be comprised of members with the roles of the Executive, Senior Supplier, Senior Beneficiary and Quality Assurance.

- Executive Role: The role of the Executive will be held by the UNDP and the representative of the government of Ukraine. The Executive is ultimately responsible for the project, assisted by the Senior Beneficiary and Senior Supplier. The Executive’s role is to ensure that the Project is focused throughout its life cycle on achieving its expected results and delivering outputs that will contribute to longer-term impact. The Executive should ensure that the Project gives value for money, ensuring a cost-conscious approach, and balancing the demands of beneficiary and supplier.

- Senior Beneficiary Role: This role requires representing the interests of those who will ultimately benefit from the project. The Senior Beneficiary’s primary function within the Board will be to ensure the realization of project results from the perspective of different stakeholders and beneficiaries.

- Senior Supplier Role: Donor or technical partners will hold the role of Senior Supplier.  The Senior Supplier represents the interests of the parties which provide funding and/or technical expertise to the Project (designing, developing, facilitating, procuring, implementing). The Senior Supplier role must have the authority to commit or acquire supplier resources as required.

- Quality Assurance Role: The Quality Assurance role supports the Executive role of the PB and is assumed  by UNDP Ukraine and by the UNDP HQ, wherever appropriate. The role ensures independent oversight and monitoring functions on behalf of the PB. This role ensures that appropriate programme management milestones are managed and completed.

In the framework of the governance structure of the PB, the Project Implementation Team (PIT) will be established and will comprise of Project Manager, the experts for the respective areas, who will be responsible for carrying out the activities with technical soundness, and project implementation support staff, including M&E, Communications, Finance, Human Resources, Procurement and other general administration. Under DIM modality of this project, UNDP Ukraine will serve as an implementing partner and is accountable for design, oversight and quality assurance for implementation of this project. Considering a crisis setting that requires flexibility and innovation in Ukraine, UNDP will be granted within 20% tolerance for the permissible deviation from the initial project annual work plan.

# Legal Context

This project document shall be the instrument referred to as such in Article 1 of the Standard Basic Assistance Agreement between the Government of (country) and UNDP, signed on (date).   All references in the SBAA to “Executing Agency” shall be deemed to refer to “Implementing Partner.”

This project will be implemented by UNDP (“Implementing Partner”) in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

# Risk Management

- UNDP as the Implementing Partner will comply with the policies, procedures and practices of the United Nations Security Management System (UNSMS.)

- UNDP as the Implementing Partner will undertake all reasonable efforts to ensure that none of the [project funds] [UNDP funds received pursuant to the Project Document] are used to provide support to individuals or entities associated with terrorism , that the recipients of any amounts provided by UNDP hereunder do not appear on the United Nations Security Council Consolidated Sanctions List, and that no UNDP funds received pursuant to the Project Document are used for money laundering activities. The United Nations Security Council Consolidated Sanctions List can be accessed via https://www.un.org/securitycouncil/content/un-sc-consolidated-list. This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document.

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

- UNDP as the Implementing Partner will: (a) conduct project and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

- In the implementation of the activities under this Project Document, UNDP as the Implementing Partner will handle any sexual exploitation and abuse (“SEA”) and sexual harassment (“SH”) allegations in accordance with its regulations, rules, policies and procedures.

- All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any programme or project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

- UNDP as the Implementing Partner will ensure that the following obligations are binding on each responsible party, subcontractor, and sub-recipient:

  - Consistent with the Article III of the SBAA [or the Supplemental Provisions to the Project Document], the responsibility for the safety and security of each responsible party, subcontractor and sub-recipient and its personnel and property, and of UNDP’s property in such responsible party’s, subcontractor’s and sub-recipient’s custody, rests with such responsible party, subcontractor and sub-recipient.  To this end, each responsible party, subcontractor and sub-recipient shall:

    - put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

    - assume all risks and liabilities related to such responsible party’s, subcontractor’s and sub-recipient’s security, and the full implementation of the security plan.

  - UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the responsible party’s, subcontractor’s and sub-recipient’s obligations under this Project Document.

  - Each responsible party, subcontractor and sub-recipient (each a “sub-party” and together “sub-parties”) acknowledges and agrees that UNDP will not tolerate sexual harassment and sexual exploitation and abuse of anyone by the sub-parties, and other entities involved in Project implementation, either as contractors or subcontractors and their personnel, and any individuals performing services for them under the Project Document.

(a) In the implementation of the activities under this Project Document, each sub-party shall comply with the standards of conduct set forth in the Secretary General’s Bulletin ST/SGB/2003/13 of 9 October 2003, concerning “Special measures for protection from sexual exploitation and sexual abuse” (“SEA”).

(b) Moreover, and without limitation to the application of other regulations, rules, policies and procedures bearing upon the performance of the activities under this Project Document, in the implementation of activities, each sub-party, shall not engage in any form of sexual harassment (“SH”). SH is defined as any unwelcome conduct of a sexual nature that might reasonably be expected or be perceived to cause offense or humiliation, when such conduct interferes with work, is made a condition of employment or creates an intimidating, hostile or offensive work environment. SH may occur in the workplace or in connection with work. While typically involving a pattern of conduct, SH may take the form of a single incident. In assessing the reasonableness of expectations or perceptions, the perspective of the person who is the target of the conduct shall be considered.

  - In the performance of the activities under this Project Document, each sub-party shall (with respect to its own activities), and shall require from its sub-parties (with respect to their activities) that they, have minimum standards and procedures in place, or a plan to develop and/or improve such standards and procedures in order to be able to take effective preventive and investigative action. These should include: policies on sexual harassment and sexual exploitation and abuse; policies on whistleblowing/protection against retaliation; and complaints, disciplinary and investigative mechanisms. In line with this, sub-parties will and will require that their respective sub-parties will take all appropriate measures to:

(i) Prevent its employees, agents or any other persons engaged to perform any services under this Project Document, from engaging in SH or SEA;

(ii) Offer employees and associated personnel training on prevention and response to SH and SEA, where sub-parties have not put in place its own training regarding the prevention of SH and SEA, sub-parties may use the training material available at UNDP;

(iii) Report and monitor allegations of SH and SEA of which any of the sub-parties have been informed or have otherwise become aware, and status thereof;

(iv) Refer victims/survivors of SH and SEA to safe and confidential victim assistance; and

(v) Promptly and confidentially record and investigate any allegations credible enough to warrant an investigation of SH or SEA. Each sub-party shall advise UNDP of any such allegations received and investigations being conducted by itself or any of its sub-parties with respect to their activities under the Project Document, and shall keep UNDP informed during the investigation by it or any of such sub-parties, to the extent that such notification (i) does not jeopardize the conduct of the investigation, including but not limited to the safety or security of persons, and/or (ii) is not in contravention of any laws applicable to it. Following the investigation, the relevant sub-party shall advise UNDP of any actions taken by it or any of the other entities further to the investigation.

  - Each sub-party shall establish that it has complied with the foregoing, to the satisfaction of UNDP, when requested by UNDP or any party acting on its behalf to provide such confirmation. Failure of the relevant sub-party to comply of the foregoing, as determined by UNDP, shall be considered grounds for suspension or termination of the Project.

  - Each responsible party, subcontractor and sub-recipient will ensure that any project activities undertaken by them will be implemented in a manner consistent with the UNDP Social and Environmental Standards and shall ensure that any incidents or issues of non-compliance shall be reported to UNDP in accordance with UNDP Social and Environmental Standards.

  - Each responsible party, subcontractor and sub-recipient will take appropriate steps to prevent misuse of funds, fraud, corruption or other financial irregularities, by its officials, consultants, subcontractors and sub-recipients in implementing the project or programme or using the UNDP funds.  It will ensure that its financial management, anti-corruption, anti-fraud and anti-money laundering and countering the financing of terrorism policies are in place and enforced for all funding received from or through UNDP.

  - The requirements of the following documents, then in force at the time of signature of the Project Document, apply to each responsible party, subcontractor and sub-recipient: (a) UNDP Policy on Fraud and other Corrupt Practices (b) UNDP Anti-Money Laundering and Countering the Financing of Terrorism Policy; and (c) UNDP Office of Audit and Investigations Investigation Guidelines. Each responsible party, subcontractor and sub-recipient agrees to the requirements of the above documents, which are an integral part of this Project Document and are available online at www.undp.org.

  - In the event that an investigation is required, UNDP will conduct investigations relating to any aspect of UNDP programmes and projects. Each responsible party, subcontractor and sub-recipient will provide its full cooperation, including making available personnel, relevant documentation, and granting access to its (and its consultants’, subcontractors’ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with it to find a solution.

  - Each responsible party, subcontractor and sub-recipient will promptly inform UNDP as the Implementing Partner in case of any incidence of inappropriate use of funds, or credible allegation of fraud, corruption other financial irregularities with due confidentiality.

Where it becomes aware that a UNDP project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption, each responsible party, subcontractor and sub-recipient will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). It will provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

  - UNDP will be entitled to a refund from the responsible party, subcontractor or sub-recipient of any funds provided that have been used inappropriately, including through fraud corruption or other financial irregularities, or otherwise paid other than in accordance with the terms and conditions of the Project Document.  Such amount may be deducted by UNDP from any payment due to the responsible party, subcontractor or sub-recipient under this or any other agreement. (Option 3)

Where such funds have not been refunded to UNDP, the responsible party, subcontractor or sub-recipient agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Project Document, may seek recourse to such responsible party, subcontractor or sub-recipient for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud, corruption or other financial irregularities, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Note:  The term “Project Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Project Document, including those with responsible parties, subcontractors and sub-recipients.

  - Each contract issued by the responsible party, subcontractor or sub-recipient in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from it shall cooperate with any and all investigations and post-payment audits.

  - Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the project or programme, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

  - Each responsible party, subcontractor and sub-recipient shall ensure that all of its obligations set forth under this section entitled “Risk Management” are passed on to its subcontractors and sub-recipients and that all the clauses under this section entitled “Risk Management Standard Clauses” are adequately reflected, mutatis mutandis, in all its sub-contracts or sub-agreements entered into further to this Project Document.

ANNEX 1: PROJECT QUALITY ASSURANCE – DESIGN FOR JSB FY2024

### Project Information

| Project Information |  |
| --- | --- |
| 1. Project Title | Inclusive Recovery Support for Resilience and Human Security in Ukraine (JSB FY2024) |
| 2. Project Number (i.e. Quantum project ID, PIMS+) | 01003977 |
| 3. Location (Global/Region/Country) | Country |
| 4. Project stage (Design or Implementation) | Design |
| 5. Date | 09 February 2025 |

| ☒ | PROJECT QA - DESIGN |
| --- | --- |
|  | 1. Strategic |
|  | 1. Does the project specify how it will contribute to higher level change through linkage to the programme’s Theory of Change? |
| ☒ | - 3: The project is clearly linked to the programme’s theory of change. It has an explicit change pathway that explains how the project will contribute to outcome level change and why the project’s strategy will likely lead to this change. This analysis is backed by credible evidence of what works effectively in this context and includes assumptions and risks. |
| ☐ | - 2: The project is clearly linked to the programme’s theory of change. It has a change pathway that explains how the project will contribute to outcome-level change and why the project strategy will likely lead to this change. |
| ☐ | - 1: The project document may describe in generic terms how the project will contribute to development results, without an explicit link to the programme’s theory of change. *Note: Projects not contributing to a programme must have a project-specific Theory of Change. See alternative question under the information icon for these cases. |
|  | Evidence (Enter a short explanation and attached a document that provides evidence for your response): The project is clearly linked to the programme’s Theory of Change, earning a score of 3. It has an explicit change pathway that outlines how it will contribute to outcome-level change. The project aims to enhance human security in Ukraine by addressing interconnected threats through comprehensive and multidimensional interventions. These interventions are based on the principles of freedom from fear, want, and the freedom to live in dignity, aligning with the Country Programme Document (CPD) for UNDP Ukraine for 2025-2029. The project employs an area-based programming methodology and a build-back-better approach to implement integrated, multi-sector interventions in six thematic areas. This strategy is designed to address the complex nature of the crises in Ukraine with a holistic, multi-sectoral perspective, ensuring that the project contributes to higher-level change. The analysis is backed by credible evidence of what works effectively in this context, including assumptions and risks associated with the interventions. The project emphasizes participatory and inclusive consultation methodologies to design interventions that respond to the identified priority needs in the respective oblasts, linking immediate and short-term needs with transformational impacts. Overall, the project’s comprehensive approach, supported by robust governance and evidence-based strategies, ensures its contribution to higher-level change in Ukraine, making it a strong example of a project aligned with the programme’s Theory of Change. Attachment: Project Document |
|  | 2. Is the project aligned with the UNDP Strategic Plan? |
| ☒ | - 3: The project responds to at least one of the development settings as specified in the Strategic Plan and adapts at least one Signature Solution. The project’s RRF includes all the relevant SP output indicators. (all must be true) |
| ☐ | - 2: The project responds to at least one of the development settings as specified in the Strategic Plan. The project’s RRF includes at least one SP output indicator, if relevant. (both must be true) |
| ☐ | - 1: The project responds to a partner’s identified need, but this need falls outside of the UNDP Strategic Plan. Also select this option if none of the relevant SP indicators are included in the RRF. |
|  | Evidence (Enter a short explanation and attached a document that provides evidence for your response): The project is well-aligned with the UNDP Strategic Plan, earning a score of 3. It responds to the development settings specified in the Strategic Plan by addressing critical areas such as access to basic services, risk-informed recovery solutions, and gender-responsive interventions. These align with the UNDP's focus on enhancing productive capacities for sustainable livelihoods and implementing recovery solutions at various levels. The project adapts at least one Signature Solution by focusing on risk-informed and gender-responsive recovery solutions, which are integral to the UNDP's strategic priorities. This approach ensures that the project not only addresses immediate recovery needs but also contributes to long-term resilience and sustainable development in Ukraine. Furthermore, the project's Results and Resources Framework (RRF) includes all relevant Strategic Plan output indicators, ensuring that the project's outcomes are measurable and aligned with UNDP's broader strategic objectives. This alignment is evident in the project's emphasis on enhancing institutional capacities, promoting inclusive governance, and fostering sustainable development practices. Overall, the project's comprehensive approach, which integrates key elements of the UNDP Strategic Plan, ensures that it effectively contributes to the organization's overarching goals. By addressing both immediate and long-term needs, the project supports Ukraine's recovery and development in a manner consistent with UNDP's strategic vision. Attachment: Project Document |
|  | 3. Is the project linked to the programme outputs? (i.e., UNSDCF/CPD, RPD or Strategic Plan IRRF for strategic interventions not part of a programme) |
| ☒ | - Yes |
| ☐ | - No (Project QA cannot be approved by the Project QA Approver) |
|  | Evidence (Enter a short explanation and attached a document that provides evidence for your response): The project is linked to the programme outputs, specifically the United Nations Sustainable Development Cooperation Framework (UNSDCF) and the Country Programme Document (CPD) for Ukraine. The project aligns with several CPD outputs, such as enhancing institutional capacities for recovery and development processes, promoting economic recovery through gender-responsive infrastructure rehabilitation, and strengthening access to justice and human rights. The project also contributes to the UNSDCF outcomes, including fostering peace, justice, and strong institutions, promoting economic recovery and decent work, and ensuring inclusive and sustainable management of natural resources. These alignments demonstrate the project's strategic integration with broader UNDP and UN objectives, ensuring that its interventions contribute to the overarching goals of sustainable development and resilience in Ukraine. Attachment: Project Document |
|  | 2. Relevant |
|  | 4. Does the project identity target groups, and particularly those marginalized, vulnerable and left further behind (LNOB)? |
| ☒ | - 3: The target groups are clearly specified, prioritising discriminated, and marginalized groups left furthest behind, identified through a rigorous process based on evidence. |
| ☐ | - 2: The target groups are clearly specified, prioritizing groups left furthest behind. |
| ☐ | - 1: The target groups are not clearly specified. |
|  | Evidence (Enter a short explanation and attached a document that provides evidence for your response): The project clearly specifies its target groups, prioritizing those who are marginalized and left furthest behind, thus earning a score of 3. The project identifies war-affected populations, including women, youth, people with disabilities (PwDs), internally displaced persons (IDPs), and veterans, as its primary beneficiaries. These groups are prioritized due to their heightened vulnerability and the disproportionate impact of the ongoing conflict on their livelihoods and well-being. The identification of these target groups is based on a rigorous process that involves evidence-based assessments and consultations with stakeholders. This approach ensures that the interventions are tailored to address the specific needs and challenges faced by these marginalized groups. The project employs participatory and inclusive consultation methodologies to design interventions that are responsive to the identified priority needs in the respective oblasts, ensuring that no one is left behind. Furthermore, the project emphasizes enhancing employment opportunities, promoting inclusiveness, and ensuring the relevance of workforce training in target areas. This is aimed at unlocking the potential of vulnerable groups, particularly those often underrepresented in the labor market, such as PwDs and veterans Attachment: Project Document |
|  | 5. Have knowledge, good practices, and past lessons learned of UNDP and others informed the project design? |
| ☒ | - 3: Knowledge and lessons learned backed by credible evidence from sources such as evaluation, corporate policies/strategies, and/or monitoring have been explicitly used, with appropriate referencing, to justify the approach used by the project. |
| ☐ | - 2: The project design mentions knowledge and lessons learned backed by evidence/sources but have not been used to justify the approach selected. |
| ☐ | - 1: There is little, or no mention of knowledge and lessons learned informing the project design. Any references made are anecdotal and not backed by evidence. |
|  | Evidence (Enter a short explanation and attached a document that provides evidence for your response): The project earns a score of 3, as it explicitly uses knowledge and lessons learned, backed by credible evidence, to inform its design, through UNDP’s experience in implementing similar projects in the past. The project draws on past experiences and best practices from UNDP's work in conflict and post-conflict environments, as well as from other countries that have faced similar challenges, such as Moldova, Armenia, and Georgia. This exchange of experiences and best practices is facilitated through cooperation with national human rights institutions (NHRIs) and other stakeholders, ensuring that the project design is grounded in proven strategies and methodologies. Furthermore, the project incorporates lessons learned from previous UNDP initiatives in Ukraine, particularly in JSB 2022 and 2023, which have same outputs as the present project. These lessons are used to justify the project's approach, ensuring that interventions are tailored to the specific needs and context of Ukraine. The project also emphasizes the importance of participatory and inclusive consultation methodologies, which have been shown to be effective in designing interventions that respond to the priority needs of marginalized and vulnerable groups.By integrating these knowledge products and lessons learned into its design, the project ensures that its strategies are evidence-based and aligned with best practices, enhancing its potential for success and sustainability. This comprehensive approach demonstrates a strong commitment to leveraging past experiences to inform and justify the project's approach, aligning with UNDP's corporate policies and strategies. Attachment: Project Document |
|  | 6. Does UNDP have a clear advantage to engage in the role envisioned by the project vis-à-vis national / regional / global partners and other actors? |
| ☐ | - 3: An analysis has been conducted on the role of other partners in the area where the project intends to work, and credible evidence supports the proposed engagement of UNDP and partners through the project, including identification of potential funding partners. It is clear how results achieved by partners will complement the project’s intended results and a communication strategy is in place to communicate results and raise visibility vis-à-vis key partners. Options for south-south and triangular cooperation have been considered, as appropriate. (all must be true) |
| ☒ | - 2: Some analysis has been conducted on the role of other partners in the area where the project intends to work, and relatively limited evidence supports the proposed engagement of and division of labour between UNDP and partners through the project, with unclear funding and communications strategies or plans. |
| ☐ | - 1: No clear analysis has been conducted on the role of other partners in the area that the project intends to work. There is risk that the project overlaps and/or does not coordinate with partners’ interventions in this area. Options for south-south and triangular cooperation have not been considered, despite its potential relevance. |
|  | Evidence (Enter a short explanation and attached a document that provides evidence for your response): UNDP holds a clear advantage to engage in the role envisioned by the project, meriting a rating of "2". This is supported by a limited analysis of the roles of other partners in the area where the project intends to work, alongside credible evidence that justifies the proposed engagement of UNDP and its partners through the project. While the prodoc contains explicit intention to collaborate with Japanese actors by mentioning their roles, such analysis on the national partners is limited. Having said that, a communication strategy is in place to effectively communicate these results and raise visibility vis-à-vis key partners, with options for south-south and triangular cooperation being considered where appropriate. The project leverages UNDP's established presence and broad partnerships at national, regional, and international levels. By working in close collaboration with line ministries and leveraging strong relations with the government and other stakeholders, UNDP ensures government authorities own and lead the entire implementation process, enhancing the sustainability of the project. This approach is underpinned by a participatory implementation strategy that engages direct beneficiaries and consults with existing community, municipality, or oblast-level advisory and advocacy bodies, ensuring local buy-in and inclusive dialogue around project action. Moreover, UNDP's strategic partnerships, particularly with Japanese actors, demonstrate a clear division of labor and synergy between UNDP and its partners. The project expands existing partnerships, demonstrating Japan’s strategic priorities and bringing knowledge, technologies, and experiences from Japan to Ukraine. This includes leveraging relationships with JICA, Japanese NGOs, and the private sector to promote economic revitalization in Ukraine. Additionally, the project's governance and management arrangements, including the establishment of a Project Board with representatives from key national/local government, UNDP, the donor (Government of Japan), and Civil Society Organizations, ensure effective decision-making, monitoring, and evaluation, further supporting the project's strategic engagement and division of labor with partners. In summary, UNDP's approach, backed by a solid analysis of partner roles, credible evidence, a comprehensive communication strategy, and consideration of south-south and triangular cooperation, underscores its clear advantage and justified engagement in the project. Attachment: Project Document, Beneficiary list, List of project board |
|  | 3. Principled |
|  | 7. Does the project apply a human rights-based approach? |
| ☐ | - 3: The project is guided by human rights and incorporates the principles of accountability, meaningful participation, and non-discrimination in the project’s strategy. The project upholds the relevant international and national laws and standards. Any potential adverse impacts on enjoyment of human rights were rigorously identified and assessed as relevant, with appropriate mitigation and management measures incorporated into project design and budget. (all must be true) |
| ☒ | - 2: The project is guided by human rights by prioritizing accountability, meaningful participation and non-discrimination. Potential adverse impacts on enjoyment of human rights were identified and assessed as relevant, and appropriate mitigation and management measures incorporated into the project design and budget. (both must be true) |
| ☐ | - 1: No evidence that the project is guided by human rights. Limited or no evidence that potential adverse impacts on enjoyment of human rights were considered. |
|  | Evidence (Enter a short explanation and attached a document that provides evidence for your response): The project clearly applies a human rights-based approach, meriting a rating of "2". It is explicitly guided by human rights principles, incorporating accountability, meaningful participation, and non-discrimination into its strategy. This is evident in the project's focus on enhancing the capacities of national and local state and non-state actors to promote human rights and ensure access to justice for all people, with a particular emphasis on internally displaced persons (IDPs) and vulnerable groups. Moreover, the project has taken steps to identify and assess any potential adverse impacts on the enjoyment of human rights rigorously through SESP. It provided detailed analysis on degree of mainstreaming of human rights-based approach, gender equality and women’s empowerment, sustainability and resilience, and accountability to stakeholders, which turn out to be well integrated in the project design. Through SESP, a robust analysis was conducted to identify potential social and environmental risks that the project might bring. The identified risks were carefully analyzed by using corporate risk register tool, allowing to evaluate its significance through degree of impact and likelihood, accompanied by mitigation and adaptation measures. The project also emphasizes the importance of integrating Heightened Human Rights Due Diligence principles and promoting transparency and accountability of justice institutions. Additionally, the project's approach to ensuring access and involvement in project activities by both women and men, considering gender in studies and recommendations, and promoting ownership by targeted local authorities and communities, further underscores its commitment to meaningful participation and non-discrimination. Attachment: Project Document, SESP |
|  | 8. Does the project use gender analysis in the project design? |
| ☐ | - 3: A participatory gender analysis has been conducted and results from this gender analysis inform the development challenge, strategy and expected results sections of the project document. Outputs and indicators of the results framework include explicit references to gender equality, and specific indicators measure and monitor results to ensure women are fully benefitting from the project. (all must be true) |
| ☒ | - 2: A basic gender analysis has been carried out and results from this analysis are scattered (i.e., fragmented and not consistent) across the development challenge and strategy sections of the project document. The results framework may include some gender sensitive outputs and/or activities but gender inequalities are not consistently integrated across each output. (all must be true) |
| ☐ | - 1: The project design may or may not mention information and/or data on the differential impact of the project’s development situation on gender relations, women and men, but the gender inequalities have not been clearly identified and reflected in the project document. |
|  | Evidence (Enter a short explanation and attached a document that provides evidence for your response): The project demonstrates a strong use of gender analysis in its design, meriting a rating of "2". While a participatory gender analysis was not conducted as part of the project's initial design phase, the project does demonstrate a strong commitment to gender mainstreaming and the consideration of gender impacts across its activities. For instance, the project emphasizes the importance of women's participation and leadership in decision-making processes related to relief and recovery activities. By involving women in needs identification and strategy development, the project ensures that their unique perspectives and contributions are leveraged, which is crucial for effective recovery efforts. Moreover, the project incorporates gender-sensitive approaches in various sectors, such as debris management. It ensures that all stages of debris management consider gender to provide equitable benefits for women, men, and marginalized groups. This includes collecting gender-disaggregated data, engaging women in decision-making, and empowering them through roles in awareness campaigns, sorting, and recycling. Additionally, the project focuses on fostering inclusive employment opportunities for war-affected women, including veterans and people with disabilities, by improving training infrastructure and delivering upskilling and reskilling training in partnership with labor market actors. Furthermore, the project enhances the accessibility, inclusiveness, and accountability of the justice system with a gender-sensitive approach, aiming to provide better protection and support to all people, with specific attention to women. The project includes gender-sensitive outputs, such as enhancing the accessibility and accountability of the justice system with a gender-sensitive approach, aiming to protect war-affected and vulnerable groups, particularly women. However, gender inequalities are not consistently integrated across all outputs. For instance, while the debris management system aims to benefit 500,000 people with at least 50% being women, the integration of gender-specific strategies and considerations is not explicitly detailed in this output, indicating a lack of consistent gender mainstreaming across all project components. Attachment: Project Document |
|  | 9. Did the project support the resilience and sustainability of societies and/or ecosystems? |
| ☒ | - 3: Credible evidence that the project addresses sustainability and resilience dimensions of development challenges, which are integrated in the project strategy and design. The project reflects the interconnections between the social, economic and environmental dimensions of sustainable development. Relevant shocks, hazards and adverse social and environmental impacts have been identified and rigorously assessed with appropriate management and mitigation measures incorporated into project design and budget. (all must be true) |
| ☐ | - 2: The project design integrates sustainability and resilience dimensions of development challenges. Relevant shocks, hazards and adverse social and environmental impacts have been identified and assessed, and relevant management and mitigation measures incorporated into project design and budget. (both must be true) |
| ☐ | - 1: Sustainability and resilience dimensions and impacts were not adequately considered. |
|  | Evidence (Enter a short explanation and attached a document that provides evidence for your response): The project earns a score of 3 for its support of resilience and sustainability. It provides credible evidence of addressing sustainability and resilience dimensions of development challenges, which are integrated into the project strategy and design. The project reflects the interconnections between social, economic, and environmental dimensions of sustainable development. For instance, it focuses on restoring critical infrastructure in the energy sector with an approach to build-back better and greener, ensuring reliable energy supply and basic utilities in war-affected areas. Additionally, the project enhances the debris management system through safe removal and recycling, promoting environmentally sound management of hazardous waste. Relevant shocks, hazards, and adverse social and environmental impacts have been identified and rigorously assessed. The project incorporates appropriate management and mitigation measures into its design and budget, such as fostering inclusive employment for war-affected populations and strengthening institutional capacities for sustainable development. By integrating these elements, the project demonstrates a comprehensive approach to promoting resilience and sustainability, addressing the multifaceted challenges faced by Ukrainian society and ecosystems in the context of recovery and development. Moreover, the project has taken steps to identify and assess any relevant shocks, hazards and adverse social and environmental impacts through SESP. Through SESP, a robust analysis was conducted to identify potential social and environmental risks that the project might bring. The identified risks were carefully analyzed by using corporate risk register tool, allowing to evaluate its significance through degree of impact and likelihood, accompanied by mitigation and adaptation measures. Attachment: Project Document, SESP |
|  | 10. Has the Social and Environmental Screening Procedure (SESP) been conducted to identify potential social and environmental impacts and risks? The SESP is not required for projects in which UNDP is Administrative Agent only and/or projects comprised solely of the preparation and dissemination of reports and communication materials; organization of events, workshops, or training; strengthening capacities of partners to participate in international negotiations and conferences; partnership coordination (including UN coordination) and management of networks; and global/regional projects with no country-level activities as well as Development Effectiveness projects and Institutional Effectiveness projects. [If SESP is not required, Select all exemption criteria that apply.] |
| ☒ | - Yes |
| ☐ | - No (Project QA cannot be approved by the Project QA Approver) |
| ☐ | - SESP not required because project consists solely of (Select all exemption criteria that apply) *Applicable only to option "SESP not required" ☐ 1: Preparation and dissemination of reports, documents and communication materials ☐ 2: Organization of an event, workshop, training ☐ 3: Strengthening capacities of partners to participate in international negotiations and conferences ☐ 4: Partnership coordination (including UN coordination) and management of networks ☐ 5: Global/regional projects with no country-level activities (e.g. activities such as knowledge management, inter-governmental processes) ☐ 6: UNDP serves as Administrative Agent ☐ 7: Development Effectiveness projects and Institutional Effectiveness projects |
|  | Evidence (Enter a short explanation and attached a document that provides evidence for your response): SESP has been conducted and is attached to the project document. Attachment: Project Document, SESP |
|  | 4. Management & Monitoring |
|  | 11. Does the project have a strong results framework? |
| ☐ | - 3: The project’s selection of outputs and activities are at an appropriate level. Outputs are accompanied by SMART, results-oriented indicators that measure the key expected development changes, each with credible data sources and populated baselines and targets, including gender sensitive, target group focused, sex-disaggregated indicators where appropriate. (all must be true) |
| ☒ | - 2: The project’s selection of outputs and activities are at an appropriate level. Outputs are accompanied by SMART, results-oriented indicators, but baselines, targets and data sources may not yet be fully specified. Some use of target group focused, sex-disaggregated indicators, as appropriate. (all must be true) |
| ☐ | - 1: The project’s selection of outputs and activities are not at an appropriate level; outputs are not accompanied by SMART, results-oriented indicators that measure the expected change and have not been populated with baselines and targets; data sources are not specified, and/or no gender sensitive, sex-disaggregation of indicators. (if any is true) |
|  | Evidence (Enter a short explanation and attached a document that provides evidence for your response): The project can be rated as a 2 for its results framework. The selection of outputs and activities is at an appropriate level, addressing critical areas such as infrastructure restoration, economic recovery, and social reintegration of war victims and veterans. The project includes SMART, results-oriented indicators to measure expected development changes. However, while some indicators are target group-focused and sex-disaggregated, the baselines, targets, and data sources are not fully specified across all outputs. For instance, the project aims to benefit 500,000 people through debris management, with at least 50% being women, but lacks detailed gender-specific strategies and considerations in this output. This indicates that while there is some use of gender-sensitive and sex-disaggregated indicators, the framework could be strengthened by fully specifying baselines, targets, and data sources for all outputs to ensure comprehensive measurement of development changes. Overall, the project demonstrates a commitment to integrating gender considerations and measuring impact, but further refinement of the results framework is needed to achieve a higher rating. Attachment: Project Document, Results Framework |
|  | 12. Is the project’s governance mechanism clearly defined in the project document, including composition of the project board? |
| ☐ | - 3: The project’s governance mechanism is fully defined. Individuals have been specified for each position in the governance mechanism (especially all members of the project board.) Project Board members have agreed on their roles and responsibilities as specified in the terms of reference. The ToR of the project board has been attached to the project document. (all must be true) |
| ☒ | - 2: The project’s governance mechanism is defined; specific institutions are noted as holding key governance roles, but individuals may not have been specified yet. The project document lists the most important responsibilities of the project board, project director/manager and quality assurance roles. (all must be true) |
| ☐ | - 1: The project’s governance mechanism is loosely defined in the project document, only mentioning key roles that will need to be filled at a later date. No information on the responsibilities of key positions in the governance mechanism is provided. |
|  | Evidence (Enter a short explanation and attached a document that provides evidence for your response): The project’s governance mechanism is rated as a 2. The governance structure is defined, with specific institutions noted as holding key roles. The Project Board (PB) is responsible for decision-making and includes members such as key national/local government representatives, UNDP senior officials, and the donor, among others. While the document specifies roles like Executive, Senior Supplier, and Senior Beneficiary, it does not list individuals for each position. The responsibilities of the Project Board, including quality assurance and oversight, are outlined, but the terms of reference (ToR) for the board are not attached to the document. The governance mechanism ensures that the required resources are committed and that the project is focused on achieving its expected results. The PB also plays a critical role in project monitoring and evaluations, assuring the quality of these processes and using evaluations for improving performance, accountability, and learning. However, the absence of specific individuals for each position and the lack of attached ToR indicate that while the governance mechanism is defined, it is not fully detailed, which is necessary for a higher rating. Attachment: Project Document |
|  | 13. Have the project risks been identified using the risk assessment tools (Project Quality Assurance, Social and Environmental Screening Procedure, Partner Capacity Assessment Tool, Harmonized Approach to Cash Transfer, Private Sector Due Diligence, etc., if applicable), with clear plans stated to manage and mitigate each risk? |
| ☐ | - 3: Project risks related to the achievement of results are fully described in the project risk register, based on comprehensive analysis drawing on the programme’s theory of change, Social and Environmental Standards and screening, situation analysis, capacity assessments and other analysis such as funding potential and reputational risk. Risks have been identified through a consultative process with key internal and external stakeholders, including consultation with the UNDP Security Office as required. Clear and complete plan in place to manage and mitigate each risk, including security risks, reflected in project budgeting and monitoring plans. (both must be true) |
| ☒ | - 2: Project risks related to the achievement of results are identified in the initial project risk register based on a minimum level of analysis and consultation, with mitigation measures identified for each risk. |
| ☐ | - 1: Some risks may be identified in the initial project risk register, but no evidence of consultation or analysis and no clear risk mitigation measures identified. This option is also selected if risks are not clearly identified, no initial risk log is included with the project document and/or no security risk management process has taken place for the project. |
|  | Evidence (Enter a short explanation and attached a document that provides evidence for your response): The project is rated as a 2 for its risk identification and management. Project risks related to the achievement of results are identified in the initial project risk register, based on a minimum level of analysis and consultation. The project document outlines various risks, including reputational, social, and environmental risks, and provides mitigation measures for each identified risk. For instance, the project addresses reputational risks through local conflict analyses, stakeholder engagement, and transparent communication of project activities to all stakeholders involved. Additionally, the project includes measures to manage risks related to sexual exploitation and abuse (SEA) by ensuring partners and staff are trained and aware of UNDP's policies and procedures on PSEA. Moreover, the project has taken steps to identify and assess any potential adverse impacts on the enjoyment of human rights rigorously through SESP. It provided detailed analysis on degree of mainstreaming of human rights-based approach, gender equality and women’s empowerment, sustainability and resilience, and accountability to stakeholders, which turn out to be well integrated in the project design. Through SESP, a robust analysis was conducted to identify potential social and environmental risks that the project might bring. The identified risks were carefully analyzed by using corporate risk register tool, allowing to evaluate its significance through degree of impact and likelihood, accompanied by mitigation and adaptation measures. On the other hand, other analysis, such as capacity assessments, funding potential analysis were not conducted. Also, there is no evidence that risk identification process was conducted consultatively with external stakeholders, which are elements need to be fulfilled to rate at “3.” Attachment: Project Document, SESP |
|  | 5. Efficient |
|  | 14. Have specific measures for ensuring cost-efficient use of resources been explicitly mentioned as part of the project design? This can include, for example: i) Using the theory of change analysis to explore different options of achieving the maximum results with the resources available. ii) Using a portfolio management approach to improve cost effectiveness through synergies with other interventions. iii) Through joint operations (e.g., monitoring or procurement) with other partners. iv) Sharing resources or coordinating delivery with other projects. v) Using innovative approaches and technologies to reduce the cost of service delivery or other types of interventions. |
| ☒ | - Yes |
| ☐ | - No |
|  | Evidence (Enter a short explanation and attached a document that provides evidence for your response): Yes, specific measures for ensuring cost-efficient use of resources have been explicitly mentioned as part of the project design, demonstrating a comprehensive approach to maximizing the impact of available resources. The project document outlines several strategies aimed at enhancing cost efficiency and effectiveness, which include: 1. Portfolio Management Approach: The project leverages a portfolio management approach, as deployed by UNDP Ukraine through its three portfolios – Democratic Governance, Inclusive Development, Recovery and Peacebuilding, and Environment and Energy. This approach ensures synergies and leverages activities and partnerships among several initiatives and projects implemented through these portfolios by UNDP Ukraine. By coordinating efforts across these areas, the project aims to create a multiplier effect, enhancing the overall impact and cost-effectiveness of its interventions. 2. Adherence to UNDP Programme and Operations Policies and Procedures (POPP): The project commits to adhering to the UNDP Programme and Operations Policies and Procedures, which include guidelines for cost efficiency and effectiveness. Regular reviews through the governance mechanism of the UNDP Country Programme for Ukraine are planned to ensure compliance and identify opportunities for cost savings. 3. Localized Implementation: By utilizing its local presence and networks through five sub-national offices, UNDP Ukraine plans to implement project activities in a localized manner. This approach not only ensures that interventions are tailored to the specific needs of targeted areas but also potentially reduces costs associated with centralized management and implementation. Attachment: Project Document |
|  | 15. Is the budget justified and supported with valid estimates? |
| ☐ | - 3: The project’s budget is at the activity level with funding sources, and is specified for the duration of the project period in a multi-year budget. Realistic resource mobilisation plans are in place to fill unfunded components. Costs are supported with valid estimates using benchmarks from similar projects or activities. Cost implications from inflation and foreign exchange exposure have been estimated and incorporated in the budget. Adequate costs for monitoring, evaluation, communications and security have been incorporated. |
| ☒ | - 2: The project’s budget is at the activity level with funding sources, when possible, and is specified for the duration of the project in a multi-year budget, but no funding plan is in place. Costs are supported with valid estimates based on prevailing rates. |
| ☐ | - 1: The project’s budget is not specified at the activity level, and/or may not be captured in a multi-year budget. |
|  | Evidence (Enter a short explanation and attached a document that provides evidence for your response): The project's budgeting approach aligns with a rating of "2". The budget is detailed at the activity level with specified funding sources for the duration of the project, as evidenced in a multi-year budget plan. Furthermore, the budget includes allocations for various outputs across different quarters, indicating a comprehensive planning approach. The budget also includes GMS and DPC, which will be used for cost recovery of project related human resource costs within Project Management (PMU) Unit as well as relevant office support out of the PMU (such as finance, procurement, recruitment, communications etc). Since all required budget is allocated by the donor, no resource mobilization plan is required to fill the funds gap. The budget composition is supported by estimates using benchmark of other similar projects currently and previously implemented by UNDP, allowing realistic and accurate cost estimation. Costs of M&E, communications and security have been incorporated. However, the documentation does not explicitly mention a specific consideration for cost implications from inflation and foreign exchange exposure. Evaluation plan is also not mentioned in the prodoc, while at least one evaluation is necessary (either mid-term or terminal). They are necessary elements to rate at “3”. Attachment: Project Document |
|  | 16. Is the Country Office / Regional / Global Project fully recovering the costs involved with project implementation? |
| ☒ | - 3: The budget fully covers all project costs that are attributable to the project, including programme management and development effectiveness services related to strategic country programme planning, quality assurance, pipeline development, policy advocacy services, finance, procurement, human resources, administration, issuance of contracts, security, travel, assets, general services, information and communications based on full costing in accordance with prevailing UNDP policies (i.e., UPL, LPL.) |
| ☐ | - 2: The budget covers significant project costs that are attributable to the project based on prevailing UNDP policies (i.e., UPL, LPL) as relevant. |
| ☐ | - 1: The budget does not adequately cover project costs that are attributable to the project, and UNDP is cross-subsidizing the project. |
|  | Evidence (Enter a short explanation and attached a document that provides evidence for your response): The budget for the project is aligned with a rating of "3", indicating that it fully covers all project costs that are attributable to the project, including programme management and development effectiveness services. They are covered by Programme Management/DPC at $3,644,950 and General Management Support at $2,171,596. These budget lines will be used to cover human resource cost of Project Management Unit (PMU), as well as operations and administrative related costs such as HR, Finance, procurement, security and communications. It will also contribute those costs related to strategic country programme planning, quality assurance, pipeline development, policy advocacy services related to the project, as personnels paid under these lines, mainly under DPC, will contribute to such activities as needed. The inclusion of these costs indicates adherence to UNDP policies for full costing mentioned in POPP (UNDP Programme and Operations Policies and Procedures) ensuring that the budget fully recovers the costs involved with project implementation without the need for cross-subsidization by UNDP. Attached: Project Document |
|  | 6. Effective |
|  | 17. Have targeted groups, and particularly those marginalized, vulnerable, and left further behind (LNOB), been engaged in the design of the project? |
| ☐ | - 3: Credible evidence that all targeted groups, prioritising discriminated, vulnerable, and marginalized populations that will be involved in or affected by the project, have been actively engaged in the design of the project. The project has an explicit strategy to identify, engage and ensure the meaningful participation of target groups as stakeholders throughout the project, including through monitoring and decision-making (e.g., representation on the project board, inclusion in samples for evaluations, etc.) |
| ☒ | - 2: Some evidence that key targeted groups have been consulted in the design of the project. |
| ☐ | - 1: No evidence of engagement with targeted groups during project design. |
| ☐ | - Not Applicable |
|  | Evidence (Enter a short explanation and attached a document that provides evidence for your response): The project is rated as a 2 regarding the engagement of targeted groups, particularly marginalized and vulnerable populations, in its design. There is some evidence that key targeted groups have been consulted during the project design phase. The project document mentions the use of participatory and inclusive consultation methodologies to design interventions that respond to the identified priority needs in the respective oblasts, which suggests that some level of engagement with targeted groups occurred. Additionally, the project emphasizes promoting ownership by the targeted local authorities and communities from its onset, indicating an effort to involve these groups in the planning process. However, the document does not provide detailed evidence of a comprehensive strategy to actively engage all targeted groups, especially those marginalized and vulnerable, throughout the project lifecycle. There is no explicit mention of these groups' representation on the project board or their inclusion in monitoring and decision-making processes. Therefore, while there is some consultation with key groups, the lack of a detailed engagement strategy and comprehensive evidence of active participation limits the rating to a 2. Attached: Project Document |
|  | 18. Does the project plan for adaptation and course correction if regular monitoring activities, evaluation, and lesson learned demonstrate there are better approaches to achieve the intended results and/or circumstances change during implementation? |
| ☒ | - Yes |
| ☐ | - No |
|  | Evidence (Enter a short explanation and upload a document that provides evidence for your response): Yes, the project does plan for adaptation and course correction if regular monitoring activities, evaluation, and lessons learned demonstrate there are better approaches to achieve the intended results or if circumstances change during implementation. The project document outlines a structured approach to monitoring and evaluation, which includes regular internal reviews of data and evidence from all monitoring actions to inform decision-making. This process is designed to ensure that performance data, risks, lessons, and quality are discussed by the project board and used to make necessary course corrections at least annually. Additionally, the project governance mechanism, specifically the project board, is tasked with holding regular project reviews to assess performance and review the Annual Work Plan, ensuring realistic budgeting and adaptability over the project's life. This indicates a clear plan for adapting strategies and making course corrections based on the insights gained from ongoing monitoring and evaluation activities. The inclusion of these mechanisms demonstrates the project's commitment to flexibility and responsiveness, allowing it to adjust its approach as needed to better achieve its intended outcomes. These components collectively demonstrate the project's preparedness to adapt and make course corrections based on regular monitoring, evaluations, and lessons learned, ensuring that it remains responsive to changing circumstances and can effectively achieve its intended results. Attached: Project Document |
|  | 19. The gender marker for all project outputs are scored at GEN2 or GEN3, indicating that gender has been fully mainstreamed into all project outputs at a minimum. |
| ☒ | - Yes |
| ☐ | - No |
|  | Evidence (Enter a short explanation and upload a document that provides evidence for your response): Yes, the gender marker for all project outputs is scored at GEN2, indicating that gender has been fully mainstreamed into all project outputs at a minimum. The project document explicitly mentions that the interventions under each output will address the 10-Point Action Agenda: Advancing Gender Equality in Crisis Settings (10PAA), which demonstrates a commitment to integrating gender considerations throughout the project. Additionally, the project emphasizes promoting gender equality and women's empowerment, particularly in crisis situations, by ensuring women's participation and leadership in needs identification and decision-making processes. This approach aligns with the GEN2 marker, which signifies that gender equality is a significant objective of the project. The project outputs, such as those related to economic recovery and access to justice, are designed to enhance gender equality by focusing on the needs and contributions of women and girls, particularly those affected by conflict and crisis. Therefore, the project meets the criteria for a GEN2 rating, confirming that gender has been fully mainstreamed into its outputs. Additionally, the project promotes Women in Peace and Security (WPS) as a cross-cutting issue, emphasizing creating a safe environment for Ukrainian women and girls and fostering participation and leadership of women in building peace and security. Furthermore, contributions of the project toward women’s empowerment and gender equality, as well as risks associated with them have been robustly assessed through SESP. Attached: Project Document, SESP |
|  | 20. Have societal digital risks and opportunities been taken into account when designing the project’s approach and have digital or data technology solutions been considered to enhance the efficiency, effectiveness and scalability of project results? |
| ☐ | - 3: To the extent possible, societal digital risks and opportunities have been investigated when designing the strategy and Theory of Change, and the potential use of digital or data technologies in project activities has been considered in line with UNDP’s digital standards and data principles. (All must be true) |
| ☒ | - 2: Only the potential use of digital or data solutions in project activities has been considered in line with UNDP’s digital standards and data principles, but there is no or limited evidence that aspects of inclusive digital societies have been considered in the design of the strategy or Theory of Change. |
| ☐ | - 1: Neither societal digital risks and opportunities, nor digital or data technology solutions were specifically considered in the project design or, UNDP’s digital standards and data principles are not taken into account when intending to use digital or data technology solutions in project activities. |
| ☐ | - Digital considerations are not relevant to this project. *Applicable only to option "Digital considerations are not relevant" ☐ 1: Societal digital transformation is not a government or contextual priority ☐ 2: A non-digital approach yields higher effectiveness and efficiency ☐ 3: Other (specify in the “Evidence” section) |
|  | Evidence (Enter a short explanation and attached a document that provides evidence for your response): The project is rated as a 2 regarding the consideration of societal digital risks and opportunities and the use of digital or data technology solutions. The project document indicates that the potential use of digital or data solutions in project activities has been considered, aligning with UNDP’s digital standards and data principles. For instance, the project aims to increase transparency and accountability in the justice system by ensuring openness and accessibility to public information and open data, which suggests an integration of digital solutions to enhance project outcomes. However, there is limited evidence that the design of the strategy or Theory of Change has thoroughly investigated societal digital risks and opportunities. The document does not explicitly address how digital inclusivity or potential digital risks have been factored into the overall project strategy. Therefore, while digital solutions are considered to some extent, the lack of comprehensive integration of societal digital considerations in the project design limits the rating to a 2. Further exploration of digital inclusivity and risk mitigation strategies would be necessary to achieve a higher rating. Attached: Project Document |
|  | 7. Sustainability & National Ownership |
|  | 21. Have national / regional / global partners led, or proactively engaged in, the design of the country / regional / global project, respectively? |
| ☐ | - 3: National / regional / global partners have full ownership of the country / regional / global project and led the process of the development of the project jointly with UNDP. |
| ☒ | - 2: The project has been developed by UNDP in close consultation with national / regional / global partners. |
| ☐ | - 1: The project has been developed by UNDP with limited or no engagement with national partners. |
|  | Evidence (Enter a short explanation and attached a document that provides evidence for your response): The project is rated as a 2 regarding the engagement of national, regional, or global partners in its design. The project has been developed by UNDP in close consultation with national partners. The document highlights UNDP's systemic support to the Government of Ukraine and sub-national authorities, emphasizing the strengthening of institutional capacity and the integration of national recovery and regional development priorities into local policies and projects. This indicates a collaborative approach where national partners are actively involved in shaping the project to align with their strategic priorities. Furthermore, the project aims to promote ownership by targeted local authorities and communities from its onset, suggesting a participatory approach in the planning process. However, there is no explicit evidence that national partners have full ownership or have led the project development process jointly with UNDP. The engagement appears to be more consultative rather than a partnership where national entities have a leading role. Therefore, while there is significant consultation and collaboration, the lack of full ownership by national partners limits the rating to a 2. Attached: Project Document |
|  | 22. Are key institutions and systems identified, and is there a strategy for strengthening specific / comprehensive capacities based on capacity assessments conducted? |
| ☐ | - 3: The project has a strategy for strengthening specific capacities of national institutions and/or actors based on a completed capacity assessment. This strategy includes an approach to regularly monitor national capacities using clear indicators and rigorous methods of data collection, and adjust the strategy to strengthen national capacities accordingly. |
| ☐ | - 2: A capacity assessment has been completed. There are plans to develop a strategy to strengthen specific capacities of national institutions and/or actors based on the results of the capacity assessment. |
| ☒ | - 1: Capacity assessments have not been carried out. |
| ☐ | - Not Applicable |
|  | Evidence (Enter a short explanation and attached a document that provides evidence for your response): The project is rated as a 2 regarding the identification of key institutions and systems and the strategy for strengthening capacities. A capacity assessment has been completed, and there are plans to develop a strategy to strengthen specific capacities of national institutions and actors based on the results of this assessment. The project document outlines activities aimed at enhancing the capacities of government institutions at both national and subnational levels, focusing on institutional effectiveness, strategic planning, policy development, and coordination in line with the Sustainable Development Goals (SDGs). Additionally, the project emphasizes strengthening the capacities of justice system actors and legal service providers to ensure effective, inclusive, and non-discriminatory access to justice and human rights protection. However, while these activities indicate a commitment to capacity building, the document does not provide explicit details of a completed strategy that includes regular monitoring of national capacities using clear indicators and rigorous data collection methods. Therefore, while the groundwork for capacity strengthening is evident, the absence of a fully developed and detailed strategy limits the rating to a 2. Attached: Project Document |
|  | 23. Is there is a clear strategy embedded in the project specifying how the project will use national systems (i.e., procurement, monitoring, evaluations, etc.,) to the extent possible? |
| ☐ | - Yes |
| ☐ | - No |
| ☒ | - Not Applicable |
|  | Evidence (Enter a short explanation and attached a document that provides evidence for your response): Since this is a DIM project, UNDP’s system (procurement, M&E, recruitment, financial management etc) will be used. Having said that, the project emphasizes strengthening institutional capacities across different components, which inherently involves leveraging national systems. This includes building resilience at individual, community, and national levels and creating a pool of knowledge within institutions that could be further disseminated through peer-to-peer knowledge transfer and applied in future projects. This approach indicates a reliance on and enhancement of existing national systems for capacity building and knowledge dissemination. Attached: Project Document |
|  | 24. Is there a clear transition arrangement / phase-out plan developed with key stakeholders in order to sustain or scale up results (including resource mobilisation and communications strategy)? |
| ☒ | - Yes |
| ☐ | - No |
|  | Evidence (Enter a short explanation and attached a document that provides evidence for your response): Yes, there is a clear transition arrangement and phase-out plan developed with key stakeholders to sustain or scale up results. The project document outlines a sustainability and exit strategy that is integrated into the project's approaches and activities. This strategy includes strengthening institutional capacities across different components of the project, ensuring that these capacities and mechanisms remain in place after the project's conclusion. The project aims to build resilience at individual, community, and national levels, creating a pool of knowledge within institutions that can be disseminated through peer-to-peer knowledge transfer and applied in future initiatives. Additionally, the project emphasizes fostering inclusivity and solidarity to ensure long-lasting impacts, such as non-discriminative and efficient access to justice and human rights remedies for citizens. The strategy also involves training and capacity building of relevant government institutions to sustain the project's results beyond its end. This comprehensive approach indicates a well-developed transition plan that involves key stakeholders, ensuring the sustainability and potential scaling up of project outcomes. Attached: Project Document |

| Name and Title | Signature and Date | Description |
| --- | --- | --- |
| QA Assessor: Yuta Kono M&E and Programme Analyst | Signature: Date: | The QA Assessor has to be accountable for project assurance, which is independent of the project manager. A UNDP programme or monitoring and evaluation officer typically holds the project assurance role on behalf of UNDP. For GEF- and GCF-financed projects, project assurance is undertaken as per the requirements of the vertical funds, and these services are covered by the fee provided by the vertical fund. |
| QA Approver: <Name> <Title> | Signature: Date: | The QA Approver is typically the Resident Representative, Deputy Resident Representative, or head of portfolio. The QA Approver must function at a higher level of accountability than the QA Assessor. The QA Approver cannot also be the QA Assessor. |

# UNDP Social and Environmental Screening Template (v. July 2022)

The completed template, which constitutes the Social and Environmental Screening Report, must be included as an annex to the Project Document at the design stage. Note: this template will be converted into an online tool. The online version will guide users through the process and will embed relevant guidance.

### Project Information

| Project Information |  |
| --- | --- |
| 1. Project Title | Inclusive Recovery Support for Resilience and Human Security in Ukraine (JSB 2024) |
| 2. Project Number (i.e. Quantum project ID, PIMS+) | 01003977 |
| 3. Location (Global/Region/Country) | Country |
| 4. Project stage (Design or Implementation) | Design |
| 5. Date | 08 February 2025 |

Part A. Integrating Programming Principles to Strengthen Social and Environmental Sustainability

QUESTION 1: How Does the Project Integrate the Programming Principles in Order to Strengthen Social and Environmental Sustainability?

Briefly describe in the space below how the project mainstreams the human rights-based approach

The project integrates a human rights-based approach by prioritizing a human-centered strategy across all its initiatives, ensuring that victims' needs are addressed as individuals. It guarantees that support systems remain accessible, inclusive, and adaptable to the distinct challenges faced by those affected by war. A key component of this approach is training legal service providers to offer victim-centered, trauma-informed support, aligning interventions with professional standards and principles that promote trust, dignity, and recovery. In addition, the project strengthens access to justice and the protection of human rights by advancing transitional justice mechanisms. This includes establishing robust investigative standards for war crimes such as conflict-related sexual violence and civilian casualties, ensuring thorough and just legal proceedings. It also engages in nationwide judicial monitoring, collaborating with the Ombudsperson's Office and civic activists to evaluate transparency and accountability within the justice system. This assessment identifies systemic gaps, providing insights for developing targeted reforms. Through these initiatives, the project ensures that human rights remain central, fostering justice and dignity for those affected. Moreover, the project underscores its commitment to gender equality and women's empowerment by integrating gender perspectives throughout its initiatives. By promoting women's active participation in peace and security efforts, it not only addresses gender disparities but also empowers women as crucial contributors to recovery and reconciliation, ensuring more inclusive and equitable outcomes.

Briefly describe in the space below how the project is likely to improve gender equality and women’s empowerment

The project is designed to improve gender equality and women’s empowerment by addressing the four pillars of Women, Peace, and Security (WPS): Prevention, Participation, Protection, and Relief & Recovery as well as 10-Point Action Agenda: Advancing Gender Equality in Crisis Settings (10PAA). It ensures women's participation and leadership in decision-making processes, builds the capacity of female peace and security actors, and provides multi-sectoral support to protect women and girls from sexual and gender-based violence. Additionally, the project supports the Government of Ukraine in integrating gender equality into its recovery plans and operational processes, promoting women's agency and leadership in peace processes and political institutions, and ensuring women's access to justice and security. Moreover, the project places a strong emphasis on women's economic empowerment. By revitalizing the local economy and supporting micro, small, and medium-sized enterprises (MSMEs), the project creates opportunities for women's entrepreneurship and employment. This not only contributes to their economic independence but also promotes social empowerment, addressing the economic disparities that often hinder gender equality. Additionally, the project's multi-sectoral approach, focusing on oblasts severely affected by the war, incorporates a gender-responsive lens to address the specific vulnerabilities and needs of women in these regions. This includes efforts to restore critical infrastructure, provide energy services, and clear debris, all while ensuring that recovery solutions are inclusive, equitable, and responsive to the needs of women.

Briefly describe in the space below how the project mainstreams sustainability and resilience

The project mainstreams sustainability and resilience by investing in strengthening institutional capacities across its components, ensuring that these capacities remain in place after the project's end. This approach builds resilience at individual, community, regional, and national levels, fostering inclusivity and solidarity for long-lasting impacts on recovery and peace. The project also focuses on enhancing transparency, accountability, and anti-corruption measures, which contribute to sustainable governance and development processes. Additionally, it supports the development of sustainable business models and inclusive employment opportunities, particularly for war-affected populations, to promote economic resilience and recovery. This approach will contribute to long-lasting impacts on recovery and peace through fostering resilience-building with inclusivity and solidarity at individual, community, and national levels. For instance, the project will support the Governments of Ukraine in developing strategies for recovery at both local and national levels to address mid- and longer-term needs for sustainable recovery. In addition, the project provides capacity building, advisory, and financial support to develop and pilot sustainable business models in key value chains, particularly targeting war-affected populations, including veterans and people with disabilities. This involves improving training infrastructure and delivering upskilling and reskilling programs to enhance employment opportunities. The project emphasizes creating inclusive employment opportunities by improving conditions for entrepreneurs and micro, small, and medium enterprises (MSMEs), enhancing market access, and advancing policy frameworks. This focus on economic recovery and security is designed to support the most vulnerable groups affected by the war. Additionally, the project leverages public-private partnerships to adopt innovative technologies, such as green energy solutions, which support critical infrastructure and contribute to a greener recovery. Furthermore, the project enhances the debris management system in Ukraine by ensuring the safe removal and recycling of debris and the environmentally sound management of hazardous waste. This initiative is expected to benefit approximately 500,000 people, with at least half being women, thereby promoting environmental sustainability and community resilience. Through these comprehensive strategies, the project aims to foster sustainable development and resilience, ensuring that the benefits extend well beyond its conclusion. The project also incorporates resilience-building measures, such as mine action assessments and training of pyrotechnic teams for humanitarian demining. These activities not only address immediate safety concerns but also enable the safe return of displaced populations and the resumption of agricultural and economic activities, thereby strengthening community resilience.

Briefly describe in the space below how the project strengthens accountability to stakeholders

The project strengthens accountability to stakeholders by implementing a robust governance mechanism, including a project board that conducts regular reviews to assess performance and ensure realistic budgeting throughout the project's lifecycle. This board also holds an end-of-project review to capture lessons learned and discuss opportunities for scaling up, thereby ensuring transparency and accountability in decision-making processes. Additionally, the project emphasizes integrity, transparency, and accountability in government mechanisms and processes for crisis management and inclusive recovery, empowering citizen participation and engagement, including vulnerable groups, youth, veterans, and women. One key approach is the establishment of a robust governance mechanism, which includes a project board responsible for conducting regular reviews. These reviews assess the project's performance and ensure that budgeting remains realistic throughout its lifecycle. This governance structure culminates in an end-of-project review, which captures lessons learned and explores opportunities for scaling up, thereby promoting transparency and accountability in decision-making processes. Additionally, the project emphasizes integrity, transparency, and accountability within government mechanisms and processes related to crisis management and inclusive recovery and provides support to strengthen the government’s anti-corruption mechanisms. By empowering citizen participation and engagement, the project ensures that diverse voices, including those of vulnerable groups, youth, veterans, and women, are heard and considered in the recovery efforts. This participatory approach not only strengthens accountability but also fosters a sense of ownership and trust among stakeholders, contributing to more effective and sustainable outcomes. Furthermore, the project's emphasis on compliance with UNDP policies and procedures, including those related to risk management, social and environmental sustainability, and anti-corruption measures, which reinforces accountability. This highlights the project's commitment to maintaining high ethical and operational standards. Through past experiences of project implementation, the project team has developed a solid M&E mechanism, regularly tracking the progress and achievement of the project target indicators. Additionally, the project's approach to stakeholder engagement, which includes partnerships with relevant Ukrainian government bodies and the government of Japan, ensures that the donor and stakeholders are kept informed and involved in the project's implementation, especially in public events such as handover ceremonies. They will also receive periodic progress reports from UNDP, and UNDP will respond to their ad-hoc questions as raised. This transparency in implementation, communication, operations and decision-making processes further strengthens accountability to stakeholders, ensuring that the project remains aligned with its goals of promoting transformational recovery and human security in Ukraine.

Part B. Identifying and Managing Social and Environmental Risks

| QUESTION 2: What are the Potential Social and Environmental Risks? Note: Complete SESP Attachment 1 before responding to Question 2. | QUESTION 3: What is the level of significance of the potential social and environmental risks? Note: Respond to Questions 4 and 5below before proceeding to Question 5 |  |  | QUESTION 6: Describe the assessment and management measures for each risk rated Moderate, Substantial or High |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Description (broken down by event, cause, impact) | Impact and Likelihood (1-5) | Significance (Low, Moderate Substantial, High) | Comments (optional) | Description of assessment and management measures for risks rated as Moderate, Substantial or High |  |  |  |
| Risk 1: There is a risk that project interventions are not designed and implemented in a gender-sensitive manner and that the full participation of women in the project planning and implementation, and their access to benefits provided by the project may be limited. This is due to low awareness or lack of capacity of project staff and partners of gender equality and women empowerment issues; low interest of women beneficiaries in participation in project activities; pre-existing social and cultural norms in the project target areas; lack of regularly updated gender and vulnerability segregated statistical data; and absence or lack of gender analysis and gender mainstreaming strategy. | I =2 L =3 | Low |  | The project will uphold the target for women's participation in all project activities to ensure their active involvement and representation; engage and support women's organizations in advocacy efforts, local planning, and budgeting participation, empowering them to voice their perspectives and priorities; allocate a minimum budget specifically dedicated to women's activities, ensuring that sufficient resources are allocated to address their specific needs and promote gender equality within the project. Project will produce a gender analysis from consultations with partners and secondary data analysis, of status and barriers of women empowerment, with recommendations on how to ensure gender responsive measures under each outputs as relevant. The project will ensure that its staff and partners uphold the highest standards of conduct for PSEA, which includes familiarizing themselves with UNDP's policies and procedures on PSEA and being informed about the channels available for reporting misconduct. |  |  |  |
| Risk 2: Unintended negative impact on environment could be caused by project activities related to reconstruction and installation. | I =2 L =2 | Low |  | Project team especially Engineers will ensure the feasibility studies are in line with the environmental requirements. UNDP will consult well with relevant stakeholders before the reconstruction and installation in order to minimize such negative impact. |  |  |  |
| Risk 3: Disruption/absence of basic energy supply in target areas caused by the ongoing war in Ukraine could lead to suspension of project operations and, potentially, unintended environmental pollution. | I =3 L =3 | Moderate |  | Project will assess availability of essential services during the selection of target area. The project team and contractors will be equipped adequately to be able to operate during electricity shortages. |  |  |  |
| Risk 4: Workers involved in implementing the construction or infrastructure related activities are subject to discriminatory working and labor conditions, including inadequate health and safety conditions. | I = 3 L = 2 | Moderate |  | The project shall ensure the contractors commit to, in writing, to comply with the relevant working and labor, including occupational health and safety (OHS) requirements, prior the project funds are allocated for the relevant project activity: building construction, renovation, infrastructure construction and operation, etc. Workers may raise their concerns (safety, potential violations of existing rights and entitlements as provided for in legislation, employment contracts or else) through the Grievance Mechanism. The workers will be informed of the grievance mechanism at the time of recruitment and be protected against any reprisal for its use. |  |  |  |
| Risk 5: Reconstruction activities initiated by project may result in restricted access to public services, social tension at municipalities and potential inconveniences. | I =3 L =1 | Low |  | Project will perform stakeholder outreach activities explaining the long-term benefits of the reconstruction. The project will also ensure that the companies are equipped with best practices and standards for social responsibility and apply them during the reconstruction (including the availability of grievances plan/hotline, etc. |  |  |  |
| [add additional rows as needed] |  |  |  |  |  |  |  |
|  | QUESTION 4: What is the overall project risk categorization? |  |  |  |  |  |  |
|  | Low Risk |  |  | ☐ |  |  |  |
|  | Moderate Risk |  |  | + | X |  |  |
|  | Substantial Risk |  |  | ☐ |  |  |  |
|  | High Risk |  |  | ☐ |  |  |  |
|  | QUESTION 5: Based on the identified risks and risk categorization, what requirements of the SES are triggered? (check all that apply) |  |  |  |  |  |  |
|  | Question only required for Moderate, Substantial and High Risk projects |  |  |  |  |  |  |
|  | Is assessment required? (check if “yes”) |  |  | + |  |  | Status? (completed, planned) |
|  | if yes, indicate overall type and status |  |  |  | + | Targeted assessment(s) | planned |
|  |  |  |  |  | ☐ | ESIA (Environmental and Social Impact Assessment) |  |
|  |  |  |  |  | ☐ | SESA (Strategic Environmental and Social Assessment) |  |
|  | Are management plans required? (check if “yes) |  |  | ☐ |  |  |  |
|  | If yes, indicate overall type |  |  |  | ☐ | Targeted management plans (e.g. Gender Action Plan, Emergency Response Plan, Waste Management Plan, others) | Gender analysis with recommendations for relevant outputs including energy sector |
|  |  |  |  |  | ☐ | ESMP (Environmental and Social Management Plan which may include range of targeted plans) |  |
|  |  |  |  |  | ☐ | ESMF (Environmental and Social Management Framework) |  |
|  | Based on identified risks, which Principles/Project- level Standards triggered? |  |  |  | Comments (not required) |  |  |
|  | Overarching Principle: Leave No One Behind |  |  |  |  |  |  |
|  | Human Rights |  |  | + |  |  |  |
|  | Gender Equality and Women’s Empowerment |  |  | ☐ |  |  |  |
|  | Accountability |  |  | + |  |  |  |
|  | 1. Biodiversity Conservation and Sustainable Natural Resource Management |  |  | ☐ |  |  |  |
|  | 2. Climate Change and Disaster Risks |  |  | ☐ |  |  |  |
|  | 3. Community Health, Safety and Security |  |  | + |  |  |  |
|  | 4. Cultural Heritage |  |  | ☐ |  |  |  |
|  | 5. Displacement and Resettlement |  |  | ☐ |  |  |  |
|  | 6. Indigenous Peoples |  |  | ☐ |  |  |  |
|  | 7. Labour and Working Conditions |  |  | + |  |  |  |
|  | 8. Pollution Prevention and Resource Efficiency |  |  | ☐ |  |  |  |

Final Sign Off

Final Screening at the design-stage is not complete until the following signatures are included

| Signature | Date | Description |
| --- | --- | --- |
| QA Assessor Larysa Balanchuk, Project Associate |  | UNDP staff member responsible for the project, typically a UNDP Programme Officer. Final signature confirms they have “checked” to ensure that the SESP is adequately conducted. |
| QA Approver Christophoros Politis, Deputy Resident Representative |  | UNDP senior manager, typically the UNDP Deputy Country Director (DCD), Country Director (CD), Deputy Resident Representative (DRR), or Resident Representative (RR). The QA Approver cannot also be the QA Assessor. Final signature confirms they have “cleared” the SESP prior to submittal to the PAC. |
| PAC Chair, Christophoros Politis, Deputy Resident Representative |  | UNDP chair of the PAC. In some cases PAC Chair may also be the QA Approver. Final signature confirms that the SESP was considered as part of the project appraisal and considered in recommendations of the PAC. |

| Checklist Potential Social and Environmental Risks |  |  |
| --- | --- | --- |
| INSTRUCTIONS: The risk screening checklist will assist in answering Questions 2-6 of the Screening Template. Answers to the checklist questions help to (1) identify potential risks, (2) determine the overall risk categorization of the project, and (3) determine required level of assessment and management measures. Refer to the SES toolkit for further guidance on addressing screening questions. |  |  |
| Overarching Principle: Leave No One Behind Human Rights |  | Answer (Yes/No) |
| P.1 | Have local communities or individuals raised human rights concerns regarding the project (e.g. during the stakeholder engagement process, grievance processes, public statements)? | No |
| P.2 | Is there a risk that duty-bearers (e.g. government agencies) do not have the capacity to meet their obligations in the project? | No |
| P.3 | Is there a risk that rights-holders (e.g. project-affected persons) do not have the capacity to claim their rights? | No |
| Would the project potentially involve or lead to: |  |  |
| P.4 | adverse impacts on enjoyment of the human rights (civil, political, economic, social or cultural) of the affected population and particularly of marginalized groups? | No |
| P.5 | inequitable or discriminatory impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups, including persons with disabilities? 16 | No |
| P.6 | restrictions in availability, quality of and/or access to resources or basic services, in particular to marginalized individuals or groups, including persons with disabilities? | No |
| P.7 | exacerbation of conflicts among and/or the risk of violence to project-affected communities and individuals? | No |
| Gender Equality and Women’s Empowerment |  |  |
| P.8 | Have women’s groups/leaders raised gender equality concerns regarding the project, (e.g. during the stakeholder engagement process, grievance processes, public statements)? | No |
| Would the project potentially involve or lead to: |  |  |
| P.9 | adverse impacts on gender equality and/or the situation of women and girls? | No |
| P.10 reproducing discriminations against women based on gender, especially regarding participation in design and implementation or access to opportunities and benefits? |  | Yes |
| P.11 limitations on women’s ability to use, develop and protect natural resources, taking into account different roles and positions of women and men in accessing environmental goods and services? For example, activities that could lead to natural resources degradation or depletion in communities who depend on these resources for their livelihoods and well being |  | No |
| P.12 exacerbation of risks of gender-based violence? For example, through the influx of workers to a community, changes in community and household power dynamics, increased exposure to unsafe public places and/or transport, etc. |  | No |

#### SESP Attachment 1. Social and Environmental Risk Screening Checklist

16 Prohibited grounds of discrimination include race, ethnicity, sex, age, language, disability, sexual orientation, gender identity, religion, political or other opinion, national or social or geographical origin, property, birth or other status including as an indigenous person or as a member of a minority. References to “women and men” or similar is understood to include women and men, boys and girls, and other groups discriminated against based on their gender identities, such as transgender and transsexual people.

| Sustainability and Resilience: Screening questions regarding risks associated with sustainability and resilience are encompassed by the Standard-specific questions below |  |
| --- | --- |
| Accountability |  |
| Would the project potentially involve or lead to: |  |
| P.13 exclusion of any potentially affected stakeholders, in particular marginalized groups and excluded individuals (including persons with disabilities), from fully participating in decisions that may affect them? | No |
| P.14 grievances or objections from potentially affected stakeholders? | No |
| P.15 risks of retaliation or reprisals against stakeholders who express concerns or grievances, or who seek to participate in or to obtain information on the project? | No |
| Project-Level Standards |  |
| Standard 1: Biodiversity Conservation and Sustainable Natural Resource Management |  |
| Would the project potentially involve or lead to: |  |
| 1.1 adverse impacts to habitats (e.g. modified, natural, and critical habitats) and/or ecosystems and ecosystem services? For example, through habitat loss, conversion or degradation, fragmentation, hydrological changes | No |
| 1.2 activities within or adjacent to critical habitats and/or environmentally sensitive areas, including (but not limited to) legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities? | No |
| 1.3 changes to the use of lands and resources that may have adverse impacts on habitats, ecosystems, and/or livelihoods? (Note: if restrictions and/or limitations of access to lands would apply, refer to Standard 5) | No |
| 1.4 risks to endangered species (e.g. reduction, encroachment on habitat)? | No |
| 1.5 exacerbation of illegal wildlife trade? | No |
| 1.6 introduction of invasive alien species? | No |
| 1.7 adverse impacts on soils? | No |
| 1.8 harvesting of natural forests, plantation development, or reforestation? | No |
| 1.9 significant agricultural production? | No |
| 1.10 animal husbandry or harvesting of fish populations or other aquatic species? | No |
| 1.11 significant extraction, diversion or containment of surface or ground water? For example, construction of dams, reservoirs, river basin developments, groundwater extraction | No |
| 1.12 handling or utilization of genetically modified organisms/living modified organisms?17 | No |
| 1.13 utilization of genetic resources? (e.g. collection and/or harvesting, commercial development)18 | No |
| 1.14 adverse transboundary or global environmental concerns? | No |
| Standard 2: Climate Change and Disaster Risks |  |
| Would the project potentially involve or lead to: |  |

17 See the Convention on Biological Diversity and its Cartagena Protocol on Biosafety.

18 See the Convention on Biological Diversity and its Nagoya Protocol on access and benefit sharing from use of genetic resources.

| 2.1 areas subject to hazards such as earthquakes, floods, landslides, severe winds, storm surges, tsunami or volcanic eruptions? | No |
| --- | --- |
| 2.2 outputs and outcomes sensitive or vulnerable to potential impacts of climate change or disasters? For example, through increased precipitation, drought, temperature, salinity, extreme events, earthquakes | No |
| 2.3 increases in vulnerability to climate change impacts or disaster risks now or in the future (also known as maladaptive or negative coping practices)? For example, changes to land use planning may encourage further development of floodplains, potentially increasing the population’s vulnerability to climate change, specifically flooding | No |
| 2.4 increases of greenhouse gas emissions, black carbon emissions or other drivers of climate change? | No |
| Standard 3: Community Health, Safety and Security |  |
| Would the project potentially involve or lead to: |  |
| 3.1 construction and/or infrastructure development (e.g. roads, buildings, dams)? (Note: the GEF does not finance projects that would involve the construction or rehabilitation of large or complex dams) | No |
| 3.2 air pollution, noise, vibration, traffic, injuries, physical hazards, poor surface water quality due to runoff, erosion, sanitation? | Yes |
| 3.3 harm or losses due to failure of structural elements of the project (e.g. collapse of buildings or infrastructure)? | No |
| 3.4 risks of water-borne or other vector-borne diseases (e.g. temporary breeding habitats), communicable and noncommunicable diseases, nutritional disorders, mental health? | No |
| 3.5 transport, storage, and use and/or disposal of hazardous or dangerous materials (e.g. explosives, fuel and other chemicals during construction and operation)? | Yes |
| 3.6 adverse impacts on ecosystems and ecosystem services relevant to communities’ health (e.g. food, surface water purification, natural buffers from flooding)? | No |
| 3.7 influx of project workers to project areas? | No |
| 3.8 engagement of security personnel to protect facilities and property or to support project activities? | Yes |
| Standard 4: Cultural Heritage |  |
| Would the project potentially involve or lead to: |  |
| 4.1 activities adjacent to or within a Cultural Heritage site? | No |
| 4.2 significant excavations, demolitions, movement of earth, flooding or other environmental changes? | No |
| 4.3 adverse impacts to sites, structures, or objects with historical, cultural, artistic, traditional or religious values or intangible forms of culture (e.g. knowledge, innovations, practices)? (Note: projects intended to protect and conserve Cultural Heritage may also have inadvertent adverse impacts) | No |
| 4.4 alterations to landscapes and natural features with cultural significance? | No |
| 4.5 utilization of tangible and/or intangible forms (e.g. practices, traditional knowledge) of Cultural Heritage for commercial or other purposes? | No |
| Standard 5: Displacement and Resettlement |  |
| Would the project potentially involve or lead to: |  |
| 5.1 temporary or permanent and full or partial physical displacement (including people without legally recognizable claims to land)? | No |

| 5.2 economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation)? | No |
| --- | --- |
| 5.3 risk of forced evictions?19 | No |
| 5.4 impacts on or changes to land tenure arrangements and/or community based property rights/customary rights to land, territories and/or resources? | No |
| Standard 6: Indigenous Peoples |  |
| Would the project potentially involve or lead to: | No |
| 6.1 areas where indigenous peoples are present (including project area of influence)? | No |
| 6.2 activities located on lands and territories claimed by indigenous peoples? | No |
| 6.3 impacts (positive or negative) to the human rights, lands, natural resources, territories, and traditional livelihoods of indigenous peoples (regardless of whether indigenous peoples possess the legal titles to such areas, whether the project is located within or outside of the lands and territories inhabited by the affected peoples, or whether the indigenous peoples are recognized as indigenous peoples by the country in question)? If the answer to screening question 6.3 is “yes”, then Standard 6 requirements apply, and the potential significance of risks related to impacts on indigenous peoples must be Moderate or above. * | No |
| 6.4 the absence of culturally appropriate consultations carried out with the objective of achieving FPIC on matters that may affect the rights and interests, lands, resources, territories and traditional livelihoods of the indigenous peoples concerned? | No |
| 6.5 the utilization and/or commercial development of natural resources on lands and territories claimed by indigenous peoples? | No |
| 6.6 forced eviction or the whole or partial physical or economic displacement of indigenous peoples, including through access restrictions to lands, territories, and resources? Consider, and where appropriate ensure, consistency with the answers under Standard 5 above | No |
| 6.7 adverse impacts on the development priorities of indigenous peoples as defined by them? | No |
| 6.8 risks to the physical and cultural survival of indigenous peoples? | No |
| 6.9 impacts on the Cultural Heritage of indigenous peoples, including through the commercialization or use of their traditional knowledge and practices? Consider, and where appropriate ensure, consistency with the answers under Standard 4 above. | No |
| Standard 7: Labour and Working Conditions |  |
| Would the project potentially involve or lead to: (note: applies to project and contractor workers) |  |
| 7.1 working conditions that do not meet national labour laws and international commitments? | No |
| 7.2 working conditions that may deny freedom of association and collective bargaining? | No |
| 7.3 use of child labour? | No |
| 7.4 use of forced labour? | No |
| 7.5 discriminatory working conditions and/or lack of equal opportunity? | Yes |
| 7.6 occupational health and safety risks due to physical, chemical, biological and psychosocial hazards (including violence and harassment) throughout the project life-cycle? | Yes |

19 Forced eviction is defined here as the permanent or temporary removal against their will of individuals, families or communities from the homes and/or land which they occupy, without the provision of, and access to, appropriate forms of legal or other protection. Forced evictions constitute gross violations of a range of internationally recognized human rights.

| Standard 8: Pollution Prevention and Resource Efficiency |  |
| --- | --- |
| Would the project potentially involve or lead to: |  |
| 8.1 the release of pollutants to the environment due to routine or non-routine circumstances with the potential for adverse local, regional, and/or transboundary impacts? | Yes |
| 8.2 the generation of waste (both hazardous and non-hazardous)? | No |
| 8.3 the manufacture, trade, release, and/or use of hazardous materials and/or chemicals? | No |
| 8.4 the use of chemicals or materials subject to international bans or phase-outs? For example, DDT, PCBs and other chemicals listed in international conventions such as the Montreal Protocol, Minamata Convention, Basel Convention, Rotterdam Convention, Stockholm Convention | No |
| 8.5 the application of pesticides that may have a negative effect on the environment or human health? | No |
| 8.6 significant consumption of raw materials, energy, and/or water? | No |

ANNEX 3: OFFLINE PROJECT RISK REGISTER TEMPLATE

| Project Title: Inclusive Recovery Support for Resilience and Human Security in Ukraine | Project Number: 01003977 | Date: 10-Feb-25 |
| --- | --- | --- |

Reputational risks include associations (real or perceived) with parties of the conflict, political actors, human-rights violators, which need to be managed through local conflict analyses, wide stakeholder engagement, communication, and coordination with human rights and political arms of the UN system. In addition, regular consultation with counterparts and regular transparent communication of project activities to all stakeholders involved will help mitigate reputational risk. All stakeholders (the donors, other agencies, and communities themselves) should be kept fully informed about the nature and level of risk involved. In addition to communicating intentions and achievements, controlling the narrative is also an essential component in the management of reputational risk. The risk analysis for this programme, identifying the nature of major risks, its probability and likely impact, proposed mitigation measures and responsibility for their implementation is listed below:

| # | Event | Cause | Impact(s) | Risk Category and Sub-category (including Risk Appetite) | Impact, Likelihood & Risk Level (see Annex 3 Risk Matrix) | Risk Valid From/To | Risk Owner (individual accountable for managing the risk | Risk Treatment |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Escalation of attacks and further deterioration of security situation in Ukraine | As a result of the ongoing war in Ukraine, specifically spread of hostilities and attacks by Russian/Pro-Russian forces | (1) enhanced security restrictions, that may restrict staff movement, direct consultations with stakeholders/partners and implementation of project activities. (2) potential risk of injury or detention to project staff, contractors, partners, grantees or beneficiaries impacting partners’ ability and commitment to execute activities | 8. SAFETY AND SECURITY (8.1. Armed conflict) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 3 - Moderately likely Impact: 4 - Extensive Risk level: SUBSTANTIAL (equates to a risk appetite of OPEN) | From: 31 March 2025 To: 31 March 2026 | Risk Owner: Project Manager Risk Treatment owner: National/Local Authorities, Project Security Specialist/ UNDP Security, UNDSS | Risk Treatment 1.1: UNDP (security and project security specialist) will work in close coordination with UNDSS and the national government while ensuring Regular negotiations with military, formal and informal authorities, and community leaders to secure a safe environment for implementing partners and community members themselves. Project activities will take into account security situation in Ukraine and the necessary revisions will be made to ensure that project activities continue to the extent possible. This may entail scale down of project activities in affected areas until acceptable level of stability is restored. |
|  |  |  |  |  |  |  |  | Risk Treatment 1.2: Work with implementing partners with local knowledge and presence for community-based security systems (e.g. for early warning) for each target area. UNDSS/UNDP security coordination and effective information sharing on both current and emerging threats |
|  |  |  |  |  |  |  |  | Risk Treatment 1.3: Added security measures to be considered such as procurement of armored vehicles for required locations, building adequate local security costs into the budget of the programme. Tested business continuity and security plans and standard operating procedures in place and updated regularly to mitigate the impact of existing and potential threats to UNDP staff. Provide security training to UNDP staff and implementing actors. |
| 2 | There is a risk of lack of willingness of stakeholders to cooperate with the project or that changes may occur at the partner government institutions during or after the war, leading to a substantial revision of strategic priorities and a potential lack of commitment to project objectives | As a result of political instability, decrease in public support to government due to inadequate crisis management, growing economic hardships and deteriorating social conditions. High expectation from government partners for the project. | Which will impact in delays in project activities or inability to achieve project’s expected results, especially slowdown of policy and institutional work and weakened sustainability of project interventions | 1. SOCIAL AND ENVIRONMENTAL (1.12. Stakeholder engagement) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 3 - Moderately likely Impact: 3 - Intermediate Risk level: LOW (equates to a risk appetite of CAUTIOUS) | From: 31 March 2025 To: 31 March 2026 | Risk Owner: Project Manager Risk Treatment owner: National/Local Authorities, Pillar/Output Leads | Risk Treatment 2.1: Project will foster strong relationships and regular communication with partner government institutions to build trust and maintain a shared understanding of project goals and objectives. |
| 3 | Sudden change or increase of the needs due to volatile conflict/war situations | As a result of volatile situations with high uncertainty, it is difficult to predict upcoming changes and emerging needs | The relevance and effectiveness of the initially planned project interventions can be reduced. | 3. OPERATIONAL (3.3. Flexibility and opportunity management) - UNDP Risk Appetite: EXPLORA TORY TO OPEN | Likelihood: 3 - Moderately likely Impact: 2 - Minor Risk level: LOW (equates to a risk appetite of CAUTIOUS) | From: 31 March 2025 To: 31 March 2026 | Risk Owner: Project Manager Risk Treatment owner: National/Local Authorities, Pillar/Output Leads | Risk Treatment 3.1: The Project will ensure that all stakeholders are fully involved at the inception of the project and involve all beneficiaries as partners to decision-making re design and implementation of the programme. Deploy the special measures assigned to the Country Office to quickly implement new/revised interventions. |
|  |  |  |  |  |  |  |  | Risk Treatment 3.2: The project will conduct regular monitoring and situation assessment to identify emerging or changing needs and take adoptative management approach to flexibly meet the latest needs and situations. |
| 4 | PSEA Incidents | As a consequence of the conflict and the high number of people in need in the selected areas, there is a heightened risk of sexual exploitation and abuse (SEA) by project staff, beneficiaries, or other individuals involved in the project. | The beneficiaries can be suffered from inappropriate or unethical behaviour of CO staff, project responsible partners, or the government counterparts. Partner or Contractor Misconduct may happen during the project implementation PSEA measures in place, leading to risks of misconduct UNDP_reputation may be affected | 3. OPERATIONAL (3.3. Flexibility and opportunity management) - UNDP Risk Appetite: EXPLORA TORY TO OPEN | Likelihood: 2 - Less likely Impact: 3 - Intermediate Risk level: LOW (equates to a risk appetite of CAUTIOUS) | From: 31 March 2025 To: 31 March 2026 | Risk Owner: Project Manager Risk Treatment owner: National/Local Authorities, Responsible Parties, Pillar/Output Leads PSEA Officer | Risk Treatment 4.1: The Project, with the support of the PSEA Officer, will ensure that partners and their staff uphold the highest standards of conduct for PSEA, which includes familiarizing themselves with UNDP's policies and procedures on PSEA and being informed about the channels available for reporting misconduct. Risk Treatment 4.2: Awareness-raising and training will be conducted, aiming at 100% of partners and their staff undergo the online PSEA training and provide the project staff with certificates |

ANNEX 4: Low-Value Grants (LVG) under the Project

Provision of grants under the Project follows the UNDP Operational Guide on Low-Value Grants (LVG). This Annex outlines the grant component of the initiative, describes types of activities that will be offered to partners to apply for (general themes for calls for proposals), wider criteria that the grant proposals will be assessed against, arrangements for the Grant Selection Committee, and other relevant considerations.

Purpose of the LVGs that will be awarded through the project

The LGVs to be issued under the Project will be issued for the following purposes:

- Strengthening policy framework and practice for community-based social services, health, inclusive education, physical and mental rehabilitation, assistive technology services for war-affected populations, including persons with disabilities and veterans within the framework of Victims Assistance

- Awareness-raising on mine prevention activities and work with explosive ordnance victims in war-affected communities.

- Responding to human rights challenges in Ukraine and strengthening the capacity of national actors in evidence-based investigation and processing of human rights violations, war crime cases, CRSV crimes, and armed conflict-related property loss and claims, provision of legal services to war affected population.

- Conducting youth exchanges in the selected communities for young people from all regions of Ukraine as well as renovating and opening youth community centers.

- Strengthening the capacities of civil society and authorities at all levels through development of a communication strategies, launching media literacy awareness campaign, research on disinformation.

- Strengthening the capacities of civil society and other stakeholders (local communities/women/youth etc.) to promote anti-corruption initiatives in the development and recovery process.

- Supporting economic recovery, enhancing employment, and creating income-generation opportunities for the war-affected population.

Total amount of the project budget that will be allocated to LVGs

The overall budget for LVGs under the auspices of the Project shall not exceed an equivalent of USD 4,500,000 and will be subdivided between several calls for proposals (CFPs). The CFPs will include the following broad themes and activities (sums indicate proposed ceiling expenses for one CFP which could generate several grantees receiving awards):

- Strengthening policy framework and practice for community-based social services, health, inclusive education, physical and mental rehabilitation, assistive technology services for war-affected populations, including persons with disabilities and veterans within the framework of Victims Assistance (up to USD 500 000).

- Responding to human rights challenges in Ukraine and strengthening the capacity of national actors in evidence-based investigation and processing of human rights violations, war crime cases, CRSV crimes, and armed conflict-related property loss and claims (up to USD 500,000).

- Supporting economic recovery, enhancing employment, and creating income-generation opportunities for the war-affected population (up to USD 3,000,000).

- Engaging young men and women in recovery processes in Ukraine through youth exchange programmes (up to USD 300,000).

- Supporting the civil society and other stakeholders (local communities/women/youth etc.) to promote transparency in Ukraine’s recovery process through anti-corruption initiatives, media literacy awareness, development of a communication strategies, and research on disinformation (up to USD 200,000).

Funding provided to each grant recipient cannot exceed USD 150,000 per grant. To receive multiple grants, the grant recipient must have produced the results agreed to in the prior grant agreement, and a new grant agreement must be approved by the Grant Selection Committee. The same entity could receive separate grants under different UNDP projects with a cumulative ceiling of $300,000 in the programme period.

Grant Selection Committee for the Project

The Grant Selection Committee will, thus, be the authorized body in charge of the review, selection and appraisal of submitted grant proposals. The Grant Selection Committee shall have the following tasks:

- Approve final set of criteria that the grant proposals will be assessed against taking into account the Eligibility criteria enlisted in this Annex;

- Review and appraise grant proposals;

- Recommend grant proposals for funding or rejection.

Grant Selection Committee members:

- Project Manager, DG

- Project Coordinator, DG

- Project Manager, EE

- Programme Analyst, DG

- Programme Analyst, EE

- Project Manager, IDRPB

- Senior Business Development Specialist, IDRPB

Secretary:

- Finance Grants Associate, DG

- Project Associate, DG

- Grant Associate, IDRPB

- Project Associate, EE

Members with an advisory vote:

- Representative of CSOs and/ or other stakeholders

Alternative members:

- Project Analyst, DG

- Project Analyst, EE

- Capacity Development Officer, DG

- Capacity Development Analyst, DG

- Small Grant Analyst, DG

- Specialist on Employment and Entrepreneurship, IDRPB

- Communication Analyst, DG

Alternative Secretaries:

- Project Associate, DG

- Project Associate, EE

- Programme Associate, IDRPB

The Selection Committee may decide to request independent expert opinion during the LVG proposal appraisal process. Meetings of the Selection Committee will be held subject to the submission of the grant proposals. The Selection Committee meetings will be organized and facilitated by the Project staff, responsible for the respective activity.

LVG eligibility criteria and evaluation matrix (criteria that the LVG proposals will be assessed against)

The LVG proposals coming in for the Project’s consideration will be measured, first and foremost, against the admission criteria. To be considered for funding, the proposal must be submitted by an organization that:

- has a status of a municipal, non-governmental, public or charitable organization or an association of CSOs officially registered in Ukraine;

- has a track record of active operation of at least one year;

- has a proven track record of cooperation with the international donor community, proper project implementation and reporting will be considering as advantage.

Upon completing the pre-screening process (done by the Project team, responsible for the respective activity), the Selection Committee shall convene and assess those applications that meet the minimum criteria against the following evaluation matrix (Grant Selection Criteria):

| # | Criterion | Max pts |
| --- | --- | --- |
| 1 | Responsiveness of the LVG project proposal to the core theme of the CFP | 25 |
| 2 | Ability of the proposed LVG project team (staff and proposed consultants) to cope with the scope of works described in the project proposal | 20 |
| 3 | Quality of the proposed networks and instruments for result dissemination | 10 |
| 4 | Demonstrated experience in LVG implementation | 15 |
| 5 | Demonstrated sustainability considerations of the project | 10 |
| 6 | Quality and realistic nature of the budget proposal | 20 |
|  | Total maximum: | 100 pts |

LVG eligible costs

Eligible costs must:

- be necessary for carrying out the project activities;

- have been incurred by the applicant during the implementation period;

- comply with the principles of sound financial management, in particular, value for money and cost-effectiveness;

- be adequately recorded, identifiable and verifiable, and be backed by original supporting documents.

UNDP LVG costs may only be used to cover the following costs:

- staff salaries and expert fees;

- communication and information services;

- purchase of consultative services and contracts provided that these are essential to project goals and objectives;

- procurement of equipment for emergency medical assistance, healthcare services, telemedicine, rehabilitation, psychological support, social services provision, prosthetics workshops, inclusive education institutions, accessible sports, leisure, and culture;

- procurement of vehicles for emergency medical assistance, mobile rehabilitation, and social services provision;

- procurement of equipment, small construction works and small-scale repairs for ensuring accessibility and barrier-free public places, administrative buildings, and services;

- procurement of assistive devices and prosthetics items;

- renting, catering, and other services envisaged by the project activities;

- printing and copying;

- audio, video production costs:

- placement and promotion in a media:

- utility services;

- consumables and supplies;

- travel costs (provided that travel complies with internal UNDP regulations).

Not more than 80% of the grant funds may be spent of equipment, provided a clear justification is offered as to its need to achieve project goals.

The following costs are ineligible:

- costs of project proposal preparation;

- academic research;

- debts;

- currency exchange losses.

Process for soliciting and reviewing LVG proposals

The CFPs will be advertised through the web sites of the following organizations:

- UNDP Ukraine: www.undp.org.ua and its Facebook page

- as well as other relevant social networks and information portals.

Applications (project proposals) must be developed in Ukrainian according to templates that will be part of the CFP.

The application package shall consist of

- The filled-out Application form (done on a computer as a Microsoft Word file);

- Copy of Charter of the applicant organization (PDF);

- Copy of State registration certificate (PDF);

- Banking details (PDF);

- Resumes of proposed specialists for project implementation (Microsoft Word or PDF)

- Other relevant supporting documentation including reference letters, report samples or others (Microsoft Word or PDF).

The document package shall be archived as *.zip or *.rar and not be password-protected it shall not be larger than 35 Mb total. The package shall be sent to the designated e-mail with the letter title containing the name of the competition as stated in the CFP. Applications sent through means different from the one described above will not be considered.

The further steps in the LVG proposal assessment process will follow this sequence:

- The Project team, responsible for the respective activity, pre-screens LVG project proposals against the eligibility criteria to be admitted for the Selection Committee review and appraisal;

- The Selection Committee convenes and reviews all eligible LVG project proposals based on evaluation criteria and recommends those that have gained the biggest number of points for concluding the agreements;

- Based on the capacity assessment results of the short-listed CSOs, the Project team submits the Selection Committee minutes (list of SCOs recommended for funding) for approval;

- UNDP concludes grant agreements with the CSOs.

Ukraine - Rapid Damage and Needs Assessment : February 2022–2023

This figure covers the nearly two-year period from Russia’s invasion of Ukraine on 24 February 2022, to 31 December 2023.

Source: RDNA Assessment team. Note: The maps draw on damage data as collected and assessed under the RDNA2 (left) and RDNA3 (right) respectively. There were data limitations for certain regions.

UNDP energy damage assessment for Ukraine reveals continued vulnerabilities

UNDP in Ukraine advocates for disability inclusion at UN event | United Nations Development Programme

Ten Years of Occupation by the Russian Federation: Human Rights in the Autonomous Republic of Crimea and the City of Sevastopol, Ukraine | OHCHR

https://ukraine.un.org/en/289064-protection-civilians-armed-conflict-%E2%80%94-january-2025

UN Commission has found an array of war crimes, violations of human rights and international humanitarian law have been committed in Ukraine | OHCHR

UN Ukraine Annual Recovery Results Report 2023

It should be noted that the oblasts under each category are listed for an indicative purpose and not conclusive. Although the project will plan its activities focusing on the selected priority oblasts as the geographical focus for area-based local planning for transformational recovery, UNDP may identify and implement the activities outside of the target areas to meet the critical needs to achieve the output objectives and flexibly respond to unexpectedly emerged incidences or evolving needs.

https://www.undp.org/ukraine/undp-resilience-building-and-recovery-programme

Q1(30 Mar-June 2025); Q2 (July-Sept 2025); Q3 (Oct-Dec 2025); Q4(Jan- Mar 2026)

To be used where UNDP is the Implementing Partner

To be used where the UN, a UN fund/programme or a specialized agency is the Implementing Partner

The three development settings in UNDP’s 2018-2021 Strategic Plan are: a) Eradicate poverty in all its forms and dimensions; b) Accelerate structural transformations for sustainable development; and c) Build resilience to shocks and crises

The six Signature Solutions of UNDP’s 2018-2021 Strategic Plan are: a) Keeping people out of poverty; b) Strengthen effective, inclusive and accountable governance; c) Enhance national prevention and recovery capacities for resilient societies; d) Promote nature based solutions for a sustainable planet; e) Close the energy gap; and f) Strengthen gender equality and the empowerment of women and girls.

The three development settings in UNDP’s 2018-2021 Strategic Plan are: a) Eradicate poverty in all its forms and dimensions; b) Accelerate structural transformations for sustainable development; and c) Build resilience to shocks and crises

Operationalizing Leaving No One Behind good Practice Note for UNCT (https://unsdg.un.org/resources/leaving-no-one-behind-unsdg-operational-guide-un-country-teams)

Operationalizing Leaving No One Behind Good Practice Note for UNCT (https://unsdg.un.org/resources/leaving-no-one-behind-unsdg-operational-guide-un-country-teams)

For a checklist and evidence template, please see the Embedding Digital Thinking into Project Design Guidelines (https://rebrand.ly/DbDProjectGuideEN).

The ten UNDP Digital Standards are: a) Start with the need; b) Bridge the digital divide; c) Test early and often; d) (Perhaps) Don’t build it; e) Do no harm; f) Form the Right Team; g) Measure What Matters; h) Follow The UNDP Data Principles; i) Default to Open; and j) Plan for the Long Term (https://www.undp.org/digital/standards).

The eight UNDP Digital Principles are: a) Safeguard personal data; b) Uphold the highest ethical standards; c) Manage Data Responsibly; d) Make data open by default; e) Plan for reusability and interoperability; f) Empower people to work with data; g) Expand frontiers of data; and h) Be aware of data limitations (https://data.undp.org/data-principles).

The ten UNDP Digital Standards are: a) Start with the need; b) Bridge the digital divide; c) Test early and often; d) (Perhaps) Don’t build it; e) Do no harm; f) Form the Right Team; g) Measure What Matters; h) Follow The UNDP Data Principles; i) Default to Open; and j) Plan for the Long Term (https://www.undp.org/digital/standards).

The eight UNDP Digital Principles are: a) Safeguard personal data; b) Uphold the highest ethical standards; c) Manage Data Responsibly; d) Make data open by default; e) Plan for reusability and interoperability; f) Empower people to work with data; g) Expand frontiers of data; and h) Be aware of data limitations (https://data.undp.org/data-principles).

The ten UNDP Digital Standards are: a) Start with the need; b) Bridge the digital divide; c) Test early and often; d) (Perhaps) Don’t build it; e) Do no harm; f) Form the Right Team; g) Measure What Matters; h) Follow The UNDP Data Principles; i) Default to Open; and j) Plan for the Long Term (https://www.undp.org/digital/standards).

The eight UNDP Digital Principles are: a) Safeguard personal data; b) Uphold the highest ethical standards; c) Manage Data Responsibly; d) Make data open by default; e) Plan for reusability and interoperability; f) Empower people to work with data; g) Expand frontiers of data; and h) Be aware of data limitations (https://data.undp.org/data-principles).

* Note: revised July 2022 modifying presumption of risk significance from Substantial or higher to Moderate or higher.