## Hárok1
Annex 3: Financial Report and indicative budget for the next reporting period
Stakeholder Engagement for Uranium Legacy Remediation - Phase III
INSC/2024/454-274, 1st progress report
Implementation period: 24 months
Financial report for the period 10/12/2024 - 9/12/2025
Results/Activities Description | Indicative breakdown for Year 1 (USD) | Indicative breakdown for Year 2 (USD) | Total (USD) | Total expenses USD 10/12/2024-9/12/2025 | Commitments USD as of 9/12/2025 | Combined actual expenses + Legal commitments USD | Indicative budget for year 2 - USD 10/12/2025-9/12/2026 | Deviation between the budget and overall allocated amount in % | Total USD (Reported amount + budget for the next reporting period) | Description of main activities, justification of costs The planning is based on the best estimations of costs and the tentative allocation of funds will not harm implementation of activities. Part of the costs has been pre-planned in 2025 and committed for enabling the implementation through 2026.
Outcome 1. Engagement, capacity building & awareness raising of local stakeholders. Regional cooperation (OSCE led)
Output 1.1. Awareness raising campaign targeting key local, regional and national project stakeholders implemented
Consultants (national & international) | 35705.6 | 39053 | 74758.6 | 7009.35 | 28696.25 | 35705.6 | 30364 | -11.62% | 66069.6 | KGZ: national and international consultants to support radioactive safety consultations and ULS Association establishment / TJK : Agreement with the Aarhus Center in Khujand to expand and develop the Green Patrols initiative in the UL zones / UZB: National consultants to develop awareness raising campaigns and trainings on radioactive safety
Contractual services, companies | 77420.8988 | 77420.8988 | 154841.7976 | 3477.49 | 73943.41 | 77420.9 | 62886 | -9.387% | 140306.9 | KGZ: printing and visibility materials for awareness-raising campaigns prizes for Green Patrols / TJK : support of mini- projects for Green Patrols ; Regional Summer Camp for Green Patrols in Guliston ; printing and visibility materials for awareness-raising campaigns /UZB: printing and visibility materials for awareness-raising campaigns prizes for Green Patrols, preparing video lessons
Workshops, trainings, consultations, study visits | 15342.25 | 15342.25 | 30684.5 | 0 | 15342.25 | 15342.25 | 44030 | 93.49% | 59372.25 | KGZ: trainings on radiation safety, consultations, preparation of statutory documents for Association of ULSs / TJK: trainings and workshops on radiation safety conducted by the CBRN Agency / UZB: trainings on radiation safety, preparation of statutory documents, equipment for the trainings
Sub-Total 1.1 | 128468.7488 | 131816.1488 | 260284.8976 | 10486.84 | 117981.91 | 128468.75 | 137280 | 2.099% | 265748.75
Output 1.2 Capacity building institutional set up | [8 empty] | 0
Consultants (national & international) | 30126.6 | 36821.4 | 66948 | 1176.4706 | 30126.6 | 31303.0706 | 15400 | -30.24% | 46703.0706 | KGZ: national consultants on tourism development in Min-Kush and Mailuu-Suu \ TJK : national consultants to support socio-economic development & investments in the UL zones /UZB: National consultant on tourism development, national consultant on museum design
Contractual services, companies | 75595.45 | 75595.45 | 151190.9 | 847.0588 | 75595.45 | 76442.5088 | 53870 | -13.81% | 130312.5088 | KGZ: Osh Aarhus Center and PEICs operations, public hearings and meetings with population \ TJK: Donation of equipment to the CBRN PEIC in Buston \ UZB: Young Atomist concept equipment, Equipment for the Museum in Yangiabad (e.g. LCD projectors, TV screens, laptops)
Workshops, trainings, consultations, audio visuals | 29289.75 | 29289.75 | 58579.5 | 0 | 15342.25 | 15342.25 | 37145.61 | -10.4% | 52487.86 | KGZ: Touristic Forum in Min-Kush, study and media tours for tourism development in Min-Kush and Mailuu-Suu \ TJK: Investment Forum in Khujand to attract investments to the UL zones\ UZB: Media tours for journalists, bloggers, and tour guides
Sub-Total 1.2 | 135011.8 | 141706.6 | 276718.4 | 2023.5294 | 121064.3 | 123087.8294 | 106415.61 | -17.06% | 229503.4394
Output 1.3. Regional cooperation: cross-country coordination and knowledge exchange implemented, M&E | [8 empty] | 0
Workshops, trainings, consultations, audio visuals | 2979 | 2979 | 5958 | 0 | 5579 | 5579 | 5372 | 83.8% | 10951 | KGZ/TJK/UZB : exchange study-tour for ULS mayors to Germany
Travel | 29010.8 | 29010.8 | 58021.6 | 3537.91 | 25472.64 | 29010.55 | 37000 | 13.77% | 66010.55 | KGZ/TJK/UZB :Monitoring visits, participation in local, regional events, travel of participants of regional meetings, study /press tours
Staff costs | 147504.2968 | 147504.2968 | 295008.5936 | 3080.79 | 124896.61 | 127977.4 | 195800 | 9.752% | 323777.4 | KGZ/TJK/UZB : Project officer, 3 project assistants in Kyrgyzstan, Tajikistan, Uzbekistan
Project office costs | 2600 | 2600 | 5200 | 0 | 0 | 0 | 5200 | 0% | 5200 | KGZ/TJK/UZB : OSCE field offices utilities, fuel and other indirect expenses
Sub-Total 1.3 | 182094.0968 | 182094.0968 | 364188.1936 | 6618.7 | 155948.25 | 162566.95 | 243372 | 11.46% | 405938.95
Total for Outcome 1 | 445574.6456 | 455616.8456 | 901191.4912 | 19129.0694 | 394994.46 | 414123.5294 | 487067.61 | -3.904e-05% | 901191.1394
Outcome 2. Improved socio-economic conditions in target communities driven by local participatory planning, gender-sensitive solutions, business development, and strengthened regional cooperation (UNDP led) | [8 empty] | 0
Output 2.1. Local participatory planning and implementation, and associated capacity building of local partners |  |  |  | 0 |  | 0 |  |  | 0
National consultants | 22316 | 20084.4 | 42400.4 | 13844 | 1000 | 14844 | 25546 | -4.741% | 40390 | UZB: revision of CDP in Yangiabad, KGZ: consultancy for capacity building
Service Contracts--Individuals | 58595.1212 | 58595.1212 | 117190.2424 | 55486.44 | 0 | 55486.44 | 76320 | 12.47% | 131806.44 | UNDP staff implementing the project - managers, coordinators, DRR specialists, associates/assistants
Contractual services, companies | 118274.8 | 65832.2 | 184107 | 15141.9 | 0 | 15141.9 | 170033.95 | 0.5806% | 185175.85 | KGZ: purchase of radiological equipment for MES
Workshops, trainings, regional consultations | 15042.0998 | 17273.6998 | 32315.7996 | 7099.84 | 0 | 7099.84 | 6499.66 | -57.92% | 13599.5 | UZB: capacity building trainings for local partners and communities (rent of premises, catering)
Travel | 17852.8 | 14505.4 | 32358.2 | 11290.43 | 1037.28 | 12327.71 | 8666.91 | -35.12% | 20994.62 | KGZ: monitoring travel for 3 pilot sites, travel for the radiological equipment handover ceremony, UZB: construction and small grants monitoring visits
Audio Visual&Print Prod. | 9484.3 | 9484.3 | 18968.6 | 2095.57 | 0 | 2095.57 | 0 | -88.95% | 2095.57 | N/A
Sub-Total 2.1 | 241565.121 | 185775.121 | 427340.242 | 104958.18 | 2037.28 | 106995.46 | 287066.52 | -7.787% | 394061.98
Output 2.2. Tailored community level solutions designed and implemented in target ULSs, regional cooperation, M&E | [8 empty] | 0
Grants/pilot projects | 110651.6544 | 230042.2544 | 340693.9088 | 0 | 0 | 0 | 393578.53 | 15.52% | 393578.53 | KGZ: Grants for pilot sites, UZB: 2 infrastructure projects in Charkesar, solar panels project in Yangiabad, small grants programme
Consultants (national & international) | 24547.6 | 39053 | 63600.6 | 8793 | 27447 | 36240 | 50673.73 | 36.66% | 86913.73 | IRH: consultancy for possible formulation of next phase of project UZB: engineer, trainers KGZ: consultancy to support small grants implementation
Service Contracts--Individuals | 95243.5722 | 92248.765 | 187492.3372 | 58682.48 | 0 | 58682.48 | 170600 | 22.29% | 229282.48 | UNDP staff implementing the project - managers, coordinators, DRR specialists, associates/assistants
Staff costs | 67753.6076 | 67753.6076 | 135507.2152 | 20276.4684 | 0 | 20276.4684 | 14900 | -74.04% | 35176.4684 | UNDP staff implementing the project - managers, coordinators, DRR specialists, associates/assistants
Workshops, trainings, regional activities | 30663.2998 | 30663.2998 | 61326.5996 | 661.55 | 0 | 661.55 | 49053 | -18.93% | 49714.55 | KGZ/UZB/IRH: Trainings for local stakeholders, regional event, final project meeting - to be combined with travel budget
Audio Visual&Print Prod. | 15621.2 | 15732.78 | 31353.98 | 207.38 | 0 | 207.38 | 20816.65 | -32.95% | 21024.03 | KGZ production of visibility items and materials for project related events, UZB visibility and promotional materials
Travel | 23431.8 | 27848.1364 | 51279.9364 | 3592.74 | 0 | 3592.74 | 79986.1 | 62.99% | 83578.84 | KGZ/UZB/IRH: Monitoring visits, participation in regional events, travel of participants of regional meetings, study tours
Project office costs | 6694.8 | 6694.8 | 13389.6 | 6340.17 | 11313.78 | 17653.95 | 1000 | 39.32% | 18653.95 | KZ/UZB: Miscellaneous costs not covered under other lines
Sub-Total 2.2 | 374607.534 | 510036.6432 | 884644.1772 | 98553.7884 | 38760.78 | 137314.5684 | 780608.01 | 3.762% | 917922.5784
Sub-total Outcome 2 | 616172.655 | 695811.7642 | 1311984.4192 | 203511.9684 | 40798.06 | 244310.0284 | 1067674.53 | 1.061e-05% | 1311984.5584
Total for Outcomes 1+2 | 1061747.3006 | 1151428.6098 | 2213175.9104 | 222641.0379 | 435792.52 | 658433.5579 | 1554742.14 | -9.603e-06% | 2213175.6979
Remuneration (7%) | 74322.311 | 80600.0027 | 154922.3137 | 15584.8727 | 0 | 15584.8727 | 139337.4298 | -7.28e-06% | 154922.3025
Total | 1136069.6116 | 1232028.6125 | 2368098.2241 | 238225.9105 | 435792.52 | 674018.4305 | 1694079.5698 | -9.451e-06% | 2368098.0003
0
Of the total 674 018,43 USD presented above USD 238 225,91 corresponds to eligible expenses (as per IPSAS terminology) and USD 435 792,52 represents legal commitments currently in force between UNDP (or UNDP’s implementing partners) and a third party.
Of the total 674 018,43 USD presented above USD 650 157,43 corresponds to the contribution by the EU, USD 21 695,82 corresponds to the contribution by UNDP and USD 2 165,18 corresponds to the contribution by the OSCE.
Of the total expenses of 238 225,91 USD, reproted for the period 10/12/2024-9/12/2025, USD 214 364,91 corresponds to the contribution by the EU, USD 21 695,82 corresponds to the contribution by UNDP and USD 2 165,18 corresponds to the contribution by the OSCE.
Of the total commitments of 435 792,52 USD reported as of 9/12/2025, USD 435 792,52 corresponds to the contribution by the EU, there are no commitments corresponding to UNDP and OSCE contribution.
Description |  | Amount USD
The Total Cost of action in USD as per article 3.1 Special Conditions |  | 2368098
The EU Contribution in USD as per article 3.1 Special Conditions |  | 2231600
The EU Prefinancing in USD |  | 1071362
The Total Project Costs (reporting period) |  | 674018.4305
The Total Project Costs (reporting period) - the EU contribution |  | 650157.43
The % of Total EU Costs Vs the EU pre-financing (1st installment) |  | 60.69%
Request of the second pre-financing as per SC art 4.2 and GC art 17.1 |  | 1060442.03