## Project Indicators
Project Indicators Monitoring
Country Programme |  | UNDP in Lao PDR
Project Name: |  | SGP OP8-Part 1
Project ID: |  | 1004260
Date of updates: |  | 2026-06-18
Instruction:
The frequency of data tracking is on a quarterly basis
The indicators are tracked for the whole project life cycle and it is counted cummulatively
The information on the baselines, targets and indicators are extracted from the Project Documents or the Multi Year Workplans
The data below is provided as a sample only and should be deleted prior to use
Global Indicators | [12 empty] | Country Programme Contributions
Indicator Level (Objective/Outcome and, or Output/Component) | Indicator Description | Strategic Initiatives | Data Collection Methods | Risks/Assumptions | Focal Areas | Baseline | Mid-Term Target | Global Indicators/End of Project Target | Responsible Party | Means of Verification/Data Source | Frequency of reporting | Baseline (2023) | Target 2024 | Actual 2024 | Target 2025 | Actual 2025 | Target 2026 | Actual 2026 | Target 2027 | Actual 2027 | Target 2028 | Actual 2028 | Cumulative Target | Cumulative Progress | On track? | Supporting Documents (must be annexed to report)
Objective: Local CSOs and CBOs in landscape around the world access grant financing and technical assistance, including capacity development and knowledge sharing to maintain and enhance their socio-ecological resilience, well-being and socio-economic conditions for Global Environmental Benefits.
Mandatory GEF Core Indicator 1: People benefitting from GEF-Financed Investments disaggregated by sex (count), (GEF core indicator 11) | This indicator measures the number of individuals who directly or indirectly benefit from project activities supported through GEF-financed investments. Benefits may include improved livelihoods, enhanced access to natural resources, increased food and water security, improved ecosystem services, strengthened resilience to climate change, access to sustainable energy, reduced exposure to environmental risks and pollution, improved knowledge and capacities, or other socio-economic and environmental gains resulting from project interventions. |  | Grantee monitoring reports, impact reviews, SGP database | Project are designed in a gender-responsive manneer. Monitoring and evaluation processes are designed to systematically desaggregate data by gender |  | 812,854 (449,588 female; 363,266 male); source: 2023 AMR | 150,000 (of whom 70,000 are female) | 500,000 (of whom 250,000 are female) | UNDP | Grantee monitoring report; impact review; SGP database | Annually | 0
Mandatory GEF CORE Indicator 3: Area of Land and Ecosystems under Restoration (hectare), (GEF core indicator 3.1) | This indicator measures the total area of degraded terrestrial, freshwater, coastal, or marine ecosystems that are under restoration as a result of project-supported interventions. Restoration refers to actions that assist the recovery of ecosystem structure, functions, biodiversity, productivity, and ecosystem services in areas that have been degraded, damaged, or converted. The indicator captures both active and passive restoration efforts aimed at improving ecological integrity and enhancing environmental, social, and economic benefits. | Community-based conservation of threatened ecosystems and species, including eco-tourism; | Grantee monitoring reports, impact reviews, SGP database | Restoration plans are adaptable to changing environmental and socio-economic conditions | Biodiversity | 31,757; source: 2023 AMR | 70,000 ha | 225,000 ha | UNDP | Annual Monitoring Reprot (AMR) | Annually | 0 | 0 | 0 | 0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  | To summerize from the progress report of the grantee partners
Mandatory GEF CORE Indicator 4: Area of Land and Landscape Under Improved Practices (excluding projected areas; hectare), (GEF core indicator 4.1 and 4.3) | This indicator measures the total area of terrestrial landscapes where improved environmental management, conservation, restoration, or sustainable production practices have been adopted as a result of project interventions. It captures areas under active management that generate global environmental benefits, including biodiversity conservation, climate change mitigation and adaptation, land degradation neutrality, sustainable forest management, sustainable agriculture, watershed protection, and ecosystem restoration. Protected areas reported under separate indicators should not be included. | Community-based conservation of threatened ecosystems and species, including eco-tourism; | Grantee monitoring reports, impact reviews, SGP database | Collaboration among stakeholders, including government agencies, non-governmental organizations, and local communities. Adequate technical knowledge and information on improved land management practices are accessible to land users and relevant stakeholders. | Biodiversity | 2,121,391 (4.1) 617,865 (4.3); source: 2023 AMR | 1,100,000 ha | 3,800,000 ha | UNDP | AMR | Annually | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project component 1: Strategic Planning and Multi-Stakeholder Governance
Project outcome 1.1: Enabling environment strengthened for effective community-driven integrated approaches
Indicator 8: number of representatives from social inclusion group (indigenous people, women, youth, persons with disability, farmers, other marginalized groups) meaningfully engage in multi-stakeholder dialogue platforms | This indicator measures the number of representatives from social inclusion groups who actively and meaningfully participate in multi-stakeholder dialogue platforms supported by the project. It captures the extent to which traditionally underrepresented and marginalized groups are engaged in consultations, planning, decision-making processes, policy discussions, knowledge-sharing events, and governance mechanisms related to environmental sustainability and community development. Meaningful engagement refers to participation that enables individuals to express their views, contribute to discussions, influence decisions, and take part in collective actions, rather than simply attending meetings. | Capacity Development | 1500 multi-stakeholder governance and dialogue platforms, records of meetings | Government and stakeholders are actively engaged. Stakeholders have the capacity to generate clear outcomes and lessons learned. | Multi-focal areas | 4,579 (total number of representatives) | 700 | 1500 | UNDP | Terms of reference multi-stakeholder governance and dialogue platforms and records of meetings | Annually | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yes | Collective information from the progress and or final reports of grantee partners
Indicator 10: Number of CSO-government-private sector dialogues formed or strengthened | his indicator measures the number of formal or informal dialogue mechanisms, platforms, forums, working groups, partnerships, or engagement processes involving civil society organizations (CSOs), government institutions, and private sector actors that have been established or strengthened through project support. The indicator captures efforts to enhance multi-stakeholder collaboration, coordination, information exchange, joint problem-solving, and collective action on environmental sustainability, climate change, natural resource management, chemicals and waste management, and sustainable development issues. | Capacity Development | 180 dialogues | Government and stakeholders are actively engaged. Stakeholders have the capacity to generate clear outcomes and lessons learned. | Multi-focal areas | 231; source: 2023 AMR | 90 dialogues | 108 dialogues | UNDP | Grantee monitoring reports and impact reviews | Annually | 0 | [10 empty] | 0 | 0
Project component 2: Demand-driven grants to CSOs/CBOs
Outcome 2.1. Landscape strategic objectives advanced through community-led grants
Indicator 11: Number of SGP countries supporting partnerships to advance sustainable agriculture and fisheries and or food security (such as diversification, sustainable intensification, sustainable fisheries management, agroecological farming practices, climate-smart agriculture, certification programmes, local sourcing initiatives waste reduction, and circular economy, etc.) | This indicator measures the number of SGP participating countries that support and promote partnerships among stakeholders to advance sustainable agriculture, sustainable fisheries, and food security objectives through project interventions. These partnerships may involve collaboration among local communities, farmers' organizations, fishers' associations, civil society organizations, government agencies, research institutions, private sector actors, and other relevant stakeholders. | Sustainable agriculture and fisheries, and food security; | Grantee monitoring reports and impact reviews. | Existing policies in SGP countries are aligned with sustainable agriculture and fisheries goals. | Biodiversity |  | 10 SGP country programs | 25 SGP countries (approx. 25% of the OP8 Part 1 Portfolio) | UNDP | Annual report | Annually | 0 | [10 empty] | 0 | 0
Indicator 12: number of locally adapted solutions promoting low-carbon technologies (such as new/modified biogas technology, locally developed energy efficient stoves, innovatives uses of solar/wind energy, etc.) | This indicator measures the number of innovative low-carbon technology solutions that have been developed, modified, adapted, tested, or adopted to address local needs and conditions while contributing to the reduction of greenhouse gas emissions and dependence on fossil fuels. It captures community-driven and locally appropriate technologies that enhance energy efficiency, increase the use of renewable energy, or promote sustainable production and consumption practices. | Low-carbon energy access co-benefits; | Grantee monitoring reports, impact reviews, SGP database | Local communities are actively engaged and participate in the identification, development, and adoption of low-carbon technologies. | Climate Change | 90; source: 2023 AMR | 30 locally adapted low emission development solutions | 70 locally adpated low emission development solutions | UNDP | Annual report | Annually | 0 | [10 empty] | 0 | 0
Indicator 13: increase in installed renewable energy capacity from community-scale systems (e.g., biomass, micro-hydro, solar, etc.) | This indicator measures the increase in renewable energy generation capacity installed through community-scale systems as a result of project interventions. It captures the deployment, expansion, or upgrading of renewable energy technologies that provide clean, reliable, and sustainable energy services for households, communities, local enterprises, and public facilities. The indicator reflects contributions to reducing greenhouse gas emissions, increasing energy access, and strengthening local energy resilience. | Low-carbon energy access co-benefits; | Grantee monitoring reports and impact reviews. | Local communities and stakeholders have the necessary capacity and skills to operate and maintain community-scale renewable energy systems. | Climate Change |  | 50 Kw increased renewable energy capacity | 150 kW increased renewable energy capacity | UNDP | Annual Monitoring Reprot (AMR) | Annually | 0 | [10 empty] | 0 | 0
Indicator 14: Number of local to global coalitions for chemicals and waste management strengthened and or established. | This indicator measures the number of multi-stakeholder coalitions, partnerships, networks, platforms, or alliances focused on chemicals and waste management that have been established or strengthened through project support. These coalitions may operate at local, national, regional, or global levels and facilitate collaboration, knowledge exchange, policy dialogue, capacity development, advocacy, and coordinated action to address chemicals, hazardous waste, plastics, electronic waste, and other pollution-related challenges | Catalysing sustainable urban solutions. | Grantee monitoring reports, impact reviews, SGP database | Stakeholders share common goals and objectives related to the management of chemicals and waste. |  | 27; source: 2023 AMR | 10 coalitions | 20 coalitions | UNDP |  | Annually
Indicator 15: Number of community-based sustainable solution in urban landscapes (e.g. transport, biodiversity conservation, chemical, and waste management, energy efficiency, watershed protection, etc.) | This indicator measures the number of community-based sustainable solutions developed, implemented, strengthened, or scaled within urban and peri-urban landscapes through project support. The solutions are designed to address environmental challenges while improving community well-being, resilience, and sustainability. They are led, managed, or actively implemented by local communities, community-based organizations, civil society organizations, or local stakeholder groups. | Catalysing sustainable urban solutions. | Grantee monitoring reports and impact reviews. | Effective collaboration among various stakeholders, including local government agencies, non-governmental organizations, businesses, and residents. Supportive policies and regulations are in place at the local and national levels. | Chemicals & Wastes |  | 3 urban solutions | 10 urban solutions | UNDP | AMR | Annually | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 2 | 0 | 0 | 0 | 6 | 2
Project component 3: Knowledge Management and Learning
Outcome 3.1. Sustainability and impact of community-led collective action enhanced through knowledge management and learning approaches across landscapes and regions
Indicator 23: Number of knowledge exchange/sharing events with participation of local communities | This indicator measures the number of knowledge exchange and knowledge-sharing events conducted with the active participation of local communities as a result of project support. These events facilitate the sharing of experiences, lessons learned, best practices, innovations, traditional knowledge, and technical information related to environmental conservation, sustainable livelihoods, climate resilience, natural resource management, and sustainable development. | Capacity Development | Grantee monitoring reports, impact reviews | Effective communication channels are established to disseminate information |  | 462 (number of peer-to-peer exchage) source: AMR 2023 | 150 | 350 | UNDP | Grantee monitoring reports and impact reviews | Annually
Project component 4: Monitoring & Evaluation
Outcome 4.1. Scale, durability and impact of locally-led community action strengthened through monitoring, evaluation, and evidence based learning
Indicator 25: Number of projects with meetings involving local CSOs/CBOs or communities to monitor project results, assess impacts, and identify lessons learned | This indicator measures the number of projects that conduct meetings involving local civil society organizations (CSOs), community-based organizations (CBOs), and/or community representatives to review project progress, monitor results, assess environmental and socio-economic impacts, and identify lessons learned during implementation. These meetings provide opportunities for stakeholders to participate in project oversight, validate results, share experiences, identify challenges, and contribute recommendations for adaptive management and future interventions. | Capacity Development | Grantee monitoring reports, impact reviews | Local stakeholders are open to adapting based on the lessons identified during meetings | Multi-focal areas |  | 50% of projects | 80% of projects | UNDP | Grantee monitoring reports and impact reviews | Annually | 0 | [10 empty] | 0 | 0
Project Management Cost (PMC)
Non-Grant Budget for Country Operational Budget (USD) | [11 empty] | 0 | 0 | 0 | 0 | 0 | 26499 | 26499 | 28000 |  | 30000
[5 empty] | Non-grant for country operational budget | [6 empty] | 0 | 0 | 0 | 0 | 0 | 26499 | 26499 | 28000 | 0 | 30000 | 0

## Thematic Areas
Strategic Iniatives | Focal Areas
Community-based conservation of threatened ecosystems and species, including eco-tourism; | Biodiversity
Sustainable agriculture and fisheries, and food security; | Climate Change
Low-carbon energy access co-benefits; | Land Degradation
Local to global coalitions for chemicals and waste management; and | Internal Waters
Catalysing sustainable urban solutions. | Chemicals & Wastes
Capacity Development | Sustainable Forest Management
Multi-focal areas

## Outcomes
Outcomes | Components
1 | Component 1: Enabling environment strengthened for effective community driven integrated approaches
2 | Component 2.1 Landscape-seascape strategic objectives advanced through community-led grants
3 | Component 3: Sustainability and impact of community-led collective action enhanced through knowledge management and learning approaches across landscapes-seascapes and regions.
4 | Component 4: Scale, durability and impact of locally-led community action strengthned through monitoring, evaluation and evidence-based learning
5 | Project Management Cost (PMC)

## Outputs
Outcomes | Components
1 | Component 1: Enabling environment strengthened for effective community driven integrated approaches
2 | Component 2.1 Landscape-seascape strategic objectives advanced through community-led grants
3 | Component 3: Sustainability and impact of community-led collective action enhanced through knowledge management and learning approaches across landscapes-seascapes and regions.
4 | Component 4: Scale, durability and impact of locally-led community action strengthned through monitoring, evaluation and evidence-based learning
5 | Project Management Cost (PMC)