## AWP
Quantum Project ID: | 01003411 | 2025 Annual Work Plan (AWP)
Project Title: | Pacific Parliamentary Effectiveness Initiative – Phase 3 (PPEI 3)
Country: | Fiji, Solomon Islands, Vanuatu, Tonga, Niue, Cook Islands
Implementation Modality (NIM, DIM, NGO-Execution) | DIM
Implementing Partner: | UNDP
Responsible Parties: | IPU, PDF, PIANGO
Country Office Support to NIM ?(Y/N) | N
Project start and end date: | 2024-11-01
Project end date | 2029-10-31
AWP 2025 Budget: | 1624143
COBP 2025 Budget: | 1624143 | [14 empty] | 180780.9167
Available resources as of AWP submission:
Donor 1, Donor 2 etc | NZ MFAT
Regular Resources/TRAC: | N/A
In kind contribution: | [13 empty] | 66.67% | 33.33% | 16.67% | 16.67% | 16.67% | 16.67% | 16.67% | 16.67%
PROJECT OUTPUTS | Main Activity (from Prodoc) | Sub-actions | Timeframe |  |  |  | Responsible Party [Name and code] | Cash trasfer modality (choose either DCT/reimbursement/direct payments) |  | Planned Budget | [11 empty] | Country Priorities
| Not to be included in Quantum |  | Q1 | Q2 | Q3 | Q4 |  |  | Fund Code | Donor | Budget Code | Budget Description | Total Amount (USD) [unit cost * quantity] | Fiji MCO | Samoa MCO | Tonga | Vanuatu | Solomon Islands | Kiribati | Cook Islands | Niue | Cook Islands | Niue
Output 1: Parliamentary committees and plenaries operate with improved procedures and practice in law-making, gender responsive budgeting, and oversight GFA Output 1: Strengthening procedures and practice of plenaries and parliamentary committees in law-making, budgeting and oversight | 1.1 Support parliamentary procedure reform and legislative excutive relations | 1.1.1 Engage a Procedural adviser to reveiw and advise on Standing Orders reforms / Procedural Guide for MPs. 1.1.2 Facilitate peer reveiw, curriculum development and publication of procedural tools. 1.1.3 Create parliamentary & expert working group on autonomy and legislative - executive relations with Technical support from IPU. | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71205 | International Consultants Expenses - Short-Term Technical Contractors | 15000 | 10000 | 5000 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 |  | Technical Expert to support Niue Parliament on initiating Parliament Autonomy Process, through a stocktake review and analysis, with key recommendations and costed multi-year plan for Niue parliament
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71635 | Travel Cost - Other | 10000 | 6666.6667 | 3333.3333 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667
Indicator 1.1: Percentage Increase in the number of oversight meetings conducted by parliament committees in the 6 countries |  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 75710 | Learning Costs - Participation of Counterparts | 12000 | 8000 | 4000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000
Baseline 1.1: |  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 74210 | Printing and Publications | 7000 | 4666.6667 | 2333.3333 | 1166.6667 | 1166.6667 | 1166.6667 | 1166.6667 | 1166.6667 | 1166.6667
Annual Target 1.1: 50% |  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 75710 | Learning Costs - Participation of Counterparts | 23708 | 15805.3333 | 7902.6667 | 3951.3333 | 3951.3333 | 3951.3333 | 3951.3333 | 3951.3333 | 3951.3333
|  |  | 1 | 1 | 1 | 1 | IPU | DCT | 30000 | MFAT | 71635 | Travel Cost - Other | 12000 | 8000 | 4000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71205 | International Consultants Expenses - Short-Term Technical Contractors | 7000 | 4666.6667 | 2333.3333 | 1166.6667 | 1166.6667 | 1166.6667 | 1166.6667 | 1166.6667 | 1166.6667
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71635 | Travel Cost - Other | 8000 | 5333.3333 | 2666.6667 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333
Indicator 1.2: Percentage increase in the number of resident and non-resident citizens participating either directly or through Social Media in oversight inquiries featuring public consultation in each of the 6 Parliament | 1.2 Strengthen committee systems and practices and support inquiry process | 1.2.1 Effective Committee Oversight Workshops. 1.2.2 Committee specific tranining, peer to peer exchanges and devleopment of "Committee Handbook". 1.2.3 Integrate digital tools and AI with Committee work including the inquiry process. | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71635 | Travel Cost - Other | 10000 | 6666.6667 | 3333.3333 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667
Baseline 1.2: |  |  | 1 | 1 | 1 | 1 | IPU | DCT | 30000 | MFAT | 71635 | Travel Cost - Other | 14500 | 9666.6667 | 4833.3333 | 2416.6667 | 2416.6667 | 2416.6667 | 2416.6667 | 2416.6667 | 2416.6667
Annual Target 1.2: 30% |  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71635 | Travel Cost - Other | 8000 | 5333.3333 | 2666.6667 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71205 | International Consultants Expenses - Short-Term Technical Contractors | 7500 | 5000 | 2500 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 72410 | Information and Communications Technology (ICT) Equipment | 10000 | 6666.6667 | 3333.3333 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 74210 | Printing and Publications | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71635 | Travel Cost - Other | 10000 | 6666.6667 | 3333.3333 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71635 | Travel Cost - Other | 15000 | 10000 | 5000 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500
Indicator 1.2: Percentage increase in the number of resident and non-resident citizens participating either directly or through Social Media in oversight inquiries featuring public consultation in each of the 6 Parliament | 1.3 Support parliamentary budget reveiw and oversight through the FBO | 1.3.1 Facilitate FBO missions for focus parliaments. 1.3.2 Undertake FBO consolidation and benchmarking exercise. | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71205 | International Consultants Expenses - Short-Term Technical Contractors | 22875 | 15250 | 7625 | 3812.5 | 3812.5 | 3812.5 | 3812.5 | 3812.5 | 3812.5
Baseline 1.2: 0 |  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71635 | Travel Cost - Other | 20000 | 13333.3333 | 6666.6667 | 3333.3333 | 3333.3333 | 3333.3333 | 3333.3333 | 3333.3333 | 3333.3333
Targget 1.2- 30% |  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71635 | Travel Cost - Other | 15150 | 10100 | 5050 | 2525 | 2525 | 2525 | 2525 | 2525 | 2525
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71205 | International Consultants Expenses - Short-Term Technical Contractors | 7500 | 5000 | 2500 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 75705 | Learning Costs - Course Fee (non staff) | 10000 | 6666.6667 | 3333.3333 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667
| 1.4 Support parliamentary diplomacy and regional integration | 1.4.1 Focus parliaments attend annual Pacific Islands parliamentary forum. |  |  | 1 |  | UNDP 001981 |  | 30000 | MFAT | 71635 | Travel Cost - Other | 25000 | 16666.6667 | 8333.3333 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667
[5 empty] | 1 |  | UNDP 001981 |  | 30000 | MFAT | 71635 | Travel Cost - Other | 10000 | 6666.6667 | 3333.3333 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667
[5 empty] | 1 |  | IPU | DCT | 30000 | MFAT | 71635 | Travel Cost - Other | 12000 | 8000 | 4000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000
|  | Sub-Total for Output 1 | [10 empty] | 292233 | 194822 | 97411 | 48705.5 | 48705.5 | 48705.5 | 48705.5 | 48705.5 | 48705.5
Output 2 Parliaments use scarce resources more effectively, providing the required knowledge and services to their MPs and parliamentary bodies. GFA Output 2: Improving parliamentary capacity for planning, results-based management delivery of key Pacific parliamentary services, including training, professional development and ICT services | 2.1 Support strategic planning and results-based management processes from improved service delivery | 2.1.1 Provide technical advice, formulation and reveiw - for strategic planning and institutional change initiatives. 2.1.2 Business continuity for Pacific Legislatures - workshop | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71205 | International Consultants Expenses - Short-Term Technical Contractors | 17000 | 11333.3333 | 5666.6667 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333
Indicator 2.1:Percentage of Parliamentary Staff and MPs trained locally and have shown improved capacities to carry out their responsibilities and where such training was funded through national resources. |  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71635 | Travel Cost - Other | 10000 | 6666.6667 | 3333.3333 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667
Baseline 2.1: 0 Annual Target 2.1: 20% |  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 75705 | Learning Costs - Course Fee (non staff) | 10000 | 6666.6667 | 3333.3333 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667
| 2.2 Support induction and MP professional development for core parliamentary duties | 2.2.1 Implement MPs induction training for focus parliaments - including pre and post induction workshops. 2.2.2 Undertake induction consolidation and curriculum development. | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 75705 | Learning Costs - Course Fee (non staff) | 27592.5 | 18395 | 9197.5 | 4598.75 | 4598.75 | 4598.75 | 4598.75 | 4598.75 | 4598.75 |  | Technical Expert to support Niue Parliament on the Final Vetting, validation, and Launch of the Induction Package for Niue Parliament
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71205 | International Consultants Expenses - Short-Term Technical Contractors | 10000 | 10000 |  |  |  |  | 10000
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 75705 | Learning Costs - Course Fee (non staff) | 11250 | 7500 | 3750 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875
|  |  | 1 | 1 | 1 | 1 | IPU |  | 30000 | MFAT | 71635 | Travel Cost - Other | 30000 | 20000 | 10000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71635 | Travel Cost - Other | 12000 | 8000 | 4000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71635 | Travel Cost - Other | 12000 | 8000 | 4000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71205 | International Consultants Expenses - Short-Term Technical Contractors | 10000 | 6666.6667 | 3333.3333 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667
| 2.3 Support sustainable training and capacity - buidling solutions serving MPs and staff | 2.3.1 Explore options with national institutions for parliamentary professional and institutional strengthening growth. | 1 | 1 | 1 | 1 | RLA with University, civil service training institute or UNDP |  | 30000 | MFAT | 75705 | Learning Costs - Course Fee (non staff) | 75000 | 50000 | 25000 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 |  | Implement priority capacity buidling component of the Induction Manual for Existing/New MPs
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71205 | International Consultants Expenses - Short-Term Technical Contractors | 30000 | 20000 | 10000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000
|  |  | 1 | 1 | 1 | 1 | IPU | DCT | 30000 | MFAT | 71635 | Travel Cost - Other | 16000 | 10666.6667 | 5333.3333 | 2666.6667 | 2666.6667 | 2666.6667 | 2666.6667 | 2666.6667 | 2666.6667
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71635 | Travel Cost - Other | 15000 | 10000 | 5000 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 75705 | Learning Costs - Course Fee (non staff) | 10000 | 6666.6667 | 3333.3333 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71635 | Travel Cost - Other | 10000 | 6666.6667 | 3333.3333 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667
Indicator 2.2:- % increase of citizens across all 6 jurisdictions who are able to digitally access documents from their Parliaments and are able to use it in meaningful manner Baseline :-0 Target:- 20% | 2.4 Support the digitalization of parliaments | 2.4.1 Engage an ICT specialist to advice, review and assess ICT infrastracture and policy. | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71205 | International Consultants Expenses - Short-Term Technical Contractors | 35000 | 23333.3333 | 11666.6667 | 5833.3333 | 5833.3333 | 5833.3333 | 5833.3333 | 5833.3333 | 5833.3333 |  | Website Development for the Niue Parliament
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 75705 | Learning Costs - Course Fee (non staff) | 25000 | 16666.6667 | 8333.3333 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667
|  | Sub-Total for Output 2 | [10 empty] | 365842.5 | 247228.3333 | 118614.1667 | 59307.0833 | 59307.0833 | 59307.0833 | 69307.0833 | 59307.0833 | 59307.0833
Output 3. Women, and PWDs are better represented and able to exert political leadership through the parliament and its bodies. GFA Output 3: Improving opportunities for and capacities of women, youth and persons with disabilities to participate and exert political leadership through parliaments and their bodies | 3.1 Support women MP advocacy, professional development and networking | 3.1.1 Facilitate annual women MPs regional meetings. 3.1.2 Technical advice for gender perspective intitiatives. | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 75705 | Learning Costs - Course Fee (non staff) | 25000 | 16666.6667 | 8333.3333 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667
Indicator 3.1: Percentage of Women , Youth and PWD activists who have declared as election candidates and have received technical support through the project (cumulative across all beneficiary parliaments) |  |  | 1 | 1 | 1 | 1 | IPU | DCT | 30000 | MFAT | 71635 | Travel Cost - Other | 14000 | 9333.3333 | 4666.6667 | 2333.3333 | 2333.3333 | 2333.3333 | 2333.3333 | 2333.3333 | 2333.3333
Baseline 3.1: 0 |  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 74210 | Printing and Publications | 3000 | 2000 | 1000 | 500 | 500 | 500 | 500 | 500 | 500
Annual Target 3.1: 5 |  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71635 | Travel Cost - Other | 10000 | 6666.6667 | 3333.3333 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71635 | Travel Cost - Other | 35000 | 23333.3333 | 11666.6667 | 5833.3333 | 5833.3333 | 5833.3333 | 5833.3333 | 5833.3333 | 5833.3333
Indicator 3.2:- No of actions taken on issues highlited in Parliment Related to Gender youth and PWD relaetd issues | 3.2 Build the capacity of women and PWD activists and potential candidates | 3.2.1 Engage with sub-national women representatives and stakeholders. 3.2.2 Facilitate mock Parliaments or a mock Committee inquiry. | 1 | 1 | 1 | 1 | RP PIANGO | DCT | 30000 | MFAT | 75705 | Learning Costs - Course Fee (non staff) | 30000 | 20000 | 10000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000
Baseline 3.2:- 0 |  |  | 1 | 1 | 1 | 1 | RP PDF | Reimbursement | 30000 | MFAT | 75705 | Learning Costs - Course Fee (non staff) | 10000 | 6666.6667 | 3333.3333 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667
Target 3.2:- 50% |  |  | 1 | 1 | 1 | 1 | RP PIANGO | DCT | 30000 | MFAT | 71635 | Travel Cost - Other | 67500 | 45000 | 22500 | 11250 | 11250 | 11250 | 11250 | 11250 | 11250
|  |  | 1 | 1 | 1 | 1 | RP PIANGO | DCT | 30000 | MFAT | 74210 | Printing and Publications | 4000 | 2666.6667 | 1333.3333 | 666.6667 | 666.6667 | 666.6667 | 666.6667 | 666.6667 | 666.6667
Indicator 3.3:- Percentage increase in women, youth and PWD candidates successfully contesting in local (municipal), provincial and national elections disaggregated by country. |  |  | 1 | 1 | 1 | 1 | IPU | DCT | 30000 | MFAT | 71635 | Travel Cost - Other | 8000 | 5333.3333 | 2666.6667 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333
Baseline 3.3:- 0 |  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71635 | Travel Cost - Other | 10000 | 6666.6667 | 3333.3333 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667
Target 3.3: 10% |  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71205 | International Consultants Expenses - Short-Term Technical Contractors | 8000 | 5333.3333 | 2666.6667 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333
|  | Sub-Total for Output 3 | [10 empty] | 224500 | 149666.6667 | 74833.3333 | 37416.6667 | 37416.6667 | 37416.6667 | 37416.6667 | 37416.6667 | 37416.6667
Output 4: Parliaments better inform and engage the public, in particular youth and marginal groups and the wider public in their decision-making. GFA Output 4: Enhance parliamentary capacity to inform and engage the public and marginalized groups including women, youth and persons with disabilities | 4.1 Support parliaments' outreach, civic education and public information planning and activities, in particular to women, youth and PWD. | 4.1.1 Consolidate engagement initiatives and explore options for curriculum development. 4.1.2 Assist focus parliaments to host Youth Parliament at national and/or sub-national level. | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 75705 | Learning Costs - Course Fee (non staff) | 29000 | 19333.3333 | 9666.6667 | 4833.3333 | 4833.3333 | 4833.3333 | 4833.3333 | 4833.3333 | 4833.3333
Indicator 4.1: Percentage of resident and non resident population reached through outreach & civic education initiatives supported by the project, disaggregated by country |  |  | 1 | 1 | 1 | 1 | IPU | DCT | 30000 | MFAT | 75705 | Learning Costs - Course Fee (non staff) | 20000 | 13333.3333 | 6666.6667 | 3333.3333 | 3333.3333 | 3333.3333 | 3333.3333 | 3333.3333 | 3333.3333
Baseline 4.1: 0 |  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71635 | Travel Cost - Other | 12000 | 8000 | 4000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000
Annual Target 4.1: 40% |  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71635 | Travel Cost - Other | 10000 | 6666.6667 | 3333.3333 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71635 | Travel Cost - Other | 9000 | 6000 | 3000 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71635 | Travel Cost - Other | 15110 | 10073.3333 | 5036.6667 | 2518.3333 | 2518.3333 | 2518.3333 | 2518.3333 | 2518.3333 | 2518.3333
Indicator 4.2 Percentage of engaged beneficiary civil society organizations & media organizations reporting improved/expanded relations with beneficiary parliaments as result of project interventions, disaggregated by country | 4.2 Support civil society's relations with parliaments and participation in parliamentary work | 4.2.1 Facilitate CSO - parliament dialogue for 4 focus parliaments. | 1 | 1 | 1 | 1 | RP National CS networks | DCT | 30000 | MFAT | 75705 | Learning Costs - Course Fee (non staff) | 30000 | 20000 | 10000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000
Baseline 4.2:-0 |  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 75705 | Learning Costs - Course Fee (non staff) | 45000 | 30000 | 15000 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500
Target 4.2:- 50% |  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71635 | Travel Cost - Other | 12000 | 8000 | 4000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000
| 4.3 Support media engagement with parliaments | 4.3.1 Develop handbook for media and press gallery guide. | 1 | 1 | 1 | 1 | UNDP 001980 |  | 30000 | MFAT | 74225 | Other Media Costs | 8000 | 5333.3333 | 2666.6667 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 74210 | Printing and Publications | 7000 | 4666.6667 | 2333.3333 | 1166.6667 | 1166.6667 | 1166.6667 | 1166.6667 | 1166.6667 | 1166.6667
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71635 | Travel Cost - Other | 15000 | 10000 | 5000 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500
|  | Sub-Total for Output 4 | [10 empty] | 212110 | 141406.6667 | 70703.3333 | 35351.6667 | 35351.6667 | 35351.6667 | 35351.6667 | 35351.6667 | 35351.6667
Project Technical Assistance and Management Support GFA Output 5: Project Technucal Assistance and Management | 5.1 Project Technical Assistance and Management |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 67305 | Labour Cost – GS Staff | 66609.2548 | 44406.1699 | 22203.0849 | 11101.5425 | 11101.5425 | 11101.5425 | 11101.5425 | 11101.5425 | 11101.5425
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71465 | Labour Cost - International Personnel Services Agreement | 45959.987 | 30639.9913 | 15319.9957 | 7659.9978 | 7659.9978 | 7659.9978 | 7659.9978 | 7659.9978 | 7659.9978
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71465 | Labour Cost - International Personnel Services Agreement | 35091.3339 | 23394.2226 | 11697.1113 | 5848.5557 | 5848.5557 | 5848.5557 | 5848.5557 | 5848.5557 | 5848.5557
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71475 | Labour Cost - National Personnel Services Agreement | 14322.6538 | 14322.6538 |  | 3580.6634 | 3580.6634 | 3580.6634 | 3580.6634
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71475 | Labour Cost - National Personnel Services Agreement | 14322.6538 | 14322.6538 |  | 3580.6634 | 3580.6634 | 3580.6634 | 3580.6634
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71475 | Labour Cost - National Personnel Services Agreement | 14322.6538 | 14322.6538 |  | 3580.6634 | 3580.6634 | 3580.6634 | 3580.6634
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71475 | Labour Cost - National Personnel Services Agreement | 14322.6538 | 14322.6538 |  | 3580.6634 | 3580.6634 | 3580.6634 | 3580.6634
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71475 | Labour Cost - National Personnel Services Agreement | 12178.92 | 8119.28 | 4059.64 | 2029.82 | 2029.82 | 2029.82 | 2029.82 | 2029.82 | 2029.82
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71475 | Labour Cost - National Personnel Services Agreement | 36366.5211 |  | 36366.5211 |  |  |  |  | 18183.2606 | 18183.2606
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71475 | Labour Cost - National Personnel Services Agreement | 16894.8894 | 11263.2596 | 5631.6298 | 2815.8149 | 2815.8149 | 2815.8149 | 2815.8149 | 2815.8149 | 2815.8149
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 67305 | Labour Cost – GS Staff | 14040.0402 | 14040.0402 |  | 3510.0101 | 3510.0101 | 3510.0101 | 3510.0101
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71635 | Travel Cost - Other | 5000 | 5000 |  | 1250 | 1250 | 1250 | 1250
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71635 | Travel Cost - Other | 5000 | 5000 |  | 1250 | 1250 | 1250 | 1250
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 73125 | Common Services - Premises | 18927 | 18927 |  | 4731.75 | 4731.75 | 4731.75 | 4731.75
| 5.2 Evaluations, HACT assesments, audits |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 74112 | HACT Assessment & Spot Check of CSO and media Partners | 5000 | 3333.3333 | 1666.6667 | 833.3333 | 833.3333 | 833.3333 | 833.3333 | 833.3333 | 833.3333
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 74112 | Audit | 5000 | 3333.3333 | 1666.6667 | 833.3333 | 833.3333 | 833.3333 | 833.3333 | 833.3333 | 833.3333
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 72105 | Evaluations (M&E 1%) | 14180.4406 | 9578.7091 | 4601.7315 | 2394.6773 | 2394.6773 | 2394.6773 | 2394.6773 | 2300.8657 | 2300.8657
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 75105 | General Management Service fees | 110711.3478 | 77395.9697 | 33315.3781 | 19348.9924 | 19348.9924 | 19348.9924 | 19348.9924 | 16657.6891 | 16657.6891
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 64397 74396 | Direct Project cost | 81207.15 | 52242.2795 | 28964.8705 | 13060.5699 | 13060.5699 | 13060.5699 | 13060.5699 | 14482.4352 | 14482.4352
|  | Sub-Total for Output 5 | [10 empty] | 529457.5 | 363964.2037 | 165493.2963 | 90991.0509 | 90991.0509 | 90991.0509 | 90991.0509 | 82746.6481 | 82746.6481
|  | Total for Outputs | [10 empty] | 1624143 | 1097087.8704 | 527055.1296 | 271771.9676 | 271771.9676 | 271771.9676 | 281771.9676 | 263527.5648 | 263527.5648
|  | Communication (1%) | [10 empty] | 14040.0402 | 14040.0402 | 0 | 3510.0101 | 3510.0101 | 3510.0101 | 3510.0101 | 0 | 0
|  | Evaluation (M&E 1%) | [10 empty] | 14180.4406 | 9578.7091 | 4601.7315 | 2394.6773 | 2394.6773 | 2394.6773 | 2394.6773 | 2300.8657 | 2300.8657
|  | Audit | [10 empty] | 5000 | 3333.3333 | 1666.6667 | 833.3333 | 833.3333 | 833.3333 | 833.3333 | 833.3333 | 833.3333
|  | Project Management costs | [10 empty] | 318358.5616 | 221413.912 | 96944.6495 | 55353.478 | 55353.478 | 55353.478 | 55353.478 | 48472.3248 | 48472.3248
|  | DES/DPC (for NIM: add executing support services costs) | [10 empty] | 81207.15 | 52242.2795 | 28964.8705 | 13060.5699 | 13060.5699 | 13060.5699 | 13060.5699 | 14482.4352 | 14482.4352
|  | Total direct costs (evaluation, audit, DES/DPC+ total ouputs) | [10 empty] | 1513431.6522 | 1019691.9007 | 493739.7515 | 252422.9752 | 252422.9752 | 252422.9752 | 262422.9752 | 246869.8757 | 246869.8757
|  | GMS [8%] (Add GMS for additional donors) | [10 empty] | 110711.3478 | 77395.9697 | 33315.3781 | 19348.9924 | 19348.9924 | 19348.9924 | 19348.9924 | 16657.6891 | 16657.6891
Total of Budget: | [12 empty] | 1624143 | 1097087.8704 | 527055.1296 | 271771.9676 | 271771.9676 | 271771.9676 | 281771.9676 | 263527.5648 | 263527.5648
Details of Project Partners 2025
Name of Partner | Code | Amount
IPU | 09599 | 126500
PIANGO | 014968 | 30000
PDF | (to be created) | 10000
National CS networks | (to be created) | 30000
University, civil service training institute or UNDP | (to be created) | 75000
UNDP | 001981 | 1352643
TOTAL PARTNER BUDGET FOR 2025 |  | 1624143
Project Manager |  |  | Implementing Partner Signature* | [8 empty] | Resident Representative/Deputy Resident Representative
Signature and Date |  |  | Title, Signature and Date | [8 empty] | Title, Signature & Date
This Annual Work Plan (AWP) is based on Results Management Guidelines (RMG) of UNDP. Once signed by UNDP and the Implementing Partner, the plan authorizes project management to manage available resources and achieve set results.
Note on B6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Thomas, kindly requesting if the signed LOA with these partners are uploaded in the same folder as AWP
Note on H16: Enter the name and the code of the responsible party assigned to conduct the transactions for the implementation of the activity.
Note on L17: Refer to the budget code tab for a list of UNDP budget codes.
Note on N98: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1% comms
Note on A111: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Thomas Gregory are these cost for monitoring only?

## AWP (2) (hidden)
Quantum Project ID: | 01003411 | 2025 Annual Work Plan (AWP)
Project Title: | Pacific Parliamentary Effectiveness Initiative – Phase 3 (PPEI 3)
Country: | Fiji, Solomon Islands, Vanuatu, Tonga, Niue, Cook Islands
Implementation Modality (NIM, DIM, NGO-Execution) | DIM
Implementing Partner: | UNDP
Responsible Parties: | IPU, PDF, PIANGO
Country Office Support to NIM ?(Y/N) | N
Project start and end date: | 2024-11-01
Project end date | 2029-10-31
AWP 2025 Budget: | 1503835
COBP 2025 Budget: | 1503835
Available resources as of AWP submission:
Donor 1, Donor 2 etc | NZ MFAT
Regular Resources/TRAC: | N/A
In kind contribution: | [13 empty] | 66.67% | 33.33% | 16.67% | 16.67% | 16.67% | 16.67% | 16.67% | 16.67%
PROJECT OUTPUTS | Main Activity (from Prodoc) | Sub-actions | Timeframe |  |  |  | Responsible Party [Name and code] | Cash trasfer modality (choose either DCT/reimbursement/direct payments) |  | Planned Budget
| Not to be included in Quantum |  | Q1 | Q2 | Q3 | Q4 |  |  | Fund Code | Donor | Budget Code | Budget Description | Total Amount (USD) [unit cost * quantity] | Fiji MCO | Samoa MCO | Tonga | Vanuatu | Solomon Islands | Kiribati | Cook Islands | Niue
Output 1: Parliamentary committees and plenaries operate with improved procedures and practice in law-making, gender responsive budgeting, and oversight | 1.1 Support parliamentary procedure reform and legislative excutive relations | 1.1.1 Engage a Procedural adviser to reveiw and advise on Standing Orders reforms / Procedural Guide for MPs. 1.1.2 Facilitate peer reveiw, curriculum development and publication of procedural tools. 1.1.3 Create parliamentary & expert working group on autonomy and legislative - executive relations with Technical support from IPU. | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71205 | Procedural Advisor (IC+DSA+travel) | 25000 | 16666.6667 | 8333.3333 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667
Indicator 1.1: Percentage Increase in the number of oversight meetings conducted by parliament committees in the 6 countries |  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 75705 | Country Support Meetings&Workshops | 12000 | 8000 | 4000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000
Baseline 1.1: |  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 74210 | Goods (graphic design & printing) | 7000 | 4666.6667 | 2333.3333 | 1166.6667 | 1166.6667 | 1166.6667 | 1166.6667 | 1166.6667 | 1166.6667
Annual Target 1.1: 50% |  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 75705 | Regional activity on autonomy and legislaitve -executive relations | 23708 | 15805.3333 | 7902.6667 | 3951.3333 | 3951.3333 | 3951.3333 | 3951.3333 | 3951.3333 | 3951.3333
|  |  | 1 | 1 | 1 | 1 | IPU | DCT | 30000 | MFAT | 71635 | IPU Technical assistance - fees & travel | 12000 | 8000 | 4000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71205 | Learning Advisor - Curriculum Development | 7000 | 4666.6667 | 2333.3333 | 1166.6667 | 1166.6667 | 1166.6667 | 1166.6667 | 1166.6667 | 1166.6667
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71635 | project TA travel | 8000 | 5333.3333 | 2666.6667 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333
Indicator 1.2: Percentage increase in the number of resident and non-resident citizens participating either directly or through Social Media in oversight inquiries featuring public consultation in each of the 6 Parliament | 1.2 Strengthen committee systems and practices and support inquiry process | 1.2.1 Effective Committee Oversight Workshops. 1.2.2 Committee specific tranining, peer to peer exchanges and devleopment of "Committee Handbook". 1.2.3 Integrate digital tools and AI with Committee work including the inquiry process. | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71635 | Country Support Meetings&Workshops- travel | 10000 | 6666.6667 | 3333.3333 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667
Baseline 1.2: |  |  | 1 | 1 | 1 | 1 | IPU | DCT | 30000 | MFAT | 71635 | IPU Technical assistance - fees & travel | 14500 | 9666.6667 | 4833.3333 | 2416.6667 | 2416.6667 | 2416.6667 | 2416.6667 | 2416.6667 | 2416.6667
Annual Target 1.2: 30% |  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71635 | Specialized training - service contract | 8000 | 5333.3333 | 2666.6667 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71205 | Learning Advisor - Curriculum Development | 7500 | 5000 | 2500 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 72410 | Committee ICT equipment | 10000 | 6666.6667 | 3333.3333 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 74210 | Goods (graphic design & printing) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71635 | project TA travel | 10000 | 6666.6667 | 3333.3333 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71635 | public consultation (meetings& travel) | 15000 | 10000 | 5000 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500
Indicator 1.2: Percentage increase in the number of resident and non-resident citizens participating either directly or through Social Media in oversight inquiries featuring public consultation in each of the 6 Parliament | 1.3 Support parliamentary budget reveiw and oversight through the FBO | 1.3.1 Facilitate FBO missions for focus parliaments. 1.3.2 Undertake FBO consolidation and benchmarking exercise. | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71205 | Lead Technical Advisor Parliament & the Budget | 22875 | 15250 | 7625 | 3812.5 | 3812.5 | 3812.5 | 3812.5 | 3812.5 | 3812.5
Baseline 1.2: 0 |  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71635 | Partner Legislatures travel and DSA | 20000 | 13333.3333 | 6666.6667 | 3333.3333 | 3333.3333 | 3333.3333 | 3333.3333 | 3333.3333 | 3333.3333
Targget 1.2- 30% |  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71635 | parliamentary resource persons travel | 15150 | 10100 | 5050 | 2525 | 2525 | 2525 | 2525 | 2525 | 2525
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71205 | Learning Advisor - Curriculum Development | 7500 | 5000 | 2500 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 75705 | FBO workshops & Meetings | 10000 | 6666.6667 | 3333.3333 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667
| 1.4 Support parliamentary diplomacy and regional integration | 1.4.1 Focus parliaments attend annual Pacific Islands parliamentary forum. |  |  | 1 |  | UNDP 001981 |  | 30000 | MFAT | 71635 | PIPG participant travel | 30000 | 20000 | 10000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000
[5 empty] | 1 |  | UNDP 001981 |  | 30000 | MFAT | 71635 | project TA travel | 10000 | 6666.6667 | 3333.3333 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667
[5 empty] | 1 |  | IPU | DCT | 30000 | MFAT | 76135 | IPU Technical assistance - fees & travel | 12000 | 8000 | 4000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000
|  | Sub-Total for Output 1 | [10 empty] | 297233 | 198155.3333 | 99077.6667 | 49538.8333 | 49538.8333 | 49538.8333 | 49538.8333 | 49538.8333 | 49538.8333
Output 2 Parliaments use scarce resources more effectively, providing the required knowledge and services to their MPs and parliamentary bodies. | 2.1 Support strategic planning and results-based management processes from improved service delivery | 2.1.1 Provide technical advice, formulation and reveiw - for strategic planning and institutional change initiatives. 2.1.2 Business continuity for Pacific Legislatures - workshop | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71205 | Technical Advisor - Strategic and service planning | 17000 | 11333.3333 | 5666.6667 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333 | 2833.3333
Indicator 2.1:Percentage of Parliamentary Staff and MPs trained locally and have shown improved capacities to carry out their responsibilities and where such training was funded through national resources. |  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 76135 | project TA travel | 10000 | 6666.6667 | 3333.3333 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667
Baseline 2.1: 0 Annual Target 2.1: 20% |  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 75705 | in-country workshops & meetings | 10000 | 6666.6667 | 3333.3333 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667
| 2.2 Support induction and MP professional development for core parliamentary duties | 2.2.1 Implement MPs induction training for focus parliaments - including pre and post induction workshops. 2.2.2 Undertake induction consolidation and curriculum development. | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 75705 | MP induction workshops& meetings | 27592.5 | 18395 | 9197.5 | 4598.75 | 4598.75 | 4598.75 | 4598.75 | 4598.75 | 4598.75
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71205 | International Consultant- Kiali | 15000 | [5 empty] | 15000
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 75705 | committee induction workshops& meetings | 11250 | 7500 | 3750 | 1875 | 1875 | 1875 | 1875 | 1875 | 1875
|  |  | 1 | 1 | 1 | 1 | IPU |  | 30000 | MFAT | 76135 | IPU Technical assistance - fees & travel | 30000 | 20000 | 10000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 76135 | Partner Legislatures resource persons travel and DSA | 12000 | 8000 | 4000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 76135 | project TA travel | 12000 | 8000 | 4000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71205 | Learning Advisor - Curriculum Development | 10000 | 6666.6667 | 3333.3333 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667
| 2.3 Support sustainable training and capacity - buidling solutions serving MPs and staff | 2.3.1 Explore options with national institutions for parliamentary professional and institutional strengthening growth. | 1 | 1 | 1 | 1 | RLA with University, civil service training institute or UNDP |  | 30000 | MFAT | 75705 | Service agreement (or contract) - institutional development, curriculum development, delivery design, M&E | 75000 | 50000 | 25000 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71205 | Learning Advisor Institutional Development | 42000 | 28000 | 14000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000
|  |  | 1 | 1 | 1 | 1 | IPU | DCT | 30000 | MFAT | 76135 | IPU technical assistance - fees& travel | 16000 | 10666.6667 | 5333.3333 | 2666.6667 | 2666.6667 | 2666.6667 | 2666.6667 | 2666.6667 | 2666.6667
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 76135 | Partner Legislatures focal point travel | 32000 | 21333.3333 | 10666.6667 | 5333.3333 | 5333.3333 | 5333.3333 | 5333.3333 | 5333.3333 | 5333.3333
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 75705 | network meetings /delivery meetings | 10000 | 6666.6667 | 3333.3333 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 76135 | project TA travel | 10000 | 6666.6667 | 3333.3333 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667
Indicator 2.2:- % increase of citizens across all 6 jurisdictions who are able to digitally access documents from their Parliaments and are able to use it in meaningful manner | 2.4 Support the digitalization of parliaments | 2.4.1 Engage an ICT specialist to advice, review and assess ICT infrastracture and policy. | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71205 | ICT specialist - assessments, policy, TA | 25000 | 16666.6667 | 8333.3333 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667
Baseline :-0 |  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 72410 | MP tablets | 10000 | 6666.6667 | 3333.3333 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667
Target:- 20% |  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 72410 | video conferencing equipment | 5000 | 3333.3333 | 1666.6667 | 833.3333 | 833.3333 | 833.3333 | 833.3333 | 833.3333 | 833.3333
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 75705 | in-country meetings | 10000 | 6666.6667 | 3333.3333 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 72410 | laptops for parliamentary administration | 15000 | 10000 | 5000 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500
|  | Sub-Total for Output 2 | [10 empty] | 404842.5 | 259895 | 129947.5 | 64973.75 | 64973.75 | 64973.75 | 79973.75 | 64973.75 | 64973.75
Output 3. Women, and PWDs are better represented and able to exert political leadership through the parliament and its bodies. | 3.1 Support women MP advocacy, professional development and networking | 3.1.1 Facilitate annual women MPs regional meetings. 3.1.2 Technical advice for gender perspective intitiatives. | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 75705 | annual women MP network meetings | 25000 | 16666.6667 | 8333.3333 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667
Indicator 3.1: Percentage of Women , Youth and PWD activists who have declared as election candidates and have received technical support through the project (cumulative across all beneficiary parliaments) |  |  | 1 | 1 | 1 | 1 | IPU | DCT | 30000 | MFAT | 76135 | IPU technical assistance - fees& travel | 14000 | 9333.3333 | 4666.6667 | 2333.3333 | 2333.3333 | 2333.3333 | 2333.3333 | 2333.3333 | 2333.3333
Baseline 3.1: 0 |  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 74210 | Goods (graphic design & printing) | 3000 | 2000 | 1000 | 500 | 500 | 500 | 500 | 500 | 500
Annual Target 3.1: 5 |  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 76135 | project TA travel | 10000 | 6666.6667 | 3333.3333 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 76135 | participating MP travel | 40000 | 26666.6667 | 13333.3333 | 6666.6667 | 6666.6667 | 6666.6667 | 6666.6667 | 6666.6667 | 6666.6667
Indicator 3.2:- No of actions taken on issues highlited in Parliment Related to Gender youth and PWD relaetd issues | 3.2 Build the capacity of women and PWD activists and potential candidates | 3.2.1 Engage with sub-national women representatives and stakeholders. 3.2.2 Facilitate mock Parliaments or a mock Committee inquiry. | 1 | 1 | 1 | 1 | RP PIANGO | DCT | 30000 | MFAT | 75705 | CSO network support services, facilitation and technical assistance | 30000 | 20000 | 10000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000
Baseline 3.2:- 0 |  |  | 1 | 1 | 1 | 1 | RP PDF | Reimbursement | 30000 | MFAT | 75705 | Women and PWD leader national capacity-building and coordination meetings | 10000 | 6666.6667 | 3333.3333 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667
Target 3.2:- 50% |  |  | 1 | 1 | 1 | 1 | RP PIANGO | DCT | 30000 | MFAT | 76135 | participant travel | 67500 | 45000 | 22500 | 11250 | 11250 | 11250 | 11250 | 11250 | 11250
|  |  | 1 | 1 | 1 | 1 | RP PIANGO | DCT | 30000 | MFAT | 74210 | Goods (education material, media & awareness raising material) | 4000 | 2666.6667 | 1333.3333 | 666.6667 | 666.6667 | 666.6667 | 666.6667 | 666.6667 | 666.6667
Indicator 3.3:- Percentage increase in women, youth and PWD candidates successfully contesting in local (municipal), provincial and national elections disaggregated by country. |  |  | 1 | 1 | 1 | 1 | IPU | DCT | 30000 | MFAT | 76135 | IPU technical assistance - fees& travel | 8000 | 5333.3333 | 2666.6667 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333
Baseline 3.3:- 0 |  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 76135 | project TA travel | 10000 | 6666.6667 | 3333.3333 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667
Target 3.3: 10% |  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71205 | Learning Advisor - Curriculum Development | 8000 | 5333.3333 | 2666.6667 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333
|  | Sub-Total for Output 3 | [10 empty] | 229500 | 153000 | 76500 | 38250 | 38250 | 38250 | 38250 | 38250 | 38250
Output 4: Parliaments better inform and engage the public, in particular youth and marginal groups and the wider public in their decision-making. | 4.1 Support parliaments' outreach, civic education and public information planning and activities, in particular to women, youth and PWD. | 4.1.1 Consolidate engagement initiatives and explore options for curriculum development. 4.1.2 Assist focus parliaments to host Youth Parliament at national and/or sub-national level. | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 75705 | in-country outreach planning meetings | 29000 | 19333.3333 | 9666.6667 | 4833.3333 | 4833.3333 | 4833.3333 | 4833.3333 | 4833.3333 | 4833.3333
Indicator 4.1: Percentage of resident and non resident population reached through outreach & civic education initiatives supported by the project, disaggregated by country |  |  | 1 | 1 | 1 | 1 | IPU | DCT | 30000 | MFAT | 75705 | LoAs: support to women practice and youth parliaments | 20000 | 13333.3333 | 6666.6667 | 3333.3333 | 3333.3333 | 3333.3333 | 3333.3333 | 3333.3333 | 3333.3333
Baseline 4.1: 0 |  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 76135 | IPU technical assistance - fees& travel | 12000 | 8000 | 4000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000
Annual Target 4.1: 40% |  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 76135 | regional event: outreach and civic education | 10000 | 6666.6667 | 3333.3333 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 76135 | project TA travel | 8000 | 5333.3333 | 2666.6667 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 76135 | support pilot outreach activity in 6 parliaments | 15110 | 10073.3333 | 5036.6667 | 2518.3333 | 2518.3333 | 2518.3333 | 2518.3333 | 2518.3333 | 2518.3333
Indicator 4.2 Percentage of engaged beneficiary civil society organizations & media organizations reporting improved/expanded relations with beneficiary parliaments as result of project interventions, disaggregated by country | 4.2 Support civil society's relations with parliaments and participation in parliamentary work | 4.2.1 Facilitate CSO - parliament dialogue for 4 focus parliaments. | 1 | 1 | 1 | 1 | RP National CS networks | DCT | 30000 | MFAT | 75705 | CSO-parliament dialogue support in 4 parliaments: national consultations, research, and facilitation | 46128 | 30752 | 15376 | 7688 | 7688 | 7688 | 7688 | 7688 | 7688
Baseline 4.2:-0 |  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 75705 | parliament -civil society dialogue at national level in 4 parliaments | 45000 | 30000 | 15000 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500
Target 4.2:- 50% |  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 76135 | project TA travel | 10000 | 6666.6667 | 3333.3333 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667
| 4.3 Support media engagement with parliaments | 4.3.1 Develop handbook for media and press gallery guide. | 1 | 1 | 1 | 1 | UNDP 001980 |  | 30000 | MFAT | 74225 | media engagement with parliaments. convening & capacity building of journalists in 4 countries | 8000 | 5333.3333 | 2666.6667 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333 | 1333.3333
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 74225 | parliament media engagement events | 14000 | 9333.3333 | 4666.6667 | 2333.3333 | 2333.3333 | 2333.3333 | 2333.3333 | 2333.3333 | 2333.3333
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 76135 | project TA travel | 10000 | 6666.6667 | 3333.3333 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667
|  | Sub-Total for Output 4 | [10 empty] | 227238 | 151492 | 75746 | 37873 | 37873 | 37873 | 37873 | 37873 | 37873
Project Technical Assistance and Management Support | 5.1 Project Technical Assistance and Management |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 67305 | Project Manager | 66609.2548 | 44406.1699 | 22203.0849 | 11101.5425 | 11101.5425 | 11101.5425 | 11101.5425 | 11101.5425 | 11101.5425
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71465 | Parliamentary Development Specialist | 45959.987 | 30639.9913 | 15319.9957 | 7659.9978 | 7659.9978 | 7659.9978 | 7659.9978 | 7659.9978 | 7659.9978
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71465 | Inclusive Parliaments Specialist (50%) | 22979.9935 | 15319.9957 | 7659.9978 | 3829.9989 | 3829.9989 | 3829.9989 | 3829.9989 | 3829.9989 | 3829.9989
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71465 | Monitoring, Evaluation, Learning & Knowledge Specialist | 35091.3339 | 23394.2226 | 11697.1113 | 5848.5557 | 5848.5557 | 5848.5557 | 5848.5557 | 5848.5557 | 5848.5557
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71475 | Project Analyst (Fiji) | 14322.6538 | 9548.4358 | 4774.2179 | 2387.109 | 2387.109 | 2387.109 | 2387.109 | 2387.109 | 2387.109
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71475 | Project Analyst (Fiji) | 14322.6538 | 9548.4358 | 4774.2179 | 2387.109 | 2387.109 | 2387.109 | 2387.109 | 2387.109 | 2387.109
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71475 | Project Analyst (Solomon Islands) | 14322.6538 | 9548.4358 | 4774.2179 | 2387.109 | 2387.109 | 2387.109 | 2387.109 | 2387.109 | 2387.109
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71475 | Project Analyst (Federated States of Micronesia) | 14322.6538 | 9548.4358 | 4774.2179 | 2387.109 | 2387.109 | 2387.109 | 2387.109 | 2387.109 | 2387.109
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71475 | Project Finance Analyst | 12178.92 | 8119.28 | 4059.64 | 2029.82 | 2029.82 | 2029.82 | 2029.82 | 2029.82 | 2029.82
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71475 | Project Analyst (Samoa) | 36366.5211 |  | 36366.5211 |  |  |  |  | 18183.2606 | 18183.2606
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71475 | Project Administrative Associates | 16894.8894 | 11263.2596 | 5631.6298 | 2815.8149 | 2815.8149 | 2815.8149 | 2815.8149 | 2815.8149 | 2815.8149
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71635 | Travel (for EG retreat at 40%) | 4932 | 3288 | 1644 | 822 | 822 | 822 | 822 | 822 | 822
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 71635 | Travel for Communications | 5000 | 3333.3333 | 1666.6667 | 833.3333 | 833.3333 | 833.3333 | 833.3333 | 833.3333 | 833.3333
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 73125 | Common Services - Premises (workstations) at 30% | 18793 | 12528.6667 | 6264.3333 | 3132.1667 | 3132.1667 | 3132.1667 | 3132.1667 | 3132.1667 | 3132.1667
| 5.2 Evaluations, HACT assesments, audits |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 74112 | HACT Assessment & Spot Check of CSO and media Partners | 5000 | 3333.3333 | 1666.6667 | 833.3333 | 833.3333 | 833.3333 | 833.3333 | 833.3333 | 833.3333
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 74112 | Audit | 5000 | 3333.3333 | 1666.6667 | 833.3333 | 833.3333 | 833.3333 | 833.3333 | 833.3333 | 833.3333
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 72105 | Evaluations (M&E 1%) | 12925.989 | 8617.326 | 4308.663 | 2154.3315 | 2154.3315 | 2154.3315 | 2154.3315 | 2154.3315 | 2154.3315
|  |  | 1 | 1 | 1 | 1 | UNDP 001981 |  | 30000 | MFAT | 75105 | General Management Service fees | 120306.8803 | 80204.5869 | 40102.2934 | 20051.1467 | 20051.1467 | 20051.1467 | 20051.1467 | 20051.1467 | 20051.1467
|  | Sub-Total for Output 5 | [10 empty] | 465329.3842 | 205770.6552 | 139251.8487 | 51442.6638 | 51442.6638 | 51442.6638 | 51442.6638 | 69625.9244 | 69625.9244
|  | Total for Outputs | [10 empty] | 1624142.8842 | 968312.9885 | 520523.0154 | 242078.2471 | 242078.2471 | 242078.2471 | 257078.2471 | 260261.5077 | 260261.5077
|  | Communication | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Evaluation (M&E 1%) | [10 empty] | 12925.989 | 9683.1299 | 5205.2302 | 2420.7825 | 2420.7825 | 2420.7825 | 2570.7825 | 2602.6151 | 2602.6151
|  | Audit | [10 empty] | 5000 | 3333.3333 | 1666.6667 | 833.3333 | 833.3333 | 833.3333 | 833.3333 | 833.3333 | 833.3333
|  | Project Management costs | [10 empty] | 322096.5148
|  | DES/DPC (for NIM: add executing support services costs) | [10 empty] | 114594.8211 | 68459.7283 | 36800.9772 | 17114.9321 | 17114.9321 | 17114.9321 | 18175.4321 | 18400.4886 | 18400.4886
|  | Total direct costs (evaluation, audit, DES/DPC+ total ouputs) | [10 empty] | 1503836.0039 | 1049789.18 | 564195.8894 | 262447.295 | 262447.295 | 262447.295 | 278657.795 | 282097.9447 | 282097.9447
|  | GMS [8%] (Add GMS for additional donors) | [10 empty] | 120306.8803 | 83983.1344 | 45135.6712 | 20995.7836 | 20995.7836 | 20995.7836 | 22292.6236 | 22567.8356 | 22567.8356
Total of Budget: | [12 empty] | 1624142.8842 | 1133772.3144 | 609331.5605 | 283443.0786 | 283443.0786 | 283443.0786 | 300950.4186 | 304665.7803 | 304665.7803
Details of Project Partners 2025
Name of Partner | Code | Amount
IPU | (to be created) | 126500
PIANGO | 014968 | 30000
PDF | (to be created) | 10000
National CS networks | (to be created) | 46128
University, civil service training institute or UNDP | (to be created) | 75000
UNDP | 001981 | 1336514.8842
TOTAL PARTNER BUDGET FOR 2025 |  | 1624142.8842
Project Manager |  |  | Implementing Partner Signature* | [8 empty] | Resident Representative/Deputy Resident Representative
Signature and Date |  |  | Title, Signature and Date | [8 empty] | Title, Signature & Date
This Annual Work Plan (AWP) is based on Results Management Guidelines (RMG) of UNDP. Once signed by UNDP and the Implementing Partner, the plan authorizes project management to manage available resources and achieve set results.
Note on H16: Enter the name and the code of the responsible party assigned to conduct the transactions for the implementation of the activity.
Note on L17: Refer to the budget code tab for a list of UNDP budget codes.

## M&E plan (hidden)
Monitoring & Evaluation Plan
Project Title
Country
Duration [end date]
Qunatum Project ID
CPD Outcome/Output | Resilience built to respond to systemic uncertainty and risk, Structural transformation accelerated, particularly green, inclusive, and digital transitions, No-one left behind, centring on equitable access to opportunities and a rights-based approach to human agency and human development
UNSDCF Output | Cooperation framework outcome involving UNDP #1: By 2027, people communities and institutions are more empowered and resilient to face diverse shocks and stresses, especially related to climate variability impacts; and ecosystems and biodiversity are better protected, managed and restored. #2: By 2027, more people especially those at risk of being left behind, contribute to and benefit from sustainable, resilient, diversified, inclusive and human centred socio-economic systems with decent work and equal livelihoods opportunities, reducing inequalities and ensuring shared prosperity. #3: By 2027, people enjoy and contribute more accountable, inclusive, resilient and responsive governance systems that promote gender equality, climate security, justice and peace, ensure participation, and protect their human rights
Strategic Plan (SP) Output | a. Supporting countries towards three directions of change: structural transformation, leaving no one behind and resilience, b) Through six signature solutions: poverty and inequality, governance, resilience, environment, energy and gender equality
SDG Target | 4) Quality Education, 5 Gender Equality, 7) Affordable and clean energy, 8) Reduced inequalities 13) Climate action 16) Peace, justice and strong institutions 17) Partnerships for the goals
Monitoring
Component/Outcome:
Project Output Indicators | Data Source | Baseline (M/Y) | Target (2024) | Q1 target | Q2 target | Q3 target | Q4 target | EOP1 Target (Year) | Progress Against Target (M/Y) | Frequency | Data Collection Methods | Resources (M&E Cost) | Assumptions and Risks
(M&E Activities)
Output 1.
1.1
1.2
1.2
Output 2
2.1
2.1
Output 3
3.1
3.2
Note on A14: As per project document
Note on E14: Provide Q targets, as applicable.

## Gender action plan
Gender Action Plan
|  | Project Name | PPEI-III
Country
AWP Sub Actions | Actions | Person/Unit Responsible | Timeline | Budget allocation |  |  | Proposed Indicator
|  |  |  | Budgeted amount | Allocation | %
1.1.1 Engage a Procedural adviser to reveiw and advise on Standing Orders reforms / Procedural Guide for MPs. | The adviser will draft a Procedural Guide/booklet for MPs to promote inclusive and equitable parliamentary practices. | Programe Manager, Project Analyst , Inclusive Parliaments Specialist, M&E | Dec-Jan 2025 | 15000 | 3750 | 25% | Procedural Guide for MPs incorporating GESI principles are submitted and endorsed by the relevant parliamentary committee.
1.1.2 Facilitate peer review, curriculum development, and publication of procedural tools. | 1.1.2:-Develop an inclusive curriculum with a gender-sensitive lens considering the GESI guidelines and ensure that the publications are gender-sensitive. | Programe Manager, Project Analyst , Inclusive Parliaments Specialist, M&E | Dec-Jan 2025 | 29000 | 13050 | 45% | Inclusive curriculum developed and at least X% of publications reviewed for gender sensitivity.
1.1.3 Create parliamentary & expert working group on autonomy and legislative-executive relations with technical support from IPU. | 1.1.3:-Ensure representation from women (at least 30%), marginalized groups, and gender experts in the working group, integrating GESI principles into its mandate and outputs. | Programe Manager, Project Analyst, Inclusive Parliaments Specialist, M&E | Dec-Jan 2025 | 15000 | 3750 | 25% | At least 30% of working group members are women or marginalized groups, with documented GESI integration in outputs.
1.2.1 Effective Committee Oversight Workshops. | 2.1:-Ensure that the workshop content is gender-inclusive with a Dedicated session on inclusive committee oversight, equipping members to address gender disparities and promote inclusive policies. | Programe Manager, Project Analyst, Inclusive Parliaments Specialist, M&E | Dec-Jan 2025 | 15500 | 6975 | 45% | At least 30% of workshop sessions incorporate gender-inclusive content, with participant feedback indicating improved understanding of gender disparities.
1.2.2 Committee specific training, peer-to-peer exchanges, and development of 'Committee Handbook'. | Incorporate a dedicated section in the 'Committee Handbook' and training modules on gender-responsive decision-making, providing practical tools to assess the gender impact of policies and ensure equitable representation. | Programe Manager, Project Analyst, Inclusive Parliaments Specialist, M&E | Dec-Jan 2025 | 30000 | 13500 | 45% | Gender-responsive decision-making section included in the handbook, with 50% of committees trained using the updated materials.
1.2.3 Integrate digital tools and AI with Committee work, including the inquiry process. | Ensure digital tools and AI collect and analyze gender-disaggregated data to support gender-responsive decision-making in inquiries. | Programe Manager, Project Analyst, Inclusive Parliaments Specialist, M&E | Dec-Jan 2025 | 20000 | 9000 | 45% | Digital tools integrated into committee work, with reports demonstrating the use of gender-disaggregated data in inquiries.
1.3.1 Facilitate FBO missions for focus parliaments. | Include gender experts in FBO missions where possible and prioritize discussions on gender-sensitive policies, budgeting and ensure respresentation of Women, PWDs and other marginlaized in CSO workshops associated with FBO | Programe Manager, Project Analyst, Inclusive Parliaments Specialist, M&E | Dec-Jan 2025 | 42875 | 19293.75 | 45% | At least 25% of FBO missions ensure represnttaion of Women and marginalized groups , with mission reports reflecting discussions on gender-sensitive policies and desegregaetd data
1.3.2 Undertake FBO consolidation and benchmarking exercise. | Include gender benchmarks in the FBO consolidation exercise and ensure participation of women and gender experts in the process. | Programe Manager, Project Analyst, Inclusive Parliaments Specialist, M&E | Dec-Jan 2025 | 32650 | 14692.5 | 45% | FBO consolidation includes at least one gender benchmark, with documented participation of women and gender experts.
1.4.1 Focus parliaments attend annual Pacific Islands parliamentary forum. | Ensure the delegation includes women MPs and representatives from marginalized groups to promote diverse perspectives and advocate for GESI priorities at the forum. |  |  | 17333 | 4333.25 | 25%
2.1.1 Provide technical advice, formulation, and review for strategic planning and institutional change initiatives. | Ensure technical advice includes a focus on integrating GESI aspects into strategic plans. | Programe Manager, Project Analyst, Inclusive Parliaments Specialist, M&E | Dec-Jan 2025 | 17000 | 7650 | 45% | Strategic plans reviewed include at least two GESI-specific recommendations.?
2.1.2 Business continuity for Pacific Legislatures - workshop. | Ensure the workshop content includes strategies for gender-responsive business continuity, equal representation in crisis planning, and addressing the needs of women and marginalized groups. | Programe Manager, Project Analyst, Inclusive Parliaments Specialist, M&E | Dec-Jan 2025 | 27593 | 12416.85 | 45% | Business continuity plans developed with at least one gender-responsive strategy.
2.2.1 Implement MPs induction training for focus parliaments, including pre- and post-induction workshops. | Include dedicated sessions on GESI in induction training and curriculum development, with pre- and post-training assessments to measure understanding and application. Ensure disaggregated data is available post-induction in reports. | Programe Manager, Project Analyst, Inclusive Parliaments Specialist, M&E | Dec-Jan 2025 | 42593 | 19166.85 | 45% | GESI sessions conducted in all induction trainings, with pre- and post-training assessments showing improved understanding by 70% of participants.
2.2.2 Undertake induction consolidation and curriculum development. | Incorporate GESI content into training modules and ensure the participation of women and persons with disabilities in parliamentary strengthening initiatives. | Programe Manager, Project Analyst, Inclusive Parliaments Specialist, M&E | Dec-Jan 2025 | 11250 | 5062.5 | 45% | Training modules with GESI content(Atleast 50?) , and at least 30% of participants are women or persons with disabilities.
3.1.1 Facilitate annual women MPs regional meetings. | Facilitate annual women MPs meetings to strengthen GESI initiatives with technical advice on integrating gender perspectives into policies. Ensure participation of Women MPs from all Parliments | Programe Manager, Project Analyst, Inclusive Parliaments Specialist, M&E | Dec-Jan 2025 | 29000 | 29000 | 100% | At least one GESI-related output or policy recommendation from women MPs' regional meetings.Peer Support ?
3.1.2 Technical advice for gender perspective intitiatives. | 3.1.2 Technical advice for gender perspective intitiatives. |  |  | 50000 | 50000 | 100%
3.2.1 Engage with sub-national women representatives and stakeholders. | Facilitate dialogues with sub-national women representatives and stakeholders to identify and address GESI priorities in local governance. | Programe Manager, Project Analyst, Inclusive Parliaments Specialist, M&E | Dec-Jan 2025 | 107500 | 107500 | 100% | Documented GESI priorities from at least two dialogues with sub-national women representatives.
3.2.2 Facilitate mock Parliaments or a mock Committee inquiry. | Design mock sessions to include gender-sensitive topics linked withbarriers and highliting enablers. Ensure equitable participation of women, persons with disabilities, and marginalized groups. | Programe Manager, Project Analyst, Inclusive Parliaments Specialist, M&E | Dec-Jan 2025 | 30000 | 30000 | 100%
4.1.1 Consolidate engagement initiatives and explore options for curriculum development. | Include gender-focused scenarios in engagement initiatives and curriculum development. | Programe Manager, Project Analyst, Inclusive Parliaments Specialist, M&E | Dec-Jan 2025 | 40667 | 18300.15 | 45% | Engagement initiatives and curriculum include at least one gender-focused scenario.
4.1.2 Assist focus parliaments to host Youth Parliament at national and/or sub-national levels. | Ensure Youth Parliaments prioritize gender balance in participant selection and include discussions on gender equality and inclusive governance. | Programe Manager, Project Analyst, Inclusive Parliaments Specialist, M&E | Dec-Jan 2025 | 29000 | 29000 | 100% | Youth Parliament participants include at least 50% women or marginalized youth, with discussions on gender equality documented.
4.2.1 Facilitate CSO-parliament dialogue for 4 focus parliaments. | Design CSO dialogues to focus on left behind and marginalized groups, especially organizations focused on gender equality and also ensure their participation in parliamentary consultations and decision-making. | Programe Manager, Project Analyst, Inclusive Parliaments Specialist, M&E | Dec-Jan 2025 | 65110 | 65110 | 100% | At least one CSOs focused on gender equality involved in dialogues for each parliament.
4.3.1 Develop handbook for media and press gallery guide. | Develop a media and press gallery guide with guidelines for gender-sensitive reporting and strategies for diverse representation in parliamentary coverage. | Programe Manager, Project Analyst, Inclusive Parliaments Specialist, M&E | Dec-Jan 2025 | 32000 | 14400 | 45% | Media guide includes at least three gender-sensitive reporting guidelines, with feedback from journalists on usefulness.
Gender aligned M&E System with all associated tools along with collection of desegregated Data | Availability of GESI aligned tools and Disegregated data | Programe Manager, Project Analyst, Inclusive Parliaments Specialist, M&E | Dec-Jan 2025 | 12926 | 12926 | 100% | 437
488876.85
|  |  | Total AWP Budget | Budget allocation for Gender | % contribution
|  |  | 1624143 | 488876 | 30.1006
Note on E4: Ensure this budget is aligned to the AWP budget.

## Monitoring plan
Monitoring Plan
January - December 2025
Project Name: 01003411- Pacific Parliamentary Effectiveness Initiative – Phase 3 (PPEI 3)
Country: Fiji, Solomon Islands, Vanuatu, Tonga, Niue, Cook Islands
DATE | LOCATION | MONITORING ACTIVITY | MISSION MEMBERS | PURPOSE | METHODOLOGY
(Month/Year) | (Country) |  | (Name / Designation)
quaterly/Six Monthly | TBC | Stakeholder Feedback Collection:- To gather in-depth insights on the success and relevancy of the project/activity/support through discussions and Q/A duing the activity/ sessions. | M&E specialist | The purpose of this feedback is to capture MPs’/CSOs perspectives on the relevance and success of the projects as well as to identify opportunities and bottlenecks for contextual improvement. The insights gathered will inform adjustments to better align the support with MPs' needs and the implementation strategy, thereby enhancing the success of the parliamentary strengthening program. Also it will help UNDP to capture success of the project . | Interviews, Feedback forms, FGDs( the most suited/relevant methodlogy as per the context wull be adopted to better triangulate data/Information
Mid-year( Six-Monthly) | Desk review and field missions based on desk review findings for De-brief( TBD) | Track and validate( Field missions if needed) quarterly progress against key targets to ensure alignment with AWP milestones across countries. | M&E and project Analysts | Monitor and validate quarterly progress against key targets to ensure alignment with AWP milestones across countries. Recommend course corrections if needed to ensure that the planning and implementation arrangements are valid and relevant and the project is moving in right direction | Validation, desk review, discussion with partner, feedback and Debrief
Semi-annually, or in the frequency required for each indicator. | Track progress on CPD and IRRF indicators | Progress data against the CPD and RRF Indicator will be collected and analysed through desk review and programatic fied missions( IF needed validation) | M&E and Programe Analysts | To collect and analyze progress data against the CPD and RRF indicators to evaluate the project's advancement toward achieving its agreed outputs, identify gaps, and implement necessary course corrections to ensure alignment with the desired outcomes. Also it woll help us to have evidences ready which will make reporting easier towards the year end | Validation, desk review, discussion with partner, feedback and success storiese,
Semi-annually | Risk Monitoring and tracking | Review of risks ,Identify specific risks that may threaten achievement of intended results. Identify and monitor risk management actions. This includes monitoring measures and plans that may have been required as per UNDP’s Social and Environmental Standards. Audits will be conducted in accordance with UNDP’s audit policy to manage financial risk. | Programe Manager, M&E and Project Analysts
DATE OF PROJECT BOARD MEETINGS
Guideline
Use the table above. Expand it, if needed.
Add all field monitoring visits planned in 2024. Plan is tentative.
Add only M&E-related field visits. DO NOT ADD any other field visit for attending a workshop/meeting, which is not relevant to M&E.
M&E-related field visits include but are not limited to: progress monitoring, results/data verification, data quality check, survey preparation, field testing of survey instruments, enumerator’s training, and data collection monitoring.
Describe a methodology briefly, if the purpose of field visit is progress monitoring or results/data verification, or data quality check. It cannot be a rigorous method due to limited time of a field visit, but a rapid method should be identified before going to the field.
Note on A18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Thomas Gregory can you please populate project board dates for 2025?

## Procurement Plan
UNDP Fiji MCO
Project Name(Pacific Parliamentary Effectiveness Initiative – Phase 3 (PPEI 3) Procurement Plan - 2025
Country | [5 empty] | Instructions: - If you need additional lines, right-click and "Insert" rows.
Submitted by:
Date:
| Sub-Action ID from AWP Tab | Type of Procurement Action | Title of Procurement Action | Procurement Category | Description of goods, services or works required | Unit of Measure | Quantity | Estimated Unit Price in USD | Estimated Total Price in USD | Multi-year contract in USD |  | Procurement request submission date | Final Delivery Date of Good/Services/Civil works/IC | Committee review
[10 empty] | 2025 | 2026
| Activity 1.1 | IC | International Consultant | IC | Procedural Advisor | each | 1 | 15000 |  | 15000 |  | 2025-03-01 | 2025-09-01
| Activity 1.1 | RFQ - 'Printing | Graphic Design and Printing | Printing | Graphic Design and Printing | each | 1 | 7000 |  | 7000 |  | 2025-06-01 | 2025-09-01
| Activity 1.1, 1.2, 1.3, 2.2, 3.2 | IC | International Consultant | IC | Learning Advisor - Curriculum Development | each | 1 | 40000 |  | 40000 |  | 2025-06-01 | 2025-11-30
| Activity 1.2 | RFQ -'ICT | IT Equipment | ICT Equipment | Committee ICT equipment | each | 1 | 10000 |  | 10000 |  | 2025-06-01 | 2025-09-01
| Activity 1.3 | IC | International Consultant | IC | Lead Technical Advisor Parliament & the Budget | each | 1 | 22875 |  | 22875 |  | 2025-06-01 | 2025-11-30
| Activity 2.1 | IC | International Consultant | IC | Technical Advisor - Strategic and service planning | each | 1 | 17000 |  | 17000 |  | 2025-06-01 | 2025-11-30
| Activity 2.2 | IC | International Consultant | IC | Parliament Support | each | 1 | 10000 |  | 10000 |  | 2025-01-03 | 2025-12-15
| Activity 2.3 | IC | International Consultant | IC | Learning Advisor Institutional Development | each | 1 | 42000 |  | 42000 |  | 2025-06-01 | 2025-11-30
| Activity 2.4 | IC | International Consultant | IC | ICT specialist - assessments, policy, TA | each | 1 | 35000 |  | 35000 |  | 2025-06-01 | 2025-11-30
| Activity 3.1 | RFQ -'Printing | Printing | Printing | Printing of booklets for annual wormen MPs regional meetings | each | 1 | 3000 |  | 3000 |  | 2025-06-01 | 2025-09-01
| Activity 3.2 | RFQ -'Printing | Printing | Printing | Printing of booklets for annual wormen MPs regional meetinhs | each | 1 | 4000 |  | 4000 |  | 2025-06-01 | 2025-09-01
| Activity 4.3 | RFQ -'Printing | Printing | Printing | Printing of handbook for media and press gallery guide | each | 1 | 7000 |  | 7000 |  | 2025-06-01 | 2025-09-01
Total Estimated 2025 Micro Procurement Plan (USD) | [7 empty] | 212875 | 0 | 212875
Total Estimated 2025 Procurement Plan (USD) | [8 empty] | 0
Note on H8: Eg: unit, day, month, etc.
Note on O8: Use format "10-Apr-2014" Leave blank if procurement is for goods
Note on Q11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: edited Type of procurement and no further comment

## HR plan
UNDP Pacific HR Plan - 2025
Project/Cluster: Pacific Parliamentary Effectiveness Initiative – Phase 3 (PPEI 3)
1. HR Plan for 2025 - positions to be recruited
Position | Country | Position reflected in Annual work Plan Yes/No | Contract modality | Type of recruitment | Category/ Band/ Grade | Contract Duration | Estimated start date | Estimated end date | Annual costs in USD | Monthly costs | % to be charged to the project | Total personnel costs
Project Analyst- Samoa | Samoa | Yes | NPSA | Competitive | 9 | 1 year | 2025-03-01 | 2026-02-28 | 36366.5211 | 3030.5434 | 100% | 36366.5211
Inclusive Parliaments Specialist (50%) | Fiji | Yes | IPSA | Competitive | 11 | 1 year | 2025-02-01 | 2026-01-31 | #REF! | #REF! | 35% | #REF!
NOTE:* Request for Service to be submitted at least 2 months prior the recruitment process
** The SCs salaries and Performance Bonus amount shall be allocated under 71400
2. Position management - Existing Staff (both national and international if applicable) - all contract type (NPSA, SC, IFTA, ITA, SSA)
Name | Position Title | Contract Modality | Level/Band | Contract end date (DD/MM/YYYY) | Planned extension
Thomas McLean Gregory | Project Manager | P | 4 | 2026-11-27
David Luta Kusilifu | Parliamentary Development Specialist | IPSA | 11 | 2025-08-27
Nisa Bibi | Programme Monitoring, Evaluation and Knowledge Specialist | IPSA | 10 | 2025-10-06
Hui Zhen Lown | Project Finance Analyst | NPSA | 9 | 2025-08-18
Komal Khushboo | Project Analyst- Fiji | NPSA | 9 | 2025-04-21
Filimoni Gadolo Yaya | Project Analyst- Fiji | NPSA | 9 | 2025-04-30
Heidi Sigrah Floyd | Project Analyst- FSM | NPSA | 9 | 2025-06-02
Gregory Lini Fineanganofo | Project Analyst- Solomon Islands | NPSA | 9 | 2025-05-14
Latanya Gwilliam | Project Administrative Associate | NPSA | 7 | 2025-07-31
Sharon Natasha Raj | Project Administrative Associate | NPSA | 7 | 2025-08-25
| Name/ Signature | Designation | Date
Prepared by
Recommended by
Certified by Team Leader
Approved by OM/DRR
Note on E5: Indicate if the recruitment is competitive, from a roster or special measures.

## Communication plan
Communication Plan
AWP Action ID | Target audience | Communication Activities & Tools | Timeline | Expected Result/Indicator of achievement | Resource requirements | Responsible CO Unit/Person
| (ranked by importance; highlight if contacts already made) | (how best to reach your respective target audiences with the key messages?) | (when is the activity due or how often?) | (for each tool chosen) | (person/days required, budget implications (also consider outsourcing costs)) | (And supporting unit/persons if any)
1.3.1, 1.3.2 | General public, acdemia, and Shared via respective Parliament Websites, social media, YouTube, and also during public outreach events or consultations | Production of Short Educational Material ( toolkits)on parliamentary roles, civic engagement, FBO, inclusion in governance, and youth representation with a purpose to educate and engage the public, especially younger demographics and remote communities | Quaterly | Vedio available fr wider reachout | Jointly with parliment /Support form communication Unit | Communication , MPO,Programe Unit and Parliments
3.1.1, 3.2.2, 4.1.2 | Media and general public | Press releases related to key events and activities of the portfolio /project, including background information, high-resolution images, and key statistics, to equip journalists with accurate information and expand media coverage of the project | Ongoing | Media toolkit for each event | Support form communication Unit | Communication , MPO,Programe Unit and Parliments
All key events | Donor, General public, Media | Social Media Posts on key project activitiese, Events | Ongoing | Ongoing | Support form communication Unit | Communication , MPO,Programe Unit and Parliments
Note on F3: Ensure communications costs are included in the AWP.

## Risk register
The PPEI has been signed recently, and the risks are being updated on Quantum. Therefore, there are no changes to the risk log at this stage
**** Only update the new risks and or updating of new risks treatments
# | Event | Cause | Impact(s) | Risk Category and Sub-category (including Risk Appetite) | Impact, Likelihood & Risk Level | Risk Valid From/To | Risk Owner | Risk Treatment and Treatment Owner
[5 empty] | (see Annex 3 Risk Matrix) |  | (individual accountable for managing the risk)
1 | There is a risk that delivery of project will be … | As a result of … | Which will impact in… |  | Likelihood: | From: | … | Risk Treatment 1.1: …
​​PLEASE SELECT​
[6 empty] | To: ​ |  | Risk Treatment Owner: …
Impact:
​​PLEASE SELECT​
[5 empty] | Risk level: |  |  | Risk Treatment 1.2: …
​​PLEASE SELECT​
Risk Treatment Owner: …
Risk Treatment 1.3: …
Risk Treatment Owner: …
2 | There is a risk that … | As a result of … | Which will impact in … |  | Likelihood: | From: | … | Risk Treatment 2.1: …
​​PLEASE SELECT​
[6 empty] | To: ​ |  | Risk Treatment Owner: …
Impact:
​​PLEASE SELECT​
[5 empty] | Risk level: |  |  | Risk Treatment 2.2: …
moderate
Risk Treatment Owner: …
Risk Treatment 2.3: …
Risk Treatment Owner: …

## Travel Plan
Project Title | Pacific Parliamentary Effectiveness Initiative – Phase 3 (PPEI 3)
Country | Fiji, Solomon Islands, Vanuatu, Tonga, Niue, Cook Islands
Duration | 1 Nov 2024 - 31 Oct 2029
Project ID (Quantum) | 01003411
| Mission | Month | Estimated Number of Travellers (staff) | Estimated Number of Travellers (external) | Local/international | Mode of transport (air, land, sea/river) | Security Planning Required (Y/N) | Estimated cost
| Tonga FBO | April | 1 | 12 | International | Air | N | 20000
| PIPG Delegations | August |  | 10 | International | Air | N | 30000
| Solomon Islands Committee Induction | May | 2 | 5 | International | Air | N | 23000
| Solomon Islands civic education | May | 1 | 6 | Local | Air | N | 8000
| Solomon Islands Committee inquiry | June | 1 | 15 | Local | Air | N | 6000
| Solomon Islands POCC | July |  | 3 | International | Air | N | 9000
| Kiribati Committee/PAC Induction | February | 2 | 3 | International | Air | N | 8000
| Vanautu MPs induction | May | 3 | 5 | International | Air | N | 15000
| Vanuatu Clerk Attachment | February | 0 | 2 | International | Air | N | 10000
| Vanuatu Youth Parliament | July | 1 | 4 | International | Air | N | 10000
| Vanuatu civic education | April | 1 |  | International | Air | N | 5000
Note on D10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Reviewed

## HACT plan (hidden)
Project Title
Country
Duration
Project ID
| IP/RP’s Name | List of Previous Observations | Actions to be undertaken | Proposed date | Status
Micro Assessment
Micro Assessment [year]
Spot Check
Spot check [year]
Audit
Audit [year]
Please add more rows if needed.
Note on C9: Provide a list of observations made by latest HACT micro-assessments and assurance activites
Note on D9: List the remedial actions agreed between UNDP and the partner to address the observations
Note on E9: Provide the estimated completion date

## Resource mobilization plan
Resource Mobilization Plan
Target partner | Expected funding | Targeted area(s) of cooperation* | Concrete actions and timing for engagement | Responsible CO Unit/Person
| (+X% or $Y from $Z in YYYY) | (Linked to new Strategic Plan) | (Consider partners’ budget cycle and most influencing persons for identifying good entry points for partnership and influencing funding decisions by partners. Specify the joint policy dialogues, high level meeting/letters, proposal submissions, etc. Indicate needed CO capacity investments) | (And supporting unit/persons if any)
(*Can also name the titles of associated projects)
UNDP | NZ$1,706,008 in 2024
NZ$2,647,352 in 2025
NZ$2,710,890 in 2026
NZ$2,429,615 in 2027
NZ$1,806,135 in 2028

## List (hidden)
Likelihood | Impact | Risk level
not likely | negligeable | low
low likelihood | minor | moderate
moderately likely | intermediate | substantial
highly likely | extensive | high
expected | extreme

## Reporting calendar
Project Title
Country
Duration
Project ID (Quantum)
| Type of Report | Reporting Frequency | Reporting Deadline
MFAT | Donor Progress Reports | Annual | 30 Oct, 2025
UNDP( Internal) | Monitoring Reports | As per frequency | TBC
UNDP( Internal) | ROAR 2025 | Annual | 2025-11-01

## UNDP Fund Codes (hidden)
Account | Description
61105 | Salaries - NO Staff
61160 | Other Payroll Costs - NO Staff
61205 | Salaries - GS Staff
61260 | Other Payroll Costs - GS Staff
61305 | Salaries - IP Staff
61310 | Post Adjustment - IP Staff
61360 | Other Payroll Costs - IP Staff
61399 | Salaries - UN MPO International Staff
62105 | Dependency Allowance - NO Staff
62110 | Contributions to Joint Staff Pension - NO Staff
62115 | Contributions to Medical, Social Insurances - NO Staff
62120 | Hazard Duty Station Allowance - NO Staff
62140 | Annual Leave Expense - NO Staff
62205 | Dependency Allowance - GS Staff
62210 | Contributions to Joint Staff Pension Fund - GS Staff
62215 | Contributions to Medical, Social Insurances - Staff outside New York
62220 | Language Allowance - GS Staff
62225 | Hazard Duty Station Allowance - GS Staff
62240 | Annual Leave Expense - GS Staff
62305 | Dependency Allowance - IP Staff
62310 | Contributions to Joint Staff Pension Fund - IP Staff
62315 | Contributions to Medical, Social Insurances - Staff in New York
62320 | Hardship and Non-Mobility Allowance - IP Staff
62325 | Representation Allowance (exclude hosplitality payment)
62330 | Rental Supplement - IP Staff
62335 | Hazard Duty Station Allowance - IP Staff
62340 | Annual Leave Expense - IP Staff
63105 | Compensatory Payments - NO Staff
63115 | Reimbursement of Income Tax - NO Staff
63125 | Termination Indemnity Cost - NO Staff
63130 | Contribution Dispensary Cost - NO Staff
63135 | Special Education Grant and Travel Expense - LNO Staff
63140 | Security Evacuation Cost - LNO Staff
63145 | Medical Evacuation Cost - LNO Staff
63150 | Reimbursement of Medical Costs - LNO Staff
63160 | Appendix D Compensation Cost - NO Staff
63205 | Compensatory Payments Cost - GS Staff
63215 | Reimbursement of Income Tax - GS Staff
63220 | Cost of Repatriation - GS Staff
63225 | Termination Indemnity Cost - GS Staff
63230 | Contribution Dispensary Cost - GS Staff
63235 | Special Education Grant and Travel Expense - GS Staff
63240 | Security Evacuation Cost - GS Staff
63245 | Medical Evacuation Cost - GS Staff
63250 | Reimbursement of Medical Costs - GS Staff
63260 | Appendix D Compensation Cost - GS Staff
63310 | Cost of Repatriation - IP Staff
63315 | Compensatory Payments Cost - IP Staff
63320 | Medical Evacuation Cost - IP Staff
63325 | Security Evacuation Cost - IP Staff
63330 | Education Grant and Travel Expense - IP Staff
63335 | Home Leave Travel Allowance - IP Staff
63340 | Rest and Recuperation Allowance - IP Staff
63350 | Reimbursement of Income Tax - IP Staff
63355 | Termination Indemnity Cost - IP Staff
63360 | Medical Exams including Pre-employment - Staff
63365 | Special Operations Living Allowance - IP
63370 | Assignment Allowance - IP Staff
63385 | Family Visit Travel - IP Staff
63405 | Learning Costs - Course Fee (staff)
63406 | Learning Costs - Air Ticket (staff)
63407 | Learning Costs - Daily Subsistence Allowance (staff)
63408 | Learning Costs - Subcontractors (staff)
63505 | Hazard Insurance
63510 | War Insurance
63511 | Staff related Insurance - Others
63515 | Security Cost - Staff Residences
63520 | Security Cost - Personal
63530 | Contribution to Repatriation Grant
63535 | Contribution to Security - Staff
63540 | Contribution to Training
63545 | Contribution to Information And Communications Technology (ICT) - Staff
63550 | Contributions to MAIP
63555 | Contribution to UN JFA
63560 | Contributions to Appendix D
64105 | Appointment Cost - National Officers
64110 | Separation Cost - National Officers
64115 | Competency Assessment - National Officers
64120 | Detail Assignment - National Officers
64205 | Appointment Cost - GS Staff
64210 | Separation Cost - GS Staff
64215 | Competency Assessment - GS Staff
64220 | Detail Assignment - GS staff
64305 | Appointment Cost - IP Staff
64306 | Appointment Cost - Air Ticket for IP Staff
64307 | Appointment Cost - Daily Subsistence Allowance for IP Staff
64308 | Appointment Cost - Lump Sum Salary for IP Staff
64309 | Appointment Cost - Shipment for IP Staff
64310 | Separation Cost - IP Staff
64315 | Detail Assignment - IP Staff
64316 | Relocation Grant upon Initial Assignment - IP Staff on Fixed-Term Appointment
64319 | Relocation Grant upon Reassignment - IP Staff on Fixed-Term Appointment
64320 | Reassignment Grant - IP Staff
64321 | Reassignment Cost - Air Ticket for IP Staff
64322 | Reassignment Cost - Daily Subsistence Allowance for IP Staff
64323 | Reassignment Cost - Lump Sum Salary for IP Staff
64324 | Reassignment Cost - Shipment for IP Staff
64325 | Recruitment Cost - IP Staff
64330 | Competency Assessment - IP Staff
64333 | Competency Assessment - Other
64397 | Direct Project Cost - Services provided by CO Staff
64399 | Expert Advisory Services - HQ Staff
65105 | Contribution to Medical Insurance Plan -Retired National Officers
65115 | Contributions to ASHI Reserve
65118 | Death Benefit Cost - Staff
65119 | Repatriation Grant Surcharge
65120 | Contribution to Medical Insurance Plan -Retired GS Staff
65135 | Payroll Management Cost Recovery - Atlas
66105 | Overtime and Night Differential Benefits - GS Staff
67205 | Labour Cost – NO Staff
67305 | Labour Cost – GS Staff
67405 | Labour Cost – IP Staff
71165 | Medical Insurance of UN Agencies NOT Administered by UNDP
71167 | Pension Fund of UN Agencies NOT Administered by UNDP
71168 | Personnel-related Cost with Other UN Agencies
71205 | International Consultants Expenses - Short-Term Technical Contractors
71210 | International Consultants Expenses - Short-Term Support Contractors
71305 | Local Consultants Expenses - Short-Term Technical Contractors
71350 | Internship Stipend
71405 | Service Contract Holders Cost
71410 | MAIP Premium - Service Contract Holders
71415 | Contribution to Security - Service Contract Holders
71420 | Payroll Management Cost Recovery - Service Contract Holders
71440 | Appendix D Compensation Cost - Service Contract Holders
71455 | Innovation Prizes - Individuals
71460 | International Personnel Services Agreement
71465 | Labour Cost - International Personnel Services Agreement
71470 | National Personnel Services Agreement
71475 | Labour Cost - National Personnel Services Agreement
71501 | Labour cost - UN Volunteers
71505 | UNV Volunteer Living Allowances
71510 | UNV Settling-In Grant
71511 | UNV Contribution towards expenses incurred for commencement of services
71515 | UNV Security Allowance
71520 | UNV Volunteer Learning
71525 | UNV Hazard Pay
71526 | UNV Wellbeing Differential
71530 | UNV Rest and Recuperation
71535 | UNV Medical Insurance
71536 | UNV Medical Evacuation Cost
71537 | UNV Security Evacuation Cost
71540 | UNV Global Charges
71541 | Contribution to Security - UN Volunteers
71545 | UNV Home Leave Travel and Allowance
71550 | UNV Resettlement Allowance
71560 | UNV International Appointment Repatriation Cost
71565 | UNV National Appointment Repatriation Cost
71581 | UNV UN Mission Housing
71582 | UNV UN Mission Liberty Mileage
71583 | UNV UN Mission Telephone
71584 | UNV UN Mission Medical Expenses
71585 | UNV Lost or Damaged Property UN Mission
71586 | UNV UN Mission Food Rations
71590 | UNV Development Effectiveness
71591 | UNV Cost Recovery Deployment
71592 | UNV Cost Recovery Recurring
71605 | Travel Tickets - International
71610 | Travel Tickets - Local
71615 | Daily Subsistence Allowance - International
71620 | Daily Subsistence Allowance - Local
71625 | Daily Subsistence Allowance - Meeting Participants (Non-Staff)
71630 | Shipment Cost
71635 | Travel Cost - Other
71810 | Long Term Contractual Service Cost - Individual Implementing Partners
72105 | Service Cost - Construction and Engineer
72110 | Service Cost - Agricultural Management
72115 | Service Cost - Natural Resources and Environment
72120 | Service Cost - Trade and Business Services
72125 | Service Cost - Studies and Research Services
72126 | Service Cost - Security Blast Assessment
72130 | Service Cost - Transportation Services
72135 | Service Cost - Communications Services
72136 | Service Cost - System Development
72137 | Service Cost - Help Desk Support Training
72138 | Service Cost - Business Analysis
72140 | Service Cost - Information Technology
72145 | Service Cost - Training and Education Services
72150 | Service Cost - Manufacturing Services
72155 | Service Cost - Public Admin and Politics
72160 | Service Cost - Education and Health Services
72165 | Service Cost - Social Services and Social Sciences
72170 | Service Cost - Humanitarian Aid and Relief
72175 | Service Cost - Urban, Rural and Regional Services
72180 | Innovation Prizes - Companies
72205 | Office Equipment
72210 | Machinery and Equipment
72215 | Transporation Equipment
72216 | Special Purpose Transportation - Armored and Mine
72220 | Furniture
72225 | Asset External Clearing
72305 | Consumables - Agriculture and Forestry Products
72310 | Consumables - Minerals, Mining and Metal Products
72311 | Consumables - Fuel, Petroleum and Other Oils
72315 | Consumables - Food and Textile Products
72320 | Comsumables - Wood and Paper Products
72325 | Consumables - Chemical, Glass and Non-Metallic Products
72330 | Consumables - Medical Equipment and Supplies
72335 | Consumables - Pharmaceutical Products
72340 | Consumables - Contraceptive Pills
72342 | Consumables - Contraceptive Condoms
72343 | Consumables - Contraceptive Injectables
72345 | Consumables - Contraceptives Spermicides
72350 | Consumables - Medical Kits
72366 | Consumables - Dignity and Hygiene Kits
72367 | Consumables - Personal Protective Equipment for Infectious Disease
72370 | Consumables - Security-related Supplies and Materials
72399 | Other Materials and Goods
72401 | Prefabricated Structure - Other Buildings
72402 | Other Building Maintenance
72406 | Security Equipment
72410 | Information and Communications Technology (ICT) Equipment
72415 | Courier Charges
72420 | Land Telephone Charges
72425 | Mobile Telephone Charges
72430 | Postage and Pouch System
72435 | E-mail-Subscription
72440 | Connectivity Charges
72445 | Common Services - Communications
72505 | Consumables - Stationery and Other Office Supplies
72515 | Print Media
72520 | Electronic Media
72605 | Grants to Institutions and Other Benefactors
72610 | Micro Capital Grants - Credit
72615 | Micro Capital Grants - Other
72620 | Joint Programming Expenditure
72625 | Non-Credit Capital Grants - Financial Service
72630 | Non-Credit Capital Grants - Local Government
72635 | Grant by International Professional (IP) toSubGrantee
72640 | Performance - based Payments Performance Based Grants (PBP)
72645 | Low Value Performance-based Payment
72705 | Hospitality Expenses - Special Events
72710 | Hospitality Expenses - Invoiced Expenses
72715 | Hospitality Expenses - Catering
72810 | Computer Software
72815 | Information and Communications Technology (ICT) Supplies
72820 | Internally Developed Software
72825 | Trademark, Copyrights and Licenses expensed
72915 | Direct Passthrough - Indirect Cost
72950 | Direct Budget Support Expenditure
73101 | Lease Expense - Land
73104 | Lease Expense - Building
73105 | Lease Expense - Adjustments
73106 | Leasehold Improvement on Leased Buildings
73107 | Rental Expense - Meeting Rooms
73108 | Rental Expense - Office Equipment and Furniture
73110 | Custodial and Cleaning Services
73115 | Office Relocation Expenses
73120 | Utilities
73125 | Common Services - Premises
73201 | Land
73204 | Building
73205 | Leasehold Improvement on Owned Premises
73210 | Security Reinforcement on Owned Premises
73216 | Construction Cost
73305 | Maintenance Cost - Hardware
73310 | Maintenance Cost - Software Licenses
73315 | Rental Expense - Information And Communications Technology (ICT) Equipment
73405 | Rental and Maintenance Cost - Other Office Equipment
73406 | Maintenance Cost - Equipment
73410 | Maintenance Cost - Transportation Equipment
73420 | Lease Expense - Vehicles
73440 | Lease Expense - Heavy Equipment and Other Equipment
73505 | Reimbursement to UNDP for Support Services
73510 | Reimbursement to UN for Support Services
73515 | Reimbursement to UN for External Audit Services
73520 | Reimbursement to UN for System Entity Support Services
74105 | Management and Reporting Services
74110 | Audit Fees
74112 | Accounting Related Fees
74115 | Legal Fees
74120 | Capacity Assessment
74125 | Investment Management Fees
74205 | Audio Visual Productions
74210 | Printing and Publications
74215 | Promotional Materials and Distribution
74220 | Translation Costs
74225 | Other Media Costs
74305 | Contributions to Consultative Committee on Administrative Questions (CCAQ)
74310 | Contributions to Joint Inspection Unit (JIU)
74315 | Contributions to International Civil Service Commission (ICSC)
74320 | Contributions to Chief Executive Board (CEB) Activity
74325 | Contributions to Country Office Common Security
74335 | Contributions to RC System
74340 | Contributions to Global Evaluation Initiative (GEI)
74410 | Charges on Financially-Completed Projects
74420 | Exchange Loss - Executing Agency
74505 | General Insurance
74507 | Warranty Expense for Office Equipment
74510 | Bank Charges
74515 | Claims and Adjustments
74520 | Storage Cost
74525 | Sundry Expenses
74530 | Staff Welfare
74595 | Appraisal and De-Risking
74596 | Services to Projects - General Opex
74597 | Direct Project Costs to Recover Waived
74599 | UNDP Cost Recovery Charged - Bills
74705 | Port Operation Costs
74710 | Land Transport Costs
74715 | Electronic Data Processing Operations Cost
74720 | Distribution Cost
74725 | Other Logistics Expenses
74906 | Gain/Loss Disposal Fixed Asset
74955 | Non - Property Plant Equipment (PPE) Transfers - Intra-unit
75105 | Facilities and Administration - Implementation
75110 | GMS current year adjustment
75115 | GMS prior year adjustment
75705 | Learning Costs - Course Fee (non staff)
75706 | Learning Costs - Air Ticket (non staff)
75707 | Learning Costs - Daily Subsistence Allowance (non staff)
75708 | Learning Costs - Subcontractors (non staff)
75709 | Learning Costs - Training of Counter
75710 | Learning Costs - Participation of Counterparts
75711 | Learning Costs - Stipends for Training, Workshop, Conference
75712 | Learning Costs - Honorariums to Professionals
76110 | Unrealized Foreign Exchange Losses
76125 | Realized Loss
77101 | Labour Cost – NO Staff on Temporary Appointment
77105 | Salaries - NO Staff on Temporary Appointment
77110 | UNJSPF Pension Contribution - NO Staff on Temporary Appointment
77115 | Employer Portion of Medical and Social Insurance - NO Staff on Temporary Appointment
77120 | Cost of Repatriation and Annual Leave - NO on Temporary Appointment
77125 | Termination Indemnity Cost - NO Staff on Temporary Appointment
77126 | Death Benefits Cost - Temporary Appointment
77135 | Special Education Grant - LNO on Temporary Appointment
77145 | Dependency Allowance - NO Staff on Temporary Appointment
77150 | Reimbursement of Medical Costs - LNO Staff on Temporary Appointment
77153 | Reimbursement of Income Tax - NO Staff on Temporary Appointment
77155 | Appointment Cost - NO Staff on Temporary Appointment
77160 | Other Payroll Costs - NO Staff on Temporary Appointment
77165 | Hazard Duty Station Allowance - NO Staff on Temporary Appointment
77170 | Overtime and Night Differential Benefits - NO Staff on Temporary Appointment
77190 | Relocation Grant - National Officers on Temporary Appointments
77195 | MAIP Premium - NO Staff on Temporary Appointment
77197 | Appendix D Compensation Cost - National Officers on Temporary Appointment
77201 | Labour Cost – GS Staff on Temporary Appointment
77205 | Salaries - GS Staff on Temporary Appointment
77210 | UNJSPF Pension Contribution - GS Staff on Temporary Appointment
77215 | Employer Portion of Medical and Social Insurance - GS Staff on Temporary Appointment
77220 | Language Allowance - GS Staff on Temporary Appointment
77225 | Termination Indemnity Cost - GS Staff on Temporary Appointment
77235 | Special Education Grant - GS Staff on Temporary Appointments
77240 | Security Evacuation Cost - GS Staff on Temporary Appointment
77245 | Dependency Allowance - GS Staff on Temporary Appointment
77250 | Reimbursement of Medical Costs - GS Staff on Temporary Appointment
77253 | Reimbursement of Income Tax - GS Staff on Temporary Appointment
77255 | Assignment Grant - GS Staff on Temporary Appointment
77260 | Other Payroll Costs - GS Staff on Temporary Appointment
77265 | Hazard Duty Station Allowance - GS Staff on Temporary Appointment
77270 | Overtime and Night Differential Benefits - GS Staff on Temporary Appointment
77290 | Relocation Grant - GS Staff on Temporary Appointments
77295 | MAIP Premium - GS Staff on Temporary Appointment
77297 | Appendix D Compensation Cost - GS Staff on Temporary Appointment
77301 | Labour Cost – IP Staff on Temporary Appointment
77305 | Salaries - IP Staff on Temporary Appointment
77306 | Appointment Cost - Air Ticket for IP Staff on Temporary Appointment
77307 | Appointment Cost - Daily Subsistence Allowance for IP Staff on Temporary Appointment
77309 | Appointment Cost - Shipment for IP Staff on Temporary Appointment
77310 | Post Adjustment - IP Staff on Temporary Appointment
77315 | Employer Portion of Medical and Social Insurance - IP Staff on Temporary Appointment
77320 | Hardship and Non-Mobility Allowance - IP Staff on Temporary Appointment
77323 | Appointment Cost - Lump Sum Salary for IP Staff on Temporary Appointment
77325 | Representation Allowance (exclude hosplitality payment) -TA
77330 | Education Grant and Travel Expense - IP Staff on Temporary Appointment
77335 | Hazard Duty Station Allowance - IP Staff on Temporary Appointment
77345 | Dependency Allowance - IP Staff on Temporary Appointment
77350 | Rental Supplement - IP Staff on Temporary Appointment
77353 | Reimbursement of Income Tax - IP Staff on Temporary Appointment
77355 | Termination Indemnity Cost - IP Staff on Temporary Appointment
77357 | Cost of Repatriation and Annual Leave - IP on Temporary Appointment
77365 | Special Operations Living Allowance - IP on Temporary Appointment
77375 | UNJSPF Pension Contribution - IP Staff on Temporary Appointment
77380 | Security Evacuation Cost - IP Staff on Temporary Appointment
77385 | Contribution to Security - IP/Temporary Appointment
77386 | Contribution to Information And Communications Technology (ICT) - TA
77390 | Relocation Grant - IP Staff on Temporary Appointments
77395 | MAIP Premium - IP Staff on Temporary Appointment
77396 | Payroll Management Cost Recovery
77397 | Appendix D Compensation Cost - IP Staff on Temporary Appointment
77401 | Contribution to Shared General Opex - Information And Communications Technology (ICT) Costs
77402 | Contribution to Shared General Opex - Security Costs
77403 | UNJSPF Pension Contribution - Shared General Opex
77923 | Investments - Impairment Loss
77924 | Investments - Impairment Reversals