Country/Region/Global: Republic of Kazakhstan

Project Initiation Plan

Project Title: Climate Promise Kazakhstan – From Pledge to Impact II

Expected UNDAF/CP Outcome(s):	Outcome 3.2. By 2025, all people in Kazakhstan, in particular most vulnerable, benefit from increased climate resilience, sustainable management of environment and clean energy, and sustainable rural and urban development.

Expected CPD Output(s): Output 4.4: Climate change measures integrated into national policies, strategies and planning

Initiation Plan Start/End Dates: March 2025-December 2025

Implementing Partner: UNDP

Brief Description

The project has been initiated as a response to the country's request for NDC Partnership. This project aims to enhance Kazakhstan’s Nationally Determined Contributions (NDC) 3.0 by integrating robust adaptation, loss and damage, and financing strategies. It focuses on strengthening institutional frameworks, mobilizing resources, and ensuring effective implementation through a comprehensive and inclusive approach.

A key aspect of the project is development and incorporation of adaptation-related provisions within the draft NDC 3.0 to strengthen the country’s resilience to climate change. In parallel, provisions addressing loss and damage are being formulated to ensure a structured response to climate-induced risks and vulnerabilities. To support these efforts, a dedicated financing chapter is being developed to outline resource needs, investment pathways, and mechanisms for mobilizing financial support. Sector-specific investment plans are being developed, providing clear roadmaps, technical requirements, and recommendations for capacity-building.

Total resources required           	$ 572 400

Total allocated resources:	$ 572 400

- Regular			_________

- Other:

  - Donor Gov of Germany $ 572 400

  - Donor		_________

  - Government	_________

Unfunded budget:		_________

In-kind Contributions		_________

Programme Period:		2021-2025

Quantum Project Number:

Quantum Output ID:

Gender Marker:			GEN-1

Agreed by UNDP:

# Purpose and Expected Output

This Project is part of the global UNDP's flagship initiative, the Climate Promise: From Pledge to Impact - Leveraging the Climate Promise to turn enhanced Nationally Determined Contributions (eNDC) into ambitious climate action.

In 2023, Kazakhstan became the first country in Central Asia to adopt the Strategy for Achieving Carbon Neutrality of the Republic of Kazakhstan until 2060 (Strategy 2060) and revised its initial Nationally Determined Contribution (NDC). The Strategy identifies the energy, industry, and waste sectors as critical for achieving this ambitious goal. The first update of the NDC includes an unconditional target, aiming for a 15% reduction in greenhouse gas (GHG) emissions by 2030, relative to the 1990 baseline year. Additionally, a conditional target aspires to achieve a more substantial 25% reduction in GHG emissions by 2030 compared to the 1990 base year.

To facilitate the implementation of the carbon neutrality vision, there is a need for a concrete action plan with sectoral and cross-sectoral activities, including a clear assessment of activities' emission reduction/absorption potential, timeframe, and responsible partners identified. The integration of these activities into government programming will ensure the direction of public funding and provide proper signals to private investment flows in line with the Strategy 2060 priorities. The introduction of requirements on climate change/environmental impact, along with the assessment of social and economic effects in the methodology of strategic planning through the development of relevant amendments, will ensure that state/regional programs/projects align with NDC/Strategy 2060 goals.

This assistance supplements ongoing programs in the country. UNDP-PAGE, for instance, collaborated with the Government to evaluate the implications of the Carbon Border Adjustment Mechanism (CBAM) on Kazakhstan's economy. The tool developed incorporates multiple CBAM implementation scheme proposals, allowing for the consideration of various future development scenarios.

The Seventh Operational Phase of the GEF Small Grants Programme in Kazakhstan (2022-2026) is directed at empowering local communities and organizations. Its goal is to facilitate integrated and adaptive actions, fostering socio-ecological resilience and sustainable livelihoods in seven designated landscapes, resulting in both local and global environmental benefits.

Furthermore, the UNDP-GEF project on sustainable forest management (2018-2024), funded at 5.42 million USD, conducted research on climate change adaptation measures. It also played a crucial role in establishing a national system for monitoring climate change indicators within the forest ecosystem.

The project intends to amplify the impact of the ongoing relevant programs mentioned above by responding to the country's request for support in the NDC Partnership and enhancing the country's capability to implement necessary measures and actions to achieve carbon neutrality by 2060.

Key outputs of the project are:

- Adaptation-related provisions have been developed and included in the draft NDC 3.0.

- Loss and Damage-related provisions have been developed and incorporated into the draft NDC 3.0

- The Financing Chapter has been developed and incorporated into the draft NDC 3.0.

- Sector-Specific Investment Plans with clear roadmaps, technical requirements, and recommendations for capacity-building.

- Comprehensive Resource Mobilization Strategy detailing funding needs, technical capacities, and enabling frameworks for implementation.

- Monitoring and Reporting Framework to track financial flows and evaluate progress.

# Management Arrangements

The Project Initiation Plan will be implemented by the UNDP Country Office under the Direct Implementation Modality (DIM) in line with UNDP’s Programme and Operations Policies and Procedures (UNDP POPP). UNDP will be responsible for overall management, ensuring project coherence, the preparation and implementation of work plans and annual audit plans; preparation of project budget and budget revisions; disbursement and administration of funds; recruitment of national and international consultants and personnel; financial and progress reporting; and monitoring and evaluation.

The Country Office will work closely with the Climate Strategies and Policy Team under the UNDP/GPN/BPPS’s Nature Climate and Energy Team. The CO will be responsible for preparation of the Final PIP Report.  Regional and global teams will be responsible for aggregating country reports to compile the overall results of the global portfolio, and the CO will be responsible for delivering and tracking activities and expenditures for the country level activities to the Regional Climate Promise Coordinator and the regional Climate Promise team.

The Project will be managed by the Project Manager assigned by UNDP Energy and Environment Unit Head and based on the Delegation of Authority approved by the Senior Management in line with local ICF. The Energy and Environment Unit will provide oversight, quality assurance, technical guidance and project management services as well as ensure the communication with the donor. The Management and Programme Support (MPSU) and Operations Units will provide administrative and financial support to the project implementation.

# Monitoring

In accordance with UNDP’s programming policies and procedures, the project will be monitored through the following monitoring plan:

| Monitoring Activity | Purpose | Frequency | Expected Action |
| --- | --- | --- | --- |
| Track results progress | Progress data and information against the expected results will be collected and analysed to assess the progress of the project in achieving the agreed activity results. | Quarterly | Slower than expected progress will be addressed by project management. |
| Track PIP expenditures | PIP expenditures will be monitored and assessed to ensure adequate delivery and to advise and course correct when needed | Monthly | Lower than expected delivery will be addressed by project management. |
| Monitor and Manage Risk | Identify specific risks that may threaten achievement of intended results. | Quarterly | Risks are identified by project management and actions are taken to manage risk. |
| Learn | Knowledge, good practices and lessons will be captured regularly, as well as actively sourced from other projects and partners and integrated back into the project. | Semi-annual | Relevant lessons are captured and used to inform management decisions. |
| On-time communication with the regional Climate Promise Coordinator | Regional Climate Promise Coordinator shall be timely informed on progress implementation dynamics, budget expenditures and delivery, as well as on potential risks in project implementation and lessons learnt. | Regularly | Delivery issues and risk are identified and tamely actions are taken to resolve the issues and address the risks |
| Final Report | The final narrative report, including financial report, will be prepared in accordance with UNDP requirements. The report will also feature a detailed description of the outputs produced by the project. | At the project’s operational closure | A final technical report and financial report will be produced upon completion of project activities. |

# WORK PLAN

Period: 6 months

| EXPECTED OUTPUTS And baseline, indicators including annual targets | PLANNED ACTIVITIES List activity results and associated actions | TIMEFRAME 2024 |  |  |  | RESPONSIBLE PARTY | PLANNED BUDGET |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount |
| Output 1 Countries have ownership, capacities and resources to enhance their NDC as part of the next revision cycle and global/regional stocktake, aligned to long-term pathways Indicator 1.1: Adaptation-related provisions have been developed and included in the draft NDC 3.0 Baseline: No Targets: Yes Indicator 1.2: Loss and Damage-related provisions have been developed and incorporated into the draft NDC 3.0 Baseline:0 Targets: 2 Baseline: No Targets: Yes Indicator 1.3: The Financing Chapter has been developed and incorporated into the draft NDC 3.0 Baseline: No Targets: Yes Indicator 1.4: Sector-Specific Investment Plans with clear roadmaps, technical requirements, and recommendations for capacity-building Baseline: No Targets: Yes | Activity 1.1: Conduct climate vulnerability and risk assessments with a gender perspective, engage with the NAP team, and organize sectoral consultations to develop a comprehensive adaptation framework that ensures alignment with NAP priorities |  | X | X | X | SEI (RPA) | CP2- BMZ 1-NDC 3.0 | 72100 - Contractual services - Companies | 30000 |
|  | Activity 1.2.: Assess the socio-economic and gender-responsive impacts of climate-related disasters, map international funding opportunities, and conduct targeted stakeholder consultations to outline L&D provisions for the NDC 3.0, including disaster resilience, early warning systems, and funding mechanisms |  | X | X | X | SEI (RPA) | CP2- BMZ 1-NDC 3.0 | 72100 - Contractual services - Companies | 20000 |
|  | Activity 1.3.: Conduct a rapid financing needs assessment, map potential funding sources, outline a roadmap for long-term resource mobilization, and draft initial financing chapter while engaging with private sector stakeholders to identify investment opportunities and co-financing models |  | X | X | X | SEI (RPA) | CP2- BMZ 1-NDC 3.0 | 72100 - Contractual services - Companies | 20000 |
|  | Activity 1.4: Organize at least three thematic workshops (including at the Central Asia sub-region), to gather and validate inputs for NDC 3.0 among all involved stakeholders, including civil sector, women and youth | X | X | X | X | UNDP | CP2- BMZ 1-NDC 3.0 | 72100 - Contractual services - Companies | 10000 |
|  |  |  |  |  |  |  |  | 71600 - Travel | 30000 |
|  | Activity 1.5: Compile key findings on adaptation, L&D, and financing, draft policy guidance for NDC 3.0 integration, and conduct an internal review with government stakeholders |  |  | X | X | SEI (RPA) | CP2- BMZ 1-NDC 3.0 | 72100 - Contractual services - Companies | 15000 |
|  | Activity 1.6: Identify priority sectors and actions requiring investment, evaluate technical and institutional requirements, design public-private partnership frameworks, and create detailed roadmaps outlining funding needs, technical requirements, and capacity-building recommendations |  |  | X | X | SEI (RPA) | CP2- BMZ 1-NDC 3.0 | 72100 - Contractual services - Companies | 60000 |
|  | Activity 1.7: Conduct a financial gap analysis across sectors, map funding sources, and identify innovative financing mechanisms |  |  |  |  | SEI (RPA) | CP2- BMZ 1-NDC 3.0 | 72100 - Contractual services - Companies | 40000 |
|  | Activity 1.8: Establish a system to monitor and track financial inflows |  |  |  |  | SEI (RPA) | CP2- BMZ 1-NDC 3.0 | 72100 - Contractual services - Companies | 30000 |
|  | Activity 1.9: Implement capacity-building initiatives to enhance expertise in climate finance and resource mobilization |  |  |  |  | UNDP | CP2- BMZ 1-NDC 3.0 | 71200 - International Consultants | 10000 |
|  | Activity 1.10: Conduct gender-responsive, economic and non-economic loss assessments, including funding sources for adaptation and L&D, climate risk insurance, and disaster resilience funds; and develop a strategy to mobilize public sector finance through national budget allocations for L&D and adaptation initiatives |  |  |  |  | SEI (RPA) | CP2- BMZ 1-NDC 3.0 | 72100 - Contractual services - Companies | 40000 |
|  | Activity 1.11: Develop recommendations to enhance institutional frameworks of coordination among agencies responsible for adaptation and L&D |  |  |  |  | UNDP | CP2- BMZ 1-NDC 3.0 | 72100 - Contractual services - Companies | 30000 |
|  | Activity 1.12: Initiate capacity building on project preparation and fund application |  |  |  |  | UNDP | CP2- BMZ 1-NDC 3.0 | 71200 - International Consultants | 10000 |
|  | Activity 1.13: Assess institutional capacities on climate finance management, project preparation, and fund management |  |  |  |  | SEI (RPA) | CP2- BMZ 1-NDC 3.0 | 72100 - Contractual services - Companies | 40000 |
|  | Activity 1.14: Facilitate consultations, knowledge-sharing sessions, and create case studies that showcase best practices in resource mobilization and investment planning, with the goal to align public and private investments |  |  |  |  | UNDP | CP2- BMZ 1-NDC 3.0 | 71200 - International Consultants | 41600 |
|  | Activity 1.15: Design a financial tracking system with progress indicators and assess institutional capacity to implement the system |  |  |  |  | UNDP | CP2- BMZ 1-NDC 3.0 | 72100 - Contractual services - Companies | 60000 |
|  | Project Management |  |  | X | X | UNDP | BMZ LT-LEDS2 | 71400 - Service Contracts-Individuals | 26400 |
|  |  |  |  | X | X |  |  | DPC operations 64397- 70%) | 17000 |
|  |  |  |  |  |  |  |  | 74596 – 30% |  |
|  |  |  |  | X | X |  |  | 75100 - Facilities & Administration | 42400 |
| TOTAL |  |  |  |  |  |  |  |  | 572400 |

ANNEX 2: OFFLINE PROJECT RISK REGISTER TEMPLATE

| Project Title: Climate Promise Kazakhstan – From Pledge to Impact II | Project Number: | Date: Click or tap to enter a date. |
| --- | --- | --- |

| # | Event | Cause | Impact(s) | Risk Category and Sub-category (including Risk Appetite) | Impact, Likelihood & Risk Level (see Annex 3 Risk Matrix) | Risk Valid From/To | Risk Owner (individual accountable for managing the risk) | Risk Treatment and Treatment Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | There is a risk that government may lack commitment to low carbon development. | As a result of change in political priorities, lack of understanding, resistance of industries or resource constrains. | Which will impact in delayed progress, reduced effectiveness or abandoning some activities. | 7. STRATEGIC (7.5. Government commitment) - UNDP Risk Appetite: OPEN TO SEEKING | Likelihood: 1 - Not likely Impact: 2 - Minor Risk level: LOW (equates to a risk appetite of MINIMAL) | From: 30-Apr-25 To: 31-Dec-25 | Project Manager | Risk Treatment 1.1: Regularly engage with government counterparts at different levels to ensure continued commitment and support. This may include workshops, joint planning sessions, and regular updates on project progress.… Risk Treatment Owner: Project Manager |
| 2 | There is a risk of delay in procurement of expert services as a result of limited market offer for the specific expertise. | As a result of limited market offer for the specific expertise . … | Which will impact in delayed delivery. … | 2. FINANCIAL (2.5. Delivery) - UNDP Risk Appetite: MINIMAL TO CAUTIOUS | Likelihood: 1 - Not likely Impact: 2 - Minor Risk level: LOW (equates to a risk appetite of MINIMAL) | From: 30-Apr-25 To: 31-Dec-25 | Project Manager | Risk Treatment 2.1: Advance planning of procurement, use of UNDP professional networks and rosters of national and international experts to engage qualified experts. Risk Treatment Owner: Project Manager |

Maximum 18 months