United Nations Development Programme

Project Document for NAP/Readiness projects

financed by the Green Climate Fund

| Project title: Developing and implementing the National Adaptation Plan (NAP) Process in Yemen |  |  |  |  |
| --- | --- | --- | --- | --- |
| Implementing Partner (GCF Executing Entity): United Nations Development program (UNDP) |  | Execution Modality: Direct Implementation Modality (DIM) |  |  |
| UNSDCF/Country Programme Outcome: Outcome 1: “By 2025, people in Yemen, especially women, adolescents and girls and those in the most vulnerable and marginalized communities benefit from better, equal and inclusive access to nutritious food, sustainable and resilient livelihoods and environmental stability. |  |  |  |  |
| UNDP Strategic Plan Output: 2.3.1 Data and risk-informed development policies, plans, systems and financing incorporate integrated and gender-responsive solutions to reduce disaster risks, enable climate change adaptation and mitigation, and prevent risk of conflict |  |  |  |  |
| UNDP Social and Environmental Screening Category: MODERATE |  |  | UNDP Gender Marker: GEN2 |  |
| Quantum Project ID: 01004504 |  |  | Quantum Award ID: 1390392 |  |
| UNDP- PIMS ID number: 10103 |  |  | GCF ID number: YEM-RS-006 |  |
| Planned start date: 22 April 2025 |  |  | Planned end date: 22 July 2029 (with an additional grace period of three months) |  |
| PAC meeting date: TBD |  |  |  |  |
| Brief project description: The project will establish the NAP process in Yemen and strengthen the institutional coordination, policy, technical and financial framework capacities in key sectors with conflict sensitive approaches for adaptation planning. The project will build technical capacity through access to climate risk and vulnerability information which includes conflict analysis, establish the NAP platform for information sharing, awareness raising and knowledge management, establish systems and capacity for effective adaptation monitoring and evaluation, develop a cross-sectoral climate finance strategy, and clearly articulate adaptation priorities by developing a set of concept notes to mobilize climate finance. The implementation of the NAP process in Yemen will ensure that vulnerable communities, including women, children, and marginalized groups, are empowered to build resilience to climate change impacts. |  |  |  |  |
| Financing Plan |  |  |  |  |
| GCF grant |  |  | USD 2,672,800.00 (without DP Fees) |  |
| - Total Budget administered by UNDP |  |  | USD 2,672,800.00 (without DP Fees) |  |
| Signatures |  |  |  |  |
| Signature: Zena Ali Ahmad Resident Representative UNDP Yemen | Agreed by UNDP |  |  | Date/Month/Year: |

Disbursement: The UNDP CO is aware of the conditions of disbursement ascribed to the first and subsequent tranches of the GCF funding as specified in the FWA (and in particular Clause 4 of the FWA). To the extent that these obligations reflect actions of UNDP, UNDP must ensure that the conditions are met and there is continuing compliance, as well as understanding that availability of GCF funding is contingent on meeting all conditions listed in the FWA.

# Table of Contents

I.	Table of Contents	6

II.	Development Challenge	6

III.	Strategy	6

IV.	Results and Partnerships	7

V.	Project Results Framework	8

VI.	Monitoring and Evaluation (M&E) Plan	9

VII.	Governance and Management Arrangements	13

VIII.	Financial Planning and Management	19

IX.	Total Budget and Work Plan	21

X.	Legal Context	22

XI.	Risk Management	23

XII.	Mandatory Annexes	26

Annex A: GCF approved Readiness and Preparatory Support Proposal	27

Annex B: GCF notification of approval letter	28

Annex C: Procurement plan	29

Annex D: Terms of Reference for Project Board and Project Team	30

Annex E: UNDP Risk Log	37

Annex F: UNDP Project Quality Assurance Report	39

# Development Challenge

Geophysical and climate context

Yemen is an arid Middle Eastern country, occupying an area of 527,970 square kilometers at the southern end of the Arabian Peninsula with a population of 34.45 million in 2023. It is bordered to the north by Saudi Arabia, to the East by Oman, and the South and West by a 2,200 km coastline along the Gulf of Aden, Arabian Sea, and the Red Sea. It is subdivided into 21 governorates (muhafazat) and one municipality (Amanah).

Yemen can be geographically divided into five distinct regions:  1) The Tihama region, a hot and humid coastal plain with low precipitation (below 130 mm annually) stretching 2,200 kilometres (30–60 km wide) along the  Red Sea to the west, and the Gulf of Aden and Arabian Sea to the south; 2) The Sarawat Mountains, which comprise western and central highlands, rise abruptly from the coast along Yemen’s entire western perimeter and continue northward into Saudi Arabia, ranging from 1,000 to over 3,000 meters, and includes Jabal Al-Nabi Shu’ayb at 3,665 meters above sea level, the highest point on the Arabian Peninsula. These highlands receive the most precipitation oi the entire Arabian Peninsula. The temperate central highlands, where the capital Sana’a is located, comprise most of the elevated expanse above 2,000 meters. 3) The sparsely populated Eastern Highlands have elevations ranging from 750 to approximately 1,000 meters. 4) Rub al-Khali Desert or “Empty Quarter” which occupies the north and northeastern interior comprising 57% of Yemen’s territory, is classified as desert and is largely devoid of settlements. 5) Yemen also claims over112 islands in the Red Sea, the largest being Socotra Island (3,900 km2), an ecologically unique archipelago, with rich mangroves, coral reefs, and fisheries, and became a separate governorate in 2013.

Yemen is highly vulnerable to climate change impacts, including droughts, floods, flash floods, sea level rise, cyclones and sea surges, heat and heat waves, and land degradation and desertification. These impacts and climate-induced hazards have caused significant consequences, such as loss of lives and livelihoods, infrastructure destruction, water scarcity, food insecurity, ecosystem damage, and disease outbreaks, which have hindered economic progress and setbacks in its Sustainable Development Goals. Recent research found that climate change in Yemen will adversely affect the health and nutrition of the population and will be responsible for over 121,000 deaths by 2060 and an estimated cumulative loss of $93 billion in gross domestic product (GDP) by 2060 if there is no action taken against climate change.

Yemen’s vulnerability to climate-induced hazards results from a combination of its geophysical characteristics, development challenges, socio-economic factors, and climate change impacts. These elements, both individually and collectively, increase the country’s exposure to risks, which are further worsened by the ongoing conflict that has persisted since 2014. Yemen faces a complex intersection of development, conflict, and climate change, with the conflict contributing to a humanitarian crisis that affects about 80% of households, limiting access to essential services and exacerbating existing vulnerabilities.

Yemen has a tropical arid and semiarid climate along its coast and inland desert, and a subtropical and temperate climate in its highlands, with generally wide temperature ranges and two monsoonal rainy and dry seasons annually (Spring (March-May) and Summer (July-September)). Between 1971 and 2020, Yemen’s mean annual temperature increased by 0.42°C per decade, with large regional and seasonal differences accompanying a significantly increasing number of hot and humid days and nights.  During the same period, Yemen experienced a decrease in annual precipitation (−6.25 mm) per decade, though not significantly at a national level, and precipitation trends varied regionally and interannually.

Under climate change scenarios Yemen’s temperatures are projected to increase by 1.64°C to 27.02°C by mid-century,. Precipitation volumes are also expected to increase nationally by midcentury with seasonally and regionally distinct shifts with significant uncertainty. By midcentury there will be a large percent change in Yemen’s total precipitation amounts and an increase in extremes. All governorates except the easternmost are projected to be at least twice as likely to experience extreme events. Governorates in the Tihama and parts of the highlands are projected to experience the greatest percent increase in precipitation by midcentury, mostly during summer months while the central and southern highlands are expected to experience the biggest changes in average largest 5-day precipitation, with locally varying seasonal patterns.

These projected changes pose risks to interannual and long-term water resources management, agricultural production and food security, health, and critical infrastructure.  Sea level rise, inundation, and erosion will increasingly threaten Yemen’s coastline (Tihama and Socotra) by the end of the century. Flooding across all of Yemen’s main regions will likely continue occurring with greater intensity and frequency as will drought and related water scarcity.

Development Context

Yemen is one of the most vulnerable countries to climate change, yet one of the least prepared to address its impacts. According to the ND-GAIn Index (2022), Yemen ranks 171st out of 181 countries for climate vulnerability, making it the 22nd most vulnerable and the 12th least ready country in the world. Despite its minimal contribution to the global GHG emissions, Yemen faces significant climate change risks, increasing the country’s vulnerability and exacerbating the country’s already fragile situation. Yemen has been embroiled in a civil conflict since 2015, which has devastated the country’s infrastructure, economy, and social services. The conflict has resulted in the collapse of central governance, a deepening humanitarian crisis, and the creation of a fractured state with multiple power centers. Political instability has severely hindered development progress in Yemen and has disrupted essential services across all sectors. The conflict has displaced millions of people, destroyed infrastructure, and diverted resources away from long-term development efforts toward immediate humanitarian needs. Today, Yemen’s food crisis is largely attributed to the ongoing crisis and the impacts of climate change. Since 2015, the country’s economy has been reduced by half, and over 80% of the population now lives below the poverty line, with 17.4 million people in need of urgent food assistance. The conflict has also exacerbated governance issues, leaving the country with weak institutions, a lack of coordination between central and local governments, and fragmented political control, limiting the state’s capacity to implement development policies and provide public services.

The conflict has inflicted significant economic and social costs on the country and its people. From 2015 to 2023, the country experienced a staggering 54% contraction in real GDP per capita (USD 2124 per capita in 2014 to USD 976 per capita in 2023) (See Annex 1). Yemen’s economy was traditionally reliant on oil exports, agriculture, and remittances, but the war has crippled these sectors causing Yemen’s poverty rate to surge with more than 80% of the population) (approximately 24 million people) living below the poverty line (less than USD 2.15 per day, and in need of humanitarian assistance. More than 45% of the population lacks basic sanitation and more than 65% is living in moderate or severe food insecurity.

The country has made limited progress in meeting the Sustainable Development Goals (SDGs), particularly in areas related to poverty reduction, education, gender equality, and health. Life expectancy, literacy rates, and access to education and healthcare are among the lowest in the region. Unemployment is high, especially among the youth (32.65%), who make up a large portion of the population. More than 54% of the employed identify as self-employed, and 29% are employed in agriculture.  Yemen ranks among the worst countries globally in terms of gender inequality (Gender Inequality Index (GII): 0.82; Gender Development Index (GDI): 0.496) and women and girls face significant barriers to accessing education, healthcare, and employment. 63% of female employed are classified as vulnerable employment. The conflict and the impacts of climate change have increased the burden on women, who are often left to manage households and care for children under extremely challenging conditions.

The conflict has resulted in widespread destruction of infrastructure, widespread and worsening displacement (2.5 million people in 2016 rising to 4.5 million in 2023), and the collapse of basic services. Yemen faces critical levels of food insecurity, with nearly half of the population suffering from acute food shortages. Disruption of agricultural production, combined with restricted imports of food and fuel due to blockades and the destruction of markets, has led to famine-like conditions in many parts of the country. Yemen’s healthcare system has been severely degraded by the conflict, with hospitals and clinics destroyed or functioning at limited capacity. This has led to outbreaks of diseases such as cholera and malnutrition, further compounding the country’s humanitarian crisis.

Yemen has one of the highest population growth rates in the world (2.4% annual average), with population growing by 6.7% since 2014 which places immense pressure on already scarce resources, especially water and arable land. Approximately 60% of Yemen’s population resides in rural areas and relies on agriculture for livelihoods. Climate-induced hazards such as droughts, floods, and soil degradation have a disproportionate impact on rural communities, as they depend on natural resources for survival. While Yemen’s urbanization rate is relatively low, migration from rural to urban areas has increased due to climate-induced agricultural failures and conflict. This rural-urban migration is leading to overcrowding in cities like Sana’a and Aden, which lack adequate infrastructure to support the growing population. Overcrowded cities face increased risks of water shortages, food insecurity, and disease outbreaks.

Yemen's economic trajectory will be heavily shaped by future climate conditions and political developments. Under a pessimistic climate scenario marked by higher temperatures and extended droughts, annual GDP is anticipated to decline by an average of 3.9% by 2040 compared to baseline estimates. This downturn is largely attributed to reduced agricultural output, declining fisheries, diminished labor productivity, and the deterioration of health and infrastructure systems. Conversely, an optimistic scenario featuring increased temperatures and precipitation could yield modest benefits, such as improved crop yields, with an average annual GDP growth of 1.5% by 2040, even without adaptation measures. However, this growth would fall short of significantly improving livelihoods.

The extent of Yemen's vulnerability to climate change will depend on its political stability, policy framework, and investments in adaptation measures. Conflict undermines investment planning, restricts market access, and leads to piecemeal climate adaptation efforts within the scope of humanitarian aid. In contrast, a peaceful political environment fosters economic resilience through market diversification and enables targeted investments in climate adaptation. With sustained peace and well-structured adaptation strategies, Yemen’s GDP growth could surpass baseline projections by 2.6 percentage points, enhancing its capacity to address climate challenges effectively.

Climate change is acting as a multiplier to Yemen’s complex and multifaceted development challenges and has the potential to seriously constrain the future of the country.  One recent study found that the effects of climate change are likely to slow economic growth gradually, with a disproportionate effect on the poor with a cumulative $93 billion in gross domestic product (GDP) lost by 2060, by which point GDP would be 10 percent lower than in a No Climate Change scenario. The rate of extreme poverty would be more than 25% higher, as 8.1 million people would be pushed into poverty by 2060. By 2060, 3.8 million more people would suffer from malnutrition which would be responsible for over 121,000 deaths. The study also found that building resilience to the expected climate change would boost economic growth and result in cumulative gains of nearly $360 billion by 2060 and a GDP per capita that would be 27% greater. In addition, building resilience would result in 9.5 million fewer Yemenis in extreme poverty 13 million fewer suffering from malnutrition, and over 400,000 deaths averted from climate change-related and other causes by 2060.

Sectoral Vulnerability to Climate Change

Yemen’s water resources sector is extremely vulnerable to climate change, facing intensified challenges from increased rainfall extremes, changing water availability, and persistent water scarcity. Yemen has one of the lowest per capita water availability rates globally, at just 65 m³, far below the 500 m³ threshold for severe water stress. Climate change amplifies these challenges, affecting water availability for agriculture, household use, sanitation, and ecological sustainability.  Yemen experiences periodic floods, particularly during the rainy season, which often devastate agricultural lands, washing away topsoil, crops, and infrastructure.

Fragmented water governance and lack of enforcement of existing water management policies further exacerbate the problem. Although Yemen has some water management policies, these policies are poorly enforced, and there is little coordination between national and local authorities. As a result, water allocation is often inequitable, and over-extraction of groundwater continues unchecked.

Due to the ongoing conflict, the water sector is severely underfunded, limiting investment in infrastructure, maintenance, and modern irrigation systems that could improve water efficiency. There is limited public or private investment in water infrastructure projects and international aid is often directed towards humanitarian relief rather than long-term development projects, leaving little room for improving water infrastructure. Over 55% of Yemen’s population lacks access to clean drinking water, with more than 45% lacking basic sanitation facilities, affecting both the health and dignity of many households.

Many projects have been addressing the water management sector’s vulnerability to transform water resource management into an inclusive participatory and reconciliatory process. The UNDP Yemen’s Strengthening Institutional and Economic Resilience in Yemen (SIERY) Project was able to provide a total of 32 rainwater tanks in Al-Haymah, Al-Kharijiha and Manakaha. While the Emergency Social Protection Enhancement and COVID-19 Response Project (ESPECRP) has rehabilitated more than 56.6 kilometers of water supply. The Enhancing Resilience through Sustainable Water Resource Management Project focuses on engaging across various communities, including with vulnerable groups, to address water demands, ultimately turning water resources into a driver for social cohesion and stabilization. The project works on enhancing the capacities of local water institutions and user associations to manage water resources in an inclusive, participatory, and transparent way to ensure that the environmental impact of using water resources is reduced to a minimum.

Yemen’s agricultural sector, which provides 30% of employment and is a vital livelihood source for rural communities, is highly vulnerable to climate change. Rising temperatures, erratic precipitation, prolonged droughts, and extreme weather events like floods, are reducing crop yields and altering agricultural seasons. Key staple crops such as wheat, sorghum, and millet are becoming less viable due to changing climate conditions, compounded by land degradation and desertification from overuse and unsustainable practices, especially in Hadramaut and Al Mahra. Yemen's severe water scarcity further strains agriculture, as agriculture uses over 90% of water resources. Groundwater, the primary source of irrigation, is over-extracted, resulting in dropping water tables and drying wells, particularly in Sana’a Basin and Taiz.

Agricultural productivity is also hindered by limited access to modern farming techniques, such as improved irrigation systems and fertilizers. The lack of extension services leaves farmers with minimal technical support, making them more vulnerable to climate impacts. Additionally, the ongoing conflict has displaced millions, destroyed essential infrastructure, and disrupted agricultural supply chains, leading to reduced food production and skyrocketing food prices. Land mines and unexploded ordnance have rendered large areas of farmland unsafe for cultivation.

Yemen’s heavy dependence on food imports, especially staples like wheat and rice, increases its vulnerability to global market fluctuations and supply chain disruptions. Import difficulties, exacerbated by port blockades, currency collapse, and recent global crises, have led to frequent shortages and price hikes, pushing over 80% of Yemen’s population, who live below the poverty line, into deeper food insecurity. Yemen relies heavily on humanitarian aid, but conflict-related access issues often delay food distribution, worsening hunger, and malnutrition, especially among children. Poor sanitation, worsened by climate-driven droughts and floods, heightens the risk of waterborne diseases, compounding malnutrition in vulnerable populations.

The UNDP “Our Food Security Response and Resilience Project” (FSRRP) constructed and improved over 20 kilometers of irrigation canals, and the irrigation of nearly 5,300 hectares of agricultural lands. The project provides support to restore degraded agricultural land, improve water resource management, and promote climate-smart agricultural practices. Interventions are combating climate change and environmental degradation together with enhancing food security in the country, ultimately restoring nearly 4,000 hectares of farmlands. The Joint Programme called “Supporting Resilient Livelihoods, Food Security, and Climate Adaptation in Yemen (ERRY III) Joint Programme” has restored 4.3 kilometers of irrigation channels, facilitating proper water distribution for farming activities. It has also restored 23 hectares of agricultural land across seven areas, focusing on land protection and reclamation.

Sustaining water infrastructure is an integral aim for sustainable agriculture and food security in Yemen. The UNDP, through its Integrated Water Resources Management to Enhance the Resilience of Agriculture and Food Security Project, is enhancing the livelihood resilience of local communities in Yemen by investing in water harvesting infrastructure and rehabilitating damaged community wells, canals, and flood protection areas, among other structures. The project also seeks to alleviate poverty by creating additional income-generating opportunities achieved by initiating small-value activities for agricultural products such as fruits and vegetables, milk products, edible oil seeds, milled rice, flour, tea, coffee, pulses, spices, honey, as well as enhancing equitable market accessibility to local communities. Implemented in four districts of Taiz and Lahj governorates, the project includes active involvement of community members in decision-making and contributes to increased livelihoods related to agriculture, benefitting over 70,000 individuals, including women, Internally Displaced Persons, and smallholder farmers.

Yemen’s healthcare sector is highly vulnerable to the impacts of climate change, with rising temperatures, extreme weather events, and increased prevalence of climate-sensitive diseases exacerbating the already fragile health system. The ongoing conflict and socio-economic challenges further compound these issues, making Yemen one of the most vulnerable countries to climate-related health impacts.

Over 50% of health facilities are non-functional or partially operational due to conflict-related damage, shortages of medical supplies, and displaced healthcare workers. The lack of emergency services and capacity to respond to extreme weather events such as floods, droughts, and heatwaves amplifies the health impacts.

Contaminated water sources increase the prevalence of diseases such as cholera, hepatitis A, and typhoid. Yemen has faced one of the world’s worst cholera outbreaks, with over 2.5 million cases reported since 2016. Flooding worsens poor sanitation by contaminating water supplies, accelerating disease outbreaks in densely populated urban areas and displacement camps while rising temperatures and changing rainfall patterns expand the habitats of disease vectors like mosquitoes, leading to increased cases of malaria and dengue fever, particularly in previously unaffected areas. Waterborne diseases, such as cholera, diarrhea, and dysentery, are exacerbated by water scarcity and poor sanitation. Ongoing droughts and reduced agricultural productivity worsen malnutrition, especially among children, weakening immune systems and increasing vulnerability to diseases like pneumonia, diarrhea, and malaria. Over 2.3 million children under five are severely malnourished, with many suffering from stunted growth and high mortality risks.

Displacement camps housing over 4 million people face overcrowding, poor sanitation, and inadequate healthcare, making them hotspots for infectious disease outbreaks. Vulnerable groups, including women, children, and the elderly, are disproportionately affected by heat waves, malnutrition, and lack of access to healthcare services. Rising temperatures and more frequent heatwaves lead to dehydration, heatstroke, and exacerbation of chronic conditions like cardiovascular and respiratory diseases, particularly in urban areas like Aden and Al Hudaydah.

The key challenges such as a lack of Climate-Responsive Infrastructure means that there is an absence of robust forecasting and early warning systems which limits preparedness for health impacts from extreme weather. Widespread poverty limits affordability of the high healthcare costs which prevents many families from accessing treatment for climate-exacerbated diseases. An overburdened system characterized by poorly equipped health facilities and limited workforce capacity hinders effective responses to rising disease burdens and climate-related disasters.

Strengthening Yemen’s health system, improving water and sanitation infrastructure, and addressing malnutrition are critical for mitigating the impacts of climate change on the health sector. Focused investment in emergency response, early warning systems, and climate-resilient health services is essential for building long-term resilience.

UNDP’s Renewable Energy Improve Access to Health Services and Livelihood Opportunities (HEAL) Project is installing solar energy systems in four hospitals in Yemen, providing sustainable solutions to the electricity shortages that affect the operational ability of the country’s healthcare system. Through the project, solar energy systems have been installed in 39 public service facilities to enhance basic services.

Yemen’s coastal zone and fisheries sector face significant climate change challenges, including sea-level rise, coastal erosion, rising ocean temperatures, extreme weather events, saltwater intrusion and ocean acidification. These impacts threaten marine ecosystems, fisheries, infrastructure and the livelihoods of vulnerable coastal communities, many of whom rely heavily on fishing and related industries.

Sea-level rise and coastal erosion threaten low-lying areas like the Tihama Plain and cities such as Al Hudaydah, Aden, and Al Mukalla which are at high risk of inundation and displacement. Ports, fishing harbors, and coastal infrastructure are vulnerable to damage or submersion, disrupting fisheries, trade, and transport. Coastal erosion threatens natural ecosystems and reduces habitable and arable land, forcing communities to relocate.

Warmer seas due to rising ocean temperatures are causing coral bleaching, particularly around Socotra Island and the Red Sea, reducing marine biodiversity and fisheries productivity. Changes in sea temperatures affect fish migration, reproduction, and stocks of commercially important species like tuna, shrimp, and sardines, leading to reduced income and food insecurity. Degradation of critical ecosystems, including mangroves and seagrass beds, diminishes natural protections against storm surges and habitat loss for marine species.

Acidifying waters impact shellfish and marine species with calcium carbonate structures, such as crabs, lobsters, and shrimp, reducing their populations and further threatening food security and livelihoods. Disruptions in marine food chains reduce overall ecosystem productivity.

Cyclones, storm surges, and heavy rainfall, such as Cyclones Chapala and Megh in 2015, cause widespread destruction to homes, fishing equipment, and infrastructure, displacing communities and disrupting fishing activities. Flooding contaminates freshwater resources, destroys agricultural land, and damages ecosystems such as mangroves and coral reefs.

Coastal communities, among Yemen’s poorest, lack access to basic infrastructure, healthcare, and clean water, compounding their vulnerability to climate impacts. Limited livelihood diversification leaves fishing communities heavily reliant on declining fish stocks, increasing poverty and food insecurity, while the absence of early warning systems and disaster preparedness plans further hinders resilience and recovery from extreme weather events.

Degradation of coastal ecosystems such as mangrove loss due to unsustainable practices and climate change, reduces protection from storm surges and erosion. Declining seagrass beds and coral reefs weaken marine biodiversity and fisheries, while also reducing natural coastal defences.

Hence, climate change threatens the ecosystems that support Yemen’s fisheries and coastal communities, intensifying socio-economic vulnerabilities. Building resilience requires investment in coastal protection, ecosystem restoration, disaster preparedness, and livelihood diversification to protect these critical sectors and communities. UNDP’s Sustainable Fishery Development in the Red Sea and Gulf of Aden (SFISH) Project collaborates with local partners, fishery cooperatives, and the private sector to revive and effectively manage Yemen's fisheries sector. SFISH addresses overexploitation and unsustainable fishing practices, ensuring equitable access to resources and benefits. By fostering resilient marine environments, SFISH supports sustainable livelihoods, especially for vulnerable communities, women, and youth. Through the project, eco-friendly cold chain systems powered by renewable energy are being developed, and fish landing centers will be rehabilitated, including Aden's main fishing port. These efforts address post-harvest losses, ensure fish quality, and adhere to high environmental and social protection standards.

Yemen is highly dependent on international aid to meet the basic needs of its population due to the ongoing conflict.  Climate change-driven events such as floods, droughts, heatwaves, and cyclones have exacerbated Yemen’s ongoing humanitarian crisis, particularly in areas already suffering from conflict-related displacement. Floods displace tens of thousands of people, increasing the pressure on humanitarian organizations to provide shelter, food, clean water, and medical care. Humanitarian efforts in Yemen are often hampered by damaged infrastructure, with access to affected regions made difficult due to washed-out roads and bridges.  The humanitarian sector has struggled to respond to the dual crises of drought and conflict. Drought has worsened food insecurity, leading to a greater need for food aid and emergency water supplies. Humanitarian organizations, such as the World Food Programme (WFP), have had to significantly increase food aid distribution during drought periods. In 2020, over 12 million Yemenis were dependent on food aid, many of whom were in drought-affected regions like Sa’dah, Amran, and Hodeidah. Humanitarian efforts to provide clean water have been critical during droughts. Organizations such as Oxfam and the International Committee of the Red Cross (ICRC) have installed water points, provided water trucking services, and rehabilitated wells in rural and urban areas affected by water shortages.Top of Form

Humanitarian organizations, including the International Committee of the Red Cross (ICRC) and United Nations Development Programme (UNDP), have provided emergency aid in the form of shelter, food, and clean water to displaced coastal populations who often live in overcrowded and under-resourced camps which often lack adequate sanitation, access to clean water, and healthcare, increasing the vulnerability of displaced populations to disease outbreaks and malnutrition. However, ongoing conflict and infrastructural damage make it difficult to reach all affected communities. Following Cyclone Luban (2018), humanitarian organizations such as the International Red Cross and the United Nations High Commissioner for Refugees (UNHCR) provided emergency shelters, food, and clean water to the displaced populations in Al Mahra and Hadramaut. Cyclones have exacerbated food and water shortages, particularly in remote areas like Socotra and Al Mahra, where storm surges destroyed water wells and agricultural land. Humanitarian organizations have had to rely on water trucking and food aid to provide relief to affected populations.

In Aden, humanitarian organizations like the International Committee of the Red Cross (ICRC) have provided emergency water supplies and cooling shelters during heatwaves, but these services remain limited. Humanitarian agencies are often forced to truck in water to areas where local water sources have dried up. The cost of emergency water trucking during heatwaves has exceeded $5 million annually in some of the hardest-hit regions.

The United Nations and other humanitarian organizations provide critical assistance (net ODA of USD 3.3 Billion per year since 2014), including food, healthcare, and shelter, to millions of Yemenis. However, funding shortages, access restrictions due to the conflict, and logistical challenges hinder the delivery of aid to the most vulnerable populations. While humanitarian assistance is crucial for Yemen’s immediate survival, long-term development programs have been limited due to the conflict. Efforts to rebuild infrastructure, restore livelihoods, and strengthen institutions have been constrained by insecurity and political instability. However, international development organizations, including the World Bank, UNDP, and FAO, continue to engage in efforts to support recovery and resilience-building in Yemen.

Sectoral Adaptation priorities

Despite the significant challenges posed by Yemen’s ongoing conflict, economic instability, and institutional weaknesses, several steps have been taken to support adaptation planning to date.  Yemen’s government with the help of development partners has developed relevant policy documents which set out the adaptation priorities for the main climate change-impacted sectors. The key documents are Yemen’s National Adaptation Programme of Action (NAPA, 2009), Intended Nationally Determined Contribution (INDC, 2015), National Water Sector Strategy and Investment Program (NWSSIP), and Yemen’s Third National Communication (TNC, 2018) to the UNFCCC. In addition, the draft Yemen Country Finance Country Programme lists a number of adaptation measures that it is prioritizing for GCF and other finance, and Yemen’s Technology Needs Assessment (TNA) report outlines CCA technologies by sector.

The national and sub-national adaptation priorities for the main sectors impacted by climate change (water resources, agriculture, health, coastal zone) are as follows:

Water resource management is at the heart of Yemen’s climate change adaptation strategy. The national and sub-national priorities identified by government agencies, development partners, and other stakeholders aim to address chronic water scarcity, improve agricultural productivity, and build resilience to climate-induced droughts and floods. Yemen’s stated water sector adaptation priorities focus on Sustainable Water Management, Water Infrastructure Development, and Climate-Resilient Agricultural Practices. The expected outcomes of these interventions include enhanced water security, poverty reduction, improved health outcomes, and strengthened livelihoods for millions of Yemenis. However, successful implementation will depend on political stability, adequate financing, and effective governance.

Adapting Yemen’s agricultural sector to climate change is essential for improving food security, reducing poverty, and enhancing the resilience of rural livelihoods. National and sub-national priorities focus on promoting climate-smart agriculture, sustainable land and water management, and building the capacity of farmers to cope with climate risks. The priority adaptation interventions aim to rehabilitate degraded land, improve water use efficiency, and increase agricultural productivity. Yemen’s climate adaptation priorities for agriculture focus on building resilience to water scarcity, improving agricultural productivity, and promoting sustainable land management practices. The expected outcomes include enhanced food security, poverty reduction, and environmental sustainability, benefiting millions of rural households in Yemen.

Yemen’s health sector faces immense challenges that are exacerbated by climate change, but through targeted adaptation interventions, the country can strengthen its healthcare system and protect vulnerable communities from climate-related health risks. National and sub-national priorities focus on building climate-resilient healthcare infrastructure, strengthening disease surveillance and early warning systems, and improving emergency preparedness, which aims to save lives, reduce poverty, and enhance Yemen’s overall resilience to the health impacts of climate change.

Adapting Yemen’s coastal zone and fisheries sector to climate change is crucial for protecting coastal ecosystems, ensuring the sustainability of fish stocks, and safeguarding the livelihoods of coastal communities. National and sub-national priorities focus on restoring marine ecosystems, promoting sustainable fisheries management, and building climate-resilient infrastructure. These interventions, supported by government agencies, international donors, NGOs, and academic institutions, aim to reduce coastal vulnerability, enhance livelihoods, and improve community resilience to climate-related hazards. The expected outcomes include improved ecosystem health, poverty reduction, income generation, and disaster preparedness, benefiting millions of people across Yemen’s coastal regions.

In order to advance adaptation planning, the government of Yemen designated Ministry of Water and Environment as the lead in NAP coordination, adaptation policy development and The Environmental Protection Authority (EPA) the designated focal point for climate change adaptation planning and coordination, is responsible for monitoring and implementing environmental adaptation measures and overseeing climate data management on the governorate level. The National Climate Change Committee (NCCC) was officially launched in 2009 and updated in 2023, with responsibility to oversee the Climate Change Coordination Mechanism (CCCM), which consists of three levels: (i) The high level Climate Change Committee (referred to as the Council or Board) chaired by the Minister of Planning and International Cooperation or by the Minister of Water and Environment; (ii) The Technical Committee  (TCCC) chaired by the EPA Chairman; and, (iii) the Sub-technical Committees, one of which is specialized on Climate Change Adaptation and DRR and DRM. Other Sub-technical Committees support low GHG emission development. The Sub-technical Committees are working groups consisting of technical professionals from different Governmental and Non-Governmental Organizations and entities. The Sub-technical Committees are intended to guide the Technical Committee and the Climate Change Unit on technical climate change adaptation and mitigation items and issues. The Climate Change Unit serves as the Executive Secretariat to the CCCM and is the UNFCCC Focal Point. While the structure of the CCCM has been endorsed by the Government, only the CCU has been established.

The Government of Yemen leverages partnerships with international organisations such as UNDP, FAO and bilateral governments to support adaptation planning, capacity building, and project implementation (Annex 2 provides a list of adaptation priorities that have been completed from 2010 to date).  Progress in adaptation planning has been achieved mainly through donor-funded development partner-implemented projects. Under these initiatives, training programs have been implemented for government officials and local stakeholders who have been trained in climate risk assessments, early warning systems, and adaptive agriculture practices. Data Collection and analysis have been advanced through international partnerships (e.g., WMO, FAO) which have improved access to satellite-based climate data and made efforts to modernize meteorological and hydrological networks to improve climate monitoring and forecasting. Climate finance has mainly been through international and bilateral funding which have provided financial and technical support for adaptation projects. GCF Readiness Support to date has focused on preparing Yemen’s institutions to access climate finance and develop a pipeline of adaptation projects.  Progress in Monitoring and Reporting is done through Yemen’s National Communications (TNC was submitted in 2018 and FNC currently under preparation) which detail its adaptation progress, climate vulnerabilities, and proposed measures as well as project-based M&E which is done through donor-funded projects which incorporate localized monitoring systems to track adaptation outcomes and gather lessons learned.

While Yemen has made progress in adaptation planning through strategic frameworks, institutional developments, and donor-supported projects, scaling up these efforts requires strengthening governance, building technical capacity, and ensuring sustainable financing. The National Adaptation Plan (NAP) process to be established by this proposed project will provide a critical opportunity to address these gaps, enhance coordination, and align Yemen’s adaptation priorities with long-term development goals.

  - Institutional and Policy Framework

i) Policy Framework

Yemen’s policy and legislative framework for climate change adaptation is guided by its international commitments, national policies, sectoral adaptation strategies, and key institutional mechanisms. This section discusses Yemen’s existing national and sectoral policies, plans, and legislative measures for climate change adaptation, focusing on the legal instruments, strategies, institutional frameworks, and key areas of focus for adaptation based on a review of existing policy documents,,,.

International Commitments

Yemen is a party to several international agreements and conventions that guide its national climate change adaptation efforts. These international commitments shape the country’s legal and policy framework for addressing climate vulnerabilities.

- United Nations Framework Convention on Climate Change (UNFCCC). Yemen ratified the UNFCCC in 1996, marking its formal engagement in global efforts to address climate change. As part of its commitments under the UNFCCC, Yemen has submitted National Communications (NCs) and an Intended Nationally Determined Contribution (INDC), outlining the country’s climate challenges, adaptation needs, and mitigation strategies.

- Yemen’s Third National Communication (TNC) to the UNFCCC (2018) provides a comprehensive assessment of the country’s vulnerability to climate change and identifies priority sectors for adaptation. The TNC highlights agriculture, water resources, and coastal zones as key areas for adaptation action.

- Yemen signed the Paris Agreement in 2016 but has not yet ratified the Paris Agreement. Yemen’s INDC emphasizes adaptation as a national priority, given the country’s low contribution to global greenhouse gas emissions and its high vulnerability to climate impacts. The INDC highlights the need for international support, including climate finance and capacity building, to implement adaptation measures effectively.

- Yemen is a signatory to the United Nations Convention to Combat Desertification (UNCCD), which provides a framework for combating desertification and promoting sustainable land management. Under the UNCCD, Yemen has developed national strategies to address land degradation and enhance ecosystem resilience, which aligns with broader climate adaptation goals.

- Yemen is also a party to the Convention on Biological Diversity (CBD), which emphasizes the protection of biodiversity and ecosystems, essential for building resilience to climate change. The National Biodiversity Strategy and Action Plan (NBSAP) aligns with Yemen’s climate adaptation goals by promoting ecosystem-based adaptation approaches.

National Policies and Strategies for Climate Change Adaptation

At the national level, Yemen has developed several policies, strategies, and action plans to guide its climate change adaptation efforts. These documents provide a framework for integrating climate change adaptation into key sectors such as water, agriculture, health, and coastal management.

- Climate Finance Country Programme (CFCP):  Yemen’s CFCP is a programme endorsed by the Government of Yemen and adopted by GCF in 2024. The programme aims to increase the climate finance mobilization to address the most urgent and crucial mitigation and adaptation priorities, enable the institutional, policy, and regulatory framework of climate change, and support the private sector engagement in the climate investment as well as GCF Direct Access (DAE) modalities. The CFCP through its eight projects focuses on four sectors:

- Water Sector: Improving water access by using alternative technologies, such as seawater desalination, water reuse, rainwater harvesting, etc.

- Agriculture: Supporting the agriculture-based livelihood by promoting innovative and smart agriculture approaches

- Coastal Zones:  Enhancing the resilient of infrastructure and livelihoods in the coastal cities

- Climate Information Services: Improving the climate information management and early warning systems

- Energy:  Promoting Off-Grid Renewable Energy Systems for adaptation and mitigation purposes as well as supporting the decarbonization pathway of the industry sector

- Technology Needs Assessment and Action Plan (TNA & TAP): Yemen TNA identified the most prioritized technologies for adaptation and mitigation in the sectors of Water, Agriculture, Energy, and Transport. TAP produced the actions needed for discussing the identified technologies into Yemen local market.

- National Adaptation Programme of Action (NAPA) – 2009. Yemen’s National Adaptation Programme of Action (NAPA), submitted in 2009, was one of the first comprehensive frameworks for addressing the country’s urgent and immediate adaptation needs. The NAPA identifies key vulnerabilities and prioritizes adaptation actions in areas such as:

  - Water resources management: Improving water storage and rainwater harvesting systems.

  - Agriculture: Introducing climate-resilient crops and improving irrigation systems.

  - Coastal zone management: Protecting coastal infrastructure and mitigating the impacts of sea-level rise.

  - Disaster risk management: Enhancing early warning systems and building local capacity to respond to climate-related disasters.

- Intended Nationally Determined Contribution (INDC) – 2015. Yemen’s INDC), submitted in 2015 as part of its signature to the Paris Agreement, emphasizes adaptation as a top national priority. The INDC highlights several key sectors where climate adaptation is critical:  water resources, agriculture, health, and coastal protection.

- Yemen National Environmental Action Plan (NEAP) – 2005. The National Environmental Action Plan (NEAP), developed in 2005, outlines Yemen’s long-term environmental management goals, including adaptation to climate change. NEAP focuses on the sustainable use of natural resources, improving land management, protecting water resources, and reducing vulnerability to environmental disasters.

- National Water Sector Strategy and Investment Program (NWSSIP) – 2004. The NWSSIP addresses the critical issue of water scarcity, which is worsened by climate change. The strategy focuses on improving water resource management, enhancing irrigation efficiency, and promoting the sustainable use of groundwater. NWSSIP is essential for addressing Yemen’s water challenges in the context of increasing droughts and water stress, which are exacerbated by climate change. The strategy aligns with broader adaptation efforts aimed at ensuring water security.

- National Water Sector Strategy and Investment Program (NWSSIP) –2008-2015: This is Yemen’s overarching water management strategy, aimed at improving water governance, ensuring sustainable water use, and addressing water scarcity through improved infrastructure and water resource management.

- National Biodiversity Strategy and Action Plan (NBSAP) – 2015. Yemen’s NBSAP, developed under the Convention on Biological Diversity, promotes the conservation of biodiversity and the sustainable use of ecosystems as part of the country’s adaptation strategy. The NBSAP emphasizes ecosystem-based adaptation approaches such as protecting mangroves and coral reefs in coastal areas, restoring degraded ecosystems to enhance natural resilience to climate impacts, and promoting sustainable agricultural practices to protect biodiversity and enhance food security.

Legislative Measures for Climate Change Adaptation

Yemen’s legal framework for climate adaptation is relatively underdeveloped due to the country’s political instability, ongoing conflict, and limited institutional capacity. However, several laws and decrees provide a basis for environmental protection and adaptation efforts.

- Environmental Protection Law (1995). The Environmental Protection Law of 1995 is Yemen’s primary legislation for environmental management. The law provides a legal framework for the protection of natural resources, prevention of environmental degradation, and promotion of sustainable development. While the law does not specifically address climate change, it offers a foundation for implementing adaptation measures. Key provisions include:

  - Regulating the use of water resources and promoting sustainable water management.

  - Encouraging reforestation and protection of forested areas to combat desertification.

  - Establishing environmental impact assessment (EIA) procedures for development projects.

- Water Law (2002). The Water Law of 2002 establishes a legal framework for the management and regulation of water resources in Yemen. The law is crucial for addressing water scarcity, a key climate adaptation issue in Yemen. Provisions of the Water Law include:

  - Regulating the use of groundwater to prevent over-extraction.

  - Promoting water conservation measures in agriculture, industry, and domestic use.

  - Encouraging the development of alternative water sources, such as desalination and rainwater harvesting.

- National Disaster Management Law (2012). The National Disaster Management Law provides a legal basis for disaster risk management in Yemen. The law emphasizes the importance of preparedness, response, and recovery in the face of natural disasters, including those exacerbated by climate change. Key provisions of the law include:

  - Establishing a national disaster management authority responsible for coordinating disaster risk reduction (DRR) efforts.

  - Developing early warning systems for floods, droughts, and other climate-induced disasters.

  - Promoting local-level disaster preparedness and resilience-building initiatives.

Sectoral Policy and Strategy Gap Analysis and alignment with NAP project

An analysis of the key sectoral policies and strategies for water, agriculture, health, and coastal zones is summarised in Table 1.  It includes a summary of each policy/strategy, identified CCA gaps, and existing alignment with NAP.  It also includes the complementarities and enhancements that the NAP will provide.

Table 1: Sectoral Policies/Strategies, summary, alignment with NAP and proposed CC mainstreaming

| Policy/strategy | Policy summary | Alignment of NAP |
| --- | --- | --- |
| National Water Sector Strategy and Investment Program (NWSSIP) – 2004, Updated 2008-2015: | This is Yemen’s overarching water management strategy, aimed at improving water governance, ensuring sustainable water use, and addressing water scarcity through improved infrastructure and water resource management. It provides a framework for sustainable water resource management, investment prioritization, and institutional reforms. The program emphasizes decentralization, stakeholder participation, and integrated water resource management (IWRM). Its key objectives are: Develop mechanisms for the equitable distribution of water resources; Prevent over-extraction and ensure groundwater conservation; Strengthen water governance by enhancing the role of regional and local water management agencies; Mobilize resources for infrastructure development, such as water supply systems, irrigation modernization, and wastewater treatment; Promote cross-sectoral collaboration among agriculture, urban development, and environmental sectors to address competing water demands; Enhance access to safe drinking water and sanitation services, particularly in rural and underserved areas. CCA Gaps: No systematic identification of climate change impacts on water resources or adaptation measures; Lacks specific climate adaptation measures, such as infrastructure resilience to extreme weather events; No integration of climate scenarios in cross-sectoral planning (e.g., agricultural adaptation to changing rainfall patterns); Limited emphasis on climate-related data collection, such as precipitation patterns and evapotranspiration rates; Does not include climate change capacity building for water management professionals or local communities; No explicit inclusion of climate change adaptation in water governance policies or basin-level planning; Does not prioritize investments in climate-resilient water infrastructure (e.g., flood defences or drought-resistant technologies). | Alignment with NAP NWSSIP emphasizes the importance of IWRM for sustainable water use. The NAP process can build on existing basin committees and WUAs to identify and integrate climate adaptation measures. NWSSIP’s focus on decentralization aligns with the NAP project’s goal of engaging local stakeholders in adaptation planning. The NWSSIP's recognition of interlinkages between water and agriculture provides a basis for the NAP’s broader integration across priority sectors. The NWSSIP prioritizes improving water access in rural areas, which aligns with the NAP project’s emphasis on supporting vulnerable populations. To further align with NAP the NWSSIP II can be enhanced by: i) including water-sector climate risks based on climate risk and vulnerability assessments to be done (Activity 3.2.2.1). ii) Align NWSSIP investments with the NAP project’s goal of building resilient water supply systems and irrigation networks; iii) Integrate climate data collection and modeling into NWSSIP’s existing water resource monitoring systems, linked to the NAP Portal; iv) Expand NWSSIP’s training programs to include climate risk management and adaptation planning for water sector professionals using the NAP training modules to be developed; v) Update water governance policies under NWSSIP to explicitly include climate adaptation strategies and ensure coherence with the NAP framework vi) Align NWSSIP’s investment priorities with the NAP project’s adaptation funding strategy, including accessing Green Climate Fund (GCF) resources. |
| Water Law (2002) | The Water Law of Yemen (2002) was enacted to provide a regulatory framework for water resource management, conservation, and sustainable use. It focuses on addressing Yemen’s critical water scarcity and promoting equitable access to water resources. It’s key objectives are to: Establish the National Water Resources Authority (NWRA) as the central body responsible for water management and policy implementation; Prevent depletion of groundwater and surface water resources; Promote efficient water use through regulation and conservation; Implement permits for drilling wells and extracting groundwater; Establish water allocation rules for agricultural, domestic, and industrial uses; Mandate the creation of local water user associations (WUAs) and basin-level committees; Prevent water pollution and protect water quality standards; Encourage stakeholder involvement in water management, particularly through WUAs. CCA Gaps: Does not include provisions for addressing climate-induced risks such as droughts, floods, and sea-level rise; Lacks climate adaptation measures such as resilient water infrastructure or drought management strategies; Does not integrate water management with climate-resilient agriculture or public health planning; Does not mandate collection of climate-specific data such as precipitation patterns or temperature trends; Does not include training or awareness-building related to climate change impacts and adaptive water resource management; NWRA’s role does not include climate change adaptation, limiting its capacity to address emerging climate risks; No provisions for adaptive governance to respond to climate variability and extreme weather events; Does not include mechanisms to increase public awareness of climate risks or involve communities in adaptive water management. | Alignment with NAP The Water Law’s emphasis on sustainable water resource management aligns with the NAP project’s objective to enhance water resilience. It promotes local water governance through WUAs and basin committees, which can be leveraged to integrate climate adaptation at the community level. NWRA’s role as the central regulatory body aligns with the NAP project’s need for institutional coordination in water sector adaptation. To further align with NAP the Water Law can be enhanced to: i) explicitly address climate risks such as reduced water availability, increased variability in precipitation, and rising sea levels impacting coastal aquifers; ii) Update NWRA’s mandate to include responsibilities for climate risk management and adaptation planning; iii) Incorporate linkages between water management and climate-resilient agriculture, health, and coastal zone planning; iv) Mandate the collection and analysis of climate-specific data, including rainfall patterns, drought indicators, and flood risks, to inform adaptive water management; v) Include provisions for infrastructure investments such as flood defenses, water storage systems, and drought-resistant technologies; vi) Expand capacity-building initiatives under the law to include climate risk management for water sector professionals and local communities; vii) Incorporate mechanisms to increase awareness of climate risks and adaptation strategies among water users and stakeholders. |
| National Agriculture and Fisheries Strategy and Investment Plan NAFSIP – 2024-2030 | The NAFSIP is Yemen’s roadmap for revitalizing the agriculture and fisheries sectors as engines of economic recovery and sustainable development, emphasizing food security, rural livelihoods, and sustainable natural resource management. It’s main objectives are: to enhance productivity and efficiency in agriculture and fisheries to ensure food security and increase exports. It’s key objectives are to: Modernize farming and fishing practices to improve yields and reduce post-harvest losses. Promote sustainable land use, water management, and marine resource conservation to prevent overexploitation. Create employment opportunities in rural areas, particularly for women and youth, by supporting smallholder farmers and fishers Build the capacity of agriculture and fisheries-related institutions to implement policies and regulations effectively; Foster partnerships with private investors to improve value chains, infrastructure, and market access; Strengthen the resilience of agriculture and fisheries to environmental shocks and economic disruptions. CCA Gaps: Lacks comprehensive identification of climate-specific risks like changing precipitation patterns, sea-level rise, and temperature increases; Does not explicitly integrate climate adaptation strategies, such as drought-resistant crops or flood-resilient aquaculture systems; Limited cross-sectoral integration of climate-resilient approaches with water, coastal zones, and health sectors; Does not mandate climate-specific data collection, such as seasonal variability impacts or extreme weather patterns; Lacks targeted training on climate adaptation techniques, such as climate-smart agriculture or sustainable fisheries under changing climatic conditions; Does not include adaptive governance mechanisms to address dynamic climate risks; No clear focus on climate-resilient infrastructure (e.g., irrigation systems, flood defenses) or access to climate finance mechanisms. | The NAFSIP emphasizes the importance of sustainable land, water, and marine resource management. The NAP process can enhance NAFSIP’s objectives by incorporating climate adaptation strategies for resource conservation. The NAP project’s focus on resilience aligns with NAFSIP’s objectives to mitigate environmental shocks in agriculture and fisheries This can be achieved by the integration of NAP’s climate risk assessments to strengthen resilience-building efforts under NAFSIP. The NAP process can build on NAFSIP’s emphasis on institutional capacity by introducing tools and frameworks for climate adaptation planning and implementation. Both NAFSIP and NAP prioritize engaging the private sector. NAP project will provide opportunity to mobilize blended investments in climate-resilient agriculture and fisheries through the finance strategy that will be developed. To further align with NAP the NAFSIP can be enhanced to: i) Incorporate the NAP project’s climate risk assessments to identify region-specific vulnerabilities in agriculture and fisheries; ii) Include climate-smart agriculture (e.g., drought-resistant crops, efficient irrigation systems) and fisheries adaptation strategies (e.g., resilient aquaculture practices) in NAFSIP; iii) Establish mechanisms for collecting and analyzing climate-specific data on agriculture and fisheries, linked to the NAP Portal; iv) Align NAFSIP’s actions with NAP project priorities in water and coastal zone management to address overlapping climate challenges; v) Access funding through the NAP project’s adaptation finance strategy to support investments in climate-resilient infrastructure and practices; vi) Expand NAFSIP’s training programs to include climate adaptation techniques, such as agroforestry, soil conservation, and sustainable marine practices. |
| National Health Strategy (2011-2025). It is being implemented through a variety of initiatives, including: National Quality of Health Care Strategy (2025–); Country Cooperation Strategy (CCS) (2024–2025); Emergency Human Capital Project (EHCP). | National Health Strategy (2011–2025): Aims to achieve universal health coverage through improved access to quality healthcare, particularly for marginalized and vulnerable populations. Focuses on maternal and child health, communicable disease control, health financing, and system strengthening. National Quality of Health Care Strategy (2025–): Emphasizes the improvement of healthcare service delivery through adherence to quality standards. Promotes capacity building for healthcare workers, patient safety protocols, and accountability mechanisms. Country Cooperation Strategy (CCS) (2024–2025): Developed in collaboration with the World Health Organization (WHO), it outlines Yemen’s priorities for health system development. Focus areas include strengthening governance, disease prevention, and addressing health inequities. Emergency Human Capital Project (EHCP): Aims to support Yemen’s health, nutrition, and social safety nets in response to the country’s ongoing crises. Provides emergency healthcare services, rehabilitation of health facilities, and nutritional support for children and pregnant women. CCA Gaps: No assessment of climate-related health risks such as heat stress, vector-borne diseases, and extreme weather events; Lacks strategies for climate-resilient health infrastructure or service delivery; Does not incorporate climate-sensitive disease trends (e.g., malaria, cholera, dengue fever); Lacks integration of climate-induced emergencies like heatwaves, floods, and droughts into preparedness planning; Does not address climate-related health risks or adaptation measures in awareness and training programs; Limited integration with climate adaptation efforts in other sectors such as agriculture, water, and coastal zone management; Does not include governance mechanisms for addressing health impacts of climate variability and change; Does not include provisions for mobilizing climate finance to address climate-sensitive health challenges. | NHS emphasizes equity and accessibility, especially for vulnerable populations in climate-affected regions which aligns with the NAP. It focuses on communicable disease control which also aligns with the NAP project’s objective to address climate-sensitive diseases. NAP project will further support these focuses areas through the climate risk and vulnerability assessments it will produce which will identify climate-induced health risk and vulnerability. The NHS prioritization of health awareness campaigns provides an entry point for integrating climate-related health risks and adaptation measures. To further align with NAP the NHS can be enhanced to: i) Include climate-related health challenges such as heat stress, vector-borne diseases, and waterborne illnesses exacerbated by climate change; ii) Identify priority investment requirements in climate-resilient health facilities capable of withstanding extreme weather events; iii) Incorporate some climate-sensitive diseases into the NHS’s surveillance programs, supported by climate risk assessments from the NAP process; iv) Include climate-induced disasters like floods and heatwaves in health sector emergency response plans; v) Collaborate with NAP’s water and agriculture components to address health risks linked to water scarcity, malnutrition, and food insecurity; vi) Develop public health campaigns addressing climate-related risks, such as hydration during heatwaves and prevention of waterborne diseases during floods; vii) Utilize the NAP project’s adaptation financing strategy to access resources for addressing climate-sensitive health priorities. |
| National Agriculture and Fisheries Strategy and Investment Plan NAFSIP – 2024-2030 | The National Agriculture and Fisheries Strategy and Investment Plan (NAFSIP) 2024–2030 aims to revitalize Yemen’s agriculture and fisheries sectors as engines of economic growth and food security. The plan identifies the coastal and fisheries sector as a priority for sustainable development, with a focus on resource conservation, market access, and resilience building. It’s key objectives are to: Implement measures to prevent overfishing and protect marine biodiversity; Enhance marine resource monitoring and enforcement of fishing regulations; Invest in fishing ports, storage facilities, and fish processing plants to reduce post-harvest losses and improve value chains; Support small-scale fishers by providing access to credit, technology, and training; Increase employment opportunities in coastal communities, particularly for women and youth; Promotes adaptive marine practices to mitigate environmental and economic shocks, including pollution and resource depletion; Strengthen domestic and international market access for fisheries products by improving quality standards and supply chains. CCA Gaps: Lacks a comprehensive assessment of climate-induced risks, such as ocean warming, sea-level rise, and changing fish migration patterns; Does not explicitly include climate-resilient aquaculture or measures to protect coastal communities from climate-induced hazards like storms or flooding; Does not mandate the collection of climate-related data such as sea temperature changes, salinity levels, and extreme weather patterns; Lacks provisions for climate-resilient infrastructure to withstand extreme weather events and sea-level rise; Does not include targeted training on climate adaptation, such as early warning systems for storms or climate-resilient fishing techniques; Does not incorporate climate adaptation into fisheries governance or promote integrated coastal zone management (ICZM); Does not emphasize community-based climate adaptation planning or inclusion of vulnerable groups in coastal zones; Does not align investments with climate finance opportunities or prioritize funding for climate adaptation in coastal zones. | NAFSIP’s recognition of coastal zones as critical for fisheries aligns with the NAP project’s focus on integrating coastal resilience into national planning. Its focus on fisheries management can be enhanced by the NAP project’s emphasis on climate-resilient natural resource management. The NAFSIP also aligns with the NAP project priority of improving livelihoods for coastal communities, through the integration climate adaptation strategies. The NAP project can enhance the NAFSIP by promoting climate-resilient infrastructure, such as storm-resistant ports and storage facilities. To further align with NAP the NAFSIP can be enhanced to: i) include assessments of climate risks such as increased frequency of coastal storms; ii) Align NAFSIP’s infrastructure investments with NAP objectives by incorporating climate resilience measures such as flood defenses and elevated port structures; iii) Promote practices such as sustainable aquaculture and early warning systems for coastal communities to address climate impacts; iv) Mandate the collection of climate-specific data on coastal and marine environments, linked to the NAP Portal for data sharing and decision-making; v) Introduce ICZM principles into NAFSIP to address the interconnected impacts of climate change on fisheries, agriculture, and coastal ecosystems; vi) Access funding through the climate finance strategy to be developed by the NAP project to support climate adaptation measures, such as community-based resilience programs and coastal protection infrastructure; vii) Expand training programs to include climate adaptation for fishers, coastal planners, and local authorities. |

# Strategy

The project goal is to make Yemen more resilient to the impacts of climate change through robust conflict-sensitive national and sub-national adaptation planning, improved institutional capacity, and the implementation of gender-responsive, inclusive, and climate-resilient development policies.

Goal Statement:

IF Yemen establishes a National Adaptation Process and strengthens its technical, financial, and institutional capacities to integrate climate change adaptation into national and sectoral plans and budgets while adopting conflict-sensitive tools and analysis,

THEN key government sectors will have the ability to design, operationalize, finance, and monitor adaptation actions effectively, ensuring that climate adaptation measures are institutionalized, sustainable, and responsive to Yemen’s socio-political and environmental context,

BECAUSE authorities and stakeholders will have the necessary systems, technical expertise, inter-ministerial coordination, and financing mechanisms to systematically design, finance, implement, monitor, and evaluate strategic, climate risk-informed, gender-responsive adaptation actions that enhance the physical and socio-economic resilience of vulnerable communities to climate change impacts.

As outlined in the goal statement, the project will support climate change adaptation planning in Yemen by developing the technical, financial, and institutional capacities for key government sectors to integrate climate change adaptation into their sectoral plans and budgets at all levels. These elements of the paradigm shifts are further described below.

The project will enable key climate-vulnerable sectors to systematically design, operationalize, finance, and monitor climate risk-informed, strategic, and operational climate change adaptation actions, ultimately leading

The project seeks to address the following barriers:

| Barrier | Primary output to address and overcome barriers |
| --- | --- |
| Barrier 1: Limited systematic inter-ministerial coordination for adaptation planning | Output 3.1.1. National, sub-national and/or sectoral adaptation plans developed or updated Output 3.1.3. Inter and Intra-institutional coordination & decision-making mechanisms established or strengthened Output 3.1.4. Stakeholder engagement frameworks, agreements and awareness raising conducted or strengthened. |
| Barrier 2: Limited access to climate risk and vulnerability data and technical capacity to integrate CRV data and information, into identification and appraisal of CCA interventions | Output 3.2.2. Studies on climate vulnerability, & identification of adaptation solutions conducted (& used) for strengthening adaptation investment |
| Barrier 3: Lack of conflict analysis and an approach to address CCA challenges in crisis contexts | Output 3.1.1. National, sub-national and/or sectoral adaptation plans developed or updated Output 3.2.2. Studies on climate vulnerability, & identification of adaptation solutions conducted (& used) for strengthening adaptation investment |
| Barrier 4: Lack of a Monitoring and Evaluation (M&E) System for Climate Adaptation | Output 3.2.1. Adaptation impact monitoring, evaluation & learning systems established or strengthened for strategic planning and investment |
| Barrier 5 - Limited availability of adaptation finance and lack of a financing strategy for developing bankable CCA projects | Output 3.4.2 Number of concept notes and/or funding proposals developed for adaptation priority actions 3.4.3 National systems developed for tracking adaptation national and international finance flows |

Theory of Change diagram of the project is:

# Results and Partnerships

Expected Results:

The project goal is to enable key climate-vulnerable sectors in Yemen to build a foundation to systematically coordinate, design, operationalize, finance, and monitor climate risk-informed, strategic, climate change adaptation actions while taking conflict-related risks and impacts into account, ultimately leading to increased community resilience in terms of physical infrastructure and socio-economic factors in response to climate change challenges.

The objective of this project is to enhance Yemen's climate change adaptation capacity and integrate climate change adaptation into sectoral plans by strengthening coordination, technical expertise, financial mechanisms, and institutional capacities and integrating conflict sensitivity into adaptation planning and to develop the NAP document. The project will establish coordination, financing, M&E, and knowledge-sharing mechanisms and systems. It will develop downscaled climate risk and vulnerability assessment data, conduct conflict analysis, and carry out stakeholder mapping. Additionally, the project will mainstream and integrate climate change adaptation into sectoral plans and budgets of four highly vulnerable sectors (water, agriculture, coastal zones, and health, as well as cross-sectoral humanitarian response and recovery efforts), and integrate sectoral NAPs into the overall NAP document. These efforts will lay the foundation for effective climate adaptation solutions supported by increased adaptation finance.

This proposal aligns with Outcome 3 of the GCF readiness for the National Adaptation Plan (NAP) and focuses on multiple key results under various Output areas.

The project goal will be met through following outcomes;

- Outcome 3.1: Adaptation planning governance and institutional coordination strengthened.

The projects Outputs 3.1.1, 3.1.3, and 3.1.4 will all contribute to Outcome 3.1 by addressing Barrier 1: Limited systematic inter-ministerial coordination for adaptation planning and Barrier 3: Lack of conflict analysis and an approach to address CCA challenges in crisis contexts.  Under Activity 3.1.1.1, the National Adaptation Plan and costed National Implementation Plan will be developed and validated, based on consolidated costed sectoral NAPs which will be developed under Activity 3.1.1.3.  The sectoral NAPs will be based on utilizing approaches and guidance for mainstreaming gender and social inclusion into adaptation planning as well as an approach and guidance for mainstreaming adaptation into humanitarian response and recovery.  Activity 3.1.1.3d will prepare a conflict-sensitive approach paper for Yemen’s adaptation planning which includes stakeholder mapping and explaining how conflict and crisis and peacebuilding approaches need a more flexible approach in Yemen’s NAP.

The project’s Output 3.1.3 a fully capacitated coordination mechanism for the NAP process in Yemen established at the national level under the Technical Climate Coordination Committee (TCCC) (Activity 3.1.3.1). Under Activity 3.1.3.1. the project will also establish National Thematic Clusters (NTCs) under the TCCC for up to four priority sectors: i) agriculture and ii) water, iii) coastal zones, iv) health; and v) a cross-sectoral humanitarian sub-cluster, and mandates of the NTCs will be developed.  Capacity development will be implemented for members of the TCC and NTC based on a Capacity Development Plan for NAP to be developed by the project under Output 3.1.4.

Under the project’s Output 3.1.4 centralized awareness-raising and knowledge-sharing mechanisms will be established, and a public awareness-raising campaign developed and implemented for government officials, NGOs, CSOs, the private sector, and local communities; a Capacity Development Strategy and Plan will be developed and implemented based on a detailed institutional capacity assessment and gap analysis.

In delivering Output 3.1, the project will need to ensure that all relevant government and non-government agencies are fully engaged and continue to be committed to cooperating on climate change adaptation planning.  The project will therefore need to overcome Risk 1 - Lack of political will and stakeholder capacity to maintain effective inter-ministerial coordination, and CCA M&E systems, and will put in place the necessary risk mitigation measures throughout implementation.

Output 3.1.1: National, sub-national, and/or sectoral adaptation plans developed or updated

Activity 3.1.1.1   Consolidate sectoral adaptation plans into a cross-cutting National Adaptation Plan (NAP)

Activity 3.1.1.1a: Under the leadership of the TCC, NTCs and sectoral experts consolidate sectoral adaptation plans, analyses and agreements into a cross-cutting National Adaptation Plan (NAP).

This activity aims to integrate sectoral adaptation plans from water, agriculture, coastal zones, and health into a unified National Adaptation Plan (NAP) for Yemen. By aligning these plans with national priorities, the process ensures a coordinated approach to climate resilience. Cross-sectoral coordination will promote coherence, address gaps, and incorporate themes like gender equity, social inclusion, and disaster risk reduction. The consolidated NAP will align with Yemen’s Intended Nationally Determined Contributions (NDCs) sectoral development plans, and international climate commitments, providing a strategic framework for implementation, financing, and monitoring climate adaptation measures, and fostering inter-sectoral collaboration to enhance Yemen’s climate resilience. The NAP will provide a strategic framework and roadmap to guide the implementation, financing and monitoring of climate adaptation measures, optimizing resources, and fostering inter-sectoral coordination.

The National Adaptation Plan (NAP) process is critical to ensuring that Yemen's updated Nationally Determined Contribution (NDC) includes a robust, evidence-based, and implementable adaptation component. The NAP development will inform the adaptation section of the NDC in several key ways:

Strengthening the Evidence Base for the NDC’s Adaptation Component. The NAP process will generate up-to-date, sector-specific climate risk and vulnerability assessments, which will directly inform the adaptation priorities in the updated NDC. NAP Vulnerability Assessments (Output 3.2.2.1c) will provide sectoral and national climate risk assessments based on updated climate projections and exposure analyses. NAP Downscaled Climate Projections (Output 3.2.2.1a) offer improved climate modeling, allowing the NDC to incorporate more accurate adaptation scenarios. NAP Hazard Mapping (Output 3.2.2.1b) will generate spatial risk maps for droughts, floods, and heatwaves, ensuring that adaptation measures in the NDC target the most at-risk regions. By integrating NAP-generated climate data, the updated NDC will reflect up-to-date climate vulnerabilities, strengthening the credibility and strategic direction of adaptation actions.

Identifying and Prioritizing Adaptation Actions for the NDC. The NAP will outline sectoral adaptation priorities for water, agriculture, coastal zones, and health, providing a structured basis for the adaptation component of the NDC. NAP Sectoral Adaptation Plans (Output 3.1.1.3a) will detail priority adaptation interventions in key sectors, which will be incorporated directly into the NDC. NAP Mainstreaming Guidance (Output 3.1.1.3b & 3.1.1.3c) will provide a framework for integrating climate adaptation into humanitarian efforts and gender-inclusive adaptation strategies, ensuring that the NDC includes socially inclusive and conflict-sensitive adaptation measures. The NAP’s emphasis on local-level adaptation (e.g., rainwater harvesting, climate-smart agriculture) will ensure that the NDC prioritizes scalable, community-driven solutions. This ensures that the adaptation measures in the NDC are not generic but aligned with Yemen’s specific climate risks, sectoral priorities, and community needs.

Establishing a Clear Adaptation Monitoring, Evaluation, and Reporting (M&E) Framework. The updated NDC requires a framework to measure progress in adaptation implementation. The NAP will develop standardized indicators and tracking mechanisms, which will be integrated into the NDC’s monitoring framework. NAP adaptation M&E System (Output 3.2.1.1a) will provide a structured framework for tracking adaptation progress, aligned with Paris Agreement requirements. NAP monitoring indicators will define measurable adaptation targets (e.g., hectares of drought-resistant crops planted, percentage of population covered by early warning systems) that can be adopted in the NDC’s monitoring framework. NAP Data Integration (Output 3.2.2.2a) will ensure that adaptation monitoring is linked to Yemen’s climate data-sharing portal, making NDC reporting more accurate and transparent. This enhanced adaptation tracking system will improve Yemen’s ability to report progress to the UNFCCC, making the NDC’s adaptation component more actionable and transparent.

Strengthening the Climate Finance Strategy in the NDC. The NAP will develop a cross-sectoral adaptation financing strategy, which will inform how the NDC identifies financial requirements for adaptation and mobilizes international climate finance. NAP Climate Finance Strategy (Output 3.4.3.1d) will identify funding needs, financing gaps, and investment priorities for adaptation, directly informing the NDC’s costing of adaptation measures. NAP Financial Working Group (Output 3.4.3.1): will coordinate with the Green Climate Fund (GCF), Adaptation Fund, and bilateral donors to ensure that the NDC is aligned with available funding mechanisms. The NAP will develop at least two GCF Concept Notes (Output 3.4.2.1), providing ready-to-fund adaptation projects that can be included in the NDC’s investment strategy. By ensuring that the NDC adaptation component is linked to a clear financing strategy, Yemen will improve its ability to attract climate finance and implement its adaptation commitments.

Aligning NAP with NDC Reporting Requirements under the Paris Agreement. The NDC must align with international climate commitments, particularly the Global Goal on Adaptation (GGA) under the Paris Agreement. The NAP will help frame Yemen’s adaptation priorities in a way that aligns with UNFCCC reporting guidelines. NAP Alignment with UNFCCC Guidelines will ensure that Yemen’s adaptation priorities follow UNFCCC’s Adaptation Communication guidelines, making the NDC adaptation component globally comparable. The NAP will contribute to Yemen’s Long-Term Strategy (LT-LEDS). The adaptation priorities defined in the NAP will also support Yemen’s long-term adaptation vision, ensuring alignment with LT-LEDS and national development goals. By ensuring alignment between the NAP process and international reporting frameworks, the NDC will be more robust, transparent, and eligible for international climate support.

Ensuring Policy Coherence Between the NAP and NDC. The NAP and NDC must be mutually reinforcing, with adaptation strategies in both documents supporting broader national climate policies. The NAP will harmonize adaptation priorities across water, agriculture, coastal, and health sectors (Output 3.1.1.1a), ensuring alignment with Yemen’s national climate policies. The NAP’s Technical Climate Coordination Committee (TCCC) (Output 3.1.3.1a) will ensure government ministries, CSOs, and international partners contribute to both NAP and NDC updates. Institutional strengthening will enhance capacity-building efforts (Output 3.1.4.1a), ensuring that key ministries are equipped to implement both NAP and NDC adaptation commitments. This policy coherence ensures that the NDC adaptation component is not standalone but embedded within Yemen’s broader climate resilience strategy.

Activity 3.1.1.1b: Workshop to validate the draft NAP engaging all relevant stakeholders to secure the buy-in for the NAP process.

A multi-stakeholder workshop will be organized to review, refine, and validate the draft NAP, bringing together representatives from government ministries, local authorities, civil society organizations, private sector actors, academia, M&E experts, international development partners, and vulnerable communities to ensure the NAP reflects diverse perspectives and priorities. The primary goal is to secure broad-based stakeholder buy-in for the NAP process, enhancing ownership and commitment to its implementation.  The workshop will share achievements, challenges, and lessons learned from the NAP process. The workshop will culminate with formalization of stakeholder commitments, including agreement on a clear roadmap, and the roles and responsibilities for the NAP’s implementation and monitoring. A summary report of the workshop will be provided including key decisions and next steps.

Activity 3.1.1.3: Develop 4 priority sectoral adaptation plans

Activity 3.1.1.3a:  Develop priority sectoral adaptation plans developed for water, agriculture, coastal zones and health sectors based on climate risk and vulnerability assessments (Activity 3.2.2.1).

This activity will develop sectoral adaptation plans for water, agriculture, coastal zones, and health, addressing each sector's specific vulnerabilities to climate change. These plans will identify risks, create tailored strategies, and engage sector stakeholders, incorporating local expertise. They will include prioritized interventions, a financing strategy, and clear indicators to track progress. The plans will integrate climate risk and vulnerability data with local knowledge, focusing on water and agriculture due to data limitations. Sectoral consultation will be conducted through National Thematic Clusters to ensure diverse perspectives and priorities are reflected in the adaptation plans.

Both the CRV and consultative assessments will use gender-sensitive and socially inclusive approaches (developed under Activity 3.1.1.3c) and will also take account of Yemen’s conflict context using the approaches and guidance on mainstreaming adaptation into humanitarian response and recovery to be developed under Activity 3.1.1.3b. The guidance documents on mainstreaming gender and social inclusion into climate adaptation and resilience programmes and plans (Activity 3.1.1.3c), the approach and guidance for mainstreaming climate change into humanitarian programmes and plans (Activity 3.1.1.3b), and the paper on conflict-sensitive approaches will be completed prior to the preparation of the sectoral plans and will fully inform the preparation of the plans.

The sectoral adaptation plans will include actionable recommendations for policy integration, financing strategies, and capacity-building initiatives (based on the Capacity Development Plan to be developed under Activity 3.1.4.1).

A systematic, evidence-based approach will guide the identification, appraisal, and prioritization of adaptation options for Yemen’s sectoral adaptation plans, ensuring they are climate risk-informed, gender-responsive, cost-effective, and conflict-sensitive. The process consists of five key phases:

- Identification of Adaptation Options – Climate Risk and Vulnerability Assessments (CRVA) will use climate projections, hazard mapping, and stakeholder consultations to compile a preliminary list of adaptation measures, including ecosystem-based solutions, infrastructure interventions, policy reforms, and economic resilience strategies.

- Appraisal of Adaptation Options – A multi-criteria analysis (MCA) and cost-benefit analysis (CBA) will evaluate technical feasibility, economic viability, and environmental sustainability. Conflict-sensitivity screening and institutional assessments will ensure adaptation actions contribute to stability and are supported by governance structures.

- Prioritization of Adaptation Options – Adaptation measures will be ranked based on urgency, policy alignment, and cross-sectoral benefits. Stakeholder workshops will validate selected interventions, ensuring they reflect community needs and enhance coordination.

- Integration into Sectoral and National Adaptation Plans – Prioritized adaptation measures will be embedded within sectoral adaptation plans and integrated into the National Adaptation Plan (NAP), with defined timelines, responsible agencies, and financial mechanisms. The Technical Climate Coordination Committee (TCCC) will oversee cross-sectoral alignment.

- Monitoring, Evaluation, and Adaptive Management – Sector-specific indicators will track progress, effectiveness, and impact. The M&E system, linked to the NAP portal, will enable continuous learning, periodic reviews, and adaptive management to refine adaptation strategies.

This structured approach will result in robust, evidence-based sectoral adaptation plans addressing climate risks in water, agriculture, coastal zones, and health. It will strengthen government capacity, improve coordination, enhance financial planning for adaptation investments, and facilitate the transition from planning to implementation. By integrating adaptation into national frameworks, Yemen will build long-term climate resilience while promoting socio-economic stability and sustainable development.

Activity 3.1.1.3b: Prepare an approach and guidance document to mainstream climate adaptation and resilience into humanitarian programmes and plans.

This activity aims to integrate climate adaptation into Yemen's conflict and post-conflict context, addressing both immediate humanitarian needs and long-term resilience. It will analyze existing humanitarian frameworks to identify gaps and opportunities for embedding resilience. Through stakeholder consultations, context-specific guidance will be developed to integrate climate adaptation into humanitarian planning.

Key approaches include developing an impact-based early warning system (EWS) using mobile technology and community radio, embedding climate risk and vulnerability assessments into humanitarian processes, promoting nature-based solutions, and designing resilient infrastructure. The project will also support adaptive livelihoods, particularly in rural, displaced, and drought-affected areas, and strengthen community involvement in local climate adaptation. Proposals combining humanitarian and adaptation needs, like climate-resilient shelters or water systems, will help link short-term relief efforts with long-term climate action.

Training will be provided to equip key stakeholders in the humanitarian and climate adaptation sectors with the necessary skills and tools to mainstream climate adaptation into humanitarian response and recovery efforts in Yemen. Given the country’s complex conflict and displacement context, the training will focus on integrating climate risk reduction strategies into humanitarian planning, relief efforts, and resilience-building initiatives to ensure that emergency responses also contribute to long-term adaptation goals.

Table 3: Activity 3.1.1.3b Indicative training topics, number of participants and targeted stakeholders

| Training Session Title | Topics Covered | Estimated Number of Participants (Gender Target: 40% Women, 60% Men) | Length/ Duration | Targeted Stakeholders |
| --- | --- | --- | --- | --- |
| Integrating Climate Adaptation into Humanitarian Planning and Response | Overview of Yemen’s humanitarian landscape and climate risks; Aligning humanitarian relief efforts with climate resilience strategies; Developing conflict-sensitive adaptation approaches for displaced communities; Linking climate adaptation with disaster risk reduction (DRR) frameworks. | 40 participants (16 women, 24 men) | 2 days | Ministry of Planning and International Cooperation (MoPIC), Ministry of Water and Environment (MoWE), Ministry of Agriculture and Irrigation (MoAI), Environment Protection Authority (EPA), Ministry of Health and Population (MoHP), UNHCR, IOM, OCHA, humanitarian NGOs, local disaster management agencies. |
| Climate Risk and Vulnerability Assessments in Humanitarian Programming | Conducting climate risk assessments in conflict-affected and displacement-prone areas; Integrating risk assessments into humanitarian interventions (food security, water supply, health, and shelter); Tools for mapping vulnerability hotspots and forecasting humanitarian needs based on climate projections. | 35 participants (14 women, 21 men) | 2 days | Government agencies (MoWE, MoAI, EPA, MoHP), UN agencies (UNDP, WFP, FAO, UNHCR), humanitarian NGOs, local adaptation project implementers, research institutions. |
| Developing Climate-Resilient Humanitarian Interventions | Designing climate-resilient infrastructure in displacement settings; Early Warning Systems (EWS) and mobile technology for climate risk communication; Nature-based solutions for food security and water management in humanitarian contexts; Strengthening adaptive livelihoods for displaced and vulnerable populations. | 35 participants (14 women, 21 men) | 2 days | Local government officials, humanitarian organizations, engineering and planning departments, community-based organizations (CBOs), private sector actors involved in humanitarian logistics and infrastructure. |
| Financing Climate Adaptation in Humanitarian Contexts | Identifying funding opportunities for climate-resilient humanitarian projects; Developing integrated funding proposals for humanitarian-adaptation interventions; Engaging donors, the private sector, and international financial institutions in adaptation finance for conflict-affected areas. | 30 participants (12 women, 18 men) | 2 days | MoPIC, MoF, MoWE, MoAI, MoHP, humanitarian actors (UN agencies, INGOs), development finance institutions, local NGOs, private sector representatives. |

Activity 3.1.1.3c: Prepare guidance document for mainstreaming gender and social inclusion into climate adaptation and resilience programmes and plans.

This activity will conduct a GESI assessment to analyze the gendered impacts of climate change and adaptation barriers faced by women, youth, the elderly, ethnic minorities, and marginalized groups in Yemen. Using participatory methods, data will be collected to identify vulnerabilities and inform culturally sensitive, inclusive strategies.

A guidance document will be developed to promote gender and social inclusion in climate adaptation, emphasizing an intersectional approach to overlapping vulnerabilities, such as those faced by displaced women. Inclusive participation will be prioritized by involving marginalized groups, particularly in rural and conflict-affected areas, to ensure their voices shape adaptation strategies.

Disaggregated data and participatory tools will be developed to inform planning, while gender-sensitive measures will be integrated into all stages. The guidance will be aligned with global frameworks such as the UNFCCC Gender Action Plan and SDGs, and will focus on equitable access to adaptation resources, removing barriers to distribution, and embedding gender-sensitive indicators in Monitoring and Evaluation systems to track progress and ensure accountability. Capacity building and awareness raising will be implemented for disparate target audiences through tailored training and awareness raising campaigns.

The Gender and Social Inclusion Guidance Document will serve as a key tool for integrating gender considerations into Yemen’s climate adaptation planning process. Given the country’s high gender inequality, social vulnerabilities, and climate-induced risks, the document will provide practical approaches to ensure equitable participation of women and vulnerable groups in climate adaptation decision-making.  It will support integration of gender-sensitive adaptation measures into key sectors, support gender-responsive budgeting in adaptation finance, and promote inclusive climate resilience strategies that address the differentiated impacts of climate change on men, women, youth, the elderly, and marginalized communities.

To effectively apply the Gender Mainstreaming Guidance Document, a comprehensive training and awareness-raising strategy will be developed. The following table summarises the training topics by target audience.

Table 4: Activity 3.1.1.3c Indicative training topics, number of participants and targeted stakeholders

| Training Session Title | Topics Covered | Estimated Number of Participants (Gender Target: 50% Women, 50% Men) | Length/ Duration | Targeted Stakeholders |
| --- | --- | --- | --- | --- |
| Mainstreaming Gender and Social Inclusion (GESI) in Climate Adaptation Policies and National Planning | Overview of Yemen’s gender and social inclusion challenges in climate adaptation; Policy frameworks for gender integration (UNFCCC Gender Action Plan, SDGs); Institutionalizing gender-responsive budgeting in adaptation finance; Aligning sectoral adaptation plans (Water, Agriculture, Coastal Zones, Health) with gender-responsive adaptation policies. | 40 participants (20 women, 20 men) | 2 days | Ministry of Planning and International Cooperation (MoPIC), Ministry of Finance (MoF), Environment Protection Authority (EPA), Ministry of Water and Environment (MoWE), Ministry of Agriculture and Irrigation (MoAI), Ministry of Health and Population (MoHP), Civil Aviation and Meteorology Authority (CAMA), gender focal points from sectoral ministries. |
| Applying Gender and Social Inclusion Tools for Climate Risk Assessments and Project Design | Conducting gender-sensitive climate risk and vulnerability assessments; Using the Gender and Climate Risk Assessment Toolkit; Screening adaptation projects for gender inclusivity; Designing gender-responsive project interventions; Practical exercises on applying gender analysis tools in project planning. | 35 participants (18 women, 17 men) | 2 days | National and local government agencies, sectoral ministries, NGOs, UN agencies, climate project developers, CSOs focusing on gender and social inclusion, local community representatives. |
| Gender-Responsive Budgeting and Access to Climate Finance for Women and Vulnerable Groups | Understanding the barriers to accessing climate finance for women and marginalized communities; Developing gender-responsive budgeting frameworks for adaptation; Introduction to the Gender-Responsive Budgeting Template; Strategies for integrating gender budgeting into sectoral and national adaptation finance mechanisms. | 30 participants (15 women, 15 men) | 2 days | MoPIC, MoF, MoWE, MoAI, MoHP, EPA, UN agencies, development finance institutions, private sector representatives, local adaptation project implementers. |
| Monitoring and Evaluation (M&E) of Gender-Responsive Adaptation Interventions | Developing gender-disaggregated indicators for adaptation programs; Establishing gender-sensitive M&E frameworks; Tracking adaptation outcomes through participatory engagement with women and marginalized groups; Integration of GESI indicators into the NAP M&E system; Data collection and reporting using gender-responsive methodologies. | 30 participants (15 women, 15 men) | 2 days | MoWE, MoAI, MoHP, EPA, MoPIC, M&E units in sectoral ministries, research institutions, UN agencies, NGOs and CSOs focused on gender equality and social inclusion. |

Activity 3.1.1.3d: Prepare a conflict-sensitive approach paper for Yemen’s adaptation planning

This activity involves the development of an approach paper on conflict sensitivity specifically tailored to Yemen’s adaptation planning process. The paper will include stakeholder mapping to identify key actors in the adaptation landscape and assess their roles and perspectives, particularly in conflict-affected regions. It will also provide a comprehensive analysis of how conflict, crisis, and peacebuilding dynamics intersect with climate change impacts and adaptation efforts, highlighting the need for a more flexible, context-specific approach within Yemen’s NAP.

The approach paper will outline how adaptation strategies should consider the complexities of the ongoing conflict and how these factors can affect resilience-building efforts. It will emphasize the need for adaptive, conflict-sensitive planning that integrates peacebuilding considerations into the NAP. Additionally, the paper will propose specific measures for enhancing stakeholder engagement, especially marginalized groups, and fostering collaboration between humanitarian, peacebuilding, and climate adaptation actors.

An expert specializing in conflict sensitivity will play a key role in this process and will be included as a member of the NAP drafting team. This expert will work closely with government representatives and other stakeholders to ensure that the approach paper aligns with Yemen's political, social, and economic realities while reflecting the best practices in conflict-sensitive climate adaptation planning.

Training will be conducted to equip stakeholders with the knowledge, tools, and methodologies necessary to apply conflict-sensitive approaches in adaptation planning. It will ensure that adaptation strategies consider the intersection of climate vulnerability, social tensions, and ongoing conflict dynamics, enabling the NAP process to contribute to both resilience-building and peacebuilding.

Table 5: Activity 3.1.1.3d:  Indicative training topics, number of participants and targeted stakeholders

| Training Session Title | Topics Covered | Estimated Number of Participants (Gender Target: 40% Women, 60% Men) | Length/ Duration | Targeted Stakeholders |
| --- | --- | --- | --- | --- |
| Understanding the Intersection of Climate Change, Conflict, and Adaptation in Yemen | Overview of Yemen’s conflict landscape and its implications for climate adaptation; How climate change exacerbates social tensions and displacement; Integrating conflict-sensitive principles into climate adaptation planning. | 40 participants (16 women, 24 men) | 2 days | Ministry of Planning and International Cooperation (MoPIC), Ministry of Water and Environment (MoWE), Environment Protection Authority (EPA), Ministry of Agriculture and Irrigation (MoAI), Ministry of Health and Population (MoHP), Civil Aviation and Meteorology Authority (CAMA), local government officials, humanitarian organizations. |
| Conflict-Sensitive Climate Risk and Vulnerability Assessments | Conducting climate risk assessments in fragile and conflict-affected areas; Identifying conflict risks in adaptation interventions; Tools for integrating conflict sensitivity into climate vulnerability assessments. | 35 participants (14 women, 21 men) | 2 days | Government agencies (MoWE, MoAI, EPA, MoHP), humanitarian actors (UNHCR, IOM, OCHA, INGOs), local CSOs, peacebuilding organizations, local adaptation project implementers. |
| Stakeholder Engagement and Participatory Planning in Conflict Zones | Mapping key actors in climate adaptation and peacebuilding; Inclusive consultation strategies for engaging vulnerable and displaced communities; Addressing gender and social inclusion challenges in fragile areas. | 30 participants (12 women, 18 men) | 2 days | Local government officials, tribal leaders, NGOs, women’s groups, community-based organizations (CBOs), humanitarian agencies. |
| Adaptive Governance and Institutional Mechanisms for Conflict-Sensitive Adaptation | Policy and institutional frameworks for conflict-sensitive adaptation planning; Strengthening coordination between climate adaptation, humanitarian response, and peacebuilding; Case studies of conflict-sensitive adaptation planning from other fragile contexts. | 30 participants (12 women, 18 men) | 2 days | MoWE, MoAI, MoHP, EPA, MoPIC, humanitarian and peacebuilding organizations, sectoral adaptation planners. |

Output 3.1.3: Inter and intra institutional coordination and decision making mechanisms established or strengthened

Activity 3.1.3.1 Establish a fully capacitated coordination mechanism for the NAP process at the national level under the TCCC.

Activity 3.1.3.1(a): Formally launch the NAP process in Yemen; Develop draft NAP Process Road Map.

This activity will officially launch the NAP Process through a stakeholder meeting. It will review and, if necessary, strengthen the terms of reference for the Technical Climate Coordination Committee (TCCC) to oversee the process. The activity will ensure inclusivity by engaging relevant stakeholders and providing the TCCC with the authority and tools needed for effective coordination. A flexible Draft NAP Roadmap will be developed, outlining key milestones, timelines, and responsibilities for NAP development and implementation, considering Yemen's socio-political challenges.

Activity 3.1.3.1b: Finalize the NAP Process Roadmap

This activity will review and revise the Draft Roadmap, conduct stakeholder consultations to gather feedback on the draft roadmap, and refine the roadmap based on inputs, ensuring feasibility and sectoral alignment.

A workshop will be conducted with stakeholders to validate the finalized roadmap and communication strategy.

Activity 3.1.3.1c: Establish and Conduct Bi-Annual TCCC Meetings and Provide Training on International Adaptation Experiences

The project will plan and establish bi-annual meetings, ensuring participation from all TCCC members and key stakeholders. Meetings will focus on enhancing coordination efforts in Yemen, especially on progress updates, challenges, and action plans for the NAP process. It will also incorporate case studies and lessons learned from international adaptation planning experiences.

Activity 3.1.3.1d: Establish National Thematic Clusters (NTCs) for Priority Sectors and Cross-Sectoral Humanitarian Sub-Cluster

The project will establish NTCs for agriculture, water, coastal zones, health, and a cross-sectoral humanitarian sub-cluster under the TCCC. ToRs for each cluster, specifying roles, responsibilities, and coordination mechanisms will be developed, with representatives from key stakeholders providing training for cluster members on their roles and deliverables, as well as developing and implementing a workplan that aligns with the NAP roadmap.

Activity 3.1.3.1e: Conduct Two Training Workshops to Strengthen Technical Capacity of the TCCC and NTCs

A series of workshops will be held to train TCC and NTCs.  The workshop design and plan based on training needs to be identified through a capacity assessment of the TCCC and NTCs (Under Activity 3.1.4.1a).  Training materials will be developed, focused on NAP planning, implementation, monitoring, and cross-sectoral coordination. Interactive training sessions that include case studies, role-playing exercises, scenario-based planning, and international best practices will address the specific roles and responsibilities of the TCCC and NTCs and will use a participatory approach to encourage active learning and practical application. Post-training evaluation will be based on the collection of feedback from participants to assess knowledge gains and identify areas for further capacity building.

The two training workshops will aim to enhance the capacity of the Technical Climate Coordination Committee (TCCC) and National Thematic Clusters (NTCs) in effectively planning, implementing, monitoring, and coordinating Yemen’s National Adaptation Plan (NAP). The workshops will be tailored based on training needs assessments (conducted under Activity 3.1.4.1a) and will ensure a practical, interactive, and sectoraly relevant approach. The workshops will be designed to strengthen participants' technical skills and understanding of NAP processes and cross-sectoral coordination. The training topics will include:

Table 6: Activity 3.1.3.1e - Workshop 1 - Fundamentals of NAP Planning and Implementation

| Module | Key Topics |
| --- | --- |
| Introduction to Climate Adaptation and NAP Process | Overview of climate change risks and vulnerabilities in Yemen. |
|  | Understanding Yemen’s NAP objectives and framework. |
|  | The role of TCCC and NTCs in NAP planning and implementation. |
| NAP Policy and Institutional Integration | How to mainstream adaptation into national and sectoral policies. |
|  | Policy coherence between NAP, NDC, and national development plans. |
|  | Role of ministries, agencies, and stakeholders. |
| Adaptation Planning Methodologies | How to conduct climate risk and vulnerability assessments. |
|  | Developing sectoral adaptation plans (water, agriculture, coastal zones, health). |
|  | Identifying and prioritizing adaptation actions. |
| Climate Finance and Resource Mobilization | Understanding adaptation finance mechanisms (GCF, GEF, Adaptation Fund). |
|  | Steps for developing bankable adaptation projects. |
|  | Public-private partnerships in adaptation finance. |
| Stakeholder Engagement and Participatory Adaptation Planning | Engaging communities, civil society, and vulnerable groups in adaptation planning. |
|  | Gender and social inclusion in adaptation planning. |
|  | Multi-stakeholder coordination mechanisms. |

Table 7: Activity 3.1.3.1e - Workshop 2 - Cross-Sectoral Coordination, M&E, and Knowledge Management

| Module | Key Topics |
| --- | --- |
| Strengthening Institutional Coordination for Adaptation | Mechanisms for cross-sectoral coordination and governance. |
|  | Role of the TCCC in overseeing NAP implementation. |
|  | Enhancing inter-ministerial and sub-national coordination. |
| Monitoring, Evaluation, and Learning (MEL) for Adaptation | Developing adaptation M&E indicators. |
|  | Tracking progress using the NAP M&E framework. |
|  | Data collection and reporting for adaptation interventions. |
| NAP Knowledge Sharing and Data Management | Best practices in adaptation knowledge management. |
|  | Use of climate information systems and decision-support tools. |
|  | Linking scientific research with policy-making. |
| International Best Practices and Case Studies in Adaptation | Reviewing successful NAP processes from similar contexts. |
|  | Scenario-based planning exercises and role-playing. |
|  | Lessons learned from other Least Developed Countries (LDCs). |

The training workshops will ensure inclusive participation, targeting a gender-balanced representation. Special efforts will be made to increase women’s participation in technical discussions. Youth, Indigenous groups, and marginalized communities will also be encouraged to participate.

| Target Group | Estimated Participants (Per Workshop) | Gender Target (Men/Women %) |
| --- | --- | --- |
| TCCC Members | 20 | 60% Men, 40% Women |
| NTC Members | 30 | 50% Men, 50% Women |
| Ministry Representatives | 15 | 60% Men, 40% Women |
| Technical Experts and Advisors | 10 | 50% Men, 50% Women |
| CSO and NGO Representatives | 10 | 40% Men, 60% Women |
| Private Sector & Academia | 5 | 50% Men, 50% Women |
| Development Partners (Observers) | 5 | 50% Men, 50% Women |
| Total Participants (Per Workshop) | 95 | 50-55% Men, 45-50% Women |

| Workshop | Duration |
| --- | --- |
| Workshop 1: Fundamentals of NAP Planning and Implementation | 3 days |
| Workshop 2: Cross-Sectoral Coordination, M&E, and Knowledge Management | 3 days |
| Total Training Duration | 6 days |

Table 8:  Targeted Stakeholders – Government Ministries and Institutions

| Institution | Role in the Training |
| --- | --- |
| Environmental Protection Authority (EPA) | Lead on NAP coordination and environmental governance. |
| Ministry of Water and Environment | Lead on water resource management adaptation. |
| Ministry of Agriculture and Irrigation | Responsible for climate-resilient agriculture initiatives. |
| Ministry of Health and Population | Ensure climate adaptation in health systems. |
| Ministry of Planning and International Cooperation | Align NAP with national development goals. |
| Civil Aviation and Meteorology Authority (CAMA) | Strengthen climate information services and early warning systems. |
| National Disaster Risk Management Unit (DRMU) | Link adaptation planning with disaster risk reduction. |

Technical Climate Coordination Committee (TCCC)

- Members from key ministries, climate adaptation experts, and finance officials.

- Responsible for NAP oversight, policy recommendations, and inter-ministerial coordination.

National Thematic Clusters (NTCs)

- Sectoral working groups focused on adaptation in water, agriculture, coastal zones, and health.

- Involved in technical planning, stakeholder engagement, and project implementation.

Civil Society Organizations (CSOs) and NGOs

- Yemeni Women’s Union & Gender-Based CSOs: Ensure gender mainstreaming in adaptation.

- Community-Based Organizations (CBOs): Provide local perspectives on adaptation challenges.

- International NGOs (Oxfam, CARE, etc.): Contribute expertise and funding support.

Private Sector & Academia

- Universities and Research Institutions: Strengthen climate research and knowledge sharing.

- Private Sector Representatives: Identify adaptation investment opportunities.

Development Partners & UN Agencies (Observers)

- UNDP, FAO, UN-HABITAT, UNEP, GCF, GEF, WFP, WHO

- Provide technical support and international best practices.

These training workshops will equip the TCCC and NTCs with the technical expertise needed to lead Yemen’s adaptation planning efforts under the NAP process. By ensuring a participatory, gender-balanced, and interactive learning approach, these workshops will enhance cross-sectoral coordination, strengthen institutional capacities, and drive effective implementation of climate adaptation initiatives in Yemen.

Output 3.1.4. Stakeholder engagement frameworks, agreements, and awareness raising conducted or strengthened.

Activity 3.1.4.1: Develop and implement CCA Capacity Development Strategy and Pla; awareness raising strategy, plan, tools and material; centralised awareness raising and knowledge-sharing mechanisms;

Activity 3.1.4.1a: Develop and implement an Institutional Capacity Development Plan for NAP based on a detailed institutional capacity assessment and gap analysis.

The project will undertake a detailed institutional Capacity Assessment and Gap Analysis to assess the current institutional capacity of key stakeholders involved in the NAP process. The assessment process will engage all relevant institutions to ensure the plan addresses diverse needs and will identify roles, responsibilities, and capacities for all CCA functions, gaps, and specific needs for the establishment/improvement of institutional capacity to CCA functions in each sector.

Based on this analysis an Institutional and Capacity Development Strategy and Plan (short-, medium, and long-term) for the long-term and continuous implementation and updating. It will do so by prioritizing capacity development for responsible institutions of the most vulnerable sectors and regions most vulnerable to climate impacts. It will also identify the funding and technical assistance that would be required for effective implementation, and establish indicators to measure implementation of the plan, and resulting improvements in institutional capacity.  Periodic reviews of the plan will be specified to adapt the plan based on lessons learned.

Based on the CDP the project will organize targeted training workshops, on-the-job coaching, and study tours for stakeholders and provide tools, guidelines, and resources to enhance institutional effectiveness in CCA.  The topics for which training will be provided under the project will be determined by the immediate needs of the project.

The following topics have been identified as likely priorities based on institutional needs for effective CCA functions at national and sub-national levels:

Table 9:  Activity 3.1.4.1a Indicative priority topics for capacity development and training under the NAP project

| Training Topic | Key Areas Covered | Relevance to NAP |
| --- | --- | --- |
| NAP Process and Governance | Roles and responsibilities of institutions in NAP implementation. | Ensures effective institutional engagement in the NAP process. |
|  | National policy frameworks and institutional mandates. |  |
|  | Cross-sectoral coordination for climate adaptation. |  |
| Climate Risk and Vulnerability Assessments (CRVA) | Conducting and interpreting risk and vulnerability assessments. | Improves evidence-based adaptation planning. |
|  | Application of climate risk data in decision-making. |  |
|  | Downscaling climate projections for adaptation planning. |  |
| Sectoral Adaptation Planning | Developing adaptation plans for water, agriculture, health, and coastal zones. | Aligns adaptation actions with sectoral priorities. |
|  | Integrating CCA into sectoral policies and plans. |  |
|  | Scenario-based adaptation planning. |  |
| Monitoring, Evaluation, and Reporting (M&E) for Adaptation | Establishing adaptation M&E systems. | Strengthens adaptation effectiveness and accountability. |
|  | Developing adaptation indicators and tracking progress. |  |
|  | Data collection and reporting for UNFCCC and NDC updates. |  |
| Climate Finance and Proposal Development | Accessing international climate finance (GCF, GEF, Adaptation Fund). | Enhances financial sustainability of adaptation initiatives. |
|  | Developing bankable adaptation project proposals. |  |
|  | Public-private partnerships for adaptation finance. |  |
| Climate Information and Early Warning Systems (EWS) | Role of meteorological data in adaptation planning. | Improves disaster risk reduction and resilience. |
|  | Strengthening climate information services. |  |
|  | Community-based early warning systems. |  |
| Gender and Social Inclusion in Adaptation | Addressing gender and social inequalities in adaptation. | Ensures equitable adaptation outcomes. |
|  | Gender-responsive adaptation planning. |  |
|  | Mainstreaming vulnerable groups in climate policies. |  |
| Ecosystem-Based Adaptation (EbA) Approaches | Nature-based solutions for climate resilience. | Enhances environmental sustainability of adaptation actions. |
|  | Coastal and watershed management strategies. |  |
|  | Agroforestry and sustainable land use planning. |  |
| Local Governance and Community-Based Adaptation (CBA) | Strengthening local government role in adaptation. | Supports decentralized adaptation planning. |
|  | Engaging communities in climate resilience planning. |  |
|  | Capacity building for municipal adaptation leadership. |  |
| Private Sector Engagement in Adaptation | Climate risk management for businesses. | Mobilizes private sector contributions to adaptation. |
|  | Investment opportunities in climate resilience. |  |
|  | Developing adaptation-focused public-private partnerships. |  |

Table 10:  Estimated participants per workshop

| Target Group | Estimated Participants per Workshop | Gender Target (% Men/Women) | Total Participants (44 Workshops) |
| --- | --- | --- | --- |
| National Government Officials | 20 | 60% Men, 40% Women | 880 |
| Local Government Representatives | 15 | 50% Men, 50% Women | 660 |
| Sectoral Ministries & Agencies | 15 | 60% Men, 40% Women | 660 |
| Civil Society & NGOs | 10 | 40% Men, 60% Women | 440 |
| Academia & Research Institutions | 5 | 50% Men, 50% Women | 220 |
| Private Sector Representatives | 5 | 50% Men, 50% Women | 220 |
| Development Partners & UN Agencies | 5 | 50% Men, 50% Women | 220 |
| Total Participants Per Workshop | 75 | 50-55% Men, 45-50% Women | 3,300 |

Special efforts will be made to increase women’s participation, particularly in leadership and decision-making roles. Marginalized groups and youth participation will be actively encouraged. Each training workshop will run for two days giving a total of 88 training days.

The workshops will involve national government agencies, technical bodies, CSOs, academia, and private sector representatives.

Table 11: Government Ministries and Institutions

| Institution | Role in Training |
| --- | --- |
| Environmental Protection Authority (EPA) | Lead institution for climate policy and adaptation planning. |
| Ministry of Water and Environment | Strengthening water resilience and resource management. |
| Ministry of Agriculture and Irrigation | Climate-smart agriculture, food security adaptation strategies. |
| Ministry of Health and Population | Public health and climate-sensitive disease adaptation. |
| Civil Aviation and Meteorology Authority (CAMA) | Climate data monitoring and early warning systems. |
| Ministry of Planning and International Cooperation (MoPIC) | Aligning adaptation with national development plans. |
| National Disaster Risk Management Unit (DRMU) | Linking adaptation to disaster risk reduction (DRR). |

Other Stakeholders will include:

- Regional and district-level government offices will be trained to decentralize adaptation efforts.

- Yemen Women’s Union & Gender-Based CSOs: Ensure gender-responsive adaptation.

- Community-Based Organizations (CBOs): Local engagement in climate resilience.

- International NGOs (Oxfam, CARE, etc.): Provide expertise and funding support.

- Universities and Climate Research Centers: Contribute climate data and knowledge-sharing.

- Chambers of Commerce, Business Associations: Mobilizing climate finance and innovation.

- UNDP, FAO, UN-HABITAT, UNEP, GCF, GEF, WFP, WHO: Provide international best practices and funding support.

Through 44 tailored training workshops, this activity will build long-term institutional capacity for adaptation planning, financing, and governance. These workshops will also address the training objectives outlined under outputs 3.1.1 and 3.1.3, ensuring sectoral integration, inclusive participation, and hands-on learning. By equipping Yemen’s institutions with the technical expertise needed to lead adaptation efforts, they will be empowered to drive the NAP process forward effectively.

.Activity 3.1.4.1b: Develop and Implement a Public Awareness-Raising Campaign

The objective is to develop awareness-raising materials such as leaflets, brochures, and videos to engage the public, CSOs, and other key stakeholders. Materials will highlight the importance of NAP, and the need to integrate considerations of national, sectoral, and regional development frameworks, plans, and priorities. Materials will be tailored for diverse audiences and ensure cultural sensitivity, while community outreach will focus on collaboration with local leaders, CSOs, and NGOs to distribute and disseminate the information.

The Communication Strategy and detailed implementation plan for the NAP process will be developed based on the identification of target audiences, key messages, and channels for raising awareness about the NAP process and will include timelines and resource requirements.

Activity 3.1.4.1c: Annual Awareness-Raising Fora on Climate Change, Adaptation, and the NAP Process

Under this activity annual awareness-raising fora on CCA and NAP process will be organised, to enhance awareness. The forums will feature expert speakers and interactive sessions, focusing on climate impacts, adaptation strategies, and regional needs through documentation and dissemination through digital platforms.

The primary objective of this activity is to enhance awareness of CCA and the NAP process in Yemen. Annual fora will serve as platforms for knowledge-sharing, stakeholder engagement, and dialogue, ensuring climate adaptation efforts are well understood and supported. They will increase awareness of climate risks among policymakers, civil society, and the private sector, helping integrate climate considerations into decision-making.

These events will provide updates on Yemen’s NAP process, highlight adaptation priorities in key sectors (water, agriculture, coastal zones, and health), and facilitate discussions on adaptation financing and resilience-building. They will promote transparency, collaboration among government agencies and communities, and institutional readiness for adaptation planning and implementation.

Key outcomes include stronger institutional and public support, improved dissemination of climate science and policy, and enhanced stakeholder engagement—particularly for underrepresented groups. The fora will also showcase best practices, adaptation innovations, and financing opportunities while fostering capacity development and climate-resilient practices.

A total of four two-day fora will be held annually over the NAP project’s four-year duration, featuring expert presentations, panel discussions, and interactive sessions to ensure broad participation and regional inclusivity.

Table 12:  Activity 3.1.4.1c Structure of the fora

| Session Type | Description |
| --- | --- |
| Plenary Sessions | Expert presentations on Yemen’s climate challenges, NAP progress, adaptation policies, and funding opportunities. |
| Panel Discussions | Experts, government officials, and civil society representatives debate and discuss sectoral adaptation priorities. |
| Breakout Sessions | Thematic group discussions focused on specific adaptation challenges (e.g., water security, food systems, health adaptation, climate finance, ecosystem resilience, urban adaptation). |
| Interactive Q&A Sessions | Participants engage directly with experts and policymakers to seek clarifications and contribute ideas. |
| Regional Adaptation Showcases | Presentation of local adaptation initiatives and best practices from Yemen and internationally. |
| Networking and Collaboration Opportunities | Participants will have the opportunity to connect, share experiences, and explore partnerships for adaptation projects. |

| Year | Key Theme |
| --- | --- |
| Year 1 | Introduction to the NAP Process, Climate Risks in Yemen, and Adaptation Priorities |
| Year 2 | Climate Resilience in Water, Agriculture, and Coastal Management |
| Year 3 | Climate Finance, Adaptation Governance, and Community-Led Adaptation |
| Year 4 | Monitoring Progress, Lessons Learned, and Strengthening Adaptation for the Future |

Each forum will engage approximately 100-150 participants per event (total 480–600 persons), ensuring a broad and inclusive representation of key stakeholders.

| Stakeholder Group | Expected Number of Participants (Per Forum) | Relevance to Adaptation Planning |
| --- | --- | --- |
| Government Ministries & Agencies | 30 | Leads in policy development, governance, and sectoral adaptation planning. |
| Local Government Authorities | 25 | Key implementers of adaptation strategies at sub-national levels. |
| Civil Society Organizations (CSOs) & NGOs | 20 | Play a major role in community-based adaptation and awareness raising. |
| Private Sector Representatives | 15 | Business engagement in climate resilience, investment in adaptation technologies. |
| Academia & Research Institutions | 15 | Provide scientific expertise, vulnerability assessments, and climate modeling insights. |
| Development Partners & International Organizations | 15 | Provide funding, technical assistance, and global adaptation best practices. |
| Youth, Women, and Marginalized Community Representatives | 10 | Ensure equitable adaptation planning and the inclusion of vulnerable groups. |
| Media & Communication Specialists | 10 | Essential for public awareness, advocacy, and dissemination of adaptation information. |

To extend the fora’s impact, key information will be digitized and widely shared via the NAP Portal, social media, and YouTube, ensuring accessibility for policymakers, researchers, and the public. Policy briefs, reports, newsletters, and infographics will provide actionable insights for government agencies, donors, and communities.

These events will enhance understanding of climate risks and adaptation solutions, strengthening collaboration between government, civil society, and the private sector. They will also support adaptation planning and financing by facilitating discussions on funding mechanisms and mobilizing resources.

As a key pillar of the NAP process, the fora will foster broad-based support, policy alignment, and inclusive planning, ensuring Yemen’s long-term climate resilience.

Activity 3.1.4.1d: Conduct Awareness Surveys to Measure the Evolution of Awareness on Climate Change and Adaptation

The project will develop processes for monitoring the awareness campaign’s effectiveness to enable tracking engagement metrics, such as the number of people reached and feedback received, and messaging and strategies adjusted based on monitoring results. Results will be compared across surveys to measure changes in awareness and identify areas where further awareness-raising efforts are needed. Results and findings will be shared with stakeholders through reports and presentations and insights used to refine awareness campaigns and training programs.

2) Outcome 3.2: Evidence produced to design adaptation solutions for maximum impact.

The projects Outputs 3.2.1, and 3.2.2 will all contribute to Outcome 3.2 by addressing Barrier 2: Limited access to climate risk and vulnerability data and technical capacity to integrate CRV data and information, into identification and appraisal of CCA interventions, Barrier 3: Lack of conflict analysis and an approach to address CCA challenges in crisis contexts and Barrier 4: Lack of CCA M&E system to monitor and evaluate how well the goals of climate change adaptation policies and priorities are being realized.  Under Output 3.2.1 a cross-sectoral M&E system for the NAP process will be established, which will include data sharing, awareness raising, e-learning, and online training, as well as capturing lessons learned from the NAP process systematically (Activity 3.2.1.1).  Under Output 3.2.2, to address Barrier 3, conflict sensitivity assessments will be conducted for key sectors (water, agriculture, coastal zones, and health) to analyze how conflict exacerbates vulnerabilities and impacts climate change adaptation efforts. Additionally, a comprehensive conflict analysis for Yemen's overall NAP will identify systemic challenges and opportunities to integrate conflict-sensitive approaches into national adaptation planning (Activity 3.2.2.1e).

Under the project’s Output 3.2.2 capacity building on climate project downscaling and risk and vulnerability assessments will be conducted and comprehensive climate risk and vulnerability assessment undertaken for up to 4 priority sectors (water, agriculture, coastal zones, health) (Activity 3.2.2.1). Information-sharing platforms, supported by relevant data-sharing mechanisms will be established, to provide access to evidence-based information for adaptation planning (Activity 3.2.2.2).  The fully operational and functioning online NAP portal with a Maintenance Schedule and Support Plan and Communication and Outreach Plan, featuring: i) climate data and information repository, ii) climate knowledge-sharing and knowledge management, iii) capacity development, awareness raising, and lessons learned pages/functionality linked to the NAP M&E system;  NAP Portal Launch Event Report.  In implementing Outcome 3.2 the project will have to overcome Risk 3: Lack of agreement on data sharing for development and analysis of climate risks and impacts in targeted sectors, and will put in place the necessary risk mitigation measures throughout implementation.

Output 3.2.1: Adaptation impact monitoring, evaluation and learning systems established or strengthened for strategic planning and investment.

Activity 3.2.1.1:  Develop and implement a cross-sectoral NAP M&E system

Activity 3.2.1.1a: Develop a Gender- and Climate-Sensitive M&E System for the NAP Process

The project will create a gender-sensitive, inclusive M&E system for climate adaptation in Yemen, addressing the unique socio-political, economic, and environmental challenges, including conflict and gender disparities. Aligned with international frameworks like the UNFCCC Gender Action Plan, SDGs, and the Sendai Framework, it will include sector-specific indicators to measure adaptation outcomes by gender, age, ethnicity, and other social factors. The system will engage key stakeholders in defining these indicators and be integrated with the NAP Portal.

A process and functionality for capturing lessons learned on an ongoing basis will be built into the M&E system and embedded in the NAP Portal. It will include a documentation plan, outlining responsibilities for data collection and reporting on key areas such as stakeholder engagement, challenges, and innovative practices.  The lessons learned functionality will enable comprehensive lesson-learned reports and summary briefs to be generated periodically, and findings shared through workshops, the NAP Portal, and international climate forums.

Pilots in priority sectors will test the M&E system, with training for government and local actors, ensuring flexibility for evolving goals and data availability.

Activity 3.2.1.1b: Training on the M&E System

The activity will conduct extensive training to finalize the M&E system, creating tailored manuals and guiding documents for TCCC, COCA, and the ministry staff. The workshop will further support the process, with pre- and post-assessments to measure knowledge improvements.

The training workshops will equip government officials, sectoral staff, and stakeholders with the skills to implement and manage Yemen’s gender- and climate-sensitive Monitoring & Evaluation (M&E) system for the NAP process. These workshops will ensure effective tracking of adaptation progress using standardized indicators aligned with national and international frameworks, including the UNFCCC, SDGs, and Sendai Framework.

A key focus will be integrating gender and social inclusion, ensuring disaggregated data collection to address the needs of vulnerable populations. The training will enhance institutional capacity for data analysis and reporting, supporting evidence-based decision-making and efficient adaptation finance use.

Table 13:  Training Modules and Topics

| Training Module | Key Topics Covered |
| --- | --- |
| 1. Introduction to Climate Adaptation M&E | Overview of the NAP’s gender-sensitive and conflict-sensitive M&E framework. |
|  | The role of M&E in tracking adaptation goals and effectiveness. |
|  | Understanding key adaptation indicators and reporting mechanisms. |
| 2. Developing and Using Adaptation Indicators | Sector-specific adaptation indicators for water, agriculture, coastal zones, and health. |
|  | Measuring adaptation outcomes by gender, age, ethnicity, and economic status. |
|  | Aligning adaptation indicators with the UNFCCC Gender Action Plan, SDGs, and Sendai Framework. |
| 3. Data Collection, Management, and Reporting | Methods for data collection (surveys, GIS, participatory approaches, remote sensing). |
|  | Strengthening institutional capacity for adaptation data management. |
|  | Developing standard reporting templates for adaptation progress and outcomes. |
| 4. Lessons Learned and Continuous Improvement | Using the NAP Portal's lessons learned function for adaptation tracking. |
|  | Identifying, documenting, and sharing best practices from sectoral adaptation efforts. |
|  | Developing summary reports and learning briefs for stakeholders and policymakers. |
| 5. Integrating M&E with National and International Reporting | Linking Yemen’s adaptation M&E system with national and UNFCCC reporting frameworks. |
|  | Aligning adaptation reporting with NDCs, National Communications (NCs), and Biennial Transparency Reports (BTRs). |
|  | Strengthening collaboration between COCA, TCCC, and ministries for M&E integration. |

Each training workshop will prioritize gender balance and include representatives from national and sub-national institutions, civil society, academia, and the private sector. Hence special attention will be given to including women, youth, and marginalized groups to promote inclusivity in adaptation monitoring and decision-making and participants from local and regional government agencies will be prioritized to enhance decentralized adaptation monitoring capacity. Each training workshop will be conducted over one day and will ensure a balance between theoretical learning and hands-on exercises.

| Target Group | Estimated Participants Per Workshop | Gender Target (Men/Women %) |
| --- | --- | --- |
| TCCC Members | 15 | 60% Men, 40% Women |
| COCA Representatives (Central Organization for Control and Auditing) | 10 | 50% Men, 50% Women |
| Sectoral Ministries (Water, Agriculture, Health, Environment, Planning) | 20 | 60% Men, 40% Women |
| Local Government & Regional Authorities | 15 | 50% Men, 50% Women |
| Civil Society Organizations (CSOs) & NGOs | 10 | 40% Men, 60% Women |
| Research & Academic Institutions | 5 | 50% Men, 50% Women |
| Private Sector & Development Partners | 5 | 50% Men, 50% Women |
| Total Participants Per Workshop | 80 | 50-55% Men, 45-50% Women |

The training will involve government institutions, technical agencies, research bodies, civil society, and development partners.

Table 14:  Targeted Stakeholders

| Institution | Role in Training |
| --- | --- |
| Environmental Protection Authority (EPA) | Lead agency for adaptation monitoring and reporting. |
| Ministry of Water and Environment | Collecting and analyzing climate-related water data. |
| Ministry of Agriculture and Irrigation | Monitoring climate impacts on agriculture and food security. |
| Ministry of Health and Population | Tracking climate-sensitive health outcomes and adaptation interventions. |
| Civil Aviation and Meteorology Authority (CAMA) | Providing climate data for adaptation M&E. |
| Ministry of Planning and International Cooperation (MoPIC) | Integrating adaptation M&E into national development plans. |
| Central Organization for Control and Auditing (COCA) | Ensuring transparency and accountability in adaptation finance reporting. |

Output 3.2.2: Studies on climate vulnerability, and identification of adaptation solutions conducted (and used) for strengthening adaptation investment

Activity 3.2.2.1: Assess Climate risk and vulnerability of 4 priority sectors and produce CRVA, conflict-sensitivity assessments and hazard maps for 4 pilot catchments.

Activity 3.2.2.1a: Workshops with climate analysis experts and relevant stakeholders from the climate information cluster to produce downscaled climate projections for four pilot catchments representative of the various ecoregions of Yemen (Abyan delta, wadi Rasyan, wadi Seham and wadi Hadramawt).

Key participants, including climate analysis experts, hydrologists, local authorities, and stakeholders from the climate information cluster will be invited to be trained in climate projects downscaling for Yemen.

The project will support the preparation of technical materials on downscaling methodologies and tools (e.g., statistical and dynamical downscaling) and the compilation and analysis of existing climate data and reports for the pilot catchments: Abyan delta, Wadi Rasyan, Wadi Seham, and Wadi Hadramawt. Given Yemen’s diverse climatic conditions, topographical variability, and significant data limitations, the selection of these four pilot catchments for climate change model downscaling and climate risk and vulnerability studies provides a strategic and practical approach to understanding localized climate impacts and informing national adaptation planning. Yemen's climate risks, including droughts, floods, flash floods, rising temperatures, and coastal erosion, vary significantly across different eco-regions.

The pilot catchments—Abyan Delta, Wadi Rasyan, Wadi Seham, and Wadi Hadramawt—represent Yemen’s key hydrological and ecological zones, covering coastal, arid, and semi-arid areas with distinct water resource challenges, and will ensure that the risk and vulnerability studies reflect the full spectrum of climate hazards Yemen faces.

- Abyan Delta (Coastal Zone): Represents low-lying coastal areas vulnerable to sea-level rise, storm surges, and saltwater intrusion.

- Wadi Rasyan (Highland Catchment): Captures mountainous and highland ecosystems where flash flooding is a key concern.

- Wadi Seham (Agricultural and Semi-Arid Region): Reflects agriculture-dependent areas where droughts and water shortages impact food security.

- Wadi Hadramawt (Desert and Arid Zone): Represents dryland regions prone to extreme heat, desertification, and water scarcity.

An estimated 38.8% of Yemen’s total population (approximately 12.8 million people) live within the four selected pilot catchments (Abyan Delta, Wadi Rasyan, Wadi Seham, and Wadi Hadramawt). These areas include densely populated regions such as Taiz, Ibb, and Hodeidah, as well as important agricultural and coastal communities. Collectively, the four pilot eco-regions account for nearly 100% of Yemen’s climate hazards. Coastal Hazards (Cyclones, Coastal Erosion, Flooding): 35%; Highland Hazards (Flash Floods, Landslides, Rainfall Variability): 30%; Semi-Arid Hazards (Droughts, Agricultural Losses): 20%; Desert Hazards (Heatwaves, Desertification, Water Scarcity): 15%.

Yemen suffers from a lack of historical climate data, sparse meteorological networks, and minimal localized climate projections, which makes it difficult to conduct a comprehensive national risk assessment without piloting targeted regional studies first. The findings from these pilot downscaling studies will provide baseline climate data for each eco-region which will allow for testing and refining downscaling methodologies before applying them nationwide. Hence, the pilot catchments will help fill data gaps through, downscaled climate models tailored to specific eco-regions, utilization of satellite and remote sensing data where ground-based measurements are unavailable, combining global climate models (GCMs) with localized observations (where they exist) to improve accuracy, and application of statistical techniques to reconstruct historical climate trends.

The project will conduct technical sessions on downscaling methodologies and best practices, facilitate collaborative exercises, and apply downscaling techniques using regional climate models (RCMs) or global climate models (GCMs), and historical data, to develop downscaled climate projections for each pilot catchment. . The activity will develop local expertise in advanced downscaling techniques, climate modelling, and the use of advanced data analysis and data modelling techniques and tools (e.g. open-source tools such as R, Python, and GIS platforms).  Importantly the downscaling exercise will provide climate projection parameters at the appropriate resolution for use in developing climate hazard, risk, and vulnerability modelling and mapping, and undertaking comprehensive risk and vulnerability assessments. Outputs of the downscaling exercise will be shared with relevant stakeholders for validation and further refinement. The activity will be achieved through the following sub-activities:

Stakeholder Meeting on Climate Projection Downscaling Needs and Data Gaps

This meeting will bring together key national and regional stakeholders to discuss Yemen’s climate data challenges, downscaling needs, and data procurement requirements. The session, which will be 3-days in duration, will introduce the methodologies and available resources for climate projections downscaling. Topics to be covered include:

- Overview of Climate Projection Needs for Yemen’s NAP Process

- Current Data Availability and Gaps in Meteorological and Hydrological Data

- Challenges in Climate Projection Downscaling for Yemen (Conflict, Data Scarcity, Regional Climate Models)

- Overview of Downscaling Techniques: Statistical vs. Dynamical Downscaling

- Potential Data Sources (Regional Climate Models, Reanalysis Datasets, Satellite-Based Observations, Proxy Data, Historical Data Reconstruction)

- Collaboration Opportunities for Data Procurement and Knowledge Sharing

- Next Steps for Climate Projection Development and Stakeholder Engagement

Table 15: Targeted stakeholders and estimated Number of Participants (with Gender Targets)

| Stakeholder Group | Estimated Participants | Gender Target (%) |
| --- | --- | --- |
| Government Agencies (EPA, CAMA, MoWE, MoAI, MoPIC, DRMU) | 15 | 60% Men, 40% Women |
| Academia and Research Institutions | 10 | 50% Men, 50% Women |
| International Development Partners (UNDP, FAO, WMO, GCF, GEF, WB) | 10 | 50% Men, 50% Women |
| CSOs and NGOs working on Climate Data and Adaptation | 10 | 40% Men, 60% Women |
| Private Sector (Tech Providers, Data Consultants) | 5 | 50% Men, 50% Women |
| Total Participants | 50 | 50-55% Men, 45-50% Women |

Technical Workshop on Climate Projections Downscaling for Yemen

This hands-on technical training will build the capacity of climate analysts, meteorologists, and hydrologists in advanced downscaling techniques, data analysis, and application of climate models for Yemen’s adaptation planning.  It will be 5-days in duration and topics to be covered include:

- Introduction to Downscaling for Climate Projections

- Comparison of Statistical vs. Dynamical Downscaling Methods

- Understanding Global Climate Models (GCMs) and Regional Climate Models (RCMs)

- Hands-on Training on Using RCMs for Downscaling Climate Projections (CORDEX, WRF, PRECIS)

- Using Satellite-Based Observations and Reanalysis Datasets for Climate Modelling

- Application of Downscaled Climate Projections for Yemen’s Four Pilot Catchments (Abyan Delta, Wadi Rasyan, Wadi Seham, and Wadi Hadramawt)

- Use of Open-Source Tools for Climate Downscaling (R, Python, GIS Platforms)

- Practical Exercises in Climate Model Data Processing and Interpretation

- Generating Climate Projection Outputs for Climate Hazard and Vulnerability Assessments

Table 16: Targeted stakeholders and estimated Number of Participants (with Gender Targets)

| Stakeholder Group | Estimated Participants | Gender Target (%) |
| --- | --- | --- |
| Government Agencies (EPA, CAMA, MoWE, MoAI, MoPIC, DRMU) | 15 | 60% Men, 40% Women |
| Academia and Research Institutions | 15 | 50% Men, 50% Women |
| Meteorologists and Climate Data Analysts | 10 | 50% Men, 50% Women |
| NGOs and CSOs Working on Climate Data and Adaptation | 10 | 40% Men, 60% Women |
| Private Sector (GIS and Remote Sensing Firms, Data Providers) | 5 | 50% Men, 50% Women |
| Total Participants | 55 | 50-55% Men, 45-50% Women |

Stakeholder Validation Workshop on Downscaled Climate Projections for Yemen’s Pilot Catchments

This workshop will engage stakeholders in validating the outputs of the climate downscaling exercise, ensuring that projections are scientifically sound and applicable for adaptation planning.  It will be 1-day in duration and the following topics will be covered:

- Presentation of Downscaled Climate Projections for Yemen’s Four Pilot Catchments

- Discussion on Data Accuracy, Challenges, and Gaps in Projections

- Validation of Key Climate Projection Parameters (Temperature, Precipitation, Extreme Weather Events)

- Application of Projections in Climate Hazard, Risk, and Vulnerability Assessments

- Feedback and Recommendations for Finalizing Climate Downscaling Outputs

Table 17: Targeted stakeholders and estimated Number of Participants (with Gender Targets)

| Stakeholder Group | Estimated Participants | Gender Target (%) |
| --- | --- | --- |
| Government Agencies (EPA, CAMA, MoWE, MoAI, MoPIC, DRMU) | 20 | 60% Men, 40% Women |
| Academia and Research Institutions | 15 | 50% Men, 50% Women |
| NGOs, CSOs, and Local Authorities | 10 | 50% Men, 50% Women |
| Private Sector (Climate Data Consultants, Water Management Firms) | 5 | 50% Men, 50% Women |
| Total Participants | 50 | 50-55% Men, 45-50% Women |

These workshops will ensure that Yemen develops robust, scientifically validated, and stakeholder-endorsed climate projections, which will support climate hazard, risk, and vulnerability assessments for adaptation planning.

Key to successful downscaling will be addressing data gaps that are significant for Yemen and pose challenges for accurate downscaling of climate projections. A combination of approaches can help overcome these gaps, enabling more reliable assessments and planning for climate change adaptation.  A combination of the following approaches will be used:

- Leverage Regional Climate Models (RCMs) and Reanalysis Data: Use high-resolution regional climate models (RCMs) that simulate climate processes at finer spatial scales.

- Utilize publicly available RCM outputs, such as those from the Coordinated Regional Downscaling Experiment (CORDEX), which provides data for the Middle East and North Africa (MENA) region.

- Supplement with reanalysis datasets (e.g., ERA5, MERRA-2), which combine observations with model outputs to fill gaps in historical climate data.

This approach provides region-specific insights even in data-scarce areas and reduces reliance on local observation networks.

- Develop Hybrid Statistical-Dynamical Downscaling Models: Combine dynamical models with statistical methods to refine projections using available local data.

- Use dynamic models to generate large-scale climate projections.

- Apply statistical relationships (e.g., regression models, machine learning) to downscale projections based on sparse local observational data.

This approach enhances precision by accounting for local climate drivers and is useful for bridging data gaps when observational datasets are incomplete.

- Satellite-Based Observations: Use satellite data to supplement or replace ground-based observations.

- Leverage remote sensing platforms like NASA’s MODIS or ESA’s Sentinel for temperature, precipitation, and land surface data.

- Use satellite-derived products for hydrological parameters such as soil moisture, evapotranspiration, and vegetation health.

This approach is beneficial for covering remote or conflict-affected areas where ground stations are non-functional and provides consistent and spatially comprehensive datasets.

- Use Proxy Data: Use alternative datasets as proxies for unavailable data.

- Substitute missing rainfall data with river discharge or soil moisture indices.

- Use vegetation indices as proxies for climate impacts on ecosystems

This approach will help bridge short-term data gaps without compromising analysis quality and enables cross-validation with other datasets.

- Historical Data Reconstruction: Reconstruct missing historical climate data using statistical and machine learning techniques.

- Use data interpolation methods to estimate missing values in time series.

- Apply machine learning algorithms (e.g., neural networks) to fill spatial and temporal gaps in historical datasets.

This would provide a baseline for validating projections and understanding historical trends and is useful for areas with partial or inconsistent records.

- Scenario-Based Approaches: Use multiple climate scenarios (RCPs/SSPs) to account for uncertainties due to data gaps.

- Simulate a range of scenarios using global and regional models to provide a spectrum of potential climate outcomes.

- Focus on scenario-based planning to address the range of uncertainties.

This approach supports decision-making despite data limitations and provides robust insights for long-term planning.

- Enhance Regional Data-Sharing Mechanisms: Collaborate with neighbouring countries and regional bodies to share climate and hydrological data.

- Establish data-sharing agreements with Gulf Cooperation Council (GCC) states or other MENA countries.

- Participate in regional climate initiatives to gain access to collective datasets and tools.

This approach would improve data availability for transboundary climate issues and strengthen regional cooperation on climate adaptation.

- Engage International Meteorological Institutions: Collaborate with international climate research centers and meteorological organizations to access expertise and data (see Activity 3.2.2.1d).

- Establish partnerships with organizations like the World Meteorological Organization (WMO) or regional climate centers.

- Use their resources, including data-sharing platforms and technical expertise, to improve projections.

This approach provides access to high-quality data and models developed for the MENA region and capacity building for local institutions in using advanced tools.

Procurement of Climate Data for climate project downscaling

The project will procure the required datasets to support the available historical and observational climate data.  These will include high-resolution global/regional climate model (GCM/RCM) data, satellite imagery, and geospatial datasets for topography, land use, and hydrology. Data from private sources may require licensing fees (e.g., commercial climate data providers or satellite imagery agencies).  However, opportunities will be sought to use open-access datasets (e.g., from NASA, ESA, or CMIP6) which might reduce costs. There may be additional costs associated with preprocessing raw data for model compatibility. In addition, licensing for specialized software required for downscaling (e.g., WRF, PRECIS, or statistical downscaling tools) may also have cost implications. An indicative cost breakdown for the procurement of data, pre-processing, and software is provided below.

Activity 3.2.2.1b: i) assess methodologies and data availability for modelling and mapping key the impact of climate hazards in Yemen (drought, floods and flash floods, heat and heatwaves, coastal erosion, and land degradation; ii) Depending on data availability and methodologies identified, develop indices and high level hazard maps, for at least two hazards (drought and flood and flashflood) for 4 pilot catchments.

This activity aims to develop hazard indices and high-level hazard maps for the climate hazards that cause significant impacts on vulnerable communities in Yemen. The project will first assess data availability and methodologies for modelling and mapping climate hazards, such as droughts, floods, heatwaves, and coastal erosion, to identify gaps in data availability and propose solutions, such as using satellite imagery or regional databases. The project will employ all possible methods to prioritize data accuracy and ensure the use of consistent methodologies across all catchments, including the use of local knowledge to improve historical records and collaboration with regional and international organizations to access additional datasets (among other data gap-filling approaches discussed above).

The desired results would be a set of hazard indices for drought based on internationally accepted parameters (e.g., Standardized Precipitation Index (SPI), Standardized Precipitation and Evapotranspiration Index (SPEI)), and where possible produce hazard maps for droughts, floods, and flash floods as a minimum, using GIS tools to develop high-level maps for the four pilot catchments. Stakeholders will be engaged throughout the process to integrate local knowledge and historical records, enhance mapping, and validate the accuracy, relevance, and applicability of the indices and maps.

Activity 3.2.2.1c: Develop comprehensive climate risk and vulnerability assessments for 4 priority sectors (water, agriculture, coastal zones and health) in Yemen and national climate risk and vulnerability assessments.

This activity will develop a climate risk assessment for the four priority sectors based on the downscaled climate projections and hazard modeling data to be developed in Activities 3.2.2.1.a and 3.2.2.1b above. These data will be integrated with sectoral socio-economic, environmental, and physical vulnerability data sets to assess the climate risks and vulnerability of each sector to climate change.

Gender-sensitive and inclusive sectoral data collection processes will be employed to collect and compile disaggregated socio-economic, environmental, and physical susceptibility data relevant to water, agriculture, coastal zones, and health, and will include engagement of stakeholders in each sector to understand sector-specific vulnerabilities, using participatory approaches.

Risk analysis will be conducted to assess the exposure, sensitivity, and adaptive capacity of the 4 catchments for each sector, using a standardized risk assessment framework, adapted to the Yemeni context, and incorporating local knowledge. Various standardized frameworks, recognized as international best practices, can be tailored for regional and sector-specific applications to perform comprehensive, sector-specific risk assessments that inform targeted and effective climate adaptation strategies and plans. For example:

- Water Sector: Use the IPCC Framework combined with CRET or the World Bank Water Risk Screening Tool to address hydrological challenges.

- Agriculture: Apply the FAO framework for assessing crop-specific risks and food security impacts.

- Coastal Zones: Leverage the Coastal Hazard Wheel Framework and ICZM guidelines to address sea-level rise and storm surges.

- Health: Use the WHO framework to strengthen climate resilience in Yemen’s health systems.

Once the climate risk and vulnerability studies are conducted for the four pilot catchments, their findings will be synthesized and scaled to inform broader national adaptation planning through the following mechanisms:

- Comparative Analysis and Extrapolation: The pilot studies will generate region-specific risk factors, which will be used to develop predictive models for similar regions across Yemen. Key climate indicators such as temperature variability, precipitation patterns, extreme event frequencies, and ecosystem stressors will be analyzed and applied to non-pilot areas using statistical extrapolation.

- Integration into the National Adaptation Plan (NAP): The insights gained from the pilot catchments will inform Yemen’s sectoral adaptation strategies, particularly for water resource management, agriculture resilience, and coastal protection. The risk maps and vulnerability assessments will be used to prioritize adaptation actions in Yemen’s National Adaptation Plan (NAP), ensuring that climate risks are well-understood at different geographical scales.

- Development of a National Climate Hazard Mapping System: The GIS-based climate risk maps developed for the pilot areas will form the basis of a national climate hazard mapping system, which will help identify priority regions for adaptation investments. By establishing a standardized methodology for climate risk assessments, Yemen will be able to conduct periodic updates using new data sources as they become available.

- Incorporation into Climate Finance and Project Development: The data from the pilot catchments will provide evidence-based justifications for climate finance proposals, supporting grant applications to the Green Climate Fund (GCF), Adaptation Fund, and bilateral donors. These assessments will also guide the design of future adaptation projects, ensuring that funding is directed to high-risk areas with scientifically validated adaptation priorities.

- Capacity-Building and Replication for Future Studies: Training materials and methodologies developed during the pilot studies will be used for national capacity-building efforts. Government institutions, universities, and research centers will be equipped with guidelines and tools to conduct similar climate risk studies in other catchments.

Focusing on these four pilot catchments provides a pragmatic approach to climate risk and vulnerability assessments in Yemen, balancing data limitations, capacity constraints, and the need for regionally tailored adaptation solutions. Moreover, the four pilot catchments are highly representative of Yemen’s broader climate challenges, making them ideal for modelling climate risk and adaptation needs. By scaling insights from the pilot studies, a national climate risk assessment will be developed using extrapolation techniques and scenario modelling and the methodologies, climate models, and risk assessments piloted in these catchments will be applied to other regions in Yemen with similar climatic conditions. Given that nearly 40% of the population lives in these catchments, adaptation actions based on pilot findings will directly benefit a large segment of the Yemeni population. By leveraging insights from these pilots, and scaling up climate risk assessments nationwide, the project will ensure that adaptation strategies are informed by reliable, localized climate projections.

Based on the results of the risk analysis, sectoral risk profiles developed for each sector, highlighting priority adaptation needs and recommendations, will be shared with stakeholders for feedback and validation. Finalized comprehensive first-order sectoral climate risk assessments will be published on the NAP Portal (to be developed under Activity 3.2,2,2).

Activity 3.2.2.1d: i) Develop a detailed specification and procurement documents for the engagement of an international Meteorological Department/Institution to provide climate information and monitoring services expertise and cooperate with the Yemen Meteorological Department and; ii) Establish a Memorandum of Understanding (MOU) with the successful institution to cooperate on the monitoring of climate variables in the Gulf of Aden.  Monitoring data will be made available via the online information-sharing platform (Activity 3.2.2.2).

Yemen's meteorological and climate data services are hindered by limited infrastructure, technical capacity, and resources due to years of conflict. CAMA, the main authority, focuses on aviation meteorology and struggles to expand its role in climate adaptation. Engaging an international meteorological institution will help address gaps in climate data, improve forecasting, and build local capacity. This project will support the development of technical specifications and procurement documents for partnering with such an institution, as well as establish an MOU outlining training, data sharing, and collaboration on climate monitoring, aligned with Yemen’s long-term adaptation goals.

Activity 3.2.2.1e: Conduct Conflict Sensitivity Assessments for Key Sectors and overall NAP in Yemen

This activity involves conducting conflict sensitivity assessments for key sectors, including water, agriculture, coastal zones, and health, in Yemen as well as a comprehensive conflict analysis for Yemen's overall NAP.  The conflict-sensitive approach paper developed under Activity 3.1.1.3d will serve as a foundational document for integrating conflict sensitivity into Yemen’s National Adaptation Plan (NAP) and sectoral adaptation planning. Given Yemen’s ongoing conflict, political instability, and humanitarian crisis, this paper will provide a framework for identifying, assessing, and mitigating conflict-related risks in adaptation interventions, ensuring that climate adaptation planning does not exacerbate tensions but instead supports resilience-building, stability, and peacebuilding efforts.  These sector-specific assessments will examine how conflict exacerbates vulnerabilities and hinders climate change adaptation efforts, identifying the interplay between conflict dynamics and sectoral resilience. The overarching NAP conflict analysis will provide a holistic understanding of how Yemen's fragile context influences national adaptation priorities, processes, and implementation capacities.

The sectoral assessments will be integrated with the climate risk assessments (Activity 3.2.2.1c) to create a unified understanding of challenges and opportunities. The NAP-level conflict analysis will include mapping socio-political dynamics, analyzing how conflict affects governance structures, and identifying systemic barriers to adaptation planning in conflict-affected areas.

Stakeholder engagement, including consultations with local communities, sector experts, government representatives, and humanitarian actors, will ensure that the assessments reflect local realities and diverse perspectives. These consultations will inform both sectoral and national-level analyses, ensuring alignment with Yemen's socio-political and environmental context.

Activity 3.2.2.2a: Develop and operationalize the NAP Platform.

This activity aims to develop, operationalize, and maintain a National Adaptation Plan (NAP) Portal for Yemen, ensuring that climate data, adaptation knowledge, and decision-making tools are easily accessible to government agencies, sectoral ministries, NGOs, development partners, researchers, and local communities.

The NAP Portal will serve as a:

- Climate data and information repository and sharing platform – Integrating climate monitoring and risk assessment data from national and international sources.

- Climate knowledge-sharing and repository – Centralizing studies, reports, training materials, guidelines, and climate adaptation planning resources.

- Capacity development, awareness raising, and lessons learned portal – e-learning platform for capacity building and awareness raising.

- Decision-support tool – Providing GIS-based visualization and analytical tools to support climate adaptation policies and investments.

- External collaboration platform – Facilitating information exchange and coordination with international climate organizations, donors, and research institutions.

Under this activity Needs Assessment and Stakeholder Engagement for NAP Portal Design will be undertaken, through consultations with key stakeholders, including Civil Aviation and Meteorological Authority (CAMA,) Environment Protection Authority (EPA), sectoral ministries, NGOs, and data users, to identify specific needs for climate data access, types of data required, and user interface preferences to ensure the design reflects the needs of all key users, including sectoral agencies and local communities. A final report and the draft Concept Design for the platform will be developed.

Based on the needs assessment and draft concept design, the detailed platform design and technical specifications will be developed, which will detail the structure of the NAP Portal, ensuring it is user-friendly, scalable and accessible.

The project will develop the online NAP Portal platform using modern database and web development tools. Rigorous testing of the NAP Portal, including its linkage to the existing CAMA) database will be conducted to ensure functionality, reliability, and ease of use.  Feedback from pilot users will be used to refine the platform. The project will develop a plan for ongoing monitoring and evaluation (M&E) to track platform performance and user engagement, and establish a maintenance schedule, including system updates and troubleshooting.

An event will be organized to launch the platform and an accompanying Communication Strategy to showcase the portal to stakeholders and the public. Communication materials (e.g., brochures, tutorials) to promote the portal and guide users will use traditional and digital media to raise awareness about the portal’s features and benefits.

3) Outcome 3.4: Adaptation finance increased.

The project’s Outcome 3.4 will address Barrier 5: Limited availability of adaptation finance and lack of a financing strategy for developing bankable CCA projects through Output 3.4.2 which will develop 2 priority concepts notes for cross-sectoral priority projects (Activity 3.4.2.1) to be identified in the sectoral plans. The concept notes will be supported by pre-feasibility studies to be developed under Activity 3.4.2.2. Under Output 3.4.3 the project will establish a cross-sectoral NAP  Finance Working Group (Activity 3.4.3.1) to steer adaptation pipeline project financing strategy, and develop a funding strategy for long-term CCA in Yemen (Activity 3.4.3.2).  In implementing this Output, the project will need to overcome Risk 4: Inadequate financing for long-term implementation due to limited financial and technical capacity and strategies for long-term systematic development of bankable CCA projects, and put in place the necessary risk mitigation measures throughout implementation.

Output 3.4.2: Number of concept notes and/or funding proposals developed for adaptation priority actions

Activity 3.4.2.1: Develop #2 Concept notes for adaptation priority actions.

The project will develop 2 priority concept notes for climate adaptation projects to mobilize climate finance for key sectors, moving from adaptation planning to implementation. The priority projects will be identified in the sectoral plans based on climate risk and vulnerability study and will identify the most appropriate financing strategy for each, based on the adaptation financing strategy to be developed in Activity 3.4.3.1.

The project will assist the NDA in the early identification of an Accredited Entity (AE) during the project ideation phase, ensuring alignment with project goals and requirements from the outset and will share the draft Concept Notes (with GCF regional teams) to gather initial feedback, fostering early collaboration and input. Throughout the grant implementation phase, it will be ensured that resources, including technical support and expertise, are made available to address and incorporate the feedback received, facilitating a smooth and responsive adaptation of the project as it progresses.

In addition, the project will ensure that new project ideas developed through the NAP process align with the existing priorities of the country programme to avoid duplication and optimize resources. The development of CNs will be closely aligned with the country programme, incorporating any new priorities that arise. If adaptation priorities change during the NAP process, the country programme’s priorities  will be updated accordingly.

Activity 3.4.2.2: Undertake  two pre-feasibility studies to support the development of at least two GCF Concept Notes.

Under this activity, the project will undertake studies and assessments culminating in pre-feasibility studies to support the development of at least two GCF Concept Notes to address cross-sectoral adaptation priorities.

The project will conduct two pre-feasibility studies to assess the viability, sustainability, and financing potential of cross-sectoral adaptation projects. These studies will provide technical, financial, and environmental assessments to support the development of GCF Concept Notes (Activity 3.4.2.1).

Project selection will be guided by climate risk assessments, sectoral adaptation planning, and financing priorities. The studies will evaluate feasibility, cost-benefit, and alignment with Yemen’s NAP, NDC, and GCF Country Programme, ensuring evidence-based adaptation investments.

Conducted in collaboration with key national agencies, the studies will include stakeholder validation and assess environmental and social impacts, focusing on vulnerable groups. Findings will strengthen project bankability, align with Yemen’s adaptation financing strategy, and enhance institutional capacity for mobilizing climate finance.

Output 3.4.3: National systems developed for tracking adaptation national and international finance flows

Activity 3.4.3.1: Establish a Cross-Sectoral NAP Financial Working Group (FWG)

Activity 3.4.3.1a: Establish a Cross-Sectoral NAP Financial Working Group (FWG)

The project will establish an Adaptation Finance Working Group (FWG) and develop a comprehensive Adaptation Finance Strategy to enhance the mobilization, coordination, and utilization of resources for climate adaptation. The FWG will address the fragmentation of funding efforts and lack of centralized coordination by bringing together stakeholders from diverse sectors and vulnerable groups to streamline funding priorities aligned with NAP goals.

The FWG will serve as a centralized entity for coordinating adaptation finance across sectors, such as water, agriculture, health, and coastal zones. It will build local capacities in climate finance, proposal development, and fund management while promoting knowledge sharing and replication of best practices.

The project will draft the FWG’s Terms of Reference (ToR), outlining roles for identifying funding opportunities, conducting gap analyses, and coordinating financial strategies. The FWG is planned to be formally established through a government resolution or agreement, with a chairperson and secretariat appointed. Capacity building will be delivered through training on climate finance mechanisms, including accessing international funds like the GCF and Adaptation Fund. An initial workplan will also be developed to guide FWG activities.

To ensure that the Cross-Sectoral NAP Financial Working Group (FWG) remains operational, functional, and effective beyond the lifespan of the project, several key measures will be put in place. These measures focus on institutionalizing the FWG, embedding it within national climate governance structures, securing sustained funding, strengthening capacity, and fostering partnerships. The aim is to ensure that the FWG continues to coordinate adaptation finance efforts, mobilize resources, and provide technical support for financing climate adaptation in Yemen long after project closure.

To strengthen the capacity of the NAP Financial Working Group (FWG) and ensure its long-term effectiveness in mobilizing, coordinating, and managing climate finance, a comprehensive training program will be delivered. This program will focus on enhancing technical expertise on climate finance mechanisms, project proposal development, financial structuring, and accessing international funds such as the Green Climate Fund (GCF), Adaptation Fund, Global Environment Facility (GEF), and bilateral/multilateral financing options. The training will be designed to equip FWG members and relevant stakeholders with the skills necessary to develop bankable climate adaptation projects, track adaptation finance flows, and integrate adaptation financing into national and sectoral budgets.

| Training Topic | Estimated Number of Participants (Gender Target: 40% Women, 60% Men) | Length/ Duration | Targeted Stakeholders |
| --- | --- | --- | --- |
| Introduction to Climate Finance and International Climate Funds | 30 participants (12 women, 18 men) | 2-day workshop | MoPIC, MoF, EPA, CAMA, MoWE, MoAI, MoHP, CSOs, private sector, academia |
| Accessing the Green Climate Fund (GCF): Policies, Investment Criteria, and Proposal Development | 30 participants (12 women, 18 men) | 3-day workshop | FWG members, NDA (GCF focal point), MoPIC, MoWE, MoAI, MoHP, CSOs, development partners |
| Adaptation Fund and GEF: Project Design, Eligibility, and Access Requirements | 25 participants (10 women, 15 men) | 2-day workshop | FWG members, MoWE, MoAI, MoF, local authorities, private sector, academia |
| Climate Finance Governance and Mainstreaming Adaptation Finance into National Budgets | 30 participants (12 women, 18 men) | 2-day workshop | MoF, MoPIC, sectoral ministries (Water, Agriculture, Health), parliament representatives, local authorities |
| Developing Bankable Adaptation Project Proposals for International Climate Finance | 35 participants (14 women, 21 men) | 3-day practical workshop | FWG members, MoWE, MoAI, MoF, CSOs, private sector |
| Climate Finance Tracking, Monitoring, and Reporting Mechanisms | 25 participants (10 women, 15 men) | 2-day workshop | FWG members, MoF, MoPIC, EPA, sectoral ministries, local government |
| Innovative Financing Instruments for Adaptation (Blended Finance, Public-Private Partnerships, Insurance Solutions) | 25 participants (10 women, 15 men) | 3-day training | FWG members, MoF, private sector, financial institutions, donors |
| Stakeholder Engagement in Adaptation Finance and Leveraging Co-Financing | 30 participants (12 women, 18 men) | 2-day interactive workshop | FWG members, donors, development banks, CSOs, sectoral ministries, private sector |

Activity 3.4.3.1b: Assess the funding gap between available funding for climate change adaptation and the costing of adaptation options determined in the adaptation action plans and frameworks developed under Output 3.1.1 in collaboration with the cross sectoral FWG

Under this activity, the project will review adaptation options and costs. It will compile costing data for adaptation measures identified under Output 3.1.1 (sectoral adaptation plans and frameworks) and categorize costs by sector and priority.

The project will provide expertise to support the analyse of available funding, mapping existing funding sources, including domestic budgets, international funds, and private sector contributions, and document financial commitments and gaps for each adaptation priority. Funding Gap Analysis will be done to compare available funding with the projected costs of adaptation measures to identify gaps, providing disaggregated findings by sector, geographic region, and beneficiary group. Draft gap analysis will be shared with the FWG for validation and feedback and the analysis based on inputs from stakeholders.

The project will ensure data accuracy by consulting multiple sources and stakeholders and will address potential underreporting of available funding due to fragmented information.  It will also highlight funding needs for vulnerable populations and conflict-affected regions. The outcome of the assessment will be a comprehensive funding gap analysis report, and sectoral and cross-sectoral breakdown of funding gaps.

Activity 3.4.3.1c: Convene three annual one-day workshops for the FWG to review potential funding sources to bridge the funding gaps identified under Activity 3.4.3.1b.

Based on the outcome of the funding analysis to be undertaken in Activity 3.4.3.1c, workshops will be held to review its findings. Each workshop will focus on reviewing funding sources, prioritizing actions, and exploring innovative financing mechanisms. The meeting will gather representatives from international funding agencies, development partners, and private sector investors.  It will facilitate discussions on traditional and innovative funding sources, such as blended finance, public-private partnerships, and green bonds, and document potential funding opportunities and actionable next steps.  Tasks will be assigned to FWG members for pursuing identified funding opportunities and a tracking system developed to monitor progress on funding applications. Workshop reports summarizing discussions, outcomes, and follow-up actions will be generated on prioritized funding opportunities and potential partners.

The workshops will ensure that the FWG remains proactive in mobilizing funds, continuously assessing new opportunities, and tracking funding applications.

Table 18: Activity 3.4.3.1c Training topics, participants and targeted stakeholders.

| Workshop Title | Topics Covered | Estimated Number of Participants (Gender Target: 40% Women, 60% Men) | Length/ Duration | Targeted Stakeholders |
| --- | --- | --- | --- | --- |
| Workshop 1: Mapping Traditional and Emerging Climate Finance Sources | Presentation of funding analysis (Activity 3.4.3.1b); Reviewing traditional adaptation finance sources (Green Climate Fund, Adaptation Fund, Global Environment Facility, bilateral/multilateral donors); Introduction to emerging funding sources (climate bonds, carbon markets, impact investment); Case studies of climate finance mobilization in LDCs. | 35 participants (14 women, 21 men) | 1 day | FWG members, MoPIC, MoF, EPA, CAMA, MoWE, MoAI, MoHP, UNDP, FAO, UNEP, World Bank, private sector, financial institutions. |
| Workshop 2: Innovative Financing Mechanisms for Adaptation in Yemen | Exploring blended finance, public-private partnerships (PPPs), and risk transfer mechanisms (insurance, resilience bonds); Private sector engagement strategies; Mobilizing domestic finance for adaptation; Identifying key sectors for private investment in adaptation (water, agriculture, coastal resilience). | 30 participants (12 women, 18 men) | 1 day | FWG members, MoPIC, MoF, private sector, commercial banks, development banks, investment funds, Chamber of Commerce. |
| Workshop 3: Prioritizing Funding Opportunities and Developing Action Plans | Reviewing and prioritizing adaptation projects with high funding potential; Establishing FWG action plan for securing financing; Assigning tasks to FWG members to pursue funding leads; Developing a funding application tracking system; Engaging stakeholders for project co-financing and partnerships. | 30 participants (12 women, 18 men) | 1 day | FWG members, MoPIC, MoF, sectoral ministries, UN agencies, development partners, financial institutions. |

Activity 3.4.3.1d: Produce a cross-sectoral funding strategy for the NAP process following the gap analysis undertaken under Activity 3.4.3.1b in collaboration with the FWG.

The project will develop a cross-sectoral funding strategy for the NAP process, outlining approaches to mobilize funding, including leveraging domestic resources, accessing international climate finance, and engaging private sector partners and ensuring alignment with sectoral adaptation plans and Yemen’s broader development goals.  It will address cross-sectoral priorities identified in the gap analysis. It will include clear timelines, roles, and responsibilities for implementing the strategy and addressing barriers to accessing international funds, such as capacity constraints and application complexities. It will also highlight co-financing opportunities to maximize resource mobilization.

The finalized strategy will be distributed to relevant ministries, donors, and stakeholders and a launch event organised to promote the strategy and secure buy-in. Communication materials will also be developed, summarizing the strategy for stakeholders.

| Session Title | Topics Covered | Targeted Stakeholders |
| --- | --- | --- |
| Opening Remarks and Presentation of the Cross-Sectoral Funding Strategy | Overview of Yemen’s climate adaptation financing needs; Summary of funding gaps identified under Activity 3.4.3.1b; Presentation of the Cross-Sectoral Funding Strategy, including key approaches and priority areas. | High-level government representatives (MoPIC, MoF, EPA, CAMA, MoWE, MoAI, MoHP), development partners, donors, private sector representatives, UN agencies. |
| Panel Discussion: Challenges and Opportunities in Mobilizing Climate Finance for Yemen | Perspectives from government officials, international donors, private sector, and financial institutions; Key barriers to accessing climate finance and strategies to overcome them; Role of co-financing and innovative financing mechanisms. | Government finance and planning agencies (MoPIC, MoF), international climate finance institutions (GCF, Adaptation Fund, UNDP, World Bank, IMF, regional development banks), private sector investors. |
| Breakout Sessions: Aligning the Funding Strategy with Sectoral Priorities | Sectoral adaptation financing needs (Water, Agriculture, Health, Coastal Zones); Identifying priority funding sources for each sector; Developing action plans to implement the strategy within ministries and organizations. | Sectoral ministries (MoWE, MoAI, MoHP, CAMA, EPA), local government authorities, NGOs, research institutions. |
| Commitments and Next Steps: Partner Engagement for Implementation | Securing government and donor commitments for financing adaptation; Establishing monitoring mechanisms for funding mobilization; Final remarks and call to action for all stakeholders. | Government officials, donors, private sector representatives, CSOs, UN agencies, adaptation finance experts. |

The launch event will raise awareness of the Cross-Sectoral Funding Strategy, fostering stakeholder engagement and investment in Yemen’s adaptation finance. It will help identify co-financing opportunities, align sectoral plans with funding priorities, and secure commitments from government and development partners. This milestone will strengthen coordination and resource mobilization for climate resilience.

Activity 3.4.3.1e: Develop Recommendations for Mainstreaming Sectoral Adaptation Plans into Ministry Budgets

The project will analyze sectoral budgets and adaptation needs by reviewing budgets and planning documents for the Ministries of Water and Environment, Agriculture and Irrigation, and Health and Population. It will identify opportunities to align sectoral adaptation plans with budgetary processes and develop ministry-specific recommendations to integrate adaptation measures into annual planning and financial frameworks.

Recommendations will address challenges such as limited fiscal space, capacity gaps, and competing priorities, ensuring they are practical, context-specific, and prioritize actions with cross-sectoral co-benefits. Draft recommendations will be refined based on feedback from the FWG and ministries. Training and tools will be provided to operationalize the recommendations, with progress monitored and areas for additional support identified.

The project will develop tools to help ministries integrate sectoral adaptation plans into budgeting, ensuring alignment with financial planning. These include sector-specific budgeting guidelines, climate-responsive templates, investment prioritization tools, an adaptation finance tracker, a PPP toolkit, and a coordination framework. Four training workshops will equip 35 government officials (14 women, 21 men) with practical skills to institutionalize climate-responsive budgeting.

| Training Session Title | Topics Covered | Length/Duration | Targeted Stakeholders |
| --- | --- | --- | --- |
| Integrating Adaptation into Budget Planning and Public Financial Management (PFM) | Overview of national budgeting cycles and opportunities for mainstreaming adaptation; Challenges in financing adaptation in Yemen; Adaptation mainstreaming strategies for the water, agriculture, coastal zones, and health sectors. | 2 days | MoF, MoPIC, MoWE, MoAI, MoHP, EPA, local government finance representatives. |
| Climate-Responsive Budgeting Tools and Expenditure Tracking | Introduction to adaptation finance tracking; Budget classification for adaptation-related expenditures; Use of climate-responsive budgeting templates and sector-specific guidelines. | 2 days | MoF, MoPIC, sectoral ministries (Water, Agriculture, Health), CSOs, local government finance officials. |
| Prioritizing Adaptation Investments and Cost-Benefit Analysis (CBA) for Budgeting | Application of cost-benefit analysis (CBA) and multi-criteria decision analysis (MCDA) for adaptation investments; Sectoral investment prioritization methodologies; Case studies on adaptation budgeting best practices. | 3 days | MoF, MoPIC, MoWE, MoAI, MoHP, FWG members, adaptation finance experts. |
| Exploring Innovative Financing Mechanisms for Adaptation (PPPs, Co-Financing, Blended Finance) | Introduction to adaptation financing mechanisms beyond government budgets; Public-private partnerships (PPPs) for adaptation; Co-financing models and leveraging international climate finance. | 2 days | MoF, MoPIC, private sector investors, international financial institutions, development banks. |

Partnerships:

Establishing and leveraging effective, sustainable partnerships is a crucial element of the project, enhancing its impact across all sectors and involving various stakeholders. The proposed action will be based on broad stakeholder participation with respective communication and cooperation platforms and mechanisms in place. Actors for collaboration will include national and sub-national level state bodies, research organizations, including finance and technical experts, civil society organizations, private sector, vulnerable populations and gender groups.

Furthermore, this project will align its efforts with ongoing international projects. Synergies will be harnessed in producing relevant climate data and information, facilitating knowledge management, and fostering dialogues on climate risks and vulnerabilities at both national and regional levels. The project will actively advocate for unified communication strategies in building climate resilience and explore opportunities for collaborative capacity development. Additionally, the project will tap into the potential for cross-sectoral and cross-border cooperation on adaptation.

Risks:

Please refer to Annex E for a comprehensive overview of risk management, as detailed in the Risk Log. In accordance with standard UNDP protocols, the Project Manager will conduct quarterly monitoring of risks and report on their status to the UNDP Country Office. Progress will be documented in the UNDP Quantum risk log. Risks will be classified as critical when both impact and probability are deemed high. Management responses to critical risks will be incorporated into the Annual Project Reports. The project's overall risk categorization is estimated as low due to its exclusive focus on technical assistance for building the capacities of stakeholders, with no involvement in field activities.

Gender equality and Women’s Empowerment:

Yemen’s population is highly vulnerable to climate change, with women, children, the elderly, people with disabilities, marginalized ethnic groups, and displaced populations facing disproportionate risks due to deep-seated gender and social inequalities. The patriarchal societal structure, ongoing conflict, and economic collapse exacerbate these vulnerabilities. Women’s restricted access to resources like land, financial services, and technology limits their adaptive capacity. Socially excluded groups, such as the Muhamasheen (Akhdam), non-Muslim minorities, and Indigenous pastoralists, face systemic discrimination that impedes their participation in adaptation efforts and access to necessary support.

In Yemen, conflict, the lingering impacts of the COVID-19 pandemic, impacts of climate change have all worsened vulnerabilities for women and girls, deepening inequalities, especially for disabled, displaced, and vulnerable groups. There is significant gender-based inequalities that are reflected in its major development indices. In 2020, Yemen was ranked 155th out of 156 countries in the World Economic Forum’s Global Gender Gap Index, depicting considerable gender disparities . Furthermore, the overlapping and compounding impacts of the crisis, climate change, and the COVID-19 pandemic have severely hindered progress towards the 2030 Agenda, escalating both humanitarian and development needs. This has made it challenging to secure essential funding. In 2021/2022, the Humanitarian Development Index ranked Yemen as the 183rd out of 191 countries, with a score of 0.455 .  Yemeni women remain severely underrepresented in leadership roles, holding only 4.1% of the managerial and decision-making positions, and play minimal roles in peace agreements.

Gender inequality in Yemen leads to restricted movement, early marriage, little to no means to adapt to climate change, and gender-based violence. Women’s workforce participation in the country is only 6%, and structural barriers limit their access to education and basic services.  Key vulnerabilities include women and girls being overburdened by household responsibilities exacerbated by climate-induced water scarcity, food insecurity, and health crises.  Children, elderly, and disabled individuals with limited mobility and weaker health which increases their vulnerability to malnutrition, waterborne diseases, and extreme weather events. Marginalized communities including nomadic and semi-nomadic populations, non-Muslims, and the Muhamasheen experience exclusion from policy discussions and adaptation programs. Internally displaced persons (IDPs) face heightened exposure to climate risks in overcrowded camps with limited resources and poor infrastructure. Climate impact exposure to sensitive sectors such as agriculture has further impacted women negatively, where women are highly represented. In Yemen, employment in the agricultural sector, with most working as contributing family workers, is estimated at 88.1% . Although women have the right to own land, possess, use, manage, and dispose of property, the laws in Yemen are often not effectively implemented in practice. As a result, women frequently face limited access to land ownership, further affecting their abilities to adapt to the impacts of climate change .

The impacts of climate change are exacerbating the vulnerabilities in Yemen, especially those linked to socio-economic challenges. As of 2023, 12.57% of employed women and 14.23% of men aged 15 and older live below the poverty line, reflecting deep economic disparities. These challenges are worsened by climate change, which negatively impacts agriculture, the main livelihood for many women in Yemen. The adolescent fertility rate, at 52 births per 1,000 girls aged 15-19 in 2022, has decreased but still reflects limited access to family planning and economic opportunities, both of which are crucial in adapting to climate-induced disruptions. Access to financial services, such as bank accounts or mobile money, is limited: only 5.4% of women and 18.4% of men have access, with a gender gap of 12.9, which is smaller than the regional average. Improving financial inclusion is essential for enabling climate adaptation strategies. In 2023, women held 0% of seats in Yemen’s national parliament, highlighting a lack of political representation and leadership in decision-making on climate-related issues. The labor force participation rate is starkly different between genders: 5.1% for women compared to 60.4% for men, emphasizing the need for more inclusive policies to enhance women’s resilience to climate change .

Women who are internally displaced face increased vulnerabilities amid ongoing crises and climate impacts in Yemen. It is estimated that three-quarters of the 4.5 million displaced people in Yemen are women and children, where around 26% of displaced households are headed by women . The damage to infrastructure and restricted access to basic services have worsened their hardship. In many shelters, the lack of proper sanitation facilities and unsafe conditions in displacement camps elevate the risk of gender-based violence, while limited access to protection and support services leaves these women even more exposed. The NAP project provides an opportunity to address these gender and social inclusion gaps through targeted and inclusive climate adaptation measures.  The project will mainstream gender and social inclusion into key sectoral policies and strategies, and it will ensure that humanitarian response and recovery frameworks are climate risk-informed, which will ensure that the above vulnerabilities are addressed within Yemen’s long-term adaptation planning framework. In addition, the project will directly address some of these vulnerabilities through interventions including developing and providing women and girls with training programs on climate-resilient practices, such as drought-resistant agriculture and water-saving techniques, tailored to women’s roles in household and community management; offering financial literacy programs and improve access to credit for women to support climate-resilient investments; design vocational training for youth in sectors like resilient agriculture, and coastal conservation; identify disaster preparedness and response training needs for caregivers of children, the elderly, and disabled individuals.

South-South and Triangular Cooperation (SSTrC):

The project will ensure interaction, communication, and the exchange of experiences, best practices, and lessons learned with other climate change adaptation projects implemented by UNDP and other donors in the region and beyond. It is also expected that representatives from other countries will have the opportunity to meet during the project's implementation to share their experiences, best practices, and collaborate on activities. There is a high potential for replicating the project's approaches and lessons learned in the region. The project will also explore opportunities for the meaningful participation of national partners in relevant regional and global forums. Innovative knowledge products, such as improved methodologies for climate risk and impact assessments and lessons learned from piloting adaptation planning at sub-national level, produced by the project, will be disseminated via global platforms.

Innovativeness, Sustainability and Potential for Scaling Up:

The project's impact sustainability is assured through its primary focus on capacity development, specifically centered on generating, managing, and utilizing climate information within well-established institutions. This capacity will be supported and institutionalized through the development of methodological tools and regulatory mechanisms, including budgeting and Monitoring & Evaluation (M&E) procedures, ensuring the integration of climate services at national and sub-national levels by both state institutions and private sector entities. Additionally, two GCF-funded project concept notes are anticipated to sustain and expand the initiatives initiated by this project.

# Project Results Framework

This project will contribute to the following Sustainable Development Goal (s): SDG 13: Take urgent action to combat climate change and its impacts, SDG 6: Clean Water and Sanitation, SDG 2: Zero Hunger, SDG 3: Good Health and Well-being, SDG 14: Life below water, SDG 15: Life on land, SDG 5: Gender equality, SGD 1: No poverty, SDG 11: Sustainable cities and communities, and SDG 17: Partnerships for the goals.

This project will contribute to the following country outcome included in the UNDAF/Country Programme Document: Outcome 1: By 2025, people in Yemen, especially women, adolescents and girls and those in the most vulnerable and marginalized communities benefit from better, equal and inclusive access to nutritious food, sustainable and resilient livelihoods and environmental stability

This project will be linked to the following output of the UNDP Strategic Plan: 2.3.1 Data and risk-informed development policies, plans, systems and financing incorporate integrated and gender-responsive solutions to reduce disaster risks, enable climate change adaptation and mitigation, and prevent risk of conflict

# Monitoring and Evaluation (M&E) Plan

The project results as outlined in the project results framework will be monitored and reported annually and evaluated periodically during project implementation to ensure the project effectively achieves these results.

Project-level monitoring and evaluation will be undertaken in compliance with UNDP requirements as outlined in the UNDP POPP and UNDP Evaluation Policy. The UNDP Country Office is responsible for ensuring full compliance with all UNDP project monitoring, quality assurance, risk management, and evaluation requirements. Additional M&E requirements will be undertaken in accordance with the GCF initial approach to monitoring and evaluation policy and other relevant GCF policies.

In addition to these mandatory UNDP and GCF M&E requirements, other M&E activities deemed necessary to support project-level adaptive management will be agreed during the Project Inception Workshop and will be detailed in the Inception Report.

M&E oversight and monitoring responsibilities:

Project Manager:  The Project Manager is responsible for day-to-day project management and regular monitoring of project results and risks, including social and environmental risks. The Project Manager will ensure that all project staff maintain a high level of transparency, responsibility and accountability in M&E and reporting of project results. The Project Manager will inform the Project Board, the UNDP Country Office and the UNDP-Climate Hub Regional Technical Advisor of any delays or difficulties as they arise during implementation so that appropriate support and corrective measures can be adopted.

The Project Manager will develop annual work plans to support the efficient implementation of the project. The Project Manager will ensure that the standard UNDP and GCF M&E requirements are fulfilled to the highest quality. This includes, but is not limited to, ensuring the results framework indicators are monitored annually in time for evidence-based reporting in the Annual Project Report, and that the monitoring of risks occurs on a regular basis.

Project Board:  The Project Board will take corrective action as needed to ensure the project achieves the desired results. The Project Board will hold project reviews to assess the performance of the project and appraise the Annual Work Plan for the following year. In the project’s final year, the Project Board will hold an end-of-project review to capture lessons learned and discuss opportunities for scaling up and to highlight project results and lessons learned with relevant audiences. This final review meeting will also discuss the findings outlined in the project completion report.

Project Implementing Partner: UNDP will initiate and organize key M&E activities including the Annual Project Report and the end-of-project workshop and report. UNDP will also ensure that the standard UNDP and GCF M&E requirements are fulfilled to the highest quality. The UNDP CO, as the Implementing Partner for the project, is responsible for providing all required information and data necessary for timely, comprehensive and evidence-based project reporting, including results and financial data, as necessary and appropriate. The UNDP CO will strive to ensure project-level M&E is undertaken effectively and is aligned with national systems so that the data used by and generated by the project supports national systems.

UNDP Country Office:  The UNDP Country Office will support the Project Manager as needed, including through annual supervision missions. The annual supervision missions will take place according to the schedule outlined in the annual work plan. Supervision mission reports will be circulated to the project team and Project Board within one month of the mission. The UNDP Country Office will initiate and organize key M&E activities including the Annual Project Report, project final assessment. The UNDP Country Office will also ensure that the standard UNDP and GCF M&E requirements are fulfilled to the highest quality.

The UNDP Country Office is responsible for complying with all UNDP project-level M&E requirements as outlined in the UNDP POPP. This includes ensuring the UNDP Quality Assurance Assessment during implementation is undertaken annually; the regular updating of the Quantum risk log; and, the updating of the UNDP gender marker on an annual basis based on gender mainstreaming progress reported in the Annual Project Report and the UNDP ROAR. Any quality concerns flagged during these M&E activities (e.g. Annual Project Report quality assessment ratings) must be addressed by the UNDP Country Office and the Project Manager.

The UNDP Country Office will support GCF staff (or their designate) during any missions undertaken in the country and support any ad-hoc checks or ex post evaluations that may be required by the GCF.

The UNDP Country Office will retain all project records for this project for up to seven years after project financial closure in order to support any ex-post reviews and evaluations undertaken by the UNDP Independent Evaluation Office (IEO) and/or the GCF.

UNDP - Climate Hub:  Additional M&E and implementation oversight, quality assurance and troubleshooting support will be provided by the UNDP-Climate Hub Regional Technical Advisor and the UNDP-VF Oversight and Compliance Unit as needed.

Additional GCF monitoring and reporting requirements:

Inception Workshop and Report:  A project inception workshop will:

a) Re-orient project stakeholders to the project strategy and discuss any changes in the overall context that influence project strategy and implementation;

b) Discuss the roles and responsibilities of the project team, including reporting and communication lines and conflict resolution mechanisms;

c) Review the results framework and finalize the indicators, means of verification and monitoring plan;

d) Discuss reporting, monitoring and evaluation roles and responsibilities and finalize the M&E budget; identify national/regional institutes to be involved in project-level M&E;

e) Identify how project M&E can support national monitoring of SDG indicators as relevant;

f) Update and review responsibilities for monitoring the various project plans and strategies, including the risk log;

g) Review financial reporting procedures and mandatory requirements, and agree on the arrangements for the periodic audit; and

h) Plan and schedule Project Board meetings and finalize the first-year annual work plan.

The Project Manager will prepare the inception workshop report no later than one month after the inception workshop. The inception report will be cleared by the UNDP Country Office and the UNDP- Climate Hub Regional Technical Adviser and approved by the Project Board.

The inception report will be cleared by the UNDP Country Office and the UNDP-Climate Hub Regional Technical Adviser and approved by the Project Board.

GCF Annual Project Report (due no later than 60 days following and 31 December for each year of project implementation):  The Project Manager, the UNDP Country Office, and the UNDP-Climate Hub Regional Technical Advisor will provide objective input to the annual project reports covering the 6 months in the calendar year for each year of project implementation. The Project Manager will ensure that the indicators included in the project results framework are monitored annually in advance so that progress can be included in the report.

The Annual Project Report will also be shared with the Project Board. The UNDP Country Office will coordinate the inputs of other stakeholders to the report as appropriate. The quality rating of the previous year’s report will be used to inform the preparation of the subsequent report.

Lessons learned and knowledge generation: Results from the project will be disseminated within and beyond the project intervention area through existing information sharing networks and forums. The project will identify and participate, as relevant and appropriate, in scientific, policy-based and/or any other networks, which may be of benefit to the project. The project will identify, analyse and share lessons learned that might be beneficial to the design and implementation of similar projects and disseminate these lessons widely. There will be continuous information exchange between this project and other projects of similar focus in the same country, region and globally.

Project Completion Report: The project’s Completion Report along with the final budget and expenditure report will serve as the final project report package. The final project report package shall be discussed with the Project Board during an end-of-project review meeting to discuss lessons learned and opportunities for scaling up.

Intellectual Property Rights: To accord acknowledgement to the GCF for providing grant funding, the GCF logo will appear together with the UNDP logo on all promotional materials, other written materials like publications developed by the project, and project hardware. Any citation on publications regarding projects funded by the GCF will also accord proper acknowledgement to the GCF. Information will be disclosed in accordance with relevant policies notably the UNDP Disclosure Policy and the relevant GCF policy. See also GCF Branding Guidelines.

Mandatory GCF M&E Requirements and M&E Budget:

| GCF M&E requirements | Primary responsibility | Indicative costs to be charged to the Project Budget (US$) |  | Time frame |
| --- | --- | --- | --- | --- |
|  |  | GCF grant | Co-financing |  |
| Inception Workshop | UNDP Country Office | 5,000 | None | Q2 Y1 |
| Inception Report and baseline assessments | Project Manager | None | None | Add date |
| Standard UNDP monitoring and reporting requirements as outlined in the UNDP POPP | UNDP Country Office | None | None | Annually |
| Risk management (including Quantum Risk logs) | Project Manager Country Office | None | None | Quarterly, annually |
| Monitoring of indicators in project results framework (including hiring of external experts, project surveys, data analysis etc…) | Project Manager | None | None | Annually |
| GCF Annual Project Report | Project Manager and UNDP Country Office and UNDP- Climate Hub Unit | None | None | Annually as per FA |
| Lessons learned, case studies, and knowledge generation | Project Manager | None | add | Annually |
| Project Board meetings | Project Board UNDP Country Office Project Manager | None | None | At minimum annually |
| Supervision missions | UNDP Country Office | None | None | Two per year |
| Oversight missions | UNDP- Climate Hub Unit | None6 | None | Troubleshooting as needed |
| GCF learning missions/site visits | UNDP Country Office and Project Manager and UNDP- Climate Hub Unit | None | None | To be determined. |
| End-of-project review workshop | UNDP Country Office and Project team and UNDP- Climate Hub Unit | 10,000 | None | Q4 Y3 |
| Translation of reports into English | UNDP Country Office | None | None | As required. GCF will only accept reports in English. |
| TOTAL indicative COST Excluding project team staff time, and UNDP staff and travel expenses |  | USD 15,000 | None |  |

# Governance and Management Arrangements

This proposal shall be governed by the terms and conditions set forth in the Second Amended and Restated Framework Readiness and Preparatory Support Grant Agreement agreed between GCF and UNDP dated 22 July 2020.

The implementation period for the Proposal approved following the date of the Second Amended Framework Agreement means the period beginning from the date  that the Fund notifies  the Applicant, the Beneficiary and the Delivery Partner that it has approved the Proposal, and ending three (3) months after the expiration of the anticipated duration of the relevant Readiness and Preparatory Support specified in such Approved R&P Support Proposal, including any extensions approved by the Fund.

Roles and responsibilities of the project’s governance mechanism:

The project will be implemented following UNDP’s direct implementation modality, in accordance with the terms of conditions set forth in the Second Amended Readiness and Preparatory Support Grant Framework agreement between UNDP and the GCF, effective as of 17 August 2020.

Implementing Partner: The Implementing Partner for this project is UNDP. UNDP, through the CO, is therefore responsible and accountable for managing this project, including the monitoring and evaluation of project interventions, achieving project outcomes, and for the effective use of UNDP resources. UNDP is responsible for:

- Approving and signing the multiyear workplan;

- Approving and signing the combined delivery report at the end of the year; and,

- Signing the financial report or the funding authorization and certificate of expenditures.

A strict firewall will be maintained between project oversight costs and personnel and implementation of the project costs and personnel.

The project organisation structure is as follows:

Figure 1: Project Organization Structure

The UNDP Resident Representative assumes full responsibility and accountability for oversight and quality assurance of this Project and ensures its timely implementation in compliance with the GCF-specific requirements and UNDP’s Programme and Operations Policies and Procedures (POPP), its Financial Regulations and Rules and Internal Control Framework. A representative of the UNDP Country Office will assume the assurance role and will present assurance findings to the Project Board, and therefore attend Project Board meetings as a non-voting member.

Roles and Responsibilities of the Project Organisation Structure:

- Project Steering Committee

The Project Steering Committee is the senior oversight body for the project. It includes representatives from all the line ministries and sectors. The committee will meet at least twice a year to guide project execution and address strategic risks.

Roles and Responsibilities:

- Provide overall strategic guidance and direction for the project.

- Approve annual workplans, and key deliverables.

- Review project progress and advise on necessary revisions or risk mitigation strategies.

- Ensure the project remains on track to achieve its objectives within approved constraints.

- Facilitate decision-making on project changes through appropriate revisions.

- NAP Coordination Unit

The NAP Coordination Unit comprises the Climate Change Unit within the Ministry of Water and Environment (MWE) and the UNDP Climate Change Unit. This unit is central to the implementation, coordination, and monitoring of the project.

Roles and Responsibilities:

- Coordinate the overall execution of project activities and ensure alignment with national adaptation priorities.

- Provide quality assurance of outputs and facilitate reporting to the Project Steering Committee and GCF.

- Supervise and support the Project Management Unit (PMU) in the delivery of project results.

- Oversee technical and financial deliverables and ensure that all reports meet the GCF's quality standards.

- Facilitate stakeholder engagement, including national consultations, workshops, and capacity-building activities.

- Validate project deliverables with relevant stakeholders and ensure compliance with quality standards.

- Support the integration of project outputs into national and sectoral climate strategies.

The Climate Change Unit team from MWE will provide strategic guidance and ensure government ownership, while the UNDP Climate Change Unit will offer technical expertise and operational support.

- Delivery Partner (UNDP)

UNDP, as the Delivery Partner, will be responsible for implementing the readiness activities under this project. The Government of Yemen has appointed UNDP as its Delivery Partner for the third phase of the readiness program to ensure the continuity and sustainability of activities and the expert team.

Roles and Responsibilities:

- Conduct fiduciary and financial management, procurement of goods and services, and monitoring and reporting activities as per UNDP policies and procedures.

- Provide financial and technical oversight services for all project outcomes and outputs.

- Facilitate recruitment of project staff and consultants, including contracting, travel arrangements, and organization of workshops.

- Delegate spending authority to the UNDP Country Office (CO) while maintaining oversight through the UNDP-GEF/GCF Global Readiness Coordinator.

- Ensure that monitoring, evaluation, and reporting comply with GCF and UNDP requirements.

- Oversee risk mitigation strategies and ensure project compliance with the UN Security Council Committee resolution 1267 (1999).

- Day-to-day management of the project will be undertaken by the UNDP Country Office in close coordination with the NDA within the NAP Coordination Unit.

- National Designated Authority (NDA)

The Ministry of Water and Environment (MWE) serves as Yemen's NDA for the GCF and is the direct beneficiary of the readiness grant.

Roles and Responsibilities:

- Guide and approve GCF priorities in Yemen, including project implementation strategies.

- Facilitate meetings and access to data, ensuring coordination among stakeholders.

- Provide technical feedback and final approval on terms of reference (ToRs) for hiring consultants and validate project deliverables.

- Facilitate workshops and consultations and involvement of the relevant stakeholders in all the project activities

- Ensure country ownership of the project and alignment with national policies and priorities.

- Project Management Unit (PMU)

Implementation will be done under the overall management of the Project Manager. The PMU will report to the Project Board and the Team Leader for Climate Change and Environment in accordance with UNDP rules and regulations. Services provided by the PMU include, inter alia, support to recruitment and contracting of project management and technical staff; procurement of goods and services for project inputs; developing Annual Work Plans; support for budget and financial management, among others. The PMU will comprise of a Project Manager and a Project Associate.

Roles and Responsibilities:

  - Oversee the day-to-day implementation of project activities.

  - Provide interim report including the budget & expenditure reporting and procurement plan for the project.

  - Identify relevant stakeholders to participate in project activities in coordination with the NAP Coordination Unit

  - Develop and approve the TORs (technically cleared by NDA) for consultants to be hired to carry out technical assessments under the project.

- Conduct regular meetings with stakeholders and local consultants including coordination of all relevant meetings

- Beneficiaries and Supporting Stakeholders

The project engages a diverse set of stakeholders, including:

- Line Ministries: Support integration of climate adaptation measures into national and sectoral strategies.

- Civil Society Organizations (CSOs): Represent vulnerable groups and ensure local needs are reflected in adaptation planning.

- Academia: Contribute to research and capacity-building initiatives.

- Women and Youth Groups: Ensure inclusivity and gender-sensitive adaptation measures.

Project Manager: The Project Manager has the authority to run the project on a day-to-day basis on behalf of the Project Board within the constraints laid down by the Board. The Project Manager is responsible for day-to-day management and decision-making for the project. The Project Manager’s prime responsibility is to ensure that the project produces the results specified in the project document, to the required standard of quality and within the specified constraints of time and cost. The Delivery Partner appoints the Project Manager, who should be different from the Delivery  Partner’s representative in the Project Board.

Specific responsibilities include:

- Ensure proper management of project implementation, personnel and engaged experts by top-quality management of project activities, outputs, expenditures and budgetary status of the project.

- Work closely with relevant project personnel, supervising and backstopping their activities, the use of project funds and timely delivery of quality results.

- Ensure timely preparation and top-quality of regular and ad-hoc project reports, and that monitoring, and evaluation of the project is conducted in accordance to donor requirements and UNDP rules and procedures.

- Provide policy advice on key issues in the area of climate change adaptation.

- Identify, collect and analyse policy-related, relevant information and data.

- Codify and provide best practices and lessons learnt, particularly linked to the areas of capacity development and national (economic, social and human) development.

- Assist in engaging the government in constructive dialogue on the achievement of Project outcomes.

- Maintain continuous dialogue and coordination with national partners regarding the implementation of projects activities,

- Contribute to visibility of project results to relevant national and international stakeholders and audiences.

- Build partnerships with various governmental agencies, international organizations, banks, the private sector and civil society with a view to creating a platform for support to the Government of Serbia.

Project Associate who supports the project manager in the day-to-day management of the project, including for providing logistical and general administrative support, preparing documentation for the recruitment of consultants and contractual aspects of the project, and tracking and monitoring the project expenditures.

Specific responsibilities include:

- Provide support to project implementation, support the day-to-day project activities.

- Provide inputs for development of project monitoring and evaluation framework.

- Assist in preparing work plans and project reports.

- Identify and collect policy-related and other relevant information, documents and data, compile and analyse data for further use in project management.

- Support organization and coordination of meetings, training sessions, workshops, conferences, and project events and prepare reports and meeting minutes, as required.

- Draft terms of reference for consultants and contractors, as required, prepare briefs, talking points and relevant communication materials, draft correspondence on project issues, as required.

- Establish and maintain project filing system, incoming and outgoing correspondence and maintain calendar of events.

- Follow up with (sub)contractors to ensure time delivery of outputs.

- Maintain cooperation and communication with project’s partners and beneficiaries on the implementation of the agreed activities, especially for the events, trainings, workshops, etc.

- Facilitate knowledge building and knowledge sharing within the project team.

- Participate in recruitment and evaluation panels, as required.

- Support in managing project finances, processing invoices, and ensuring tax exemption for project related goods and services.

- Support procurement processes, provide inputs for request for quotations/proposals, prepare tenders and small procurements (canvassing), provide inputs for UNDP procurement plan.

- Support recruitment of short-term consultants in line with rules and regulations

- Assist project teams, experts and consultants on travel and logistics matters.

- Ensure full compliance of activities with UNDP rules, regulations, and policies.

Project Assurance: UNDP provides a three–tier oversight and quality assurance role involving UNDP staff in Country Offices and at regional and headquarters levels. For the CO level, the project assurance role will be played by the team leader, with the RTA and the UNDP-Climate Hub NY team at regional and NY levels respectively. The quality assurance role supports the Project Board by carrying out objective and independent project oversight and monitoring functions. This role ensures appropriate project management milestones are managed and completed. Project Assurance must be independent of the Project Management function; the Project Board cannot delegate any of its quality assurance responsibilities to the Project Manager.  The project assurance role is covered by the delivery partner fee provided by the GCF. As an Accredited Entity to the GCF, UNDP is required to deliver GCF-specific oversight and quality assurance services including: (i) Day-to-day oversight supervision, (ii) Oversight of project completion, (iii) Oversight of project reporting. Therefore, UNDP- Climate Hub Unit will provide technical advisory services to country under the GCF NAP projects; guide and review country activities focused on stocktaking of on-going and completed initiatives of relevance to informing and contributing to the national adaptation plans process; and provide timely quality information and technical advice on policies, priorities and activities for GCF funded NAP and related projects.

As a Delivery Partner to the GCF, UNDP delivers the following GCF-specific oversight and quality assurance services: (i) day to day project oversight supervision covering the start-up and implementation; (ii) oversight of project completion; and (iii) oversight of project reporting. A detailed list of the services is presented in the table below.

| Function | Detailed description of activity | Typical GCF fee breakdown |
| --- | --- | --- |
| Day-to-day oversight supervision | - Project start-up: - In the case of readiness proposals, if needed assist the NDA and/or government partners prepare all the necessary documentation for approval of a readiness grant proposal - Prepare the Project Document with the government counterparts - Technical and financial clearance for the Project Document - Organize Local Project Appraisal Committee - Project document signature - Ensure quick project start and first disbursement - Hire project management unit staff - Coordinate/prepare the project inception workshop - Oversee finalization of the project inception workshop report - Project implementation: - Project Board: Coordinate/prepare/attend annual Project Board Meetings - Annual work plans: Quality assurance of annual work plans prepared by the project team; issue UNDP annual work plan; strict monitoring of the implementation of the work plan and the project timetable according to the approved readiness proposal - Prepare GCF/UNDP annual project report: review input provided by Project Manager/team; provide specialized technical support and complete required sections - Portfolio Report (readiness): Prepare and review a Portfolio Report of all readiness activities done by UNDP in line with Clause 9.02 of the FWA. - Procurement plan: Monitor the implementation of the project procurement plan - Supervision missions: Participate in and support in-country GCF visits/learning mission/site visits; conduct annual supervision/oversight site missions - Risk management and troubleshooting: Ensure that risks are properly managed, and that the risk log in Quantum (UNDP financial management system) is regularly updated; Troubleshooting project missions from the regional technical advisors or management and programme support unit staff as and when necessary (i.e. high risk, slow performing projects) - Project budget: Provide quality assurance of project budget and financial transactions according to UNDP and GCF policies - Performance management of staff: where UNDP supervises or co-supervises project staff - Corporate level policy functions: Overall fiduciary and financial policies, accountability and oversight; Treasury Functions including banking information and arrangements and cash management; Travel services, asset management, and procurement policies and support; Management and oversight of the audit exercise for all GCF projects; Information Systems and Technology provision, maintenance and support; Legal advice and contracting/procurement support policy advice; Strategic Human Resources Management and related entitlement administration; Office of Audit and Investigations oversight/investigations into allegations of misconduct, corruption, wrongdoing and fraud; and social and environmental compliance unit and grievance mechanism. | 70% |
| Oversight of project completion | - Initiate, coordinate, finalize the Project Completion Report, Final Independent Evaluation Report and management response - Quality assurance of final evaluation report and management response - Independent Evaluation Office assessment of final evaluation reports; evaluation guidance and standard setting - Quality assurance of final cumulative budget implementation and reporting to the GCF - Return of any un-spent GCF resources to the GCF | 10% |
| Oversight of project reporting | - Technical review of project reports: quality assurance and technical inputs in relevant project reports - Quality assurance of the GCF annual project interim progress reports and portfolio reports - Preparation and certification of UNDP annual financial statements and donor reports - Prepare and submit fund specific financial reports | 20% |
|  | TOTAL | 100% |

Changes to the Approved R&P Support Proposal: Any modification or proposed changes to the approved readiness proposal which could reasonably constitute a major change shall require prior approval of the GCF. Prior to a final Project Board decision to approve and effect such modifications or proposed changes, UNDP will inform the GCF in writing and seek the GCF’s instructions on the necessary steps to effect such changes. Upon GCF approval, these changes would be signed by the Delivery Partner, the GCF and the NDA.

Project Extension: The UNDP-VF Executive Coordinator must approve all project extension requests. Note that all extensions incur costs and the GCF project budget cannot be increased. A single extension may be granted on an exceptional basis and only if the following conditions are met: one extension only for a project for a maximum of six months; the project management costs during the extension period must remain within the originally approved amount, and any increase in PMC costs will need to be covered by non-GCF resources; the UNDP Country Office oversight costs during the extension period must be covered by non-GCF resources.

Agreement on Intellectual Property Rights and use of logo on the project’s deliverables and disclosure of information: To accord proper acknowledgement to the GCF for providing grant funding, the GCF logo will appear together with the UNDP logo on all promotional materials, other written materials like publications developed by the project, and project hardware. Any citation on publications regarding projects funded by the GCF will also accord proper acknowledgement to the GCF. Information will be disclosed in accordance with relevant policies notably the UNDP Disclosure Policy and the relevant GCF policy. See also GCF Branding Guidelines.

Disclosure of information: Information will be disclosed in accordance with relevant policies notably the UNDP Disclosure Policy and the GCF Disclosure Policy.

# Financial Planning and Management

The total cost of the project is USD 2,672,800.00. This is financed through a GCF grant. UNDP, as the GCF Delivery Partner, is responsible for the oversight and quality assurance of the execution of GCF resources.

GCF Disbursement schedule: GCF grant funds will be disbursed in accordance with the terms and conditions set out in the Second Amended and Restated Framework Readiness and Preparatory Support Grant Agreement. The Country Office will submit an annual work plan to the UNDP- Climate Hub Unit and comply with the GCF milestones in order for the next tranche of project funds to be released. All efforts must be made to achieve 80% delivery annually.

Disbursement requests will be managed at portfolio level by UNDP-VF Hub MPSU in NY, as agreed in the Second Amended and Restated Framework Readiness and Preparatory Support Grant Agreement” between GCF and UNDP. Under Clause 4 of said Second Amended and Restated Framework Readiness and Preparatory Support Grant Agreement, the Delivery Partner shall be required, when submitting Requests for Disbursement, to provide confirmation or evidence that at least 70% of the aggregate amounts previously disbursed by GCF have been committed and/or expended for Eligible Expenditures.

An Indicative Disbursement Schedule is provided below for reference.

| Month | 12 months | 24 months | 36 months | 48 months |
| --- | --- | --- | --- | --- |
| Amount in USD | 807,882.50 | 973,262.50 | 613,242.50 | 278,412.50 |
| Total Project Outcomes in USD | 2,672,800.00 |  |  |  |
| DP Fee in USD | 227,188.00 |  |  |  |
| Total Project Budget in USD | $2,899,988.00 |  |  |  |

Budget Revision and Tolerance:  20% of the total overall projected costs can be reallocated among outcomes. No changes are allowed in the PMC. Any budget reallocation involving a major change in the project’s scope, structure, design or objectives or any other change that substantially alters the purpose or benefit of the project requires the GCF’s prior written consent.

As outlined in the UNDP POPP, the project board will agree on a budget tolerance level for each plan under the overall annual work plan allowing the project manager to expend up to the tolerance level beyond the approved project budget amount for the year without requiring a revision from the Project Board (within the GCF requirements noted above). Should such deviation occur, the Project Manager and UNDP Country office will seek the approval of the UNDP-Climate Hub.

Any over expenditure incurred beyond the available GCF grant amount will be absorbed by the Country Office using non-GCF resources (e.g. UNDP TRAC or cash co-financing).

Audit: The project will be audited according to UNDP Financial Regulations and Rules and applicable audit policies on DIM implemented projects. Upon request, project audit reports (s) will be shared with the GCF (the donor).

Refund to GCF:  Unspent GCF resources must be returned to the GCF.  Should a refund of unspent funds to the GCF be necessary, this will be managed directly by the UNDP-VF Unit in New York.

Project Closure: Project closure will be conducted as per UNDP requirements outlined in the UNDP POPP. On an exceptional basis only, a no-cost extension beyond the initial duration of the project will be sought from in-country UNDP colleagues and then the UNDP-VF Executive Coordinator.

Operational completion: The project will be operationally completed when the last UNDP-financed inputs have been provided and the related activities have been completed. This includes the final clearance of the end-of-project review Project Board meeting. The UNDP CO through a Project Board decision will notify the UNDP  Climate Hub when operational closure has been completed.

Transfer or disposal of assets: In consultation with the other parties of the project, UNDP programme manager (UNDP Resident Representative) is responsible for deciding on the transfer or other disposal of assets. Transfer or disposal of assets is recommended to be reviewed and endorsed by the project board following UNDP rules and regulations. Assets may be transferred to the government for project activities managed by a national institution at any time during the life of a project. In all cases of transfer, a transfer document must be prepared and kept on file.

Financial completion: The project will be financially closed when the following conditions have been met: a) The project is operationally completed or has been cancelled; b) UNDP CO has closed the accounts for the project; d) UNDP CO has certified a final Combined Delivery Report (which serves as final budget revision).

The project is required to be financially completed within 6 months of operational closure or after the date of cancellation. Between operational and financial closure, the UNDP CO will identify and settle all financial obligations and prepare a final expenditure report. The UNDP Country Office will send the final signed closure documents including confirmation of final cumulative expenditure and unspent balance to the UNDP-VF Unit for confirmation before the project will be financially closed in Quantum by the UNDP Country Office.

# Total Budget and Work Plan

| Total Budget and Work Plan |  |  |  |
| --- | --- | --- | --- |
| Quantum Award ID: | 1390392 | Quantum Output Project ID: | 01004504 |
| Quantum Proposal or Award Title: | PIMS 10103 Yemen GCF NAP Readiness |  |  |
| Quantum Business Unit | YEM10 |  |  |
| Quantum Primary Output Project Title: | Building Capacity for the National Adaptation Planning Process in Yemen |  |  |
| UNDP-GCF PIMS No. | 10103 |  |  |
| Implementing Partner | UNDP |  |  |

| Quantum Output (GCF Outcome) | Quantum Activity | Quantum Responsible Party | Quantum Fund ID | Quantum Donor ID | Quantum Budgetary Account Code | Quantum Budget Account Description | Amount Year 1 (USD) | Amount Year 2 (USD) | Amount Year 3 (USD) | Amount Year 4 (USD) | Total (USD) | Budget Note |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | (GCF Output) |  |  |  |  |  |  |  |  |  |  |  |
| Outcome 3.1: Adaptation planning governance and institutional coordination strengthened | Output 3.1.1 National, sub-national and/or sectoral adaptation plans developed or updated | UNDP | 66001 | 12526 | 71200 | Consultant - Individual - International | 16,850.00 | 67,400.00 | 67,400.00 | 16,850.00 | 168,500.00 | A |
|  |  |  |  |  | 71300 | Consultant - Individual - Local | 12,980.00 | 51,920.00 | 51,920.00 | 12,980.00 | 129,800.00 | B |
|  |  |  |  |  | 75700 | Workshop/Training | 1,500.00 | 6,000.00 | 6,000.00 | 1,500.00 | 15,000.00 | C, G |
|  |  |  |  |  | 71600 | Travel – Local | 375.00 | 1,500.00 | 1,500.00 | 375.00 | 3,750.00 | D |
|  |  |  |  |  | 71600 | Travel - International | 1,600.00 | 6,400.00 | 6,400.00 | 1,600.00 | 16,000.00 | E |
|  |  |  |  |  | 72100 | Contractual Services – Companies/Firm | 1,000.00 | 4,000.00 | 4,000.00 | 1,000.00 | 10,000.00 | F |
|  | Total Output 3.1.1 |  |  |  |  |  | 34,305.00 | 137,220.00 | 137,220.00 | 34,305.00 | 343,050.00 |  |
|  | Output 3.1.3 Inter and intra institutional coordination and decision making mechanisms established or strengthened | UNDP | 66001 | 12526 | 71200 | Consultant - Individual - International | 10,500.00 | 10,500.00 | 7,000.00 | 7,000.00 | 35,000.00 | H |
|  |  |  |  |  | 71300 | Consultant - Individual - Local | 34,140.00 | 34,140.00 | 22,760.00 | 22,760.00 | 113,800.00 | I |
|  |  |  |  |  | 75700 | Workshop/Training | 15,000.00 | 15,000.00 | 10,000.00 | 10,000.00 | 50,000.00 | J, L |
|  |  |  |  |  | 74200 | Audio Visual & Printing | 2,400.00 | 2,400.00 | 1,600.00 | 1,600.00 | 8,000.00 | K |
|  |  |  |  |  | 71600 | Travel - International | 4,500.00 | 4,500.00 | 3,000.00 | 3,000.00 | 15,000.00 | M |
|  | Total Output 3.1.3 |  |  |  |  |  | 66,540.00 | 66,540.00 | 44,360.00 | 44,360.00 | 221,800.00 |  |
|  | Output 3.1.4 Stakeholder engagement frameworks, agreements and awareness raising conducted or strengthened | UNDP | 66001 | 12526 | 71200 | Consultant - Individual - International | 11,400.00 | 11,400.00 | 7,600.00 | 7,600.00 | 38,000.00 | N |
|  |  |  |  |  | 71300 | Consultant - Individual - Local | 32,760.00 | 32,760.00 | 21,840.00 | 21,840.00 | 109,200.00 | O |
|  |  |  |  |  | 75700 | Workshop/Training | 66,000.00 | 66,000.00 | 44,000.00 | 44,000.00 | 220,000.00 | P |
|  |  |  |  |  | 74200 | Audio Visual & Printing | 12,000.00 | 12,000.00 | 8,000.00 | 8,000.00 | 40,000.00 | Q |
|  |  |  |  |  | 72100 | Contractual Services – Companies/Firm | 13,500.00 | 13,500.00 | 9,000.00 | 9,000.00 | 45,000.00 | R |
|  | Total Output 3.1.4 |  |  |  |  |  | 135,660.00 | 135,660.00 | 90,440.00 | 90,440.00 | 452,200.00 |  |
| Total Outcome 3.1 |  |  |  |  |  |  | 236,505.00 | 339,420.00 | 272,020.00 | 169,105.00 | 1,017,050.00 |  |
| Outcome 3.2: Evidence basis produced to design adaptation solutions for maximum impact | Output 3.2.1 Adaptation impact monitoring, evaluation & learning systems established or strengthened for strategic planning and investment | UNDP | 66001 | 12526 | 71200 | Consultant - Individual - International | 18,600.00 | 18,600.00 | 12,400.00 | 12,400.00 | 62,000.00 | S |
|  |  |  |  |  | 71300 | Consultant - Individual - Local | 24,900.00 | 24,900.00 | 16,600.00 | 16,600.00 | 83,000.00 | T |
|  |  |  |  |  | 72100 | Contractual Services – Companies/Firm | 15,000.00 | 15,000.00 | 10,000.00 | 10,000.00 | 50,000.00 | U |
|  |  |  |  |  | 75700 | Workshop/Training | 7,500.00 | 7,500.00 | 5,000.00 | 5,000.00 | 25,000.00 | V, W |
|  |  |  |  |  | 74200 | Audio Visual & Printing | 2,250.00 | 2,250.00 | 1,500.00 | 1,500.00 | 7,500.00 | X |
|  | Total Output 3.2.1 |  |  |  |  |  | 68,250.00 | 68,250.00 | 45,500.00 | 45,500.00 | 227,500.00 |  |
|  | Output 3.2.2 Studies on climate vulnerability, & identification of adaptation solutions conducted (& used) for strengthening adaptation investment | UNDP | 66001 | 12526 | 71200 | Consultant - Individual - International | 209,000.00 | 167,200.00 | 41,800.00 | - | 418,000.00 | Z |
|  |  |  |  |  | 71300 | Consultant - Individual - Local | 110,625.00 | 88,500.00 | 22,125.00 | - | 221,250.00 | AA |
|  |  |  |  |  | 75700 | Workshop/Training | 22,500.00 | 18,000.00 | 4,500.00 | - | 45,000.00 | AB |
|  |  |  |  |  | 72100 | Contractual Services – Companies/Firm | 71,500.00 | 57,200.00 | 14,300.00 | - | 143,000.00 | AC |
|  |  |  |  |  | 72800 | IT Equipment | 10,000.00 | 8,000.00 | 2,000.00 | - | 20,000.00 | AD |
|  | Total Output 3.2.2 |  |  |  |  |  | 423,625.00 | 338,900.00 | 84,725.00 | - | 847,250.00 |  |
| Total Outcome 3.2 |  |  |  |  |  |  | 491,875.00 | 407,150.00 | 130,225.00 | 45,500.00 | 1,074,750.00 |  |
| Outcome 3.4. Adaptation finance increased | Output 3.4.2 Number of concept notes and/or funding proposals developed for adaptation priority actions | UNDP | 66001 | 12526 | 71200 | Consultant - Individual - International |  | 40,000.00 | 50,000.00 | 10,000.00 | 100,000.00 | AE |
|  |  |  |  |  | 71300 | Consultant - Individual - Local |  | 37,200.00 | 46,500.00 | 9,300.00 | 93,000.00 | AF |
|  | Total Output 3.4.2 |  |  |  |  |  | - | 77,200.00 | 96,500.00 | 19,300.00 | 193,000.00 |  |
|  | Output 3.4.3 National systems developed for tracking adaptation national and international finance flows | UNDP | 66001 | 12526 | 71200 | Consultant - Individual - International | 21,890.00 | 43,780.00 | 32,835.00 | 10,945.00 | 109,450.00 | AG |
|  |  |  |  |  | 71300 | Consultant - Individual - Local | 12,080.00 | 24,160.00 | 18,120.00 | 6,040.00 | 60,400.00 | AH |
|  |  |  |  |  | 75700 | Workshop/Training | 3,000.00 | 6,000.00 | 4,500.00 | 1,500.00 | 15,000.00 | AI |
|  | Total Output 3.4.3 |  |  |  |  |  | 36,970.00 | 73,940.00 | 55,455.00 | 18,485.00 | 184,850.00 |  |
| Total Outcome 3.4 |  |  |  |  |  |  | 36,970.00 | 151,140.00 | 151,955.00 | 37,785.00 | 377,850.00 |  |
| Total Outcome Budget |  |  |  |  |  |  | 765,350.00 | 897,710.00 | 554,200.00 | 252,390.00 | 2,469,650.00 |  |
| Project Management Cost (PMC) | Project Management Cost (PMC) | UNDP | 66001 | 12526 | 71300 | Consultant - Individual - Local | 30,720.00 | 61,440.00 | 46,080.00 | 15,360.00 | 153,600.00 | AK |
|  |  |  |  |  | 74100 | Professional Services-Audit Fees | 1,000.00 | 2,000.00 | 1,500.00 | 500.00 | 5,000.00 | AL |
|  |  |  |  |  | 71600 | Travel – Local | 400.00 | 800.00 | 600.00 | 200.00 | 2,000.00 | AM |
|  |  |  |  |  | 72500 | Office Supplies | 100.00 | 200.00 | 150.00 | 50.00 | 500.00 | AN |
|  |  |  |  |  | 72800 | IT Equipment | 800.00 | 1,600.00 | 1,200.00 | 400.00 | 4,000.00 | AO |
|  |  |  |  |  | 74596 | Services to Project | 5,007.00 | 5,007.00 | 5,007.00 | 5,007.00 | 20,028.00 | AP |
| Total PMC |  |  |  |  |  |  | 38,027.00 | 71,047.00 | 54,537.00 | 21,517.00 | 185,128.00 |  |
| Contingency | Contingency | UNDP | 66001 | 12526 | 74500 | Miscellaneous | 4,505.50 | 4,505.50 | 4,505.50 | 4,505.50 | 18,022.00 |  |
| Total Outcomes budget + PMC |  |  |  |  |  |  | 807,882.50 | 973,262.50 | 613,242.50 | 278,412.50 | 2,672,800.00 |  |

Budget Notes:

| Budget Note | Detailed Description |
| --- | --- |
| A | International Consultants @ $500 USD/day for a total of 337 days. Broken down as follows: Climate Adaptation Specialist (Team Lead) - 112days; Climate Risk and Vulnerability Expert - 40 days; Climate and Humanitarian Specialist - 40 days; Disaster Risk Reduction Expert - 30days; Gender and Social Inclusion Specialist (GESI Team Lead) - 40 days; Environmental Expert - 25 days. Conflict analysis expert 50 days Output 3.1.1 |
| B | Local Experts @ $200 USD/day for a total of 649 days. Broken down as follows: Sectoral Experts (Water, Agriculture, Coastal Zones, Health) - 240 days; Policy and Governance Expert - 50 days; Data Analyst - 20 days; Coordinator Facilitor - 27 days; Techncial writer - 62 days; Stakeholder Engagement Specialist - 55 days; M&E Specialist - 65 days; Gender Inclusion Specialist - 50 days; Survey team - 80 days Output 3.1.1 |
| C | 5 Meetings of the Technical Climate Coordination Committee (TCCC) and NTC's to develop the sectoral and national NAPS - 5 meetings @$2000/meeting, including the cost of venue and catering for 50 participants e.g. Ministeries, CSO, Community leaders etc. Output 3.1.1/ Activity 3.1.3.1a |
| D | Travel – Local - Trips related to consultations and meetings - 15 @ 250 per trip, E.g Transportation, ticket cost, DSA etc Output 3.1.1 Activity 3.1.1.1b/c/d |
| E | Travel - International - International experts' missions - 8 @ 2,000 per trip, E.g Transportation, ticket cost, DSA etc Output 3.1.1 Activity 3.1.1.1b/c/d |
| F | Professional Services Firm to conduct 4 GESI surveys to support development of guidance document at the cost of USD 2,500/survey totalling USD 10,000 Output 3.1.1 |
| G | NAP Launch Workshop at the cost of USD 5,000 under Activity 3.1.3.1a. The budget includes the cost of venue and catering for 100 number of participants (Ministeries, CSO, Community leaders etc) Output 3.1.1 |
| H | International Consultants @ $500 USD/day: Climate Adaptation Specialist (Team Lead) - 40 days; Climate and Humanitarian Specialist - 30 days Output 3.1.3 |
| I | Local Experts @ $200 USD/day for a total of 569 days. Broken down as follows: Climate Adaptation Specialist - 50 days; Policy and Governance Expert - 65 days; Stakeholder Engagement Specialist - 70 days; Communication Specialist - 40 days; Graphic Designer - 30 days; Facilitator - 49 days; Training Coordinator - 45 days; Sectoral Experts - 200 days; Monitoring and Evaluation (M&E) Specialist - 20 days Output 3.1.3 |
| J | Training workshops to strengthen the technical capacity of TCCC and NTCs. There will be 2 workshops(one day each), with each costing $5,000 including the cost of venue and catering, totalling $10,000 Output 3.1.3 Activity 3.1.3.1e |
| K | Audio Visual & Printing to support Training sessions and meetings. 2 packages of audio visual and printing at $4,000 each. Activity 3.1.3.1c and Activity 3.1.3.1e |
| L | Bi-annual meetings of the Technical Climate Coordination Committee (TCCC) on the NAP process; Activity 3.1.3.1c |
| M | International trips for training and exposure to international experiences in adaptation planning, eg: South south exchange visits. There will be 6 trips at USD 2,500 per trip, totalling USD 15,000. 3 pax x2 trips Output 3.1.3 |
| N | International Consultants @ $500 USD/day: Institutional Capacity Development Specialist (Team Lead) - 50 days; Climate Change Adaptation Specialist - 26 days; Activity 3.1.4a |
| O | Local Experts @ $200 USD/day for a total of 546 days. Broken down as follows: Institutional Capacity Development Expert - 60 days; Policy and Governance Expert - 30 days; Training Specialist - 40 days; Stakeholder Engagement Specialist - 99 days; Monitoring and Evaluation (M&E) Specialist - 25 days; Communication Specialist (Team Lead) - 74 days; Media and Content Developer - 30 days; Community Mobilizer - 30 days; Graphic Designer - 20 days; Awareness Raising Expert (Team Lead) - 64 days; Logistics coordinator - 24 days; Data Analyst - 30 days; Report writer - 20 days Activity 3.1.4a/b/c/d |
| P | Training workshops covering 160 practitioners across 4 sectors in multiple climate change adaptation topics (at least 30% women) Activity 3.1.4.1b Output 3.1.4 |
| Q | Audio Visual & Printing for training workshops. 10 packages of audit visual and printing at $4,000 each totalling USD 40,000 Output 3.1.4 |
| R | Professional Services Firm to conduct awareness surveys at the start, midpoint, and end of the project to measure the level and evolution of awareness on climate change and adaptation. Each of the three surveys is estimated to cost USD 15,000 totalling USD 45,000. Output 3.1.4 |
| S | International Consultants @ $500 USD/day: M&E Specialist (Team Lead) - 104 days; Climate change adaptation Expert - 20 days; Output 3.2.1 |
| T | Local Experts @ $200 USD/day for a total of 415 days. Broken down as follows: Gender and Social Inclusion Specialist - 30; Sectoral Climate Adaptation Specialists - 120 days; Data Analyst - 60 days; Technical Writer - 65 days; Stakeholder Engagement Specialist - 60 days; Training Specialist (Team Lead) - 30 days; Software/Web Dveloper - 10 days; Knowledge Management Specialist (Team Lead) - 30 days; Facilitator (Team Lead) - 5 days; Logistics Coordinator - 5 days Output 3.2.1 |
| U | Software/web Developer (Professional Services Company) to develop the technical components of the M&E system, ensuring seamless integration with the NAP Portal and user accessibility. Estimated at a lumpsum of USD 50,000 Output 3.2.1 |
| V | Training workshops on the M&E system for COCA, TCCC, and staff of at least three ministries Output 3.2.1 |
| W | Final national meeting to present and discuss the main results of the project and agree on a roadmap for the next iteration of the NAP. The meeting is estimated at a cost of USD 5,000 including the cost of venue and catering for the participants. Output 3.2.1 |
| X | Audio Visual & Printing for training workshops and final meeting. 5 packages of audio visual and printing at $1,500 each totalling USD7,500 Output 3.2.1 |
| Z | International Consultants @ $550 USD/day for a total of 760 days. Broken down as follows: Climate Modeler (Team Lead) - 60 days; International team of Climate Modellers, Hydrologist, Meteorologist, GIS Expert, Data Modelling expert) - 170 days; Conflict Analysis Expert for key Sectors- 60 days Climate multi-hazard and risk modelling and mapping expert/risk assessment expert (Team Lead) - 60 days; Hydrologist/multi-hazard modelling expert - 60 days; GIS Specialist - 30 days; Socio-economics Expert - 40 days; Procurement Specialist (Team Lead) - 30 days; Climate Data Specialist (team lead) - 60 days; IT Systems Architect - 70 days; Software Developer - 70 days; Data Integration Specialist - 30 days; Software Developer - 20 days Output 3.2.2. |
| AA | Local Experts @ $250 USD/day for a total of 885 days. Broken down as follows: Hydrologist - 60 days; Meteorologist - 145 days; Data Analyst - 120 days; Facilitator - 20 days; Stakeholder Engagement Specialist - 60 days; GIS Analyst/Speciaist - 85 days; Sectoral Experts (Water, Agriculture, Coastal Zones, Health) - 180 days; Technical Writer - 30 days; Climate Data Specialist - 25 days; Monitoring and Evaluation (M&E) Specialist - 50 days; Communication Specialist - 30 days; Graphic Designer - 80 days; Output 3.2.2. |
| AB | Workshops on climate projections downscaling. There will be 9 workshops at an estimate of $5000/workshop including the cost of venue and catering for the participants. Output 3.2.2. |
| AC | Procurement of data for climate projects downscaling (Licensing and acquisition of high-resolution GCM/RCM data, hydrological data, and satellite imagery. Example sources: Copernicus, ECMWF, commercial providers - $80,000; Preprocessing and cleaning data for compatibility with downscaling models. Includes data integration for climate and hydrological models - $30,000; Procurement or licensing of software such as WRF, PRECIS, or GIS tools for statistical or dynamic downscaling.- $20,000; Contingency Allowance for unforeseen costs during data procurement, processing, or training - $13,000. Output 3.2.2. |
| AD | Procurement or licensing of software such as WRF, PRECIS, or GIS tools for statistical or dynamic downscaling - $20,000; Output 3.2.2. |
| AE | International Consultants @ $500 USD/day for a total of 200 days. Broken down as follows: Project Formulation Expert/Climate Adaptation Specialist/Climate Finance Specialist (Team Lead) - 30 days; International Sectoral Experts (Water, agriculture, Coastal Zones, Health) - 120 days; Socio-Economist/Analyst - 25 days; Social and Environmental Impact/Safeguards Specialist - 25 days; Output 3.4.2 |
| AF | Local Experts @ $200 USD/day for a total of 465 days. Broken down as follows: Sectoral Experts (Water, Agriculture, Coastal Zones, Health) - 240 days; Policy and Governance Expert - 10 days; Data Analyst - 45 days; Gender and Social Inclusion Specialist - 45 days; Monitoring and Evaluation (M&E) Specialist - 10 days; Stakeholder Engagement Specialist - 30 days; Climate Risk Analyst - 30 days; GIS Specialist - 25 days; Technical Writer - 30 days. Output 3.4.2. |
| AG | International Consultants @ $550 USD/day: Climate Finance Specialist (Team Lead) - 144 days; Economic Analyst - 55 days; Output 3.4.3 |
| AH | Local Experts @ $200 USD/day for a total of 302 days. Broken down as follows: Stakeholder Engagement Specialist - 87 days; Policy and Governance Expert - 45 days; Communication Specialist - 27 days; Data Analyst - 25 days; Facilitator - 23 days; Logistics Coordinator - 15 days; Technical Writer - 50 days; Sectoral Experts (Water, Agriculture, Health) - 30 days Output 3.4.3 |
| AI | 3 annual one-day workshops for the FWG to review potential funding sources to bridge the funding gaps identified. Each workshop is estimated to cost USD 5,000 totalling USD 15,000 including the cost of venue and catering for the participants. Output 3.4.3 |
| AK | a) Cost of a Project Manager @$2,500 per month for 48 months, totalling USD120,000 b) Cost of a Project Assistant @$700 per month for 48 months, totalling USD 33,600. |
| AL | Project audit will be conducted by external audit firm, hired competitively |
| AM | Travel for project personnel to reach project sites for project management, monitoring and implementation - approx. 8 trips at USD250 per trip. |
| AN | Office supplies for the printing of documents for various project management activities, communications, monitoring and reporting documents and other informative documents for dissemination to key stakeholders, as appropriate. Budgeted at a lumpsum of USD500. |
| AO | Acquisition of laptops, software licenses, portable hard drive, printer etc. for the Project Manager and Assistant at a total of USD 4,000 |
| AP | Procurement support, recruitment, travel management, etc. 20,028 USD USD for 4 years. The direct services to project will be charged based on UNDP UPL |

# Legal Context

This project document shall be the instrument referred to as such in Article 1 of the Standard Basic Assistance Agreement between the Government of Burundi) and UNDP, signed on 20 November 1975.   All references in the SBAA to “Executing Agency” shall be deemed to refer to “Implementing Partner.”

This project will be implemented by UNDP (“Implementing Partner”) in accordance with its Financial Regulations and Rules, practices, procedures and financial governance to ensure best value for money, fairness, integrity, transparency, and effective international competition.

The designations employed and the presentation of material on this map do not imply the expression of any opinion whatsoever on the part of the Secretariat of the United Nations or UNDP concerning the legal status of any country, territory, city or area or its authorities, or concerning the delimitation of its frontiers or boundaries.

# Risk Management

UNDP (DIM)

- UNDP as the Implementing Partner will comply with the policies, procedures and practices of the United Nations Security Management System (UNSMS.)

- UNDP as the Implementing Partner will undertake all reasonable efforts to ensure that none of the [project funds] [UNDP funds received pursuant to the Project Document] are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/sc/committees/1267/aq_sanctions_list.shtml.  This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document.

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

- UNDP as the Implementing Partner will: (a) conduct project and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

- In the implementation of the activities under this Project Document, UNDP as the Implementing Partner will handle any sexual exploitation and abuse (“SEA”) and sexual harassment (“SH”) allegations in accordance with its regulations, rules, policies and procedures.

- All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any programme or project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

- UNDP as the Implementing Partner will ensure that the following obligations are binding on each responsible party, subcontractor and sub-recipient:

  - Consistent with the Article III of the SBAA [or the Supplemental Provisions to the Project Document], the responsibility for the safety and security of each responsible party, subcontractor and sub-recipient and its personnel and property, and of UNDP’s property in such responsible party’s, subcontractor’s and sub-recipient’s custody, rests with such responsible party, subcontractor and sub-recipient.  To this end, each responsible party, subcontractor and sub-recipient shall:

    - put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

    - assume all risks and liabilities related to such responsible party’s, subcontractor’s and sub-recipient’s security, and the full implementation of the security plan.

  - UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the responsible party’s, subcontractor’s and sub-recipient’s obligations under this Project Document.

  - In the performance of the activities under this Project, UNDP as the Implementing Partner shall ensure, with respect to the activities of any of its responsible parties, sub-recipients and other entities engaged under the Project, either as contractors or subcontractors, their personnel and any individuals performing services for them, that those entities have in place adequate and proper procedures, processes and policies to prevent and/or address SEA and SH.

  - Each responsible party, subcontractor and sub-recipient will take appropriate steps to prevent misuse of funds, fraud or corruption, by its officials, consultants, subcontractors and sub-recipients in implementing the project or programme or using the UNDP funds.  It will ensure that its financial management, anti-corruption and anti-fraud policies are in place and enforced for all funding received from or through UNDP.

  - The requirements of the following documents, then in force at the time of signature of the Project Document, apply to each responsible party, subcontractor and sub-recipient: (a) UNDP Policy on Fraud and other Corrupt Practices and (b) UNDP Office of Audit and Investigations Investigation Guidelines. Each responsible party, subcontractor and sub-recipient agrees to the requirements of the above documents, which are an integral part of this Project Document and are available online at www.undp.org.

  - In the event that an investigation is required, UNDP will conduct investigations relating to any aspect of UNDP programmes and projects. Each responsible party, subcontractor and sub-recipient will provide its full cooperation, including making available personnel, relevant documentation, and granting access to its (and its consultants’, subcontractors’ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with it to find a solution.

  - Each responsible party, subcontractor and sub-recipient will promptly inform UNDP as the Implementing Partner in case of any incidence of inappropriate use of funds, or credible allegation of fraud or corruption with due confidentiality.

Where it becomes aware that a UNDP project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption, each responsible party, subcontractor and sub-recipient will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). It will provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

  - UNDP will be entitled to a refund from the responsible party, subcontractor or sub-recipient of any funds provided that have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of this Project Document.  Such amount may be deducted by UNDP from any payment due to the responsible party, subcontractor or sub-recipient under this or any other agreement.  Recovery of such amount by UNDP shall not diminish or curtail any responsible party’s, subcontractor’s or sub-recipient’s obligations under this Project Document.

Where such funds have not been refunded to UNDP, the responsible party, subcontractor or sub-recipient agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Project Document, may seek recourse to such responsible party, subcontractor or sub-recipient for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Note:  The term “Project Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Project Document, including those with responsible parties, subcontractors and sub-recipients.

  - Each contract issued by the responsible party, subcontractor or sub-recipient in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from it shall cooperate with any and all investigations and post-payment audits.

  - Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the project or programme, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

  - Each responsible party, subcontractor and sub-recipient shall ensure that all of its obligations set forth under this section entitled “Risk Management” are passed on to its subcontractors and sub-recipients and that all the clauses under this section entitled “Risk Management Standard Clauses” are adequately reflected, mutatis mutandis, in all its sub-contracts or sub-agreements entered into further to this Project Document.

# Mandatory Annexes

Annex A: GCF approved Readiness and Preparatory Support Proposal

Annex B: GCF notification of approval letter

Annex C: Procurement plan

Annex D: Terms of Reference for Project Board and Project Team

Annex E: UNDP Risk Log

Annex F: UNDP Project Quality Assurance Report

## Annex A: GCF approved Readiness and Preparatory Support Proposal

https://pims.undp.org/attachments/10103/221989/1793907/1876322/Readiness%20Proposal_National%20Adaptation%20Plan_Yemen.pdf

## Annex B: GCF notification of approval letter

Annex C: Procurement plan

| No | Status | Item Description | Category | Estimated Cost (US$) | Procurement Method (e.g. open, limited RFP,ITB,RFQ) | Thresholds as per applicable procurement policy (Min-Max monetary value for which indicated procurement method must be used) | Name of Entity executing Procurement (DP/EE, etc.) | Date of initiating procurement (Tender Issuence) | Estimated contract start date | Remarks |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Planned | International Consultants to support Output 3.1.1 Total of 287 days @ $550 USD/day: Climate Adaptation Specialist (Team Lead) - 112days; Climate Risk and Vulnerability Expert - 40 days; Climate and Humanitarian Specialist - 40 days; Disaster Risk Reduction Expert - 30days; Gender and Social Inclusion Specialist (GESI Team Lead) - 40 days; Environmental Socio-economics Expert - 25 days. | Consulting Services (Individual Consultants) | $ 185,350.00 | Competitive procurement | 5000-149,999 | DP | Y1 Q2 | Y1 Q2 | Budget Note A |  |
| 1 | Revised1 |  |  |  |  |  |  |  |  |  |  |
| 1 | Actual |  |  |  |  |  |  |  |  |  |  |
| 2 | Planned | Local Experts to support Output 3.1.1. Total 649 days @ $200 USD/day: Sectoral Experts (Water, Agriculture, Coastal Zones, Health) - 240 days; Policy and Governance Expert - 50 days; Data Analyst - 20 days; Coordinator Facilitor - 27 days; Techncial writer - 62 days; Stakeholder Engagement Specialist - 55 days; M&E Specialist - 65 days; Gender Inclusion Specialist - 50 days; Survey team - 80 days | Consulting Services (Individual Consultants) | $ 129,800.00 | Competitive procurement | 5000-149,999 | DP | Y1 Q2 | Y1 Q2 | Budget Note B |  |
| 2 | Revised1 |  |  |  |  |  |  |  |  |  |  |
| 2 | Actual |  |  |  |  |  |  |  |  |  |  |
| 3 | Planned | Professional Services – Companies/Firm to provide GESI surveys under Output 3.1.1 | Consulting Services (Professional Firms) | 10,000.00 | RFQ | 5000-149,999 | DP | Y1 Q3 | Y1 Q3 | Budget Note F |  |
| 3 | Revised1 |  |  |  |  |  |  |  |  |  |  |
| 3 | Actual |  |  |  |  |  |  |  |  |  |  |
| 4 | Planned | International Consultants to support Output 3.1.3. Total 70 days @ $500 USD/day: Climate Adaptation Specialist (Team Lead) - 40 days; Humanitarian Specialist - 30 days | Consulting Services (Individual Consultants) | $ 35,000.00 | Competitive procurement | 5000-149,999 | DP | Y1 Q3 | Y1 Q3 | Budget Note H |  |
| 4 | Revised1 |  |  |  |  |  |  |  |  |  |  |
| 4 | Actual |  |  |  |  |  |  |  |  |  |  |
| 5 | Planned | Local Experts to support Output 3.1.3 Total 569 days @ $200 USD/day: Climate Adaptation Specialist - 50 days; Policy and Governance Expert - 65 days; Stakeholder Engagement Specialist - 70 days; Communication Specialist - 40 days; Graphic Designer - 30 days; Facilitator - 49 days; Training Coordinator - 45 days; Sectoral Experts - 200 days; Monitoring and Evaluation (M&E) Specialist - 20 days | Consulting Services (Individual Consultants) | $ 113,800.00 | Competitive procurement | 5000-149,999 | DP | Y1 Q3 | Y1 Q3 | Budget Note I |  |
| 5 | Revised1 |  |  |  |  |  |  |  |  |  |  |
| 5 | Actual |  |  |  |  |  |  |  |  |  |  |
| 6 | Planned | International Consultants to support Output 3.1.4. Total 76 days @ $500 USD/day: Institutional Capacity Development Specialist (Team Lead) - 50 days; Climate Change Adaptation Specialist - 26 days; | Consulting Services (Individual Consultants) | $ 38,000.00 | Competitive procurement | 5000-149,999 | DP | Y1 Q3 | Y1 Q3 | Budget Note N |  |
| 6 | Revised1 |  |  |  |  |  |  |  |  |  |  |
| 6 | Actual |  |  |  |  |  |  |  |  |  |  |
| 7 | Planned | Local Experts to Support Output 3.14. Total 546 days @ $200 USD/day: Institutional Capacity Development Expert - 60 days; Policy and Governance Expert - 30 days; Training Specialist - 40 days; Stakeholder Engagement Specialist - 99 days; Monitoring and Evaluation (M&E) Specialist - 25 days; Communication Specialist (Team Lead) - 74 days; Media and Content Developer - 30 days; Community Mobilizer - 30 days; Graphic Designer - 20 days; Awareness Raising Expert (Team Lead) - 64 days; Logistics coordinator - 24 days; Data Analyst - 30 days; Report writer - 20 days | Consulting Services (Individual Consultants) | $ 109,200.00 | Competitive procurement | 5000-149,999 | DP | Y1 Q3 | Y1 Q3 | Budget Note O |  |
| 7 | Revised1 |  |  |  |  |  |  |  |  |  |  |
| 7 | Actual |  |  |  |  |  |  |  |  |  |  |
| 8 | Planned | Firm to Conduct awareness surveys at the start, midpoint, and end of the project to measure the level and evolution of awareness on climate change and adaptation.See Budget Note "R" | Consulting Services (Professional Firms) | $ 45,000.00 | RFQ | 5000-149,999 | DP | Y1 Q2 | Y1 Q2 | Budget Note R |  |
| 8 | Revised1 |  |  |  |  |  |  |  |  |  |  |
| 8 | Actual |  |  |  |  |  |  |  |  |  |  |
| 9 | Planned | International Consultants to support Output 3.2.1. Total 124 days @ $500 USD/day: M&E Specialist (Team Lead) - 104 days; Climate change adaptation Expert - 20 days; | Consulting Services (Individual Consultants) | $ 62,000.00 | Competitive procurement | 5000-149,999 | DP | Y1 Q3 | Y1 Q3 | Budget Note S |  |
| 9 | Revised1 |  |  |  |  |  |  |  |  |  |  |
| 9 | Actual |  |  |  |  |  |  |  |  |  |  |
| 10 | Planned | Local Experts to support Output 3.2.1. Total 415 days @ $200 USD/day: Gender and Social Inclusion Specialist - 30; Sectoral Climate Adaptation Specialists - 120 days; Data Analyst - 60 days; Technical Writer - 65 days; Stakeholder Engagement Specialist - 60 days; Training Specialist (Team Lead) - 30 days; Software/Web Dveloper - 10 days; Knowledge Management Specialist (Team Lead) - 30 days; Facilitator (Team Lead) - 5 days; Logistics Coordinator - 5 days | Consulting Services (Individual Consultants) | $ 83,000.00 | Competitive procurement | 5000-149,999 | DP | Y1 Q4 | Y1 Q4 | Budget Note T |  |
| 10 | Revised1 |  |  |  |  |  |  |  |  |  |  |
| 10 | Actual |  |  |  |  |  |  |  |  |  |  |
| 11 | Planned | Professional Services Company of Software/web Developers to develop the technical components of the M&E system, ensuring seamless integration with the NAP Portal and user accessibility. See Budget note "U" | Consulting Services (Professional Firms) | $ 50,000.00 | RFQ | 5000-149,999 | DP | Y1 Q4 | Y1 Q4 | Budget Note U |  |
| 11 | Revised1 |  |  |  |  |  |  |  |  |  |  |
| 11 | Actual |  |  |  |  |  |  |  |  |  |  |
| 12 | Planned | International Consultants to support Output 3.2.2. Total 700 days @ $600 USD/day: Climate Modeler (Team Lead) - 60 days; International team of Climate Modellers, Hydrologist, Meteorologist, GIS Expert, Data Modelling expert) - 180 days; Climate multi-hazard and risk modelling and mapping expert/risk assessment expert (Team Lead) - 60 days; Hydrologist/multi-hazard modelling expert - 60 days; GIS Specialist - 30 days; Socio-economics Expert - 40 days; Procurement Specialist (Team Lead) - 30 days; Climate Data Specialist (team lead) - 60 days; IT Systems Architect - 80 days; Software Developer - 80 days; Data Integration Specialist - 30 days; Software Developer - 20 days | Consulting Services (Individual Consultants) | $ 456,000.00 | Competitive procurement | 5000-149,999 | DP | Y1 Q3 | Y1 Q3 | Budget Note Z |  |
| 12 | Revised1 |  |  |  |  |  |  |  |  |  |  |
| 12 | Actual |  |  |  |  |  |  |  |  |  |  |
| 13 | Planned | Local Experts to support Output 3.2.2. Total 885 days @ $250 USD/day: Hydrologist - 60 days; Meteorologist - 145 days; Data Analyst - 120 days; Facilitator - 20 days; Stakeholder Engagement Specialist - 60 days; GIS Analyst/Speciaist - 85 days; Sectoral Experts (Water, Agriculture, Coastal Zones, Health) - 180 days; Technical Writer - 30 days; Climate Data Specialist - 25 days; Monitoring and Evaluation (M&E) Specialist - 50 days; Communication Specialist - 30 days; Graphic Designer - 80 days; | Consulting Services (Individual Consultants) | $ 221,250.00 | Competitive procurement | 5000-149,999 | DP | Y1 Q4 | Y1 Q4 | Budget Note AA |  |
| 13 | Revised1 |  |  |  |  |  |  |  |  |  |  |
| 13 | Actual |  |  |  |  |  |  |  |  |  |  |
| 14 | Planned | Procurement of data for climate projects downscaling (Licensing and acquisition of high-resolution GCM/RCM data, hydrological data, and satellite imagery. Example sources: Copernicus, ECMWF, commercial providers - $80,000; Preprocessing and cleaning data for compatibility with downscaling models. Includes data integration for climate and hydrological models - $30,000; Contingency Allowance for unforeseen costs during data procurement, processing, or training - $13,000. | Goods | $ 143,000.00 | RFQ | 5000-149,999 | DP | Y1 Q4 | Y1 Q4 | Budget Note AC |  |
| 14 | Revised1 |  |  |  |  |  |  |  |  |  |  |
| 14 | Actual |  |  |  |  |  |  |  |  |  |  |
| 15 | Planned | Procurement or licensing of software such as WRF, PRECIS, or GIS tools for statistical or dynamic downscaling - $20,000; | Goods | $ 20,000.00 | RFQ | 5000-149,999 | DP | Y1 Q4 | Y1 Q4 | Budget Note AD |  |
| 15 | Revised1 |  |  |  |  |  |  |  |  |  |  |
| 15 | Actual |  |  |  |  |  |  |  |  |  |  |
| 16 | Planned | International Consultantsto support Output 3.4.2. Total 200 days @ $500 USD/day: Project Formulation Expert/Climate Adaptation Specialist/Climate Finance Specialist (Team Lead) - 30 days; International Sectoral Experts (Water, agriculture, Coastal Zones, Health) - 120 days; Socio-Economist/Analyst - 25 days; Social and Environmental Impact/Safeguards Specialist - 25 days; | Consulting Services (Individual Consultants) | $ 100,000.00 | Competitive procurement | 5000-149,999 | DP | Y3Q1 | Y3Q1 | Budget Note AE |  |
| 16 | Revised1 |  |  |  |  |  |  |  |  |  |  |
| 16 | Actual |  |  |  |  |  |  |  |  |  |  |
| 17 | Planned | Local Experts to support Output 4.3.2. Total 465 days @ $200 USD/day: Sectoral Experts (Water, Agriculture, Coastal Zones, Health) - 240 days; Policy and Governance Expert - 10 days; Data Analyst - 45 days; Gender and Social Inclusion Specialist - 45 days; Monitoring and Evaluation (M&E) Specialist - 10 days; Stakeholder Engagement Specialist - 30 days; Climate Risk Analyst - 30 days; GIS Specialist - 25 days; Technical Writer - 30 days. | Consulting Services (Individual Consultants) | $ 93,000.00 | Competitive procurement | 5000-149,999 | DP | Y3Q1 | Y3Q1 | Budget Note AF |  |
| 17 | Revised1 |  |  |  |  |  |  |  |  |  |  |
| 17 | Actual |  |  |  |  |  |  |  |  |  |  |
| 18 | Planned | International Consultants to support Output 3.4.3. Total 199 @ $550 USD/day: Climate Finance Specialist (Team Lead) - 144 days; Economic Analyst - 55 days; | Consulting Services (Individual Consultants) | $ 109,450.00 | Competitive procurement | 5000-149,999 | DP | Y2Q2 | Y2Q2 | Budget Note AG |  |
| 18 | Revised1 |  |  |  |  |  |  |  |  |  |  |
| 18 | Actual |  |  |  |  |  |  |  |  |  |  |
| 19 | Planned | Local Experts to support Output 3.4.3. Total 302 days @ $200 USD/day: Stakeholder Engagement Specialist - 97 days; Policy and Governance Expert - 55 days; Communication Specialist - 27 days; Data Analyst - 25 days; Facilitator - 23 days; Logistics Coordinator - 15 days; Technical Writer - 60 days; Sectoral Experts (Water, Agriculture, Health) - 40 days | Consulting Services (Individual Consultants) | $ 60,400.00 | Competitive procurement | 5000-149,999 | DP | Y2Q2 | Y2Q2 | Budget Note AH |  |
| 19 | Revised1 |  |  |  |  |  |  |  |  |  |  |
| 19 | Actual |  |  |  |  |  |  |  |  |  |  |
| 20 | Planned | Meetings, Workshops and Training workshops | Non-Consulting Services | $ 370,000.00 | RFQ | 5000-149,999 | DP | Y1 Q2 | Y1 Q2 | Budget Notes C,G,J,L,P,V,W,AB, and AI |  |
| 20 | Revised1 |  |  |  |  |  |  |  |  |  |  |
| 20 | Actual |  |  |  |  |  |  |  |  |  |  |
| 21 | Planned | Firms to provide Audio Visual & Printing to the project | Consulting Services (Professional Firms) | $ 55,500.00 | RFQ | 5000-149,999 | DP | Y1 Q2 | Y1 Q2 | Budget Notes K,Q, and X |  |
| 21 | Revised1 |  |  |  |  |  |  |  |  |  |  |
| 21 | Actual |  |  |  |  |  |  |  |  |  |  |
| 22 | Planned | Travel - Local | Non-Consulting Services | $ 5,750.00 | Competitive procurement | 5000-149,999 | DP | Y1 Q2 | Y1 Q2 | Budget Notes D and AM |  |
| 22 | Revised1 |  |  |  |  |  |  |  |  |  |  |
| 22 | Actual |  |  |  |  |  |  |  |  |  |  |
| 23 | Planned | Travel - International | Non-Consulting Services | $ 5,000.00 | Competitive procurement | 5000-149,999 | DP | Y1 Q2 | Y1 Q2 | Budget Notes E,M,and Y |  |
| 23 | Revised1 |  |  |  |  |  |  |  |  |  |  |
| 23 | Actual |  |  |  |  |  |  |  |  |  |  |
| 24 | Planned | Audit Fee | Consulting Services (Professional Firms) | 5,000.00 | Competitive procurement | <5,000 | DP | Y4Q1 | Y4Q1 | Budget Notes AL |  |
| 24 | Revised1 |  |  |  |  |  |  |  |  |  |  |
| 24 | Actual |  |  |  |  |  |  |  |  |  |  |
| 25 | Planned | IT Equipment |  | 4,000.00 | Competitive procurement | 5000-149,999 | DP | Y1Q2 | Y1Q2 | Budget Notes AO |  |
| 25 | Revised1 |  |  |  |  |  |  |  |  |  |  |
| 25 | Actual |  |  |  |  |  |  |  |  |  |  |
|  | Planned | Total $(USD) |  | $ 2,509,500.00 |  |  |  |  | $0.00 |  |  |
|  | Revised1 | Total $(USD) |  | $ - |  |  |  |  | $0.00 |  |  |
|  | Actual | Total $(USD) |  | $ - |  |  |  |  | $0.00 |  |  |
|  | Breakdown per Category |  |  |  |  |  |  |  |  |  |  |
|  | Planned Goods | Total $(USD) |  | $ 163,000.00 |  |  |  |  |  |  |  |
|  | Planned Non-Consulting Services | Total $(USD) |  | $ 380,750.00 |  |  |  |  |  |  |  |
|  | Planned Works | Total $(USD) |  | $ - |  |  |  |  |  |  |  |
|  | Planned Consulting Services (PS) | Total $(USD) |  | $ 165,500.00 |  |  |  |  |  |  |  |
|  | Planned Consulting Services (IC) | Total $(USD) |  | $ 1,796,250.00 |  |  |  |  |  |  |  |

## Annex D: Terms of Reference for Project Board, Project Team and UNDP Staff

Terms of Reference for Key Project Staff

Project Manager

    - Project Background and Description

Under the direct supervision and overall guidance of the Climate Change, Energy, and Environment Team Leader (CCEE-TL), the PM is responsible for administrative, financial, and overall project management, implementation, and regular monitoring of project results and risks, ensuring that the project is efficiently managed to fulfil its mission and objectives, and in accordance with the UNDP standards and best practices. The PM works in close collaboration with UNDP programme and operations team, the UNFCCC Focal Point, Climate Change Unit, technical advisors and experts, ensuring successful project implementation.

Tasks and responsibilities:

- Developing a comprehensive/detailed project work-plan and annual workplans, including roles and responsibilities of the stakeholders and milestones.

- Managing day-to-day implementation and management of the project by maintaining the delivery of appropriate technical, operational, financial, and administrative outputs, and tracking the progress of the project by monitoring and reporting.

- Ensuring adherence of the project work plan to the project document, prepare revisions if required.

- Managing and coordinating the implementation of the project activities, including supervision and guidance of other project staff, consultants, and experts with a view to achieving project results.

- Developing Terms of reference (ToRs) for consultants and ensuring timely recruitment and procurement of quality services and implementation of project activities in line with UNDP rules.

- Managing the human and financial resources for achieving results in line with the outputs and activities outlined in the project document and annual work plan.

- Maintaining collaborative working relationships among key project partners and stakeholders through effective communication, consultation and reporting

- Managing and monitoring project risks initially identified, submitting information on the new risks and possible mitigating measures to the Project Steering Committee for consideration and updating the status of these risks by maintaining a Project Risk Log.

- Providing technical support in developing the national level MEL Framework for the NAP process.

- Performing tasks in Quantum in line with the given function.

- Ensuring that the project produces the outputs specified in the project document, to the required standard of quality and within the specified constraints of time and cost.

- Ensuring effective project management by maintaining the delivery of appropriate technical, operational, financial and administrative outputs.

- Overseeing and monitoring implementation of work plans and budgets for all project activities.

- Monitoring the project expenditures, commitments, and balance of funds under the project budget lines, and draft project budget revisions in accordance with UNDP’s QUANTUM system including the reporting on project funds and related record keeping.

- Monitoring project expenditure, commitments and balance of funds under the project budget lines for cost-efficiency and consistency with the Project Document and corresponding Annual Work Plan.

- Managing delivery of results by using up-to-date best practices and know-how in the subject area and accordingly plan delivery of resources for the performance year.

- Ensuring timely preparation of regular, quarterly, biannual, and annual reports required by GCF and other stakeholders, and that monitoring, and evaluation of the project is conducted in accordance with donor requirements and UNDP rules and procedures.

- Performing regular progress reporting to the project board as agreed with the board, including measures to address challenges and opportunities.

- Preparing the final project report and processing all other requirements for the project auditing and closure as per UNDP standard procedures.

- Ensuring that the standard UNDP and Green Climate Fund (GCF) Monitoring and Evaluation (M&E) requirements are fulfilled to the highest quality.

- Reviewing professional performance and document implementation processes and results through project-based professional reports.

- Managing and monitoring requests for financial resources and ensuring accuracy and reliability of financial reports.

- Liaising with the contracted consultants and other UNDP project staff on financial management of the project activities, including monitoring project financial expenditure and transactions.

- Ensuring creation of strategic partnership and supporting implementation of the resource mobilization strategy.

- Contributing to policy briefs, strategic notes, discussion papers on emerging climate change adaptation related issues, for consideration by the Government and other stakeholders.

- Reviewing and contributing to all outputs and deliverables produced under the project.

- Identifying, collecting, and analyzing policy-related, relevant information and data.

- Assisting in engaging the government in constructive dialogue on the achievement of project outcomes.

- Maintaining continuous dialogue and coordination with national partners regarding the implementation of projects activities.

- Contributing to visibility of project results to relevant national and international stakeholders and audiences.

- Coordinating, systemizing, codifying, and integrating successful approaches, methodologies and tools developed in the relevant area, into a cohesive UNDP framework for supporting governments efforts in different aspects of climate change.

- Supporting establishing effective linkages with other UNDP projects and with other initiatives in the sector with a view to developing substantive partnerships and generating synergies.

- Analyzing and aggregating project results/outputs, and reporting of project progress at the objective and outcome level.

- Engaging in a constructive dialogue with official counterparts, partners, and other stakeholders, especially to maximize consistency and synergy between the various support components, as informed by the priorities of the Climate Change Energy and Environment Unit.

- Contributing written inputs to UNDP flagship products/newsletter/policy briefs, based on project results, data and information, lessons learned and best practices.

- Formulating a framework for data sharing among stakeholders, for project implementation.

- Supporting the government with analysis and substantive research into national adaptation planning, and other major national and local development issues.

- Sharing international best practices on implementation of climate change adaptation policies and practices through participatory processes and techniques involving civil society, women and minority groups.

- Ensuring systemic capturing of key lessons learned generated by the project through feasibility studies, research, surveys as well as other primary and secondary sources to produce knowledge-based products.

- Participating in knowledge networks and other fora to draw on best practice and lessons learned in other similar contexts to apply to Yemen.

Required skills and expertise:

- Advanced University Degree (master's degree or equivalent) or bachelor’s degree in environmental science, Natural Resource Management, Environmental Economics, or other related fields.

- Master’s Level Degree with (2) years’ experience or Bachelor with at least 4 years of relevant professional work in experience on issues related to climate change, natural resources management, environment and community development.

- At least 5 years of project management experience in VF/or GCF funded projects.

- At least 5 years of proven experience working with ministries, national or provincial institutions and knowledge of the country’s institutional framework and policies related to climate change and natural resource management are desirable.

- Working/Consulting experience related to the area of climate change, national commitments under various International Conventions, water resources management, ecosystem restoration and biodiversity conservation is an advantage.

- Experience in working and coordinating with multi stakeholders including the government, NGOs, consultants, private sector, and CSOs is an advantage.

- Strong planning and organizational skills; ability to handle planning and budgeting or multiple concurrent projects/activities are desirable.

- Knowledge of relevant UNFCCC, COP-decisions, and national commitments will be an advantage.

- Sound understanding of developmental strategies - particularly focusing on community empowerment and participation.

Competencies

- Strong leadership, managerial and coordination skills, with a demonstrated ability to effectively coordinate the implementation of large multi-stakeholder projects, including financial and technical aspects.

- Ability to effectively manage technical and administrative teams, work with a wide range of stakeholders across various sectors and at all levels, to develop durable partnerships with collaborating agencies.

- Ability to administer budgets, train and work effectively with counterpart staff at all levels and with all groups involved in the project.

- Ability to coordinate and supervise multiple Project Implementation Units in their implementation of technical activities in partnership with a variety of subnational stakeholder groups, including community and government.

- Strong drafting, presentation and reporting skills.

- Strong communication skills, especially in timely and accurate responses to emails.

- Strong computer skills, in particular mastery of all applications of the MS Office package and internet search.

- Strong knowledge about the political and socio-economic context related to the Yemen climate change at national and subnational levels.

- Excellent command of English and Arabic languages.

NAP Lead Technical Specialist

The Technical Specialist will provide technical guidance on all climate policy and strategic related matters across the three outcomes of the project. He/She will be the main person responsible for establishing baselines on adaptation planning in Yemen by reviewing the climate and socio-economic information available, existing policies and strategies, alignment with the NDC and other UNFCCC related processes, and will provide quality assurance on all technical outputs.

Lead integration work and climate finance related activities:

- Provide overall technical supervision and support to the existing NAP coordinating committee, to conduct the NAP process, and to guarantee its national and local appropriation;

- Lead capacity building activities related to climate finance; o Lead technical studies that will contribute to concept note development;

- Lead activities related to budget integration;

- Oversee the review of institutional framework for climate change adaptation planning, budgeting and integration into national, sectoral and provincial processes and the GCF national coordination;

- Oversee the drafting of climate change law/decree is available and submitted to the Parliament’s Environmental Committee;

- Oversee the national and sectoral adaptation action prioritization aligned with the Climate Resilient Economy vision of the 2015-2019 National Development Plan and the preparation of guidelines on local – level CC integration;

- Identify climate finance needs and provide trainings to key ministries, local authorities, private sector, NGOs, and researchers on climate finance, including on-the-job mentoring of the National Office of Climate Change, Carbon and REDD (BN-CCCREDD);

- Develop a strategy to promote private sector investment on CCA, in the five priority sectors (agriculture, forestry, water, energy and health).

Required skills and expertise:

- A university degree (MSc or PhD) in a subject related to environment/development economics, natural resource management or environmental sciences, project management;

- Minimum seven (7) years of experience in policy analysis, advice and capacity development related to climate finance, and public policy/finance/budget management in developing countries;

Project Monitoring and Evaluation Expert (National UNV)

Under the overall supervision and guidance of the Project Manager, the M&E Expert will have the responsibility for project monitoring and evaluation. The M&E Expert will work closely with the Communication and Knowledge Management Specialist on knowledge management aspects of the project. Specific responsibilities will include:

- Review: how the project addresses country priorities; decision-making processes; the logframe indicators against progress made towards the end-of-project targets; the problem addressed by the project and the underlying assumptions; the relevance of the project strategy to assess whether it provides the most effective route towards expected/intended results.

- Support the development of the M&E framework, the project indicators and the baseline survey.

- Monitor project progress and participate in the production of progress reports ensuring that they meet the necessary reporting requirements and standards;

- Ensure project’s M&E meets the requirements of the Government, the UNDP Country Office, and UNDP- Climate Hub; develop project-specific M&E tools as necessary;

- Oversee and ensure the implementation of the project’s M&E plan, including periodic appraisal of the Project’s Theory of Change and Results Framework with reference to actual and potential project progress and results;

- Oversee/develop/coordinate the implementation of the stakeholder engagement plan;

- Oversee and guide the design of surveys/ assessments commissioned for monitoring and evaluating project results;

- Facilitate annual reviews of the project and produce analytical reports from these annual reviews, including learning and other knowledge management products;

- Support project site M&E and learning missions;

- Visit project sites as and when required to appraise project progress on the ground and validate written progress reports.

The Project M&E Expert will be recruited based on the following qualifications

- Masters degree, preferably in the field of environmental or natural resources management;

- At least five years of relevant work experience preferably in a project management setting involving multi-lateral/ international funding agency. Previous experience with UN project will be a definite asset;

- Significant experience in collating, analyzing and writing up results for reporting purposes;

- Very good knowledge of results-based management and project cycle management, particularly with regards to M&E approach and methods. Formal training in RBM/ PCM will be a definite asset;

- Knowledge and working experience of the application of gender mainstreaming in international projects;

- Understanding of biodiversity conservation, law enforcement, sustainable livelihoods and associated issues;

- Very good inter-personal skills;

- Proficiency in computer application and information technology.

- Excellent language skills in English (writing, speaking and reading) and in Arabic languages.

Project Administrative and Financial Assistant

Under the guidance and supervision of the Project Manager, the Project Administrative and Financial Assistant will have the following specific responsibilities:

- Keep records of project funds and expenditures, and ensure all project-related financial documentation are well maintained and readily available when required by the Project Manager;

- Review project expenditures and ensure that project funds are used in compliance with the Project Document and financial rules and procedures;

- Provide necessary financial information as and when required for project management decisions;

- Provide necessary financial information during project audit(s);

- Review annual budgets and project expenditure reports, and notify the Project Manager if there are any discrepancies or issues;

- Provide PMU-related administrative and logistical assistance in organizing training events, workshops and meetings.

- Assist in recruitment process of experts, consultants, and in the preparation of their contracts.

- Assist international, short-term consultants by organizing their travel schedules, arranging meetings with different stakeholders; draft necessary correspondence with local and national agencies and stakeholders;

- Assist in the timely issuance of contracts and issuance of other eligible entitlements of the project personnel, experts, and consultants;

- Prepare financial status reports, progress reports, and others;

- Provide other substantive support to the team for overall implementation;

The Project Administrative and Financial Assistant will be recruited based on the following qualifications:

- A Bachelor’s degree or an advanced diploma in accounting/ financial management;

- At least five years of relevant work experience preferably in a project management setting involving multi-lateral/ international funding agency. Previous experience with UNDP or UN project will be a definite asset;

- Proficiency in the use of computer software applications particularly MS Excel;

- Excellent language skills in English (writing, speaking and reading) and in Arabic as well.

Project Communication and Knowledge Management Specialist

Under the overall supervision and guidance of the Project Manager, the Communication and Knowledge Management Specialist will have the responsibility for leading knowledge management outputs in Component 4 and developing the project communications strategy at the project outset and coordinating its implementation across all project components. The Communication and Knowledge Management Specialist will work closely with the M&E Expert on knowledge management aspects of the project.

Specific responsibilities will include:

- Develop a project communications strategy / plan which will target civil society organizations and the private sector at national level and in the priority provinces of Yemen, incorporate it with the annual work plans and update it annually in consultation with project stakeholders and coordinate its implementation;

- Coordinate the implementation of knowledge management outputs of the project; identify case studies demonstrating the link between building adaptation capacity and reducing vulnerability (i.e. reflecting the overall NAP objectives);

- Coordinate and oversee the implementation of public awareness activities across all project components;

- Facilitate the design and maintenance of the project website/webpages and ensure it is up-to-date and dynamic;

- Facilitate learning and sharing of knowledge and experiences relevant to the project;

- Design inception workshop information and booklets;

- Work with the project team and country teams to collect best practices and lessons learned related to the NAP process;

- Disseminate through appropriate channels (not exclusive to the NAP platform);

- Support the development of outreach activities such as flyers on climate change impacts, trainings for community radios etc.;

- Develop print, web-based and video products detailing case studies;

- Be responsible for documenting trainings, meetings, and outreach sessions through video and photo, provide summaries, and develop web based and print products detailing meetings;

- Provide graphic design and type-setting assistance for printed products such as project document, flyers, posters, policy briefs, and annual reports;

- Work with communications staff at the regional hub to draft and publish content for the Adaptation website;

- Maintain social media updates on the project in conjunction with the CO Communications staff.

The Project Communication and Knowledge Management Specialist will be recruited based on the following qualifications:

- A Bachelor’s degree, preferably in the field of community development or natural resource / environmental management;

- A communications qualification (diploma, Bachelor’s degree)

- At least three years of relevant work experience of communications for project or programme implementation, ideally involving international donors. Previous experience with UN projects will be a definite asset;

- Previous experience in developing and implementing communications strategies for organizations or projects

- Strong professional working capacity to use information and communications technology, specifically including website design and desk top publishing software

- Understanding of illegal wildlife trade, biodiversity conservation, sustainable livelihoods and associated issues;

- Very good inter-personal skills

- Excellent language skills in English (writing, speaking and reading) and in local languages

## ANNEX E: UNDP Risk Log

| Risk category | Specific risk(s) / Risk(s) description | Probability of occurrence (low, medium, high) | Impact level (low, medium, high) | Mitigation action(s) If relevant, specify the strategies adopted by the ongoing readiness grant in the country to mitigate the risks | Entity(ies) responsible to manage the risk(s) |
| --- | --- | --- | --- | --- | --- |
| Operational | Risk 1: Lack of political will and stakeholder capacity to maintain effective inter-ministerial coordination, and CCA M&E systems | Low | Medium | To mitigate the risk of limited political will and stakeholder capacity, the project will engage high-level leadership to secure commitments for institutionalizing inter-ministerial coordination and CCA M&E systems, while providing targeted training and technical assistance to strengthen capacity at all levels. The project will also embed these systems within existing structures to ensure sustainability and foster stakeholder ownership through regular consultations and workshops. | MoWE UNDP |
| Political | Risk 2: Limited institutional capacity may hinder the integration of adaptation into national and sectoral policies and plans. | Low | Medium | To mitigate the risk of limited institutional capacity hindering the integration of adaptation into national and sectoral policies, the project will provide targeted capacity-building programs and technical assistance to enhance the skills and knowledge of key institutions. It will embed adaptation planning into existing policy frameworks and processes, ensuring alignment with national priorities. Additionally, the project will foster cross-sectoral collaboration through multi-stakeholder platforms and support the development of clear guidelines and tools to streamline the integration process. | MoWE UNDP |
| Stakeholder engagement | Risk 3: Lack of agreement on data sharing for development and analysis of climate risks and impacts in targeted sectors | Low | Medium | To mitigate the risk of lack of agreement on data sharing for climate risk and impact analysis, the project will establish formal data-sharing agreements and protocols among key stakeholders to ensure clarity and accountability. It will promote trust and collaboration through regular stakeholder dialogues and workshops, highlighting the mutual benefits of shared data for informed decision-making and sectoral planning. The project will also support the development of centralized data platforms to facilitate access and use while ensuring data security and ownership concerns are addressed. | MoWE UNDP MoH MoA MoFI |
| Technical | Risk 4: Inadequate financing for long-term implementation due to limited financial and technical capacity, lack of climate data and strategies for long-term systematic development of bankable CCA projects | Low | Medium | The project will address the lack of adaptation finance by developing two priority concept notes for cross-sectoral projects, supported by pre-feasibility studies. A cross-sectoral NAP Finance Working Group will be established to steer the financing strategy for the adaptation project pipeline and develop a long-term funding strategy for CCA in Yemen | MoWE MoPIC UNDP |
| Operational | Risk 5: Delays in GCF disbursements and the recruitment of project staff and experts. | Medium | High | This may slow down the implementation of key activities, affecting project timelines and deliverables. To mitigate delays in GCF disbursements and staff recruitment, the project will closely monitor disbursement schedules and maintain proactive communication with GCF to expedite fund transfers. Timely submission of disbursement requests with all required documentation will help prevent administrative delays. Recruitment processes will be initiated early, utilizing roster mechanisms. |  |
| Environmental/Social | Risk 6: Limited inclusion of women and marginalized groups in NAP processes and consultations may lead to inequitable adaptation planning | Medium | Medium | Conduct gender analysis and develop a GAP; ensure gender balanced participation in consultations, support women’s CSOs to engage in policy dialogue. | MoWE, UNDP, EPA |
| Institutional Sustainability | Risk 7: High staff turnover in public institutions may undermine the retention of technical capacity developed through the NAP project | Medium | High | Institutionalize training via national curricula, implement ToT models, document procedures and tools into SOPs for institutional memory. | MoWE, EPA, UNDP |

## Annex F: UNDP Project Quality Assurance Report

Country Programme (2024). GCF. https://www.greenclimate.fund/sites/default/files/document/yemen-country-programme.pdf

https://www.adaptation-undp.org/explore/arab-states/yemen

https://www.undp.org/arab-states/publications/impact-climate-change-human-development-yemen

https://documents1.worldbank.org/curated/en/099111824082514197/pdf/P5006381e44f0109719b871d68f6833548e.pdf

Climate Risk Profile: Yemen (2023): The World Bank Group

Using the WB Climate change Knowledge Portal. https://climateknowledgeportal.worldbank.org/country/yemen-rep/climate-data-projections

Development indicators are mainly derived from the World Bank Human Development Report. https://databank.worldbank.org/Human-development-index/id/363d401b

https://reliefweb.int/report/yemen/climate-change-impacts-yemen-and-adaptation-strategies

https://www.oxfam.org/en/yemen-brink-conflict-pushing-millions-towards-famine

UNDP Human Development Report https://hdr.undp.org/data-center/thematic-composite-indices/gender-inequality-index#/indicies/GII

World Bank’s Yemen Country Climate and Development report https://documents1.worldbank.org/curated/en/099111824082514197/pdf/P5006381e44f0109719b871d68f6833548e.pdf

https://www.undp.org/arab-states/publications/impact-climate-change-human-development-yemen

Yemen Country Climate and Development Report, World Bank (2024). https://openknowledge.worldbank.org/server/api/core/bitstreams/45f4c808-a757-4d01-9aef-b9a4f37d6c7c/content

Yemen’s Third National Communication to the UNFCCC (2018).

United Nations Development Programme (UNDP). (2020). Yemen Climate Change Adaptation Strategies.

National Adaptation Programme of Action (NAPA) – Yemen. (2009).

World Bank. (2020). Climate Change and Water Resources in Yemen: Policy Options and Challenges.

Examples include, The IPCC risk framework; UNFCCC Vulnerability and Adaptation Assessment Guidelines, World Bank Climate and Disaster Risk Screening Tools; Climate Resilience Evaluation and Awareness Tool (CREAT); Coastal Hazard Wheel Framework, Integrated Risk Assessment Framework (IRAF), Health Vulnerability and Adaptation Assessment Framework (WHO), FAO Climate Risk Assessment Framework for Agriculture

See https://www.undp.org/accountability/transparency/information-disclosure-policy

Excluding project team staff time and UNDP staff time and travel expenses.

The costs of UNDP Country Office and UNDP-Climate Hub Unit’s participation and time are charged to the GCF Agency Fee.

See https://popp.undp.org/_layouts/15/WopiFrame.aspx?sourcedoc=/UNDP_POPP_DOCUMENT_LIBRARY/Public/PPM_Project%20Management_Closing.docx&action=default.

To be used where UNDP is the Implementing Partner

To be used where the UN, a UN fund/programme or a specialized agency is the Implementing Partner

Risk categories can include: Operational, Political, Stakeholder engagement, Implementation, Natural-hazards related disasters, Unsustainability, Compliance, Money laundering, terrorist financing and prohibited practices, etc.