## Summary
UNDP
| Item line budget* |  |  |  | Budgeted Work Plan*
Detailed description | $ | Unit | Quantity | Total* | Year 1 | Year 2 | Year 3 | Responsible Agency | Total* | Reporting Object class
Policy dialogue with parliamentarians, civil society, and other stakeholders to advocate for the bill. |  | Workshop | 2 | 20000 | 10000 | 5000 | 5000 | UNDP |  | Travel | TRUE
Collaborate with the Ministry of Justice and other relevant authorities to draft and refine the bill. |  | Collaboration | 3 | 20000 | 10000 | 10000 |  | UNDP |  | Contractual Services | TRUE
Advocate for amendments through collaboration with parliamentarians and civil society. |  | Advocacy | 3 | 20000 | 10000 | 10000 |  | UNDP |  | Contractual Services | TRUE
Support the Ministry of Local Government and Rural Development in policy revision. |  | Support | 5 | 30000 | 15000 | 5000 | 10000 | UNDP |  | Supplies | TRUE
Conduct public consultations and campaigns to gather input and build consensus. |  | Advocacy | 5 | 40000 | 30000 | 5000 | 5000 | UNDP |  | Travel | TRUE
Collaborate with the Ministry of Finance and National Planning to draft the sin tax policy. |  | Collaboration | 5 | 20000 | 10000 | 5000 | 5000 | UNDP |  | Contractual Services | TRUE
Establish a transparent allocation criterion for NCD prevention and control programs. |  | Criterion Dev | 3 | 15000 | 10000 | 5000 | 0 | UNDP |  | Supplies | TRUE
Develop an implementation and monitoring framework for the sin tax policy. |  | Framework | 5 | 15000 | 15000 | 0 | 0 | UNDP |  | Contractual Services | TRUE
Identify and engage key stakeholders from various sectors (government, food industry, academia). |  | Engagement | 5 | 40000 | 20000 | 10000 | 10000 | UNDP |  | Contractual Services | TRUE
Covene platforrms to facilitate implementation and monitor of NCDs and Mental Health. |  | Meetings | 6 | 20000 | 10000 | 10000 | 0 | UNDP |  | Travel | TRUE
Identify key programmatic areas and form relevant working groups. |  | Identification | 2 | 20000 | 10000 | 10000 |  | UNDP |  | Supplies | TRUE
Recruit and train young people as health champions and peer mentors. |  | Training | 2 | 15000 | 5000 | 5000 | 5000 | UNDP |  | Supplies | TRUE
Organize peer-led workshops and support groups. |  | Workshops | 5 | 20000 | 10000 | 10000 |  | UNDP |  | Travel | TRUE
Develop creative art and sport activities for youth and prevention of Mental health |  | Creative work | 3 | 37984 | 15000 | 10430 |  | UNDP |  |  | FALSE
Develop and promote telehealth services, online counseling platforms, and mental health apps. |  | Development | 1 | 30000 | 30000 |  |  | UNDP |  | Contractual Services | TRUE
Subtotal |  |  |  | 362984 | 210000 | 100430 | 40000
GMS 7% |  |  |  | 25408.88 | 14700 | 7030.1 | 2800
GRAND TOTAL |  |  |  | 388392.88 | 224700 | 107460.1 | 42800
UNICEF
| Item line budget* |  |  |  | Budgeted Work Plan*
Detailed description | $ | Unit | Quantity | Total* | Year 1 | Year 2 | Year 3 | Responsible Agency | Total* | Reporting Object class
Organize community outreach programs to educate the public about the benefits of the Tobacco Control Bill. |  | Program | 2 | 15000 | 5000 | 5000 | 5000 | UNICEF |  | Contractual Services
Develop and distribute educational materials on NCD prevention. |  | Materials | 10 | 30000 | 10000 | 10000 | 10000 | UNICEF |  | Supplies
Create gamified health education apps to engage youth in healthy behaviors. |  | App | 1 | 35000 | 35000 | 0 | 0 | UNICEF |  | Contractual Services
Monitor and evaluate the effectiveness of digital interventions |  | Monitoring | 5 | 10000 |  | 5000 | 5000 | UNICEF |  | Supplies
Design and test interventions using behavioral insights. |  | Intervention Design | 3 | 34080 | 15000 | 10000 | 9080 | UNICEF |  | Supplies
Scale up successful interventions. |  | Scale-up | 5 | 30000 |  | 10000 | 20000 | UNICEF |  | Travel
Subtotal |  |  |  | 154080 | 65000 | 40000 | 49080
Admin Cost 7% |  |  |  | 10785.6 | 4550 | 2800 | 3435.6
GRAND TOTAL UNICEF |  |  |  | 164865.6 | 69550 | 42800 | 52515.6
WHO
Table 1: Detailed Budget by Results
| Item line budget* |  |  |  | Budgeted Work Plan*
Detailed description | $ | Unit | Quantity | Total* | Year 1 | Year 2 | Year 3 | Responsible Agency | Total* | Reporting Object class
Work with the Ministry of Green Economy and Environment, Ministry of Commerce, Trade and Industry, Ministry of Health, and Food Manufacturers. |  | Collaboration | 4 | 30000 | 10000 | 10000 | 10000 | WHO |  | Supplies
Conduct workshops and consultations to develop the policy. |  | Workshop | 3 | 40000 | 20000 | 10000 | 10000 | WHO |  | Travel
Implement and monitor the standards through regular assessments and compliance checks. |  | Assessment | 8 | 50000 | 10000 | 30000 | 10000 | WHO |  | Contractual Services
Develop a framework for coordination and collaboration for NCDs and Mental Health. |  | Framework | 1 | 30000 | 10000 | 10000 | 10000 | WHO |  | Supplies
Develop a financing and operational strategy for NCD prevention and control. |  | Strategy | 1 | 54000 | 18000 | 18000 | 18000 | WHO |  | Contractual Services
Develop and implement a strategy for monitoring and preventing from vested interests of the tobacco, alcohol, and food industries on the working groups. |  | Monitoring | 5 | 20000 | 15000 | 5000 |  | WHO |  | Contractual Services
Conduct research to understand behavioral drivers related to tobacco use, alcohol consumption, and unhealthy diets. |  | Research | 3 | 20000 | 10000 | 10000 |  | WHO |  | Contractual Services
Monitor and evaluate the effectiveness of integrated mental health services |  | Monitoring | 5 | 10000 | 5000 | 5000 |  | WHO |  | Supplies
Integrate mental health services into existing health care and educational facilities. |  | Integration | 3 | 20000 | 10000 | 5000 | 5000 | WHO |  | Supplies
Provide training and resources to support mental health service delivery. |  | Training | 5 | 20000 | 10000 | 5000 | 5000 | WHO |  | Contractual Services
Develop and deliver training programs for healthcare workers. |  | Training | 5 | 36642 | 12214 | 12214 | 12214 | WHO |  | Contractual Services
Provide ongoing support and supervision to ensure quality care. |  | Support | 5 | 30000 | 10000 | 10000 | 10000 | WHO |  | Supplies
Conduct regular assessments to identify training needs and gaps |  | Assessment | 5 | 20000 | 10000 | 10000 |  | WHO |  | Travel
Staff |  | Staff |  | 30000 | 10000 | 10000 | 10000 | WHO |  | Staff
Operations |  | Operations |  | 6000 | 2000 | 2000 | 2000 |  |  | Operations
Subtotal WHO |  |  |  | 416642 | 162214 | 152214 | 102214
Admin Cost 7% |  |  |  | 29164.94 | 11354.98 | 10654.98 | 7154.98
GRAND TOTAL |  |  |  | 445806.94 | 173568.98 | 162868.98 | 109368.98
Summary
| Agency | Request Support | Contribution | Total
| WHO | 445806.94 | 50000 | 495806.94
| UNDP | 388392.88 | 50000 | 438392.88
| UNICEF | 164865.6 | 50000 | 214865.6
|  | 999065.42 | 150000 | 1149065.42

## Tab1. Detailed budget
Project Title: Enhancing Youth Health through Governance and Policy for NCD and Mental Health Prevention
Implementing Organization: WHO, UNDP, UNICEF
Country: Zambia
Date submission: 12 July 2024
Table 1: Detailed Budget by Results
|  | Item line budget* |  |  |  | Budgeted Work Plan*
| Detailed description | $ | Unit | Quantity | Total* | Year 1 | Year 2 | Year 3 | Responsible Agency | Total* | Reporting Object class
O1 | Objective 1: Policies and Laws for NCDs, tobacco control, alcohol misuse, sodium and sugar in processed food regulations and mental health developed by 2027
EA1 | Expected Outcome (EO) 1.1: Strengthened policy environment and taxation for reducing risk factors and improving population health.
EA1.1 | Output 1.1: The Tobacco Control Bill is aligned with WHO FCTC and presented in the parliamant, |  |  |  | 55000 | 25000 | 20000 | 10000 |  | 55000 | Guidance: 1. Please leave blank the cell in correspondence to the total by Output, and instead specify the object class in each of the breakdown line. 2. Even if the whole Output fall into one object class, please repeat it in each row. 3. Pls use only and solely the provided list in "budget summary by obj class".Do not add any word or description. See example.
| Policy dialogue with parliamentarians, civil society, and other stakeholders to advocate for the bill. |  | Policy | 2 | 20000 | 10000 | 5000 | 5000 | UNDP |  | Travel
| Organize community outreach programs to educate the public about the benefits of the Tobacco Control Bill. |  | Program | 2 | 15000 | 5000 | 5000 | 5000 | UNICEF |  | Contractual Services
| Collaborate with the Ministry of Justice and other relevant authorities to draft and refine the bill. |  | Collaboration | 3 | 20000 | 10000 | 10000 |  | UNDP |  | Contractual Services
[5 empty] | 0 |  |  |  |  | 0
EA1.2 | Output 1.2: The Alcohol Licensing Act and National Alcohol Policy are amended |  |  |  | 90000 | 55000 | 20000 | 15000 |  | 90000
| Advocate for amendments through collaboration with parliamentarians and civil society. |  | Advocacy | 3 | 20000 | 10000 | 10000 |  | UNDP |  | Contractual Services
| Support the Ministry of Local Government and Rural Development in policy revision. |  | Support | 5 | 30000 | 15000 | 5000 | 10000 | UNDP |  | Supplies
| Conduct public consultations and campaigns to gather input and build consensus. |  | Advocacy | 5 | 40000 | 30000 | 5000 | 5000 | UNDP |  | Travel
EA1.3 | Output 1.3:Comprehensive Health tax policy developed and implemented |  |  |  | 50000 | 35000 | 10000 | 5000 |  | 50000
| Collaborate with the Ministry of Finance and National Planning to draft the Health tax policy. |  | Collaboration | 5 | 20000 | 10000 | 5000 | 5000 | UNDP |  | Contractual Services
| Establish a transparent allocation criterion for NCD prevention and control programs. |  | Criterion Dev | 3 | 15000 | 10000 | 5000 | 0 | UNDP |  | Supplies
| Develop an implementation and monitoring framework for the health tax policy. |  | Framework | 5 | 15000 | 15000 | 0 | 0 | UNDP |  | Contractual Services
EA1.4 | Output 1.4: National policy/strategy/standards on sodium and sugar content in processed foods developed and implemented |  |  |  | 150000 | 50000 | 60000 | 40000 |  | 150000
| Work with the Ministry of Green Economy and Environment, Ministry of Commerce, Trade and Industry, Ministry of Health, and Food Manufacturers. |  | Collaboration | 4 | 30000 | 10000 | 10000 | 10000 | WHO |  | Supplies
| Consultations to develop the policy and standards for sodium and sugar |  | Consultations | 3 | 40000 | 20000 | 10000 | 10000 | WHO |  | Travel
| Implement and monitor the standards through regular assessments and compliance checks. |  | Assessment | 8 | 80000 | 20000 | 40000 | 20000 | WHO |  | Contractual Services
EA1 | EO 1.1 Subtotal |  |  |  | 345000 | 165000 | 110000 | 70000 |  | 345000
EA2 | EO 2: Transformation of Systems to address NCDs and Mental Health:
EA2.1 | Output 2.1:NCM established to implement the Health in All Policies Framework |  |  |  | 190000 | 85000 | 65000 | 40000 |  | 190000
| Identify and engage key stakeholders from various sectors (government, food industry, academia). |  | Engagement | 5 | 40000 | 20000 | 10000 | 10000 | UNDP |  | Contractual Services
| Develop a framework for coordination and collaboration for NCDs and Mental Health. |  | Framework | 1 | 30000 | 10000 | 10000 | 10000 | WHO |  | Supplies
| Covene platforms to facilitate implementation and monitor of NCDs and Mental Health. |  | Monitoring | 6 | 20000 | 10000 | 10000 | 0 | UNDP |  | Travel
| Develop a financing and operational strategy for NCD prevention and control. |  | Strategy | 1 | 60000 | 20000 | 20000 | 20000 | WHO |  | Contractual Services
| Identify key programmatic areas and form relevant working groups. |  | Identification | 2 | 20000 | 10000 | 10000 |  | UNDP |  | Supplies
| Develop and implement a strategy for monitoring and preventing from vested interests of the tobacco, alcohol, and food industries on the working groups. |  | Monitoring | 5 | 20000 | 15000 | 5000 |  | WHO |  | Contractual Services
| EO 2 Subtotal |  |  |  | 190000 |  |  |  |  | 0
| EO 3: Improved healthty behaviors to prevent NCDs among youth (Harmful use of Alcohol and smoking) |  |  |  | 0 |  |  |  |  | 0
EA3.1 | Output 3.1: Increased awareness among adolescents and youth in schools, colleges, universities, and communities |  |  |  | 75000 | 45000 | 15000 | 15000 |  | 75000
| Develop and distribute educational materials on NCD prevention. |  | Materials | 10 | 30000 | 10000 | 10000 | 10000 | UNICEF |  | Supplies
| Create gamified health education apps to engage youth in healthy behaviors. |  | App | 1 | 35000 | 35000 | 0 | 0 | UNICEF |  | Contractual Services
| Monitor and evaluate the effectiveness of digital interventions |  | Monitoring | 5 | 10000 |  | 5000 | 5000 | UNICEF |  | Supplies
EA3.2 | Output 3.2: Effective interventions designed and tested to change youth behaviors. |  |  |  | 84080 | 25000 | 30000 | 29080 |  | 84080
| Conduct research to understand behavioral drivers related to tobacco use, alcohol consumption, and unhealthy diets. |  | Research | 3 | 20000 | 10000 | 10000 |  | WHO |  | Contractual Services
| Design and test interventions using behavioral insights. |  | Intervention Design | 3 | 34080 | 15000 | 10000 | 9080 | UNICEF |  | Supplies
| Scale up successful interventions. |  | Scale-up | 5 | 30000 |  | 10000 | 20000 | UNICEF |  | Travel
EA3 | EO 3 Subtotal |  |  |  | 159080 | 70000 | 45000 | 44080 |  | 159080
EA34 | EO 4: Increased Institutional capacity and investment in Mental Health Services for Youth
EA4.1 | Output 4.1: Increased understanding of mental health conditions and importance of seeking help. |  |  |  | 82984 | 32661.3333 | 32661.3333 | 17661.3333 |  | 82984
| Recruit and equip young people with knowledge as health champions and peer mentors. |  | Orientation | 2 | 15000 | 5000 | 5000 | 5000 | UNDP |  | Supplies
| Organize peer-led workshops and support groups. |  | Workshops | 5 | 20000 | 10000 | 10000 |  | UNDP |  | Travel
| Monitor and evaluate the effectiveness of integrated mental health services |  | Monitoring | 5 | 10000 | 5000 | 5000 |  | WHO |  | Supplies
| Develop creative art and sport activities for youth and prevention of Mental health |  | Creative work | 3 | 37984 | 12661.3333 | 12661.3333 | 12661.3333 | UNDP
EA4.2 | Output 4.2: Increased access to mental health services through digital tools |  |  |  | 30000 | 30000 | 0 | 0 |  | 30000
| Develop and promote telehealth services, online counseling platforms, and mental health apps. |  | Development | 1 | 30000 | 30000 |  |  | UNDP |  | Contractual Services
EA4.3 | Output 4.3: Expanded access to mental health services in primary health care, schools, youth resource centers, and community centers |  |  |  | 40000 | 20000 | 10000 | 10000 |  | 40000
| Integrate mental health services into existing health care and educational facilities. |  | Integration | 3 | 20000 | 10000 | 5000 | 5000 | WHO |  | Supplies
| Provide tools and resources to support mental health service delivery. |  | Tools | 5 | 20000 | 10000 | 5000 | 5000 | WHO |  | Contractual Services
EA4.4 | Output 4.4: Healthcare workers at primary health care level equipped with skills and knowledge in mental health care |  |  |  | 86642 | 32214 | 32214 | 22214 |  | 86642
| Develop and deliver mental health capacity building programs for healthcare workers. |  | Training | 5 | 36642 | 12214 | 12214 | 12214 | WHO |  | Contractual Services
| Provide ongoing support and supervision to ensure quality care. |  | Support | 5 | 30000 | 10000 | 10000 | 10000 | WHO |  | Supplies
| Conduct regular assessments to identify training needs and gaps |  | Assessment | 5 | 20000 | 10000 | 10000 |  | WHO |  | Travel
[5 empty] | 0 |  |  |  |  | 0
EA4.5 | Output 4.5: This is further detailed below as follows: |  |  |  | 0 | 0 | 0 | 0 |  | 0
[5 empty] | 0 |  |  |  |  | 0
[5 empty] | 0 |  |  |  |  | 0
[5 empty] | 0 |  |  |  |  | 0
[5 empty] | 0 |  |  |  |  | 0
[5 empty] | 0 |  |  |  |  | 0
EA3 | EO 1.4 Subtotal |  |  |  | 239626 | 114875.3333 | 74875.3333 | 49875.3333 |  | 239626
| Objective 1 Sub-Total |  |  |  | 345000 | 165000 | 110000 | 70000 | 0 | 345000
| Objective 2 Sub-Total |  |  |  | 190000 | 85000 | 65000 | 40000 | 0 | 190000
| Objective 3 Sub-Total |  |  |  | 159080 | 70000 | 45000 | 44080 | 0 | 159080
| Objective 4 Sub-Total |  |  |  | 239626 | 114875.3333 | 74875.3333 | 49875.3333 | 0 | 239626
| GRAND TOTAL |  |  |  | 933706 | 434875.3333 | 294875.3333 | 203955.3333 | 0 | 933706
Coord | Other Project Inputs (including project management, monitoring and evaluation, and other costs that cannot be directly attributed to an Output) |  |  |  | 65359.42 | 21786.4733 | 21786.4733 | 21786.4733 |  | 65359.42
| WHO admin cost | 7% | Admin Cost |  | 29164.94 | 9721.6467 | 9721.6467 | 9721.6467 |  | 29164.94
| UNDP GMS | 7% | Admin Cost |  | 25408.88 | 8469.6267 | 8469.6267 | 8469.6267 |  | 25408.88
| UNICEF Admin Cost | 7% | Admin Cost |  | 10785.6 | 3595.2 | 3595.2 | 3595.2 |  | 10785.6
[5 empty] | 0 |  |  |  |  | 0
[5 empty] | 0 |  |  |  |  | 0
[5 empty] | 0 |  |  |  |  | 0
[5 empty] | 0 |  |  |  |  | 0
[5 empty] | 0 |  |  |  |  | 0
[5 empty] | 0 |  |  |  |  | 0
[5 empty] | 0 |  |  |  |  | 0
[5 empty] | 0 |  |  |  |  | 0
[5 empty] | 0 |  |  |  |  | 0
| Total Project Cost (Requested from H4LF) - A |  |  |  |  | 434875.3333 | 294875.3333 | 203955.3333 |  | 933706 | Guidance: Please ensure the Total Project Cost values result as the sum of the Objectives Sub-totals. In this regard, particular attention should be given when adding rows for (1 )additional activities and/or (2) for additional item lines under each activities: in inserting new row, please copy formatting and formulas from the existing section of the template.
| Programme support costs for PUNO(s) (7% of the total project cost above) -B |  |  |  |  | 21786.4733 | 21786.4733 | 21786.4733 |  | 65359.42
| TOTAL Project BUDGET - requested from H4LF (total programme costs A + Programme Support Cost B) |  |  |  |  | 456661.8067 | 316661.8067 | 225741.8067 |  | 999065.42

## Budget by PUNO
WHO
Project Title: Enhancing Youth Health through Governance and Policy for NCD and Mental Health Prevention | Item line budget* |  |  |  | Budgeted Work Plan*
Detailed description | $ | Unit | Quantity | Total* | Year 1 | Year 2 | Year 3 | Responsible Agency | Total* | Reporting Object class
Work with the Ministry of Green Economy and Environment, Ministry of Commerce, Trade and Industry, Ministry of Health, and Food Manufacturers. |  | Collaboration | 4 | 30000 | 10000 | 10000 | 10000 | WHO |  | Supplies
Consultations to develop the policy and standards for sodium and sugar |  | Consultations | 3 | 40000 | 20000 | 10000 | 10000 | WHO |  | Travel
Implement and monitor the standards through regular assessments and compliance checks. |  | Assessment | 8 | 80000 | 20000 | 40000 | 20000 | WHO |  | Contractual Services
Develop a framework for coordination and collaboration for NCDs and Mental Health. |  | Framework | 1 | 30000 | 10000 | 10000 | 10000 | WHO |  | Supplies
Develop a financing and operational strategy for NCD prevention and control. |  | Strategy | 1 | 60000 | 20000 | 20000 | 20000 | WHO |  | Contractual Services
Develop and implement a strategy for monitoring and preventing from vested interests of the tobacco, alcohol, and food industries on the working groups. |  | Monitoring | 5 | 20000 | 15000 | 5000 |  | WHO |  | Contractual Services
Conduct research to understand behavioral drivers related to tobacco use, alcohol consumption, and unhealthy diets. |  | Research | 3 | 20000 | 10000 | 10000 |  | WHO |  | Contractual Services
Monitor and evaluate the effectiveness of integrated mental health services |  | Monitoring | 5 | 10000 | 5000 | 5000 |  | WHO |  | Supplies
Integrate mental health services into existing health care and educational facilities. |  | Integration | 3 | 20000 | 10000 | 5000 | 5000 | WHO |  | Supplies
Provide tools and resources to support mental health service delivery. |  | Tools | 5 | 20000 | 10000 | 5000 | 5000 | WHO |  | Contractual Services
Develop and deliver mental health capacity building programs for healthcare workers. |  | Training | 5 | 36642 | 12214 | 12214 | 12214 | WHO |  | Contractual Services
Provide ongoing support and supervision to ensure quality care. |  | Support | 5 | 30000 | 10000 | 10000 | 10000 | WHO |  | Supplies
Conduct regular assessments to identify training needs and gaps |  | Assessment | 5 | 20000 | 10000 | 10000 |  | WHO |  | Travel
Sub Total |  |  |  | 416642 | 162214 | 152214 | 102214
Admin Cost (7%) |  |  |  | 29164.94 | 11354.98 | 10654.98 | 7154.98
GRAND TOTAL |  |  |  | 445806.94 | 173568.98 | 162868.98 | 109368.98
UNDP
Project Title: Enhancing Youth Health through Governance and Policy for NCD and Mental Health Prevention | Item line budget* |  |  |  | Budgeted Work Plan*
Detailed description | $ | Unit | Quantity | Total* | Year 1 | Year 2 | Year 3 | Responsible Agency | Total* | Reporting Object class
Policy dialogue with parliamentarians, civil society, and other stakeholders to advocate for the bill. |  | Policy | 2 | 20000 | 10000 | 5000 | 5000 | UNDP |  | Travel
Collaborate with the Ministry of Justice and other relevant authorities to draft and refine the bill. |  | Collaboration | 3 | 20000 | 10000 | 10000 |  | UNDP |  | Contractual Services
Advocate for amendments through collaboration with parliamentarians and civil society. |  | Advocacy | 3 | 20000 | 10000 | 10000 |  | UNDP |  | Contractual Services
Support the Ministry of Local Government and Rural Development in policy revision. |  | Support | 5 | 30000 | 15000 | 5000 | 10000 | UNDP |  | Supplies
Conduct public consultations and campaigns to gather input and build consensus. |  | Advocacy | 5 | 40000 | 30000 | 5000 | 5000 | UNDP |  | Travel
Collaborate with the Ministry of Finance and National Planning to draft the Health tax policy. |  | Collaboration | 5 | 20000 | 10000 | 5000 | 5000 | UNDP |  | Contractual Services
Establish a transparent allocation criterion for NCD prevention and control programs. |  | Criterion Dev | 3 | 15000 | 10000 | 5000 | 0 | UNDP |  | Supplies
Develop an implementation and monitoring framework for the health tax policy. |  | Framework | 5 | 15000 | 15000 | 0 | 0 | UNDP |  | Contractual Services
Identify and engage key stakeholders from various sectors (government, food industry, academia). |  | Engagement | 5 | 40000 | 20000 | 10000 | 10000 | UNDP |  | Contractual Services
Covene platforms to facilitate implementation and monitor of NCDs and Mental Health. |  | Monitoring | 6 | 20000 | 10000 | 10000 | 0 | UNDP |  | Travel
Identify key programmatic areas and form relevant working groups. |  | Identification | 2 | 20000 | 10000 | 10000 |  | UNDP |  | Supplies
Recruit and equip young people with knowledge as health champions and peer mentors. |  | Orientation | 2 | 15000 | 5000 | 5000 | 5000 | UNDP |  | Supplies
Organize peer-led workshops and support groups. |  | Workshops | 5 | 20000 | 10000 | 10000 |  | UNDP |  | Travel
Develop creative art and sport activities for youth and prevention of Mental health |  | Creative work | 3 | 37984 | 12661.3333 | 12661.3333 | 12661.3333 | UNDP
Develop and promote telehealth services, online counseling platforms, and mental health apps. |  | Development | 1 | 30000 | 30000 |  |  | UNDP |  | Contractual Services
Sub Total |  |  |  | 362984 | 207661.3333 | 102661.3333 | 52661.3333
GMS (7%) |  |  |  | 25408.88 | 14536.2933 | 7186.2933 | 3686.2933
GRAND TOTAL |  |  |  | 388392.88 | 222197.6267 | 109847.6267 | 56347.6267
UNICEF
Project Title: Enhancing Youth Health through Governance and Policy for NCD and Mental Health Prevention | Item line budget* |  |  |  | Budgeted Work Plan*
Detailed description | $ | Unit | Quantity | Total* | Year 1 | Year 2 | Year 3 | Responsible Agency | Total* | Reporting Object class
Organize community outreach programs to educate the public about the benefits of the Tobacco Control Bill. |  | Program | 2 | 15000 | 5000 | 5000 | 5000 | UNICEF |  | Contractual Services
Develop and distribute educational materials on NCD prevention. |  | Materials | 10 | 30000 | 10000 | 10000 | 10000 | UNICEF |  | Supplies
Create gamified health education apps to engage youth in healthy behaviors. |  | App | 1 | 35000 | 35000 | 0 | 0 | UNICEF |  | Contractual Services
Monitor and evaluate the effectiveness of digital interventions |  | Monitoring | 5 | 10000 |  | 5000 | 5000 | UNICEF |  | Supplies
Design and test interventions using behavioral insights. |  | Intervention Design | 3 | 34080 | 15000 | 10000 | 9080 | UNICEF |  | Supplies
Scale up successful interventions. |  | Scale-up | 5 | 30000 |  | 10000 | 20000 | UNICEF |  | Travel
SubTotal |  |  |  | 154080 | 65000 | 40000 | 49080
Admin cost (7%) |  |  |  | 10785.6 | 4550 | 2800 | 3435.6
GRAND TOTAL |  |  |  | 164865.6 | 69550 | 42800 | 52515.6

## Tab2. by reporting class
Blue, yellow, and grey cells are with formulas and should not be altered. Fill ONLY the while cells.
Project Title: Enhancing Youth Health through Governance and Policy for NCD and Mental Health Prevention
Implementing Organization: WHO, UNDP, UNICEF
Country: Zambia
Date submission: 12 July 2024
ANNEX 2: Table 2 Budget Summary by reporting object class
Object Class | Approved Budget (US$)
| Year 1 Org A | Year 2 Org A | Year 3 Org A | Total | % over Programme Cost
Staff and other personnel Costs | 0 | 0 | 0 | 0 | 0%
Travel on official business | 0 | 0 | 0 | 0 | 0%
Contractual Services | 222214 | 132214 | 77214 | 431642 | 61.16%
General Operating and Other Direct Costs | 0 | 0 | 0 | 0 | 0%
Equipment, Vehicles and Furniture (including depreciation) | 0 | 0 | 0 | 0 | 0%
Supplies, Commodities and Materials | 110000 | 90000 | 74080 | 274080 | 38.84%
Transfers and Grants to Counterparts | 0 | 0 | 0 | 0 | 0%
Total project cost | 332214 | 222214 | 151294 | 705722 | 100%
Programme Support Costs (7% for PUNO(s)) | 23254.98 | 15554.98 | 10590.58 | 49400.54 | 7%
Total project budget | 355468.98 | 237768.98 | 161884.58 | 755122.54 | 107%

## Tab3. Workplan
Please do not alter or manually enter any information in this Annex 1.
Project Title: Enhancing Youth Health through Governance and Policy for NCD and Mental Health Prevention | Enhancing Youth Health through Governance and Policy for NCD and Mental Health Prevention
Implementing Organization: WHO, UNDP, UNICEF | WHO
Country: Zambia | Zambia
Date submission: 12 July 2024 | 2024-07-12
Annex 1: Workplan
LOGFRAME | Year 1 | Year 2 | Year 3
Objective 1: Policies and Laws for NCDs, tobacco control, alcohol misuse, sodium and sugar in processed food regulations and mental health developed by 2027
Expected Outcome (EO) 1.1: Strengthened policy environment and taxation for reducing risk factors and improving population health.
Output 1.1: The Tobacco Control Bill is aligned with WHO FCTC and presented in the parliamant, | X | X | X
Output 1.2: The Alcohol Licensing Act and National Alcohol Policy are amended | X | X | X
Output 1.3:Comprehensive Health tax policy developed and implemented | X | X | X
Output 1.4: National policy/strategy/standards on sodium and sugar content in processed foods developed and implemented
EO 2: Transformation of Systems to address NCDs and Mental Health:
Output 2.1:NCM established to implement the Health in All Policies Framework | X | X | X
Output 3.1: Increased awareness among adolescents and youth in schools, colleges, universities, and communities | X | X | X
Output 3.2: Effective interventions designed and tested to change youth behaviors.
EO 4: Increased Institutional capacity and investment in Mental Health Services for Youth
Output 4.1: Increased understanding of mental health conditions and importance of seeking help. | X | X | X
Output 4.2: Increased access to mental health services through digital tools | X | - | -
Output 4.3: Expanded access to mental health services in primary health care, schools, youth resource centers, and community centers | X | X | X
Output 4.4: Healthcare workers at primary health care level equipped with skills and knowledge in mental health care | X | X | X
Output 4.5: This is further detailed below as follows:
Other Project Inputs (including project management, monitoring and evaluation, and other costs that cannot be directly attributed to an Output) | X | X | X