## Please enable macros (hidden)
Please enable macros to use this document.
If this message appears below the ribbon, click the "Enable Content" button.
If a security warning window pops up, click the "Yes" or "Enable macros" button.
If you don't see either option, go to "File" > "Options" > "Trust Center"
Then go to "Trust Center Settings" > "Macro Settings." Select "Enable all macros" then close and reopen this document.

## Dashboard
Progress dashboard |  |  |  |  | About the dashboard
Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003)
UNDP Panama
ACTIVITIES COMPLETED |  | OUTPUTS COMPLETED
3 / 26 |  | 0 / 9
PROJECT PROGRESS | [9 empty] | EXPENDITURE BY ACTIVITY (CCAC funding) | [9 empty] | SUMMARY BY COST CATEGORY
Description | Delivery date | Reporting period: 11/12/2025 - 30/06/2026 | Reporting period: 01/07/2026 - 31/12/2026 | Reporting period: 01/01/2027 - 30/06/2027 | Reporting period: | Reporting period: | Activity complete | Output complete | Outcome completed | Related activity | Category | Total budget | Total expenditure | Reporting period: 11/12/2025 - 30/06/2026 | Reporting period: 01/07/2026 - 31/12/2026 | Reporting period: 01/01/2027 - 30/06/2027 |  |  | Expenditure per avtivity Cofunding | Category | Total budget | Total expenditure | Variance
Outcome 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Project end | On track |  |  |  |  | no | no | no |  | Total | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Total | 390000 | 19586.75 | -94.98%
Output 1.1 Pre-feasibility studies for organic waste treatment options | 2025-12-01 | Delayed |  |  |  |  | no | no | no | Activity 1.1.1 Conduct consultations with government entities, MERCA representatives, and private sector players, ensuring equal participation of women and men, to define treatment options. | Staff and Other Personnel Costs | 15000 | 5880 | 5880 | 0 | 0 | 0 | 0 | 0 | Contractual Services | 102686 | 0 | -100%
Activity 1.1.1 Conduct consultations with government entities, MERCA representatives, and private sector players, ensuring equal participation of women and men, to define treatment options. | 2025-09-01 | Complete |  |  |  |  | yes | no | no | Activity 1.1.1 Conduct consultations with government entities, MERCA representatives, and private sector players, ensuring equal participation of women and men, to define treatment options. | Travel | 2000 | 1333 | 1333 | 0 | 0 | 0 | 0 | 0 | Equipment Vehicles and Furniture | 3000 | 0 | -100%
Activity 1.1.2 Evaluate technical and economic feasibility for technologies like composting and anaerobic digestion, including an analysis of how these benefit women-led businesses and communities. | 2025-12-01 | Delayed |  |  |  |  | no | no | no | Activity 1.1.2 Evaluate technical and economic feasibility for technologies like composting and anaerobic digestion, including an analysis of how these benefit women-led businesses and communities. | Staff and Other Personnel Costs | 20000 | 12373.75 | 12373.75 | 0 | 0 | 0 | 0 | 0 | Operating and Other Direct Costs | 0 | 0
Output 1.2 Estimates of decentralized infraestructure supporting diverted organic waste | 2025-12-01 | On track |  |  |  |  | no | no | no | Activity 1.2.1 Map existing and potential decentralized infrastructure for waste management, engaging municipalities and local organizations to provide on-ground insights. | Staff and Other Personnel Costs | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Staff and Other Personnel Costs | 255000 | 18253.75 | -92.84%
Activity 1.2.1 Map existing and potential decentralized infrastructure for waste management, engaging municipalities and local organizations to provide on-ground insights. | 2025-09-01 | Delayed |  |  |  |  | no | no | no | Activity 1.2.2 Conduct site visits and surveys, collecting gender-disaggregated data to ensure proposed infrastructure meets the needs of both genders. | Travel | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supplies Commodities and Materials | 0 | 0
Activity 1.2.2 Conduct site visits and surveys, collecting gender-disaggregated data to ensure proposed infrastructure meets the needs of both genders. | 2025-12-01 | Complete |  |  |  |  | yes | no | no | Activity 1.2.3 Develop cost-benefit analyses, incorporating feedback from diverse stakeholders through an online webinar. | Staff and Other Personnel Costs | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Travel | 3800 | 1333 | -64.92%
Activity 1.2.3 Develop cost-benefit analyses, incorporating feedback from diverse stakeholders through an online webinar. | 2026-03-01 | Complete |  |  |  |  | yes | no | no | Activity 1.3.1 Develop a list of complementary technologies and infrastructure to enhance organic waste management, consulting stakeholders such as circular economy specialists and private sector innovators. | Staff and Other Personnel Costs | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | UN-PSC | 25514 | 1371.0725 | -94.63%
Output 1.3 Recommendations for alternative/ complementary infraestrucutre | 2026-09-01 | On track |  |  |  |  | no | no | no | Activity 1.3.2 Host a gender-balanced expert panel to validate recommendations, prioritizing options that create employment for women. | Contractual Services | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 1.3.1 Develop a list of complementary technologies and infrastructure to enhance organic waste management, consulting stakeholders such as circular economy specialists and private sector innovators. | 2026-06-01 | On track |  |  |  |  | no | no | no | Activity 1.3.3 Prepare an accessible visual infographic summarizing key recommendations for public dissemination. | Contractual Services | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 1.3.2 Host a gender-balanced expert panel to validate recommendations, prioritizing options that create employment for women. | 2026-06-01 | On track |  |  |  |  | no | no | no | Activity 1.4.1 Conduct an in-depth evaluation of essential infrastructure for organic waste management (e.g., composting plants, biodigesters) | Staff and Other Personnel Costs | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 1.3.3 Prepare an accessible visual infographic summarizing key recommendations for public dissemination. | 2026-09-01 | On track |  |  |  |  | no | no | no | Activity 1.4.2 Compile findings into a comprehensive report highlighting investment opportunities, environmental and economic benefits, and potential social impacts. Share the report through workshops and online platforms targeting public and private stakeholders. | Staff and Other Personnel Costs | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 1.4 Report indentifying necessary infraestructure and investment to support organic waste management | 2026-12-01 | Not started |  |  |  |  | no | no | no | Activity 2.1.1Identify and evaluate projects with business potential, ensuring inclusion of women-led initiatives and alignment with national goals. | Contractual Services | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 1.4.1 Conduct an in-depth evaluation of essential infrastructure for organic waste management (e.g., composting plants, biodigesters) | 2026-12-01 | Not started |  |  |  |  | no | no | no | Activity 2.1.2Develop a portfolio of selected projects with detailed descriptions and expected outcomes, highlighting gender-specific benefits. | Staff and Other Personnel Costs | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 1.4.2 Compile findings into a comprehensive report highlighting investment opportunities, environmental and economic benefits, and potential social impacts. Share the report through workshops and online platforms targeting public and private stakeholders. | 2026-12-01 | Not started |  |  |  |  | no | no | no | Activity 2.1.3Engage private sector investors and financial institutions in the evaluation process to co-create viable financing strategies. | Staff and Other Personnel Costs | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outcome 2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | Project end | On track |  |  |  |  | no | no | no | Activity 2.2.1Host a multi-stakeholder workshop, ensuring representation from women-led organizations, to prioritize three high-impact projects. | Contractual Services | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 2.1 Identification of projects/inititives | 2026-06-01 | Delayed |  |  |  |  | no | no | no | Activity 2.2.2Develop detailed financial plans for selected projects, including specific tools tailored to benefit marginalized groups. | Staff and Other Personnel Costs | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 2.1.1Identify and evaluate projects with business potential, ensuring inclusion of women-led initiatives and alignment with national goals. | 2026-06-01 | Delayed |  |  |  |  | no | no | no | Activity 2.2.3Release a press statement highlighting the selected projects to attract further investment and support. | Equipment Vehicles and Furniture | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 2.1.2Develop a portfolio of selected projects with detailed descriptions and expected outcomes, highlighting gender-specific benefits. | 2026-06-01 | Delayed |  |  |  |  | no | no | no | Activity 2.2.3Release a press statement highlighting the selected projects to attract further investment and support. | Staff and Other Personnel Costs | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 2.1.3Engage private sector investors and financial institutions in the evaluation process to co-create viable financing strategies. | 2026-06-01 | Delayed |  |  |  |  | no | no | no | Activity 3.1.1Review existing policies and regulations related to organic waste and SLCPs, engaging policymakers, academics, and gender specialists. | Staff and Other Personnel Costs | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 2.2 Stakeholder Engagement and Strategic Financial Planning for Selected Projects | 2026-09-01 | On track |  |  |  |  | no | no | no | Activity 3.1.2Identify policy gaps and prioritize actions for short, medium, and long-term implementation, ensuring gender-disaggregated data is part of the analysis. | Staff and Other Personnel Costs | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 2.2.1Host a multi-stakeholder workshop, ensuring representation from women-led organizations, to prioritize three high-impact projects. | 2026-06-01 | On track |  |  |  |  | no | no | no | Activity 3.1.3Develop a policy evaluation report and share findings through a case study targeted at stakeholders. | Contractual Services | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 2.2.2Develop detailed financial plans for selected projects, including specific tools tailored to benefit marginalized groups. | 2026-09-01 | Not started |  |  |  |  | no | no | no | Activity 3.2.1Host a workshop with financial institutions, government agencies, and private entities to co-design financial instruments tailored to organic waste projects, ensuring gender inclusion in discussions. | Contractual Services | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 2.2.3Release a press statement highlighting the selected projects to attract further investment and support. | 2026-09-01 | Not started |  |  |  |  | no | no | no | Activity 3.2.2Draft a comprehensive roadmap with actionable steps and estimated budgets, prioritizing funds for women-led initiatives. | Staff and Other Personnel Costs | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outcome 3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Project end | On track |  |  |  |  | no | no | no | Activity 3.2.3Create an interactive digital roadmap for dissemination to public and private stakeholders. | Contractual Services | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 3.1 Analysis of policies to mitigate SLCPs | 2026-03-01 | Delayed |  |  |  |  | no | no | no | Activity 4.1.1Organize training workshops for government officials and market stakeholders on SLCP mitigation strategies, offering flexible schedules and childcare options to ensure women’s participation. | Contractual Services | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 3.1.1Review existing policies and regulations related to organic waste and SLCPs, engaging policymakers, academics, and gender specialists. | 2025-12-01 | Complete |  |  |  |  | yes | no | no | Activity 4.1.2Develop training materials tailored to Panama’s context, including gender-sensitive approaches to waste management. | Contractual Services | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 3.1.2Identify policy gaps and prioritize actions for short, medium, and long-term implementation, ensuring gender-disaggregated data is part of the analysis. | 2025-12-01 | Delayed |  |  |  |  | no | no | no | Activity 4.1.2Develop training materials tailored to Panama’s context, including gender-sensitive approaches to waste management. | Contractual Services | 20686 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 3.1.3Develop a policy evaluation report and share findings through a case study targeted at stakeholders. | 2026-03-01 | Delayed |  |  |  |  | no | no | no | Activity 4.1.3Establish a knowledge-sharing platform for continuous capacity-building, | Contractual Services | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 3.2 Draft roadmap of financial intruments | 2026-09-01 | On track |  |  |  |  | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 3.2.1Host a workshop with financial institutions, government agencies, and private entities to co-design financial instruments tailored to organic waste projects, ensuring gender inclusion in discussions. | 2026-03-01 | On track |  |  |  |  | no | no | no | Activity 4.1.4Project Management and Administration | Staff and Other Personnel Costs | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 3.2.2Draft a comprehensive roadmap with actionable steps and estimated budgets, prioritizing funds for women-led initiatives. | 2026-09-01 | Not started |  |  |  |  | no | no | no | Activity 4.1.4Project Management and Administration | Staff and Other Personnel Costs | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 3.2.3Create an interactive digital roadmap for dissemination to public and private stakeholders. | 2026-09-01 | Not started |  |  |  |  | no | no | no | Activity 4.1.4Project Management and Administration | UN-PSC | 25514 | 1371.0725 | 1371.0725 | 0 | 0 | 0 | 0 | 0
Outcome 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Project end | On track |  |  |  |  | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output 4.1 Capacity building and technical assistance | 2027-06-01 | On track |  |  |  |  | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 4.1.1Organize training workshops for government officials and market stakeholders on SLCP mitigation strategies, offering flexible schedules and childcare options to ensure women’s participation. | 2026-12-01 | On track |  |  |  |  | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 4.1.2Develop training materials tailored to Panama’s context, including gender-sensitive approaches to waste management. | 2026-09-01 | Not started |  |  |  |  | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 4.1.3Establish a knowledge-sharing platform for continuous capacity-building, | 2027-06-01 | Not started |  |  |  |  | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 4.1.4Project Management and Administration | 2027-06-01 | On track |  |  |  |  | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | no | no | no |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0

## 1.Signature page
1. Signature & submission page | #VALUE!
ADMINISTRATIVE INFORMATION |  |  | INSTRUCTIONS
Project title | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) |  | This page must be completed, signed and sent to the CCAC Secretariat each reporting period along with the completed Progress Report template in Excel. The Cover Page can be saved as a PDF or printed. Insert logo --Click "Insert" in the ribbon / tool bar --Click "Illustrations", then "Pictures" --Select the location of the logo --Select the image file (file such as JPG) and click "Insert" --Move and/or resize logo over top the red text Sign the cover page Option 1 - insert signature as image --Scan and save your signature as an image (JPG or PNG) --In the Progress Report template, select the cell into which you want to add your signature --Click "Insert" in the ribbon / tool bar --Click "Illustrations", then "Pictures" --Select the location of the signature --Select the image file and click "Insert" --Move and/or resize signature as needed Option 2 - sign digital or printed copy --Complete all required fields on the cover page (except signature) --Click "File" in the ribbon / tool bar --Click "Print" --Select your printer OR print to PDF
Implementer | UNDP Panama
Co-implementers
Agreement ID | 25-016-PA-24-003
Name of contact person | Jose de Garcia
jose.degracia@undp.org
Funding cycle (programme ID) | GP00007985
Budget line (WBSE) | SB-022934.02.01.03.01 / M1-32SLP-000080
Contract amount $US | 390000
Project amount $US | 390000
BP number | 1400000203
Subprogramme | Climate Change
Contract start date (dd/mm/yyyy) | 2025-11-12
Contract end date (dd/mm/yyyy) | 2027-12-01
Activities end date (dd/mm/yyyy) | 2027-06-01
STATUS SUMMARY - FIRST REPORTING PERIOD
First reporting period dates: (dd/mm/yy - dd/mm/yy) | 11/12/2025 - 30/06/2026
| Summary/description (max. 500 characters) | Status
Schedule | The project established the technical and institutional foundation for improving organic waste management and reducing methane emissions in Panama. Key achievements included stakeholder coordination, policy and regulatory assessments, characterization of organic waste at Merca Panamá, evaluation of technology alternatives, identification of financing opportunities, and strengthened collaboration among government institutions, the private sector, and development partners. | On track
Budget | The project is progressing largely according to schedule. During the reporting period, implementation focused on establishing coordination mechanisms with national counterparts, conducting baseline technical assessments, and initiating key consultancies. Minor adjustments were made to sequencing certain activities to align with stakeholder availability and ensure that technical studies informed subsequent investment planning and decision-making. These adjustments have not affected the overall implementation timeline. | Issues
Scope | There were no changes to the project scope during the reporting period. Implementation remains fully aligned with the approved project document and results framework, focusing on strengthening organic waste management, reducing methane emissions, promoting circular economy approaches, assessing sustainable technologies, identifying financing mechanisms, and strengthening institutional coordination to support the implementation of scalable solutions in Panama. | On track
Payments received to date | 195061
Sign here before submitting your report:
| Signature | Date
Read and approved by CCAC Secretariat/UNEP:
| Signature | Date
STATUS SUMMARY - 2ND REPORTING PERIOD
Second reporting period dates: (dd/mm/yy - dd/mm/yy) | 01/07/2026 - 31/12/2026
| Summary/description (max. 500 characters) | Status
Schedule
Budget
Scope
Payments received to date | 0
Sign here before submitting your report:
| Signature | Date
Read and approved by CCAC Secretariat/UNEP:
| Signature | Date
STATUS SUMMARY - 3RD REPORTING PERIOD
Third reporting period dates: (dd/mm/yy - dd/mm/yy) | 01/01/2027 - 30/06/2027
| Summary/description (max. 500 characters) | Status
Schedule
Budget
Scope
Payments received to date | 0
Sign here before submitting your report:
| Signature | Date
Read and approved by CCAC Secretariat/UNEP:
| Signature | Date
STATUS SUMMARY - 4TH REPORTING PERIOD
Fourth reporting period dates: (dd/mm/yy - dd/mm/yy)
| Summary/description (max. 500 characters) | Status
Schedule
Budget
Scope
Payments received to date | 0
Sign here before submitting your report:
| Signature | Date
Read and approved by CCAC Secretariat/UNEP:
| Signature | Date
STATUS SUMMARY - 5TH REPORTING PERIOD
Fifth reporting period dates: (dd/mm/yy - dd/mm/yy)
| Summary/description (max. 500 characters) | Status
Schedule
Budget
Scope
Payments received to date | 0
Sign here before submitting your report:
| Signature | Date
Read and approved by CCAC Secretariat/UNEP:
| Signature | Date

## 2. Narrative
2. Narrative report |  |  | See instructions
Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003)
UNDP Panama
PLANNED | [15 empty] | FIRST REPORTING PERIOD: 11/12/2025 - 30/06/2026 | [5 empty] | SECOND REPORTING PERIOD: 01/07/2026 - 31/12/2026 | [5 empty] | THIRD REPORTING PERIOD: 01/01/2027 - 30/06/2027 | [5 empty] | FOURTH REPORTING PERIOD: | [5 empty] | FIFTH REPORTING PERIOD:
Deliverable | Indicator | Target | Unit | Delivery date | Proof of delivery | Description2 | Acceptance criteria | Project name | Full code | Implementer | Sector | Beneficiary | Other beneficiary | blank1 | blank2 | Status at end of 1st period | Progress made during 1st period | Variance during 1st period | Further actions at end of 1st period | Proof of delivery (document URLs or file names) 1st period | Type of document 1st period | Status at end of 2nd period | Progress made during 2nd period | Variance during 2nd period | Further actions at end of 2nd period | Proof of delivery (document URLs or file names) 2nd period | Type of document 2nd period | Status at end of 3rd period | Progress made during 3rd period | Variance during 3rd period | Further actions at end of 3rd period | Proof of delivery (document URLs or file names) 3rd period | Type of document 3rd period | Status at end of 4th period | Progress made during 4th period | Variance during 4th period | Further actions at end of 4th period | Proof of delivery (document URLs or file names) 4th period | Type of document 4th period | Status at end of 5th period | Progress made during 5th period | Variance during 5th period | Further actions at end of 5th period | Proof of delivery (document URLs or file names) 5th period | Type of document 5th period | Status | INSTRUCTIONS â
Outcome 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Number of government entities with a demonstrated improved capacity for SLCP action | 4 | 4 government entities with improved capacity for SLCP action. | By project end | - | The project’s outputs will identify and develop innovative and practical treatment options and solutions for managing organic waste, generating critical data on decentralized infrastructure needs, such as composting plants, biodigesters, food and material recovery, and waste reduction technologies. These solutions will integrate circular economy principles, prioritize locally based consultants with local language capabilities, and actively engage the private sector through targeted knowledge exchange initiatives. By leveraging activities such as pre-feasibility studies, infrastructure estimates, and actionable recommendations, the project will equip the government with comprehensive knowledge to make informed decisions on effective and sustainable waste management solutions. This enhanced knowledge is expected to contribute to significant environmental, economic, and social benefits, including reduced food waste, methane emissions, and support for national and international sustainability goals. The projec | - | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | (blank) | Waste | (blank) | (blank) |  |  | On track | Progress was made in generating knowledge about alternatives for the valorization of organic waste through consultations with key stakeholders, prefeasibility studies for composting and anaerobic digestion, the identification and characterization of decentralized infrastructure, technical visits, specialized interviews, and preliminary cost-benefit analyses. Likewise, information on complementary infrastructures was collected and outreach activities were initiated. | Project implementation started later than originally planned following the signature of the Implementing Partner Agreement and the first fund disbursement. Activities were subsequently reprioritized and the implementation schedule updated to maintain overall progress toward the expected results. | Finalize the pre-feasibility studies for organic waste treatment options, initiate the consultancy for the systematization and assessment of decentralized infrastructure, continue the analysis of alternative and complementary infrastructure solutions, and advance the development of the report identifying infrastructure and investment requirements to support organic waste management in Panama. | See above | Research or study | [25 empty] | The first 8 columns in this table contain the planned project items (outcomes, outputs, and activities) for this implementer agreement. These items are listed in ascending order by item number. Scroll up and down the list to ensure you see all project items. Columns to the right of the project item list contain fields that must be completed for each project item at the indicated reporting period. Scroll left and right to find the relevant reporting period under which to enter results. Note that results entered for previous reporting periods will be locked for editing and cannot be changed once they have been approved. Complete all cells for each project item in the relevant reporting period. No cell should be left blank. If there is no progress to report for an item, enter "N/A", "Not started", or "No change". Cells with grey backgrounds are locked from editing. This includes projects items that have been marked as complete in the previous reporting period.
Output 1.1 Pre-feasibility studies for organic waste treatment options | Number of plans, policies, laws, or regulations drafted or updated | 1 | 1 pre-feasibility study report developed. | 2025-12-01 | Research or study | Pre-feasibility studies for organic waste treatment options conducted in Panama City. These studies will evaluate the technical and economic feasibility of potential treatment technologies/solutions, such as composting, anaerobic digestion, and other technologies to manage organic waste effectively. The goal is to identify the most viable treatment methods that support waste diversion, reduce methane emissions, and promote circular economies. The studies will provide critical data and analysis on costs, environmental benefits, and operational feasibility, laying the groundwork for informed decision-making and future investments in sustainable organic waste management infrastructure, ensuring alignment with national policies and international commitments. | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/1.1 Pre-feasibility studies for organic waste treatment options | UNDP () | Waste | Panama | National and local governments responsible for waste management. |  |  | Delayed | Extensive consultations were conducted with national institutions, Merca Panamá, Mercados Nacionales de la Cadena de Frío, private sector representatives and technical experts to validate priority treatment options. Technical studies evaluating composting, anaerobic digestion and complementary technologies progressed substantially, providing the basis for selecting technically and economically viable solutions for organic waste valorization. | Implementation was rescheduled following project inception and first disbursement. Foundational activities were prioritized to minimize impacts on the overall workplan. | This output has been scheduled for completion at the first month of the following period. | See above | Nothing to deliver this period
Activity 1.1.1 Conduct consultations with government entities, MERCA representatives, and private sector players, ensuring equal participation of women and men, to define treatment options. | Organising, holding, or participating in a meeting or event | #VALUE! | null |  | Policy, regulation or other guideline | This activity will involve organizing consultations with key stakeholders to identify feasible organic waste treatment technologies. These sessions will include representatives from government entities, MERCA, private sector players, and NGOs, with a focus on ensuring gender-balanced participation. The consultations will evaluate existing waste management practices, discuss potential treatment solutions (e.g., composting, biodigesters), and collect stakeholder input to define the best approaches. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/1.1.1 Conduct consultations with government entities, MERCA representatives, and private sector players, ensuring equal participation of women and men, to define treatment options. | UNDP () | Waste | Panama | null |  |  | Complete | During the initial phase, various consultations were held with key stakeholders in the government sector, Merca Panama and Mercados Nacionales de la Cadena de Frío, S.A., and private sector players. | The delivery date for this activity was previously set for Sep 1, 2025, but the project signing and submission of the first payment took place after Dec 1, 2025, resulting in a variance of the implementation phase for this activity during the first period. | The activity has been completed. | https://drive.google.com/drive/folders/1mf8BkiJhA9S1rUsruaVPkjj3JGVB3vV5?usp=sharing | Meeting report
Activity 1.1.2 Evaluate technical and economic feasibility for technologies like composting and anaerobic digestion, including an analysis of how these benefit women-led businesses and communities. | Research, data collection, and/or report writing | #VALUE! | null | 2025-12-01 | Research or study | This activity focuses on conducting technical and economic feasibility studies for organic waste treatment technologies. The evaluation will assess factors such as cost efficiency, scalability, and environmental impact. Special attention will be given to understanding how these technologies can create opportunities for women-led businesses and promote inclusive economic benefits in local communities. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/1.1.2 Evaluate technical and economic feasibility for technologies like composting and anaerobic digestion, including an analysis of how these benefit women-led businesses and communities. | UNDP () | Waste | Panama | null |  |  | Delayed | Preparation of terms of reference; selection of a consulting firm to conduct a technical and economic feasibility evaluation of composting and energy generation technologies tailored to the needs of Merca Panamá; and a waste characterization. In addition, the first phase of the study was completed. | The planned delivery date preceded the signing and receipt of funds, resulting in a variance on the execution period and an impact on the schedule. Activities were rescheduled, and priority was given to the development of 1.1.2. | The final report will be completed during the first month of the second period. | https://drive.google.com/drive/folders/1qQ3DP5hxh2NXzxRg9oXC-KZhy6lPv1oB?usp=sharing | Research or study
Output 1.2 Estimates of decentralized infraestructure supporting diverted organic waste | Number of SLCP assessments, emissions inventories, and other emissions datasets produced | 4 | 4 SLCP assessments, emissions inventories, or other emissions datasets produced. | 2025-12-01 | Research or study | Estimates of decentralized infrastructure supporting organic waste diversion, including materials separation and recovery centers, black soldier fly infrastructure, and compositing plants. These systems will promote a circular economy by processing organic waste closer to its source, reducing transportation costs and emissions. The estimates will determine the scale, location, capacity and investment requirements for these facilities, providing a strategic roadmap for developing an efficient, sustainable waste management network. This will enable the government to plan effectively for organic waste management. | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/1.2 Estimates of decentralized infraestructure supporting diverted organic waste | UNDP () | Waste | Panama | Municipalities and local governments. |  |  | On track | Progress was made in the identification and characterization of decentralized infrastructure for organic waste management through the compilation of existing mappings and the development of terms of reference for their systematization. In addition, four technical visits and three specialized interviews were conducted, and a draft cost-benefit analysis was developed for alternatives for the recovery of organic waste. | The delivery date for this output precedes the actual date of the agreement's signing and the disbursement of the first payment, resulting in a delay to its commencement. Rescheduling and adjustments to the timeline were carried out, prioritizing the project's foundational activities. | Launch of the termsof references generated for Activity 1.2.1 and start-up of the service | See above | Nothing to deliver this period
Activity 1.2.1 Map existing and potential decentralized infrastructure for waste management, engaging municipalities and local organizations to provide on-ground insights. | Research, data collection, and/or report writing | #VALUE! | null | 2025-09-01 | Research or study | This activity involves mapping current and potential decentralized infrastructure for organic waste management, such as composting plants, biodigesters, and material recovery facilities. Municipal governments and local organizations will be actively engaged to ensure accurate data collection and context-specific recommendations. The mapping process will also consider socio-economic and environmental factors to identify priority areas for infrastructure development. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/1.2.1 Map existing and potential decentralized infrastructure for waste management, engaging municipalities and local organizations to provide on-ground insights. | UNDP () | Waste | Panama | null |  |  | Delayed | Currently, there are certain scattered mappings and publications that point out the needs for improvement regarding waste management infrastructure. A terms of reference was developed to carry out its systematization, with special emphasis on potential infrastructures. | The delivery date for this activity was previously set for Sep 1, 2025, but the project signing and submission of the first payment took place after Dec 1, 2025, resulting in a variance of the implementation phase for this activity during the first period. | Service launch for its execution during the second period | https://drive.google.com/drive/folders/1lE4T0HLJjULdgQ5XVbH7G6ZAiM0xGh1r?usp=sharing | Work plan
Activity 1.2.2 Conduct site visits and surveys, collecting gender-disaggregated data to ensure proposed infrastructure meets the needs of both genders. | Research, data collection, and/or report writing | #VALUE! | null | 2025-12-01 | Research or study | This activity will include field visits and stakeholder surveys to collect data on waste management infrastructure needs. Surveys will include gender-disaggregated data to ensure that proposed infrastructure supports both men and women, particularly those in waste-related informal sectors. The findings will inform inclusive and equitable infrastructure planning. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/1.2.2 Conduct site visits and surveys, collecting gender-disaggregated data to ensure proposed infrastructure meets the needs of both genders. | UNDP () | Waste | Panama | null |  |  | Complete | During the first period, 4 technical field visits and 3 specialized interviews with stakeholders were carried out to learn about aspects of waste management infrastructure needs. | Instead of being completed on Dec 1, 2025, it was finished in the first half of 2026. This was due to the previously mentioned delay and the rescheduling done once the project started. | The activity has been completed. | https://drive.google.com/drive/folders/1UyHa7xEazNbAQ0ZRbzjf-Y59xhc4wTba?usp=sharing | Research or study
Activity 1.2.3 Develop cost-benefit analyses, incorporating feedback from diverse stakeholders through an online webinar. | Research, data collection, and/or report writing | #VALUE! | null | 2026-03-01 | Research or study | This activity will involve conducting cost-benefit analyses for proposed decentralized infrastructure options, such as composting and biodigesters. Stakeholders, including government officials, NGOs, and private sector representatives, will provide feedback through an interactive online webinar. The analysis will highlight economic, environmental, and social benefits, emphasizing SLCP mitigation and inclusion of marginalized groups. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/1.2.3 Develop cost-benefit analyses, incorporating feedback from diverse stakeholders through an online webinar. | UNDP () | Waste | Panama | null |  |  | Complete | Research and draft of a cost-benefit analysis prepared for a series of technological alternatives focused on the utilization of organic waste (aerobic composting with mechanical turning, anaerobic digestion, and integrated bioconversion system). | Its execution period was rescheduled given the project's start date; however, it was completed within the set period. | The activity has been completed. | https://drive.google.com/drive/folders/1K8Coe28YSdI7TLIoYomJlf_HHfn9N-MT?usp=drive_link | Research or study
Output 1.3 Recommendations for alternative/ complementary infraestrucutre | Number of SLCP knowledge resources or tools produced | 1 | 1 SLCP knowledge resource or tool produced. | 2026-09-01 | Research or study | Recommendations for alternative and complementary infrastructure to support organic waste diversion and fosters circular economies. The proposed infraestructure aims to enhance existing waste management systems, such as advanced compositing technologies, anaerobic digestion, and resource recovery facilities. These recommendation will serve as a blueprint for the government to integreate into its organic waste management strategy, with focus on creating value to the organic waste, lowers emissions, reducing landfill dependency, and promoting environmental, economic and social benefits, achieve the goals establishd in the NDC's and roadmap for the Mitigation of SLCPs in Panama. The findings will guide future investements and policies for an integrated waste managemente approach | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/1.3 Recommendations for alternative/ complementary infraestrucutre | UNDP () | Waste | Panama | National and local governments. |  |  | On track | Information gathering and market research to understand alternatives and complementary infrastructures for waste management, as well as event planning for their discussion and the initiation of infographic development | N/A; this output is expected to be completed on future periods. | Will continue with the development of the activities listed below | See above | Nothing to deliver this period
Activity 1.3.1 Develop a list of complementary technologies and infrastructure to enhance organic waste management, consulting stakeholders such as circular economy specialists and private sector innovators. | Research, data collection, and/or report writing | #VALUE! | null | 2026-06-01 | Meeting report | This activity will identify and prioritize complementary technologies and infrastructure to improve the efficiency of organic waste management systems. Circular economy specialists and private sector innovators will be consulted to ensure the recommendations align with sustainable practices and promote innovation. Examples of technologies include biogas recovery systems and advanced composting units. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/1.3.1 Develop a list of complementary technologies and infrastructure to enhance organic waste management, consulting stakeholders such as circular economy specialists and private sector innovators. | UNDP () | Waste | Panama | null |  |  | On track | Search and generation of a list with complementary technologies that are being developed in the country | Activity affected by the initial delay in the project. Under the rescheduling carried out, it was planned to be completed during the next period | Review of generated list and search of international experiences at public markets | https://drive.google.com/drive/folders/1DWR2CUqwCDmL84I2p6i2iQfTc_qBOStH?usp=sharing | Research or study | [24 empty] | On track
Activity 1.3.2 Host a gender-balanced expert panel to validate recommendations, prioritizing options that create employment for women. | Organising, holding, or participating in a meeting or event | #VALUE! | null | 2026-06-01 | null | A panel of experts, ensuring gender balance, will review and validate the recommendations for complementary technologies and infrastructure. Discussions will focus on prioritizing solutions that foster economic opportunities for women, particularly in waste collection and processing. The validated recommendations will guide subsequent project activities. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/1.3.2 Host a gender-balanced expert panel to validate recommendations, prioritizing options that create employment for women. | UNDP () | Waste | Panama | null |  |  | On track | Future panel organization and preparation of its work plan | Activity affected by the initial delay in the project. Under the rescheduling carried out, it was planned to be completed during the next period | Continue with the procedures for its completion | https://drive.google.com/drive/folders/1_SyV_Tz8bGLQdXkj27Cdi_pchqlLmemZ?usp=sharing | Work plan | [24 empty] | On track
Activity 1.3.3 Prepare an accessible visual infographic summarizing key recommendations for public dissemination. | Producing and distributing communications materials | #VALUE! | null | 2026-09-01 | Research or study | This activity will focus on creating an infographic to visually communicate the key recommendations from the expert panel to a broad audience. The infographic will highlight the technologies and infrastructure proposed, their environmental and social benefits, and their alignment with SLCP mitigation goals. The design will prioritize accessibility, ensuring it can be understood by diverse stakeholders, including policymakers, community groups, and private sector actors. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/1.3.3 Prepare an accessible visual infographic summarizing key recommendations for public dissemination. | UNDP () | Waste | Panama | null |  |  | On track | Preparation of infographics for the initial phase and dissemination of the project to diverse audiences, creating a base infographic in Spanish and the draft for an English version. | N/A | Generation of information and key recommendations for public dissemination | https://drive.google.com/drive/folders/1hUB3dA96_8f5tixKGxqgYXhhi_ZzAFm5?usp=sharing | Photo or video | [24 empty] | On track
Output 1.4 Report indentifying necessary infraestructure and investment to support organic waste management | Number of plans, policies, laws, or regulations drafted or updated | 1 | 1 plan, policy, law, or regulation drafted or updated. | 2026-12-01 | Research or study | A report identifying necessary infrastructure and investment to support organic waste management (recovery of organic waste, production of biofertilizer and energy, savings by avoiding waste, redistribution of food that otherwise would be discarded to people in need). The report will cover key areas such as the recovery of organic waste, the production of biofertilizers and renewable enerty, and economic savings from waste reduction. It will also highlight the potential for redistributing surplus food to people in need, preventing it from being discarded. By identifying these necessary components, the report will serve as a strategic roadmap for decision-makers to prioritize investements and implementing sustainable solutions for organic waste management. | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/1.4 Report indentifying necessary infraestructure and investment to support organic waste management | UNDP () | Waste | Panama | National and local governments, investors. |  |  | Not started | N/A | N/A | N/A | N/A | Nothing to deliver this period | [24 empty] | Not started
Activity 1.4.1 Conduct an in-depth evaluation of essential infrastructure for organic waste management (e.g., composting plants, biodigesters) | Research, data collection, and/or report writing | #VALUE! | null | 2026-12-01 | Meeting report | This activity will evaluate the critical infrastructure required for effective organic waste management in Panama, focusing on facilities such as composting plants and biodigesters. The evaluation will include cost estimates for infrastructure development, operational considerations, and potential funding sources. Special attention will be paid to how these facilities can generate employment opportunities for women and marginalized groups. This in-depth assessment will also examine environmental and economic impacts to support informed decision-making. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/1.4.1 Conduct an in-depth evaluation of essential infrastructure for organic waste management (e.g., composting plants, biodigesters) | UNDP () | Waste | Panama | null |  |  | Not started | N/A | N/A | N/A | N/A | Nothing to deliver this period | [24 empty] | Not started
Activity 1.4.2 Compile findings into a comprehensive report highlighting investment opportunities, environmental and economic benefits, and potential social impacts. Share the report through workshops and online platforms targeting public and private stakeholders. | Policy, project, or tool design | #VALUE! | null | 2026-12-01 | Meeting report | This activity will consolidate the findings of the infrastructure evaluation into a comprehensive report that highlights key investment opportunities and the potential benefits of organic waste management infrastructure. The report will outline environmental, economic, and social impacts, emphasizing gender-inclusive opportunities such as job creation for women. The findings will be disseminated through workshops with stakeholders and made available on online platforms to ensure accessibility. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/1.4.2 Compile findings into a comprehensive report highlighting investment opportunities, environmental and economic benefits, and potential social impacts. Share the report through workshops and online platforms targeting public and private stakeholders. | UNDP () | Waste | Panama | null |  |  | Not started | N/A | N/A | N/A | N/A | Nothing to deliver this period | [24 empty] | Not started
Outcome 2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 5 | 5 action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures | By project end | - | The project will create a portfolio of 5-7 initiatives and projects with demonstrated business potential, aligned with national goals, and designed to attract funding from both public and private sectors. Specific financial plans will be developed for at least three selected projects, including tailored financial tools and agreements among stakeholders, to enhance the likelihood of securing financing, scaling, and promoting sustainable solutions. The process will include the establishment of collaborative, multi-stakeholder partnerships, which are essential for co-creating comprehensive and lasting solutions. Key activities will involve delivering workshops to financial and governmental stakeholders to explore innovative financing mechanisms and develop actionable financial instruments that address the needs of the selected initiatives. The project assumes that the identified initiatives will generate significant interest from funding institutions and public and private entities, with active participation | - | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | (blank) | Waste | (blank) | (blank) |  |  | On track | Research and project identification initiated, a preliminary project record created (food bank, bioeconomy, cold storage), and a multi‑stakeholder workshop held to prioritize three high‑impact projects with women‑led representation was initially planned. The financial planning, investor engagement, and press outreach are scheduled for upcoming periods. | During this first period, multiple variances occurred due to the date of signing the agreement and the disbursement of the first payment. Rescheduling was carried out taking into account the prioritization of activities and the updated start period. | Finalize the portfolio and complete key-actor identification; develop detailed, gender-responsive financial plans; and resume engagement with investors and financial institutions to co-create financing strategies. A press release will be issued to attract support, the MERCA market pilot will be planned, and follow-up and capacity‑building activities for prioritized actors will be scheduled. | See above | Nothing to deliver this period | [24 empty] | On track
Output 2.1 Identification of projects/inititives | Number of partnerships, associations, or campaigns launched to drive SLCP action | 5 | 5 Partnerships to drive SLCP action. | 2026-06-01 | Research or study, Work plan | Identification of at least 5-7 appropriate projects/initiatives with business potential in integral organic waste management, supported by the public and private sector based on the findings of output 1.3. and will be evaluated for their potential to contribute to a circular economy. The assesment will include project descriptions, expected outcomes, involved entities, and financing strategies. By identifying these opportunities, the project aims to establish a solid foundation for future investements and actions in organic waste management. | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/2.1 Identification of projects/inititives | UNDP () | Waste | Panama | Investors, public and private stakeholders. |  |  | Delayed | Progress was initiated through research and identification of potential actors and allies, including women-led initiatives. A preliminary record of projects was developed, while engagement with investors was rescheduled pending completion of portfolio activities. | The delay caused by the signing and disbursement dates, as well as the rescheduling of Outcome 1, affected the development of the activities related to Outcome 2. For that reason, its execution has been prioritized for the next reporting period. | Formalizar acuerdos de colaboración y definir pilotos conjuntos. | See above | Nothing to deliver this period | [24 empty] | Delayed
Activity 2.1.1Identify and evaluate projects with business potential, ensuring inclusion of women-led initiatives and alignment with national goals. | Other | #VALUE! | null | 2026-06-01 | Work plan | This activity will focus on identifying and evaluating 5–7 organic waste management projects that demonstrate strong business potential. The evaluation will include criteria such as alignment with national sustainability goals, economic viability, and SLCP mitigation potential. Women-led initiatives will be prioritized to ensure gender inclusion and equitable benefits. Key stakeholders, including government and private sector representatives, will provide input during the evaluation process. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/2.1.1Identify and evaluate projects with business potential, ensuring inclusion of women-led initiatives and alignment with national goals. | UNDP () | Waste | Panama | null |  |  | Delayed | For the development of the portfolio, the process of research, identification of potential actors and allies, as well as the preparation of a key actors matrix, was initiated. | The delay caused by the signing and disbursement dates, as well as the rescheduling of Outcome 1, affected the development of the activities related to Outcome 2. For that reason, its execution has been prioritized for the next reporting period. | Evaluation of the projects taking into account the criteria of sustainability goals, economic viability, and SCLP mitigation potential. | https://drive.google.com/drive/folders/1N3S6bvFB5fxWmk8ZKTbD64af2daJuT8n?usp=sharing | Research or study | [24 empty] | Delayed
Activity 2.1.2Develop a portfolio of selected projects with detailed descriptions and expected outcomes, highlighting gender-specific benefits. | Research, data collection, and/or report writing | #VALUE! | null | 2026-06-01 | Policy, regulation or other guideline | Based on the evaluations conducted, this activity will create a portfolio of selected projects with detailed descriptions, expected outcomes, and their contributions to SLCP mitigation. The portfolio will emphasize gender-specific benefits, such as creating economic opportunities for women in waste management. The document will serve as a key resource for attracting public and private investments. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/2.1.2Develop a portfolio of selected projects with detailed descriptions and expected outcomes, highlighting gender-specific benefits. | UNDP () | Waste | Panama | null |  |  | Delayed | Generation of a record with information on potential projects, such as food recovery and byproduct generation. | The delay caused by the signing and disbursement dates, as well as the rescheduling of Outcome 1, affected the development of the activities related to Outcome 2. For that reason, its execution has been prioritized for the next reporting period. | Portfolio development consistent with the results obtained from activity 2.1.1 | https://drive.google.com/drive/folders/1ZnhbcLitwk_WJdjVy7uV3XMT_J5bDtPN?usp=sharing | Research or study | [24 empty] | Delayed
Activity 2.1.3Engage private sector investors and financial institutions in the evaluation process to co-create viable financing strategies. | Other | #VALUE! | null | 2026-06-01 | Meeting report | This activity will involve engaging private sector investors and financial institutions to develop financing strategies for the selected projects. Workshops and one-on-one consultations will be conducted to present the portfolio and discuss potential financing options, including public-private partnerships and innovative financial instruments. The activity will emphasize strategies that support women-led initiatives and community-based projects. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/2.1.3Engage private sector investors and financial institutions in the evaluation process to co-create viable financing strategies. | UNDP () | Waste | Panama | null |  |  | Delayed | N/A; this activity was rescheduled after activities 2.1.1 and 2.1.2 | The delay caused by the signing and disbursement dates, as well as the rescheduling of Outcome 1, affected the development of the activities related to Outcome 2. For that reason, its execution has been prioritized for the next reporting period. | Closure of activities 2.1.1 and 2.1.2, for subsequent engagement with private sector investors and financial institutions (workshops and/or consultations). | N/A | Nothing to deliver this period | [24 empty] | Delayed
Output 2.2 Stakeholder Engagement and Strategic Financial Planning for Selected Projects | Number of partnerships, associations, or campaigns launched to drive SLCP action | 3 | 3 Associations launched to drive SLCP action. | 2026-09-01 | Work plan | Stakeholders, including government agencies, private companies, and financial institutions, will be convened and engaged to select at least 3 priority projects/ initiatives for organic waste management. This process will focus on identifying potential funding sources and aligning stakeholders to support these initiatives. The selected projects will be developed into deteiled plans, including financial strategies and implementation pathways, ensuring coodinated efforts amog all stakeholders to advance sustainable waste management solution. | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/2.2 Stakeholder Engagement and Strategic Financial Planning for Selected Projects | UNDP () | Waste | Panama | Investors, public and private stakeholders. |  |  | On track | A multi-stakeholder workshop was organized, ensuring women-led participation, to prioritize three high-impact projects from the portfolio. Financial planning and press statement activities are scheduled for future periods, with implementation aligned to upcoming milestones. | Although delays have occurred for some of its activities, we are still on schedule for the delivery of this output | N/A | See above | Nothing to deliver this period | [24 empty] | On track
Activity 2.2.1Host a multi-stakeholder workshop, ensuring representation from women-led organizations, to prioritize three high-impact projects. | Organising, holding, or participating in a meeting or event | #VALUE! | null | 2026-06-01 | Work plan | This activity will bring together key stakeholders, including government agencies, financial institutions, private sector representatives, and women-led organizations, to prioritize three high-impact projects from the identified portfolio. The workshop will use a participatory approach to ensure that diverse perspectives are incorporated in the decision-making process. Criteria for prioritization will include business potential, environmental and social benefits, and alignment with national goals. The outcomes of the workshop will guide the development of detailed financial plans for the selected projects. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/2.2.1Host a multi-stakeholder workshop, ensuring representation from women-led organizations, to prioritize three high-impact projects. | UNDP () | Waste | Panama | null |  |  | On track | Multi-stakeholder workshop organized and work plan prepared with the objective of developing an event that allows prioritizing three high-impact projects, contemplated in the portfolio of Output 2.1 | Due to the delay and rescheduling of Output 2.1, the development date of the event was changed for future periods. | Carry out the workshop once the results of activity 2.1.2 are available. | https://drive.google.com/drive/folders/1zz-nWM8nITDzeicd855_6wkakpNqeCjH?usp=sharing | Work plan | [24 empty] | On track
Activity 2.2.2Develop detailed financial plans for selected projects, including specific tools tailored to benefit marginalized groups. | Research, data collection, and/or report writing | #VALUE! | null | 2026-09-01 | Web article | This activity involves creating comprehensive financial plans for the three prioritized projects. The plans will include cost estimates, funding requirements, and proposed financial instruments such as grants, loans, or public-private partnerships. Special attention will be given to designing tools that benefit marginalized groups, including women-led initiatives and small businesses. The financial plans will align with national and international sustainability goals and provide a clear roadmap for securing investment. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/2.2.2Develop detailed financial plans for selected projects, including specific tools tailored to benefit marginalized groups. | UNDP () | Waste | Panama | null |  |  | Not started | N/A | N/A | N/A | N/A | Nothing to deliver this period | [24 empty] | Not started
Activity 2.2.3Release a press statement highlighting the selected projects to attract further investment and support. | Producing and distributing communications materials | #VALUE! | null | 2026-09-01 | Meeting report | To raise awareness and attract investment, this activity will involve drafting and disseminating a press statement announcing the three selected projects. The statement will highlight the projects’ environmental, economic, and social benefits, as well as their alignment with SLCP mitigation goals. The press release will be shared with local and international media outlets, government websites, and social media platforms. The announcement will also emphasize opportunities for private sector involvement and partnerships. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/2.2.3Release a press statement highlighting the selected projects to attract further investment and support. | UNDP () | Waste | Panama | null |  |  | Not started | N/A | N/A | N/A | N/A | Nothing to deliver this period | [24 empty] | Not started
Outcome 3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 1 | 1 roadmap | By project end | - | Workshops under Output 2 will convene key stakeholders, including representatives from the financial sector, local and national governments, and private entities, to explore and design financial mechanisms aligned with Panama's national goals. These workshops will focus on evaluating policies to mitigate Short-Lived Climate Pollutants (SLCPs) from organic waste and identifying opportunities for financial innovation. The outcome will include the creation of a draft roadmap detailing necessary financial instruments and resources tailored to the unique needs and characteristics of organic waste projects in Panama. This roadmap will serve as a foundation for developing long-term financing strategies and a comprehensive resource mobilization plan, fostering sustainable investment and alignment with national and global sustainability goals. | - | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | (blank) | Waste | (blank) | (blank) |  |  | On track | A comprehensive policy review on organic waste, SLCPs and market administration and a draft gap analysis outlining short‑to‑long‑term actions; stakeholder engagement began with a SNAPP meeting, and the planification process for a gender‑inclusive workshop begins, while the financial roadmap awaits workshop outcomes. | As noted above, this outcome is expected to be completed by the end of the project; consequently, mitigation actions will be implemented through the specific outputs and associated activities. | See above | See above | Nothing to deliver this period | [24 empty] | On track
Output 3.1 Analysis of policies to mitigate SLCPs | Number of plans, policies, laws, or regulations drafted or updated | 1 | 1 plan, drafted or updated. | 2026-03-01 | Policy, regulation or other guideline | Evaluation and analysis of policies to mitigate Short-Lived Climate Pollutants (SLCPs) from organic waste and prioritize actions for short, medium, and long term implementation. This evaluation will assess current measures and identify gaps in policy, recommending interventions that can effectively reduce SLCPs. The analysis will also provide estimated costs, responsible parties, and progress indicators. The result will be a comprehensive plan that outlines the necessary steps for Panama to reduce SLCP emissions through better organic waste management practices. | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/3.1 Analysis of policies to mitigate SLCPs | UNDP () | Waste | Panama | Government policymakers, NGOs, private sector. |  |  | Delayed | A comprehensive review of policies and regulations on organic waste, circular economy, SLCPs, and public market administration was completed using various sources of information. A draft gap analysis TDR was prepared; the policy evaluation report and case study are scheduled for the next period. | Delay in the signing and receipt of funds altered the period required for the completion of this output. Rescheduling and prioritization of activities were carried out, starting with the review of what already exists. This impact will be mitigated in the coming months with the hiring of a specialist for the completion of the pending activities. | Contemplating the completion of activities in the upcoming period. | See above | Research or study | [24 empty] | Delayed
Activity 3.1.1Review existing policies and regulations related to organic waste and SLCPs, engaging policymakers, academics, and gender specialists. | Research, data collection, and/or report writing | #VALUE! | null | 2025-12-01 | Policy, regulation or other guideline | This activity involves a comprehensive review of existing policies and regulations governing organic waste management and SLCP mitigation in Panama. The review will engage policymakers, academics, and gender specialists to provide diverse perspectives and insights. The analysis will assess the effectiveness of current regulations, identify potential overlaps or gaps, and evaluate their alignment with national and international sustainability goals. Special emphasis will be placed on examining the gender impacts of these policies to ensure inclusivity and equity in future recommendations. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/3.1.1Review existing policies and regulations related to organic waste and SLCPs, engaging policymakers, academics, and gender specialists. | UNDP () | Waste | Panama | null |  |  | Complete | Comprehensive review of existing policies and regulations related to organic waste management, circular economy, SLCP and public markets administration. | The delivery date for this output precedes the actual date of the agreement's signing and the disbursement of the first payment, resulting in a delay to its commencement. However, the activity was successfully completed in the first period | N/A | https://drive.google.com/drive/folders/1Uy4elEi_8uCvGaC78vbJMWUnL_1aZgWG?usp=sharing | Research or study | [24 empty] | Complete
Activity 3.1.2Identify policy gaps and prioritize actions for short, medium, and long-term implementation, ensuring gender-disaggregated data is part of the analysis. | Research, data collection, and/or report writing | #VALUE! | null | 2025-12-01 | Policy, regulation or other guideline | Building on the findings from the policy review, this activity will identify critical gaps and barriers in existing policies and propose prioritized actions for addressing them. Recommendations will be categorized into short, medium, and long-term strategies, ensuring alignment with Panama’s national goals and SLCP reduction targets. Gender-disaggregated data will be used to assess the differentiated impacts of these actions on men and women, with a focus on promoting inclusivity in policy reforms. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/3.1.2Identify policy gaps and prioritize actions for short, medium, and long-term implementation, ensuring gender-disaggregated data is part of the analysis. | UNDP () | Waste | Panama | null |  |  | Delayed | A draft was created for the systematization and analysis of policies, identifying gaps and recommending actions for short, medium, and long-term implementation | The delivery date for this output precedes the actual date of the agreement's signing and the disbursement of the first payment, resulting in a delay to its commencement. Rescheduling and adjustments to the timeline were carried out, this would be realized at the next period. | Use of the results from activity 3.1.1 and launch of the service | https://drive.google.com/drive/folders/182kHy-sVhJClYqnS1z-RL9tgxY5mPWnp?usp=sharing | Research or study | [24 empty] | Delayed
Activity 3.1.3Develop a policy evaluation report and share findings through a case study targeted at stakeholders. | Policy, project, or tool design | #VALUE! | null | 2026-03-01 | Meeting report | This activity will consolidate the results of the policy analysis into an evaluation report, including actionable recommendations for strengthening SLCP mitigation policies. The report will also include a case study highlighting the potential impact of policy reforms on organic waste management and gender inclusivity. The findings will be shared with stakeholders through targeted communication efforts, including workshops, digital platforms, and printed materials. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/3.1.3Develop a policy evaluation report and share findings through a case study targeted at stakeholders. | UNDP () | Waste | Panama | null |  |  | Delayed | N/A; Activity rescheduled for the next period. | The delivery date for this output precedes the actual date of the agreement's signing and the disbursement of the first payment, resulting in a delay to its commencement. Rescheduling and adjustments to the timeline were carried out, this would be realized at the next period. | Consolidation of results and sharing them with the stakeholders | N/A | Nothing to deliver this period | [24 empty] | Delayed
Output 3.2 Draft roadmap of financial intruments | Number of plans, policies, laws, or regulations drafted or updated | 1 | 1 plan drafted or updated. | 2026-09-01 | Policy, regulation or other guideline | A draft roadmap for financial instruments in organic waste management will be developed. This roadmap will be based on the findings of the previous evaluations and workshops, tailoring financial tools to the specific needs of the identified projects. It will include a detailed assessment of existing financial mechanisms and propose new ones that address key challenges and opportunities. The roadmap will guide the government and private sector in mobilizing resources for the sustainable implementation of organic waste management projects. | Available in English or other agreed UN language, and grammatically correct + English summary Involvement of the beneficiary government throughout the development process, for example through consultation meetings Involvement of the CCAC focal point Agreement to, or acknowledgement of, the product presented by the beneficiary government (at the appropriate level) and the CCAC Secretariat | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/3.2 Draft roadmap of financial intruments | UNDP () | Waste | Panama | Financial institutions and government agencies. |  |  | On track | A first meeting with the National Secretariat of Public‑Private Partnerships (SNAPP) was held. The planning for a gender‑inclusive workshop to co‑design financial instruments was started. The comprehensive roadmap and an interactive digital version are scheduled for upcoming periods, pending workshop outcomes and budget estimates. | Due to the previously indicated delay and the dependency on having outputs 1 and 2 completed, rescheduling had to be carried out regarding this. As a mitigation, it has been considered to carry out a greater number of actions in upcoming periods. | Rescheduling due to delay in base activities, also the project will convene a gender‑inclusive co‑design workshop with financial institutions and public agencies. | See above | Nothing to deliver this period | [24 empty] | On track
Activity 3.2.1Host a workshop with financial institutions, government agencies, and private entities to co-design financial instruments tailored to organic waste projects, ensuring gender inclusion in discussions. | Organising, holding, or participating in a meeting or event | #VALUE! | null | 2026-03-01 | Work plan | This workshop will bring together financial institutions, government agencies, private sector representatives, and women-led organizations to co-design innovative financial instruments for organic waste projects. Participants will collaborate on identifying barriers to financing and brainstorming tailored solutions, including gender-inclusive tools such as microfinance or capacity-building grants. The outcomes will form the foundation for a draft roadmap of financial mechanisms. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/3.2.1Host a workshop with financial institutions, government agencies, and private entities to co-design financial instruments tailored to organic waste projects, ensuring gender inclusion in discussions. | UNDP () | Waste | Panama | null |  |  | On track | A first meeting was held with the National Secretariat of Public-Private Partnerships (SNAPP), and the planning of the workshop to be held in a future period was initiated with the creation of its work plan. | It depends on outputs 1 and 2 in order to be carried out; it will be performed as soon as these results are available. | Identification of the financial institutions, government agencies, and private entities competent for this activity and hosting of the workshop. | https://drive.google.com/drive/folders/19acUHrMg4Jg0gjop2w_U_UppIU08nJ2-?usp=sharing | Research or study | [24 empty] | On track
Activity 3.2.2Draft a comprehensive roadmap with actionable steps and estimated budgets, prioritizing funds for women-led initiatives. | Research, data collection, and/or report writing | #VALUE! | null | 2026-09-01 | Tool | This activity will build on the workshop outcomes to develop a comprehensive roadmap for implementing financial instruments for organic waste management. The roadmap will include actionable steps, estimated budgets, and a clear timeline for implementation. Special attention will be given to prioritizing funding mechanisms that support women-led initiatives and community-based projects. The roadmap will serve as a strategic guide for stakeholders to mobilize resources and align efforts with national sustainability goals. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/3.2.2Draft a comprehensive roadmap with actionable steps and estimated budgets, prioritizing funds for women-led initiatives. | UNDP () | Waste | Panama | null |  |  | Not started | N/A | N/A | N/A | N/A | Nothing to deliver this period | [24 empty] | Not started
Activity 3.2.3Create an interactive digital roadmap for dissemination to public and private stakeholders. | Producing and distributing communications materials | #VALUE! | null | 2026-09-01 | Meeting report | To enhance accessibility and engagement, this activity will involve transforming the financial roadmap into an interactive digital format. The digital roadmap will include user-friendly navigation features, visualizations of key data, and links to supporting resources. It will be disseminated through online platforms and shared with public and private stakeholders to facilitate its use in decision-making and investment planning. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/3.2.3Create an interactive digital roadmap for dissemination to public and private stakeholders. | UNDP () | Waste | Panama | null |  |  | Not started | N/A | N/A | N/A | N/A | Nothing to deliver this period | [24 empty] | Not started
Outcome 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Number of government entities with a demonstrated improved capacity for SLCP action | 20 | 20 government entities with improved capacity for SLCP action. | By project end | - | The project aims to strengthen the government’s capacity to evaluate and monitor organic waste management projects effectively. By developing targeted training programs and fostering collaboration with key stakeholders, the project ensures that newly acquired knowledge and skills are applied in practice. Knowledge-sharing platforms will play a pivotal role in disseminating results, lessons learned, and case studies while supporting the development of training materials and fostering local expertise. These efforts aim to facilitate the sustainable implementation of Short-Lived Climate Pollutant (SLCP) mitigation measures. The project assumes that by enhancing technical capacity, the government will be better equipped to design and implement effective policies and measures, creating a strong foundation for the long-term success of SLCP reduction initiatives linked to organic waste management. | - | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | (blank) | Waste | (blank) | (blank) |  |  | On track | Programmed output to be completed in future periods; for the moment, the planning of the first workshops has begun and one of them has been carried out. | Activity scheduled to take place in future periods. | Activity scheduled to take place in future periods. | N/A | Nothing to deliver this period | [24 empty] | On track
Output 4.1 Capacity building and technical assistance | Number of public events, webinars, or side events hosted | 4 | 4 workshops conducted with government entities. | 2027-06-01 | Meeting report, Training materials | Capacity building workshops and Technical Assistance for stakeholders working on organic waste management. These workshops will focus on enhancing the participants understanding of project development, cost-benefit analysis, and SLCP mitigation strategies. Training materials will be tailored to Panama's context, particulary focusing on the MERCA market in Panama City. The goal is to equip governemnt entities and other stakeholders with the knowledge and tools to implement effective organic waste management projects, while promoting collaboration and knowledge-sharing across sectors. | Agenda and event plan cleared by the beneficiary and/or CCAC Secretariat Event is promoted & details about event shared with CCAC at least one week in advance to support promotion CCAC is recognised (logo and as part of the agenda) Uses CCAC presentation template (where relevant / as an option) | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/4.1 Capacity building and technical assistance | UNDP () | Waste | Panama | Local governments, private sector, and NGOs. |  |  | On track | Capacity building progressed with an initial SLCP workshop delivered and a second workshop scheduled to support the national SLCP roadmap. Development of Panama‑specific training materials and a knowledge‑sharing platform is planned for upcoming periods to sustain technical assistance and stakeholder capacity. | Activity scheduled to take place in future periods. | Activity scheduled to take place in future periods. | See above | Meeting report | [24 empty] | On track
Activity 4.1.1Organize training workshops for government officials and market stakeholders on SLCP mitigation strategies, offering flexible schedules and childcare options to ensure women’s participation. | Developing and/or delivering training | #VALUE! | null | 2026-12-01 | Training materials | This activity will involve organizing a series of capacity-building workshops aimed at enhancing the technical knowledge of government officials, market stakeholders, and other relevant actors on SLCP mitigation strategies. The workshops will cover topics such as best practices in organic waste management, SLCP reduction, and the integration of gender-sensitive approaches. To ensure equal participation, flexible schedules and childcare options will be provided for women participants. Training sessions will be delivered both in-person and virtually to maximize accessibility. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/4.1.1Organize training workshops for government officials and market stakeholders on SLCP mitigation strategies, offering flexible schedules and childcare options to ensure women’s participation. | UNDP () | Waste | Panama | null |  |  | On track | An initial introductory workshop was held, and a technical follow-up workshop focused on the country's SLCP roadmap is currently being planned.d | N/A | N/A | https://drive.google.com/drive/folders/14fWkMAq6Ul5etzC3Ot7PSdeM2JdMaNjn?usp=sharing | Meeting report | [24 empty] | On track
Activity 4.1.2Develop training materials tailored to Panama’s context, including gender-sensitive approaches to waste management. | Producing and distributing communications materials | #VALUE! | null | 2026-09-01 | Tool | This activity will focus on designing and developing training materials that are tailored to Panama’s specific context in waste management and SLCP mitigation. The materials will include presentations, handouts, case studies, and practical exercises that address local challenges and opportunities. Gender-sensitive approaches will be integrated into the materials to highlight the role of women in waste management and promote inclusive practices. These resources will be made available in both print and digital formats to ensure broad accessibility. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/4.1.2Develop training materials tailored to Panama’s context, including gender-sensitive approaches to waste management. | UNDP () | Waste | Panama | null |  |  | Not started | N/A | N/A | N/A | N/A | Nothing to deliver this period | [24 empty] | Not started
Activity 4.1.3Establish a knowledge-sharing platform for continuous capacity-building, | Producing and distributing communications materials | #VALUE! | null | 2027-06-01 | Work plan | This activity involves creating a knowledge-sharing platform to provide ongoing support and capacity-building for stakeholders engaged in SLCP mitigation. The platform will feature resources such as training materials, case studies, and interactive forums for peer learning. Best practices and lessons learned from both women and men will be documented and showcased to promote gender-inclusive approaches. The platform will be accessible online, ensuring that stakeholders from across Panama can benefit from the resources and collaborate on shared goals. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/4.1.3Establish a knowledge-sharing platform for continuous capacity-building, | UNDP () | Waste | Panama | null |  |  | Not started | N/A | N/A | N/A | N/A | Nothing to deliver this period | [24 empty] | Not started
Activity 4.1.4Project Management and Administration | Other | #VALUE! | null | 2027-06-01 | null | This activity will ensure the efficient management of the project, covering general operational costs, monitoring, financial and administrative reporting, as well as overall project coordination. It will also include expenses related to technical supervision and contract management. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/4.1.4Project Management and Administration | UNDP () | Waste | Panama | null |  |  | On track | Project management and administration functions were established to ensure efficient implementation: operational and coordination mechanisms were activated, initial monitoring and financial reporting templates were developed, and procurement and contract management processes were initiated. Technical supervision arrangements and regular coordination meetings were held, expenditures were tracked against the budget | Activity scheduled to take place throughout the project | Activity scheduled to take place throughout the project | N/A | Nothing to deliver this period | [24 empty] | On track
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-

## 3. Expenditures
3. Expenditure report |  |  |  | See instructions
Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003)
UNDP Panama
PLANNED | [9 empty] | FIRST REPORTING PERIOD: 11/12/2025 - 30/06/2026 |  | SECOND REPORTING PERIOD: 01/07/2026 - 31/12/2026 |  | THIRD REPORTING PERIOD: 01/01/2027 - 30/06/2027 |  | FOURTH REPORTING PERIOD: |  | FIFTH REPORTING PERIOD: |  | TOTAL EXPENDITURE
Related activity | Category | Source | Total budget | 2025 Cost (US$) | 2026 Cost (US$) | 2027 cost (US$) | Implementer agreement | Project | Unique code | Expenditure (US$) during 1st period | Comments on 1st period | Expenditure (US$) during 2nd period | Comments on 2nd period | Expenditure (US$) during 3rd period | Comments on 3rd period | Expenditure (US$) during 4th period | Comments on 4th period | Expenditure (US$) during 5th period | Comments on 5th period | Total Expenditure | Variance | Var.% | INSTRUCTIONS
Activity 1.1.1 Conduct consultations with government entities, MERCA representatives, and private sector players, ensuring equal participation of women and men, to define treatment options. | Staff and Other Personnel Costs | CCAC | 15000 | 15000 | "" | "" | PA-24-003/1.1.1-1 Pre-feasibility studies for organic waste visit different market and landfills | Waste | 15000 | 5880 | N/A | [8 empty] | 5880 | -9120 | -60.8% | The first 12 columns in this table contain the budgeted costs for this implementer agreement. These costs are listed in ascending order by expenditure number. Scroll up and down the list to ensure you see all expenditure items. Columns to the right of the budget list contain fields that must be completed for each expenditure item at the indicated reporting period. Scroll left and right to find the relevant reporting period under which to enter expenditures. Note that expenditures and comments entered for previous reporting periods will be locked for editing and cannot be changed once they have been approved. Complete all cells for each expenditure item in the relevant reporting period. No cell should be left blank. If there is no expenditure to report for an item, enter "0" in the expenditure column and "N/A" or "Not started" in the notes column.
Activity 1.1.1 Conduct consultations with government entities, MERCA representatives, and private sector players, ensuring equal participation of women and men, to define treatment options. | Travel | CCAC | 2000 | 2000 | "" | "" | PA-24-003/1.1.1-2 Waste Management and Infrastructure Consultant | Waste | 2000 | 1333 | Due to the nature of the activities, part of the allocated budget was used to support the organization of local workshops and meetings. Since these activities were conducted locally, no per diem or transportation costs were incurred. | [8 empty] | 1333 | -667 | -33.35%
Activity 1.1.2 Evaluate technical and economic feasibility for technologies like composting and anaerobic digestion, including an analysis of how these benefit women-led businesses and communities. | Staff and Other Personnel Costs | CCAC | 20000 | 20000 | "" | "" | PA-24-003/1.1.2-1 Waste Management and Infrastructure Consultant | Waste | 20000 | 12373.75 | N/A | [8 empty] | 12373.75 | -7626.25 | -38.13%
Activity 1.2.1 Map existing and potential decentralized infrastructure for waste management, engaging municipalities and local organizations to provide on-ground insights. | Staff and Other Personnel Costs | CCAC | 10000 | "" | 10000 | "" | PA-24-003/1.2.1-1 Field visits for data collection | Waste | 10000 | 0
Activity 1.2.2 Conduct site visits and surveys, collecting gender-disaggregated data to ensure proposed infrastructure meets the needs of both genders. | Travel | CCAC | 1800 | 1800 | "" | "" | PA-24-003/1.2.2-1 Waste Management and Infrastructure Consultant | Waste | 1800 | 0
Activity 1.2.3 Develop cost-benefit analyses, incorporating feedback from diverse stakeholders through an online webinar. | Staff and Other Personnel Costs | CCAC | 5000 | "" | 5000 | "" | PA-24-003/1.2.3-1 Waste Management and Infrastructure Consultant | Waste | 5000 | 0
Activity 1.3.1 Develop a list of complementary technologies and infrastructure to enhance organic waste management, consulting stakeholders such as circular economy specialists and private sector innovators. | Staff and Other Personnel Costs | CCAC | 20000 | "" | 20000 | "" | PA-24-003/1.3.1-1 Training workshops, seminars and meetings | Waste | 20000 | 0
Activity 1.3.2 Host a gender-balanced expert panel to validate recommendations, prioritizing options that create employment for women. | Contractual Services | CCAC | 1000 | 1000 | "" | "" | PA-24-003/1.3.2-1 Infographic design | Waste | 1000 | 0
Activity 1.3.3 Prepare an accessible visual infographic summarizing key recommendations for public dissemination. | Contractual Services | CCAC | 2000 | "" | 2000 | "" | PA-24-003/1.3.3-1 Waste Management and Infrastructure Consultant | Waste | 2000 | 0
Activity 1.4.1 Conduct an in-depth evaluation of essential infrastructure for organic waste management (e.g., composting plants, biodigesters) | Staff and Other Personnel Costs | CCAC | 10000 | "" | 10000 | "" | PA-24-003/1.4.1-1 Waste Management and Infrastructure Consultant | Waste | 10000 | 0
Activity 1.4.2 Compile findings into a comprehensive report highlighting investment opportunities, environmental and economic benefits, and potential social impacts. Share the report through workshops and online platforms targeting public and private stakeholders. | Staff and Other Personnel Costs | CCAC | 5000 | "" | 5000 | "" | PA-24-003/1.4.2-1 Support innovation challenge | Waste | 5000 | 0
Activity 2.1.1Identify and evaluate projects with business potential, ensuring inclusion of women-led initiatives and alignment with national goals. | Contractual Services | CCAC | 20000 | "" | 20000 | "" | PA-24-003/2.1.1-1 Circular Economy Specialist | Waste | 20000 | 0
Activity 2.1.2Develop a portfolio of selected projects with detailed descriptions and expected outcomes, highlighting gender-specific benefits. | Staff and Other Personnel Costs | CCAC | 15000 | "" | 15000 | "" | PA-24-003/2.1.2-1 Circular Economy Specialist | Waste | 15000 | 0
Activity 2.1.3Engage private sector investors and financial institutions in the evaluation process to co-create viable financing strategies. | Staff and Other Personnel Costs | CCAC | 15000 | "" | 15000 | "" | PA-24-003/2.1.3-1 Training workshops, seminars and meetings | Waste | 15000 | 0
Activity 2.2.1Host a multi-stakeholder workshop, ensuring representation from women-led organizations, to prioritize three high-impact projects. | Contractual Services | CCAC | 3000 | "" | 3000 | "" | PA-24-003/2.2.1-1 Financial and Business Development Consultant | Waste | 3000 | 0
Activity 2.2.2Develop detailed financial plans for selected projects, including specific tools tailored to benefit marginalized groups. | Staff and Other Personnel Costs | CCAC | 15000 | "" | 10000 | 5000 | PA-24-003/2.2.2-1 computers | Waste | 15000 | 0
Activity 2.2.3Release a press statement highlighting the selected projects to attract further investment and support. | Equipment Vehicles and Furniture | CCAC | 3000 | 3000 | "" | "" | PA-24-003/2.2.3-1 Circular Economy Specialist | Waste | 3000 | 0
Activity 2.2.3Release a press statement highlighting the selected projects to attract further investment and support. | Staff and Other Personnel Costs | CCAC | 15000 | "" | "" | 15000 | PA-24-003/2.2.3-2 National Consultant - Policy and SLCP Mitigation Consultant | Waste | 15000 | 0
Activity 3.1.1Review existing policies and regulations related to organic waste and SLCPs, engaging policymakers, academics, and gender specialists. | Staff and Other Personnel Costs | CCAC | 15000 | "" | 15000 | "" | PA-24-003/3.1.1-1 National Consultant - Policy and SLCP Mitigation Consultant | Waste | 15000 | 0
Activity 3.1.2Identify policy gaps and prioritize actions for short, medium, and long-term implementation, ensuring gender-disaggregated data is part of the analysis. | Staff and Other Personnel Costs | CCAC | 15000 | "" | 15000 | "" | PA-24-003/3.1.2-1 Training workshops, seminars and meetings | Waste | 15000 | 0
Activity 3.1.3Develop a policy evaluation report and share findings through a case study targeted at stakeholders. | Contractual Services | CCAC | 3000 | "" | 3000 | "" | PA-24-003/3.1.3-1 Training workshops, seminars and meetings | Waste | 3000 | 0
Activity 3.2.1Host a workshop with financial institutions, government agencies, and private entities to co-design financial instruments tailored to organic waste projects, ensuring gender inclusion in discussions. | Contractual Services | CCAC | 3000 | "" | 3000 | "" | PA-24-003/3.2.1-1 Financial and Business Development Consultant | Waste | 3000 | 0
Activity 3.2.2Draft a comprehensive roadmap with actionable steps and estimated budgets, prioritizing funds for women-led initiatives. | Staff and Other Personnel Costs | CCAC | 20000 | "" | 20000 | "" | PA-24-003/3.2.2-1 Contractual services for the design financial roadmap | Waste | 20000 | 0
Activity 3.2.3Create an interactive digital roadmap for dissemination to public and private stakeholders. | Contractual Services | CCAC | 5000 | "" | 5000 | "" | PA-24-003/3.2.3-1 Training workshops, seminars and meetings | Waste | 5000 | 0
Activity 4.1.1Organize training workshops for government officials and market stakeholders on SLCP mitigation strategies, offering flexible schedules and childcare options to ensure women’s participation. | Contractual Services | CCAC | 4000 | 1000 | 2000 | 1000 | PA-24-003/4.1.1-1 Communications materials | Waste | 4000 | 0
Activity 4.1.2Develop training materials tailored to Panama’s context, including gender-sensitive approaches to waste management. | Contractual Services | CCAC | 25000 | "" | 10000 | 15000 | PA-24-003/4.1.2-1 Communications specialist | Waste | 25000 | 0
Activity 4.1.2Develop training materials tailored to Panama’s context, including gender-sensitive approaches to waste management. | Contractual Services | CCAC | 20686 | "" | 10343 | 10343 | PA-24-003/4.1.2-2 communication materials | Waste | 20686 | 0
Activity 4.1.3Establish a knowledge-sharing platform for continuous capacity-building, | Contractual Services | CCAC | 16000 | "" | 16000 | "" | PA-24-003/4.1.2-1 communication materials | Waste | 16000 | 0
Activity 4.1.4Project Management and Administration | Operating and Other Direct Costs | Co-funding | 15000 | 7500 | 7500 | "" | PA-24-003/4.1.3-1 Rental Offices | Waste | 15000 | 0
Activity 4.1.4Project Management and Administration | Staff and Other Personnel Costs | CCAC | 40000 | 10000 | 20000 | 10000 | PA-24-003/4.1.4-1 Contract Project Asistant | Waste | 40000 | 0
Activity 4.1.4Project Management and Administration | Staff and Other Personnel Costs | CCAC | 20000 | 5000 | 10000 | 5000 | PA-24-003/4.1.4-2 Programme Support Costs (PSC) | Waste | 20000 | 0
Activity 4.1.4Project Management and Administration | UN-PSC | CCAC | 25514 | 6378.5 | 12757 | 6378.5 | PA-24-003/4.1.4-3 Waste Management and Infrastructure Consultant | Waste | 25514 | 1371.0725 | N/A | [8 empty] | 1371.0725 | -24142.9275 | -94.63%
Total

## 4. Outputs
4. Output indicators |  | See instructions
Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003)
UNDP Panama
Outputs to report by project end: 9 | [12 empty] | RELEVANT DOCUMENT 1 (optional) | [7 empty] | RELEVANT DOCUMENT 2 (optional)
Output | Indicator | Target | Unit | Indicator unit of measure | Amount delivered | Disaggregation info instructions 1 | Dissagregation info (if requested) | Disaggregation info instructions 2 | Dissagregation info (if requested)2 | Additional info instructions | Additional info (if requested) | Pollutants directly addressed | Document title | Document summary | Document URL | Add to the CCAC website? | Document type | Authors | Sources | Date published (m yy) | Document title2 | Document summary2 | Document URL2 | Add to the CCAC website?2 | Document type2 | Authors2 | Sources2 | Date published (m yy)2 | Unique code | Sector | Project | Beneficiaries | Implementer | Complete? | INSTRUCTIONS
Output 1.1 Pre-feasibility studies for organic waste treatment options | Number of plans, policies, laws, or regulations drafted or updated | 1 | 1 pre-feasibility study report developed. | Amount: |  | Type: |  | Scale: |  | SLCP mitigation actions and/or targets included: | [18 empty] | PA-24-003/1.1 Pre-feasibility studies for organic waste treatment options | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Panama | UNDP () | no | The first 4 columns in this table list the outputs, indicators, and targets for this implementer agreement in ascending order by output number. Columns to the right of the output list contain instructions on how to report on the performance indicators selected for the output. Information in this table is reported only once for each output and only after the output is marked as "Complete" in the tab "2. Narrative." All cells in this table must be completed unless they are marked as "optional".
Output 1.2 Estimates of decentralized infraestructure supporting diverted organic waste | Number of SLCP assessments, emissions inventories, and other emissions datasets produced | 4 | 4 SLCP assessments, emissions inventories, or other emissions datasets produced. | Amount: |  | Type: |  | n/a |  | Briefly describe what was produced and how this information will be used by the beneficiary: | [18 empty] | PA-24-003/1.2 Estimates of decentralized infraestructure supporting diverted organic waste | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Panama | UNDP () | no
Output 1.3 Recommendations for alternative/ complementary infraestrucutre | Number of SLCP knowledge resources or tools produced | 1 | 1 SLCP knowledge resource or tool produced. | Number of resources produced: |  | Type of resource: |  | n/a |  | Briefly descbribe how the resource is being used by the intended audience: | [18 empty] | PA-24-003/1.3 Recommendations for alternative/ complementary infraestrucutre | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Panama | UNDP () | no
Output 1.4 Report indentifying necessary infraestructure and investment to support organic waste management | Number of plans, policies, laws, or regulations drafted or updated | 1 | 1 plan, policy, law, or regulation drafted or updated. | Amount: |  | Type: |  | Scale: |  | SLCP mitigation actions and/or targets included: | [18 empty] | PA-24-003/1.4 Report indentifying necessary infraestructure and investment to support organic waste management | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Panama | UNDP () | no
Output 2.1 Identification of projects/inititives | Number of partnerships, associations, or campaigns launched to drive SLCP action | 5 | 5 Partnerships to drive SLCP action. | Number of initiatives: |  | Type of action: |  | Scale: |  | Mitigation actions, targets: | [18 empty] | PA-24-003/2.1 Identification of projects/inititives | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Panama | UNDP () | no
Output 2.2 Stakeholder Engagement and Strategic Financial Planning for Selected Projects | Number of partnerships, associations, or campaigns launched to drive SLCP action | 3 | 3 Associations launched to drive SLCP action. | Number of initiatives: |  | Type of action: |  | Scale: |  | Mitigation actions, targets: | [18 empty] | PA-24-003/2.2 Stakeholder Engagement and Strategic Financial Planning for Selected Projects | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Panama | UNDP () | no
Output 3.1 Analysis of policies to mitigate SLCPs | Number of plans, policies, laws, or regulations drafted or updated | 1 | 1 plan, drafted or updated. | Amount: |  | Type: |  | Scale: |  | SLCP mitigation actions and/or targets included: | [18 empty] | PA-24-003/3.1 Analysis of policies to mitigate SLCPs | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Panama | UNDP () | no
Output 3.2 Draft roadmap of financial intruments | Number of plans, policies, laws, or regulations drafted or updated | 1 | 1 plan drafted or updated. | Amount: |  | Type: |  | Scale: |  | SLCP mitigation actions and/or targets included: | [18 empty] | PA-24-003/3.2 Draft roadmap of financial intruments | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Panama | UNDP () | no
Output 4.1 Capacity building and technical assistance | Number of public events, webinars, or side events hosted | 4 | 4 workshops conducted with government entities. | Number of events hosted: |  | Size of event: |  | n/a |  | Link to the event details: | [18 empty] | PA-24-003/4.1 Capacity building and technical assistance | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Panama | UNDP () | no

## 5. Outcomes
5. Outcome indicators |  | See instructions
Project: Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003)
UNDP Panama
Outcomes to report by project end: 3 | [11 empty] | RELEVANT DOCUMENT 1 | [7 empty] | RELEVANT DOCUMENT 2
Outcome | Indicator | Target | Unit | Unit of measure | Amount | Disaggregation info instructions | Disaggregation info (if applicable) | Disaggregation info instructions2 | Disaggregation info (if applicable)2 | Additional info (if applicable) | Additional info | Title Document 1 | Summary Document 1 | URL Document 1 | Add to CCAC website? Document 1 | Type Document 1 | Authors Document 1 | Sources Document 1 | Date published (mmmm yyyy) Document 1 | Title Document 2 | Summary Document 2 | URL Document 2 | Add to CCAC website? Document 2 | Type Document 2 | Authors Document 2 | Sources Document 2 | Date published (mmmm yyyy) Document 2 | Sector | Beneficiaries | Contract | Beneficiary | Complete | INSTRUCTIONS
(blank) | (blank) | (blank) | (blank) | [24 empty] | (blank) | (blank) | (blank) |  | #N/A | The first 4 columns in this table list the outcomes, indicators, and targets for this implementer agreement in ascending order by outcome number. Columns to the right of the outcome list contain instructions on how to report on the performance indicators selected for the outcome. Information in this table is reported only once for each output and only after the output is marked as "Complete" in the tab "2. Narrative." All cells in this table must be completed unless they are marked as "optional".
Outcome 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Number of government entities with a demonstrated improved capacity for SLCP action | 4 | 4 government entities with improved capacity for SLCP action. | Number of entities: |  | Type of entity: |  | n/a |  | List the government entities by name: | [17 empty] | PA-24-003/1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste |  | no
Outcome 2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 5 | 5 action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures | Number of plans: |  | Type of plan: |  | Status: |  | List the SLCP-relevant details included in the plan, including the sectors, pollutants, mitigation actions or targets mentioned: | [17 empty] | PA-24-003/2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste |  | no
Outcome 3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 1 | 1 roadmap | Number of plans: |  | Type of plan: |  | Status: |  | List the SLCP-relevant details included in the plan, including the sectors, pollutants, mitigation actions or targets mentioned: | [17 empty] | PA-24-003/3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste |  | no
Outcome 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Number of government entities with a demonstrated improved capacity for SLCP action | 20 | 20 government entities with improved capacity for SLCP action. | Number of entities: |  | Type of entity: |  | n/a |  | List the government entities by name: | [17 empty] | PA-24-003/4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after.

## Paste Implementation Plan here (hidden)
1. Paste entire Implementation Plan table here. 2. Check that columns match. Delete duplicate headings. 3. Click: Data > Refresh all 4. Filter by implementer + (blank). Save a copy for each implementer 5. "Permanently" hide this tab - Developer > Visual basic.
Selected agreement:
Agreement
UNDP ()
(blank)
RELATED ACTIVITY | EXPENDITURE CATEGORY | EXPENDITURE # | DESCRIPTION OF EXPENDITURE | IMPLEMENTER | NOTES | SOURCE OF FUNDING | QUANTITY | UNIT | UNIT COST ($US) | TOTAL COST | YEAR 1 COST ($US) | YEAR 2 COST ($US) | YEAR 3 COST ($US) | ADD UP TO TOTAL? | Activity code | Expenditure for summary | Related activity for summary | Implementer agreement | Unique code | Expenditure/Code | Expenditure/Level above | Expenditure/Level | Project | Activities.RELATED OUTPUT | Activities.ACTIVITY # | Activities.ACTIVITY NAME | Activities.ACTIVITY DESCRIPTION | Activities.ACTIVITY CATEGORY | Activities.AMOUNT | Activities.UNIT | Activities.IMPLEMENTER | Activities.LOCATION | Activities.BENEFICIARY COUNTRIES | Activities.OTHER BENEFICIARIES | Activities.ACTIVITY START DATE | Activities.DELIVERY DATE | Activities.PROOF OF DELIVERY TYPE | Delivery description | Activities.ACTIVITY END DATE | Activities.CCAC ACCEPTANCE CRITERIA | Activities.Output # for formula | Activities.Activity for summary | Activities.Related output for summary | Activities.Activity name for list | Activities.Activity/Unique code | Activities.Activity/Code/Name | Activities.Activity/Level above | Activities.Activity/Level | Activities.Activity/Project | Outputs.OUTPUT # | Outputs.OUTPUT NAME | Outputs.DESCRIPTION | Outputs.RELATED OUTCOME | Outputs.INDICATOR | Outputs.AMOUNT | Outputs.UNIT | Outputs.IMPLEMENTER | Outputs.USERS/BENEFICIARIES | Outputs.OTHER BENEFICIARIES | Outputs.INTENDED USE | Outputs.PROOF OF DELIVERY TYPE | Outputs.DELIVERY DESCRIPTION | Outputs.DELIVERY DATE | Outputs.CCAC ACCEPTANCE CRITERIA | Outputs.Output for dropdown | Outputs.Output for summary | Outputs.Related outcome for summary | Outputs.Output/Unique code | Outputs.Output/Code/Name | Outputs.Output/Level | Outputs.Output/Level above | Outputs.Output/Project | Outcomes.OUTCOME # | Outcomes.OUTCOME NAME | Outcomes.OUTCOME DESCRIPTION | Outcomes.OUTCOME INDICATOR | Outcomes.TARGET | Outcomes.TARGET UNIT | Outcomes.Outcome for dropdown | Outcomes.Outcome for summary | Outcomes.Unique code | Outcomes.Outcome/Code | Outcomes.Outcome/Level above | Outcomes.Oucome/Level | Outcomes.Outcome/Project | Project.1.PROJECT # | Project.1.Sector | Project.1.Full project name | Expenditure.Agreement-Implementer | Output.Agreement-Implementer | Activity.Agreement-Implementer
4.1.4Project Management and Administration | Staff and Other Personnel Costs | 4.1.4-1 | Contract Project Asistant | UNDP | null | CCAC | 1 | Cost | 40000 | 40000 | 10000 | 20000 | 10000 | Yes. | 4/1/2004 | Expenditure 4.1.4-1 Contract Project Asistant | Activity 4.1.4Project Management and Administration | UNDP () | PA-24-003/4.1.4-1 | PA-24-003/4.1.4-1 Contract Project Asistant | PA-24-003/4.1.4Project Management and Administration | Expenditure | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 4.1 Capacity building and technical assistance | 4.1.4 | 4.1.4Project Management and Administration | This activity will ensure the efficient management of the project, covering general operational costs, monitoring, financial and administrative reporting, as well as overall project coordination. It will also include expenses related to technical supervision and contract management. | Other | null | null | UNDP | Panama | Panama | null | 6/1/2025 | 6/1/2027 | null | null | null | null | 4.1 | Activity 4.1.4Project Management and Administration | Output 4.1 Capacity building and technical assistance | 4.1.4Project Management and Administration | PA-24-003/4.1.4 | PA-24-003/4.1.4Project Management and Administration | PA-24-003/4.1 Capacity building and technical assistance | Activity | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 4.1 | Capacity building and technical assistance | Capacity building workshops and Technical Assistance for stakeholders working on organic waste management. These workshops will focus on enhancing the participants understanding of project development, cost-benefit analysis, and SLCP mitigation strategies. Training materials will be tailored to Panama's context, particulary focusing on the MERCA market in Panama City. The goal is to equip governemnt entities and other stakeholders with the knowledge and tools to implement effective organic waste management projects, while promoting collaboration and knowledge-sharing across sectors. | 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Number of public events, webinars, or side events hosted | 4 | 4 workshops conducted with government entities. | UNDP | Panama | Local governments, private sector, and NGOs. | stakeholders with skills to implement SLCP reduction strategies. | Meeting report, Training materials | 2/1/2027 12:00:00 AM | 6/1/2027 | Agenda and event plan cleared by the beneficiary and/or CCAC Secretariat Event is promoted & details about event shared with CCAC at least one week in advance to support promotion CCAC is recognised (logo and as part of the agenda) Uses CCAC presentation template (where relevant / as an option) | 4.1 Capacity building and technical assistance | Output 4.1 Capacity building and technical assistance | Outcome 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | PA-24-003/4.1 | PA-24-003/4.1 Capacity building and technical assistance | Output | PA-24-003/4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 4 | The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | The project aims to strengthen the government’s capacity to evaluate and monitor organic waste management projects effectively. By developing targeted training programs and fostering collaboration with key stakeholders, the project ensures that newly acquired knowledge and skills are applied in practice. Knowledge-sharing platforms will play a pivotal role in disseminating results, lessons learned, and case studies while supporting the development of training materials and fostering local expertise. These efforts aim to facilitate the sustainable implementation of Short-Lived Climate Pollutant (SLCP) mitigation measures. The project assumes that by enhancing technical capacity, the government will be better equipped to design and implement effective policies and measures, creating a strong foundation for the long-term success of SLCP reduction initiatives linked to organic waste management. | Number of government entities with a demonstrated improved capacity for SLCP action | 20 | 20 government entities with improved capacity for SLCP action. | 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Outcome 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | PA-24-003/4. | PA-24-003/4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Outcome | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003 | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | UNDP () | UNDP ()
4.1.4Project Management and Administration | Staff and Other Personnel Costs | 4.1.4-2 | Programme Support Costs (PSC) | UNDP | null | CCAC | 1 | consultant | 20000 | 20000 | 5000 | 10000 | 5000 | Yes. | 4/1/2004 | Expenditure 4.1.4-2 Programme Support Costs (PSC) | Activity 4.1.4Project Management and Administration | UNDP () | PA-24-003/4.1.4-2 | PA-24-003/4.1.4-2 Programme Support Costs (PSC) | PA-24-003/4.1.4Project Management and Administration | Expenditure | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 4.1 Capacity building and technical assistance | 4.1.4 | 4.1.4Project Management and Administration | This activity will ensure the efficient management of the project, covering general operational costs, monitoring, financial and administrative reporting, as well as overall project coordination. It will also include expenses related to technical supervision and contract management. | Other | null | null | UNDP | Panama | Panama | null | 6/1/2025 | 6/1/2027 | null | null | null | null | 4.1 | Activity 4.1.4Project Management and Administration | Output 4.1 Capacity building and technical assistance | 4.1.4Project Management and Administration | PA-24-003/4.1.4 | PA-24-003/4.1.4Project Management and Administration | PA-24-003/4.1 Capacity building and technical assistance | Activity | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 4.1 | Capacity building and technical assistance | Capacity building workshops and Technical Assistance for stakeholders working on organic waste management. These workshops will focus on enhancing the participants understanding of project development, cost-benefit analysis, and SLCP mitigation strategies. Training materials will be tailored to Panama's context, particulary focusing on the MERCA market in Panama City. The goal is to equip governemnt entities and other stakeholders with the knowledge and tools to implement effective organic waste management projects, while promoting collaboration and knowledge-sharing across sectors. | 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Number of public events, webinars, or side events hosted | 4 | 4 workshops conducted with government entities. | UNDP | Panama | Local governments, private sector, and NGOs. | stakeholders with skills to implement SLCP reduction strategies. | Meeting report, Training materials | 2/1/2027 12:00:00 AM | 6/1/2027 | Agenda and event plan cleared by the beneficiary and/or CCAC Secretariat Event is promoted & details about event shared with CCAC at least one week in advance to support promotion CCAC is recognised (logo and as part of the agenda) Uses CCAC presentation template (where relevant / as an option) | 4.1 Capacity building and technical assistance | Output 4.1 Capacity building and technical assistance | Outcome 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | PA-24-003/4.1 | PA-24-003/4.1 Capacity building and technical assistance | Output | PA-24-003/4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 4 | The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | The project aims to strengthen the government’s capacity to evaluate and monitor organic waste management projects effectively. By developing targeted training programs and fostering collaboration with key stakeholders, the project ensures that newly acquired knowledge and skills are applied in practice. Knowledge-sharing platforms will play a pivotal role in disseminating results, lessons learned, and case studies while supporting the development of training materials and fostering local expertise. These efforts aim to facilitate the sustainable implementation of Short-Lived Climate Pollutant (SLCP) mitigation measures. The project assumes that by enhancing technical capacity, the government will be better equipped to design and implement effective policies and measures, creating a strong foundation for the long-term success of SLCP reduction initiatives linked to organic waste management. | Number of government entities with a demonstrated improved capacity for SLCP action | 20 | 20 government entities with improved capacity for SLCP action. | 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Outcome 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | PA-24-003/4. | PA-24-003/4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Outcome | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003 | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | UNDP () | UNDP ()
4.1.4Project Management and Administration | UN-PSC | 4.1.4-3 | Waste Management and Infrastructure Consultant | UNDP | null | CCAC | 1 | Cost | 25514 | 25514 | 6378.5 | 12757 | 6378.5 | Yes. | 4/1/2004 | Expenditure 4.1.4-3 Waste Management and Infrastructure Consultant | Activity 4.1.4Project Management and Administration | UNDP () | PA-24-003/4.1.4-3 | PA-24-003/4.1.4-3 Waste Management and Infrastructure Consultant | PA-24-003/4.1.4Project Management and Administration | Expenditure | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 4.1 Capacity building and technical assistance | 4.1.4 | 4.1.4Project Management and Administration | This activity will ensure the efficient management of the project, covering general operational costs, monitoring, financial and administrative reporting, as well as overall project coordination. It will also include expenses related to technical supervision and contract management. | Other | null | null | UNDP | Panama | Panama | null | 6/1/2025 | 6/1/2027 | null | null | null | null | 4.1 | Activity 4.1.4Project Management and Administration | Output 4.1 Capacity building and technical assistance | 4.1.4Project Management and Administration | PA-24-003/4.1.4 | PA-24-003/4.1.4Project Management and Administration | PA-24-003/4.1 Capacity building and technical assistance | Activity | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 4.1 | Capacity building and technical assistance | Capacity building workshops and Technical Assistance for stakeholders working on organic waste management. These workshops will focus on enhancing the participants understanding of project development, cost-benefit analysis, and SLCP mitigation strategies. Training materials will be tailored to Panama's context, particulary focusing on the MERCA market in Panama City. The goal is to equip governemnt entities and other stakeholders with the knowledge and tools to implement effective organic waste management projects, while promoting collaboration and knowledge-sharing across sectors. | 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Number of public events, webinars, or side events hosted | 4 | 4 workshops conducted with government entities. | UNDP | Panama | Local governments, private sector, and NGOs. | stakeholders with skills to implement SLCP reduction strategies. | Meeting report, Training materials | 2/1/2027 12:00:00 AM | 6/1/2027 | Agenda and event plan cleared by the beneficiary and/or CCAC Secretariat Event is promoted & details about event shared with CCAC at least one week in advance to support promotion CCAC is recognised (logo and as part of the agenda) Uses CCAC presentation template (where relevant / as an option) | 4.1 Capacity building and technical assistance | Output 4.1 Capacity building and technical assistance | Outcome 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | PA-24-003/4.1 | PA-24-003/4.1 Capacity building and technical assistance | Output | PA-24-003/4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 4 | The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | The project aims to strengthen the government’s capacity to evaluate and monitor organic waste management projects effectively. By developing targeted training programs and fostering collaboration with key stakeholders, the project ensures that newly acquired knowledge and skills are applied in practice. Knowledge-sharing platforms will play a pivotal role in disseminating results, lessons learned, and case studies while supporting the development of training materials and fostering local expertise. These efforts aim to facilitate the sustainable implementation of Short-Lived Climate Pollutant (SLCP) mitigation measures. The project assumes that by enhancing technical capacity, the government will be better equipped to design and implement effective policies and measures, creating a strong foundation for the long-term success of SLCP reduction initiatives linked to organic waste management. | Number of government entities with a demonstrated improved capacity for SLCP action | 20 | 20 government entities with improved capacity for SLCP action. | 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Outcome 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | PA-24-003/4. | PA-24-003/4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Outcome | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003 | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | UNDP () | UNDP ()
1.1.1 Conduct consultations with government entities, MERCA representatives, and private sector players, ensuring equal participation of women and men, to define treatment options. | Staff and Other Personnel Costs | 1.1.1-1 | Pre-feasibility studies for organic waste visit different market and landfills | UNDP | Consultant hired for pre-feasibility analysis | CCAC | 1 | Consultant-month | 15000 | 15000 | 15000 | null | null | Yes. | 1/1/2001 | Expenditure 1.1.1-1 Pre-feasibility studies for organic waste visit different market and landfills | Activity 1.1.1 Conduct consultations with government entities, MERCA representatives, and private sector players, ensuring equal participation of women and men, to define treatment options. | UNDP () | PA-24-003/1.1.1-1 | PA-24-003/1.1.1-1 Pre-feasibility studies for organic waste visit different market and landfills | PA-24-003/1.1.1 Conduct consultations with government entities, MERCA representatives, and private sector players, ensuring equal participation of women and men, to define treatment options. | Expenditure | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 1.1 Pre-feasibility studies for organic waste treatment options | 1.1.1 | 1.1.1 Conduct consultations with government entities, MERCA representatives, and private sector players, ensuring equal participation of women and men, to define treatment options. | This activity will involve organizing consultations with key stakeholders to identify feasible organic waste treatment technologies. These sessions will include representatives from government entities, MERCA, private sector players, and NGOs, with a focus on ensuring gender-balanced participation. The consultations will evaluate existing waste management practices, discuss potential treatment solutions (e.g., composting, biodigesters), and collect stakeholder input to define the best approaches. | Organising, holding, or participating in a meeting or event | null | null | UNDP | Panama | Panama | null | 6/1/2025 | 9/1/2025 | Policy, regulation or other guideline | null | null | null | 1.1 | Activity 1.1.1 Conduct consultations with government entities, MERCA representatives, and private sector players, ensuring equal participation of women and men, to define treatment options. | Output 1.1 Pre-feasibility studies for organic waste treatment options | 1.1.1 Conduct consultations with government entities, MERCA representatives, and private sector players, ensuring equal participation of women and men, to define treatment options. | PA-24-003/1.1.1 | PA-24-003/1.1.1 Conduct consultations with government entities, MERCA representatives, and private sector players, ensuring equal participation of women and men, to define treatment options. | PA-24-003/1.1 Pre-feasibility studies for organic waste treatment options | Activity | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 1.1 | Pre-feasibility studies for organic waste treatment options | Pre-feasibility studies for organic waste treatment options conducted in Panama City. These studies will evaluate the technical and economic feasibility of potential treatment technologies/solutions, such as composting, anaerobic digestion, and other technologies to manage organic waste effectively. The goal is to identify the most viable treatment methods that support waste diversion, reduce methane emissions, and promote circular economies. The studies will provide critical data and analysis on costs, environmental benefits, and operational feasibility, laying the groundwork for informed decision-making and future investments in sustainable organic waste management infrastructure, ensuring alignment with national policies and international commitments. | 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Number of plans, policies, laws, or regulations drafted or updated | 1 | 1 pre-feasibility study report developed. | UNDP | Panama | National and local governments responsible for waste management. | Provide data to guide government decisions on sustainable and effective organic waste management solutions. | Research or study | 11/1/2025 12:00:00 AM | 12/1/2025 | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | 1.1 Pre-feasibility studies for organic waste treatment options | Output 1.1 Pre-feasibility studies for organic waste treatment options | Outcome 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | PA-24-003/1.1 | PA-24-003/1.1 Pre-feasibility studies for organic waste treatment options | Output | PA-24-003/1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 1 | The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | The project’s outputs will identify and develop innovative and practical treatment options and solutions for managing organic waste, generating critical data on decentralized infrastructure needs, such as composting plants, biodigesters, food and material recovery, and waste reduction technologies. These solutions will integrate circular economy principles, prioritize locally based consultants with local language capabilities, and actively engage the private sector through targeted knowledge exchange initiatives. By leveraging activities such as pre-feasibility studies, infrastructure estimates, and actionable recommendations, the project will equip the government with comprehensive knowledge to make informed decisions on effective and sustainable waste management solutions. This enhanced knowledge is expected to contribute to significant environmental, economic, and social benefits, including reduced food waste, methane emissions, and support for national and international sustainability goals. The projec... | Number of government entities with a demonstrated improved capacity for SLCP action | 4 | 4 government entities with improved capacity for SLCP action. | 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Outcome 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | PA-24-003/1. | PA-24-003/1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Outcome | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003 | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | UNDP () | UNDP ()
1.1.1 Conduct consultations with government entities, MERCA representatives, and private sector players, ensuring equal participation of women and men, to define treatment options. | Travel | 1.1.1-2 | Waste Management and Infrastructure Consultant | UNDP | Travel for on-site studies and stakeholder engagement | CCAC | 5 | Trips | 400 | 2000 | 2000 | null | null | Yes. | 1/1/2001 | Expenditure 1.1.1-2 Waste Management and Infrastructure Consultant | Activity 1.1.1 Conduct consultations with government entities, MERCA representatives, and private sector players, ensuring equal participation of women and men, to define treatment options. | UNDP () | PA-24-003/1.1.1-2 | PA-24-003/1.1.1-2 Waste Management and Infrastructure Consultant | PA-24-003/1.1.1 Conduct consultations with government entities, MERCA representatives, and private sector players, ensuring equal participation of women and men, to define treatment options. | Expenditure | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 1.1 Pre-feasibility studies for organic waste treatment options | 1.1.1 | 1.1.1 Conduct consultations with government entities, MERCA representatives, and private sector players, ensuring equal participation of women and men, to define treatment options. | This activity will involve organizing consultations with key stakeholders to identify feasible organic waste treatment technologies. These sessions will include representatives from government entities, MERCA, private sector players, and NGOs, with a focus on ensuring gender-balanced participation. The consultations will evaluate existing waste management practices, discuss potential treatment solutions (e.g., composting, biodigesters), and collect stakeholder input to define the best approaches. | Organising, holding, or participating in a meeting or event | null | null | UNDP | Panama | Panama | null | 6/1/2025 | 9/1/2025 | Policy, regulation or other guideline | null | null | null | 1.1 | Activity 1.1.1 Conduct consultations with government entities, MERCA representatives, and private sector players, ensuring equal participation of women and men, to define treatment options. | Output 1.1 Pre-feasibility studies for organic waste treatment options | 1.1.1 Conduct consultations with government entities, MERCA representatives, and private sector players, ensuring equal participation of women and men, to define treatment options. | PA-24-003/1.1.1 | PA-24-003/1.1.1 Conduct consultations with government entities, MERCA representatives, and private sector players, ensuring equal participation of women and men, to define treatment options. | PA-24-003/1.1 Pre-feasibility studies for organic waste treatment options | Activity | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 1.1 | Pre-feasibility studies for organic waste treatment options | Pre-feasibility studies for organic waste treatment options conducted in Panama City. These studies will evaluate the technical and economic feasibility of potential treatment technologies/solutions, such as composting, anaerobic digestion, and other technologies to manage organic waste effectively. The goal is to identify the most viable treatment methods that support waste diversion, reduce methane emissions, and promote circular economies. The studies will provide critical data and analysis on costs, environmental benefits, and operational feasibility, laying the groundwork for informed decision-making and future investments in sustainable organic waste management infrastructure, ensuring alignment with national policies and international commitments. | 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Number of plans, policies, laws, or regulations drafted or updated | 1 | 1 pre-feasibility study report developed. | UNDP | Panama | National and local governments responsible for waste management. | Provide data to guide government decisions on sustainable and effective organic waste management solutions. | Research or study | 11/1/2025 12:00:00 AM | 12/1/2025 | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | 1.1 Pre-feasibility studies for organic waste treatment options | Output 1.1 Pre-feasibility studies for organic waste treatment options | Outcome 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | PA-24-003/1.1 | PA-24-003/1.1 Pre-feasibility studies for organic waste treatment options | Output | PA-24-003/1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 1 | The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | The project’s outputs will identify and develop innovative and practical treatment options and solutions for managing organic waste, generating critical data on decentralized infrastructure needs, such as composting plants, biodigesters, food and material recovery, and waste reduction technologies. These solutions will integrate circular economy principles, prioritize locally based consultants with local language capabilities, and actively engage the private sector through targeted knowledge exchange initiatives. By leveraging activities such as pre-feasibility studies, infrastructure estimates, and actionable recommendations, the project will equip the government with comprehensive knowledge to make informed decisions on effective and sustainable waste management solutions. This enhanced knowledge is expected to contribute to significant environmental, economic, and social benefits, including reduced food waste, methane emissions, and support for national and international sustainability goals. The projec... | Number of government entities with a demonstrated improved capacity for SLCP action | 4 | 4 government entities with improved capacity for SLCP action. | 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Outcome 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | PA-24-003/1. | PA-24-003/1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Outcome | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003 | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | UNDP () | UNDP ()
1.1.2 Evaluate technical and economic feasibility for technologies like composting and anaerobic digestion, including an analysis of how these benefit women-led businesses and communities. | Staff and Other Personnel Costs | 1.1.2-1 | Waste Management and Infrastructure Consultant | UNDP | Consultant hired for pre-feasibility analysis | CCAC | 1 | Consultant-month | 20000 | 20000 | 20000 | null | null | Yes. | 1/1/2002 | Expenditure 1.1.2-1 Waste Management and Infrastructure Consultant | Activity 1.1.2 Evaluate technical and economic feasibility for technologies like composting and anaerobic digestion, including an analysis of how these benefit women-led businesses and communities. | UNDP () | PA-24-003/1.1.2-1 | PA-24-003/1.1.2-1 Waste Management and Infrastructure Consultant | PA-24-003/1.1.2 Evaluate technical and economic feasibility for technologies like composting and anaerobic digestion, including an analysis of how these benefit women-led businesses and communities. | Expenditure | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 1.1 Pre-feasibility studies for organic waste treatment options | 1.1.2 | 1.1.2 Evaluate technical and economic feasibility for technologies like composting and anaerobic digestion, including an analysis of how these benefit women-led businesses and communities. | This activity focuses on conducting technical and economic feasibility studies for organic waste treatment technologies. The evaluation will assess factors such as cost efficiency, scalability, and environmental impact. Special attention will be given to understanding how these technologies can create opportunities for women-led businesses and promote inclusive economic benefits in local communities. | Research, data collection, and/or report writing | null | null | UNDP | Panama | Panama | null | 9/1/2025 | 12/1/2025 | Research or study | null | null | null | 1.1 | Activity 1.1.2 Evaluate technical and economic feasibility for technologies like composting and anaerobic digestion, including an analysis of how these benefit women-led businesses and communities. | Output 1.1 Pre-feasibility studies for organic waste treatment options | 1.1.2 Evaluate technical and economic feasibility for technologies like composting and anaerobic digestion, including an analysis of how these benefit women-led businesses and communities. | PA-24-003/1.1.2 | PA-24-003/1.1.2 Evaluate technical and economic feasibility for technologies like composting and anaerobic digestion, including an analysis of how these benefit women-led businesses and communities. | PA-24-003/1.1 Pre-feasibility studies for organic waste treatment options | Activity | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 1.1 | Pre-feasibility studies for organic waste treatment options | Pre-feasibility studies for organic waste treatment options conducted in Panama City. These studies will evaluate the technical and economic feasibility of potential treatment technologies/solutions, such as composting, anaerobic digestion, and other technologies to manage organic waste effectively. The goal is to identify the most viable treatment methods that support waste diversion, reduce methane emissions, and promote circular economies. The studies will provide critical data and analysis on costs, environmental benefits, and operational feasibility, laying the groundwork for informed decision-making and future investments in sustainable organic waste management infrastructure, ensuring alignment with national policies and international commitments. | 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Number of plans, policies, laws, or regulations drafted or updated | 1 | 1 pre-feasibility study report developed. | UNDP | Panama | National and local governments responsible for waste management. | Provide data to guide government decisions on sustainable and effective organic waste management solutions. | Research or study | 11/1/2025 12:00:00 AM | 12/1/2025 | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | 1.1 Pre-feasibility studies for organic waste treatment options | Output 1.1 Pre-feasibility studies for organic waste treatment options | Outcome 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | PA-24-003/1.1 | PA-24-003/1.1 Pre-feasibility studies for organic waste treatment options | Output | PA-24-003/1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 1 | The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | The project’s outputs will identify and develop innovative and practical treatment options and solutions for managing organic waste, generating critical data on decentralized infrastructure needs, such as composting plants, biodigesters, food and material recovery, and waste reduction technologies. These solutions will integrate circular economy principles, prioritize locally based consultants with local language capabilities, and actively engage the private sector through targeted knowledge exchange initiatives. By leveraging activities such as pre-feasibility studies, infrastructure estimates, and actionable recommendations, the project will equip the government with comprehensive knowledge to make informed decisions on effective and sustainable waste management solutions. This enhanced knowledge is expected to contribute to significant environmental, economic, and social benefits, including reduced food waste, methane emissions, and support for national and international sustainability goals. The projec... | Number of government entities with a demonstrated improved capacity for SLCP action | 4 | 4 government entities with improved capacity for SLCP action. | 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Outcome 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | PA-24-003/1. | PA-24-003/1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Outcome | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003 | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | UNDP () | UNDP ()
1.2.1 Map existing and potential decentralized infrastructure for waste management, engaging municipalities and local organizations to provide on-ground insights. | Staff and Other Personnel Costs | 1.2.1-1 | Field visits for data collection | UNDP | Consultant hired for mapping infrastructure | CCAC | 1 | Consultant-month | 10000 | 10000 | null | 10000 | null | Yes. | 1/2/2001 | Expenditure 1.2.1-1 Field visits for data collection | Activity 1.2.1 Map existing and potential decentralized infrastructure for waste management, engaging municipalities and local organizations to provide on-ground insights. | UNDP () | PA-24-003/1.2.1-1 | PA-24-003/1.2.1-1 Field visits for data collection | PA-24-003/1.2.1 Map existing and potential decentralized infrastructure for waste management, engaging municipalities and local organizations to provide on-ground insights. | Expenditure | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 1.2 Estimates of decentralized infraestructure supporting diverted organic waste | 1.2.1 | 1.2.1 Map existing and potential decentralized infrastructure for waste management, engaging municipalities and local organizations to provide on-ground insights. | This activity involves mapping current and potential decentralized infrastructure for organic waste management, such as composting plants, biodigesters, and material recovery facilities. Municipal governments and local organizations will be actively engaged to ensure accurate data collection and context-specific recommendations. The mapping process will also consider socio-economic and environmental factors to identify priority areas for infrastructure development. | Research, data collection, and/or report writing | null | null | UNDP | Panama | Panama | null | 6/1/2025 | 9/1/2025 | Research or study | null | null | null | 1.2 | Activity 1.2.1 Map existing and potential decentralized infrastructure for waste management, engaging municipalities and local organizations to provide on-ground insights. | Output 1.2 Estimates of decentralized infraestructure supporting diverted organic waste | 1.2.1 Map existing and potential decentralized infrastructure for waste management, engaging municipalities and local organizations to provide on-ground insights. | PA-24-003/1.2.1 | PA-24-003/1.2.1 Map existing and potential decentralized infrastructure for waste management, engaging municipalities and local organizations to provide on-ground insights. | PA-24-003/1.2 Estimates of decentralized infraestructure supporting diverted organic waste | Activity | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 1.2 | Estimates of decentralized infraestructure supporting diverted organic waste | Estimates of decentralized infrastructure supporting organic waste diversion, including materials separation and recovery centers, black soldier fly infrastructure, and compositing plants. These systems will promote a circular economy by processing organic waste closer to its source, reducing transportation costs and emissions. The estimates will determine the scale, location, capacity and investment requirements for these facilities, providing a strategic roadmap for developing an efficient, sustainable waste management network. This will enable the government to plan effectively for organic waste management. | 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Number of SLCP assessments, emissions inventories, and other emissions datasets produced | 4 | 4 SLCP assessments, emissions inventories, or other emissions datasets produced. | UNDP | Panama | Municipalities and local governments. | Guide investment in infrastructure to divert organic waste sustainably. | Research or study | 11/1/2025 12:00:00 AM | 12/1/2025 | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | 1.2 Estimates of decentralized infraestructure supporting diverted organic waste | Output 1.2 Estimates of decentralized infraestructure supporting diverted organic waste | Outcome 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | PA-24-003/1.2 | PA-24-003/1.2 Estimates of decentralized infraestructure supporting diverted organic waste | Output | PA-24-003/1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 1 | The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | The project’s outputs will identify and develop innovative and practical treatment options and solutions for managing organic waste, generating critical data on decentralized infrastructure needs, such as composting plants, biodigesters, food and material recovery, and waste reduction technologies. These solutions will integrate circular economy principles, prioritize locally based consultants with local language capabilities, and actively engage the private sector through targeted knowledge exchange initiatives. By leveraging activities such as pre-feasibility studies, infrastructure estimates, and actionable recommendations, the project will equip the government with comprehensive knowledge to make informed decisions on effective and sustainable waste management solutions. This enhanced knowledge is expected to contribute to significant environmental, economic, and social benefits, including reduced food waste, methane emissions, and support for national and international sustainability goals. The projec... | Number of government entities with a demonstrated improved capacity for SLCP action | 4 | 4 government entities with improved capacity for SLCP action. | 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Outcome 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | PA-24-003/1. | PA-24-003/1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Outcome | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003 | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | UNDP () | UNDP ()
1.2.2 Conduct site visits and surveys, collecting gender-disaggregated data to ensure proposed infrastructure meets the needs of both genders. | Travel | 1.2.2-1 | Waste Management and Infrastructure Consultant | UNDP | site visits and surveys | CCAC | 4.5 | Trips | 400 | 1800 | 1800 | null | null | Yes. | 1/2/2002 | Expenditure 1.2.2-1 Waste Management and Infrastructure Consultant | Activity 1.2.2 Conduct site visits and surveys, collecting gender-disaggregated data to ensure proposed infrastructure meets the needs of both genders. | UNDP () | PA-24-003/1.2.2-1 | PA-24-003/1.2.2-1 Waste Management and Infrastructure Consultant | PA-24-003/1.2.2 Conduct site visits and surveys, collecting gender-disaggregated data to ensure proposed infrastructure meets the needs of both genders. | Expenditure | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 1.2 Estimates of decentralized infraestructure supporting diverted organic waste | 1.2.2 | 1.2.2 Conduct site visits and surveys, collecting gender-disaggregated data to ensure proposed infrastructure meets the needs of both genders. | This activity will include field visits and stakeholder surveys to collect data on waste management infrastructure needs. Surveys will include gender-disaggregated data to ensure that proposed infrastructure supports both men and women, particularly those in waste-related informal sectors. The findings will inform inclusive and equitable infrastructure planning. | Research, data collection, and/or report writing | null | null | UNDP | Panama | Panama | null | 9/1/2025 | 12/1/2025 | Research or study | null | null | null | 1.2 | Activity 1.2.2 Conduct site visits and surveys, collecting gender-disaggregated data to ensure proposed infrastructure meets the needs of both genders. | Output 1.2 Estimates of decentralized infraestructure supporting diverted organic waste | 1.2.2 Conduct site visits and surveys, collecting gender-disaggregated data to ensure proposed infrastructure meets the needs of both genders. | PA-24-003/1.2.2 | PA-24-003/1.2.2 Conduct site visits and surveys, collecting gender-disaggregated data to ensure proposed infrastructure meets the needs of both genders. | PA-24-003/1.2 Estimates of decentralized infraestructure supporting diverted organic waste | Activity | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 1.2 | Estimates of decentralized infraestructure supporting diverted organic waste | Estimates of decentralized infrastructure supporting organic waste diversion, including materials separation and recovery centers, black soldier fly infrastructure, and compositing plants. These systems will promote a circular economy by processing organic waste closer to its source, reducing transportation costs and emissions. The estimates will determine the scale, location, capacity and investment requirements for these facilities, providing a strategic roadmap for developing an efficient, sustainable waste management network. This will enable the government to plan effectively for organic waste management. | 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Number of SLCP assessments, emissions inventories, and other emissions datasets produced | 4 | 4 SLCP assessments, emissions inventories, or other emissions datasets produced. | UNDP | Panama | Municipalities and local governments. | Guide investment in infrastructure to divert organic waste sustainably. | Research or study | 11/1/2025 12:00:00 AM | 12/1/2025 | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | 1.2 Estimates of decentralized infraestructure supporting diverted organic waste | Output 1.2 Estimates of decentralized infraestructure supporting diverted organic waste | Outcome 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | PA-24-003/1.2 | PA-24-003/1.2 Estimates of decentralized infraestructure supporting diverted organic waste | Output | PA-24-003/1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 1 | The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | The project’s outputs will identify and develop innovative and practical treatment options and solutions for managing organic waste, generating critical data on decentralized infrastructure needs, such as composting plants, biodigesters, food and material recovery, and waste reduction technologies. These solutions will integrate circular economy principles, prioritize locally based consultants with local language capabilities, and actively engage the private sector through targeted knowledge exchange initiatives. By leveraging activities such as pre-feasibility studies, infrastructure estimates, and actionable recommendations, the project will equip the government with comprehensive knowledge to make informed decisions on effective and sustainable waste management solutions. This enhanced knowledge is expected to contribute to significant environmental, economic, and social benefits, including reduced food waste, methane emissions, and support for national and international sustainability goals. The projec... | Number of government entities with a demonstrated improved capacity for SLCP action | 4 | 4 government entities with improved capacity for SLCP action. | 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Outcome 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | PA-24-003/1. | PA-24-003/1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Outcome | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003 | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | UNDP () | UNDP ()
1.2.3 Develop cost-benefit analyses, incorporating feedback from diverse stakeholders through an online webinar. | Staff and Other Personnel Costs | 1.2.3-1 | Waste Management and Infrastructure Consultant | UNDP | Prepare a report | CCAC | 1 | Consultant-month | 5000 | 5000 | null | 5000 | null | Yes. | 1/2/2003 | Expenditure 1.2.3-1 Waste Management and Infrastructure Consultant | Activity 1.2.3 Develop cost-benefit analyses, incorporating feedback from diverse stakeholders through an online webinar. | UNDP () | PA-24-003/1.2.3-1 | PA-24-003/1.2.3-1 Waste Management and Infrastructure Consultant | PA-24-003/1.2.3 Develop cost-benefit analyses, incorporating feedback from diverse stakeholders through an online webinar. | Expenditure | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 1.2 Estimates of decentralized infraestructure supporting diverted organic waste | 1.2.3 | 1.2.3 Develop cost-benefit analyses, incorporating feedback from diverse stakeholders through an online webinar. | This activity will involve conducting cost-benefit analyses for proposed decentralized infrastructure options, such as composting and biodigesters. Stakeholders, including government officials, NGOs, and private sector representatives, will provide feedback through an interactive online webinar. The analysis will highlight economic, environmental, and social benefits, emphasizing SLCP mitigation and inclusion of marginalized groups. | Research, data collection, and/or report writing | null | null | UNDP | Panama | Panama | null | 12/1/2025 | 3/1/2026 | Research or study | null | null | null | 1.2 | Activity 1.2.3 Develop cost-benefit analyses, incorporating feedback from diverse stakeholders through an online webinar. | Output 1.2 Estimates of decentralized infraestructure supporting diverted organic waste | 1.2.3 Develop cost-benefit analyses, incorporating feedback from diverse stakeholders through an online webinar. | PA-24-003/1.2.3 | PA-24-003/1.2.3 Develop cost-benefit analyses, incorporating feedback from diverse stakeholders through an online webinar. | PA-24-003/1.2 Estimates of decentralized infraestructure supporting diverted organic waste | Activity | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 1.2 | Estimates of decentralized infraestructure supporting diverted organic waste | Estimates of decentralized infrastructure supporting organic waste diversion, including materials separation and recovery centers, black soldier fly infrastructure, and compositing plants. These systems will promote a circular economy by processing organic waste closer to its source, reducing transportation costs and emissions. The estimates will determine the scale, location, capacity and investment requirements for these facilities, providing a strategic roadmap for developing an efficient, sustainable waste management network. This will enable the government to plan effectively for organic waste management. | 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Number of SLCP assessments, emissions inventories, and other emissions datasets produced | 4 | 4 SLCP assessments, emissions inventories, or other emissions datasets produced. | UNDP | Panama | Municipalities and local governments. | Guide investment in infrastructure to divert organic waste sustainably. | Research or study | 11/1/2025 12:00:00 AM | 12/1/2025 | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | 1.2 Estimates of decentralized infraestructure supporting diverted organic waste | Output 1.2 Estimates of decentralized infraestructure supporting diverted organic waste | Outcome 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | PA-24-003/1.2 | PA-24-003/1.2 Estimates of decentralized infraestructure supporting diverted organic waste | Output | PA-24-003/1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 1 | The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | The project’s outputs will identify and develop innovative and practical treatment options and solutions for managing organic waste, generating critical data on decentralized infrastructure needs, such as composting plants, biodigesters, food and material recovery, and waste reduction technologies. These solutions will integrate circular economy principles, prioritize locally based consultants with local language capabilities, and actively engage the private sector through targeted knowledge exchange initiatives. By leveraging activities such as pre-feasibility studies, infrastructure estimates, and actionable recommendations, the project will equip the government with comprehensive knowledge to make informed decisions on effective and sustainable waste management solutions. This enhanced knowledge is expected to contribute to significant environmental, economic, and social benefits, including reduced food waste, methane emissions, and support for national and international sustainability goals. The projec... | Number of government entities with a demonstrated improved capacity for SLCP action | 4 | 4 government entities with improved capacity for SLCP action. | 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Outcome 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | PA-24-003/1. | PA-24-003/1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Outcome | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003 | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | UNDP () | UNDP ()
1.3.1 Develop a list of complementary technologies and infrastructure to enhance organic waste management, consulting stakeholders such as circular economy specialists and private sector innovators. | Staff and Other Personnel Costs | 1.3.1-1 | Training workshops, seminars and meetings | UNDP | null | CCAC | 1 | Consultant-month | 20000 | 20000 | null | 20000 | null | Yes. | 1/3/2001 | Expenditure 1.3.1-1 Training workshops, seminars and meetings | Activity 1.3.1 Develop a list of complementary technologies and infrastructure to enhance organic waste management, consulting stakeholders such as circular economy specialists and private sector innovators. | UNDP () | PA-24-003/1.3.1-1 | PA-24-003/1.3.1-1 Training workshops, seminars and meetings | PA-24-003/1.3.1 Develop a list of complementary technologies and infrastructure to enhance organic waste management, consulting stakeholders such as circular economy specialists and private sector innovators. | Expenditure | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 1.3 Recommendations for alternative/ complementary infraestrucutre | 1.3.1 | 1.3.1 Develop a list of complementary technologies and infrastructure to enhance organic waste management, consulting stakeholders such as circular economy specialists and private sector innovators. | This activity will identify and prioritize complementary technologies and infrastructure to improve the efficiency of organic waste management systems. Circular economy specialists and private sector innovators will be consulted to ensure the recommendations align with sustainable practices and promote innovation. Examples of technologies include biogas recovery systems and advanced composting units. | Research, data collection, and/or report writing | null | null | UNDP | Panama | Panama | null | 3/1/2026 | 6/1/2026 | Meeting report | null | null | null | 1.3 | Activity 1.3.1 Develop a list of complementary technologies and infrastructure to enhance organic waste management, consulting stakeholders such as circular economy specialists and private sector innovators. | Output 1.3 Recommendations for alternative/ complementary infraestrucutre | 1.3.1 Develop a list of complementary technologies and infrastructure to enhance organic waste management, consulting stakeholders such as circular economy specialists and private sector innovators. | PA-24-003/1.3.1 | PA-24-003/1.3.1 Develop a list of complementary technologies and infrastructure to enhance organic waste management, consulting stakeholders such as circular economy specialists and private sector innovators. | PA-24-003/1.3 Recommendations for alternative/ complementary infraestrucutre | Activity | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 1.3 | Recommendations for alternative/ complementary infraestrucutre | Recommendations for alternative and complementary infrastructure to support organic waste diversion and fosters circular economies. The proposed infraestructure aims to enhance existing waste management systems, such as advanced compositing technologies, anaerobic digestion, and resource recovery facilities. These recommendation will serve as a blueprint for the government to integreate into its organic waste management strategy, with focus on creating value to the organic waste, lowers emissions, reducing landfill dependency, and promoting environmental, economic and social benefits, achieve the goals establishd in the NDC's and roadmap for the Mitigation of SLCPs in Panama. The findings will guide future investements and policies for an integrated waste managemente approach | 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Number of SLCP knowledge resources or tools produced | 1 | 1 SLCP knowledge resource or tool produced. | UNDP | Panama | National and local governments. | Provide actionable recommendations to optimize waste treatment systems. | Research or study | 5/1/2026 12:00:00 AM | 9/1/2026 | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | 1.3 Recommendations for alternative/ complementary infraestrucutre | Output 1.3 Recommendations for alternative/ complementary infraestrucutre | Outcome 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | PA-24-003/1.3 | PA-24-003/1.3 Recommendations for alternative/ complementary infraestrucutre | Output | PA-24-003/1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 1 | The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | The project’s outputs will identify and develop innovative and practical treatment options and solutions for managing organic waste, generating critical data on decentralized infrastructure needs, such as composting plants, biodigesters, food and material recovery, and waste reduction technologies. These solutions will integrate circular economy principles, prioritize locally based consultants with local language capabilities, and actively engage the private sector through targeted knowledge exchange initiatives. By leveraging activities such as pre-feasibility studies, infrastructure estimates, and actionable recommendations, the project will equip the government with comprehensive knowledge to make informed decisions on effective and sustainable waste management solutions. This enhanced knowledge is expected to contribute to significant environmental, economic, and social benefits, including reduced food waste, methane emissions, and support for national and international sustainability goals. The projec... | Number of government entities with a demonstrated improved capacity for SLCP action | 4 | 4 government entities with improved capacity for SLCP action. | 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Outcome 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | PA-24-003/1. | PA-24-003/1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Outcome | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003 | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | UNDP () | UNDP ()
1.3.2 Host a gender-balanced expert panel to validate recommendations, prioritizing options that create employment for women. | Contractual Services | 1.3.2-1 | Infographic design | UNDP | null | CCAC | 1 | Workshop | 1000 | 1000 | 1000 | null | null | Yes. | 1/3/2002 | Expenditure 1.3.2-1 Infographic design | Activity 1.3.2 Host a gender-balanced expert panel to validate recommendations, prioritizing options that create employment for women. | UNDP () | PA-24-003/1.3.2-1 | PA-24-003/1.3.2-1 Infographic design | PA-24-003/1.3.2 Host a gender-balanced expert panel to validate recommendations, prioritizing options that create employment for women. | Expenditure | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 1.3 Recommendations for alternative/ complementary infraestrucutre | 1.3.2 | 1.3.2 Host a gender-balanced expert panel to validate recommendations, prioritizing options that create employment for women. | A panel of experts, ensuring gender balance, will review and validate the recommendations for complementary technologies and infrastructure. Discussions will focus on prioritizing solutions that foster economic opportunities for women, particularly in waste collection and processing. The validated recommendations will guide subsequent project activities. | Organising, holding, or participating in a meeting or event | null | null | UNDP | Panama | Panama | null | 3/1/2026 | 6/1/2026 | null | null | null | null | 1.3 | Activity 1.3.2 Host a gender-balanced expert panel to validate recommendations, prioritizing options that create employment for women. | Output 1.3 Recommendations for alternative/ complementary infraestrucutre | 1.3.2 Host a gender-balanced expert panel to validate recommendations, prioritizing options that create employment for women. | PA-24-003/1.3.2 | PA-24-003/1.3.2 Host a gender-balanced expert panel to validate recommendations, prioritizing options that create employment for women. | PA-24-003/1.3 Recommendations for alternative/ complementary infraestrucutre | Activity | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 1.3 | Recommendations for alternative/ complementary infraestrucutre | Recommendations for alternative and complementary infrastructure to support organic waste diversion and fosters circular economies. The proposed infraestructure aims to enhance existing waste management systems, such as advanced compositing technologies, anaerobic digestion, and resource recovery facilities. These recommendation will serve as a blueprint for the government to integreate into its organic waste management strategy, with focus on creating value to the organic waste, lowers emissions, reducing landfill dependency, and promoting environmental, economic and social benefits, achieve the goals establishd in the NDC's and roadmap for the Mitigation of SLCPs in Panama. The findings will guide future investements and policies for an integrated waste managemente approach | 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Number of SLCP knowledge resources or tools produced | 1 | 1 SLCP knowledge resource or tool produced. | UNDP | Panama | National and local governments. | Provide actionable recommendations to optimize waste treatment systems. | Research or study | 5/1/2026 12:00:00 AM | 9/1/2026 | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | 1.3 Recommendations for alternative/ complementary infraestrucutre | Output 1.3 Recommendations for alternative/ complementary infraestrucutre | Outcome 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | PA-24-003/1.3 | PA-24-003/1.3 Recommendations for alternative/ complementary infraestrucutre | Output | PA-24-003/1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 1 | The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | The project’s outputs will identify and develop innovative and practical treatment options and solutions for managing organic waste, generating critical data on decentralized infrastructure needs, such as composting plants, biodigesters, food and material recovery, and waste reduction technologies. These solutions will integrate circular economy principles, prioritize locally based consultants with local language capabilities, and actively engage the private sector through targeted knowledge exchange initiatives. By leveraging activities such as pre-feasibility studies, infrastructure estimates, and actionable recommendations, the project will equip the government with comprehensive knowledge to make informed decisions on effective and sustainable waste management solutions. This enhanced knowledge is expected to contribute to significant environmental, economic, and social benefits, including reduced food waste, methane emissions, and support for national and international sustainability goals. The projec... | Number of government entities with a demonstrated improved capacity for SLCP action | 4 | 4 government entities with improved capacity for SLCP action. | 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Outcome 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | PA-24-003/1. | PA-24-003/1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Outcome | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003 | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | UNDP () | UNDP ()
1.3.3 Prepare an accessible visual infographic summarizing key recommendations for public dissemination. | Contractual Services | 1.3.3-1 | Waste Management and Infrastructure Consultant | UNDP | null | CCAC | 1 | Infographic | 2000 | 2000 | null | 2000 | null | Yes. | 1/3/2003 | Expenditure 1.3.3-1 Waste Management and Infrastructure Consultant | Activity 1.3.3 Prepare an accessible visual infographic summarizing key recommendations for public dissemination. | UNDP () | PA-24-003/1.3.3-1 | PA-24-003/1.3.3-1 Waste Management and Infrastructure Consultant | PA-24-003/1.3.3 Prepare an accessible visual infographic summarizing key recommendations for public dissemination. | Expenditure | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 1.3 Recommendations for alternative/ complementary infraestrucutre | 1.3.3 | 1.3.3 Prepare an accessible visual infographic summarizing key recommendations for public dissemination. | This activity will focus on creating an infographic to visually communicate the key recommendations from the expert panel to a broad audience. The infographic will highlight the technologies and infrastructure proposed, their environmental and social benefits, and their alignment with SLCP mitigation goals. The design will prioritize accessibility, ensuring it can be understood by diverse stakeholders, including policymakers, community groups, and private sector actors. | Producing and distributing communications materials | null | null | UNDP | Panama | Panama | null | 6/1/2026 | 9/1/2026 | Research or study | null | null | null | 1.3 | Activity 1.3.3 Prepare an accessible visual infographic summarizing key recommendations for public dissemination. | Output 1.3 Recommendations for alternative/ complementary infraestrucutre | 1.3.3 Prepare an accessible visual infographic summarizing key recommendations for public dissemination. | PA-24-003/1.3.3 | PA-24-003/1.3.3 Prepare an accessible visual infographic summarizing key recommendations for public dissemination. | PA-24-003/1.3 Recommendations for alternative/ complementary infraestrucutre | Activity | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 1.3 | Recommendations for alternative/ complementary infraestrucutre | Recommendations for alternative and complementary infrastructure to support organic waste diversion and fosters circular economies. The proposed infraestructure aims to enhance existing waste management systems, such as advanced compositing technologies, anaerobic digestion, and resource recovery facilities. These recommendation will serve as a blueprint for the government to integreate into its organic waste management strategy, with focus on creating value to the organic waste, lowers emissions, reducing landfill dependency, and promoting environmental, economic and social benefits, achieve the goals establishd in the NDC's and roadmap for the Mitigation of SLCPs in Panama. The findings will guide future investements and policies for an integrated waste managemente approach | 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Number of SLCP knowledge resources or tools produced | 1 | 1 SLCP knowledge resource or tool produced. | UNDP | Panama | National and local governments. | Provide actionable recommendations to optimize waste treatment systems. | Research or study | 5/1/2026 12:00:00 AM | 9/1/2026 | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | 1.3 Recommendations for alternative/ complementary infraestrucutre | Output 1.3 Recommendations for alternative/ complementary infraestrucutre | Outcome 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | PA-24-003/1.3 | PA-24-003/1.3 Recommendations for alternative/ complementary infraestrucutre | Output | PA-24-003/1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 1 | The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | The project’s outputs will identify and develop innovative and practical treatment options and solutions for managing organic waste, generating critical data on decentralized infrastructure needs, such as composting plants, biodigesters, food and material recovery, and waste reduction technologies. These solutions will integrate circular economy principles, prioritize locally based consultants with local language capabilities, and actively engage the private sector through targeted knowledge exchange initiatives. By leveraging activities such as pre-feasibility studies, infrastructure estimates, and actionable recommendations, the project will equip the government with comprehensive knowledge to make informed decisions on effective and sustainable waste management solutions. This enhanced knowledge is expected to contribute to significant environmental, economic, and social benefits, including reduced food waste, methane emissions, and support for national and international sustainability goals. The projec... | Number of government entities with a demonstrated improved capacity for SLCP action | 4 | 4 government entities with improved capacity for SLCP action. | 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Outcome 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | PA-24-003/1. | PA-24-003/1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Outcome | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003 | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | UNDP () | UNDP ()
1.4.1 Conduct an in-depth evaluation of essential infrastructure for organic waste management (e.g., composting plants, biodigesters) | Staff and Other Personnel Costs | 1.4.1-1 | Waste Management and Infrastructure Consultant | UNDP | null | CCAC | 1 | evaluation. | 10000 | 10000 | null | 10000 | null | Yes. | 1/4/2001 | Expenditure 1.4.1-1 Waste Management and Infrastructure Consultant | Activity 1.4.1 Conduct an in-depth evaluation of essential infrastructure for organic waste management (e.g., composting plants, biodigesters) | UNDP () | PA-24-003/1.4.1-1 | PA-24-003/1.4.1-1 Waste Management and Infrastructure Consultant | PA-24-003/1.4.1 Conduct an in-depth evaluation of essential infrastructure for organic waste management (e.g., composting plants, biodigesters) | Expenditure | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 1.4 Report indentifying necessary infraestructure and investment to support organic waste management | 1.4.1 | 1.4.1 Conduct an in-depth evaluation of essential infrastructure for organic waste management (e.g., composting plants, biodigesters) | This activity will evaluate the critical infrastructure required for effective organic waste management in Panama, focusing on facilities such as composting plants and biodigesters. The evaluation will include cost estimates for infrastructure development, operational considerations, and potential funding sources. Special attention will be paid to how these facilities can generate employment opportunities for women and marginalized groups. This in-depth assessment will also examine environmental and economic impacts to support informed decision-making. | Research, data collection, and/or report writing | null | null | UNDP | Panama | Panama | null | 9/1/2026 | 12/1/2026 | Meeting report | null | null | null | 1.4 | Activity 1.4.1 Conduct an in-depth evaluation of essential infrastructure for organic waste management (e.g., composting plants, biodigesters) | Output 1.4 Report indentifying necessary infraestructure and investment to support organic waste management | 1.4.1 Conduct an in-depth evaluation of essential infrastructure for organic waste management (e.g., composting plants, biodigesters) | PA-24-003/1.4.1 | PA-24-003/1.4.1 Conduct an in-depth evaluation of essential infrastructure for organic waste management (e.g., composting plants, biodigesters) | PA-24-003/1.4 Report indentifying necessary infraestructure and investment to support organic waste management | Activity | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 1.4 | Report indentifying necessary infraestructure and investment to support organic waste management | A report identifying necessary infrastructure and investment to support organic waste management (recovery of organic waste, production of biofertilizer and energy, savings by avoiding waste, redistribution of food that otherwise would be discarded to people in need). The report will cover key areas such as the recovery of organic waste, the production of biofertilizers and renewable enerty, and economic savings from waste reduction. It will also highlight the potential for redistributing surplus food to people in need, preventing it from being discarded. By identifying these necessary components, the report will serve as a strategic roadmap for decision-makers to prioritize investements and implementing sustainable solutions for organic waste management. | 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Number of plans, policies, laws, or regulations drafted or updated | 1 | 1 plan, policy, law, or regulation drafted or updated. | UNDP | Panama | National and local governments, investors. | Inform stakeholders about required investments and potential returns in waste management infrastructure. | Research or study | 8/1/2026 12:00:00 AM | 12/1/2026 | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | 1.4 Report indentifying necessary infraestructure and investment to support organic waste management | Output 1.4 Report indentifying necessary infraestructure and investment to support organic waste management | Outcome 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | PA-24-003/1.4 | PA-24-003/1.4 Report indentifying necessary infraestructure and investment to support organic waste management | Output | PA-24-003/1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 1 | The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | The project’s outputs will identify and develop innovative and practical treatment options and solutions for managing organic waste, generating critical data on decentralized infrastructure needs, such as composting plants, biodigesters, food and material recovery, and waste reduction technologies. These solutions will integrate circular economy principles, prioritize locally based consultants with local language capabilities, and actively engage the private sector through targeted knowledge exchange initiatives. By leveraging activities such as pre-feasibility studies, infrastructure estimates, and actionable recommendations, the project will equip the government with comprehensive knowledge to make informed decisions on effective and sustainable waste management solutions. This enhanced knowledge is expected to contribute to significant environmental, economic, and social benefits, including reduced food waste, methane emissions, and support for national and international sustainability goals. The projec... | Number of government entities with a demonstrated improved capacity for SLCP action | 4 | 4 government entities with improved capacity for SLCP action. | 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Outcome 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | PA-24-003/1. | PA-24-003/1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Outcome | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003 | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | UNDP () | UNDP ()
1.4.2 Compile findings into a comprehensive report highlighting investment opportunities, environmental and economic benefits, and potential social impacts. Share the report through workshops and online platforms targeting public and private stakeholders. | Staff and Other Personnel Costs | 1.4.2-1 | Support innovation challenge | UNDP | null | CCAC | 1 | Final report | 5000 | 5000 | null | 5000 | null | Yes. | 1/4/2002 | Expenditure 1.4.2-1 Support innovation challenge | Activity 1.4.2 Compile findings into a comprehensive report highlighting investment opportunities, environmental and economic benefits, and potential social impacts. Share the report through workshops and online platforms targeting public and private stakeholders. | UNDP () | PA-24-003/1.4.2-1 | PA-24-003/1.4.2-1 Support innovation challenge | PA-24-003/1.4.2 Compile findings into a comprehensive report highlighting investment opportunities, environmental and economic benefits, and potential social impacts. Share the report through workshops and online platforms targeting public and private stakeholders. | Expenditure | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 1.4 Report indentifying necessary infraestructure and investment to support organic waste management | 1.4.2 | 1.4.2 Compile findings into a comprehensive report highlighting investment opportunities, environmental and economic benefits, and potential social impacts. Share the report through workshops and online platforms targeting public and private stakeholders. | This activity will consolidate the findings of the infrastructure evaluation into a comprehensive report that highlights key investment opportunities and the potential benefits of organic waste management infrastructure. The report will outline environmental, economic, and social impacts, emphasizing gender-inclusive opportunities such as job creation for women. The findings will be disseminated through workshops with stakeholders and made available on online platforms to ensure accessibility. | Policy, project, or tool design | null | null | UNDP | Panama | Panama | null | 9/1/2026 | 12/1/2026 | Meeting report | null | null | null | 1.4 | Activity 1.4.2 Compile findings into a comprehensive report highlighting investment opportunities, environmental and economic benefits, and potential social impacts. Share the report through workshops and online platforms targeting public and private stakeholders. | Output 1.4 Report indentifying necessary infraestructure and investment to support organic waste management | 1.4.2 Compile findings into a comprehensive report highlighting investment opportunities, environmental and economic benefits, and potential social impacts. Share the report through workshops and online platforms targeting public and private stakeholders. | PA-24-003/1.4.2 | PA-24-003/1.4.2 Compile findings into a comprehensive report highlighting investment opportunities, environmental and economic benefits, and potential social impacts. Share the report through workshops and online platforms targeting public and private stakeholders. | PA-24-003/1.4 Report indentifying necessary infraestructure and investment to support organic waste management | Activity | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 1.4 | Report indentifying necessary infraestructure and investment to support organic waste management | A report identifying necessary infrastructure and investment to support organic waste management (recovery of organic waste, production of biofertilizer and energy, savings by avoiding waste, redistribution of food that otherwise would be discarded to people in need). The report will cover key areas such as the recovery of organic waste, the production of biofertilizers and renewable enerty, and economic savings from waste reduction. It will also highlight the potential for redistributing surplus food to people in need, preventing it from being discarded. By identifying these necessary components, the report will serve as a strategic roadmap for decision-makers to prioritize investements and implementing sustainable solutions for organic waste management. | 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Number of plans, policies, laws, or regulations drafted or updated | 1 | 1 plan, policy, law, or regulation drafted or updated. | UNDP | Panama | National and local governments, investors. | Inform stakeholders about required investments and potential returns in waste management infrastructure. | Research or study | 8/1/2026 12:00:00 AM | 12/1/2026 | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | 1.4 Report indentifying necessary infraestructure and investment to support organic waste management | Output 1.4 Report indentifying necessary infraestructure and investment to support organic waste management | Outcome 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | PA-24-003/1.4 | PA-24-003/1.4 Report indentifying necessary infraestructure and investment to support organic waste management | Output | PA-24-003/1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 1 | The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | The project’s outputs will identify and develop innovative and practical treatment options and solutions for managing organic waste, generating critical data on decentralized infrastructure needs, such as composting plants, biodigesters, food and material recovery, and waste reduction technologies. These solutions will integrate circular economy principles, prioritize locally based consultants with local language capabilities, and actively engage the private sector through targeted knowledge exchange initiatives. By leveraging activities such as pre-feasibility studies, infrastructure estimates, and actionable recommendations, the project will equip the government with comprehensive knowledge to make informed decisions on effective and sustainable waste management solutions. This enhanced knowledge is expected to contribute to significant environmental, economic, and social benefits, including reduced food waste, methane emissions, and support for national and international sustainability goals. The projec... | Number of government entities with a demonstrated improved capacity for SLCP action | 4 | 4 government entities with improved capacity for SLCP action. | 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Outcome 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | PA-24-003/1. | PA-24-003/1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Outcome | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003 | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | UNDP () | UNDP ()
2.1.1Identify and evaluate projects with business potential, ensuring inclusion of women-led initiatives and alignment with national goals. | Contractual Services | 2.1.1-1 | Circular Economy Specialist | UNDP | Support innovation challenge in organic waste management | CCAC | 1 | Innovation Challenge | 20000 | 20000 | null | 20000 | null | Yes. | 2/1/2001 | Expenditure 2.1.1-1 Circular Economy Specialist | Activity 2.1.1Identify and evaluate projects with business potential, ensuring inclusion of women-led initiatives and alignment with national goals. | UNDP () | PA-24-003/2.1.1-1 | PA-24-003/2.1.1-1 Circular Economy Specialist | PA-24-003/2.1.1Identify and evaluate projects with business potential, ensuring inclusion of women-led initiatives and alignment with national goals. | Expenditure | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 2.1 Identification of projects/inititives | 2.1.1 | 2.1.1Identify and evaluate projects with business potential, ensuring inclusion of women-led initiatives and alignment with national goals. | This activity will focus on identifying and evaluating 5–7 organic waste management projects that demonstrate strong business potential. The evaluation will include criteria such as alignment with national sustainability goals, economic viability, and SLCP mitigation potential. Women-led initiatives will be prioritized to ensure gender inclusion and equitable benefits. Key stakeholders, including government and private sector representatives, will provide input during the evaluation process. | Other | null | null | UNDP | Panama | Panama | null | 12/1/2025 | 6/1/2026 | Work plan | null | null | null | 2.1 | Activity 2.1.1Identify and evaluate projects with business potential, ensuring inclusion of women-led initiatives and alignment with national goals. | Output 2.1 Identification of projects/inititives | 2.1.1Identify and evaluate projects with business potential, ensuring inclusion of women-led initiatives and alignment with national goals. | PA-24-003/2.1.1 | PA-24-003/2.1.1Identify and evaluate projects with business potential, ensuring inclusion of women-led initiatives and alignment with national goals. | PA-24-003/2.1 Identification of projects/inititives | Activity | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 2.1 | Identification of projects/inititives | Identification of at least 5-7 appropriate projects/initiatives with business potential in integral organic waste management, supported by the public and private sector based on the findings of output 1.3. and will be evaluated for their potential to contribute to a circular economy. The assesment will include project descriptions, expected outcomes, involved entities, and financing strategies. By identifying these opportunities, the project aims to establish a solid foundation for future investements and actions in organic waste management. | 2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | Number of partnerships, associations, or campaigns launched to drive SLCP action | 5 | 5 Partnerships to drive SLCP action. | UNDP | Panama | Investors, public and private stakeholders. | Build a project portfolio to attract funding and investment. | Research or study, Work plan | 2/1/2026 12:00:00 AM | 6/1/2026 | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | 2.1 Identification of projects/inititives | Output 2.1 Identification of projects/inititives | Outcome 2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | PA-24-003/2.1 | PA-24-003/2.1 Identification of projects/inititives | Output | PA-24-003/2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 2 | The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | The project will create a portfolio of 5-7 initiatives and projects with demonstrated business potential, aligned with national goals, and designed to attract funding from both public and private sectors. Specific financial plans will be developed for at least three selected projects, including tailored financial tools and agreements among stakeholders, to enhance the likelihood of securing financing, scaling, and promoting sustainable solutions. The process will include the establishment of collaborative, multi-stakeholder partnerships, which are essential for co-creating comprehensive and lasting solutions. Key activities will involve delivering workshops to financial and governmental stakeholders to explore innovative financing mechanisms and develop actionable financial instruments that address the needs of the selected initiatives. The project assumes that the identified initiatives will generate significant interest from funding institutions and public and private entities, with active participation ... | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 5 | 5 action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures | 2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | Outcome 2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | PA-24-003/2. | PA-24-003/2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Outcome | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003 | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | UNDP () | UNDP ()
2.1.2Develop a portfolio of selected projects with detailed descriptions and expected outcomes, highlighting gender-specific benefits. | Staff and Other Personnel Costs | 2.1.2-1 | Circular Economy Specialist | UNDP | Specialist hired to integrate circular economy practices | CCAC | 1 | Consultant | 15000 | 15000 | null | 15000 | null | Yes. | 2/1/2002 | Expenditure 2.1.2-1 Circular Economy Specialist | Activity 2.1.2Develop a portfolio of selected projects with detailed descriptions and expected outcomes, highlighting gender-specific benefits. | UNDP () | PA-24-003/2.1.2-1 | PA-24-003/2.1.2-1 Circular Economy Specialist | PA-24-003/2.1.2Develop a portfolio of selected projects with detailed descriptions and expected outcomes, highlighting gender-specific benefits. | Expenditure | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 2.1 Identification of projects/inititives | 2.1.2 | 2.1.2Develop a portfolio of selected projects with detailed descriptions and expected outcomes, highlighting gender-specific benefits. | Based on the evaluations conducted, this activity will create a portfolio of selected projects with detailed descriptions, expected outcomes, and their contributions to SLCP mitigation. The portfolio will emphasize gender-specific benefits, such as creating economic opportunities for women in waste management. The document will serve as a key resource for attracting public and private investments. | Research, data collection, and/or report writing | null | null | UNDP | Panama | Panama | null | 12/1/2025 | 6/1/2026 | Policy, regulation or other guideline | null | null | null | 2.1 | Activity 2.1.2Develop a portfolio of selected projects with detailed descriptions and expected outcomes, highlighting gender-specific benefits. | Output 2.1 Identification of projects/inititives | 2.1.2Develop a portfolio of selected projects with detailed descriptions and expected outcomes, highlighting gender-specific benefits. | PA-24-003/2.1.2 | PA-24-003/2.1.2Develop a portfolio of selected projects with detailed descriptions and expected outcomes, highlighting gender-specific benefits. | PA-24-003/2.1 Identification of projects/inititives | Activity | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 2.1 | Identification of projects/inititives | Identification of at least 5-7 appropriate projects/initiatives with business potential in integral organic waste management, supported by the public and private sector based on the findings of output 1.3. and will be evaluated for their potential to contribute to a circular economy. The assesment will include project descriptions, expected outcomes, involved entities, and financing strategies. By identifying these opportunities, the project aims to establish a solid foundation for future investements and actions in organic waste management. | 2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | Number of partnerships, associations, or campaigns launched to drive SLCP action | 5 | 5 Partnerships to drive SLCP action. | UNDP | Panama | Investors, public and private stakeholders. | Build a project portfolio to attract funding and investment. | Research or study, Work plan | 2/1/2026 12:00:00 AM | 6/1/2026 | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | 2.1 Identification of projects/inititives | Output 2.1 Identification of projects/inititives | Outcome 2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | PA-24-003/2.1 | PA-24-003/2.1 Identification of projects/inititives | Output | PA-24-003/2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 2 | The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | The project will create a portfolio of 5-7 initiatives and projects with demonstrated business potential, aligned with national goals, and designed to attract funding from both public and private sectors. Specific financial plans will be developed for at least three selected projects, including tailored financial tools and agreements among stakeholders, to enhance the likelihood of securing financing, scaling, and promoting sustainable solutions. The process will include the establishment of collaborative, multi-stakeholder partnerships, which are essential for co-creating comprehensive and lasting solutions. Key activities will involve delivering workshops to financial and governmental stakeholders to explore innovative financing mechanisms and develop actionable financial instruments that address the needs of the selected initiatives. The project assumes that the identified initiatives will generate significant interest from funding institutions and public and private entities, with active participation ... | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 5 | 5 action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures | 2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | Outcome 2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | PA-24-003/2. | PA-24-003/2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Outcome | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003 | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | UNDP () | UNDP ()
2.1.3Engage private sector investors and financial institutions in the evaluation process to co-create viable financing strategies. | Staff and Other Personnel Costs | 2.1.3-1 | Training workshops, seminars and meetings | UNDP | Specialist hired to integrate circular economy practices | CCAC | 1 | Consultant | 15000 | 15000 | null | 15000 | null | Yes. | 2/1/2003 | Expenditure 2.1.3-1 Training workshops, seminars and meetings | Activity 2.1.3Engage private sector investors and financial institutions in the evaluation process to co-create viable financing strategies. | UNDP () | PA-24-003/2.1.3-1 | PA-24-003/2.1.3-1 Training workshops, seminars and meetings | PA-24-003/2.1.3Engage private sector investors and financial institutions in the evaluation process to co-create viable financing strategies. | Expenditure | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 2.1 Identification of projects/inititives | 2.1.3 | 2.1.3Engage private sector investors and financial institutions in the evaluation process to co-create viable financing strategies. | This activity will involve engaging private sector investors and financial institutions to develop financing strategies for the selected projects. Workshops and one-on-one consultations will be conducted to present the portfolio and discuss potential financing options, including public-private partnerships and innovative financial instruments. The activity will emphasize strategies that support women-led initiatives and community-based projects. | Other | null | null | UNDP | Panama | Panama | null | 12/1/2025 | 6/1/2026 | Meeting report | null | null | null | 2.1 | Activity 2.1.3Engage private sector investors and financial institutions in the evaluation process to co-create viable financing strategies. | Output 2.1 Identification of projects/inititives | 2.1.3Engage private sector investors and financial institutions in the evaluation process to co-create viable financing strategies. | PA-24-003/2.1.3 | PA-24-003/2.1.3Engage private sector investors and financial institutions in the evaluation process to co-create viable financing strategies. | PA-24-003/2.1 Identification of projects/inititives | Activity | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 2.1 | Identification of projects/inititives | Identification of at least 5-7 appropriate projects/initiatives with business potential in integral organic waste management, supported by the public and private sector based on the findings of output 1.3. and will be evaluated for their potential to contribute to a circular economy. The assesment will include project descriptions, expected outcomes, involved entities, and financing strategies. By identifying these opportunities, the project aims to establish a solid foundation for future investements and actions in organic waste management. | 2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | Number of partnerships, associations, or campaigns launched to drive SLCP action | 5 | 5 Partnerships to drive SLCP action. | UNDP | Panama | Investors, public and private stakeholders. | Build a project portfolio to attract funding and investment. | Research or study, Work plan | 2/1/2026 12:00:00 AM | 6/1/2026 | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | 2.1 Identification of projects/inititives | Output 2.1 Identification of projects/inititives | Outcome 2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | PA-24-003/2.1 | PA-24-003/2.1 Identification of projects/inititives | Output | PA-24-003/2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 2 | The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | The project will create a portfolio of 5-7 initiatives and projects with demonstrated business potential, aligned with national goals, and designed to attract funding from both public and private sectors. Specific financial plans will be developed for at least three selected projects, including tailored financial tools and agreements among stakeholders, to enhance the likelihood of securing financing, scaling, and promoting sustainable solutions. The process will include the establishment of collaborative, multi-stakeholder partnerships, which are essential for co-creating comprehensive and lasting solutions. Key activities will involve delivering workshops to financial and governmental stakeholders to explore innovative financing mechanisms and develop actionable financial instruments that address the needs of the selected initiatives. The project assumes that the identified initiatives will generate significant interest from funding institutions and public and private entities, with active participation ... | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 5 | 5 action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures | 2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | Outcome 2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | PA-24-003/2. | PA-24-003/2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Outcome | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003 | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | UNDP () | UNDP ()
2.2.1Host a multi-stakeholder workshop, ensuring representation from women-led organizations, to prioritize three high-impact projects. | Contractual Services | 2.2.1-1 | Financial and Business Development Consultant | UNDP | null | CCAC | 1 | Training workshops, seminars and meetings | 3000 | 3000 | null | 3000 | null | Yes. | 2/2/2001 | Expenditure 2.2.1-1 Financial and Business Development Consultant | Activity 2.2.1Host a multi-stakeholder workshop, ensuring representation from women-led organizations, to prioritize three high-impact projects. | UNDP () | PA-24-003/2.2.1-1 | PA-24-003/2.2.1-1 Financial and Business Development Consultant | PA-24-003/2.2.1Host a multi-stakeholder workshop, ensuring representation from women-led organizations, to prioritize three high-impact projects. | Expenditure | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 2.2 Stakeholder Engagement and Strategic Financial Planning for Selected Projects | 2.2.1 | 2.2.1Host a multi-stakeholder workshop, ensuring representation from women-led organizations, to prioritize three high-impact projects. | This activity will bring together key stakeholders, including government agencies, financial institutions, private sector representatives, and women-led organizations, to prioritize three high-impact projects from the identified portfolio. The workshop will use a participatory approach to ensure that diverse perspectives are incorporated in the decision-making process. Criteria for prioritization will include business potential, environmental and social benefits, and alignment with national goals. The outcomes of the workshop will guide the development of detailed financial plans for the selected projects. | Organising, holding, or participating in a meeting or event | null | null | UNDP | Panama | Panama | null | 3/1/2026 | 6/1/2026 | Work plan | null | null | null | 2.2 | Activity 2.2.1Host a multi-stakeholder workshop, ensuring representation from women-led organizations, to prioritize three high-impact projects. | Output 2.2 Stakeholder Engagement and Strategic Financial Planning for Selected Projects | 2.2.1Host a multi-stakeholder workshop, ensuring representation from women-led organizations, to prioritize three high-impact projects. | PA-24-003/2.2.1 | PA-24-003/2.2.1Host a multi-stakeholder workshop, ensuring representation from women-led organizations, to prioritize three high-impact projects. | PA-24-003/2.2 Stakeholder Engagement and Strategic Financial Planning for Selected Projects | Activity | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 2.2 | Stakeholder Engagement and Strategic Financial Planning for Selected Projects | Stakeholders, including government agencies, private companies, and financial institutions, will be convened and engaged to select at least 3 priority projects/ initiatives for organic waste management. This process will focus on identifying potential funding sources and aligning stakeholders to support these initiatives. The selected projects will be developed into deteiled plans, including financial strategies and implementation pathways, ensuring coodinated efforts amog all stakeholders to advance sustainable waste management solution. | 2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | Number of partnerships, associations, or campaigns launched to drive SLCP action | 3 | 3 Associations launched to drive SLCP action. | UNDP | Panama | Investors, public and private stakeholders. | Provide detailed plans to advance selected projects. | Work plan | 5/1/2026 12:00:00 AM | 9/1/2026 | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | 2.2 Stakeholder Engagement and Strategic Financial Planning for Selected Projects | Output 2.2 Stakeholder Engagement and Strategic Financial Planning for Selected Projects | Outcome 2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | PA-24-003/2.2 | PA-24-003/2.2 Stakeholder Engagement and Strategic Financial Planning for Selected Projects | Output | PA-24-003/2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 2 | The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | The project will create a portfolio of 5-7 initiatives and projects with demonstrated business potential, aligned with national goals, and designed to attract funding from both public and private sectors. Specific financial plans will be developed for at least three selected projects, including tailored financial tools and agreements among stakeholders, to enhance the likelihood of securing financing, scaling, and promoting sustainable solutions. The process will include the establishment of collaborative, multi-stakeholder partnerships, which are essential for co-creating comprehensive and lasting solutions. Key activities will involve delivering workshops to financial and governmental stakeholders to explore innovative financing mechanisms and develop actionable financial instruments that address the needs of the selected initiatives. The project assumes that the identified initiatives will generate significant interest from funding institutions and public and private entities, with active participation ... | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 5 | 5 action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures | 2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | Outcome 2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | PA-24-003/2. | PA-24-003/2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Outcome | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003 | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | UNDP () | UNDP ()
2.2.2Develop detailed financial plans for selected projects, including specific tools tailored to benefit marginalized groups. | Staff and Other Personnel Costs | 2.2.2-1 | computers | UNDP | Consultant hired to provide business development advice | CCAC | 1 | Consultant | 15000 | 15000 | null | 10000 | 5000 | Yes. | 2/2/2002 | Expenditure 2.2.2-1 computers | Activity 2.2.2Develop detailed financial plans for selected projects, including specific tools tailored to benefit marginalized groups. | UNDP () | PA-24-003/2.2.2-1 | PA-24-003/2.2.2-1 computers | PA-24-003/2.2.2Develop detailed financial plans for selected projects, including specific tools tailored to benefit marginalized groups. | Expenditure | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 2.2 Stakeholder Engagement and Strategic Financial Planning for Selected Projects | 2.2.2 | 2.2.2Develop detailed financial plans for selected projects, including specific tools tailored to benefit marginalized groups. | This activity involves creating comprehensive financial plans for the three prioritized projects. The plans will include cost estimates, funding requirements, and proposed financial instruments such as grants, loans, or public-private partnerships. Special attention will be given to designing tools that benefit marginalized groups, including women-led initiatives and small businesses. The financial plans will align with national and international sustainability goals and provide a clear roadmap for securing investment. | Research, data collection, and/or report writing | null | null | UNDP | Panama | Panama | null | 3/1/2026 | 9/1/2026 | Web article | null | null | null | 2.2 | Activity 2.2.2Develop detailed financial plans for selected projects, including specific tools tailored to benefit marginalized groups. | Output 2.2 Stakeholder Engagement and Strategic Financial Planning for Selected Projects | 2.2.2Develop detailed financial plans for selected projects, including specific tools tailored to benefit marginalized groups. | PA-24-003/2.2.2 | PA-24-003/2.2.2Develop detailed financial plans for selected projects, including specific tools tailored to benefit marginalized groups. | PA-24-003/2.2 Stakeholder Engagement and Strategic Financial Planning for Selected Projects | Activity | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 2.2 | Stakeholder Engagement and Strategic Financial Planning for Selected Projects | Stakeholders, including government agencies, private companies, and financial institutions, will be convened and engaged to select at least 3 priority projects/ initiatives for organic waste management. This process will focus on identifying potential funding sources and aligning stakeholders to support these initiatives. The selected projects will be developed into deteiled plans, including financial strategies and implementation pathways, ensuring coodinated efforts amog all stakeholders to advance sustainable waste management solution. | 2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | Number of partnerships, associations, or campaigns launched to drive SLCP action | 3 | 3 Associations launched to drive SLCP action. | UNDP | Panama | Investors, public and private stakeholders. | Provide detailed plans to advance selected projects. | Work plan | 5/1/2026 12:00:00 AM | 9/1/2026 | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | 2.2 Stakeholder Engagement and Strategic Financial Planning for Selected Projects | Output 2.2 Stakeholder Engagement and Strategic Financial Planning for Selected Projects | Outcome 2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | PA-24-003/2.2 | PA-24-003/2.2 Stakeholder Engagement and Strategic Financial Planning for Selected Projects | Output | PA-24-003/2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 2 | The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | The project will create a portfolio of 5-7 initiatives and projects with demonstrated business potential, aligned with national goals, and designed to attract funding from both public and private sectors. Specific financial plans will be developed for at least three selected projects, including tailored financial tools and agreements among stakeholders, to enhance the likelihood of securing financing, scaling, and promoting sustainable solutions. The process will include the establishment of collaborative, multi-stakeholder partnerships, which are essential for co-creating comprehensive and lasting solutions. Key activities will involve delivering workshops to financial and governmental stakeholders to explore innovative financing mechanisms and develop actionable financial instruments that address the needs of the selected initiatives. The project assumes that the identified initiatives will generate significant interest from funding institutions and public and private entities, with active participation ... | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 5 | 5 action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures | 2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | Outcome 2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | PA-24-003/2. | PA-24-003/2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Outcome | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003 | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | UNDP () | UNDP ()
2.2.3Release a press statement highlighting the selected projects to attract further investment and support. | Equipment Vehicles and Furniture | 2.2.3-1 | Circular Economy Specialist | UNDP | null | CCAC | 1 | computers | 3000 | 3000 | 3000 | null | null | Yes. | 2/2/2003 | Expenditure 2.2.3-1 Circular Economy Specialist | Activity 2.2.3Release a press statement highlighting the selected projects to attract further investment and support. | UNDP () | PA-24-003/2.2.3-1 | PA-24-003/2.2.3-1 Circular Economy Specialist | PA-24-003/2.2.3Release a press statement highlighting the selected projects to attract further investment and support. | Expenditure | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 2.2 Stakeholder Engagement and Strategic Financial Planning for Selected Projects | 2.2.3 | 2.2.3Release a press statement highlighting the selected projects to attract further investment and support. | To raise awareness and attract investment, this activity will involve drafting and disseminating a press statement announcing the three selected projects. The statement will highlight the projects’ environmental, economic, and social benefits, as well as their alignment with SLCP mitigation goals. The press release will be shared with local and international media outlets, government websites, and social media platforms. The announcement will also emphasize opportunities for private sector involvement and partnerships. | Producing and distributing communications materials | null | null | UNDP | Panama | Panama | null | 6/1/2026 | 9/1/2026 | Meeting report | null | null | null | 2.2 | Activity 2.2.3Release a press statement highlighting the selected projects to attract further investment and support. | Output 2.2 Stakeholder Engagement and Strategic Financial Planning for Selected Projects | 2.2.3Release a press statement highlighting the selected projects to attract further investment and support. | PA-24-003/2.2.3 | PA-24-003/2.2.3Release a press statement highlighting the selected projects to attract further investment and support. | PA-24-003/2.2 Stakeholder Engagement and Strategic Financial Planning for Selected Projects | Activity | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 2.2 | Stakeholder Engagement and Strategic Financial Planning for Selected Projects | Stakeholders, including government agencies, private companies, and financial institutions, will be convened and engaged to select at least 3 priority projects/ initiatives for organic waste management. This process will focus on identifying potential funding sources and aligning stakeholders to support these initiatives. The selected projects will be developed into deteiled plans, including financial strategies and implementation pathways, ensuring coodinated efforts amog all stakeholders to advance sustainable waste management solution. | 2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | Number of partnerships, associations, or campaigns launched to drive SLCP action | 3 | 3 Associations launched to drive SLCP action. | UNDP | Panama | Investors, public and private stakeholders. | Provide detailed plans to advance selected projects. | Work plan | 5/1/2026 12:00:00 AM | 9/1/2026 | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | 2.2 Stakeholder Engagement and Strategic Financial Planning for Selected Projects | Output 2.2 Stakeholder Engagement and Strategic Financial Planning for Selected Projects | Outcome 2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | PA-24-003/2.2 | PA-24-003/2.2 Stakeholder Engagement and Strategic Financial Planning for Selected Projects | Output | PA-24-003/2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 2 | The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | The project will create a portfolio of 5-7 initiatives and projects with demonstrated business potential, aligned with national goals, and designed to attract funding from both public and private sectors. Specific financial plans will be developed for at least three selected projects, including tailored financial tools and agreements among stakeholders, to enhance the likelihood of securing financing, scaling, and promoting sustainable solutions. The process will include the establishment of collaborative, multi-stakeholder partnerships, which are essential for co-creating comprehensive and lasting solutions. Key activities will involve delivering workshops to financial and governmental stakeholders to explore innovative financing mechanisms and develop actionable financial instruments that address the needs of the selected initiatives. The project assumes that the identified initiatives will generate significant interest from funding institutions and public and private entities, with active participation ... | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 5 | 5 action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures | 2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | Outcome 2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | PA-24-003/2. | PA-24-003/2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Outcome | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003 | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | UNDP () | UNDP ()
2.2.3Release a press statement highlighting the selected projects to attract further investment and support. | Staff and Other Personnel Costs | 2.2.3-2 | National Consultant - Policy and SLCP Mitigation Consultant | UNDP | null | CCAC | 1 | Consultant | 15000 | 15000 | null | null | 15000 | Yes. | 2/2/2003 | Expenditure 2.2.3-2 National Consultant - Policy and SLCP Mitigation Consultant | Activity 2.2.3Release a press statement highlighting the selected projects to attract further investment and support. | UNDP () | PA-24-003/2.2.3-2 | PA-24-003/2.2.3-2 National Consultant - Policy and SLCP Mitigation Consultant | PA-24-003/2.2.3Release a press statement highlighting the selected projects to attract further investment and support. | Expenditure | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 2.2 Stakeholder Engagement and Strategic Financial Planning for Selected Projects | 2.2.3 | 2.2.3Release a press statement highlighting the selected projects to attract further investment and support. | To raise awareness and attract investment, this activity will involve drafting and disseminating a press statement announcing the three selected projects. The statement will highlight the projects’ environmental, economic, and social benefits, as well as their alignment with SLCP mitigation goals. The press release will be shared with local and international media outlets, government websites, and social media platforms. The announcement will also emphasize opportunities for private sector involvement and partnerships. | Producing and distributing communications materials | null | null | UNDP | Panama | Panama | null | 6/1/2026 | 9/1/2026 | Meeting report | null | null | null | 2.2 | Activity 2.2.3Release a press statement highlighting the selected projects to attract further investment and support. | Output 2.2 Stakeholder Engagement and Strategic Financial Planning for Selected Projects | 2.2.3Release a press statement highlighting the selected projects to attract further investment and support. | PA-24-003/2.2.3 | PA-24-003/2.2.3Release a press statement highlighting the selected projects to attract further investment and support. | PA-24-003/2.2 Stakeholder Engagement and Strategic Financial Planning for Selected Projects | Activity | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 2.2 | Stakeholder Engagement and Strategic Financial Planning for Selected Projects | Stakeholders, including government agencies, private companies, and financial institutions, will be convened and engaged to select at least 3 priority projects/ initiatives for organic waste management. This process will focus on identifying potential funding sources and aligning stakeholders to support these initiatives. The selected projects will be developed into deteiled plans, including financial strategies and implementation pathways, ensuring coodinated efforts amog all stakeholders to advance sustainable waste management solution. | 2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | Number of partnerships, associations, or campaigns launched to drive SLCP action | 3 | 3 Associations launched to drive SLCP action. | UNDP | Panama | Investors, public and private stakeholders. | Provide detailed plans to advance selected projects. | Work plan | 5/1/2026 12:00:00 AM | 9/1/2026 | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | 2.2 Stakeholder Engagement and Strategic Financial Planning for Selected Projects | Output 2.2 Stakeholder Engagement and Strategic Financial Planning for Selected Projects | Outcome 2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | PA-24-003/2.2 | PA-24-003/2.2 Stakeholder Engagement and Strategic Financial Planning for Selected Projects | Output | PA-24-003/2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 2 | The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | The project will create a portfolio of 5-7 initiatives and projects with demonstrated business potential, aligned with national goals, and designed to attract funding from both public and private sectors. Specific financial plans will be developed for at least three selected projects, including tailored financial tools and agreements among stakeholders, to enhance the likelihood of securing financing, scaling, and promoting sustainable solutions. The process will include the establishment of collaborative, multi-stakeholder partnerships, which are essential for co-creating comprehensive and lasting solutions. Key activities will involve delivering workshops to financial and governmental stakeholders to explore innovative financing mechanisms and develop actionable financial instruments that address the needs of the selected initiatives. The project assumes that the identified initiatives will generate significant interest from funding institutions and public and private entities, with active participation ... | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 5 | 5 action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures | 2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | Outcome 2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | PA-24-003/2. | PA-24-003/2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Outcome | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003 | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | UNDP () | UNDP ()
3.1.1Review existing policies and regulations related to organic waste and SLCPs, engaging policymakers, academics, and gender specialists. | Staff and Other Personnel Costs | 3.1.1-1 | National Consultant - Policy and SLCP Mitigation Consultant | UNDP | Conduct policy analysis and deliver actionable recommendations | CCAC | 1 | Consultant | 15000 | 15000 | null | 15000 | null | Yes. | 3/1/2001 | Expenditure 3.1.1-1 National Consultant - Policy and SLCP Mitigation Consultant | Activity 3.1.1Review existing policies and regulations related to organic waste and SLCPs, engaging policymakers, academics, and gender specialists. | UNDP () | PA-24-003/3.1.1-1 | PA-24-003/3.1.1-1 National Consultant - Policy and SLCP Mitigation Consultant | PA-24-003/3.1.1Review existing policies and regulations related to organic waste and SLCPs, engaging policymakers, academics, and gender specialists. | Expenditure | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 3.1 Analysis of policies to mitigate SLCPs | 3.1.1 | 3.1.1Review existing policies and regulations related to organic waste and SLCPs, engaging policymakers, academics, and gender specialists. | This activity involves a comprehensive review of existing policies and regulations governing organic waste management and SLCP mitigation in Panama. The review will engage policymakers, academics, and gender specialists to provide diverse perspectives and insights. The analysis will assess the effectiveness of current regulations, identify potential overlaps or gaps, and evaluate their alignment with national and international sustainability goals. Special emphasis will be placed on examining the gender impacts of these policies to ensure inclusivity and equity in future recommendations. | Research, data collection, and/or report writing | null | null | UNDP | Panama | Panama | null | 9/1/2025 | 12/1/2025 | Policy, regulation or other guideline | null | null | null | 3.1 | Activity 3.1.1Review existing policies and regulations related to organic waste and SLCPs, engaging policymakers, academics, and gender specialists. | Output 3.1 Analysis of policies to mitigate SLCPs | 3.1.1Review existing policies and regulations related to organic waste and SLCPs, engaging policymakers, academics, and gender specialists. | PA-24-003/3.1.1 | PA-24-003/3.1.1Review existing policies and regulations related to organic waste and SLCPs, engaging policymakers, academics, and gender specialists. | PA-24-003/3.1 Analysis of policies to mitigate SLCPs | Activity | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 3.1 | Analysis of policies to mitigate SLCPs | Evaluation and analysis of policies to mitigate Short-Lived Climate Pollutants (SLCPs) from organic waste and prioritize actions for short, medium, and long term implementation. This evaluation will assess current measures and identify gaps in policy, recommending interventions that can effectively reduce SLCPs. The analysis will also provide estimated costs, responsible parties, and progress indicators. The result will be a comprehensive plan that outlines the necessary steps for Panama to reduce SLCP emissions through better organic waste management practices. | 3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Number of plans, policies, laws, or regulations drafted or updated | 1 | 1 plan, drafted or updated. | UNDP | Panama | Government policymakers, NGOs, private sector. | Guide future policy reforms and actions for SLCP mitigation. | Policy, regulation or other guideline | 11/1/2025 12:00:00 AM | 3/1/2026 | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | 3.1 Analysis of policies to mitigate SLCPs | Output 3.1 Analysis of policies to mitigate SLCPs | Outcome 3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | PA-24-003/3.1 | PA-24-003/3.1 Analysis of policies to mitigate SLCPs | Output | PA-24-003/3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 3 | A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Workshops under Output 2 will convene key stakeholders, including representatives from the financial sector, local and national governments, and private entities, to explore and design financial mechanisms aligned with Panama's national goals. These workshops will focus on evaluating policies to mitigate Short-Lived Climate Pollutants (SLCPs) from organic waste and identifying opportunities for financial innovation. The outcome will include the creation of a draft roadmap detailing necessary financial instruments and resources tailored to the unique needs and characteristics of organic waste projects in Panama. This roadmap will serve as a foundation for developing long-term financing strategies and a comprehensive resource mobilization plan, fostering sustainable investment and alignment with national and global sustainability goals. | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 1 | 1 roadmap | 3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Outcome 3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | PA-24-003/3. | PA-24-003/3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Outcome | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003 | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | UNDP () | UNDP ()
3.1.2Identify policy gaps and prioritize actions for short, medium, and long-term implementation, ensuring gender-disaggregated data is part of the analysis. | Staff and Other Personnel Costs | 3.1.2-1 | Training workshops, seminars and meetings | UNDP | Conduct policy analysis and deliver actionable recommendations | CCAC | 1 | Consultant | 15000 | 15000 | null | 15000 | null | Yes. | 3/1/2002 | Expenditure 3.1.2-1 Training workshops, seminars and meetings | Activity 3.1.2Identify policy gaps and prioritize actions for short, medium, and long-term implementation, ensuring gender-disaggregated data is part of the analysis. | UNDP () | PA-24-003/3.1.2-1 | PA-24-003/3.1.2-1 Training workshops, seminars and meetings | PA-24-003/3.1.2Identify policy gaps and prioritize actions for short, medium, and long-term implementation, ensuring gender-disaggregated data is part of the analysis. | Expenditure | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 3.1 Analysis of policies to mitigate SLCPs | 3.1.2 | 3.1.2Identify policy gaps and prioritize actions for short, medium, and long-term implementation, ensuring gender-disaggregated data is part of the analysis. | Building on the findings from the policy review, this activity will identify critical gaps and barriers in existing policies and propose prioritized actions for addressing them. Recommendations will be categorized into short, medium, and long-term strategies, ensuring alignment with Panama’s national goals and SLCP reduction targets. Gender-disaggregated data will be used to assess the differentiated impacts of these actions on men and women, with a focus on promoting inclusivity in policy reforms. | Research, data collection, and/or report writing | null | null | UNDP | Panama | Panama | null | 9/1/2025 | 12/1/2025 | Policy, regulation or other guideline | null | null | null | 3.1 | Activity 3.1.2Identify policy gaps and prioritize actions for short, medium, and long-term implementation, ensuring gender-disaggregated data is part of the analysis. | Output 3.1 Analysis of policies to mitigate SLCPs | 3.1.2Identify policy gaps and prioritize actions for short, medium, and long-term implementation, ensuring gender-disaggregated data is part of the analysis. | PA-24-003/3.1.2 | PA-24-003/3.1.2Identify policy gaps and prioritize actions for short, medium, and long-term implementation, ensuring gender-disaggregated data is part of the analysis. | PA-24-003/3.1 Analysis of policies to mitigate SLCPs | Activity | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 3.1 | Analysis of policies to mitigate SLCPs | Evaluation and analysis of policies to mitigate Short-Lived Climate Pollutants (SLCPs) from organic waste and prioritize actions for short, medium, and long term implementation. This evaluation will assess current measures and identify gaps in policy, recommending interventions that can effectively reduce SLCPs. The analysis will also provide estimated costs, responsible parties, and progress indicators. The result will be a comprehensive plan that outlines the necessary steps for Panama to reduce SLCP emissions through better organic waste management practices. | 3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Number of plans, policies, laws, or regulations drafted or updated | 1 | 1 plan, drafted or updated. | UNDP | Panama | Government policymakers, NGOs, private sector. | Guide future policy reforms and actions for SLCP mitigation. | Policy, regulation or other guideline | 11/1/2025 12:00:00 AM | 3/1/2026 | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | 3.1 Analysis of policies to mitigate SLCPs | Output 3.1 Analysis of policies to mitigate SLCPs | Outcome 3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | PA-24-003/3.1 | PA-24-003/3.1 Analysis of policies to mitigate SLCPs | Output | PA-24-003/3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 3 | A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Workshops under Output 2 will convene key stakeholders, including representatives from the financial sector, local and national governments, and private entities, to explore and design financial mechanisms aligned with Panama's national goals. These workshops will focus on evaluating policies to mitigate Short-Lived Climate Pollutants (SLCPs) from organic waste and identifying opportunities for financial innovation. The outcome will include the creation of a draft roadmap detailing necessary financial instruments and resources tailored to the unique needs and characteristics of organic waste projects in Panama. This roadmap will serve as a foundation for developing long-term financing strategies and a comprehensive resource mobilization plan, fostering sustainable investment and alignment with national and global sustainability goals. | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 1 | 1 roadmap | 3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Outcome 3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | PA-24-003/3. | PA-24-003/3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Outcome | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003 | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | UNDP () | UNDP ()
3.1.3Develop a policy evaluation report and share findings through a case study targeted at stakeholders. | Contractual Services | 3.1.3-1 | Training workshops, seminars and meetings | UNDP | null | CCAC | 1 | Workshop | 3000 | 3000 | null | 3000 | null | Yes. | 3/1/2003 | Expenditure 3.1.3-1 Training workshops, seminars and meetings | Activity 3.1.3Develop a policy evaluation report and share findings through a case study targeted at stakeholders. | UNDP () | PA-24-003/3.1.3-1 | PA-24-003/3.1.3-1 Training workshops, seminars and meetings | PA-24-003/3.1.3Develop a policy evaluation report and share findings through a case study targeted at stakeholders. | Expenditure | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 3.1 Analysis of policies to mitigate SLCPs | 3.1.3 | 3.1.3Develop a policy evaluation report and share findings through a case study targeted at stakeholders. | This activity will consolidate the results of the policy analysis into an evaluation report, including actionable recommendations for strengthening SLCP mitigation policies. The report will also include a case study highlighting the potential impact of policy reforms on organic waste management and gender inclusivity. The findings will be shared with stakeholders through targeted communication efforts, including workshops, digital platforms, and printed materials. | Policy, project, or tool design | null | null | UNDP | Panama | Panama | null | 9/1/2025 | 3/1/2026 | Meeting report | null | null | null | 3.1 | Activity 3.1.3Develop a policy evaluation report and share findings through a case study targeted at stakeholders. | Output 3.1 Analysis of policies to mitigate SLCPs | 3.1.3Develop a policy evaluation report and share findings through a case study targeted at stakeholders. | PA-24-003/3.1.3 | PA-24-003/3.1.3Develop a policy evaluation report and share findings through a case study targeted at stakeholders. | PA-24-003/3.1 Analysis of policies to mitigate SLCPs | Activity | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 3.1 | Analysis of policies to mitigate SLCPs | Evaluation and analysis of policies to mitigate Short-Lived Climate Pollutants (SLCPs) from organic waste and prioritize actions for short, medium, and long term implementation. This evaluation will assess current measures and identify gaps in policy, recommending interventions that can effectively reduce SLCPs. The analysis will also provide estimated costs, responsible parties, and progress indicators. The result will be a comprehensive plan that outlines the necessary steps for Panama to reduce SLCP emissions through better organic waste management practices. | 3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Number of plans, policies, laws, or regulations drafted or updated | 1 | 1 plan, drafted or updated. | UNDP | Panama | Government policymakers, NGOs, private sector. | Guide future policy reforms and actions for SLCP mitigation. | Policy, regulation or other guideline | 11/1/2025 12:00:00 AM | 3/1/2026 | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | 3.1 Analysis of policies to mitigate SLCPs | Output 3.1 Analysis of policies to mitigate SLCPs | Outcome 3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | PA-24-003/3.1 | PA-24-003/3.1 Analysis of policies to mitigate SLCPs | Output | PA-24-003/3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 3 | A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Workshops under Output 2 will convene key stakeholders, including representatives from the financial sector, local and national governments, and private entities, to explore and design financial mechanisms aligned with Panama's national goals. These workshops will focus on evaluating policies to mitigate Short-Lived Climate Pollutants (SLCPs) from organic waste and identifying opportunities for financial innovation. The outcome will include the creation of a draft roadmap detailing necessary financial instruments and resources tailored to the unique needs and characteristics of organic waste projects in Panama. This roadmap will serve as a foundation for developing long-term financing strategies and a comprehensive resource mobilization plan, fostering sustainable investment and alignment with national and global sustainability goals. | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 1 | 1 roadmap | 3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Outcome 3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | PA-24-003/3. | PA-24-003/3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Outcome | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003 | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | UNDP () | UNDP ()
3.2.1Host a workshop with financial institutions, government agencies, and private entities to co-design financial instruments tailored to organic waste projects, ensuring gender inclusion in discussions. | Contractual Services | 3.2.1-1 | Financial and Business Development Consultant | UNDP | null | CCAC | 1 | Workshop | 3000 | 3000 | null | 3000 | null | Yes. | 3/2/2001 | Expenditure 3.2.1-1 Financial and Business Development Consultant | Activity 3.2.1Host a workshop with financial institutions, government agencies, and private entities to co-design financial instruments tailored to organic waste projects, ensuring gender inclusion in discussions. | UNDP () | PA-24-003/3.2.1-1 | PA-24-003/3.2.1-1 Financial and Business Development Consultant | PA-24-003/3.2.1Host a workshop with financial institutions, government agencies, and private entities to co-design financial instruments tailored to organic waste projects, ensuring gender inclusion in discussions. | Expenditure | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 3.2 Draft roadmap of financial intruments | 3.2.1 | 3.2.1Host a workshop with financial institutions, government agencies, and private entities to co-design financial instruments tailored to organic waste projects, ensuring gender inclusion in discussions. | This workshop will bring together financial institutions, government agencies, private sector representatives, and women-led organizations to co-design innovative financial instruments for organic waste projects. Participants will collaborate on identifying barriers to financing and brainstorming tailored solutions, including gender-inclusive tools such as microfinance or capacity-building grants. The outcomes will form the foundation for a draft roadmap of financial mechanisms. | Organising, holding, or participating in a meeting or event | null | null | UNDP | Panama | Panama | null | 12/1/2025 | 3/1/2026 | Work plan | null | null | null | 3.2 | Activity 3.2.1Host a workshop with financial institutions, government agencies, and private entities to co-design financial instruments tailored to organic waste projects, ensuring gender inclusion in discussions. | Output 3.2 Draft roadmap of financial intruments | 3.2.1Host a workshop with financial institutions, government agencies, and private entities to co-design financial instruments tailored to organic waste projects, ensuring gender inclusion in discussions. | PA-24-003/3.2.1 | PA-24-003/3.2.1Host a workshop with financial institutions, government agencies, and private entities to co-design financial instruments tailored to organic waste projects, ensuring gender inclusion in discussions. | PA-24-003/3.2 Draft roadmap of financial intruments | Activity | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 3.2 | Draft roadmap of financial intruments | A draft roadmap for financial instruments in organic waste management will be developed. This roadmap will be based on the findings of the previous evaluations and workshops, tailoring financial tools to the specific needs of the identified projects. It will include a detailed assessment of existing financial mechanisms and propose new ones that address key challenges and opportunities. The roadmap will guide the government and private sector in mobilizing resources for the sustainable implementation of organic waste management projects. | 3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Number of plans, policies, laws, or regulations drafted or updated | 1 | 1 plan drafted or updated. | UNDP | Panama | Financial institutions and government agencies. | Provide actionable steps for financing organic waste projects. | Policy, regulation or other guideline | 5/1/2026 12:00:00 AM | 9/1/2026 | Available in English or other agreed UN language, and grammatically correct + English summary Involvement of the beneficiary government throughout the development process, for example through consultation meetings Involvement of the CCAC focal point Agreement to, or acknowledgement of, the product presented by the beneficiary government (at the appropriate level) and the CCAC Secretariat | 3.2 Draft roadmap of financial intruments | Output 3.2 Draft roadmap of financial intruments | Outcome 3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | PA-24-003/3.2 | PA-24-003/3.2 Draft roadmap of financial intruments | Output | PA-24-003/3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 3 | A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Workshops under Output 2 will convene key stakeholders, including representatives from the financial sector, local and national governments, and private entities, to explore and design financial mechanisms aligned with Panama's national goals. These workshops will focus on evaluating policies to mitigate Short-Lived Climate Pollutants (SLCPs) from organic waste and identifying opportunities for financial innovation. The outcome will include the creation of a draft roadmap detailing necessary financial instruments and resources tailored to the unique needs and characteristics of organic waste projects in Panama. This roadmap will serve as a foundation for developing long-term financing strategies and a comprehensive resource mobilization plan, fostering sustainable investment and alignment with national and global sustainability goals. | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 1 | 1 roadmap | 3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Outcome 3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | PA-24-003/3. | PA-24-003/3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Outcome | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003 | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | UNDP () | UNDP ()
3.2.2Draft a comprehensive roadmap with actionable steps and estimated budgets, prioritizing funds for women-led initiatives. | Staff and Other Personnel Costs | 3.2.2-1 | Contractual services for the design financial roadmap | UNDP | null | CCAC | 1 | Trips | 20000 | 20000 | null | 20000 | null | Yes. | 3/2/2002 | Expenditure 3.2.2-1 Contractual services for the design financial roadmap | Activity 3.2.2Draft a comprehensive roadmap with actionable steps and estimated budgets, prioritizing funds for women-led initiatives. | UNDP () | PA-24-003/3.2.2-1 | PA-24-003/3.2.2-1 Contractual services for the design financial roadmap | PA-24-003/3.2.2Draft a comprehensive roadmap with actionable steps and estimated budgets, prioritizing funds for women-led initiatives. | Expenditure | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 3.2 Draft roadmap of financial intruments | 3.2.2 | 3.2.2Draft a comprehensive roadmap with actionable steps and estimated budgets, prioritizing funds for women-led initiatives. | This activity will build on the workshop outcomes to develop a comprehensive roadmap for implementing financial instruments for organic waste management. The roadmap will include actionable steps, estimated budgets, and a clear timeline for implementation. Special attention will be given to prioritizing funding mechanisms that support women-led initiatives and community-based projects. The roadmap will serve as a strategic guide for stakeholders to mobilize resources and align efforts with national sustainability goals. | Research, data collection, and/or report writing | null | null | UNDP | Panama | Panama | null | 3/1/2026 | 9/1/2026 | Tool | null | null | null | 3.2 | Activity 3.2.2Draft a comprehensive roadmap with actionable steps and estimated budgets, prioritizing funds for women-led initiatives. | Output 3.2 Draft roadmap of financial intruments | 3.2.2Draft a comprehensive roadmap with actionable steps and estimated budgets, prioritizing funds for women-led initiatives. | PA-24-003/3.2.2 | PA-24-003/3.2.2Draft a comprehensive roadmap with actionable steps and estimated budgets, prioritizing funds for women-led initiatives. | PA-24-003/3.2 Draft roadmap of financial intruments | Activity | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 3.2 | Draft roadmap of financial intruments | A draft roadmap for financial instruments in organic waste management will be developed. This roadmap will be based on the findings of the previous evaluations and workshops, tailoring financial tools to the specific needs of the identified projects. It will include a detailed assessment of existing financial mechanisms and propose new ones that address key challenges and opportunities. The roadmap will guide the government and private sector in mobilizing resources for the sustainable implementation of organic waste management projects. | 3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Number of plans, policies, laws, or regulations drafted or updated | 1 | 1 plan drafted or updated. | UNDP | Panama | Financial institutions and government agencies. | Provide actionable steps for financing organic waste projects. | Policy, regulation or other guideline | 5/1/2026 12:00:00 AM | 9/1/2026 | Available in English or other agreed UN language, and grammatically correct + English summary Involvement of the beneficiary government throughout the development process, for example through consultation meetings Involvement of the CCAC focal point Agreement to, or acknowledgement of, the product presented by the beneficiary government (at the appropriate level) and the CCAC Secretariat | 3.2 Draft roadmap of financial intruments | Output 3.2 Draft roadmap of financial intruments | Outcome 3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | PA-24-003/3.2 | PA-24-003/3.2 Draft roadmap of financial intruments | Output | PA-24-003/3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 3 | A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Workshops under Output 2 will convene key stakeholders, including representatives from the financial sector, local and national governments, and private entities, to explore and design financial mechanisms aligned with Panama's national goals. These workshops will focus on evaluating policies to mitigate Short-Lived Climate Pollutants (SLCPs) from organic waste and identifying opportunities for financial innovation. The outcome will include the creation of a draft roadmap detailing necessary financial instruments and resources tailored to the unique needs and characteristics of organic waste projects in Panama. This roadmap will serve as a foundation for developing long-term financing strategies and a comprehensive resource mobilization plan, fostering sustainable investment and alignment with national and global sustainability goals. | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 1 | 1 roadmap | 3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Outcome 3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | PA-24-003/3. | PA-24-003/3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Outcome | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003 | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | UNDP () | UNDP ()
3.2.3Create an interactive digital roadmap for dissemination to public and private stakeholders. | Contractual Services | 3.2.3-1 | Training workshops, seminars and meetings | UNDP | Interactive digital roadmap | CCAC | 1 | design | 5000 | 5000 | null | 5000 | null | Yes. | 3/2/2003 | Expenditure 3.2.3-1 Training workshops, seminars and meetings | Activity 3.2.3Create an interactive digital roadmap for dissemination to public and private stakeholders. | UNDP () | PA-24-003/3.2.3-1 | PA-24-003/3.2.3-1 Training workshops, seminars and meetings | PA-24-003/3.2.3Create an interactive digital roadmap for dissemination to public and private stakeholders. | Expenditure | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 3.2 Draft roadmap of financial intruments | 3.2.3 | 3.2.3Create an interactive digital roadmap for dissemination to public and private stakeholders. | To enhance accessibility and engagement, this activity will involve transforming the financial roadmap into an interactive digital format. The digital roadmap will include user-friendly navigation features, visualizations of key data, and links to supporting resources. It will be disseminated through online platforms and shared with public and private stakeholders to facilitate its use in decision-making and investment planning. | Producing and distributing communications materials | null | null | UNDP | Panama | Panama | null | 6/1/2026 | 9/1/2026 | Meeting report | null | null | null | 3.2 | Activity 3.2.3Create an interactive digital roadmap for dissemination to public and private stakeholders. | Output 3.2 Draft roadmap of financial intruments | 3.2.3Create an interactive digital roadmap for dissemination to public and private stakeholders. | PA-24-003/3.2.3 | PA-24-003/3.2.3Create an interactive digital roadmap for dissemination to public and private stakeholders. | PA-24-003/3.2 Draft roadmap of financial intruments | Activity | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 3.2 | Draft roadmap of financial intruments | A draft roadmap for financial instruments in organic waste management will be developed. This roadmap will be based on the findings of the previous evaluations and workshops, tailoring financial tools to the specific needs of the identified projects. It will include a detailed assessment of existing financial mechanisms and propose new ones that address key challenges and opportunities. The roadmap will guide the government and private sector in mobilizing resources for the sustainable implementation of organic waste management projects. | 3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Number of plans, policies, laws, or regulations drafted or updated | 1 | 1 plan drafted or updated. | UNDP | Panama | Financial institutions and government agencies. | Provide actionable steps for financing organic waste projects. | Policy, regulation or other guideline | 5/1/2026 12:00:00 AM | 9/1/2026 | Available in English or other agreed UN language, and grammatically correct + English summary Involvement of the beneficiary government throughout the development process, for example through consultation meetings Involvement of the CCAC focal point Agreement to, or acknowledgement of, the product presented by the beneficiary government (at the appropriate level) and the CCAC Secretariat | 3.2 Draft roadmap of financial intruments | Output 3.2 Draft roadmap of financial intruments | Outcome 3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | PA-24-003/3.2 | PA-24-003/3.2 Draft roadmap of financial intruments | Output | PA-24-003/3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 3 | A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Workshops under Output 2 will convene key stakeholders, including representatives from the financial sector, local and national governments, and private entities, to explore and design financial mechanisms aligned with Panama's national goals. These workshops will focus on evaluating policies to mitigate Short-Lived Climate Pollutants (SLCPs) from organic waste and identifying opportunities for financial innovation. The outcome will include the creation of a draft roadmap detailing necessary financial instruments and resources tailored to the unique needs and characteristics of organic waste projects in Panama. This roadmap will serve as a foundation for developing long-term financing strategies and a comprehensive resource mobilization plan, fostering sustainable investment and alignment with national and global sustainability goals. | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 1 | 1 roadmap | 3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Outcome 3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | PA-24-003/3. | PA-24-003/3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Outcome | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003 | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | UNDP () | UNDP ()
4.1.1Organize training workshops for government officials and market stakeholders on SLCP mitigation strategies, offering flexible schedules and childcare options to ensure women’s participation. | Contractual Services | 4.1.1-1 | Communications materials | UNDP | null | CCAC | 2 | Workshop | 2000 | 4000 | 1000 | 2000 | 1000 | Yes. | 4/1/2001 | Expenditure 4.1.1-1 Communications materials | Activity 4.1.1Organize training workshops for government officials and market stakeholders on SLCP mitigation strategies, offering flexible schedules and childcare options to ensure women’s participation. | UNDP () | PA-24-003/4.1.1-1 | PA-24-003/4.1.1-1 Communications materials | PA-24-003/4.1.1Organize training workshops for government officials and market stakeholders on SLCP mitigation strategies, offering flexible schedules and childcare options to ensure women’s participation. | Expenditure | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 4.1 Capacity building and technical assistance | 4.1.1 | 4.1.1Organize training workshops for government officials and market stakeholders on SLCP mitigation strategies, offering flexible schedules and childcare options to ensure women’s participation. | This activity will involve organizing a series of capacity-building workshops aimed at enhancing the technical knowledge of government officials, market stakeholders, and other relevant actors on SLCP mitigation strategies. The workshops will cover topics such as best practices in organic waste management, SLCP reduction, and the integration of gender-sensitive approaches. To ensure equal participation, flexible schedules and childcare options will be provided for women participants. Training sessions will be delivered both in-person and virtually to maximize accessibility. | Developing and/or delivering training | null | null | UNDP | Panama | Panama | null | 6/1/2026 | 12/1/2026 | Training materials | null | null | null | 4.1 | Activity 4.1.1Organize training workshops for government officials and market stakeholders on SLCP mitigation strategies, offering flexible schedules and childcare options to ensure women’s participation. | Output 4.1 Capacity building and technical assistance | 4.1.1Organize training workshops for government officials and market stakeholders on SLCP mitigation strategies, offering flexible schedules and childcare options to ensure women’s participation. | PA-24-003/4.1.1 | PA-24-003/4.1.1Organize training workshops for government officials and market stakeholders on SLCP mitigation strategies, offering flexible schedules and childcare options to ensure women’s participation. | PA-24-003/4.1 Capacity building and technical assistance | Activity | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 4.1 | Capacity building and technical assistance | Capacity building workshops and Technical Assistance for stakeholders working on organic waste management. These workshops will focus on enhancing the participants understanding of project development, cost-benefit analysis, and SLCP mitigation strategies. Training materials will be tailored to Panama's context, particulary focusing on the MERCA market in Panama City. The goal is to equip governemnt entities and other stakeholders with the knowledge and tools to implement effective organic waste management projects, while promoting collaboration and knowledge-sharing across sectors. | 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Number of public events, webinars, or side events hosted | 4 | 4 workshops conducted with government entities. | UNDP | Panama | Local governments, private sector, and NGOs. | stakeholders with skills to implement SLCP reduction strategies. | Meeting report, Training materials | 2/1/2027 12:00:00 AM | 6/1/2027 | Agenda and event plan cleared by the beneficiary and/or CCAC Secretariat Event is promoted & details about event shared with CCAC at least one week in advance to support promotion CCAC is recognised (logo and as part of the agenda) Uses CCAC presentation template (where relevant / as an option) | 4.1 Capacity building and technical assistance | Output 4.1 Capacity building and technical assistance | Outcome 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | PA-24-003/4.1 | PA-24-003/4.1 Capacity building and technical assistance | Output | PA-24-003/4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 4 | The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | The project aims to strengthen the government’s capacity to evaluate and monitor organic waste management projects effectively. By developing targeted training programs and fostering collaboration with key stakeholders, the project ensures that newly acquired knowledge and skills are applied in practice. Knowledge-sharing platforms will play a pivotal role in disseminating results, lessons learned, and case studies while supporting the development of training materials and fostering local expertise. These efforts aim to facilitate the sustainable implementation of Short-Lived Climate Pollutant (SLCP) mitigation measures. The project assumes that by enhancing technical capacity, the government will be better equipped to design and implement effective policies and measures, creating a strong foundation for the long-term success of SLCP reduction initiatives linked to organic waste management. | Number of government entities with a demonstrated improved capacity for SLCP action | 20 | 20 government entities with improved capacity for SLCP action. | 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Outcome 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | PA-24-003/4. | PA-24-003/4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Outcome | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003 | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | UNDP () | UNDP ()
4.1.2Develop training materials tailored to Panama’s context, including gender-sensitive approaches to waste management. | Contractual Services | 4.1.2-1 | Communications specialist | UNDP | null | CCAC | 1 | Communications toolkits | 25000 | 25000 | null | 10000 | 15000 | Yes. | 4/1/2002 | Expenditure 4.1.2-1 Communications specialist | Activity 4.1.2Develop training materials tailored to Panama’s context, including gender-sensitive approaches to waste management. | UNDP () | PA-24-003/4.1.2-1 | PA-24-003/4.1.2-1 Communications specialist | PA-24-003/4.1.2Develop training materials tailored to Panama’s context, including gender-sensitive approaches to waste management. | Expenditure | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 4.1 Capacity building and technical assistance | 4.1.2 | 4.1.2Develop training materials tailored to Panama’s context, including gender-sensitive approaches to waste management. | This activity will focus on designing and developing training materials that are tailored to Panama’s specific context in waste management and SLCP mitigation. The materials will include presentations, handouts, case studies, and practical exercises that address local challenges and opportunities. Gender-sensitive approaches will be integrated into the materials to highlight the role of women in waste management and promote inclusive practices. These resources will be made available in both print and digital formats to ensure broad accessibility. | Producing and distributing communications materials | null | null | UNDP | Panama | Panama | null | 6/1/2026 | 9/1/2026 | Tool | null | null | null | 4.1 | Activity 4.1.2Develop training materials tailored to Panama’s context, including gender-sensitive approaches to waste management. | Output 4.1 Capacity building and technical assistance | 4.1.2Develop training materials tailored to Panama’s context, including gender-sensitive approaches to waste management. | PA-24-003/4.1.2 | PA-24-003/4.1.2Develop training materials tailored to Panama’s context, including gender-sensitive approaches to waste management. | PA-24-003/4.1 Capacity building and technical assistance | Activity | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 4.1 | Capacity building and technical assistance | Capacity building workshops and Technical Assistance for stakeholders working on organic waste management. These workshops will focus on enhancing the participants understanding of project development, cost-benefit analysis, and SLCP mitigation strategies. Training materials will be tailored to Panama's context, particulary focusing on the MERCA market in Panama City. The goal is to equip governemnt entities and other stakeholders with the knowledge and tools to implement effective organic waste management projects, while promoting collaboration and knowledge-sharing across sectors. | 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Number of public events, webinars, or side events hosted | 4 | 4 workshops conducted with government entities. | UNDP | Panama | Local governments, private sector, and NGOs. | stakeholders with skills to implement SLCP reduction strategies. | Meeting report, Training materials | 2/1/2027 12:00:00 AM | 6/1/2027 | Agenda and event plan cleared by the beneficiary and/or CCAC Secretariat Event is promoted & details about event shared with CCAC at least one week in advance to support promotion CCAC is recognised (logo and as part of the agenda) Uses CCAC presentation template (where relevant / as an option) | 4.1 Capacity building and technical assistance | Output 4.1 Capacity building and technical assistance | Outcome 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | PA-24-003/4.1 | PA-24-003/4.1 Capacity building and technical assistance | Output | PA-24-003/4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 4 | The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | The project aims to strengthen the government’s capacity to evaluate and monitor organic waste management projects effectively. By developing targeted training programs and fostering collaboration with key stakeholders, the project ensures that newly acquired knowledge and skills are applied in practice. Knowledge-sharing platforms will play a pivotal role in disseminating results, lessons learned, and case studies while supporting the development of training materials and fostering local expertise. These efforts aim to facilitate the sustainable implementation of Short-Lived Climate Pollutant (SLCP) mitigation measures. The project assumes that by enhancing technical capacity, the government will be better equipped to design and implement effective policies and measures, creating a strong foundation for the long-term success of SLCP reduction initiatives linked to organic waste management. | Number of government entities with a demonstrated improved capacity for SLCP action | 20 | 20 government entities with improved capacity for SLCP action. | 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Outcome 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | PA-24-003/4. | PA-24-003/4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Outcome | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003 | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | UNDP () | UNDP ()
4.1.2Develop training materials tailored to Panama’s context, including gender-sensitive approaches to waste management. | Contractual Services | 4.1.2-2 | communication materials | UNDP | null | CCAC | 1 | Communications consultant | 20686 | 20686 | null | 10343 | 10343 | Yes. | 4/1/2002 | Expenditure 4.1.2-2 communication materials | Activity 4.1.2Develop training materials tailored to Panama’s context, including gender-sensitive approaches to waste management. | UNDP () | PA-24-003/4.1.2-2 | PA-24-003/4.1.2-2 communication materials | PA-24-003/4.1.2Develop training materials tailored to Panama’s context, including gender-sensitive approaches to waste management. | Expenditure | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 4.1 Capacity building and technical assistance | 4.1.2 | 4.1.2Develop training materials tailored to Panama’s context, including gender-sensitive approaches to waste management. | This activity will focus on designing and developing training materials that are tailored to Panama’s specific context in waste management and SLCP mitigation. The materials will include presentations, handouts, case studies, and practical exercises that address local challenges and opportunities. Gender-sensitive approaches will be integrated into the materials to highlight the role of women in waste management and promote inclusive practices. These resources will be made available in both print and digital formats to ensure broad accessibility. | Producing and distributing communications materials | null | null | UNDP | Panama | Panama | null | 6/1/2026 | 9/1/2026 | Tool | null | null | null | 4.1 | Activity 4.1.2Develop training materials tailored to Panama’s context, including gender-sensitive approaches to waste management. | Output 4.1 Capacity building and technical assistance | 4.1.2Develop training materials tailored to Panama’s context, including gender-sensitive approaches to waste management. | PA-24-003/4.1.2 | PA-24-003/4.1.2Develop training materials tailored to Panama’s context, including gender-sensitive approaches to waste management. | PA-24-003/4.1 Capacity building and technical assistance | Activity | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 4.1 | Capacity building and technical assistance | Capacity building workshops and Technical Assistance for stakeholders working on organic waste management. These workshops will focus on enhancing the participants understanding of project development, cost-benefit analysis, and SLCP mitigation strategies. Training materials will be tailored to Panama's context, particulary focusing on the MERCA market in Panama City. The goal is to equip governemnt entities and other stakeholders with the knowledge and tools to implement effective organic waste management projects, while promoting collaboration and knowledge-sharing across sectors. | 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Number of public events, webinars, or side events hosted | 4 | 4 workshops conducted with government entities. | UNDP | Panama | Local governments, private sector, and NGOs. | stakeholders with skills to implement SLCP reduction strategies. | Meeting report, Training materials | 2/1/2027 12:00:00 AM | 6/1/2027 | Agenda and event plan cleared by the beneficiary and/or CCAC Secretariat Event is promoted & details about event shared with CCAC at least one week in advance to support promotion CCAC is recognised (logo and as part of the agenda) Uses CCAC presentation template (where relevant / as an option) | 4.1 Capacity building and technical assistance | Output 4.1 Capacity building and technical assistance | Outcome 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | PA-24-003/4.1 | PA-24-003/4.1 Capacity building and technical assistance | Output | PA-24-003/4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 4 | The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | The project aims to strengthen the government’s capacity to evaluate and monitor organic waste management projects effectively. By developing targeted training programs and fostering collaboration with key stakeholders, the project ensures that newly acquired knowledge and skills are applied in practice. Knowledge-sharing platforms will play a pivotal role in disseminating results, lessons learned, and case studies while supporting the development of training materials and fostering local expertise. These efforts aim to facilitate the sustainable implementation of Short-Lived Climate Pollutant (SLCP) mitigation measures. The project assumes that by enhancing technical capacity, the government will be better equipped to design and implement effective policies and measures, creating a strong foundation for the long-term success of SLCP reduction initiatives linked to organic waste management. | Number of government entities with a demonstrated improved capacity for SLCP action | 20 | 20 government entities with improved capacity for SLCP action. | 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Outcome 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | PA-24-003/4. | PA-24-003/4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Outcome | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003 | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | UNDP () | UNDP ()
4.1.3Establish a knowledge-sharing platform for continuous capacity-building, | Contractual Services | 4.1.2-1 | communication materials | UNDP | null | CCAC | 1 | lesson learned, | 16000 | 16000 | null | 16000 | null | Yes. | 4/1/2003 | Expenditure 4.1.2-1 communication materials | Activity 4.1.3Establish a knowledge-sharing platform for continuous capacity-building, | UNDP () | PA-24-003/4.1.2-1 | PA-24-003/4.1.2-1 communication materials | PA-24-003/4.1.3Establish a knowledge-sharing platform for continuous capacity-building, | Expenditure | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 4.1 Capacity building and technical assistance | 4.1.3 | 4.1.3Establish a knowledge-sharing platform for continuous capacity-building, | This activity involves creating a knowledge-sharing platform to provide ongoing support and capacity-building for stakeholders engaged in SLCP mitigation. The platform will feature resources such as training materials, case studies, and interactive forums for peer learning. Best practices and lessons learned from both women and men will be documented and showcased to promote gender-inclusive approaches. The platform will be accessible online, ensuring that stakeholders from across Panama can benefit from the resources and collaborate on shared goals. | Producing and distributing communications materials | null | null | UNDP | Panama | Panama | null | 12/1/2026 | 6/1/2027 | Work plan | null | null | null | 4.1 | Activity 4.1.3Establish a knowledge-sharing platform for continuous capacity-building, | Output 4.1 Capacity building and technical assistance | 4.1.3Establish a knowledge-sharing platform for continuous capacity-building, | PA-24-003/4.1.3 | PA-24-003/4.1.3Establish a knowledge-sharing platform for continuous capacity-building, | PA-24-003/4.1 Capacity building and technical assistance | Activity | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 4.1 | Capacity building and technical assistance | Capacity building workshops and Technical Assistance for stakeholders working on organic waste management. These workshops will focus on enhancing the participants understanding of project development, cost-benefit analysis, and SLCP mitigation strategies. Training materials will be tailored to Panama's context, particulary focusing on the MERCA market in Panama City. The goal is to equip governemnt entities and other stakeholders with the knowledge and tools to implement effective organic waste management projects, while promoting collaboration and knowledge-sharing across sectors. | 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Number of public events, webinars, or side events hosted | 4 | 4 workshops conducted with government entities. | UNDP | Panama | Local governments, private sector, and NGOs. | stakeholders with skills to implement SLCP reduction strategies. | Meeting report, Training materials | 2/1/2027 12:00:00 AM | 6/1/2027 | Agenda and event plan cleared by the beneficiary and/or CCAC Secretariat Event is promoted & details about event shared with CCAC at least one week in advance to support promotion CCAC is recognised (logo and as part of the agenda) Uses CCAC presentation template (where relevant / as an option) | 4.1 Capacity building and technical assistance | Output 4.1 Capacity building and technical assistance | Outcome 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | PA-24-003/4.1 | PA-24-003/4.1 Capacity building and technical assistance | Output | PA-24-003/4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 4 | The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | The project aims to strengthen the government’s capacity to evaluate and monitor organic waste management projects effectively. By developing targeted training programs and fostering collaboration with key stakeholders, the project ensures that newly acquired knowledge and skills are applied in practice. Knowledge-sharing platforms will play a pivotal role in disseminating results, lessons learned, and case studies while supporting the development of training materials and fostering local expertise. These efforts aim to facilitate the sustainable implementation of Short-Lived Climate Pollutant (SLCP) mitigation measures. The project assumes that by enhancing technical capacity, the government will be better equipped to design and implement effective policies and measures, creating a strong foundation for the long-term success of SLCP reduction initiatives linked to organic waste management. | Number of government entities with a demonstrated improved capacity for SLCP action | 20 | 20 government entities with improved capacity for SLCP action. | 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Outcome 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | PA-24-003/4. | PA-24-003/4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Outcome | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003 | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | UNDP () | UNDP ()
4.1.4Project Management and Administration | Operating and Other Direct Costs | 4.1.3-1 | Rental Offices | UNDP | null | Co-funding | 1 | null | 15000 | 15000 | 7500 | 7500 | null | Yes. | 4/1/2004 | Expenditure 4.1.3-1 Rental Offices | Activity 4.1.4Project Management and Administration | UNDP () | PA-24-003/4.1.3-1 | PA-24-003/4.1.3-1 Rental Offices | PA-24-003/4.1.4Project Management and Administration | Expenditure | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 4.1 Capacity building and technical assistance | 4.1.4 | 4.1.4Project Management and Administration | This activity will ensure the efficient management of the project, covering general operational costs, monitoring, financial and administrative reporting, as well as overall project coordination. It will also include expenses related to technical supervision and contract management. | Other | null | null | UNDP | Panama | Panama | null | 6/1/2025 | 6/1/2027 | null | null | null | null | 4.1 | Activity 4.1.4Project Management and Administration | Output 4.1 Capacity building and technical assistance | 4.1.4Project Management and Administration | PA-24-003/4.1.4 | PA-24-003/4.1.4Project Management and Administration | PA-24-003/4.1 Capacity building and technical assistance | Activity | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 4.1 | Capacity building and technical assistance | Capacity building workshops and Technical Assistance for stakeholders working on organic waste management. These workshops will focus on enhancing the participants understanding of project development, cost-benefit analysis, and SLCP mitigation strategies. Training materials will be tailored to Panama's context, particulary focusing on the MERCA market in Panama City. The goal is to equip governemnt entities and other stakeholders with the knowledge and tools to implement effective organic waste management projects, while promoting collaboration and knowledge-sharing across sectors. | 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Number of public events, webinars, or side events hosted | 4 | 4 workshops conducted with government entities. | UNDP | Panama | Local governments, private sector, and NGOs. | stakeholders with skills to implement SLCP reduction strategies. | Meeting report, Training materials | 2/1/2027 12:00:00 AM | 6/1/2027 | Agenda and event plan cleared by the beneficiary and/or CCAC Secretariat Event is promoted & details about event shared with CCAC at least one week in advance to support promotion CCAC is recognised (logo and as part of the agenda) Uses CCAC presentation template (where relevant / as an option) | 4.1 Capacity building and technical assistance | Output 4.1 Capacity building and technical assistance | Outcome 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | PA-24-003/4.1 | PA-24-003/4.1 Capacity building and technical assistance | Output | PA-24-003/4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | 4 | The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | The project aims to strengthen the government’s capacity to evaluate and monitor organic waste management projects effectively. By developing targeted training programs and fostering collaboration with key stakeholders, the project ensures that newly acquired knowledge and skills are applied in practice. Knowledge-sharing platforms will play a pivotal role in disseminating results, lessons learned, and case studies while supporting the development of training materials and fostering local expertise. These efforts aim to facilitate the sustainable implementation of Short-Lived Climate Pollutant (SLCP) mitigation measures. The project assumes that by enhancing technical capacity, the government will be better equipped to design and implement effective policies and measures, creating a strong foundation for the long-term success of SLCP reduction initiatives linked to organic waste management. | Number of government entities with a demonstrated improved capacity for SLCP action | 20 | 20 government entities with improved capacity for SLCP action. | 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Outcome 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | PA-24-003/4. | PA-24-003/4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Outcome | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003 | Waste | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | UNDP () | UNDP ()
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## INT-Pivots (hidden)
|  |  | NARRATIVE REPORT + DASHBOARD | [13 empty] | OUTPUTS | [20 empty] | Expenditure (uncheck all but expenditure) | [10 empty] | Project title | OUTPUTS | [13 empty] | Activities
|  |  | Agreement filter | All | [12 empty] | Agreement filter | All | [12 empty] | OUTCOMES REPORTING | [6 empty] | Agreement filter | All | [10 empty] | Agreement filter | All | [12 empty] | Agreement filter | All
Selected agreement |  |  | Level | (Multiple Items) | [12 empty] | Level | Output | [19 empty] | Level | Expenditure | [10 empty] | Level | Output | [12 empty] | Level | Activity
Agreement | Agreement number | Count of Implementer | Unique code | Component | Indicator | Target | Unit | Date | Description | Acceptance criteria | Project | Agreement | Sector | Beneficiaries | Other beneficiaries | Delivery type | Unique code | Component | Indicator | Target | Unit | Date | Description | Acceptance criteria | Project | Agreement | Sector | Beneficiaries | Other beneficiaries | Delivery type | Component | Indicator | Target | Unit | Unique code | Project | Sector | Expenditure related activity | Indicator | Budget SOURCE OF FUNDING | Project | Sector | Agreement | Unique code | Sum of TOTAL COST | Sum of YEAR 1 COST ($US) | Sum of YEAR 2 COST ($US) | Sum of YEAR 3 COST ($US) | Project | Unique code | Component | Indicator | Target | Unit | Date | Description | Acceptance criteria | Project | Agreement | Sector | Beneficiaries | Other beneficiaries | Delivery type | Unique code | Component | Indicator | Target | Unit | Date | Description | Acceptance criteria | Project | Agreement | Sector | Beneficiaries | Other beneficiaries | Delivery type
UNDP () | (blank) | 67 | PA-24-003/1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Outcome 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Number of government entities with a demonstrated improved capacity for SLCP action | 4 | 4 government entities with improved capacity for SLCP action. | (blank) | The project’s outputs will identify and develop innovative and practical treatment options and solutions for managing organic waste, generating critical data on decentralized infrastructure needs, such as composting plants, biodigesters, food and material recovery, and waste reduction technologies. These solutions will integrate circular economy principles, prioritize locally based consultants with local language capabilities, and actively engage the private sector through targeted knowledge exchange initiatives. By leveraging activities such as pre-feasibility studies, infrastructure estimates, and actionable recommendations, the project will equip the government with comprehensive knowledge to make informed decisions on effective and sustainable waste management solutions. This enhanced knowledge is expected to contribute to significant environmental, economic, and social benefits, including reduced food waste, methane emissions, and support for national and international sustainability goals. The projec | (blank) | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | (blank) | Waste | (blank) | (blank) | (blank) | PA-24-003/1.1 Pre-feasibility studies for organic waste treatment options | Output 1.1 Pre-feasibility studies for organic waste treatment options | Number of plans, policies, laws, or regulations drafted or updated | 1 | 1 pre-feasibility study report developed. | 2025-12-01 | Pre-feasibility studies for organic waste treatment options conducted in Panama City. These studies will evaluate the technical and economic feasibility of potential treatment technologies/solutions, such as composting, anaerobic digestion, and other technologies to manage organic waste effectively. The goal is to identify the most viable treatment methods that support waste diversion, reduce methane emissions, and promote circular economies. The studies will provide critical data and analysis on costs, environmental benefits, and operational feasibility, laying the groundwork for informed decision-making and future investments in sustainable organic waste management infrastructure, ensuring alignment with national policies and international commitments. | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | National and local governments responsible for waste management. | Research or study | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | Activity 1.1.1 Conduct consultations with government entities, MERCA representatives, and private sector players, ensuring equal participation of women and men, to define treatment options. | Staff and Other Personnel Costs | CCAC | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste | UNDP () | PA-24-003/1.1.1-1 Pre-feasibility studies for organic waste visit different market and landfills | 15000 | 15000 | "" | "" | (blank) | PA-24-003/1.1 Pre-feasibility studies for organic waste treatment options | Output 1.1 Pre-feasibility studies for organic waste treatment options | Number of plans, policies, laws, or regulations drafted or updated | 1 | 1 pre-feasibility study report developed. | 2025-12-01 | Pre-feasibility studies for organic waste treatment options conducted in Panama City. These studies will evaluate the technical and economic feasibility of potential treatment technologies/solutions, such as composting, anaerobic digestion, and other technologies to manage organic waste effectively. The goal is to identify the most viable treatment methods that support waste diversion, reduce methane emissions, and promote circular economies. The studies will provide critical data and analysis on costs, environmental benefits, and operational feasibility, laying the groundwork for informed decision-making and future investments in sustainable organic waste management infrastructure, ensuring alignment with national policies and international commitments. | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | National and local governments responsible for waste management. | Research or study | PA-24-003/1.1.1 Conduct consultations with government entities, MERCA representatives, and private sector players, ensuring equal participation of women and men, to define treatment options. | Activity 1.1.1 Conduct consultations with government entities, MERCA representatives, and private sector players, ensuring equal participation of women and men, to define treatment options. | Organising, holding, or participating in a meeting or event | null | null | 2025-09-01 | This activity will involve organizing consultations with key stakeholders to identify feasible organic waste treatment technologies. These sessions will include representatives from government entities, MERCA, private sector players, and NGOs, with a focus on ensuring gender-balanced participation. The consultations will evaluate existing waste management practices, discuss potential treatment solutions (e.g., composting, biodigesters), and collect stakeholder input to define the best approaches. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Policy, regulation or other guideline
|  |  | PA-24-003/1.1 Pre-feasibility studies for organic waste treatment options | Output 1.1 Pre-feasibility studies for organic waste treatment options | Number of plans, policies, laws, or regulations drafted or updated | 1 | 1 pre-feasibility study report developed. | 2025-12-01 | Pre-feasibility studies for organic waste treatment options conducted in Panama City. These studies will evaluate the technical and economic feasibility of potential treatment technologies/solutions, such as composting, anaerobic digestion, and other technologies to manage organic waste effectively. The goal is to identify the most viable treatment methods that support waste diversion, reduce methane emissions, and promote circular economies. The studies will provide critical data and analysis on costs, environmental benefits, and operational feasibility, laying the groundwork for informed decision-making and future investments in sustainable organic waste management infrastructure, ensuring alignment with national policies and international commitments. | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | National and local governments responsible for waste management. | Research or study | PA-24-003/1.2 Estimates of decentralized infraestructure supporting diverted organic waste | Output 1.2 Estimates of decentralized infraestructure supporting diverted organic waste | Number of SLCP assessments, emissions inventories, and other emissions datasets produced | 4 | 4 SLCP assessments, emissions inventories, or other emissions datasets produced. | 2025-12-01 | Estimates of decentralized infrastructure supporting organic waste diversion, including materials separation and recovery centers, black soldier fly infrastructure, and compositing plants. These systems will promote a circular economy by processing organic waste closer to its source, reducing transportation costs and emissions. The estimates will determine the scale, location, capacity and investment requirements for these facilities, providing a strategic roadmap for developing an efficient, sustainable waste management network. This will enable the government to plan effectively for organic waste management. | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | Municipalities and local governments. | Research or study | Outcome 1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Number of government entities with a demonstrated improved capacity for SLCP action | 4 | 4 government entities with improved capacity for SLCP action. | PA-24-003/1. The Government of Panama has increased knowledge on opportunities and options for organic waste diversion including their positive impacts by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste | Activity 1.1.1 Conduct consultations with government entities, MERCA representatives, and private sector players, ensuring equal participation of women and men, to define treatment options. | Travel | CCAC | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste | UNDP () | PA-24-003/1.1.1-2 Waste Management and Infrastructure Consultant | 2000 | 2000 | "" | "" | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | PA-24-003/1.2 Estimates of decentralized infraestructure supporting diverted organic waste | Output 1.2 Estimates of decentralized infraestructure supporting diverted organic waste | Number of SLCP assessments, emissions inventories, and other emissions datasets produced | 4 | 4 SLCP assessments, emissions inventories, or other emissions datasets produced. | 2025-12-01 | Estimates of decentralized infrastructure supporting organic waste diversion, including materials separation and recovery centers, black soldier fly infrastructure, and compositing plants. These systems will promote a circular economy by processing organic waste closer to its source, reducing transportation costs and emissions. The estimates will determine the scale, location, capacity and investment requirements for these facilities, providing a strategic roadmap for developing an efficient, sustainable waste management network. This will enable the government to plan effectively for organic waste management. | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | Municipalities and local governments. | Research or study | PA-24-003/1.1.2 Evaluate technical and economic feasibility for technologies like composting and anaerobic digestion, including an analysis of how these benefit women-led businesses and communities. | Activity 1.1.2 Evaluate technical and economic feasibility for technologies like composting and anaerobic digestion, including an analysis of how these benefit women-led businesses and communities. | Research, data collection, and/or report writing | null | null | 2025-12-01 | This activity focuses on conducting technical and economic feasibility studies for organic waste treatment technologies. The evaluation will assess factors such as cost efficiency, scalability, and environmental impact. Special attention will be given to understanding how these technologies can create opportunities for women-led businesses and promote inclusive economic benefits in local communities. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Research or study
|  |  | PA-24-003/1.1.1 Conduct consultations with government entities, MERCA representatives, and private sector players, ensuring equal participation of women and men, to define treatment options. | Activity 1.1.1 Conduct consultations with government entities, MERCA representatives, and private sector players, ensuring equal participation of women and men, to define treatment options. | Organising, holding, or participating in a meeting or event | null | null | 2025-09-01 | This activity will involve organizing consultations with key stakeholders to identify feasible organic waste treatment technologies. These sessions will include representatives from government entities, MERCA, private sector players, and NGOs, with a focus on ensuring gender-balanced participation. The consultations will evaluate existing waste management practices, discuss potential treatment solutions (e.g., composting, biodigesters), and collect stakeholder input to define the best approaches. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Policy, regulation or other guideline | PA-24-003/1.3 Recommendations for alternative/ complementary infraestrucutre | Output 1.3 Recommendations for alternative/ complementary infraestrucutre | Number of SLCP knowledge resources or tools produced | 1 | 1 SLCP knowledge resource or tool produced. | 2026-09-01 | Recommendations for alternative and complementary infrastructure to support organic waste diversion and fosters circular economies. The proposed infraestructure aims to enhance existing waste management systems, such as advanced compositing technologies, anaerobic digestion, and resource recovery facilities. These recommendation will serve as a blueprint for the government to integreate into its organic waste management strategy, with focus on creating value to the organic waste, lowers emissions, reducing landfill dependency, and promoting environmental, economic and social benefits, achieve the goals establishd in the NDC's and roadmap for the Mitigation of SLCPs in Panama. The findings will guide future investements and policies for an integrated waste managemente approach | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | National and local governments. | Research or study | Outcome 2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 5 | 5 action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures | PA-24-003/2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste | Activity 1.1.2 Evaluate technical and economic feasibility for technologies like composting and anaerobic digestion, including an analysis of how these benefit women-led businesses and communities. | Staff and Other Personnel Costs | CCAC | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste | UNDP () | PA-24-003/1.1.2-1 Waste Management and Infrastructure Consultant | 20000 | 20000 | "" | "" |  | PA-24-003/1.3 Recommendations for alternative/ complementary infraestrucutre | Output 1.3 Recommendations for alternative/ complementary infraestrucutre | Number of SLCP knowledge resources or tools produced | 1 | 1 SLCP knowledge resource or tool produced. | 2026-09-01 | Recommendations for alternative and complementary infrastructure to support organic waste diversion and fosters circular economies. The proposed infraestructure aims to enhance existing waste management systems, such as advanced compositing technologies, anaerobic digestion, and resource recovery facilities. These recommendation will serve as a blueprint for the government to integreate into its organic waste management strategy, with focus on creating value to the organic waste, lowers emissions, reducing landfill dependency, and promoting environmental, economic and social benefits, achieve the goals establishd in the NDC's and roadmap for the Mitigation of SLCPs in Panama. The findings will guide future investements and policies for an integrated waste managemente approach | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | National and local governments. | Research or study | PA-24-003/1.2.1 Map existing and potential decentralized infrastructure for waste management, engaging municipalities and local organizations to provide on-ground insights. | Activity 1.2.1 Map existing and potential decentralized infrastructure for waste management, engaging municipalities and local organizations to provide on-ground insights. | Research, data collection, and/or report writing | null | null | 2025-09-01 | This activity involves mapping current and potential decentralized infrastructure for organic waste management, such as composting plants, biodigesters, and material recovery facilities. Municipal governments and local organizations will be actively engaged to ensure accurate data collection and context-specific recommendations. The mapping process will also consider socio-economic and environmental factors to identify priority areas for infrastructure development. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Research or study
|  |  | PA-24-003/1.1.2 Evaluate technical and economic feasibility for technologies like composting and anaerobic digestion, including an analysis of how these benefit women-led businesses and communities. | Activity 1.1.2 Evaluate technical and economic feasibility for technologies like composting and anaerobic digestion, including an analysis of how these benefit women-led businesses and communities. | Research, data collection, and/or report writing | null | null | 2025-12-01 | This activity focuses on conducting technical and economic feasibility studies for organic waste treatment technologies. The evaluation will assess factors such as cost efficiency, scalability, and environmental impact. Special attention will be given to understanding how these technologies can create opportunities for women-led businesses and promote inclusive economic benefits in local communities. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Research or study | PA-24-003/1.4 Report indentifying necessary infraestructure and investment to support organic waste management | Output 1.4 Report indentifying necessary infraestructure and investment to support organic waste management | Number of plans, policies, laws, or regulations drafted or updated | 1 | 1 plan, policy, law, or regulation drafted or updated. | 2026-12-01 | A report identifying necessary infrastructure and investment to support organic waste management (recovery of organic waste, production of biofertilizer and energy, savings by avoiding waste, redistribution of food that otherwise would be discarded to people in need). The report will cover key areas such as the recovery of organic waste, the production of biofertilizers and renewable enerty, and economic savings from waste reduction. It will also highlight the potential for redistributing surplus food to people in need, preventing it from being discarded. By identifying these necessary components, the report will serve as a strategic roadmap for decision-makers to prioritize investements and implementing sustainable solutions for organic waste management. | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | National and local governments, investors. | Research or study | Outcome 3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 1 | 1 roadmap | PA-24-003/3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste | Activity 1.2.1 Map existing and potential decentralized infrastructure for waste management, engaging municipalities and local organizations to provide on-ground insights. | Staff and Other Personnel Costs | CCAC | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste | UNDP () | PA-24-003/1.2.1-1 Field visits for data collection | 10000 | "" | 10000 | "" |  | PA-24-003/1.4 Report indentifying necessary infraestructure and investment to support organic waste management | Output 1.4 Report indentifying necessary infraestructure and investment to support organic waste management | Number of plans, policies, laws, or regulations drafted or updated | 1 | 1 plan, policy, law, or regulation drafted or updated. | 2026-12-01 | A report identifying necessary infrastructure and investment to support organic waste management (recovery of organic waste, production of biofertilizer and energy, savings by avoiding waste, redistribution of food that otherwise would be discarded to people in need). The report will cover key areas such as the recovery of organic waste, the production of biofertilizers and renewable enerty, and economic savings from waste reduction. It will also highlight the potential for redistributing surplus food to people in need, preventing it from being discarded. By identifying these necessary components, the report will serve as a strategic roadmap for decision-makers to prioritize investements and implementing sustainable solutions for organic waste management. | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | National and local governments, investors. | Research or study | PA-24-003/1.2.2 Conduct site visits and surveys, collecting gender-disaggregated data to ensure proposed infrastructure meets the needs of both genders. | Activity 1.2.2 Conduct site visits and surveys, collecting gender-disaggregated data to ensure proposed infrastructure meets the needs of both genders. | Research, data collection, and/or report writing | null | null | 2025-12-01 | This activity will include field visits and stakeholder surveys to collect data on waste management infrastructure needs. Surveys will include gender-disaggregated data to ensure that proposed infrastructure supports both men and women, particularly those in waste-related informal sectors. The findings will inform inclusive and equitable infrastructure planning. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Research or study
|  |  | PA-24-003/1.2 Estimates of decentralized infraestructure supporting diverted organic waste | Output 1.2 Estimates of decentralized infraestructure supporting diverted organic waste | Number of SLCP assessments, emissions inventories, and other emissions datasets produced | 4 | 4 SLCP assessments, emissions inventories, or other emissions datasets produced. | 2025-12-01 | Estimates of decentralized infrastructure supporting organic waste diversion, including materials separation and recovery centers, black soldier fly infrastructure, and compositing plants. These systems will promote a circular economy by processing organic waste closer to its source, reducing transportation costs and emissions. The estimates will determine the scale, location, capacity and investment requirements for these facilities, providing a strategic roadmap for developing an efficient, sustainable waste management network. This will enable the government to plan effectively for organic waste management. | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | Municipalities and local governments. | Research or study | PA-24-003/2.1 Identification of projects/inititives | Output 2.1 Identification of projects/inititives | Number of partnerships, associations, or campaigns launched to drive SLCP action | 5 | 5 Partnerships to drive SLCP action. | 2026-06-01 | Identification of at least 5-7 appropriate projects/initiatives with business potential in integral organic waste management, supported by the public and private sector based on the findings of output 1.3. and will be evaluated for their potential to contribute to a circular economy. The assesment will include project descriptions, expected outcomes, involved entities, and financing strategies. By identifying these opportunities, the project aims to establish a solid foundation for future investements and actions in organic waste management. | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | Investors, public and private stakeholders. | Research or study, Work plan | Outcome 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Number of government entities with a demonstrated improved capacity for SLCP action | 20 | 20 government entities with improved capacity for SLCP action. | PA-24-003/4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste | Activity 1.2.2 Conduct site visits and surveys, collecting gender-disaggregated data to ensure proposed infrastructure meets the needs of both genders. | Travel | CCAC | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste | UNDP () | PA-24-003/1.2.2-1 Waste Management and Infrastructure Consultant | 1800 | 1800 | "" | "" |  | PA-24-003/2.1 Identification of projects/inititives | Output 2.1 Identification of projects/inititives | Number of partnerships, associations, or campaigns launched to drive SLCP action | 5 | 5 Partnerships to drive SLCP action. | 2026-06-01 | Identification of at least 5-7 appropriate projects/initiatives with business potential in integral organic waste management, supported by the public and private sector based on the findings of output 1.3. and will be evaluated for their potential to contribute to a circular economy. The assesment will include project descriptions, expected outcomes, involved entities, and financing strategies. By identifying these opportunities, the project aims to establish a solid foundation for future investements and actions in organic waste management. | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | Investors, public and private stakeholders. | Research or study, Work plan | PA-24-003/1.2.3 Develop cost-benefit analyses, incorporating feedback from diverse stakeholders through an online webinar. | Activity 1.2.3 Develop cost-benefit analyses, incorporating feedback from diverse stakeholders through an online webinar. | Research, data collection, and/or report writing | null | null | 2026-03-01 | This activity will involve conducting cost-benefit analyses for proposed decentralized infrastructure options, such as composting and biodigesters. Stakeholders, including government officials, NGOs, and private sector representatives, will provide feedback through an interactive online webinar. The analysis will highlight economic, environmental, and social benefits, emphasizing SLCP mitigation and inclusion of marginalized groups. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Research or study
|  |  | PA-24-003/1.2.1 Map existing and potential decentralized infrastructure for waste management, engaging municipalities and local organizations to provide on-ground insights. | Activity 1.2.1 Map existing and potential decentralized infrastructure for waste management, engaging municipalities and local organizations to provide on-ground insights. | Research, data collection, and/or report writing | null | null | 2025-09-01 | This activity involves mapping current and potential decentralized infrastructure for organic waste management, such as composting plants, biodigesters, and material recovery facilities. Municipal governments and local organizations will be actively engaged to ensure accurate data collection and context-specific recommendations. The mapping process will also consider socio-economic and environmental factors to identify priority areas for infrastructure development. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Research or study | PA-24-003/2.2 Stakeholder Engagement and Strategic Financial Planning for Selected Projects | Output 2.2 Stakeholder Engagement and Strategic Financial Planning for Selected Projects | Number of partnerships, associations, or campaigns launched to drive SLCP action | 3 | 3 Associations launched to drive SLCP action. | 2026-09-01 | Stakeholders, including government agencies, private companies, and financial institutions, will be convened and engaged to select at least 3 priority projects/ initiatives for organic waste management. This process will focus on identifying potential funding sources and aligning stakeholders to support these initiatives. The selected projects will be developed into deteiled plans, including financial strategies and implementation pathways, ensuring coodinated efforts amog all stakeholders to advance sustainable waste management solution. | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | Investors, public and private stakeholders. | Work plan | [7 empty] | Activity 1.2.3 Develop cost-benefit analyses, incorporating feedback from diverse stakeholders through an online webinar. | Staff and Other Personnel Costs | CCAC | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste | UNDP () | PA-24-003/1.2.3-1 Waste Management and Infrastructure Consultant | 5000 | "" | 5000 | "" |  | PA-24-003/2.2 Stakeholder Engagement and Strategic Financial Planning for Selected Projects | Output 2.2 Stakeholder Engagement and Strategic Financial Planning for Selected Projects | Number of partnerships, associations, or campaigns launched to drive SLCP action | 3 | 3 Associations launched to drive SLCP action. | 2026-09-01 | Stakeholders, including government agencies, private companies, and financial institutions, will be convened and engaged to select at least 3 priority projects/ initiatives for organic waste management. This process will focus on identifying potential funding sources and aligning stakeholders to support these initiatives. The selected projects will be developed into deteiled plans, including financial strategies and implementation pathways, ensuring coodinated efforts amog all stakeholders to advance sustainable waste management solution. | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | Investors, public and private stakeholders. | Work plan | PA-24-003/1.3.1 Develop a list of complementary technologies and infrastructure to enhance organic waste management, consulting stakeholders such as circular economy specialists and private sector innovators. | Activity 1.3.1 Develop a list of complementary technologies and infrastructure to enhance organic waste management, consulting stakeholders such as circular economy specialists and private sector innovators. | Research, data collection, and/or report writing | null | null | 2026-06-01 | This activity will identify and prioritize complementary technologies and infrastructure to improve the efficiency of organic waste management systems. Circular economy specialists and private sector innovators will be consulted to ensure the recommendations align with sustainable practices and promote innovation. Examples of technologies include biogas recovery systems and advanced composting units. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Meeting report
|  |  | PA-24-003/1.2.2 Conduct site visits and surveys, collecting gender-disaggregated data to ensure proposed infrastructure meets the needs of both genders. | Activity 1.2.2 Conduct site visits and surveys, collecting gender-disaggregated data to ensure proposed infrastructure meets the needs of both genders. | Research, data collection, and/or report writing | null | null | 2025-12-01 | This activity will include field visits and stakeholder surveys to collect data on waste management infrastructure needs. Surveys will include gender-disaggregated data to ensure that proposed infrastructure supports both men and women, particularly those in waste-related informal sectors. The findings will inform inclusive and equitable infrastructure planning. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Research or study | PA-24-003/3.1 Analysis of policies to mitigate SLCPs | Output 3.1 Analysis of policies to mitigate SLCPs | Number of plans, policies, laws, or regulations drafted or updated | 1 | 1 plan, drafted or updated. | 2026-03-01 | Evaluation and analysis of policies to mitigate Short-Lived Climate Pollutants (SLCPs) from organic waste and prioritize actions for short, medium, and long term implementation. This evaluation will assess current measures and identify gaps in policy, recommending interventions that can effectively reduce SLCPs. The analysis will also provide estimated costs, responsible parties, and progress indicators. The result will be a comprehensive plan that outlines the necessary steps for Panama to reduce SLCP emissions through better organic waste management practices. | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | Government policymakers, NGOs, private sector. | Policy, regulation or other guideline | [7 empty] | Activity 1.3.1 Develop a list of complementary technologies and infrastructure to enhance organic waste management, consulting stakeholders such as circular economy specialists and private sector innovators. | Staff and Other Personnel Costs | CCAC | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste | UNDP () | PA-24-003/1.3.1-1 Training workshops, seminars and meetings | 20000 | "" | 20000 | "" |  | PA-24-003/3.1 Analysis of policies to mitigate SLCPs | Output 3.1 Analysis of policies to mitigate SLCPs | Number of plans, policies, laws, or regulations drafted or updated | 1 | 1 plan, drafted or updated. | 2026-03-01 | Evaluation and analysis of policies to mitigate Short-Lived Climate Pollutants (SLCPs) from organic waste and prioritize actions for short, medium, and long term implementation. This evaluation will assess current measures and identify gaps in policy, recommending interventions that can effectively reduce SLCPs. The analysis will also provide estimated costs, responsible parties, and progress indicators. The result will be a comprehensive plan that outlines the necessary steps for Panama to reduce SLCP emissions through better organic waste management practices. | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | Government policymakers, NGOs, private sector. | Policy, regulation or other guideline | PA-24-003/1.3.2 Host a gender-balanced expert panel to validate recommendations, prioritizing options that create employment for women. | Activity 1.3.2 Host a gender-balanced expert panel to validate recommendations, prioritizing options that create employment for women. | Organising, holding, or participating in a meeting or event | null | null | 2026-06-01 | A panel of experts, ensuring gender balance, will review and validate the recommendations for complementary technologies and infrastructure. Discussions will focus on prioritizing solutions that foster economic opportunities for women, particularly in waste collection and processing. The validated recommendations will guide subsequent project activities. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | null
|  |  | PA-24-003/1.2.3 Develop cost-benefit analyses, incorporating feedback from diverse stakeholders through an online webinar. | Activity 1.2.3 Develop cost-benefit analyses, incorporating feedback from diverse stakeholders through an online webinar. | Research, data collection, and/or report writing | null | null | 2026-03-01 | This activity will involve conducting cost-benefit analyses for proposed decentralized infrastructure options, such as composting and biodigesters. Stakeholders, including government officials, NGOs, and private sector representatives, will provide feedback through an interactive online webinar. The analysis will highlight economic, environmental, and social benefits, emphasizing SLCP mitigation and inclusion of marginalized groups. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Research or study | PA-24-003/3.2 Draft roadmap of financial intruments | Output 3.2 Draft roadmap of financial intruments | Number of plans, policies, laws, or regulations drafted or updated | 1 | 1 plan drafted or updated. | 2026-09-01 | A draft roadmap for financial instruments in organic waste management will be developed. This roadmap will be based on the findings of the previous evaluations and workshops, tailoring financial tools to the specific needs of the identified projects. It will include a detailed assessment of existing financial mechanisms and propose new ones that address key challenges and opportunities. The roadmap will guide the government and private sector in mobilizing resources for the sustainable implementation of organic waste management projects. | Available in English or other agreed UN language, and grammatically correct + English summary Involvement of the beneficiary government throughout the development process, for example through consultation meetings Involvement of the CCAC focal point Agreement to, or acknowledgement of, the product presented by the beneficiary government (at the appropriate level) and the CCAC Secretariat | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | Financial institutions and government agencies. | Policy, regulation or other guideline | [7 empty] | Activity 1.3.2 Host a gender-balanced expert panel to validate recommendations, prioritizing options that create employment for women. | Contractual Services | CCAC | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste | UNDP () | PA-24-003/1.3.2-1 Infographic design | 1000 | 1000 | "" | "" |  | PA-24-003/3.2 Draft roadmap of financial intruments | Output 3.2 Draft roadmap of financial intruments | Number of plans, policies, laws, or regulations drafted or updated | 1 | 1 plan drafted or updated. | 2026-09-01 | A draft roadmap for financial instruments in organic waste management will be developed. This roadmap will be based on the findings of the previous evaluations and workshops, tailoring financial tools to the specific needs of the identified projects. It will include a detailed assessment of existing financial mechanisms and propose new ones that address key challenges and opportunities. The roadmap will guide the government and private sector in mobilizing resources for the sustainable implementation of organic waste management projects. | Available in English or other agreed UN language, and grammatically correct + English summary Involvement of the beneficiary government throughout the development process, for example through consultation meetings Involvement of the CCAC focal point Agreement to, or acknowledgement of, the product presented by the beneficiary government (at the appropriate level) and the CCAC Secretariat | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | Financial institutions and government agencies. | Policy, regulation or other guideline | PA-24-003/1.3.3 Prepare an accessible visual infographic summarizing key recommendations for public dissemination. | Activity 1.3.3 Prepare an accessible visual infographic summarizing key recommendations for public dissemination. | Producing and distributing communications materials | null | null | 2026-09-01 | This activity will focus on creating an infographic to visually communicate the key recommendations from the expert panel to a broad audience. The infographic will highlight the technologies and infrastructure proposed, their environmental and social benefits, and their alignment with SLCP mitigation goals. The design will prioritize accessibility, ensuring it can be understood by diverse stakeholders, including policymakers, community groups, and private sector actors. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Research or study
|  |  | PA-24-003/1.3 Recommendations for alternative/ complementary infraestrucutre | Output 1.3 Recommendations for alternative/ complementary infraestrucutre | Number of SLCP knowledge resources or tools produced | 1 | 1 SLCP knowledge resource or tool produced. | 2026-09-01 | Recommendations for alternative and complementary infrastructure to support organic waste diversion and fosters circular economies. The proposed infraestructure aims to enhance existing waste management systems, such as advanced compositing technologies, anaerobic digestion, and resource recovery facilities. These recommendation will serve as a blueprint for the government to integreate into its organic waste management strategy, with focus on creating value to the organic waste, lowers emissions, reducing landfill dependency, and promoting environmental, economic and social benefits, achieve the goals establishd in the NDC's and roadmap for the Mitigation of SLCPs in Panama. The findings will guide future investements and policies for an integrated waste managemente approach | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | National and local governments. | Research or study | PA-24-003/4.1 Capacity building and technical assistance | Output 4.1 Capacity building and technical assistance | Number of public events, webinars, or side events hosted | 4 | 4 workshops conducted with government entities. | 2027-06-01 | Capacity building workshops and Technical Assistance for stakeholders working on organic waste management. These workshops will focus on enhancing the participants understanding of project development, cost-benefit analysis, and SLCP mitigation strategies. Training materials will be tailored to Panama's context, particulary focusing on the MERCA market in Panama City. The goal is to equip governemnt entities and other stakeholders with the knowledge and tools to implement effective organic waste management projects, while promoting collaboration and knowledge-sharing across sectors. | Agenda and event plan cleared by the beneficiary and/or CCAC Secretariat Event is promoted & details about event shared with CCAC at least one week in advance to support promotion CCAC is recognised (logo and as part of the agenda) Uses CCAC presentation template (where relevant / as an option) | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | Local governments, private sector, and NGOs. | Meeting report, Training materials | [7 empty] | Activity 1.3.3 Prepare an accessible visual infographic summarizing key recommendations for public dissemination. | Contractual Services | CCAC | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste | UNDP () | PA-24-003/1.3.3-1 Waste Management and Infrastructure Consultant | 2000 | "" | 2000 | "" |  | PA-24-003/4.1 Capacity building and technical assistance | Output 4.1 Capacity building and technical assistance | Number of public events, webinars, or side events hosted | 4 | 4 workshops conducted with government entities. | 2027-06-01 | Capacity building workshops and Technical Assistance for stakeholders working on organic waste management. These workshops will focus on enhancing the participants understanding of project development, cost-benefit analysis, and SLCP mitigation strategies. Training materials will be tailored to Panama's context, particulary focusing on the MERCA market in Panama City. The goal is to equip governemnt entities and other stakeholders with the knowledge and tools to implement effective organic waste management projects, while promoting collaboration and knowledge-sharing across sectors. | Agenda and event plan cleared by the beneficiary and/or CCAC Secretariat Event is promoted & details about event shared with CCAC at least one week in advance to support promotion CCAC is recognised (logo and as part of the agenda) Uses CCAC presentation template (where relevant / as an option) | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | Local governments, private sector, and NGOs. | Meeting report, Training materials | PA-24-003/1.4.1 Conduct an in-depth evaluation of essential infrastructure for organic waste management (e.g., composting plants, biodigesters) | Activity 1.4.1 Conduct an in-depth evaluation of essential infrastructure for organic waste management (e.g., composting plants, biodigesters) | Research, data collection, and/or report writing | null | null | 2026-12-01 | This activity will evaluate the critical infrastructure required for effective organic waste management in Panama, focusing on facilities such as composting plants and biodigesters. The evaluation will include cost estimates for infrastructure development, operational considerations, and potential funding sources. Special attention will be paid to how these facilities can generate employment opportunities for women and marginalized groups. This in-depth assessment will also examine environmental and economic impacts to support informed decision-making. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Meeting report
|  |  | PA-24-003/1.3.1 Develop a list of complementary technologies and infrastructure to enhance organic waste management, consulting stakeholders such as circular economy specialists and private sector innovators. | Activity 1.3.1 Develop a list of complementary technologies and infrastructure to enhance organic waste management, consulting stakeholders such as circular economy specialists and private sector innovators. | Research, data collection, and/or report writing | null | null | 2026-06-01 | This activity will identify and prioritize complementary technologies and infrastructure to improve the efficiency of organic waste management systems. Circular economy specialists and private sector innovators will be consulted to ensure the recommendations align with sustainable practices and promote innovation. Examples of technologies include biogas recovery systems and advanced composting units. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Meeting report | [21 empty] | Activity 1.4.1 Conduct an in-depth evaluation of essential infrastructure for organic waste management (e.g., composting plants, biodigesters) | Staff and Other Personnel Costs | CCAC | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste | UNDP () | PA-24-003/1.4.1-1 Waste Management and Infrastructure Consultant | 10000 | "" | 10000 | "" | [15 empty] | PA-24-003/1.4.2 Compile findings into a comprehensive report highlighting investment opportunities, environmental and economic benefits, and potential social impacts. Share the report through workshops and online platforms targeting public and private stakeholders. | Activity 1.4.2 Compile findings into a comprehensive report highlighting investment opportunities, environmental and economic benefits, and potential social impacts. Share the report through workshops and online platforms targeting public and private stakeholders. | Policy, project, or tool design | null | null | 2026-12-01 | This activity will consolidate the findings of the infrastructure evaluation into a comprehensive report that highlights key investment opportunities and the potential benefits of organic waste management infrastructure. The report will outline environmental, economic, and social impacts, emphasizing gender-inclusive opportunities such as job creation for women. The findings will be disseminated through workshops with stakeholders and made available on online platforms to ensure accessibility. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Meeting report
|  |  | PA-24-003/1.3.2 Host a gender-balanced expert panel to validate recommendations, prioritizing options that create employment for women. | Activity 1.3.2 Host a gender-balanced expert panel to validate recommendations, prioritizing options that create employment for women. | Organising, holding, or participating in a meeting or event | null | null | 2026-06-01 | A panel of experts, ensuring gender balance, will review and validate the recommendations for complementary technologies and infrastructure. Discussions will focus on prioritizing solutions that foster economic opportunities for women, particularly in waste collection and processing. The validated recommendations will guide subsequent project activities. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | null | [21 empty] | Activity 1.4.2 Compile findings into a comprehensive report highlighting investment opportunities, environmental and economic benefits, and potential social impacts. Share the report through workshops and online platforms targeting public and private stakeholders. | Staff and Other Personnel Costs | CCAC | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste | UNDP () | PA-24-003/1.4.2-1 Support innovation challenge | 5000 | "" | 5000 | "" | [15 empty] | PA-24-003/2.1.1Identify and evaluate projects with business potential, ensuring inclusion of women-led initiatives and alignment with national goals. | Activity 2.1.1Identify and evaluate projects with business potential, ensuring inclusion of women-led initiatives and alignment with national goals. | Other | null | null | 2026-06-01 | This activity will focus on identifying and evaluating 5–7 organic waste management projects that demonstrate strong business potential. The evaluation will include criteria such as alignment with national sustainability goals, economic viability, and SLCP mitigation potential. Women-led initiatives will be prioritized to ensure gender inclusion and equitable benefits. Key stakeholders, including government and private sector representatives, will provide input during the evaluation process. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Work plan
|  |  | PA-24-003/1.3.3 Prepare an accessible visual infographic summarizing key recommendations for public dissemination. | Activity 1.3.3 Prepare an accessible visual infographic summarizing key recommendations for public dissemination. | Producing and distributing communications materials | null | null | 2026-09-01 | This activity will focus on creating an infographic to visually communicate the key recommendations from the expert panel to a broad audience. The infographic will highlight the technologies and infrastructure proposed, their environmental and social benefits, and their alignment with SLCP mitigation goals. The design will prioritize accessibility, ensuring it can be understood by diverse stakeholders, including policymakers, community groups, and private sector actors. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Research or study | [21 empty] | Activity 2.1.1Identify and evaluate projects with business potential, ensuring inclusion of women-led initiatives and alignment with national goals. | Contractual Services | CCAC | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste | UNDP () | PA-24-003/2.1.1-1 Circular Economy Specialist | 20000 | "" | 20000 | "" | [15 empty] | PA-24-003/2.1.2Develop a portfolio of selected projects with detailed descriptions and expected outcomes, highlighting gender-specific benefits. | Activity 2.1.2Develop a portfolio of selected projects with detailed descriptions and expected outcomes, highlighting gender-specific benefits. | Research, data collection, and/or report writing | null | null | 2026-06-01 | Based on the evaluations conducted, this activity will create a portfolio of selected projects with detailed descriptions, expected outcomes, and their contributions to SLCP mitigation. The portfolio will emphasize gender-specific benefits, such as creating economic opportunities for women in waste management. The document will serve as a key resource for attracting public and private investments. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Policy, regulation or other guideline
|  |  | PA-24-003/1.4 Report indentifying necessary infraestructure and investment to support organic waste management | Output 1.4 Report indentifying necessary infraestructure and investment to support organic waste management | Number of plans, policies, laws, or regulations drafted or updated | 1 | 1 plan, policy, law, or regulation drafted or updated. | 2026-12-01 | A report identifying necessary infrastructure and investment to support organic waste management (recovery of organic waste, production of biofertilizer and energy, savings by avoiding waste, redistribution of food that otherwise would be discarded to people in need). The report will cover key areas such as the recovery of organic waste, the production of biofertilizers and renewable enerty, and economic savings from waste reduction. It will also highlight the potential for redistributing surplus food to people in need, preventing it from being discarded. By identifying these necessary components, the report will serve as a strategic roadmap for decision-makers to prioritize investements and implementing sustainable solutions for organic waste management. | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | National and local governments, investors. | Research or study | [21 empty] | Activity 2.1.2Develop a portfolio of selected projects with detailed descriptions and expected outcomes, highlighting gender-specific benefits. | Staff and Other Personnel Costs | CCAC | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste | UNDP () | PA-24-003/2.1.2-1 Circular Economy Specialist | 15000 | "" | 15000 | "" | [15 empty] | PA-24-003/2.1.3Engage private sector investors and financial institutions in the evaluation process to co-create viable financing strategies. | Activity 2.1.3Engage private sector investors and financial institutions in the evaluation process to co-create viable financing strategies. | Other | null | null | 2026-06-01 | This activity will involve engaging private sector investors and financial institutions to develop financing strategies for the selected projects. Workshops and one-on-one consultations will be conducted to present the portfolio and discuss potential financing options, including public-private partnerships and innovative financial instruments. The activity will emphasize strategies that support women-led initiatives and community-based projects. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Meeting report
|  |  | PA-24-003/1.4.1 Conduct an in-depth evaluation of essential infrastructure for organic waste management (e.g., composting plants, biodigesters) | Activity 1.4.1 Conduct an in-depth evaluation of essential infrastructure for organic waste management (e.g., composting plants, biodigesters) | Research, data collection, and/or report writing | null | null | 2026-12-01 | This activity will evaluate the critical infrastructure required for effective organic waste management in Panama, focusing on facilities such as composting plants and biodigesters. The evaluation will include cost estimates for infrastructure development, operational considerations, and potential funding sources. Special attention will be paid to how these facilities can generate employment opportunities for women and marginalized groups. This in-depth assessment will also examine environmental and economic impacts to support informed decision-making. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Meeting report | [21 empty] | Activity 2.1.3Engage private sector investors and financial institutions in the evaluation process to co-create viable financing strategies. | Staff and Other Personnel Costs | CCAC | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste | UNDP () | PA-24-003/2.1.3-1 Training workshops, seminars and meetings | 15000 | "" | 15000 | "" | [15 empty] | PA-24-003/2.2.1Host a multi-stakeholder workshop, ensuring representation from women-led organizations, to prioritize three high-impact projects. | Activity 2.2.1Host a multi-stakeholder workshop, ensuring representation from women-led organizations, to prioritize three high-impact projects. | Organising, holding, or participating in a meeting or event | null | null | 2026-06-01 | This activity will bring together key stakeholders, including government agencies, financial institutions, private sector representatives, and women-led organizations, to prioritize three high-impact projects from the identified portfolio. The workshop will use a participatory approach to ensure that diverse perspectives are incorporated in the decision-making process. Criteria for prioritization will include business potential, environmental and social benefits, and alignment with national goals. The outcomes of the workshop will guide the development of detailed financial plans for the selected projects. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Work plan
|  |  | PA-24-003/1.4.2 Compile findings into a comprehensive report highlighting investment opportunities, environmental and economic benefits, and potential social impacts. Share the report through workshops and online platforms targeting public and private stakeholders. | Activity 1.4.2 Compile findings into a comprehensive report highlighting investment opportunities, environmental and economic benefits, and potential social impacts. Share the report through workshops and online platforms targeting public and private stakeholders. | Policy, project, or tool design | null | null | 2026-12-01 | This activity will consolidate the findings of the infrastructure evaluation into a comprehensive report that highlights key investment opportunities and the potential benefits of organic waste management infrastructure. The report will outline environmental, economic, and social impacts, emphasizing gender-inclusive opportunities such as job creation for women. The findings will be disseminated through workshops with stakeholders and made available on online platforms to ensure accessibility. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Meeting report | [21 empty] | Activity 2.2.1Host a multi-stakeholder workshop, ensuring representation from women-led organizations, to prioritize three high-impact projects. | Contractual Services | CCAC | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste | UNDP () | PA-24-003/2.2.1-1 Financial and Business Development Consultant | 3000 | "" | 3000 | "" | [15 empty] | PA-24-003/2.2.2Develop detailed financial plans for selected projects, including specific tools tailored to benefit marginalized groups. | Activity 2.2.2Develop detailed financial plans for selected projects, including specific tools tailored to benefit marginalized groups. | Research, data collection, and/or report writing | null | null | 2026-09-01 | This activity involves creating comprehensive financial plans for the three prioritized projects. The plans will include cost estimates, funding requirements, and proposed financial instruments such as grants, loans, or public-private partnerships. Special attention will be given to designing tools that benefit marginalized groups, including women-led initiatives and small businesses. The financial plans will align with national and international sustainability goals and provide a clear roadmap for securing investment. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Web article
|  |  | PA-24-003/2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | Outcome 2. The Government of Panama endorses project proposals/ initiatives for organic waste management using MERCA market as a pilot for submission to public and private funding sources by the end of the project. | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 5 | 5 action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures | (blank) | The project will create a portfolio of 5-7 initiatives and projects with demonstrated business potential, aligned with national goals, and designed to attract funding from both public and private sectors. Specific financial plans will be developed for at least three selected projects, including tailored financial tools and agreements among stakeholders, to enhance the likelihood of securing financing, scaling, and promoting sustainable solutions. The process will include the establishment of collaborative, multi-stakeholder partnerships, which are essential for co-creating comprehensive and lasting solutions. Key activities will involve delivering workshops to financial and governmental stakeholders to explore innovative financing mechanisms and develop actionable financial instruments that address the needs of the selected initiatives. The project assumes that the identified initiatives will generate significant interest from funding institutions and public and private entities, with active participation | (blank) | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | (blank) | Waste | (blank) | (blank) | (blank) | [21 empty] | Activity 2.2.2Develop detailed financial plans for selected projects, including specific tools tailored to benefit marginalized groups. | Staff and Other Personnel Costs | CCAC | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste | UNDP () | PA-24-003/2.2.2-1 computers | 15000 | "" | 10000 | 5000 | [15 empty] | PA-24-003/2.2.3Release a press statement highlighting the selected projects to attract further investment and support. | Activity 2.2.3Release a press statement highlighting the selected projects to attract further investment and support. | Producing and distributing communications materials | null | null | 2026-09-01 | To raise awareness and attract investment, this activity will involve drafting and disseminating a press statement announcing the three selected projects. The statement will highlight the projects’ environmental, economic, and social benefits, as well as their alignment with SLCP mitigation goals. The press release will be shared with local and international media outlets, government websites, and social media platforms. The announcement will also emphasize opportunities for private sector involvement and partnerships. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Meeting report
|  |  | PA-24-003/2.1 Identification of projects/inititives | Output 2.1 Identification of projects/inititives | Number of partnerships, associations, or campaigns launched to drive SLCP action | 5 | 5 Partnerships to drive SLCP action. | 2026-06-01 | Identification of at least 5-7 appropriate projects/initiatives with business potential in integral organic waste management, supported by the public and private sector based on the findings of output 1.3. and will be evaluated for their potential to contribute to a circular economy. The assesment will include project descriptions, expected outcomes, involved entities, and financing strategies. By identifying these opportunities, the project aims to establish a solid foundation for future investements and actions in organic waste management. | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | Investors, public and private stakeholders. | Research or study, Work plan | [21 empty] | Activity 2.2.3Release a press statement highlighting the selected projects to attract further investment and support. | Equipment Vehicles and Furniture | CCAC | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste | UNDP () | PA-24-003/2.2.3-1 Circular Economy Specialist | 3000 | 3000 | "" | "" | [15 empty] | PA-24-003/3.1.1Review existing policies and regulations related to organic waste and SLCPs, engaging policymakers, academics, and gender specialists. | Activity 3.1.1Review existing policies and regulations related to organic waste and SLCPs, engaging policymakers, academics, and gender specialists. | Research, data collection, and/or report writing | null | null | 2025-12-01 | This activity involves a comprehensive review of existing policies and regulations governing organic waste management and SLCP mitigation in Panama. The review will engage policymakers, academics, and gender specialists to provide diverse perspectives and insights. The analysis will assess the effectiveness of current regulations, identify potential overlaps or gaps, and evaluate their alignment with national and international sustainability goals. Special emphasis will be placed on examining the gender impacts of these policies to ensure inclusivity and equity in future recommendations. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Policy, regulation or other guideline
|  |  | PA-24-003/2.1.1Identify and evaluate projects with business potential, ensuring inclusion of women-led initiatives and alignment with national goals. | Activity 2.1.1Identify and evaluate projects with business potential, ensuring inclusion of women-led initiatives and alignment with national goals. | Other | null | null | 2026-06-01 | This activity will focus on identifying and evaluating 5–7 organic waste management projects that demonstrate strong business potential. The evaluation will include criteria such as alignment with national sustainability goals, economic viability, and SLCP mitigation potential. Women-led initiatives will be prioritized to ensure gender inclusion and equitable benefits. Key stakeholders, including government and private sector representatives, will provide input during the evaluation process. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Work plan | [21 empty] | Activity 2.2.3Release a press statement highlighting the selected projects to attract further investment and support. | Staff and Other Personnel Costs | CCAC | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste | UNDP () | PA-24-003/2.2.3-2 National Consultant - Policy and SLCP Mitigation Consultant | 15000 | "" | "" | 15000 | [15 empty] | PA-24-003/3.1.2Identify policy gaps and prioritize actions for short, medium, and long-term implementation, ensuring gender-disaggregated data is part of the analysis. | Activity 3.1.2Identify policy gaps and prioritize actions for short, medium, and long-term implementation, ensuring gender-disaggregated data is part of the analysis. | Research, data collection, and/or report writing | null | null | 2025-12-01 | Building on the findings from the policy review, this activity will identify critical gaps and barriers in existing policies and propose prioritized actions for addressing them. Recommendations will be categorized into short, medium, and long-term strategies, ensuring alignment with Panama’s national goals and SLCP reduction targets. Gender-disaggregated data will be used to assess the differentiated impacts of these actions on men and women, with a focus on promoting inclusivity in policy reforms. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Policy, regulation or other guideline
|  |  | PA-24-003/2.1.2Develop a portfolio of selected projects with detailed descriptions and expected outcomes, highlighting gender-specific benefits. | Activity 2.1.2Develop a portfolio of selected projects with detailed descriptions and expected outcomes, highlighting gender-specific benefits. | Research, data collection, and/or report writing | null | null | 2026-06-01 | Based on the evaluations conducted, this activity will create a portfolio of selected projects with detailed descriptions, expected outcomes, and their contributions to SLCP mitigation. The portfolio will emphasize gender-specific benefits, such as creating economic opportunities for women in waste management. The document will serve as a key resource for attracting public and private investments. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Policy, regulation or other guideline | [21 empty] | Activity 3.1.1Review existing policies and regulations related to organic waste and SLCPs, engaging policymakers, academics, and gender specialists. | Staff and Other Personnel Costs | CCAC | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste | UNDP () | PA-24-003/3.1.1-1 National Consultant - Policy and SLCP Mitigation Consultant | 15000 | "" | 15000 | "" | [15 empty] | PA-24-003/3.1.3Develop a policy evaluation report and share findings through a case study targeted at stakeholders. | Activity 3.1.3Develop a policy evaluation report and share findings through a case study targeted at stakeholders. | Policy, project, or tool design | null | null | 2026-03-01 | This activity will consolidate the results of the policy analysis into an evaluation report, including actionable recommendations for strengthening SLCP mitigation policies. The report will also include a case study highlighting the potential impact of policy reforms on organic waste management and gender inclusivity. The findings will be shared with stakeholders through targeted communication efforts, including workshops, digital platforms, and printed materials. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Meeting report
|  |  | PA-24-003/2.1.3Engage private sector investors and financial institutions in the evaluation process to co-create viable financing strategies. | Activity 2.1.3Engage private sector investors and financial institutions in the evaluation process to co-create viable financing strategies. | Other | null | null | 2026-06-01 | This activity will involve engaging private sector investors and financial institutions to develop financing strategies for the selected projects. Workshops and one-on-one consultations will be conducted to present the portfolio and discuss potential financing options, including public-private partnerships and innovative financial instruments. The activity will emphasize strategies that support women-led initiatives and community-based projects. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Meeting report | [21 empty] | Activity 3.1.2Identify policy gaps and prioritize actions for short, medium, and long-term implementation, ensuring gender-disaggregated data is part of the analysis. | Staff and Other Personnel Costs | CCAC | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste | UNDP () | PA-24-003/3.1.2-1 Training workshops, seminars and meetings | 15000 | "" | 15000 | "" | [15 empty] | PA-24-003/3.2.1Host a workshop with financial institutions, government agencies, and private entities to co-design financial instruments tailored to organic waste projects, ensuring gender inclusion in discussions. | Activity 3.2.1Host a workshop with financial institutions, government agencies, and private entities to co-design financial instruments tailored to organic waste projects, ensuring gender inclusion in discussions. | Organising, holding, or participating in a meeting or event | null | null | 2026-03-01 | This workshop will bring together financial institutions, government agencies, private sector representatives, and women-led organizations to co-design innovative financial instruments for organic waste projects. Participants will collaborate on identifying barriers to financing and brainstorming tailored solutions, including gender-inclusive tools such as microfinance or capacity-building grants. The outcomes will form the foundation for a draft roadmap of financial mechanisms. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Work plan
|  |  | PA-24-003/2.2 Stakeholder Engagement and Strategic Financial Planning for Selected Projects | Output 2.2 Stakeholder Engagement and Strategic Financial Planning for Selected Projects | Number of partnerships, associations, or campaigns launched to drive SLCP action | 3 | 3 Associations launched to drive SLCP action. | 2026-09-01 | Stakeholders, including government agencies, private companies, and financial institutions, will be convened and engaged to select at least 3 priority projects/ initiatives for organic waste management. This process will focus on identifying potential funding sources and aligning stakeholders to support these initiatives. The selected projects will be developed into deteiled plans, including financial strategies and implementation pathways, ensuring coodinated efforts amog all stakeholders to advance sustainable waste management solution. | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | Investors, public and private stakeholders. | Work plan | [21 empty] | Activity 3.1.3Develop a policy evaluation report and share findings through a case study targeted at stakeholders. | Contractual Services | CCAC | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste | UNDP () | PA-24-003/3.1.3-1 Training workshops, seminars and meetings | 3000 | "" | 3000 | "" | [15 empty] | PA-24-003/3.2.2Draft a comprehensive roadmap with actionable steps and estimated budgets, prioritizing funds for women-led initiatives. | Activity 3.2.2Draft a comprehensive roadmap with actionable steps and estimated budgets, prioritizing funds for women-led initiatives. | Research, data collection, and/or report writing | null | null | 2026-09-01 | This activity will build on the workshop outcomes to develop a comprehensive roadmap for implementing financial instruments for organic waste management. The roadmap will include actionable steps, estimated budgets, and a clear timeline for implementation. Special attention will be given to prioritizing funding mechanisms that support women-led initiatives and community-based projects. The roadmap will serve as a strategic guide for stakeholders to mobilize resources and align efforts with national sustainability goals. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Tool
|  |  | PA-24-003/2.2.1Host a multi-stakeholder workshop, ensuring representation from women-led organizations, to prioritize three high-impact projects. | Activity 2.2.1Host a multi-stakeholder workshop, ensuring representation from women-led organizations, to prioritize three high-impact projects. | Organising, holding, or participating in a meeting or event | null | null | 2026-06-01 | This activity will bring together key stakeholders, including government agencies, financial institutions, private sector representatives, and women-led organizations, to prioritize three high-impact projects from the identified portfolio. The workshop will use a participatory approach to ensure that diverse perspectives are incorporated in the decision-making process. Criteria for prioritization will include business potential, environmental and social benefits, and alignment with national goals. The outcomes of the workshop will guide the development of detailed financial plans for the selected projects. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Work plan | [21 empty] | Activity 3.2.1Host a workshop with financial institutions, government agencies, and private entities to co-design financial instruments tailored to organic waste projects, ensuring gender inclusion in discussions. | Contractual Services | CCAC | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste | UNDP () | PA-24-003/3.2.1-1 Financial and Business Development Consultant | 3000 | "" | 3000 | "" | [15 empty] | PA-24-003/3.2.3Create an interactive digital roadmap for dissemination to public and private stakeholders. | Activity 3.2.3Create an interactive digital roadmap for dissemination to public and private stakeholders. | Producing and distributing communications materials | null | null | 2026-09-01 | To enhance accessibility and engagement, this activity will involve transforming the financial roadmap into an interactive digital format. The digital roadmap will include user-friendly navigation features, visualizations of key data, and links to supporting resources. It will be disseminated through online platforms and shared with public and private stakeholders to facilitate its use in decision-making and investment planning. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Meeting report
|  |  | PA-24-003/2.2.2Develop detailed financial plans for selected projects, including specific tools tailored to benefit marginalized groups. | Activity 2.2.2Develop detailed financial plans for selected projects, including specific tools tailored to benefit marginalized groups. | Research, data collection, and/or report writing | null | null | 2026-09-01 | This activity involves creating comprehensive financial plans for the three prioritized projects. The plans will include cost estimates, funding requirements, and proposed financial instruments such as grants, loans, or public-private partnerships. Special attention will be given to designing tools that benefit marginalized groups, including women-led initiatives and small businesses. The financial plans will align with national and international sustainability goals and provide a clear roadmap for securing investment. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Web article | [21 empty] | Activity 3.2.2Draft a comprehensive roadmap with actionable steps and estimated budgets, prioritizing funds for women-led initiatives. | Staff and Other Personnel Costs | CCAC | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste | UNDP () | PA-24-003/3.2.2-1 Contractual services for the design financial roadmap | 20000 | "" | 20000 | "" | [15 empty] | PA-24-003/4.1.1Organize training workshops for government officials and market stakeholders on SLCP mitigation strategies, offering flexible schedules and childcare options to ensure women’s participation. | Activity 4.1.1Organize training workshops for government officials and market stakeholders on SLCP mitigation strategies, offering flexible schedules and childcare options to ensure women’s participation. | Developing and/or delivering training | null | null | 2026-12-01 | This activity will involve organizing a series of capacity-building workshops aimed at enhancing the technical knowledge of government officials, market stakeholders, and other relevant actors on SLCP mitigation strategies. The workshops will cover topics such as best practices in organic waste management, SLCP reduction, and the integration of gender-sensitive approaches. To ensure equal participation, flexible schedules and childcare options will be provided for women participants. Training sessions will be delivered both in-person and virtually to maximize accessibility. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Training materials
|  |  | PA-24-003/2.2.3Release a press statement highlighting the selected projects to attract further investment and support. | Activity 2.2.3Release a press statement highlighting the selected projects to attract further investment and support. | Producing and distributing communications materials | null | null | 2026-09-01 | To raise awareness and attract investment, this activity will involve drafting and disseminating a press statement announcing the three selected projects. The statement will highlight the projects’ environmental, economic, and social benefits, as well as their alignment with SLCP mitigation goals. The press release will be shared with local and international media outlets, government websites, and social media platforms. The announcement will also emphasize opportunities for private sector involvement and partnerships. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Meeting report | [21 empty] | Activity 3.2.3Create an interactive digital roadmap for dissemination to public and private stakeholders. | Contractual Services | CCAC | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste | UNDP () | PA-24-003/3.2.3-1 Training workshops, seminars and meetings | 5000 | "" | 5000 | "" | [15 empty] | PA-24-003/4.1.2Develop training materials tailored to Panama’s context, including gender-sensitive approaches to waste management. | Activity 4.1.2Develop training materials tailored to Panama’s context, including gender-sensitive approaches to waste management. | Producing and distributing communications materials | null | null | 2026-09-01 | This activity will focus on designing and developing training materials that are tailored to Panama’s specific context in waste management and SLCP mitigation. The materials will include presentations, handouts, case studies, and practical exercises that address local challenges and opportunities. Gender-sensitive approaches will be integrated into the materials to highlight the role of women in waste management and promote inclusive practices. These resources will be made available in both print and digital formats to ensure broad accessibility. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Tool
|  |  | PA-24-003/3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Outcome 3. A draft roadmap designed based on the findings of the workshop to put financial instruments in place by the financial sector. | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | 1 | 1 roadmap | (blank) | Workshops under Output 2 will convene key stakeholders, including representatives from the financial sector, local and national governments, and private entities, to explore and design financial mechanisms aligned with Panama's national goals. These workshops will focus on evaluating policies to mitigate Short-Lived Climate Pollutants (SLCPs) from organic waste and identifying opportunities for financial innovation. The outcome will include the creation of a draft roadmap detailing necessary financial instruments and resources tailored to the unique needs and characteristics of organic waste projects in Panama. This roadmap will serve as a foundation for developing long-term financing strategies and a comprehensive resource mobilization plan, fostering sustainable investment and alignment with national and global sustainability goals. | (blank) | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | (blank) | Waste | (blank) | (blank) | (blank) | [21 empty] | Activity 4.1.1Organize training workshops for government officials and market stakeholders on SLCP mitigation strategies, offering flexible schedules and childcare options to ensure women’s participation. | Contractual Services | CCAC | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste | UNDP () | PA-24-003/4.1.1-1 Communications materials | 4000 | 1000 | 2000 | 1000 | [15 empty] | PA-24-003/4.1.3Establish a knowledge-sharing platform for continuous capacity-building, | Activity 4.1.3Establish a knowledge-sharing platform for continuous capacity-building, | Producing and distributing communications materials | null | null | 2027-06-01 | This activity involves creating a knowledge-sharing platform to provide ongoing support and capacity-building for stakeholders engaged in SLCP mitigation. The platform will feature resources such as training materials, case studies, and interactive forums for peer learning. Best practices and lessons learned from both women and men will be documented and showcased to promote gender-inclusive approaches. The platform will be accessible online, ensuring that stakeholders from across Panama can benefit from the resources and collaborate on shared goals. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Work plan
|  |  | PA-24-003/3.1 Analysis of policies to mitigate SLCPs | Output 3.1 Analysis of policies to mitigate SLCPs | Number of plans, policies, laws, or regulations drafted or updated | 1 | 1 plan, drafted or updated. | 2026-03-01 | Evaluation and analysis of policies to mitigate Short-Lived Climate Pollutants (SLCPs) from organic waste and prioritize actions for short, medium, and long term implementation. This evaluation will assess current measures and identify gaps in policy, recommending interventions that can effectively reduce SLCPs. The analysis will also provide estimated costs, responsible parties, and progress indicators. The result will be a comprehensive plan that outlines the necessary steps for Panama to reduce SLCP emissions through better organic waste management practices. | Grammatically correct and available in English, or other agreed UN language Recognizes CCAC support Final version approved by the beneficiary and/or CCAC Secretariat Ready for uploading in CCAC website (when applicable) (laid out in PDF with CCAC logo, contents proof-read) | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | Government policymakers, NGOs, private sector. | Policy, regulation or other guideline | [21 empty] | Activity 4.1.2Develop training materials tailored to Panama’s context, including gender-sensitive approaches to waste management. | Contractual Services | CCAC | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste | UNDP () | PA-24-003/4.1.2-1 Communications specialist | 25000 | "" | 10000 | 15000 | [15 empty] | PA-24-003/4.1.4Project Management and Administration | Activity 4.1.4Project Management and Administration | Other | null | null | 2027-06-01 | This activity will ensure the efficient management of the project, covering general operational costs, monitoring, financial and administrative reporting, as well as overall project coordination. It will also include expenses related to technical supervision and contract management. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | null
|  |  | PA-24-003/3.1.1Review existing policies and regulations related to organic waste and SLCPs, engaging policymakers, academics, and gender specialists. | Activity 3.1.1Review existing policies and regulations related to organic waste and SLCPs, engaging policymakers, academics, and gender specialists. | Research, data collection, and/or report writing | null | null | 2025-12-01 | This activity involves a comprehensive review of existing policies and regulations governing organic waste management and SLCP mitigation in Panama. The review will engage policymakers, academics, and gender specialists to provide diverse perspectives and insights. The analysis will assess the effectiveness of current regulations, identify potential overlaps or gaps, and evaluate their alignment with national and international sustainability goals. Special emphasis will be placed on examining the gender impacts of these policies to ensure inclusivity and equity in future recommendations. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Policy, regulation or other guideline | [21 empty] | Activity 4.1.2Develop training materials tailored to Panama’s context, including gender-sensitive approaches to waste management. | Contractual Services | CCAC | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste | UNDP () | PA-24-003/4.1.2-2 communication materials | 20686 | "" | 10343 | 10343
|  |  | PA-24-003/3.1.2Identify policy gaps and prioritize actions for short, medium, and long-term implementation, ensuring gender-disaggregated data is part of the analysis. | Activity 3.1.2Identify policy gaps and prioritize actions for short, medium, and long-term implementation, ensuring gender-disaggregated data is part of the analysis. | Research, data collection, and/or report writing | null | null | 2025-12-01 | Building on the findings from the policy review, this activity will identify critical gaps and barriers in existing policies and propose prioritized actions for addressing them. Recommendations will be categorized into short, medium, and long-term strategies, ensuring alignment with Panama’s national goals and SLCP reduction targets. Gender-disaggregated data will be used to assess the differentiated impacts of these actions on men and women, with a focus on promoting inclusivity in policy reforms. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Policy, regulation or other guideline | [21 empty] | Activity 4.1.3Establish a knowledge-sharing platform for continuous capacity-building, | Contractual Services | CCAC | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste | UNDP () | PA-24-003/4.1.2-1 communication materials | 16000 | "" | 16000 | ""
|  |  | PA-24-003/3.1.3Develop a policy evaluation report and share findings through a case study targeted at stakeholders. | Activity 3.1.3Develop a policy evaluation report and share findings through a case study targeted at stakeholders. | Policy, project, or tool design | null | null | 2026-03-01 | This activity will consolidate the results of the policy analysis into an evaluation report, including actionable recommendations for strengthening SLCP mitigation policies. The report will also include a case study highlighting the potential impact of policy reforms on organic waste management and gender inclusivity. The findings will be shared with stakeholders through targeted communication efforts, including workshops, digital platforms, and printed materials. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Meeting report | [21 empty] | Activity 4.1.4Project Management and Administration | Operating and Other Direct Costs | Co-funding | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste | UNDP () | PA-24-003/4.1.3-1 Rental Offices | 15000 | 7500 | 7500 | ""
|  |  | PA-24-003/3.2 Draft roadmap of financial intruments | Output 3.2 Draft roadmap of financial intruments | Number of plans, policies, laws, or regulations drafted or updated | 1 | 1 plan drafted or updated. | 2026-09-01 | A draft roadmap for financial instruments in organic waste management will be developed. This roadmap will be based on the findings of the previous evaluations and workshops, tailoring financial tools to the specific needs of the identified projects. It will include a detailed assessment of existing financial mechanisms and propose new ones that address key challenges and opportunities. The roadmap will guide the government and private sector in mobilizing resources for the sustainable implementation of organic waste management projects. | Available in English or other agreed UN language, and grammatically correct + English summary Involvement of the beneficiary government throughout the development process, for example through consultation meetings Involvement of the CCAC focal point Agreement to, or acknowledgement of, the product presented by the beneficiary government (at the appropriate level) and the CCAC Secretariat | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | Financial institutions and government agencies. | Policy, regulation or other guideline | [21 empty] | Activity 4.1.4Project Management and Administration | Staff and Other Personnel Costs | CCAC | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste | UNDP () | PA-24-003/4.1.4-1 Contract Project Asistant | 40000 | 10000 | 20000 | 10000
|  |  | PA-24-003/3.2.1Host a workshop with financial institutions, government agencies, and private entities to co-design financial instruments tailored to organic waste projects, ensuring gender inclusion in discussions. | Activity 3.2.1Host a workshop with financial institutions, government agencies, and private entities to co-design financial instruments tailored to organic waste projects, ensuring gender inclusion in discussions. | Organising, holding, or participating in a meeting or event | null | null | 2026-03-01 | This workshop will bring together financial institutions, government agencies, private sector representatives, and women-led organizations to co-design innovative financial instruments for organic waste projects. Participants will collaborate on identifying barriers to financing and brainstorming tailored solutions, including gender-inclusive tools such as microfinance or capacity-building grants. The outcomes will form the foundation for a draft roadmap of financial mechanisms. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Work plan | [21 empty] | Activity 4.1.4Project Management and Administration | Staff and Other Personnel Costs | CCAC | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste | UNDP () | PA-24-003/4.1.4-2 Programme Support Costs (PSC) | 20000 | 5000 | 10000 | 5000
|  |  | PA-24-003/3.2.2Draft a comprehensive roadmap with actionable steps and estimated budgets, prioritizing funds for women-led initiatives. | Activity 3.2.2Draft a comprehensive roadmap with actionable steps and estimated budgets, prioritizing funds for women-led initiatives. | Research, data collection, and/or report writing | null | null | 2026-09-01 | This activity will build on the workshop outcomes to develop a comprehensive roadmap for implementing financial instruments for organic waste management. The roadmap will include actionable steps, estimated budgets, and a clear timeline for implementation. Special attention will be given to prioritizing funding mechanisms that support women-led initiatives and community-based projects. The roadmap will serve as a strategic guide for stakeholders to mobilize resources and align efforts with national sustainability goals. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Tool | [21 empty] | Activity 4.1.4Project Management and Administration | UN-PSC | CCAC | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | Waste | UNDP () | PA-24-003/4.1.4-3 Waste Management and Infrastructure Consultant | 25514 | 6378.5 | 12757 | 6378.5
|  |  | PA-24-003/3.2.3Create an interactive digital roadmap for dissemination to public and private stakeholders. | Activity 3.2.3Create an interactive digital roadmap for dissemination to public and private stakeholders. | Producing and distributing communications materials | null | null | 2026-09-01 | To enhance accessibility and engagement, this activity will involve transforming the financial roadmap into an interactive digital format. The digital roadmap will include user-friendly navigation features, visualizations of key data, and links to supporting resources. It will be disseminated through online platforms and shared with public and private stakeholders to facilitate its use in decision-making and investment planning. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Meeting report
|  |  | PA-24-003/4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Outcome 4. The Government of Panama has increased its capacity to assess and implement SLCP mitigation measures by the end of the project or soon after. | Number of government entities with a demonstrated improved capacity for SLCP action | 20 | 20 government entities with improved capacity for SLCP action. | (blank) | The project aims to strengthen the government’s capacity to evaluate and monitor organic waste management projects effectively. By developing targeted training programs and fostering collaboration with key stakeholders, the project ensures that newly acquired knowledge and skills are applied in practice. Knowledge-sharing platforms will play a pivotal role in disseminating results, lessons learned, and case studies while supporting the development of training materials and fostering local expertise. These efforts aim to facilitate the sustainable implementation of Short-Lived Climate Pollutant (SLCP) mitigation measures. The project assumes that by enhancing technical capacity, the government will be better equipped to design and implement effective policies and measures, creating a strong foundation for the long-term success of SLCP reduction initiatives linked to organic waste management. | (blank) | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | (blank) | Waste | (blank) | (blank) | (blank)
|  |  | PA-24-003/4.1 Capacity building and technical assistance | Output 4.1 Capacity building and technical assistance | Number of public events, webinars, or side events hosted | 4 | 4 workshops conducted with government entities. | 2027-06-01 | Capacity building workshops and Technical Assistance for stakeholders working on organic waste management. These workshops will focus on enhancing the participants understanding of project development, cost-benefit analysis, and SLCP mitigation strategies. Training materials will be tailored to Panama's context, particulary focusing on the MERCA market in Panama City. The goal is to equip governemnt entities and other stakeholders with the knowledge and tools to implement effective organic waste management projects, while promoting collaboration and knowledge-sharing across sectors. | Agenda and event plan cleared by the beneficiary and/or CCAC Secretariat Event is promoted & details about event shared with CCAC at least one week in advance to support promotion CCAC is recognised (logo and as part of the agenda) Uses CCAC presentation template (where relevant / as an option) | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | Local governments, private sector, and NGOs. | Meeting report, Training materials
|  |  | PA-24-003/4.1.1Organize training workshops for government officials and market stakeholders on SLCP mitigation strategies, offering flexible schedules and childcare options to ensure women’s participation. | Activity 4.1.1Organize training workshops for government officials and market stakeholders on SLCP mitigation strategies, offering flexible schedules and childcare options to ensure women’s participation. | Developing and/or delivering training | null | null | 2026-12-01 | This activity will involve organizing a series of capacity-building workshops aimed at enhancing the technical knowledge of government officials, market stakeholders, and other relevant actors on SLCP mitigation strategies. The workshops will cover topics such as best practices in organic waste management, SLCP reduction, and the integration of gender-sensitive approaches. To ensure equal participation, flexible schedules and childcare options will be provided for women participants. Training sessions will be delivered both in-person and virtually to maximize accessibility. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Training materials
|  |  | PA-24-003/4.1.2Develop training materials tailored to Panama’s context, including gender-sensitive approaches to waste management. | Activity 4.1.2Develop training materials tailored to Panama’s context, including gender-sensitive approaches to waste management. | Producing and distributing communications materials | null | null | 2026-09-01 | This activity will focus on designing and developing training materials that are tailored to Panama’s specific context in waste management and SLCP mitigation. The materials will include presentations, handouts, case studies, and practical exercises that address local challenges and opportunities. Gender-sensitive approaches will be integrated into the materials to highlight the role of women in waste management and promote inclusive practices. These resources will be made available in both print and digital formats to ensure broad accessibility. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Tool
|  |  | PA-24-003/4.1.3Establish a knowledge-sharing platform for continuous capacity-building, | Activity 4.1.3Establish a knowledge-sharing platform for continuous capacity-building, | Producing and distributing communications materials | null | null | 2027-06-01 | This activity involves creating a knowledge-sharing platform to provide ongoing support and capacity-building for stakeholders engaged in SLCP mitigation. The platform will feature resources such as training materials, case studies, and interactive forums for peer learning. Best practices and lessons learned from both women and men will be documented and showcased to promote gender-inclusive approaches. The platform will be accessible online, ensuring that stakeholders from across Panama can benefit from the resources and collaborate on shared goals. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | Work plan
|  |  | PA-24-003/4.1.4Project Management and Administration | Activity 4.1.4Project Management and Administration | Other | null | null | 2027-06-01 | This activity will ensure the efficient management of the project, covering general operational costs, monitoring, financial and administrative reporting, as well as overall project coordination. It will also include expenses related to technical supervision and contract management. | null | Accelerating actions to improve organic waste management and reduce methane emissions. (PA-24-003) | UNDP () | Waste | Panama | null | null

## Indicator validation (hidden)
Main indicator | Unit of measure | Instructions for first dropdown | 1st dropdown list | Instructions for 2nd dropdown | 2nd dropdown list | Instructions for open text | Level | Level | Outcome |  |  |  | Level | Output |  |  |  | Level | Outcome | Level | Outcome | Level | Output | Level | Output
Amount of external funding (“catalysed funding”) for SLCP actions | Amount in USD: | Type of funding: | Grant, Loan, Private equity | n/a | n/a | List the funding organisations: | Outcome
Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | Number of plans: | Type of plan: | Policy, Action plan, National budget, Long-term strategy, Recovery plan or stimulus package, Development plan | Status: | Adopted, Implemented | List the SLCP-relevant details included in the plan, including the sectors, pollutants, mitigation actions or targets mentioned: | Outcome | Main indicator | Unit of measure | Instructions for first dropdown | Instructions for 2nd dropdown | Instructions for open text | Main indicator | Unit of measure | Instructions for first dropdown | Instructions for 2nd dropdown | Instructions for open text | Main indicator | 1st dropdown list | Main indicator | 2nd dropdown list | Main indicator | 1st dropdown list | Main indicator | 2nd dropdown list |  |  | Black carbon
Number of articles published in scientific journals as the result of CCAC support | Number of published articles: | n/a | n/a | n/a | n/a | Name of journal and link to the article: | Outcome | Amount of external funding (“catalysed funding”) for SLCP actions | Amount in USD: | Type of funding: | n/a | List the funding organisations: | Amount of co-funding secured to support SLCP projects | Amount in USD: | Type: | n/a | Name of funding source(s): | Amount of external funding (“catalysed funding”) for SLCP actions | Grant | Amount of external funding (“catalysed funding”) for SLCP actions | n/a | Amount of co-funding secured to support SLCP projects | Co-funding | Amount of co-funding secured to support SLCP projects | n/a | Output first list | OFFSET('Indicator validation'!$AC$3,MATCH('4. Outputs'!$C$12,'Indicator validation'!$AB$4:$AB$59,0),0,COUNTIF('Indicator validation'!$AB$4:$AB$59,'4. Outputs'!$C$12),1) | HFCs
Number of commitments to reduce SLCPs through international or regional agreements | Number of entities making commitment (enter total): | Type of commitment: | Bilateral agreement, Legally-binding decision or treaty, Memorandum of Understanding (MoU), Voluntary international framework, Multilateral agreement | Type of entity: | National governments, Businesses, Subnational governments, NGO or IGO | List the SLCP-relevant details included in the commitment or agreement, including the sectors, pollutants, mitigation actions or targets mentioned: | Outcome | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | Number of plans: | Type of plan: | Status: | List the SLCP-relevant details included in the plan, including the sectors, pollutants, mitigation actions or targets mentioned: | Number of decision makers participating in outreach events | Number of attendees: | Type of decision maker: | n/a | List the attendees: | Amount of external funding (“catalysed funding”) for SLCP actions | Loan | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | Adopted | Amount of co-funding secured to support SLCP projects | In-kind contribution | Number of decision makers participating in outreach events | n/a | Output second list | OFFSET('Indicator validation'!$AF$3,MATCH('4. Outputs'!$C$12,'Indicator validation'!$AE$4:$AE$59,0),0,COUNTIF('Indicator validation'!$AE$4:$AE$59,'4. Outputs'!$C$12),1) | Methane
Number of government entities with a demonstrated improved capacity for SLCP action | Number of entities: | Type of entity: | Regional entity, National government, Sub-national government | n/a | n/a | List the government entities by name: | Outcome | Number of articles published in scientific journals as the result of CCAC support | Number of published articles: | n/a | n/a | Name of journal and link to the article: | Number of partnerships, associations, or campaigns launched to drive SLCP action | Number of initiatives: | Type of action: | Scale: | Mitigation actions, targets: | Amount of external funding (“catalysed funding”) for SLCP actions | Private equity | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | Implemented | Number of decision makers participating in outreach events | Head of State | Number of partnerships, associations, or campaigns launched to drive SLCP action | National |  |  | Tropospheric ozone
Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | Number of instruments: | Type: | Law, Regulation, By-law, Standard | Status: | Adopted, Implemented | List the SLCP-relevant details included in the regulation, including the sectors, pollutants, mitigation actions or targets mentioned: | Outcome | Number of commitments to reduce SLCPs through international or regional agreements | Number of entities making commitment (enter total): | Type of commitment: | Type of entity: | List the SLCP-relevant details included in the commitment or agreement, including the sectors, pollutants, mitigation actions or targets mentioned: | Number of plans, policies, laws, or regulations drafted or updated | Amount: | Type: | Scale: | SLCP mitigation actions and/or targets included: | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | Action plan | Number of articles published in scientific journals as the result of CCAC support | n/a | Number of decision makers participating in outreach events | Leader of organisation | Number of partnerships, associations, or campaigns launched to drive SLCP action | Sub-national | Outcome first list | OFFSET('Indicator validation'!$W$3,MATCH('5. Outcomes'!$C$11,'Indicator validation'!$V$4:$V$59,0),0,COUNTIF('Indicator validation'!$V$4:$V$59,'5. Outcomes'!$C$11),1) | All SLCPs
Number of mentions of SLCPs or the CCAC by a Minister or equivalent | Number of mentions: | n/a | n/a | n/a | n/a | Provide the name of the Minister, date of mention, and link to more details where possible: | Outcome | Number of government entities with a demonstrated improved capacity for SLCP action | Number of entities: | Type of entity: | n/a | List the government entities by name: | Number of public events, webinars, or side events hosted | Number of events hosted: | Size of event: | n/a | Link to the event details: | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | Development plan | Number of commitments to reduce SLCPs through international or regional agreements | Businesses | Number of decision makers participating in outreach events | Mayor | Number of partnerships, associations, or campaigns launched to drive SLCP action | Regional/International | Outcome second list | OFFSET('Indicator validation'!$Z$3,MATCH('5. Outcomes'!$C$11,'Indicator validation'!$Y$4:$Y$59,0),0,COUNTIF('Indicator validation'!$Y$4:$Y$59,'5. Outcomes'!$C$11),1)
Number of NDCs that include SLCPs | Number of NDCs: | CCAC involvement: | CCAC-funded, CCAC partner, Non-partner | n/a | n/a | List the SLCP-relevant details included in the NDC, including the sectors, pollutants, mitigation actions or targets mentioned: | Outcome | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | Number of instruments: | Type: | Status: | List the SLCP-relevant details included in the regulation, including the sectors, pollutants, mitigation actions or targets mentioned: | Number of SLCP assessments, emissions inventories, and other emissions datasets produced | Amount: | Type: | n/a | Briefly describe what was produced and how this information will be used by the beneficiary: | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | Long-term strategy | Number of commitments to reduce SLCPs through international or regional agreements | National governments | Number of decision makers participating in outreach events | Minister or equivalent | Number of plans, policies, laws, or regulations drafted or updated | National
Number of news outlets that have covered CCAC-funded activities | Number of articles: | Reach: | Regional, National, Local | n/a | n/a | Name of media outlets and links to overage: | Outcome | Number of mentions of SLCPs or the CCAC by a Minister or equivalent | Number of mentions: | n/a | n/a | Provide the name of the Minister, date of mention, and link to more details where possible: | Number of SLCP knowledge resources or tools produced | Number of resources produced: | Type of resource: | n/a | Briefly descbribe how the resource is being used by the intended audience: | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | National budget | Number of commitments to reduce SLCPs through international or regional agreements | NGO or IGO | Number of partnerships, associations, or campaigns launched to drive SLCP action | Binding | Number of plans, policies, laws, or regulations drafted or updated | Sub-national |  | #N/A
Number of non-government entities with a demonstrated improved capacity for SLCP action | Number of government entities: | Type of entity: | NGO, IGO, Company, Independent/self-employed | n/a | n/a | List the government entities by name: | Outcome | Number of monitoring, reporting, and verification (MRV) systems developed or updated that include SLCPs | Quantity: | n/a | n/a | List the SLCP-relevant details covered, including the sectors and pollutants: | Number of tools, equipment, or technologies installed or tested | Quantity: | Type of recipient: | n/a | Briefly descbribe the tool or technology and its intended use: | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | Policy | Number of commitments to reduce SLCPs through international or regional agreements | Subnational governments | Number of partnerships, associations, or campaigns launched to drive SLCP action | Voluntary | Number of plans, policies, laws, or regulations drafted or updated | Regional/International
Number of SLCP mitigation tools, technologies, or practices adopted | Number of changes: | Level of change: | Individual or household, Entity or institution, Industry | n/a | n/a | Describe the practice or technology: | Outcome | Number of NDCs that include SLCPs | Number of NDCs: | CCAC involvement: | n/a | List the SLCP-relevant details included in the NDC, including the sectors, pollutants, mitigation actions or targets mentioned: | Number of training sessions, workshops delivered | Person hours of training (# participants x # of hours of training): | Type of training: | Type of trainees: | Number of male and female trainees: | Number of action plans, roadmaps, strategies, or other future plans with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | Recovery plan or stimulus package | Number of government entities with a demonstrated improved capacity for SLCP action | n/a | Number of plans, policies, laws, or regulations drafted or updated | Action plan | Number of public events, webinars, or side events hosted | n/a
Number of monitoring, reporting, and verification (MRV) systems developed or updated that include SLCPs | Quantity: | n/a | n/a | n/a | n/a | List the SLCP-relevant details covered, including the sectors and pollutants: | Outcome | Number of news outlets that have covered CCAC-funded activities | Number of articles: | Reach: | n/a | Name of media outlets and links to overage: | [5 empty] | Number of articles published in scientific journals as the result of CCAC support | n/a | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | Adopted | Number of plans, policies, laws, or regulations drafted or updated | By-law | Number of SLCP assessments, emissions inventories, and other emissions datasets produced | n/a
Amount of co-funding secured to support SLCP projects | Amount in USD: | Type: | Co-funding, In-kind contribution | n/a | n/a | Name of funding source(s): | Output | Number of non-government entities with a demonstrated improved capacity for SLCP action | Number of government entities: | Type of entity: | n/a | List the government entities by name: | [5 empty] | Number of commitments to reduce SLCPs through international or regional agreements | Bilateral agreement | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | Implemented | Number of plans, policies, laws, or regulations drafted or updated | Development plan | Number of SLCP knowledge resources or tools produced | n/a
Number of decision makers participating in outreach events | Number of attendees: | Type of decision maker: | Head of State, Minister or equivalent, Mayor, Leader of organisation | n/a | n/a | List the attendees: | Output | Number of SLCP mitigation tools, technologies, or practices adopted | Number of changes: | Level of change: | n/a | Describe the practice or technology: | [5 empty] | Number of commitments to reduce SLCPs through international or regional agreements | Legally-binding decision or treaty | Number of mentions of SLCPs or the CCAC by a Minister or equivalent | n/a | Number of plans, policies, laws, or regulations drafted or updated | Law | Number of tools, equipment, or technologies installed or tested | n/a
Number of partnerships, associations, or campaigns launched to drive SLCP action | Number of initiatives: | Type of action: | Binding, Voluntary | Scale: | Regional/International, National, Sub-national | Mitigation actions, targets: | Output | [10 empty] | Number of commitments to reduce SLCPs through international or regional agreements | Memorandum of Understanding (MoU) | Number of NDCs that include SLCPs | n/a | Number of plans, policies, laws, or regulations drafted or updated | Long-term strategy | Number of training sessions, workshops delivered | For-profit organisation
Number of plans, policies, laws, or regulations drafted or updated | Amount: | Type: | Policy, Action plan, National budget, Long-term strategy, Recovery plan or stimulus package, Development plan, Law, Regulation, By-law, Standard | Scale: | Regional/International, National, Sub-national | SLCP mitigation actions and/or targets included: | Output | [10 empty] | Number of commitments to reduce SLCPs through international or regional agreements | Multilateral agreement | Number of news outlets that have covered CCAC-funded activities | n/a | Number of plans, policies, laws, or regulations drafted or updated | National budget | Number of training sessions, workshops delivered | Government
Number of public events, webinars, or side events hosted | Number of events hosted: | Size of event: | Small (<50), Medium (50-100), Large (>100) | n/a | n/a | Link to the event details: | Output | [10 empty] | Number of commitments to reduce SLCPs through international or regional agreements | Voluntary international framework | Number of non-government entities with a demonstrated improved capacity for SLCP action | n/a | Number of plans, policies, laws, or regulations drafted or updated | Policy | Number of training sessions, workshops delivered | Non-profit organisation
Number of SLCP assessments, emissions inventories, and other emissions datasets produced | Amount: | Type: | Assessment, Benefits calculation, Inventory, Projection | n/a | n/a | Briefly describe what was produced and how this information will be used by the beneficiary: | Output | [10 empty] | Number of government entities with a demonstrated improved capacity for SLCP action | National government | Number of SLCP mitigation tools, technologies, or practices adopted | n/a | Number of plans, policies, laws, or regulations drafted or updated | Recovery plan or stimulus package | Number of training sessions, workshops delivered | Self-employed
Number of SLCP knowledge resources or tools produced | Number of resources produced: | Type of resource: | Awareness material, Best practice, Case study or report, Guideline or tool, Knowledge platform, Scientific research, Training material | n/a | n/a | Briefly descbribe how the resource is being used by the intended audience: | Output | [10 empty] | Number of government entities with a demonstrated improved capacity for SLCP action | Regional entity | Number of monitoring, reporting, and verification (MRV) systems developed or updated that include SLCPs | n/a | Number of plans, policies, laws, or regulations drafted or updated | Regulation
Number of tools, equipment, or technologies installed or tested | Quantity: | Type of recipient: | Individual or household, Entity or institution, Industry | n/a | n/a | Briefly descbribe the tool or technology and its intended use: | Output | [10 empty] | Number of government entities with a demonstrated improved capacity for SLCP action | Sub-national government |  |  | Number of plans, policies, laws, or regulations drafted or updated | Standard
Number of training sessions, workshops delivered | Person hours of training (# participants x # of hours of training): | Type of training: | General awarenesss, Policy or planning, Technical skills or practices | Type of trainees: | For-profit organisation, Government, Non-profit organisation, Self-employed | Number of male and female trainees: | Output | [10 empty] | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | By-law |  |  | Number of public events, webinars, or side events hosted | Large (>100)
[18 empty] | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | Law |  |  | Number of public events, webinars, or side events hosted | Medium (50-100)
[18 empty] | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | Regulation |  |  | Number of public events, webinars, or side events hosted | Small (<50)
[18 empty] | Number of laws, regulations, or other policy mechanisms with SLCP targets or mitigation measures formally adopted, endorsed, and/or implemented | Standard |  |  | Number of SLCP assessments, emissions inventories, and other emissions datasets produced | Assessment
[18 empty] | Number of mentions of SLCPs or the CCAC by a Minister or equivalent | n/a |  |  | Number of SLCP assessments, emissions inventories, and other emissions datasets produced | Benefits calculation
[18 empty] | Number of monitoring, reporting, and verification (MRV) systems developed or updated that include SLCPs | n/a |  |  | Number of SLCP assessments, emissions inventories, and other emissions datasets produced | Inventory
[18 empty] | Number of NDCs that include SLCPs | CCAC partner |  |  | Number of SLCP assessments, emissions inventories, and other emissions datasets produced | Projection
[18 empty] | Number of NDCs that include SLCPs | CCAC-funded |  |  | Number of SLCP knowledge resources or tools produced | Awareness material
[18 empty] | Number of NDCs that include SLCPs | Non-partner |  |  | Number of SLCP knowledge resources or tools produced | Best practice
[18 empty] | Number of news outlets that have covered CCAC-funded activities | Local |  |  | Number of SLCP knowledge resources or tools produced | Case study or report
OFFSET(Indicators!$P$1,MATCH('2. Results'!$D$10,Indicators!$O$2:$O$67,0),0,COUNTIF(Indicators!$O$2:$O$67,'2. Results'!$D$10),1) | [5 empty] | OFFSET(Indicators!$S$1,MATCH('2. Results'!$D$10,Indicators!$R$2:$R$40,0),0,COUNTIF(Indicators!$R$2:$R$40,'2. Results'!$D$10),1) | [11 empty] | Number of news outlets that have covered CCAC-funded activities | National |  |  | Number of SLCP knowledge resources or tools produced | Guideline or tool
[18 empty] | Number of news outlets that have covered CCAC-funded activities | Regional |  |  | Number of SLCP knowledge resources or tools produced | Knowledge platform
[18 empty] | Number of non-government entities with a demonstrated improved capacity for SLCP action | Company |  |  | Number of SLCP knowledge resources or tools produced | Scientific research
[18 empty] | Number of non-government entities with a demonstrated improved capacity for SLCP action | IGO |  |  | Number of SLCP knowledge resources or tools produced | Training material
[18 empty] | Number of non-government entities with a demonstrated improved capacity for SLCP action | Independent/self-employed |  |  | Number of tools, equipment, or technologies installed or tested | Entity or institution
[18 empty] | Number of non-government entities with a demonstrated improved capacity for SLCP action | NGO |  |  | Number of tools, equipment, or technologies installed or tested | Individual or household
[18 empty] | Number of SLCP mitigation tools, technologies, or practices adopted | Entity or institution |  |  | Number of tools, equipment, or technologies installed or tested | Industry
[18 empty] | Number of SLCP mitigation tools, technologies, or practices adopted | Individual or household |  |  | Number of training sessions, workshops delivered | General awarenesss
[18 empty] | Number of SLCP mitigation tools, technologies, or practices adopted | Industry |  |  | Number of training sessions, workshops delivered | Policy or planning
[22 empty] | Number of training sessions, workshops delivered | Technical skills or practices

## Form validation (hidden)
Project status | Activity status | Output status | Objective status | UNEP expenditure | Type of expenditure | Activity category | Means of verification | Reporting periods | CCAC objective | Sectors | Regions | Pollutants addressed | Resource type | Regional scope
On track | Not started | Not started | Achieved | Consultants | Contractual Services | Developing and/or delivering training | Nothing to deliver this period | 2022-01-15 | Drive an ambitious agenda | Agriculture | Africa | All SLCPs | Awareness materials | Global
Issues | On track | On track | Not yet achieved | Operating costs | Equipment Vehicles and Furniture | Organising, holding, or participating in a meeting or event | Funding proposal | 2022-07-15 | Support national action | Assessments | Asia and the Pacific | Black carbon and co-pollutants | Event documents | Regional
| Delayed | Delayed |  | Personnel | Operating and Other Direct Costs | Policy, project, or tool design | Inventory | 2023-01-15 | Support transformative actions | Bricks | Europe | Hydrofluorocarbons (HFCs) | Guidelines & tools | National
| Complete | Complete |  | Travel & workshops | Staff and Other Personnel Costs | Producing and distributing communications materials | Meeting report | 2023-07-15 | Advance policy-relevant research and analysis | Cooling | Global | Methane | Knowledge platforms | Local
[5 empty] | Supplies Commodities and Materials | Project management | Participant list with gender breakdown | 2024-01-15 |  | Health | Latin America and the Caribbean | Tropospheric ozone | Official statements
[5 empty] | Travel | Research, data collection, and/or writing | Photo or video | 2024-07-15 |  | Household energy | North America |  | Online training & related materials
[5 empty] | UN-PSC | Other | Policy paper | 2025-01-15 |  | National planning | West Asia |  | Policies, plans & regulations
[7 empty] | Policy, regulation or other guideline | 2025-07-15 |  | Oil & gas |  |  | Reports, case studies & assessments
[7 empty] | Publication | 2026-01-15 |  | Vehicles |  |  | Scientific publications
[7 empty] | Research or study | 2026-07-15 |  | Waste
Tool
Training materials
Web article
Work plan
Enable multiple choice

## Import order (hidden)
Component
Indicator
Target
Unit
Date
Delivery type
Description
Acceptance criteria
Project
Unique code
Agreement
Sector
Beneficiaries
Agreement filter
Other beneficiaries
Implementer
Delivery description
Level