# Bridges of Trust – Improving social cohesion and resilience in Bosnia and Herzegovina

# SCORE PROJECT

2025 ANNUAL REPORT

TABLE OF CONTENTS

list of Abbreviations	3

BASIC INFORMATION	4

Strategic Review and Outlook	4

Chapter 1 - Stakeholder Engagement	5

Chapter 2 – RISKS AND CHALLENGES	6

chapter 3 – Progress review and ACHIEVEMENTS AGAINST outPUTS	7

CHAPTER 4 – TRANSVERSAL THEMES: Social inclusion and gender EQUALITY	10

CHAPTER 5 – FINANCES, MANAGEMENT, AND COMMUNICATIONS	10

chApter 6 – lessons learnt AND SUSTAINABILITY	11

# list of Abbreviations

BIH ─ Bosnia and Herzegovina

BD – Brčko District of Bosnia and Herzegovina

CSO – Civil Society Organisation

EU – European Union

FBIH – Federation of Bosnia and Herzegovina

LG ─ Local Government

RS – Republika Srpska

RP – Responsible Party

SP - Service Provider

UNDP – United Nations Development Programme

USD – United States Dollar

OHR - Office of the High Representative

ToR - Terms of Reference

LDGs - Local Dialogue Groups

DFF - Dialogue for the Future Project

DANIDA - Danish Ministry of Foreign Affairs

CRG - Core Reflection Group

# BASIC INFORMATION

The "Bridges of Trust – Improving social cohesion and resilience in Bosnia and Herzegovina" (SCORE Project) is an initiative funded by the Danish Ministry of Foreign Affairs (DANIDA), aimed at fostering social cohesion, resilience, and inclusive participation in Bosnia and Herzegovina (BIH). The project is implemented by the United Nations Development Programme (UNDP) from July 2025 to December 2026.This initiative is part of a broader Danish engagement in support of media independence, civil society, gender inclusion, and social cohesion in BiH, which aligns with Denmark's goals under the Danish Finance Act for 2025.

The core objective of this project is to generate an evidence-based understanding of the social divides in BiH and create opportunities for trust-building across its ethnically fragmented society. The project leverages the UNDP’s Social Cohesion and Reconciliation (SCORE) Index, a tool that has been previously used in various global contexts, including Cyprus, Ukraine, and Moldova. The SCORE Index will provide critical data that identifies divisive narratives, social tensions, and opportunities for positive change, especially among marginalized communities like women and youth.

Given the complex socio-political landscape in BIH, characterized by entrenched ethnic divisions, political instability, and restrictive laws limiting civil society freedoms, the project aims to address these issues through three primary outputs:

- Establishing a Robust Research Framework: The project will establish comprehensive datasets on social cohesion, resilience, and inclusive participation, which will inform policy decisions and development programming in BiH. These datasets will serve as a crucial resource for addressing key drivers of division, such as misinformation, exclusion, and identity-based tensions.

- Local Oversampling and Analysis: Targeted research will be conducted at the local level, particularly in communities prone to heightened social tensions. This localized data will provide in-depth insights that will inform tailored policy responses addressing specific challenges to social cohesion and gender inclusion.

- Strengthening Local Mechanisms: The project will enhance multi-stakeholder platforms across BiH, fostering intergroup trust and providing spaces for constructive dialogue. Special attention will be given to the inclusive participation of youth, women, and marginalized groups, ensuring their voices are heard in public decision-making processes.

The underlying theory of change for the project is rooted in the belief that strengthened social cohesion, supported by inclusive dialogue and data-driven analysis, will lead to a more resilient, democratic, and peaceful society in BiH. By addressing divisive narratives, fostering mutual trust, and promoting inclusive participation, the project aims to contribute to BiH's European integration process and help unlock further funding for peacebuilding initiatives.

Ultimately, the SCORE Project seeks to build a more unified society in BiH by reducing polarization and creating an enabling environment for sustainable peace and development. Through its strategic combination of research, policy advocacy, and multi-stakeholder engagement, the project will support BiH’s long-term stability and European integration aspirations.

# Strategic Review and Outlook

As BIH continues its journey toward EU membership, social cohesion remains a critical factor for stability and long-term integration. While some progress has been made in aligning with European Union (EU) standards, particularly in areas such as rule of law, anti-corruption, and judicial reform, the country faces persistent challenges rooted in its complex political landscape and deeply ingrained ethnic divisions. These divisions, which trace their origins to the country’s post-conflict period and the implementation of the Dayton Peace Agreement, continue to hinder BiH’s development, exacerbating political fragmentation, economic pressures, and societal mistrust.

The continued prominence of divisive narratives, often linked to ethnic identity, historical grievances, and political rhetoric, presents a significant barrier to fostering mutual trust and cooperation among BIH’s diverse groups. These narratives, amplified by media and political leaders, contribute to a culture of fear, mistrust, and exclusion, particularly among marginalized groups such as women, youth, and ethnic minorities. This situation undermines efforts toward reconciliation, sustainable peace, and democratic governance, which are essential for BIH’s EU integration process.

In this context, the need for initiatives that promote social cohesion, counter divisive narratives, and build resilience against polarization is more pressing than ever. Social cohesion and the ability to address divisive narratives are fundamental to building a unified, resilient society where democratic values and inclusive governance can thrive. International development organizations, including UN agencies and EU bodies, require accurate, reliable data to effectively plan and implement programs aimed at resolving these challenges. The ability to assess the underlying causes of division and identify communities at risk of further polarization is essential for designing targeted, context-specific interventions that can foster trust, reduce tensions, and promote inclusivity.

Without a clear, data-driven understanding of the root causes of these divisions, international organizations risk implementing one-size-fits-all solutions that fail to address local dynamics or produce lasting results. This is particularly important as BIH moves closer to meeting the necessary EU integration criteria, where a more cohesive and resilient society will be crucial for the country’s stability. Efforts to promote social cohesion are integral to both BIH’s internal development and its integration into the European community. Through evidence-based analysis and localized interventions, international development organizations can support BIH in overcoming its social and political divisions, contributing to a more democratic, stable, and unified society.

# Chapter 1 - Stakeholder Engagement

At the initial stage of SCORE project implementation, key partners were identified and engaged to establish a strong and well-coordinated foundation for delivery, clearly defining their roles in supporting the rollout of project activities. By combining international expertise, local knowledge, and institutional support from the outset, the project is well-positioned to respond to the complex realities of social cohesion, governance, and reconciliation in Bosnia and Herzegovina.

From the outset of implementation, the SCORE project has brought together a diverse group of partners, each contributing in a complementary and mutually reinforcing manner.

Center for Social Cohesion and Development (SeeD) is the main implementing partner, engaged through a responsible party agreement. With strong experience in conflict resolution, social cohesion, and research in post-conflict societies, Seed ensures the methodological guidance and support, and ensures that the research approach is sensitive to the local context. Following up on studies conducted in 2014 and 2020 that utilized the SCORE Index in Bosnia and Herzegovina, SeeDs understanding of Bosnia and Herzegovina’s social and political dynamics helps ensure that findings are both relevant and practical

Prism Research, the local research partner, was selected through a transparent and open procurement procedure for its expertise in conducting research tailored to the local context. Their deep understanding of Bosnia and Herzegovina's socio-political dynamics ensures that the project’s findings are accurate and relevant. Prism has significant experience, having successfully conducted the previous two waves of the SCORE research, which provides them with a strong foundation in the methodology and context. This prior experience, coupled with their proven track record in research and data analysis, makes them an ideal partner for ensuring the effective collection, processing, and initial dissemination of data throughout the SCORE project.

Local governments (LGs) play an important role in implementing the SCORE project, supporting the project to reach out to communities and conduct a deeper dive on social cohesion in specific territories. The selection of these LGs was guided by a set of criteria that ensured geographic and demographic diversity, ethnic balance, and a strong local presence of civil society organizations (CSOs). The municipalities were selected based on their capacity to support the project’s objectives and their readiness to engage in social cohesion efforts. The ten selected LGs, including Brčko District BIH, Velika Kladuša, Doboj, Mostar, Stolac, Teslić, Srebrenica, Odžak, Prnjavor, and Jajce, are diverse in terms of population size, ethnic composition, and socio-political context, ensuring that the project captures a wide range of governance and social cohesion challenges across BiH.

In the initial stage of the project, Local Dialogue Groups (LDGs) were established in each of the selected LGs to bring together stakeholders for discussions on social cohesion challenges at the community level. In the later phases of implementation, LDGs will guide the project’s planned support, ensuring that interventions, including targeted assistance, tailored activities, and capacity-building efforts, are aligned with the specific needs of each locality. The comprehensive and strategic selection of LGs ensures that the SCORE project responds effectively to diverse local contexts, delivering impactful, locally driven solutions to governance and social cohesion challenges across Bosnia and Herzegovina.

The Core Reflection Group (CRG) under the SCORE project plays a vital role in guiding the strategic direction and ensuring the effective implementation of the research findings. Composed of key individuals and institutions active in the field of social cohesion, the CRG serves as an advisory body, offering expertise and insights on various aspects of the local context, methodologies, and activities. The CRG members are responsible for providing feedback on reviewing findings and ensuring that the research results align with broader social cohesion and governance priorities. Their role also includes contributing to the design of research, analysis, and interventions, as well as addressing any emerging challenges during the research lifecycle. Through regular meetings, the CRG facilitates coordination between different stakeholders, including UN agencies, international organizations, government ministries, and civil society institutions, ensuring that the project’s implementation is informed by a diverse range of perspectives. The CRG will also play an important role in fostering collaboration and strengthening partnerships between key institutional actors across Bosnia and Herzegovina, helping to create a more inclusive approach to social cohesion and reconciliation efforts.

The Dialogue for the Future (DFF) project, financed by the UN Peacebuilding Fund and implemented by UNDP, UNICEF, and UNESCO, serves as a key partner through a complementary set of activities at the local level. The SCORE project has ensured strong synergies and effective cooperation with DFF, particularly in localities where both projects are active (Doboj, Teslić, Stolac, and Mostar).

A major strength of the SCORE project is its collaborative approach, bringing together SeeD, Prism Research, local governments, external experts, donors, and community associations. Each stakeholder contributes distinct expertise and resources, enabling the project to deliver meaningful, evidence-informed, and sustainable results.

# Chapter 2 – RISKS AND CHALLENGES

In 2025, the SCORE Project encountered several risks that impacted its implementation, particularly in terms of timing and the availability of surveyors in specific localities. These challenges were both contextual and programmatic in nature, leading to limited delays and complications during the initial phase of the project.

Political instability, especially in RS entity, created a tense operating environment, and in some instances, local authorities demonstrated a degree of resistance to participation, adding further complexity to project implementation. In addition, the human capital gap caused by outward migration, particularly among youth and young women, made it challenging to recruit sufficiently skilled personnel to conduct the SCORE survey. This shortage of skilled enumerators for data collection, combined with the compressed timelines for Cycle 1 implementation, led to minor delays in field activities and created bottlenecks within the overall survey process. Despite these obstacles, the exceptional commitment and coordinated efforts of all parties involved ensured that delays were kept to an absolute minimum and will not affect the timely progress of subsequent activities.

Another major issue arose from the reliance on 2013 census data, which is now outdated and no longer reflective of the current demographic landscape. The census data did not account for significant population movements, including emigration and youth migration, especially from rural areas. This made it particularly challenging to locate and survey youth, a key demographic for understanding social cohesion in rural areas.

Additionally, the Croat population in some municipalities, such as Odžak, was underrepresented in the available data, requiring additional efforts to locate these citizens and ensure a balanced sample. Moving forward, it will be critical to address these challenges by adjusting data collection methodologies and timelines and investing in capacity-building to ensure the success of the project and its long-term impact on social cohesion and policy reform.

# chapter 3 – Progress review and ACHIEVEMENTS AGAINST outPUTS

Output 1: Robust research framework and publicly accessible datasets on social cohesion, resilience, and inclusive participation are established and used to inform policy decisions and development programming in Bosnia and Herzegovina

In 2025, the project established a robust research framework on social cohesion, resilience, and inclusive participation toward achieving its Output 1. This output is pivotal for generating evidence-based insights to inform policy decisions and development programming throughout the country.

A key development in Q3 2025 was the adaptation of the SCORE methodology to Bosnia and Herzegovina’s unique socio-political context through collaboration with SeeD, a Cyprus-based think tank recognized as the global host of the SCORE methodology. This partnership ensured that the methodology was highly relevant to the country's dynamics, integrating local realities and addressing emerging societal challenges such as intergroup tensions and political instability.

In collaboration with UNDP, SeeD thoroughly reviewed and refined the research methodology, ensuring that the SCORE framework accurately captured the dynamic political landscape of Bosnia and Herzegovina. Leveraging SeeD's extensive experience with previous SCORE implementations in the country (2014 and 2020), the methodology was further tailored to address the current challenges, such as intergroup tensions, social divides, and barriers to civic participation. This adaptation not only allowed for more precise tracking of trends but also facilitated the identification of emerging hotspots across the country. A key innovation in this iteration of the SCORE methodology was the inclusion of 10 booster localities, which focused attention on regions critical to social cohesion. These localities were selected for their relevance to social integration issues and the involvement of various development actors, offering a deeper understanding of localized challenges.

The research design included consultations with civil society organizations (CSOs), government institutions, and community stakeholders to ensure the framework was both contextually relevant and reflective of BIH’s socio-political dynamics. The SCORE questionnaire was updated to include questions that addressed recent phenomena while maintaining continuity for longitudinal analysis.

The process of adapting the methodology and establishing the Core Reflection Group (CRG), the body responsible for shaping the design of research, analysis, and interventions, as well as addressing any emerging challenges throughout the research lifecycle, was a critical prerequisite for the successful launch of field research activities. The inaugural CRG meeting took place in October 2025, where extensive discussions led to further refinement of the methodology. As a result, the approach was fine-tuned to more accurately align with the specific contextual needs of the project, ensuring its relevance and effectiveness in addressing the unique challenges at hand.

To ensure national representativeness, the sample design was meticulously developed using stratified random sampling across 15 geographic regions. In addition, the research incorporated booster samples targeting 10 municipalities with fragile intergroup relations and elevated social tensions. This approach allowed the project to capture a comprehensive and nuanced picture of the socio-political landscape. The sampling size and structure were carefully optimized to ensure robust findings, minimizing the potential for error while providing reliable and actionable insights.

Immediately after the project began, the project team conducted a rigorous and transparent selection process for a local service provider and Prism Research was selected and contracted in early November 2025. Prism Research enumerator training took place in October 2025, ensuring that field staff were adequately prepared for data collection. The field research phase began in November 2025, with SeeD providing continuous technical assistance and quality control. The enumerators followed strict protocols to ensure the accuracy and reliability of the collected data.

By the end of December 2025, the first wave of data collection was completed. SeeD ensured that the fieldwork adhered to the highest standards of quality control. Following data collection, the data were cleaned, and preliminary analysis began. Additional follow-up research was conducted in certain regions where initial sampling had proven insufficient, such as Posavina and Odžak municipality, where follow-up fieldwork was needed due to sampling gaps.

Furthermore, in support of the project, a resource person from Ukraine with a strong background in SCORE methodology was engaged to provide expert technical support to the local team. This brought additional expertise to the project, particularly in navigating the complexities of implementing research methodologies in a politically sensitive and divided environment.

Preliminary findings from the first wave of data collection will be shared with the CRG in early 2026. These findings will form the foundation for the Social Cohesion Trends & Changes Report, which will provide critical insights into trends such as identity dynamics, intergroup cooperation, and civic engagement.

By the end of 2025, the SCORE Project successfully established a solid research framework and laid the groundwork for future evidence-based interventions. This will serve as an essential resource for policymakers, development practitioners, and civil society organizations working to address divisions and promote long-term stability in Bosnia and Herzegovina.

Output 2: Targeted oversampling and analysis at the local level, in communities prone to heightened social tensions, to generate in-depth local insights that inform tailored policy responses and address context-specific challenges to social cohesion and gender inclusion.

The municipalities selected for the Booster SCORE Survey were proposed by the project team and formally approved by the Project Board (PB). These municipalities were strategically chosen to ensure both national representativeness and local relevance. The selection process considered geographic, demographic, and socio-political factors to create a balanced mix of urban and rural municipalities with varying ethnic compositions and levels of social cohesion. The chosen municipalities included Brčko District BIH, Velika Kladuša, Doboj, Mostar, Stolac, Teslić, Srebrenica, Odžak, Prnjavor, and Jajce. These locations were selected to represent a cross-section of Bosnia and Herzegovina’s complex social and ethnic landscape, with a particular focus on areas that have experienced historical intergroup tension, low civic participation, and the need for targeted interventions. The only exception to this process was Čapljina, which declined participation.

The project’s approach to municipal selection was aligned with the SCORE methodology, ensuring that the sample was both statistically robust and contextually meaningful. The municipalities represented both entities, FBIH and RS, as well as Brčko District BIH, guaranteeing equitable geographic representation across regions. The selected municipalities also include a range of socio-political dynamics, from urban centers like Mostar and Doboj to smaller, rural areas such as Stolac, Prnjavor, and Odžak. This diversity ensures that the project captures variations in social cohesion, governance challenges, and community engagement across BiH.

In 2025, the SCORE Project made significant strides in its efforts to improve social cohesion, resilience, and inclusive participation at the local level. A major milestone was the successful establishment of 10 LDGs across selected municipalities, which were formally institutionalized through mayoral decisions. These LDGs, consisting of representatives from youth and women’s organizations, local civil society organizations (CSOs), and municipal officials, were designed to serve as consultative bodies. The total number of members across the 10 LDGs in the selected municipalities is 150.

The role of LDGs is to advise on local priorities, provide feedback on project activities, and contribute to the development of interventions that are closely aligned with community needs.

The Booster Survey, as an additional, targeted survey, was conducted in the aforementioned municipalities to provide deeper insights into local dynamics, particularly in areas with heightened social tensions or historical interethnic conflict. It particularly focused on issues such as intergroup relations, youth engagement, and women’s participation. This data is critical for understanding local challenges and tailoring future interventions to address the most pressing needs. By oversampling in these municipalities, the project ensured enhanced statistical precision and the generation of actionable insights at the municipal level.

The SCORE project also aims to enhance the capacity of local authorities and CSOs to drive social cohesion efforts within their communities. To achieve this, the project is committed to transferring ownership of social cohesion initiatives by actively involving LG authorities in the selection and establishment of LDGs, and engaging local CSOs in the design and implementation of interventions. Local stakeholders played a pivotal role in shaping the direction of future activities and the allocation of project grant support for 2026. This collaborative approach not only strengthens community involvement but also ensures that the project's impact will be enduring and sustainable over the long term.

As the SCORE Project moves into 2026, the data collected from the Booster SCORE Survey and the insights from the LDGs will provide the foundation for targeted interventions in municipalities with the greatest need. The project will continue to work closely with local authorities, CSOs, and other stakeholders to ensure that interventions are tailored to the specific challenges of each community. This process will not only address the current issues facing these municipalities but will also help strengthen their ability to lead social cohesion efforts independently in the future, ensuring the sustainability of the project’s outcomes in Bosnia and Herzegovina.

Output 3: Enhanced local mechanisms and multi-stakeholder platforms in place across Bosnia and Herzegovina to foster intergroup trust, counter divisive narratives, and support inclusive participation of underrepresented groups, particularly women and youth in public decision-making.

Throughout 2025, the SCORE Project focused on identifying local CSOs, particularly those led by youth and women, and assessing their capacity development needs. This was achieved through field research, including a gender-sensitive mapping of key civil society actors in 10 targeted municipalities, which identified 58 grassroots organizations with experience in reconciliation, civic participation, and local development. Extensive consultations with local stakeholders helped pinpoint organizations capable of leading or collaborating on community-based initiatives for social cohesion. A capacity assessment was conducted alongside this mapping to evaluate the operational strengths of these organizations. The findings will guide the design of tailored capacity-building initiatives in 2026, empowering local CSOs to lead and implement impactful projects that foster social trust, resilience, and long-term cohesion in their communities.

A flexible grant mechanism using the Low-Value Grant Agreement (LVGA) modality is planned to be launched in 2026 to support community-driven initiatives. This mechanism will allow for quick and flexible support to grassroots actions that foster trust and cooperation between communities. This sub-granting mechanism will be used to support activities such as youth dialogues, cultural events, and small-scale community projects that encourage cross-community engagement. This work is closely aligned with complementary initiatives, including those funded by the UN Peacebuilding Fund (PBF), fostering strong synergies and mutual reinforcement between projects. By actively collaborating with these efforts, the SCORE Project ensures that resources and expertise are maximized, particularly in the four common LGs, where targeted initiatives are mutually supportive. This approach not only enhances the overall impact of the projects but also strengthens the collective capacity to drive social cohesion and reconciliation, creating a more integrated and cohesive framework for sustainable development across the region.

Further, the project has started preparations for amplifying positive narratives in the public sphere by curating and disseminating stories that highlight interethnic cooperation and youth and women’s leadership in strengthening social cohesion. Through partnerships with civil society groups, youth networks, and media outlets, these stories will be shared via both traditional and digital platforms, aiming to reach marginalized communities and counter divisive narratives. This effort will empower local actors to shape the narrative, spotlighting examples of coexistence and collaboration that inspire positive change.

# CHAPTER 4 – TRANSVERSAL THEMES: Social inclusion and gender EQUALITY

Social inclusion has been at the core of the SCORE project since its launch in the summer of 2025. Although the scope of activities was limited in the initial year, the project has made significant strides in fostering communities where all individuals, regardless of their background or identity, feel valued, safe, and empowered. Throughout 2025, the project focused on creating environments of trust, respect, and belonging, particularly through the establishment of 10 LDGs in 10 partner LGs. These groups have provided marginalized communities with a platform to share their concerns, encourage active participation, and lay the foundation for stronger community cohesion.

Although the project is in its early stages, efforts to engage socially excluded groups in local decision-making processes were initiated. These early activities have begun to promote more inclusive representation, with local governments expressing a commitment to addressing the needs of these groups in future initiatives. Gender equality remained a central priority, with initial actions aimed at ensuring women's participation and empowering them in the community. This ongoing dedication to gender equality has set the foundation for more comprehensive efforts, contributing to the creation of more resilient, inclusive communities as the project progresses.

# CHAPTER 5 – FINANCES, MANAGEMENT, AND COMMUNICATIONS

In the first year of the SCORE Project (2025), initial implementation was focused on setting the foundation for the research framework and identifying key local stakeholders. The project’s activities are fully financed by the grant from the Danish Ministry of Foreign Affairs (MFA/EUNABO), officially covering the period from July 2025 to December 2026.

The total expenditure for the period from the project's start in July until December 31, 2025, is USD 129,573.76. The budget balance on 31st December 2025 was USD 1,423,035.63. These figures are still the subject of possible minor changes since the final formal finance data are not yet available.

Management and communications

The project gradually developed since its initiation in July 2025, with responsibilities initially designated during the early stages. The project team was fully staffed in early November, when the Project Analyst was added to the team of the Project Manager and Project Associate. The first Project Board meeting took place in October, during which the work plan was officially approved.

During this phase, the project focused on initiating key activities under Output 1, including establishing the research methodology and engaging with local civil society organizations.

In 2025, the SCORE Project maintained a low public profile during its initial implementation period, as outlined in the draft Communication Plan developed in October 2025. This approach allowed the team to focus on establishing the research framework, completing data collection, and building key partnerships ahead of the project's public-facing phase.

Communication activities in 2025 focused on preparing the ground for the project's public engagement in 2026. This included coordinating with partners on the deployment of the third SCORE survey wave, preparing presentations for focus group discussions in five municipalities, and engaging with stakeholders ahead of the planned publication of findings.

The communication strategy aimed to position the SCORE Project as an evidence-based platform for strengthening social cohesion and resilience in Bosnia and Herzegovina. The project ensured visibility for UNDP and the Danish Government, with their roles as implementing agency and donor clearly acknowledged across all materials. The Communication Plan established key messages, target audiences, visual identity standards, and the donor acknowledgement framework to guide all outreach activities.

In 2026, communication efforts will shift toward the phased release of SCORE findings, including national and local presentations of results, the publication of the Social Cohesion Trends & Changes Report, and promotion of local initiatives in the ten booster municipalities. Social media platforms, the UNDP BiH website, and national and local press will serve as primary channels, with engagement metrics used to evaluate effectiveness and adjust outreach accordingly.

# chApter 6 – lessons learnt AND SUSTAINABILITY

In 2025, during initial steps in project implementation, the SCORE Project faced several challenges that provided valuable lessons for future implementation.

1. Tailored approaches for diverse local contexts: The project highlighted the importance of a tailored approach in addressing the unique needs of each local government and community. What worked in one municipality often did not apply in another, due to varying socio-political dynamics, demographic compositions, and governance capacities. The establishment of LDGs was crucial, as it allowed the project to adapt to each municipality’s specific challenges, ensuring that solutions were locally driven and context-specific. Moving forward, further customization and flexibility will be key to meeting diverse community needs.

2. Importance of local ownership and engagement: A key lesson learned was the necessity of local ownership for the sustainability of the project’s outcomes. The involvement of relevant institutions, academia representatives, LGs and CSOs in processes and the establishment of LDGs helped ensure that the solutions were not only relevant but also embraced by local communities. As the project progresses, strengthening local leadership and deepening engagement will be critical to maintaining momentum and ensuring that social cohesion initiatives are sustained over the long term. Cross-Institutional Collaboration between key institutional partners, such as the BiH Ministry of Civil Affairs, LGs, and CSOs, is vital for fostering broad-based support and achieving lasting social change.

3. Challenges with outdated data and recruitment difficulties: The reliance on outdated 2013 census data created challenges in accurately capturing the current demographic landscape, particularly in rural areas and for marginalized groups. These discrepancies made it difficult to target key populations, such as youth, and ensured that the project’s survey processes encountered significant delays. Going forward, the project will need to adopt more current data sources and improve recruitment strategies to ensure more accurate data collection.

4. Continuous feedback and communication: Effective communication and feedback mechanisms were critical in building trust within communities. When local governments implemented projects based on community input, it led to increased engagement and positive outcomes. Moving forward, ensuring timely communication of both successes and setbacks, coupled with a strong feedback mechanism, will enhance trust and sustain community involvement in decision-making processes.

These lessons learned have shaped the project’s approach in 2025 and will continue to guide future phases of the SCORE Project, ensuring that activities are more adaptable, sustainable, and impactful in addressing the challenges of social cohesion and inclusive governance across Bosnia and Herzegovina.

Preliminary finance report is attached to this narrative report.