Funding Windows Proposal Template

(Maximum 5 pages of narrative + Work Plan)

The UNDP Funding Windows provide flexible resources to COs through four pooled thematic funds:

- Poverty and Inequality

- Governance, Peacebuilding, Crisis and Resilience

- Nature, Climate and Energy

- Gender Equality and Women’s Empowerment

Proposal Format

- If the team/CO is requesting resources for an existing project(s), use this proposal template to explain the rationale for FWs resources and clearly identify the outputs and activities that will be delivered with FWs resources. The project(s) can be at global, regional and/or CO-level. Please insert the project title(s) and share the project document(s) for all projects associated with this proposal.

- If the team/CO is requesting funding for a new project, please use this proposal template as an intermediary step and use the latest UNDP project document template to prepare your project document.

All proposals must comply with corporate programming standards outlined in the POPP, including UNDP’s Social and Environmental Standards (SES) programming principles and screening procedure.

The quantum project setup should follow UNDP Quantum setup guidance from POPP Quantum Project Creation Process Overview and Quantum Project Setup - Training Recording Link.

Country/Context*: Tunisia and Mongolia

Operational Overview

Proposal Title*:	Accelerating integrated implementation of climate and biodiversity goals through food systems transformation

Funding Windows (FWs) resources will support (please check one) *:

☒  An ongoing output within an existing Prodoc

☐  A new output within an existing Prodoc

☐  A new Prodoc (please provide estimated PAC date)

Linked SDG Goal(s) and Target(s): SDG 1 (1.5), SDG 5 (5.c), SDG 6 (6.5, 6.a), SDG 7 (7.2, 7.3, 7.a, 7.b), SDG 8 (8.4, 8.6), SDG 11 (11.3, 11.5, 11.6, 11.a, 11.b), SDG 13 (13.1, 13.2, 13.3, 13.a, 13.b), SDG 14, SDG 15 (15.2)

Linked SP Moonshot(s): NA

Linked Strategic Plan Output*:

Output 1.1. The 2030 Agenda, Paris Agreement and other intergovernmentally- agreed frameworks integrated in national and local development plans, measures to accelerate progress put in place, and budgets and progress assessed using data-driven solutions

Linked Strategic Plan Indicator*:	 Indicator 1.1.2: Number of countries that have policy measures in place to enable the enhancement and/or implementation of Nationally Determined Contributions under the Paris Agreement

Linked Flagship target(s)*:	 # of countries with policy measures in place to enable the enhancement and/or implementation of NDCs [Target 30]. UNDP will support at least 140 countries to integrate nature into their national development and spatial and sectoral plans and practice with gender-responsive approaches (Nature Pledge).

Linked CPD Output(s):	 		TBC

Expected FW funding duration*:		12 months

Technical Engagement and Endorsement

Names and expertise of the experts who have contributed to this proposal:

- Gender*:			Verania Chao, Gender Specialist, Climate Hub

- M&E/RBM*:			Bianca Tejada, M&E Specialist, Nature Hub

- Youth:				Click or tap here to enter text

- Environment/Climate:		Click or tap here to enter text

- Other Technical expertise*:

- Global/Regional Hub thematic focal point*: James Leslie, Nature Hub and Claudia Ortiz, Climate Hub

- RB advisor/country desk*:

- Abdullah Zahiruddin Ahmad (Amman Regional Hub)

- Benjamin Basmaci (Amman Regional Hub)

- Thomas Pitaud (RBAS)

- Tashi Dorji (Bangkok Regional Hub)

- Akiko Yamamoto (RBAP)

- Global Substantive Lead for Flagship*:	Midori Paxton, Director Nature Hub and Cassie Flynn, Director Climate Hub

Department ID: 	Click or tap here to enter text.

Quantum Project Award: Click or tap here to enter text

Project/Output ID(s):	Click or tap here to enter text.

Gender Marker*:	3

Total resources required*:	US $1,000,000

Total allocated resources: Click or tap here to enter text

- Regular:	Click or tap here to enter text

- Other:

  - Funding Windows*:	 US $1,000,000

  - Government:	Click or tap here to enter text

  - Other donor(s):	Click or tap here to enter text

Unfunded budget: 	Click or tap here to enter text

In-kind contributions: 	Click or tap here to enter text

* required fields

Brief Description (200-250 words)

Healthy ecosystems and biodiversity are the foundation of sustainable development. Since the 1992 Rio Conference, various reforms have been pursued to promote green transitions, nature-based solutions, net-zero targets, and sustainable finance. However, the diverse approaches and financial instruments have led to fragmented policy frameworks, resulting in duplication and competition for resources. An integrated approach, leveraging synergies between Nationally Determined Contributions (NDCs) and National Biodiversity Strategies and Action Plans (NBSAPs), is essential for efficient resource allocation and achieving synergies at the climate-nature-development nexus, particularly in sectors like food and agriculture.

The project aims to drive transformational change by strengthening policy and finance coherence at the national level, and delivering on national priorities and targets captured in NDCs and NBSAPs by ensuring that agriculture and food systems contribute simultaneously to biodiversity conservation and climate action. In Tunisia and Mongolia, agriculture and food production are identified as key priorities in their NDCs and NBSAPs, particularly given they have led to biodiversity loss due to unsustainable practices and weak governance. The project seeks to deliver these priority targets and measures by embedding biodiversity and climate considerations into national development policies, aligning financial strategies, and enhancing inter-ministerial and inter-stakeholder collaboration.

To turn these targets into action with a focus on the food and agriculture sector, the strategy involves optimizing finance for nature-based solutions in food and agriculture, strengthening capacities for collaborative action, and developing policy reforms. The project also focuses on engaging marginalized actors, particularly women, in policy-making and enhancing collaboration for strategic investments. Expected results include strengthened coherence among biodiversity, climate, and food systems policies, aligned financial incentives, improved governance, and increased participation of women and girls in shaping nature-positive, climate-resilient food systems. This comprehensive approach aims to create positive outcomes for people, climate, and nature.

Allocation Proposal

# Development Challenge (1/2 page)

Since the 1992 Rio Conference, sustainability is widely recognized as indispensable for human development, emphasizing the critical role of healthy ecosystems and biodiversity for thriving societies. To address these issues, reforms promoting green transition, nature-based solutions, net-zero targets, and sustainable finance, among others, are being pursued to mitigate environmental impact and support sustainable development.

However, proliferating approaches remain as varied and diverse as the financial logics and instruments that aim to facilitate their implementation. We need to avoid further splintering of policy frameworks that, at best, address climate, nature, and sustainable development in parallel in within separate discursive forums or, at worst, compete against each other for scarce public and private resources. Any distinction between climate and nature in terms of policy and finance appears rather artificial, and could lead to duplication, overlap, and double-counting.

Hence, an integrated approach triangulating coherent policies such as Nationally Determined Contributions (NDCs) and National Biodiversity Strategies and Action Plans (NBSAPs), which are at the heart of the Rio Convention, and their financial frameworks are necessary to achieve efficient resource allocation processes and mechanisms conducive to synergies and mutually reinforcing effects at the epicenter of the climate-nature-development nexus. This is particularly important in key sectors where this nexus is vital and stand as high priorities in countries’ self-defined NDCs and NBSAPs, namely food and agriculture. Moreover, targeted financial planning in the food and agriculture sectors—aligned with national climate and biodiversity commitments—enables countries to identify investment priorities, build resilience in rural communities, the most vulnerable and unlock international support from climate and development finance mechanisms. It also strengthens institutional coordination and enhances the ability to monitor and evaluate progress in a transparent and accountable manner.

Agriculture and food-related policy is shaped by multiple ministries and agencies, such as Agriculture, Production, Trade, Environment, Forestry and Energy, as well as Planning and Finance, among others. However, these entities often administer policies that are unaligned and even contradictory, and they fail to coordinate policy delivery, such as through integrated public finance programming. This fragmentation results in policy conflicts, where economic, social, agriculture and trade policies undermine biodiversity and climate goals. While National Biodiversity Strategies and Nationally Determined Contributions may identify solutions, siloed decision-making and limited stakeholder engagement persist, leading to disconnected and dispersed actions.

In both Tunisia and Mongolia, the expansion and intensification of agriculture and food production has become a leading driver of biodiversity loss, exacerbated by the indiscriminate use of agrochemicals, deforestation, land degradation, and weak governance mechanisms. In Mongolia, public policies and subsidies have led to overstocking and unsustainable grazing, accelerating land degradation. Pasturelands are treated as inexhaustible resources, a mindset that extends from herders to policymakers. Despite the existence of the Livestock Tax Law and Natural Resource Use Fee Law, these biodiversity finance instruments remain either poorly implemented or politically sensitive.

Similarly, in Tunisia the agricultural and food sectors are major employers and key sources for rural livelihoods, yet it is increasingly affected by drought, land degradation, shifting climate patterns and fragmented policies that does not prioritize integration between nature, biodiversity and climate. Meanwhile, Tunisia’s agricultural and food sector is hindered by inefficient policies that disproportionately favor large-scale producers through subsidies, trade protection, and preferential access to land and credit, while marginalizing smallholder farmers who make up the majority of the rural population. These policies have led to distortions in production and trade, inefficiencies in resource allocation, and a reliance on costly subsidies that do not effectively reach the most vulnerable. Furthermore, limited access to formal credit and inadequate financial support weaken the resilience of small farmers, exacerbating rural poverty and unemployment.

This project helps these two countries to apply a sustainable food systems approach to improve biodiversity and climate outcomes aligned with the Kunming-Montreal Global Biodiversity Framework (K-M GBF) and the Paris Climate Agreement – delivering NBSAPs and NDCs. It aims to strengthen policy coherence and align financial strategies or frameworks such as biodiversity finance plans, NDC finance strategies and Integrated National Financial Frameworks (INFFs) at the national level so that agriculture and food systems support biodiversity, climate and development goals.

# Strategy (1/2 page)

The challenges described above point to a larger systems failure: while Tunisia and Mongolia have made strong commitments to climate and biodiversity goals, food systems continue to drive biodiversity loss, land degradation, and rural inequality. This is not due to a lack of vision—both countries are updating their NBSAPs and NDCs with ambitious targets—but because the policies, institutions, and financing needed to implement them remain fragmented, under-resourced, and disconnected from rural realities.

The project’s objective is to accelerate the implementation of NDCs and NBSAPs by addressing these underlying barriers to food systems transformation.

UNDP’s theory of change is that if governments can align food, climate, and biodiversity policies; develop coherent financial strategies that support nature-based and climate-resilient agriculture; strengthen governance and cross-sectoral coordination; and increase the participation and leadership of women in food systems governance—then they will be able to accelerate the implementation of their NDCs and NBSAPs through food systems transformation. This acceleration is essential for enabling food systems to become key drivers of biodiversity protection, climate resilience, and inclusive rural development.

First, policy coherence is essential, as existing strategies often work at cross-purposes. For example, food production and trade policies may encourage practices that undermine biodiversity goals, while national frameworks such as NDCs and NBSAPs call for reduced deforestation, restoration of ecosystems, and closing yield gaps. Aligning these objectives across strategies such as the NDCs and NBSAPs will support more coordinated implementation and help reduce contradictions between policy areas.

Second, aligning financial frameworks is equally important, as current subsidy structures and public investments frequently reinforce unsustainable agricultural models and fail to support smallholder farmers. By developing integrated financing strategies—using tools such as the Integrated National Financing Framework (INFF)—the project will help redirect finance toward nature-based solutions in food and agriculture that also promote resilience and equity.

Third, governance and coordination must be strengthened. Ministries often operate in isolation, and policy delivery is fragmented across sectors. The project will support institutional reforms and collaborative mechanisms that enable joint planning and implementation across agriculture, environment, finance, and other relevant sectors—helping countries move from siloed actions to systemic change.

Finally, the meaningful inclusion of women is critical to food systems transformation. Despite their central role in food production and rural livelihoods, women often lack access to land, finance, and leadership opportunities. This project will strengthen women’s participation in food systems governance, support women-led organizations and enterprises, and ensure that national strategies reflect their needs and priorities. By addressing these systemic barriers, the project will contribute to more equitable and durable outcomes.

# Results and Partnerships (1.5-2 pages)

Expected Results

Achieving biodiversity and climate-positive food systems requires a whole-of-government, whole-of-society approach that integrates and aligns food systems-related national policies, public finance and governance with integrated nature-climate solutions. This approach focuses on 4 key results for success, to be achieved through execution of the corresponding indicative activities:

- Strengthened coherence among biodiversity, climate and food systems policies, facilitating accelerated implementation of NBSAP, NDC, LDN, and NAP.

  - Conduct policy analysis to identify existing gaps and entry points, including on gender equality, to strengthen alignment of food systems policies with NDC, NBSAPs, LDN, and NAP

  - Strengthen government and stakeholder capacity on the nature- climate nexus in food systems and gender-responsive policy planning.

  - Develop roadmap to strengthen policy coherence across biodiversity and climate in food systems, with support of enhanced and inclusive multi-stakeholder coordination spaces and governance mechanisms.

  - Draft and implement monitoring, learning and evaluation plan to measure progress towards policy coherence

- Financial incentives aligned and coherent financing frameworks (for public and private funding flows) developed for gender-responsive, nature-based climate solutions and investments in food systems.

  - Assess costs for addressing food and agriculture sectoral targets in NDC and NBSAP, including on gender, to define a common funding and financial framework; use the INFF as a platform to address trade-offs and synergies between revenue, expenditure and financing policies.

  - Identification/mapping of subsidies harmful to biodiversity and climate, and develop concrete policy recommendations for their reform or redirection.

  - Develop investment case for private sector and agribusiness to engage in nature-based and gender-responsive climate solutions for food and agriculture

  - Engage the private sector and agribusinesses, supported by risk-informed political economy analysis, to integrate biodiversity and climate risk management into business and investment decisions.

- Strengthened food systems governance and inter-ministerial collaboration that facilitates integration of gender-sensitive, nature-based climate solutions in agricultural and economic planning, linking up to the NBSAP and NDC.

  - Assess the overall baseline state of existing governance structures, multistakeholder collaboration spaces and mechanisms that influence food systems, climate and biodiversity policies, including through identification, mapping and analysis of stakeholder engagement and power dynamics, including on gender equality.

  - Develop recommendations for enhancing representation and effective participation of relevant stakeholders – with special attention to women, youth, Indigenous Peoples and local communities – in governance mechanisms.

  - Co-design and implement with relevant public and private stakeholders country-specific capacity building plans for effective collaborative action for more sustainable and climate resilient agricultural practices

- Women and girls' priorities, rights, needs and capacities related to shaping nature-positive, climate-resilient food systems are addressed and strengthened and asset ownership is increased.

  - Conduct a gender-responsive and socially inclusive climate cost-benefit analysis to understand the different impacts and opportunities of biodiversity and climate policies on women at the national level, specifically in context of food systems.

  - De-risk investments through seed funding in women-led projects and enterprises focused on nature-based climate solutions in food systems.

  - Promote women’s rights, including land rights, and strengthen the capacities of women and women-led organizations to participate effectively in food systems governance mechanisms and multi-stakeholder collaboration.

Resources Required to Achieve the Expected Results

To achieve the expected results, the resources needed include financial resources, technical expertise, and human resources. Funding is necessary for implementing on-the-ground activities, including for covering the venues for trainings, meals, travels, other services (eg. External support for producing communication products). Technical expertise in nature-positive and climate-resilient food systems and related specific topics (eg. Inter-stakeholder power dynamics, integrated finance frameworks) will be needed. Human resources, including project management staff, national coordinators, and local facilitators, are crucial to ensure the effective engagement of stakeholders, adherence to timelines, and adaptation of interventions based on real-time feedback. Additionally, partnerships with governments, civil society and private sector may be needed to provide specialized support and extend project outreach.

| Co-Funding source(s) | Amount | Existing or expected? | Additional information (duration of co-funding, specific thematic area, etc.) |
| --- | --- | --- | --- |
| MONGOLIA |  |  |  |
| WB | USD30 Million | Existing | 1st phase 2020-2025, Value Chain Commercialization, aims to improve livestock productivity and increase the volume of livestock products that meet market requirements on quality and food safety standards, and has the following sub-components: (i) Livestock Productivity; and (ii) Productive Partnerships. |
| EU German Federal Ministry of Economic Cooperation and Development | 4.5M Euro | Existing | STREAM - Sustainable Resilient Ecosystem and Agriculture Management in Mongolia: 1st phase- 2021-2025, second phase until 2028. aims at increasing the capacity of Mongolian communities to implement innovative and sustainable long-term landscape management to address food system challenges and climate stresses. |
| Germany | USD0.5M | Existing | BIOFIN: Screening negative financial flows into nature and exploring greening options of food system investments. |
| GCF | USD23Million | Existing | ADAPT- Improving adaptive capacity and risk management of rural communities: Until March 2028, Value chain and market access support of livestock products, development of Livestock sector policy, supporting climate risk informed decision making. |
| UK funded | USD250k | Existing | Climate Promise 2: Supporting the development of Long term low emission development strategy, Development of NDC 3.0 Adaptation targets, overall finance and investment plan for NDC 3.0. |
| GEF-8 | USD 463K | Existing | NBSAP Support Programme: Supporting updating NBSAP aligned with new GBF and 7th national reporting to CBD. |
| GEF-8 | USD3.2M | Expected | Eliminating hazardous chemicals from supply chain: Innovative, regenerative products are available and designed using circular business models. Sustainably sourced, innovative, responsibly managed, recycled and recyclable materials, regenerative or nature-based where possible, are used in products. |
| TUNISIA |  |  |  |
| GCF | USD 2M | Existing | National Adaptation Plan: Delivers technical support for Tunisia’s National Adaptation Plan (NAP) into key dimensions of Tunisia’s development planning processes, including socio-economic planning and land-use planning, at both national and sub-national levels. The project also contributes to the development and formal adoption of the National Adaptation Framework and the integration of climate-risks into the National Economic and Social Development Plans as well as the Master Land-Use Plan, as well as the identification and incorporation of climate change risks and adaptation needs into relevant planning instruments. |
| GEF-8 | USD 314K | Existing | BIOFIN: Supports Tunisia in developing and implementing tailored strategies to finance biodiversity conservations by identifying funding gaps and aligning public finance expenditure and private financial flows with national biodiversity goals. |
| GCF | USD 721.5K | Expected | NDA Readiness: Supports the Government and builds capacities of key institutions, strategic frameworks and enabling environments to effectively implement its NDC 3.0, while fostering low-emission and climate resilient development. |
| Spain | USD 300K | Existing | Climate Promise – Pledge to Impact Delivering technical support for the formulation and refinement of NDC 3.0, with a focus on ensuring coherence between adaptation and mitigation targets and developing an integrated finance and investment framework to facilitate its effective implementation. |
| GEF-8 | USD 463.6K | Existing | NBSAP Support Programme: Update and support in delivering technical capacity to the government on the National Biodiversity Strategy and Action Plan, as well as the 7th National Report on the implementation of the Convention on Biological Diversity and the Kunming Montreal Global Biodiversity Framework in Tunisia. |
| GCF | USD 1M | Existing | National Adaptation Plan “Food Security and Adaptation Priorities in the Agricultural Sector in Tunisia” This project is being implemented in coordination and complementarity with NAP GCF readiness proposal it is led by the Ministry of Local Affairs and Environment and the Ministry of Agriculture, Hydraulic Resources and Fisheries (MARHP) with the support of FAO. This project aims to enhance the resilience of the agricultural sector — encompassing water resources, land, crop production, livestock, fisheries, aquaculture, and forestry — along with rural communities and food security. This will be achieved by fostering an enabling policy and institutional environment and implementing integrated, evidence-based adaptation programs to address the impacts of climate change. |

Partnerships

The project is grounded in a whole-of-government and whole-of-society approach to strengthen coherence between food systems, biodiversity and climate policies. In Mongolia and Tunisia, the project will partner with the ministries of Agriculture, Environment, Finance, Planning and Gender to align NBSAP and NDC targets with food systems reform. In Mongolia, the project builds on UNDP-supported agricultural policy reforms and the current work of the White Gold Initiative Platform. In Tunisia, it will build on UNDP-supported initiatives under the NPSA&7thNR and BIOFIN projects, including efforts to mainstream biodiversity into public finance, enhance the integration of NBSAP and NDC targets in agricultural and climate planning, and promote sustainable practices through national subsidy reform dialogues and multi-stakeholder platforms. The project will be carried out in coordination with existing projects and studies: GCP/TUN/043/GCR: National Adaptation Plan: Food security and adaptation priorities in the agricultural sector / TUNISIA'S FOOD SECURITY in 2035 ( ITCEQ study), and on National Adaptation Plan: Advancing risk-informed development and land-use planning in Tunisia.

The project will aim to engage the United Nations Convention to Combat Desertification (UNCCD) Secretariat, offering support to connect the outcomes of the COP16 held in Saudi Arabia with the priorities outlined for the upcoming COP17 in Mongolia. The project will engage development finance institutions such as the World Bank, IMF, where there is a particular good relationship at RBAS level, in addition to national development banks, linking food systems financing with INFFs and the public finance framework. Early conversations are ongoing with Germany, Norway and the Government of Saudi Arabia to attract bilateral investment to support scaling and replication.

Communications and Advocacy

A strategic communications and advocacy plan will raise visibility and promote the funding windows, including donor’s contributions to food systems transformation to attract co-investment. The project will leverage global milestones, including UNFSS+4 (Ethiopia), COP30 (Brazil) and the UNCCD COP17 (Mongolia) to showcase alignment of national food systems policies, finance and governance with biodiversity and climate targets. National and global stories, including those highlighting women-led cooperatives, youth innovations, and Indigenous participation, will be shared through newsletters, social media and blogs. Target products, such as spotlight briefs and donor-specific updates, will demonstrate impact to bilateral partners.

Risks and Assumptions

| Risk type | Risk description | Risk assessment (Impact, Likelihood & Risk Level) | Mitigation measures |
| --- | --- | --- | --- |
| Political | Government transitions or shifting priorities in Mongolia or Tunisia could delay or disrupt continuity in food systems, NDC/NBSAP integration. | 4 – Extensive impact 3 – Moderately likely Substantial risk level | Anchor activities in existing national strategies (e.g. NDCs, NBSAPs, INFFs); work through multi-ministerial structures to reduce reliance on individual political champions. |
| Institutional | Weak inter-ministerial coordination or siloed mandates may hinder policy and financing alignment across food, biodiversity, and climate sectors. | 4 – Extensive impact 4 – Likely High risk level | Apply UNDP’s Effective Collaborative Action methodology; establish formal coordination platforms and regular joint work planning among core ministries. |
| Financial | Lack of fiscal space or misalignment between food systems priorities and public spending/investment decisions. | 3 – Moderate impact 3 – Moderately likely Moderate risk level | Engage Ministries of Finance early; leverage INFFs and collaboration with IMF and World Bank to mainstream nature- and climate-positive spending in budgets and subsidy reform. |
| Social Inclusion | Exclusion of women, youth, pastoralists, and Indigenous Peoples may undermine inclusive governance and reduce long-term ownership and sustainability of results. | 4 – Extensive impact 3 – Moderately likely Substantial risk level | Conduct early stakeholder mapping; ensure inclusive consultation and co-design processes; invest in capacity-building and platforms for marginalized voices to influence decisions. |
| Operational | Coordination challenges across global, regional, and national teams may lead to delays or miscommunication in implementation. | 3 – Moderate impact 2 –Unlikely Moderate risk level | Clarify roles and responsibilities early; establish strong project governance, national focal points, and regular coordination meetings at all levels. |
| Environmental | Climate shocks (e.g. droughts, floods) may disrupt implementation or reduce the effectiveness of interventions before resilience measures take root. | 3 – Moderate impact 3 – Moderately likely Moderate risk level | Prioritize early-stage resilience-building actions; apply adaptive management and flexible implementation planning to respond to climate-related disruptions. |

Stakeholder and Beneficiary Engagement

In both countries, the project will support multi-stakeholder collaboration by engaging stakeholders from government, civil society and the private sector with a particular focus on those most marginalized including women, youth and indigenous peoples. At the national level, Ministries of Agriculture, Environment, Finance, Planning and Gender, among other national institutions, will play key roles in aligning policy and financing strategies with NDC and NBSAP targets. Sub-national and local authorities will also play a crucial role, in particular in terms of connecting the national with local level. At local (and national) level the focus will be on herders, pasture cooperatives, NGO’s working on food revolution programs and women-led rural organizations in Mongolia, while small-holder farmers, women-led agricultural cooperatives, and water-user associations in climate-vulnerable regions will be integral to implementation and raising awareness in Tunisia.

Youth, Indigenous Peoples, and other marginalized groups will be prioritized through stakeholder engagement plans, inclusive consultation processes and co-design of capacity development activities. Stakeholder engagement will be monitored and adapted throughout implementation to ensure responsive and locally grounded action.

South-South and Triangular Cooperation (SSC/TrC)

This initiative leverages the momentum from UNCCD COP16 (Saudi Arabia) and looks ahead to COP17 (Mongolia) as entry points for interregional cooperation. The initiative will position both countries as regional leaders in integrating food systems with land governance, biodiversity finance, and climate action. Tunisia, as a part of the Arab States, and Mongolia, in Central Asia, will share challenges in managing dryland and rangeland systems, and this project will formalize learning exchanges and policy dialogues between them and potentially in collaboration with the UNCCD Secretariat.

Additionally, fostering cooperation between UNDP’s Nature and Climate Hubs’ teams that work on food will be critical for the success of this project. The teams offer global expertise which will benefit both countries in aligning their national priorities.

Sustainability and Scaling Up

This project aligns with several ongoing and pipeline initiatives in Tunisia and Mongolia, complementing efforts by the UNDP, GEF, and GCF to integrate climate and nature action into sustainable development strategies.

In Mongolia, the project responds to the NDC, in which the government has prioritized agriculture sector for both adaptation and mitigation measures. It builds on national initiatives such as agroforestry under Billion Tree Campaign, which aims to combat desertification and restore ecological connectivity. It will also align with GEF-funded ENSURE, GCF-funded ADAPT, SCALA project, and the White Gold Initiative (former Mongolian Sustainable Cashmere Platform), all of which focus on sustainable rangeland management, biodiversity-friendly agricultural supply chains, and rural livelihoods. The BIOFIN initiative, which is supporting the reduction of harmful agricultural subsidies, further contributes to the project’s objectives. The upcoming UNCCD COP17 in Mongolia will serve as a critical platform for knowledge exchange and project visibility, facilitating national and global engagement in biodiversity conservation efforts.

In Tunisia, the project builds on national initiatives to promote agroecology, sustainable land management, and climate-resilient agriculture, in alignment with the National Adaptation Plan and the updated NBSAP. It will also build on the GEF-funded biodiversity initiatives, which are supporting biodiversity mainstreaming, public finance reform, and alignment of agricultural subsidies with climate and biodiversity goals. The project will further contribute to national dialogues on food systems transformation, and leverage Tunisia’s active engagement in regional platforms such as the Great Green Wall and the 4 per 1000 Initiative to enhance knowledge exchange and policy coherence. Furthermore, the initiative will ensure alignment with the GEF-funded BIOFIN, which is advancing efforts to reduce environmentally harmful agricultural subsidies, thereby reinforcing the project’s overarching objectives. To ensure full coherence with broader investment planning and financial architecture, the project will also align with Tunisia’s third NDC, currently supported by the Green Climate Fund (GCF), and will contribute to the development of an integrated policy framework. This framework aims to optimize the mobilization, coordination, and alignment of financial resources for nature-based solutions in the food and agriculture sectors, in accordance with national and international commitments, including the NBSAPs, NDCs, NAPs, and INFF.

This project is designed to extend and enhance previous and ongoing efforts by integrating lessons learned and fostering stronger collaboration across initiatives, including the work done by governments to implement Food Systems Pathways. By building upon existing frameworks and integrating innovative biodiversity and climate strategies into agriculture and food policies, the project will ensure greater sustainability and long-term impact. The FW investment will ensure integration with national strategies and existing funding mechanisms. Through close coordination with implementing entities, the project will leverage existing resources, scale best practices, and contribute to the broader goal of achieving sustainable economic growth while achieving nature and climate goals in both Tunisia and Mongolia.

# Management and Governance Arrangements, and Accountability (1/2 page)

**Implementation of Funding Windows resources must adhere to the established corporate policies and procedures as prescribed in the POPP. The Head of the recipient office (at country, regional, and/or global level) will be held accountable for the effective and prudent use of the funds allocated to your office, including following the Social and Environmental Screening Procedure. For flagship initiatives, Global Leads are responsible for effective coordination, oversight, management and reporting across countries. This includes providing substantive technical support to aggregate and elevate results from Country Offices, thereby demonstrating the overall impact of the flagship initiatives. The delivery of country-level outputs and related expenditures will be led by the respective Country Offices, ensuring that interventions are relevant to the specific country context and needs.**

The project will be jointly implemented by the UNDP’s Nature and Climate Hubs, as well as by the Mongolia and Tunisia Country Offices. The NH and CH teams take on the overall global management responsibility and accountability, while UNDP Country Offices in Tunisia and Mongolia will hold the accountability for project implementation at country level. National and local implementation teams in Tunisia and Mongolia will work closely with key stakeholders to ensure that activities are relevant to local needs and effectively executed. Regular coordination meetings between all levels will ensure that challenges are promptly addressed, and decisions are informed by local realities. An overall project coordination function will be located in the NH Food Systems team. Implementation at country level will be carried out by existing Project Management Units, with implementation support provided in-kind by ongoing projects. This project will enhance the portfolio approach to programming in each country.

# Monitoring and Learning (1/2 page)

Monitoring & Learning

**Annual reports for the FWs are collected from Global Substantive teams for flagship initiatives in Q1 for the previous calendar year. In coordination with recipient COs and regional offices, Global Substantive teams for flagship initiatives will need to respond to a set of questions to help the FWs aggregate results across all allocations and create narrative around the impact of our investments for our partners. Continuous monitoring throughout the year – including following up on completed activities to gather evidence and assess their lasting impact – will make the process of annual reporting smoother and more efficient. **

A robust monitoring and learning framework will be implemented to track progress, assess the impact, and inform adaptive management. This framework will involve regular data collection on key indicators – ref. to workplan and resource framework. Baseline, mid-term, and end-line evaluations will be conducted to measure progress towards objectives. The project will also emphasize continuous learning through the documentation of successes, challenges, and lessons learned, which will be shared with partners and stakeholders. Feedback loops will be established to adjust strategies in response to emerging findings and ensure that the project remains responsive to community needs.

# Distribution of the FWs allocations

| Country/Region/Global | Dept ID | Amount |
| --- | --- | --- |
| Mongolia |  | 445,038 |
| Tunisia |  | 445,038 |
| Global (BPPS) |  | 44,504 |
| GMS |  | 65,420 |
| Total |  | 1,000,000 |

# WORK PLAN

If resources will be used beyond one calendar year, please use the resource framework in the project document template.

**According to the UNDP Gender Equality Strategy 2022-2025 global, regional and country office programmes and projects will identify, at their design stage, at least one stand-alone gender-specific component (GEN3 output of project document) with at least of 15 percent of the total resources of the initiative allocated to this component. For more information, please refer to the updated Funding Windows Gender Marker Guidance Note.**

Strategic Plan 2022 – 2025:

Indicator 1.1.2: Number of countries that have policy measures in place to enable the enhancement and/or implementation of Nationally Determined Contributions under the Paris Agreement

Baseline: 0 (SP 2024 milestone: 45)

Target: 2 (SP target 2025: 80)

Period (m-Y to m-Y): July 2025 – June 2026

| EXPECTED OUTPUTS | PLANNED ACTIVITIES | Planned Budget by Year |  |  |  | RESPONSIBLE PARTY | PLANNED BUDGET |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Q3 | Q4 | Q1 | Q2 |  | Funding Source | Budget Category | Budget Description | Amount |
| Output 1: Strengthened coherence among biodiversity, climate and food systems policies, facilitating accelerated implementation of NBSAP, NDC, LDN, and NAP targets Gender marker: 2 Indicator 1: Number of Food and Agriculture policies with targets, including on gender, aligned with NBSAP, NDC, LDN, and/or NAP to improve policy coherence Baseline: 0 Target: 2 Related SP indicator: 1.1.2 | 1.1: Conduct policy analysis to identify existing gaps and entry points, including on gender equality, to strengthen alignment of food systems policies with NDC, NBSAPs, LDN, and NAP | X |  |  |  | UNDP Country Offices and National Teams | FW | IC | Hiring one consultant per country to undertake analysis | 30,000 |
|  | 1.2: Conduct training for government and stakeholders on the integration and alignment of nature and climate goals in food systems policies, including on gender related aspects. | X | x | x | x | UNDP Country Offices and National Teams |  | Training, Workshops and Conference | Organization of multistakeholder dialogues | 90,000 |
|  |  |  |  |  |  |  |  | IC | Hiring of experts to support the delivery of activity | 30,000 |
|  |  |  |  |  |  |  |  | IPSA | Technical Assistance (Food Systems) | 30,000 |
|  |  |  |  |  |  |  |  | Travel | Cost for participants and facilitators to conferences/workshops | 20,000 |
|  | 1.3: Develop roadmap to strengthen policy coherence across biodiversity, climate and food systems, with support of enhanced and inclusive multi-stakeholder coordination spaces and governance mechanisms | X | x | x |  |  |  | Training, Workshops and Conference | Organization of trainings and CB programs on identified topics | 40,000 |
|  |  |  |  |  |  |  |  | IPSA | Technical Assistance (Food Systems) | 30,000 |
|  |  |  |  |  |  |  |  | IC | To advise on specific training and CB topics | 30,000 |
|  |  |  |  |  |  |  |  | Travel | Travel costs for participants and trainers | 10,000 |
|  | 1.4 Draft and implement monitoring, learning and evaluation plan to measure progress towards policy coherence |  |  |  |  |  |  | IC | COs to draft MLE plan | 10,000 |
|  | Sub-Total for Output 1 |  |  |  |  |  |  |  |  | 320,000 |
| Output 2: Financial incentives aligned and coherent financing frameworks (for public and private funding flows) developed for gender-responsive, nature-based climate solutions and investments in food systems Gender marker: 2 Indicator 1:Number of financial strategies aligned with biodiversity, climate and land degradation neutrality targets, including on gender, with development finance (INFF if available) Baseline: 0 Target: 2 Indicator 2: Number of business cases for agri-business investment in NbS Baseline: 0 Target: 2 Related SP indicator: 1.1.2 | 2.1 Assess costs for addressing food and ag sectoral targets in NDC and NBSAP, including on gender, to define a common funding and financial framework; use the INFF as a platform to address trade-offs and synergies between revenue, expenditure and financing policies. | X |  |  |  | UNDP Country Offices and National Teams |  | IC | Support cost analysis | 20,000 |
|  |  |  |  |  |  |  |  | IPSA | Technical Assistance (Climate) | 30,000 |
|  | 2.2: Identification/mapping of subsidies harmful to biodiversity, climate, and gender equality, and develop concrete policy recommendations for their reform or redirection. |  | x | x | x | UNDP Country Offices and National Teams |  | Training, Workshops and Conference | Holding multistakeholder processes | 10,000 |
|  |  |  |  |  |  |  |  | IC | Support drafting of documents, provision of ad hoc advisory support | 25,000 |
|  |  |  |  |  |  |  |  | IPSA | Technical Assistance (Climate) | 30,000 |
|  | 2.3 Develop investment case for private sector and agribusiness to engage in gender-responsive nature-based climate solutions for food and agriculture |  | x |  |  |  |  | IC | Support drafting of documents, provision of ad hoc advisory support | 20,000 |
|  | 2.4: Engage the private sector and agribusinesses, supported by risk-informed political economy analysis, to integrate biodiversity and climate risk management into business and investment decisions |  | x | x |  |  |  | Training, Workshops and Conference | Holding multistakeholder processes | 10,000 |
|  |  |  |  |  |  |  |  | IC | Support drafting of documents, provision of ad hoc advisory support | 20,000 |
|  |  |  |  |  |  |  |  | IPSA | Technical Assistance (Climate) | 10,000 |
|  | Sub-Total for Output 2 |  |  |  |  |  |  |  |  | 175,000 |
| Output 3: Strengthened food systems governance and inter-ministerial collaboration that facilitates integration of gender-responsive, nature-based climate solutions in agricultural and economic planning, linking up to the NBSAP and NDC Indicator 1: Number of food systems inter-ministerial or inclusive multistakeholder mechanisms with improved capacity to coordinate food, climate, and biodiversity policy and planning Baseline: 0 Target: 2 (To be measured through a pre-assessment of current capacities and a post-assessment to track changes over time) Gender marker: 2 Related SP indicator: 1.1.2 | 3.1: Assess the overall baseline state of existing governance structures, multistakeholder collaboration spaces and mechanisms that influence food systems, climate and biodiversity policies, including through identification, mapping and analysis of stakeholder engagement and power dynamics, including on gender equality | x |  |  |  |  | FW | IC | Hiring one consultant per country to undertake analysis | 30,000 |
|  | 3.2: Develop recommendations for enhancing representation and effective participation of relevant stakeholders – with special attention to women, youth, Indigenous Peoples and local communities – in governance mechanisms | x |  |  |  |  |  | IC | Hiring of experts to support the delivery of activity | 30,000 |
|  |  |  |  |  |  |  |  | IPSA | Technical Assistance (Climate) | 20,000 |
|  | 3.3: Co-design and implement with relevant public and private stakeholders country-specific capacity building plans for effective collaborative action for more sustainable, climate resilient, and gender-responsive agricultural practices. |  | x | x | x |  |  | Training, Workshops and Conference | Organization of trainings and CB programs on identified topics | 75,000 |
|  |  |  |  |  |  |  |  | IC | Communications support (COs) | 5,000 |
|  |  |  |  |  |  |  |  | IPSA | Technical Assistance (Food Systems) | 30,000 |
|  |  |  |  |  |  |  |  | IC | To advise on specific training and CB topics | 30,000 |
|  |  |  |  |  |  |  |  | Travel | Travel costs for participants and trainers | 25,000 |
|  | Sub-Total for Output 3 |  |  |  |  |  |  |  |  | 245,000 |
| Output 4: Women and girls' priorities, rights, needs and capacities related to shaping nature-positive, climate-resilient food systems are addressed and strengthened and asset ownership is increased Indicator 1: Number of gender action plans to guide nature positive, climate resilient food systems policies and investments Baseline: 0 Target: 2 Indicator 2: Number of women reporting increased decision-making power over productive assets or income, or increased participation in policy making related to food systems, climate or biodiversity. (Self-reported through surveys or focus groups to capture empowerment and agency) Baseline: 0 Target: TBD Gender marker: 3 Related SP indicator: 1.1.2 | 4.1: Conduct a gender-responsive and socially inclusive climate cost-benefit analysis to understand the different impacts and opportunities of biodiversity and climate policies on women at the national level, specifically in context of food systems. |  | x |  |  |  | FW | IC | Hiring one consultant per country to undertake analysis | 20,000 |
|  | 4.2: De-risk investments through seed funding in women-led projects and enterprises focused on nature-based climate solutions in food systems. |  | x | x |  |  |  | Grants | Small grants for women-led organizations | 75,000 |
|  | 4.3: Draft gender action plan to guide nature positive, climate resilient food systems policies and investments |  | x | x | x |  |  | Training, Workshops and Conference | Organization of trainings and CB programs on identified topics | 35,000 |
|  |  |  |  |  |  |  |  | Travel | Travel costs for participants and trainers | 20,075 |
|  | Sub-Total for Output 4 |  |  |  |  |  |  |  |  | 150,075 |
| Global Component (5% TA) |  |  |  |  |  |  |  | IPSA | General global coordinator Food Systems | 44,504 |
| General Management Support |  |  |  |  |  |  |  | GMS |  | 65,421 |
| TOTAL |  |  |  |  |  |  |  |  |  | 1,000,000 |

All proposals should align to at least one SP output and related indicator and include those in the workplan/result-framework below to show contribution to the SP IRRF. The linkage to the SP Output and indicator should also be reflected in Quantum.

As per UNDP’s Enterprise Risk Management Policy

Cost definitions and classifications for programme and development effectiveness costs to be charged to the project are defined in the Executive Board decision DP/2010/32

Changes to a budget affecting the scope (outputs), completion date, or total estimated costs require a formal budget revision that must be signed by the project board. In other cases, the UNDP programme manager alone may sign the revision provided the other signatories have no objection. This procedure may be applied for example when the purpose of the revision is only to re-phase activities among years.

* As indicated in the distribution of the FWs allocations table, budget for global and regional teams will be used for technical accompaniment (up to 5%). However, additional budget will be available for Food Systems and Climate Hub teams to cover the costs of ICs provided by the global teams, as indicated in brackets in the work plan table. The costs will be co-shared from the COs.

These activities should be considered indicative and will be tailored and further refined in individual country work plans according to country priorities and needs. It is not expected that all activities will be implemented in both countries, however should guide countries to achieve the stated outputs and indicators.