Project Title: Increasing Employability in the Renewable Energy Sector Project Phase II

Project Number:

Implementing Partner: Ministry of National Education (MoNE)

Start Date:01/06/2025			End Date:31/12/2026		PAC Meeting Date: 02/06/2025

Brief Description

The project’s overall objective is to strengthen the livelihoods and employment prospects of Syrians under Temporary Protection (SuTP) and the Turkish Citizens in Türkiye while supporting Türkiye’s renewable energy (RE) sector. The project aims to contribute to the achievement of these dual objectives by capitalising on the potential synergy between employment support initiatives and the opportunities presented by the emergence of a young renewable energy sector. The project will build upon the learnings, feasibility studies, evaluations of the Phase I, vocational training and skills certification initiative, launched under the Increasing Employability for Syrian Refugees and Turkish Citizens in the Renewable Energy Sector Project in 2020, aimed at enhancing the employability of Syrian refugees and Turkish Citizens in the renewable energy sector. This second phase will shift focus from broad training delivery towards a more analytical and targeted approach, concentrating on assessing the outcomes and needs of Phase I graduates, providing tailored employability support and mentorship to promising candidates, exploring potential entrepreneurship pathways, and developing needs-based training modules for future use, all with a particular emphasis on promoting women empowerment.

| Contributing Outcome (UNSDCF, CPD, RPD): Outcome #1.3: By 2025, people under the Law on Foreigners and International Protection are supported towards self-reliance. Indicative Output(s) with gender* marker: GEN 2 Output 1.1. Displaced populations are equipped with the knowledge and skills to engage in the socioeconomic life of their host community. Output 1.4. Sustainable job opportunities created for displaced populations and host communities. |  | Total resources required: | $564.526,72 USD |  |
| --- | --- | --- | --- | --- |
|  |  | Total resources allocated: | $564.526,72 USD |  |
|  |  |  | UNDP TRAC: | N/A |
|  |  |  | Donor (Government of Korea ): | $564.526,72 USD (including GMS) |
|  |  |  | Government: | N/A |
|  |  |  | In-Kind: | N/A |
|  |  | Unfunded: | N/A |  |

| Government | UNDP | Implementing Partner |
| --- | --- | --- |
| The Ministry of Foreign Affairs (MoFA) | Monica Merino Resident Representative | Ministry of National Education (MoNE) |
| Date: | Date: | Date: |

# Development Challenge

The global energy transition presents both an opportunity and a challenge for populations, particularly refugees and Turkish Citizens. As one of world’s largest host of refugees since 2014, Türkiye accommodates nearly four million officially registered refugees, including approximately three million Syrians under Temporary Protection (SuTP), many of whom face precarious socio-economic conditions. With limited access to work permits, a significant proportion remains engaged in informal employment, exacerbating financial insecurity and deepening economic disparities.

Despite Türkiye’s strong national ownership in addressing the refugee crisis through legal frameworks and social assistance programs, existing interventions have not fully bridged the gap between labour market demand and workforce preparedness. Evaluations of employment initiatives reveal a misalignment between supply-side measures—such as vocational training programs—and the evolving needs of the labour market. Moreover, while humanitarian aid remains essential for immediate relief, it risks fostering long-term dependency rather than self-sufficiency. Combined with the significant risk for the shrinking humanitarian support at a global level, self-sufficiency through access to regular labour market is crucial. As at mid-2023 more than half of the SuTP and International Protection Status Holders and Applicants (IPSHA) in Türkiye benefited from various forms of social and financial aid.

Simultaneously, climate change and rising global energy demands underscore the urgency of transitioning toward renewable energy solutions. The UNDP Strategic Plan 2022-2025 recognizes the interconnectedness of energy, environment, resilience, and women empowerment, emphasizing inclusive access to clean and sustainable energy. This shift presents a strategic opportunity to integrate refugees and Turkish Citizens into the labour market while addressing broader socio-economic challenges. However, overcoming systemic barriers—including bureaucratic constraints, a shortage of employable skills, and limited formalization of refugee employment—remains essential to unlocking this potential.

Energy access is a fundamental driver of development, shaping health, education, and economic well-being, yet universal access to clean energy remains a challenge despite advancements in renewables. Approximately 2.1 billion people lack access to clean cooking, while 957.5 million remain without electricity, highlighting the urgent need for accelerated investment, particularly in developing economies where financing costs are higher. Simultaneously, global energy systems must align with climate goals, as current policies put the world on track for 2.4°C of warming by 2100—far exceeding the 1.5°C target. Achieving this requires a decisive shift away from fossil fuels, with no new fossil fuel projects needed under a 1.5°C pathway and 95% of total energy investment directed toward clean energy by 2035. Beyond reducing emissions, this transition enhances energy security by decreasing reliance on volatile fossil fuel markets. The critical role of renewables in ensuring a sustainable energy future is clear but closing energy access gaps while meeting climate targets demands urgent and coordinated action, including investments in clean energy technologies and policies that ensure equitable access to electricity and clean cooking solutions worldwide. As part of this effort, UNDP prioritizes decentralized renewable energy solutions, particularly in crisis-affected regions, to enhance resilience and economic self-sufficiency.

Despite ongoing efforts to integrate refugees into the labour force, significant challenges persist. More than half of working-age SuTP and IPSHA in Türkiye remain engaged in informal employment, with only a small fraction securing work permits. A 2023 UN assessment revealed that 91% of SuTP and IPSHA respondents struggled to meet basic monthly expenses despite participating in informal work and receiving humanitarian aid. Employment opportunities in the renewable energy sector offer a significant added value for job seekers due to the higher skill requirements and specialization needed in the industry. Unlike many low-skilled sectors where employment is often informal and precarious, jobs in renewable energy generally require certification, technical expertise, and structured training, which in turn reduces reliance on informal job prospects. By equipping beneficiaries with recognized vocational qualifications and sector-specific competencies, the project aims to increase their access to formal, stable employment opportunities. This structured approach not only enhances long-term employability but also contributes to broader labour market formalization, ensuring that SuTP and Turkish Citizens can secure decent work with social protections and career progression pathways.

The renewable energy sector represents a particularly promising pathway for employment, given its rapid expansion and alignment with global sustainability goals. Projections indicate that the sector will contribute $98 trillion to global GDP by 2050 and generate employment at a rate four times higher than traditional energy industries. This expansion is especially relevant for Türkiye, where the renewable energy sector is poised to be crucial for economic growth and sustainability, aiming to reduce energy import dependency from 69% in 2020 to just 9% by 2053, thereby improving the country's trade balance. While specific estimates for the sector's GDP contribution by 2050 are not available, the required investments in the electricity sector are projected to reach $526 billion between 2020 and 2055, with an annual average of $15 billion.

Despite these developments, structural problems associated with women empowerment persist within Türkiye’s energy sector, including renewables, where women remain significantly underrepresented, particularly in technical and leadership roles. These disparities are reflected in lower enrolment of women in vocational training for renewable energy and fewer pathways for career advancement. However, the sector’s dynamic growth presents an opportunity to proactively foster a more inclusive and women participation to workforce. The potential synergy between the areas of employment support to SuTP and Turkish Citizens and the renewable energy sector in Türkiye presents not only a major opportunity for economic development, but also a critical entry point for advancing women empowerment.

This initiative seeks to build on previous efforts by revising and enhancing a training program developed in Phase I, with a primary focus on identifying gaps and aligning workforce skills with industry demands. By equipping SuTP and Turkish Citizens with a particular attention to empowering women beneficiaries with relevant technical competencies, the project aims to create a skilled and more women participation to workforce that contributes to Türkiye’s renewable energy transition while securing stable, formal employment opportunities for its beneficiaries.

# Strategy

The proposed initiative Phase II strategy is aligned with the guiding principles of structural transformation, leaving no-one behind and building resilience as reflected in UNDP’s Strategic Plan for 2022-2025, and directly builds upon the learnings and outcomes of Phase I (2020-2024). The UNDP Strategic Plan prioritizes structural transformation, resilience-building, and inclusive economic systems, with a strong emphasis on women empowerment and sustainable livelihoods. Its six signature solutions—poverty and inequality, governance, resilience, environment, energy, and women empowerment—align directly with this initiative’s objective of enhancing sustainable employment pathways in the renewable energy sector for Phase I graduates and informing future workforce development. By addressing employment disparities through targeted interventions and promoting women empowerment policies, the project advances the broader goal of sustainable, inclusive economic growth.

Phase II adopts a focused, two-pronged strategic approach:

Output 1. Labour Market Analysis and Targeted Employability Support: Conducting a thorough analysis of the Phase I graduate pool and the RE labour market to identify concrete employment barriers and opportunities, followed by implementing tailored support mechanisms (including CV enhancement, mentorship, and job matching support via a dedicated consultancy) for job-ready candidates, while also exploring potential entrepreneurship pathways.

Output 2. Learning Management System Updated to Support Access to the Renewable Energy Sector: Developing and updating customized RE training modules and digital infrastructure based on the findings of the labour market analysis and direct industry requirements, ensuring relevance and future readiness.

This approach aims to maximize the impact of Phase I investments by directly addressing the employment challenges faced by graduates and strategically developing resources for future skills enhancement in the sector. By enhancing employability first through analysis and targeted support, and second through future skills development informed by this analysis, the project supports the structural transformation towards a green and inclusive economy. UNDP recognizes that decarbonizing global economies could add $98 trillion to global GDP by 2050, with renewable energy employment expected to quadruple to 42 million jobs worldwide, offering a higher degree of women empowerment than traditional energy sectors. By facilitating pathways for Phase I graduates —particularly women and Syrians under Temporary Protection (SuTP)— to gain meaningful employment or explore entrepreneurship in the RE sector, the project directly supports UNDP’s goal to expand access to clean energy for 500 million people globally while fostering inclusive economic participation.

The project also advances UNDP’s commitment to leaving no one behind by focusing on marginalized groups within the Phase I graduates, addressing women in employment outcomes, and ensuring SuTP and Turkish Citizens receive equitable access to employability support and future training opportunities. This aligns with UNDP’s focus on reducing multidimensional poverty and supporting 100 million people to escape persistent vulnerability. Additionally, by incorporating a proactive women targeting approach throughout the needs assessment, mentorship design, and in training content development, the project contributes to UNDP’s efforts to promote women’s economic empowerment in line with its commitment to closing women and men participation to workforce gaps in access to economic resources and leadership roles.

From a resilience-building perspective, the project aligns with UNDP’s strategy to equip individuals and economies to withstand economic and environmental shocks. By first analysing employment barriers and then focusing on understanding the employability of previously trained workers and developing updated skills modules for an industry that is key to climate resilience and sustainability, the project supports UNDP’s broader goal of promoting risk-informed, future-proof employment pathways. Furthermore, the integration of digital learning tools, such as the Learning Management System (LMS)for both soft skills and future technical training and online soft skills training, aligns with UNDP’s digitalization strategy, which aims to increase accessibility, foster innovation, and enable inclusive development models.

This project is also in line with UNDP’s call for integrated and systemic solutions to complex development challenges. By first undertaking a detailed analysis (Activity 1.1), then providing targeted support (Activity 1.2), and finally developing needs-based resources (Output 2) addressing skills development, labour market integration, and women inclusion within the RE sector, the project demonstrates a multidimensional approach that reflects UNDP’s emphasis on leveraging synergies across poverty reduction, sustainable energy, and women empowerment interventions. Through its engagement with national institutions like the Ministry of National Education (MoNE) and utilization of the national employment system database, as well as private sector stakeholders, the project also embodies UNDP’s vision for fostering collaboration between governments, the private sector, and development actors to drive long-term impact. By operationalizing UNDP’s global vision at the local level, this project contributes to inclusive, sustainable, and climate-resilient economic growth, ensuring that SuTP and Turkish Citizens are supported towards job opportunities or entrepreneurship in a future-oriented sector.

The Project and its strategy are also developed in alignment with Türkiye’s programmatic strategies for refugee and host community integration, as outlined in the FRiT’s (Facility for Refugees in Turkey) theory of change. Its core objective is to enhance the livelihoods and employment prospects of Syrians under Temporary Protection (SuTP) and Turkish Citizens, while simultaneously supporting the growth of Türkiye’s renewable energy sector. Phase II will achieve this primarily by assessing the outcomes for the 1,875 Phase I graduates, providing targeted employability support to this group, exploring entrepreneurship avenues identified during the assessment, and developing updated vocational training modules based on these findings, specifically women and men from both SuTP and Turkish Citizens, with dedicated strategies to enhance women's participation and outcomes.

Furthermore, Phase I recommendation the project complements Türkiye’s 12th Development Plan, which prioritizes socio-cultural integration, vocational training, and skilled labour retention, alongside the expansion of renewable energy as part of Türkiye’s green transition strategy. The plan sets ambitious goals to quadruple Türkiye’s renewable energy capacity from 30,000 MW to 120,000 MW by 2035, with solar capacity alone expected to reach 77 GW. To meet these targets, an estimated $80 billion will be invested specifically in renewable energy projects, as part of a broader $108 billion investment plan for energy infrastructure. Achieving these objectives will require the installation of 7,500-8,000 MW of new renewable energy capacity annually, leading to renewable sources comprising 64.7% of total installed capacity by 2035.

To effectively bridge the gap between the Phase I graduates (women and men from SuTP and Turkish Citizens) and the renewable energy labour market, Phase II adopts a strategy grounded in first conducting a comprehensive assessment (Activity 1.1) to understand the status, barriers, market needs, and potential entrepreneurship niches. Subsequently, it will implement tailored employability interventions (Activity 1.2) for promising graduates, including mentorship and placement support, and develop demand-driven training content (Activity 2.2), ensuring alignment with identified industry needs and potential pathways to Vocational Qualification Certification where relevant.

The needs and gaps shaping this phase are informed by Phase I learnings, including two feasibility reports produced in Phase I, which examined key employment determinants and labour market requirements, with the educational aspects report explicitly incorporating a women and men workforce analysis and identifying women-specific barriers and needs. These reports highlight the necessity for a more specialized training model and structured course framework, ensuring that participants acquire advanced technical competencies relevant to industry expectations. Phase II will use the new Gaps and Needs Assessment (Activity 1.1) to further refine the understanding of required competencies. The development of training curricula (Activity 2.2) will follow a modular approach, covering areas such as Foundational Skills, Project Design & Installation, Maintenance & Repair, and Panel Production & Innovation, as identified in the Gaps and Needs Assessment conducted under the project. This structured approach will ensure that graduates are better prepared for sectoral demands, addressing prior gaps in expertise and practical experience.

Furthermore, an increased focus on hands-on training has been emphasized, responding to participant feedback that practice-oriented learning enhances confidence and job readiness. Special emphasis will be placed on empowering women by addressing barriers to their participation in the workforce, ensuring they have equitable access to targeted support services and training opportunities with a target for women’s representation in support activities of 40%.

Phase II will implement a dedicated Employability Support and Mentorship service (Activity 1.2) for a group of Phase I graduates. This involves engaging a consultancy to review graduate CVs, enhancing profiles of employable candidates, supporting their registration in the national employment system's database, and providing mentorship to facilitate job matching. This targeted support aims to replace broad job matching efforts and aims to connect vetted candidates with opportunities identified through collaboration with key stakeholders, including the Ministry of National Education (MoNE), private sector companies, chambers of commerce, and utilizing the National Employment System (İŞKUR), etc. A key recommendation from the feasibility reports highlights the importance of integrating training graduates into the job-seeking database of the National Employment System to improve job placement rates and ensure a more structured employment pathway.

Engaging the private sector is critical throughout Phase II, primarily during the assessment (Activity 1.1) to understand needs, barriers, and entrepreneurship potential and during the employability support phase (Activity 1.2) for job matching. The program will work with actors in the renewable energy sector to identify specific skill demands, needs and gaps in creating sustainable job placement opportunities, explore potential for outsources services/entrepreneurship, enhance workplace inclusivity, and integrate women-sensitive employment policies. The feasibility reports developed under Phase 1 underline the need for stronger collaboration with industry bodies such as GENSED, TÜREB, and ENSİA, which will be leveraged during the assessment and module development phases. Aligning with UNDP’s Gender Equality Strategy, the initiative will prioritize the economic empowerment of women in green energy jobs, ensuring they are not only beneficiaries but active participants in shaping the sector’s future. Based on the feasibility findings and the new assessment, a regional needs analysis will be inform both employability support strategies and future training content conducted to ensure training content aligns with the specific labour demands of each project province. This differentiated approach is expected to improve job placement outcomes and strengthen workforce adaptability in diverse renewable energy sub-sectors.

The development of new training curricula (Activity 2.2) will incorporate key findings from the feasibility reports from Phase I as well as the Gaps and Needs Assessment (Activity 1.1), ensuring that the skills targeted align with labour market demands and enable participants to transition into formal employment. One of the major insights from the feasibility report of Phase 1 was the growing demand for solar panels and related components, which is driving rapid growth in renewable energy equipment manufacturing. In response to this trend, the project will prioritize the development of specialized training modules focused on renewable energy equipment production, ensuring that vocational training aligns with this emerging sectoral need.

By implementing these strategies, the project aims to create direct pathways to long-term employment opportunities for entrepreneurship for Phase I graduates and develop foundational resources (updated curricula and LMS) to support future skill development for SuTP and Turkish Citizens, while supporting Türkiye’s transition to a sustainable energy economy. Building on Phase I learnings, this second phase focuses on analysis, targeted support, and needs-based development to better match workforce skills with industry needs. In conjunction with the Gaps and Needs Assessment, planned as the first activity under the proposed project, the feasibility reports will serve as critical reference points, ensuring that curriculum adjustments are evidence-based and responsive to labour market expectations.

The project connects multiple interlinked interventions in a strategic sequence under its two outputs to strengthen the employability of Phase I graduates and prepare the ground for future skills development. The first output focuses on understanding the labour market and the status of Phase I graduates through a comprehensive assessment (Activity 1.1), including identifying skills gaps, barriers, employer needs, and entrepreneurship potential. The second part of Output 1 is providing targeted employability support and mentorship (Activity 1.2) to promising Phase I graduates, including CV enhancement and facilitated job matching using the national employment system. Output 2 focuses on resource development: The third priority is providing accessible soft skills training (Activity 2.1) via an LMS, leveraging existing content. Finally, the project will focus on developing customized renewable energy training modules and an associated LMS (Activity 2.2) based on insights from the comprehensive needs assessment, feasibility studies, and previous project learnings, ensuring that training content developed remains relevant and responsive to evolving industry demands like manufacturing and potential Vocational Qualification Certification alignment.

Anchored in Türkiye’s national development priorities, the UNDP Strategic Plan, and international frameworks such as the Decent Work Agenda and the European Pillar of Social Rights, the initiative promotes labour standards and equitable working conditions. By harnessing the renewable energy sector’s potential, the project fosters economic stability, resilience, and social cohesion, while ensuring that women empowerment remains a fundamental pillar. Women will not only be beneficiaries of targeted support but active contributors to the renewable energy transition. This approach aims at enabling the project to make a lasting impact—unlocking new economic opportunities for Phase I graduates, driving sustainability, and assist Türkiye in advancing its RE workforce through updated, relevant training resources.

Gender Mainstreaming

In alignment with the EU Gender Equality Strategy (2020-2025) (particularly towards “closing women and men gaps in the labour market” under priority 2 “thriving in a women empowerment-equal economy”) and UNDP's Gender Equality Strategy for 2022-2025 (specifically with the priority for women empowerment and sustainable economies), the Project is dedicated to promoting women empowerment and the empowerment of women within its framework. This commitment aligns with SDG 5 - Gender Equality and with the strategic objectives of the 12th National Development Plan (NDP), which emphasizes the empowerment of women in employment and labour markets within the framework of a strong approach towards equal opportunities for men and women.

In the newly announced Women’s Empowerment Strategy Document and Action Plan (2024-28), Activity 2.1 outlines the priority of enhancing women’s participation in on-the-job training programs to facilitate their access to decent employment opportunities: “Efforts will be made to ensure that women, especially NEET young women, benefit more from vocational training courses, on-the-job training programs, and counselling activities aimed at acquiring skills tailored to the evolving needs of the labour market, thereby enhancing their access to dignified job opportunities.”

Key strategies for women empowerment will include equitable participation and leadership, and man and women balance in activities. This includes ensuring that women have equal opportunities to participate in training programs and employment support initiatives. Activities and programs will be designed to address the specific needs of women, particularly those who require specific policies. This involves creating safe and inclusive training environments and providing resources that are tailored to the unique challenges faced by women in the labour market.

In order to outline this approach, some responses are planned as follow:

o	Women-inclusive communication and outreach will be the centre of the women empowerment policy. Women-sensitive language will be used in announcements to encourage women's participation to the courses.

o	Tailor-made Training Program will be conducted to respond the women’s specific needs, such as flexible schedules, care giving responsibilities, or limited access to resources. Training modules will be developed or updated accordingly.

o         Tailored employability support, including dedicated mentorship targeting women, will be a key mechanism to address specific barriers and facilitate career advancement.

o	Women's decision-making and representation will be actively promoted to achieve women empowerment within the leadership structures of activities. Women will be encouraged and supported to apply to positions with leadership roles.

o	Specific policies to support women’s economic participation, particularly for those facing additional vulnerabilities (refugee women, women with disabilities, single mother) will be developed and lobbying activities will take place for the greater policy integration to reduce structural inequalities, such as addressing wage gaps or ensuring equal rights in employment. All beneficiaries’ data on intersectionality will be collected to inform programmatic adjustments and selection of beneficiaries such as sex, age, education, employment, marital, migratory status, income, disability, care burden etc.

o	The project's monitoring and evaluation (M&E) framework will ensure the collection of women and men-disaggregated data and women-focused qualitative data (e.g., qualitative insights on perceived barriers, access to resources and support services, safety concerns, confidence levels, career aspirations, and impact on household decision-making, etc.). This data, tracked through specific indicators within the logical framework, will be used to assess the project's effectiveness in reducing women and men inequalities.

o	Engaging men in women empowerment by organizing fatherhood information sessions is crucial for shifting societal norms and fostering shared responsibilities in both households and workplaces.

o	Procurement processes will prioritize women-responsive principles, assessing suppliers on their commitment to women empowerment and ensuring equipment and renovations meet the needs of all users. Renovations will include women-friendly designs, such as proper lighting and safety features, while staff will be trained to implement women-responsive practices effectively.

o	Recruitment processes will integrate UNDP's commitment to women empowerment by including specific language in job descriptions that requires candidates to demonstrate experience or knowledge in women-sensitive practices. Policies will emphasize gender inclusivity, ensuring equal opportunities at every stage of hiring, from advertising to final selection. To promote fairness and minimize unconscious biases, interview and selection panels will be diverse and women and men-balanced.

o	Recognizing that women may face specific barriers to understanding and accessing social protection mechanisms, the project will organize women-specific sessions highlighting the benefits of social security, such as maternity leave, health insurance, etc. Tailored materials will address common misconceptions, and accessible communication channels, like women’s organizations and social media, will be used to spread the message.

The project will ensure the collection and analysis of women-focused and disaggregated data. This data will inform the project's approach and ensure that interventions are effectively addressing women and men disparities. The project will include specific measures to raise awareness among beneficiaries and stakeholders about the importance of women in the labour market. This will involve activities focused on understanding and addressing women related challenges.

Through these strategies, the Project aims to contribute significantly to the advancement of gender equality, ensuring that both women and men benefit equally from the project’s initiatives and opportunities.

To mitigate barriers faced by women, the project will set specific, measurable targets for women's engagement across all support programs, aiming for a minimum of 30% overall women beneficiaries. Furthermore, specific targets will be developed and monitored for key intervention stages (e.g., training uptake, completion rates in different modules, job placement support through the national employment platform, etc.) to ensure progress across the project cycle. The project will also integrate women-specific needs into program design, conduct women-responsive participatory assessments, data collection and analysis, and provide capacity-building trainings to partners and stakeholders. Through these measures, the project aims to significantly advance women empowerment and ensure equal opportunities for both women and men.

Equal Opportunities

The Project’s attention to the advancement of decent work agenda, as laid out by the International Labour Organization, promotes the rights of the refugees and of the members of the Turkish Citizens. This is integral to reducing inequalities among the target group affected by a number of vulnerabilities in a sustainable way.

Under the Project’s activities, including development of employability support mechanisms and future training materials, information on concepts such as decent work and international labour standards (including principles like equal remuneration for work of equal value safe working environments free from harassment, and equitable access to social protection) will be integrated and relevant standards followed through the ILO frameworks, UN Guiding Principles on Business and Human Rights as well as European Pillars of Social Rights, EU Commission’s Communication on Decent Work Worldwide and Corporate Sustainability Due Diligence Directive.

The principles of transparency, inclusiveness, equality, and non-discrimination will be applied across all activities and at every stage of the Project’s implementation. While designing the training modules and materials the needs of people with disabilities including those who are visually impaired and hearing-impaired will be included.  Furthermore, the project's utilization of online platforms (LMS) for delivering selected soft skills content (Activity 2.1) and potentially future technical modules aims to enhance accessibility, thereby supporting the participation of disadvantaged groups or individuals, such as women with caregiving responsibilities, who may face barriers to attending traditional face-to-face programs.

Sustainable Development Goals (SDGs), Leaving no One behind and Other Global and Regional Frameworks

Although not strictly a humanitarian intervention, the project aligns with key humanitarian principles by addressing one of the primary challenges hindering the social and economic inclusion of Syrians under Temporary Protection (SuTP) and Turkish Citizens members. Given its medium-term development focus, the project will adhere to UNDP’s rights-based approach, ensuring that all activities are inclusive, responsive, and accountable. Special attention will be placed on supporting those furthest behind, including women from SuTP and Turkish Citizens who face specific barriers, ensuring that barriers to formal employment and skills development are addressed effectively.

The project also fully aligns with UNDP’s Strategic Plan 2022-2025, particularly its commitments to structural transformation, leaving no one behind, and resilience-building. Through its focus on equipping marginalized populations with employable skills, integrating them into formal labour markets, and promoting sustainable energy workforce development, the project embodies UNDP’s systems-thinking approach to poverty reduction, energy transition, and women empowerment. By leveraging digital learning tools, private sector partnerships, and government collaboration, it also supports UNDP’s strategic direction of fostering innovation, digitalization, and financing for sustainable development.

The project is strongly aligned with the 2030 Agenda for Sustainable Development, making direct contributions to several Sustainable Development Goals (SDGs). By developing needs-based training resources, the project supports SDG 4 (Quality Education), ensuring that beneficiaries acquire market-relevant skills for long-term employability. Through its women-sensitive approach, which prioritizes the inclusion and empowerment of women in the renewable energy sector, the project contributes to SDG 5 (Gender Equality) by actively working to reduce barriers to women's participation in vocational training and employment within the non-traditional renewable energy sector. By facilitating access to decent work opportunities for Phase I graduates through targeted support in a high-growth sector, strengthening job-matching mechanisms within the national system and developing resources to equip participants with future-ready skills, the project directly advances SDG 8 (Decent Work and Economic Growth). Additionally, given its focus on renewable energy workforce development, the project aligns with SDG 7 (Affordable and Clean Energy), supporting the broader transition toward sustainable energy solutions in Türkiye.

Beyond its contribution to the SDGs, the project also supports two key objectives of the Global Compact on Refugees by reducing pressures on Turkish Citizens through structured employment interventions for existing graduates and by promoting refugee self-reliance through targeted employability and future skills resource development. The project’s alignment with Türkiye’s national development priorities further ensures its sustainability and long-term impact.

By integrating global, regional, and national frameworks, this project contributes to a more inclusive, equitable, and sustainable renewable energy workforce in Türkiye, ensuring that SuTP and Turkish Citizens alike benefit from long-term employment opportunities in a sector that is critical for Türkiye’s green transition.

# Results and Partnerships

Expected Results

The project is expected to achieve its objectives through two main outputs:

- Output 1: Employability of Jobseekers Enhanced Through Labour Market Analysis and Job Counselling Services

- Output 2: Learning Management System Updated to Support Access to the Renewable Energy Sector

Inception

During the 4-month Inception Phase, the following preparatory activities will be realized:

Act. 0.1. Establishment of the project implementation team and the project office: Assembling a dedicated team and setting up a central office to coordinate and manage all project activities effectively.

Act. 0.2. Kick-off meeting: An initial gathering of key project stakeholders and project team members to discuss the project's objectives, expectations, roles, and the roadmap ahead.

Output 1: Employability of Jobseekers Enhanced Through Labour Market Analysis and Job Counselling Services

This output focuses on understanding the gap between the existing labour supply (Phase I graduates) and market demand, and providing direct, tailored support to enhance the employability of promising Phase I graduates.

Activity 1.1: Comprehensive Assessment of RE Labour Market Dynamics and Phase I Graduate Employability

To enhance the employability of the target group consisting of Phase I graduates (with the assessment aiming to capture perspectives from this pool of 1,875 individuals, ensuring ~40% representation of women graduates and prioritizing insights from SuTP), and to address skill mismatches and employment barriers identified in Phase I, a comprehensive gaps and needs assessment will be conducted. This assessment will provide an in-depth analysis of the graduates' current skills, employment status, aspirations, and specific barriers faced (including dedicated attention to understanding the barriers and needs of Persons with Disabilities (PwD) within the graduate pool), alongside labour market demand, to ensure that targeted support and training programs are aligned with industry needs and graduate realities. The assessment methodology will include consultations with relevant Disabled People's Organizations (DPOs) to inform this analysis.

The assessment will be carried out in Kocaeli, Bursa, İstanbul, Mardin, Gaziantep and İzmir (with potential comparative analysis based on provincial variations) and will be conducted in close collaboration with private sector umbrella organizations, industry representatives, and government institutions, including Chambers of Commerce and Industry, GÜNDER, GENSED, and TÜREB. These key stakeholders will provide insights into current labour market trends, regional employment needs, specific competency requirements, hiring challenges (including potential under-utilization of skills or salary barriers), and the effectiveness of existing matchmaking mechanisms. The assessment will focus on mapping industry expectations with the Phase I graduates’ competencies, identifying the reasons why some Phase I graduates remain unemployed despite completing vocational training, examining employer expectations, hiring trends to pinpoint barriers to employment and exploring the potential for small-scale entrepreneurship or outsourced services based on industry needs. The assessment will also systematically explore the women’s labour supply and employer preferences, including the reasons that may hold women back from enrolling in technical training programmes or pursuing employment in the renewable energy sector. These aspects will be examined through desk research, focus group discussions, field consultations, interviews with MoNE trainers and stakeholders. By doing so, the project will generate evidence-based recommendations for improving employability prospects and informing subsequent project activities.

Another key aspect of the assessment will be the consideration of regional differences in renewable energy production and employment trends. Given that Türkiye’s geographic and climatic conditions shape the demand for specific renewable energy skills, the research will account for location-specific expertise needs. For example, provinces with high solar potential such as Gaziantep, Şanlıurfa, and Mardin may require a stronger focus on photovoltaic system installation and maintenance, while coastal regions like İzmir and İstanbul may present greater demand for wind energy technicians.

The assessment will also address emerging sectoral needs identified since Phase I, such as skills related to Türkiye’s increasing manufacturing capacity in solar panel production (quality control, assembly) and the growing importance of advanced technical expertise identified by employers. Findings from feasibility reports developed under Phase I will be integrated into the assessment, alongside analysis of global RE trends and field consultations.

In addition to ensuring alignment with market needs, the assessment will incorporate a women focused perspective to guarantee that revised training modules and delivery methods are accessible and inclusive for women. This will involve examining any women-specific barriers to participation in the renewable energy sector and ensuring that training content, outreach and communication strategies, and monitoring, evaluation and learning (MEL) approaches are designed to support women’s entry, participation and advancement in the field. Findings related to PwD barriers and needs will similarly inform the design of accessible support mechanisms and future resources.

Findings from feasibility reports developed under Phase I will be incorporated into the assessment, alongside desk research and field consultations.

The methodology will include the following:

- Desk research conducted by technical experts, integrating previous feasibility reports and evaluations, relevant labour market data, and global RE sector trends.

- Participatory assessment sessions (e.g., focus group discussions, workshops, interviews) conducted with women and men from the Phase I graduate pool to capture their current employment status, skill levels, aspirations, perceived barriers (including specific ones for women), and overall experience.

- Consultative meetings with key private sector stakeholders, sectoral NGOs, Phase I MoNE trainers, and relevant government actors in selected provinces to understand employer needs, hiring barriers, matchmaking issues, and potential entrepreneurship/outsourcing opportunities.

- Development of guiding principles for designing targeted employability support mechanisms the preparation of customized renewable energy modules based on assessment findings and industry feedback.

- Drafting of a comprehensive Gaps and Needs Assessment Report detailing findings on Phase I graduate status and barriers, labour market dynamics (demand, employer perspectives, provincial variations), skills gaps, matchmaking effectiveness, potential entrepreneurship niches, and women-specific and disability-specific considerations, to inform the implementation of Activity 1.2 and the development activities under Output 2.

By leveraging Phase I learnings, private sector expertise and direct graduate insights, the assessment will lay the foundation for targeted employability interventions and stronger job placement strategies.

Activity 1.2: Targeted Employability Support and Mentorship Service for Phase I Graduates

Building on the assessment in Activity 1.1, this activity implements a targeted employability support and mentorship service focusing on connecting promising Phase I graduates with tangible opportunities. This involves engaging a specialized consultancy or service provider to proactively reach out to the Phase I graduate pool (1,875). Outreach methods will consider the need to effectively engage graduates with disabilities based on assessment findings. The initial focus will be to support the registration of approximately 600 eligible graduates, aiming for representation with targets of at least 40% women and at least 40% SuTP within this group, in the national employment system's database (İŞKUR) to increase their general visibility to potential employers. Following this registration support and further assessment based on Activity 1.1 findings, the employment counselling service provider will review graduate profiles/CVs (ensuring inclusion of SuTP) to identify a smaller subset of highly promising candidates (e.g., up to 100 individuals, again aiming for significant representation with targets of at least 40% women and at least 40% SuTP within this subset) for intensive support. The selection criteria and review process will be sensitive to the diverse needs identified in the assessment, including those related to disability where applicable. For this selected subset, the employment counselling will provided through CV enhancement and personalized mentorship and career guidance following one-on-one interviews to understand their skills and aspirations. The mentorship approach will be adapted as needed, informed by the assessment findings, to ensure mentors provide inclusive guidance and support, addressing specific needs including those related to disability. This mentorship aims to actively match these vetted candidates with suitable job opportunities identified through direct engagement with RE companies and chambers of commerce in pilot provinces (e.g., İzmir, Bursa, Mardin, Gaziantep, Şanlıurfa), with an effort to identify and liase with employers with employers demonstrating inclusive hiring practices.. This targeted support mechanism links assessment findings directly to placement efforts, contributing to long-term employability by facilitating effective transitions into the RE workforce for motivated graduates selected for intensive support.

The methodology will include the following:

- Engagement of a specialized consultant or service provider with expertise in CV development, career counselling, mentorship and outreach.

- Targeted outreach to Phase I graduates to inform them about the employability support service and encourage participation, utilizing accessible communication methods where indicated by the assessment.

- Support facilitated registration for approximately 600 eligible Phase I graduates on the national employment system's database (İŞKUR) to enhance their general visibility to employers.

- Review and assessment of graduate profiles/CVs from the registered/assessed pool based on criteria developed from Activity 1.1 findings (considering motivation, skills, language proficiency, prioritizing SuTP/women and informed by assessment findings regarding PwD needs) to identify candidates for intensive support.

- Selection of a smaller subset (e.g., 100 individuals) from the assessed pool for intensive mentorship based on potential and commitment.

- CV enhancement support provided specifically to the selected subset of candidates identified as having strong employment potential.

- Conducting one-on-one consultations/interviews with the selected subset to tailor support.

- Providing personalized mentorship and career guidance sessions (online or in-person) to the selected subset.

- Proactive job matching efforts, including liaison with HR departments of RE companies and relevant chambers of commerce in pilot provinces to identify and facilitate access to suitable vacancies for mentored candidates.

Through this targeted employability support and mentorship service, the project will aim to bridge the gap between training and employment for Phase I graduates, enhancing their visibility through registration in the national employment system and providing structured, facilitated access to job placement opportunities for a selected group of mentored candidates within Türkiye’s renewable energy sector.

Output 2: Learning Management System Updated to Support Access to the Renewable Energy Sector

This output focuses on developing and enhancing vocational training resources for the RE sector, ensuring alignment with identified needs and leveraging digital platforms for accessibility.

Activity 2.1: Soft Skills Training Programme Platform and Content Adaptation

One of the key barriers to employment in the renewable energy sector, as in many other industries, is the lack of soft skills among job seekers. While technical expertise is essential, employers also seek candidates with competencies in entrepreneurship, workplace communication, entrepreneurship, problem-solving, and professional CV preparation. To enhance the employability of beneficiaries, a digital platform will be developed to provide targeted soft skills training.

The platform will host online courses designed to equip participants with necessary skills to navigate the job market effectively. This activity will leverage existing general soft skills content developed under the FRIT Project. Relevant modules from the FRIT project will be carefully selected based on the findings of the Gaps and Needs Assessment (Activity 1.1) to align with the identified needs of the target beneficiaries and the RE sector context. The platform will be designed with inclusivity and accessibility in mind, ensuring both Turkish citizens and SuTP can benefit A women-sensitive approach will guide the selection and presentation of the chosen modules, including highlighting examples or focus areas relevant for women in the RE workforce where available within the existing content. Access to the platform and the selected training programme will be granted to beneficiaries participating in the employability support service (Activity 1.2).

The methodology will include the following:

- Development and establishment of the online platform (LMS) for delivering adapted soft skills training

- Review and adaptation of existing soft skills training content (e.g., from FRIT project) to ensure relevance for the RE sector context, including integration of women-sensitive approaches and examples.

- Maintenance of the platform and continuous reporting throughout the project duration.

By providing accessible, adapted soft skills training via a dedicated platform, this activity aims to complement technical readiness and strengthen beneficiaries' overall employability.

Activity 2.2 Development of Needs-Based RE Training Modules and Learning Management System (LMS)

Since the implementation of Phase I, new industry developments—such as the expansion of solar panel production in Türkiye and potential regulatory changes regarding mandatory solar panels on new buildings—have reshaped workforce needs in the renewable energy sector. Additionally, employers are increasingly seeking workers with specialized technical skills, including expertise in hybrid renewable energy systems. To ensure that vocational training remains aligned with evolving industry standards, this activity will develop new modules to complement the existing training curricula and address emerging workforce demands.

The development will be directly informed by the Comprehensive Needs Assessment under Activity 1.1 and reflect specific industry requirements highlighted during stakeholder consultations, such as the expansion of solar panel manufacturing in Türkiye, the need for skills related to new technologies (e.g., hybrid systems), and potential alignment with vocational qualification certification pathways. Based on these findings, new customized training modules will be developed and potentially existing ones updated, covering domains such as Foundational Skills, Project Design & Installation, Maintenance & Repair, and Panel Production & Innovation. By adopting this structured approach, the project aims to ensure future training resources better prepare learners for sector-specific roles, addressing prior gaps in both technical expertise and practical experience.

This activity will also enhance the digital learning infrastructure by creating online training materials and establishing a Learning Management System (LMS) to facilitate structured, interactive, and blended learning opportunities. The LMS will improve accessibility and adaptability, ensuring that training remains relevant to both SuTP and host community members. The resources developed under this activity (modules and LMS) are primarily intended for future use within MoNE's vocational training system, benefiting MoNE's general beneficiary audience. While Phase II does not include direct training delivery using these modules for a specific target group, Phase I graduates could potentially access these resources in the future through MoNE's platforms.

The Ministry of National Education (MoNE) will be the main beneficiary and partner institution for this output, as it currently oversees renewable energy training programs. The newly developed modules will be informed by lessons learned from Phase I, the sectoral needs assessment, and feasibility reports, ensuring that they meet national training standards and contribute to sustained workforce development. Once finalized, the training content and LMS will be transferred to MoNE, allowing for long-term integration into Türkiye’s vocational education system and use by MoNE's broad beneficiary base, potentially including Phase I graduates seeking further learning.

To ensure the quality and effectiveness of the new training content, the project will collaborate with vocational trainers, industry professionals, and academic experts. Course materials will undergo review and testing to validate both their technical accuracy and practical applicability before full-scale implementation. Feedback mechanisms will be incorporated, allowing for continuous improvement of the training modules.

Considerations for women will be integrated into the training approach, with women-sensitive delivery methods and segregated reporting mechanisms to ensure inclusivity. Additionally, the blended learning methodology—already applied in modules developed under Phase 1—will be continued, improving women’s access to training opportunities.

The methodology will include the following:

- Development of two new online modules, tools and technical course content

- Design of training delivery and assessment methods by technical experts for the developed modules.

- Updating the Learning Management System (LMS) to host the new modules.

- Review of the developed content by technical experts to ensure quality, technical accuracy and practical applicability.

- Transfer of finalized training modules and the LMS to MoNE for integration into vocational education programs.

By updating and expanding the vocational training system resources, this activity will strengthen the foundation for future workforce readiness in the renewable energy sector, increasing potential employability for future trainees including SuTP and host community members while contributing to the sector’s long-term growth and sustainability.

Activity 2.3: Capacity Development Support for MoNE

To ensure effective coordination and implementation support within the primary implementing partner, the project will provide targeted capacity development support to MoNE. This will involve the recruitment and placement of a dedicated Project Assistant within MoNE structures, primarily tasked with facilitating day-to-day project activities, managing correspondence, and handling specific reporting functions, such as reporting from MoNE’s LMS platforms relevant to the project for monitoring purposes. Additionally, based on needs identified during project implementation, limited IT equipment may be procured to enhance the capacity of relevant MoNE units or the dedicated assistant to effectively engage with project management and digital tools (like the LMS platforms developed under Activities 2.1 and 2.2). This activity aims to strengthen MoNE's operational capacity for project engagement and contribute to smoother implementation.

Target groups and final beneficiaries:

Phase I Graduates (SuTP and Turkish Citizens, including Women and Men): These 1,875 individuals represent the primary target group for Phase II’s direct employability support activities. They face challenges in securing stable employment due to factors such as language barriers, potential skill gaps despite Phase I training, lack of updated knowledge or qualifications in the evolving RE field, and limited understanding of the Turkish labour market or effective job search strategies. primarily through the targeted assessment, employability support, and mentorship service outlined in Output 1 (Activities 1.1 and 1.2). While Phase II focuses less on direct training delivery, Output 2 (adapted soft skills via LMS and newly developed RE training modules for future use by MoNE) will also indirectly benefit this group by providing resources and enhancing the overall training ecosystem.

Businesses in the RE sector: These businesses are key stakeholders and indirect beneficiaries. The project will engage with them during the needs assessment (Activity 1.1) to understand labour demands and hiring barriers. They will potentially benefit from access to the pool of assessed and mentored Phase I graduates facilitated through Activity 1.2, and from the long-term availability of a better-skilled workforce resulting from the needs-based RE training modules (developed under Activity 2.2) being integrated by MoNE.

Government institutions involved in job matching and training delivery in the RE sector: Ministry of National Education (MoNE) and the National Employment System (represented by İŞKUR): These institutions play crucial roles in facilitating employment in the RE sector. Through the project, MoNE’s capacities in training delivery will be supported with newly developed, needs-based training modules and an LMS platform (Activity 2.2) The potential employee pool within the national employment system database will be expanded and potentially enhanced by the registration of assessed and supported Phase I graduates (Activity 1.2).

Resources Required to Achieve the Expected Results

The project will be financed by the Korean Government (500,000.00 USD). The technical cooperation model applied by the UNDP in collaboration with the local implementing partners will be maintained in the implementation of the current project (i.e. National Implementing Model with full Country Office support).

In this regard, through Preparedness, Response and Resilience Programme, UNDP will provide contribution both in programmatic areas and project implementation areas (operation) in the light of the experiences gained through projects already implemented/being implemented by UNDP through the following items in accordance with its corporate competencies and operation model:

- Provision of qualified individual and/or corporate expertise support, access to national and international knowledge and cooperation networks

- Transferring field level implementation experience into the project gained in other countries where UNDP operates,

- Using the analysis and planning tools developed/supported by UNDP within local/regional development areas in planning, implementation and monitoring of project activities,

- Human resources management, financial management, procurement, monitoring, and evaluation etc. and provision of services and procurement of goods provided in UNDP’s corporate operation model, and

- Fund raising for the next phases of the project.

By its mandate, UNDP does not provide direct financial resources for the projects. Among others, UNDP’s main corporate competency areas rather include provision of synergies and cooperation among projects, enabling and facilitating access to financial resources/schemes for qualified project ideas and management of fund-raising processes. In this sense, the project will benefit from the lessons learned and key project outputs derived from different completed and/or on-going projects of UNDP.

Required human resources for the project is determined as a Project Team consisting of a part-time Project Manager, Project Associate, part-time Project Assistant, and, in addition to the Project Team, short-term consultants. Moreover, MoNE project team will be supported by a project assistant primarily tasked with handling the reporting from the MoNE’s LMS in relation to the Project to ensure accurate payments and monitoring. In addition to human resources, equipment and furniture, hardware and software, communication and audio-visual equipment, IT equipment are determined to be needed during the Project. Rental and maintenance premises and other support services provided by operations and program staff are required within the scope of the Project.

Risks and Assumptions

The main assumptions for the success of the overall Action and its implementation are:

- The political and security situation in Türkiye remains stable, ensuring uninterrupted implementation of the project activities

- The regulatory framework for work permits remains supportive, allowing smooth issuance of work permits for migrant workers.

- Developments in relation to the regime change in Syria do not lead to stricter legislation and policies for SuTP in Türkiye.

- Private sector in RE sector has the capacity and willingness to absorb new employees.

- MoNE’s ownership and utilisation of the new vocational training modules.

- National Employment System’s utilisation of the new soft skills training modules.

- Training programs are relevant and effective in leading to employment.

- Training programs are aligned with market needs.

- SuTP beneficiaries have Turkish language skills to complete the soft skills training programme.

Identified risks and mitigation measures for smooth implementation of the project are listed in Annex-

‘’Project Risk Register’’.

Partnerships

The success of the initiative relies on strong collaboration with key institutional partners, particularly MoNE and academia for the development of RE modules, as well as effective engagement with the national employment system and private sector actors. These partnerships and engagements are instrumental in ensuring that workforce development efforts align with Türkiye’s renewable energy labour market realities and vocational training priorities.

The Ministry of National Education (MoNE) is a crucial stakeholder and implementing partner in shaping vocational education and workforce development. As Türkiye’s leading institution in vocational training and education policy, MoNE’s involvement ensures that the project’s developed training modules (Activity 2.2) align with national vocational education standards and integrates the latest industry requirements. This is particularly important given the evolving technological landscape of the renewable energy sector. By collaborating with MoNE, the initiative will benefit from institutional expertise and facilitate the potential long-term integration of the developed training resources into the national system. MoNE already has 5 different curricula on renewable energy vocational trainings; (i) Solar Energy Systems, (ii) Solar Panel and PV Installation, Maintenance and Repairment, (iii) Wind Farm Installation, Maintenance and Repairment, (iv) Solar and Wind Energy System Development Compatibility, (v) Composite Material Production. While developing the new curricula and the training materials under Activity 2.2, the UNDP and MoNE project teams will review the existing curricula to ensure complementarity and avoid duplication.

The national employment system’s job-seeker database serves as a critical platform for increasing the visibility of Phase I graduates. The project, through the Employability Support and Mentorship service (Activity 1.2), will facilitate the registration of selected, job-ready Phase I graduates onto this database. Utilizing the İŞKUR database in this manner is expected to enhance beneficiaries' connection to the formal labour market, aligning with recommendations from Phase I feasibility reports.

Other stakeholders remain crucial for project success. Private sector companies and industry associations (such as GENSED, TÜREB, GÜNDER, ENSİA) are key informants for the Gaps and Needs Assessment (Activity 1.1) and essential partners for the job matching and placement efforts under the mentorship service (Activity 1.2). Universities, local governorates/municipalities, research institutes, development agencies, vocational high-schools, foundations related to the RE sector, and NGOs in provinces where activities will take place will also be engaged as relevant during the assessment and implementation phases.

Communication and Visibility

An outcome-driven communication strategy will be developed to showcase the continued support of Government of Korea, while highlighting how Phase II builds on achievements of Phase I. The focus will be on communicating the transition from vocational training to employability, system integration, and curriculum customization—emphasizing the journey from learning to earning.

The priority will be on continuity, scaling, and long-term sustainability, reflecting how communication strategy will effectively convey the programme’s outcomes and long-term contributions through transformative results, especially rebuilding efforts to restoring livelihoods and economic stability.

Outcome level communication will also increase public awareness. Regular communications will incorporate real-time milestones and cumulative achievements to increase public awareness and stakeholder engagement.

Effective communication will play a vital role in highlighting the transformative impact of Government of Korea’s support. By shifting the narrative from activities to outcomes, the programme’s real success—improved livelihoods, economic stability, and social resilience—will be widely recognized. Communication efforts will focus on ensuring that the voices of beneficiaries remain central to the story of Türkiye’s recovery. To strengthen this aspect, success stories of Phase I and key impact data will be a reference source to demonstrate the expanded support of the Government of Korea as a respond to the devastating earthquakes in Türkiye.

It will underscore how support from the Republic of Korea has not only contributed to skills development but also inspired collective hope and direction for a more resilient, inclusive, and sustainable future.

Stakeholder Engagement

Phase I Graduates (Unemployed SuTP and host community members, women and men) are the identified main target group for the direct support interventions of the project in Phase II. Recognizing the challenges they face in securing stable employment due to factors such as language barriers, potential skills gaps, lack of knowledge and qualifications, and limited understanding of the Turkish labour market, the Project will address these needs primarily through targeted assessment of their status and barriers (Activity 1.1), provision of tailored employability support including CV enhancement, mentorship, and facilitated job matching (Activity 1.2), and access to adapted soft skills training via an online platform (Activity 2.1). The development of vocational training modules under Output 2 primarily benefits future potential employees and the sector by addressing identified needs.

The main stakeholder in the project is the Ministry of National Education (MoNE) which will be the implementing partner, collaborating closely on project oversight and assuming ownership of the training modules to be developed (Activity 2.2) as part of its potential future curricula framework in the RE field. Engagement with other key stakeholders identified in the Partnerships section (private sector companies, industry associations, etc.) will be crucial for the needs assessment, mentorship/placement activities, and module development.

Stakeholder engagement plan

| Stakeholder/Target Group | Interests/Responsibility | Role in project | Information to be disclosed | Method and timeframe |
| --- | --- | --- | --- | --- |
| Government of Korea | As the donor, contributing to the refugee response activities in Türkiye | Donor | PSC Board Project outputs Project reports | Method: Meeting E-mail Formal Letter Time Frame: As per M&E (Monitoring and Evaluation) Plan |
| Ministry of National Education, Department of Lifelong Learning | MoNE regulates and oversees lifelong learning practices | Implementing Partner | PSC Board Project outputs Project reports Trainings/Workshops | Method: Meeting Training, E-mail, Formal Letter Time Frame: As per M&E Plan and AWP (Activity Work Plan) |
| Public Institutions |  |  |  |  |
| Presidency of Republic of Türkiye, Strategy and Budget Office (PSB) | The SBO’s role is to accelerate the economic and social development of the Republic of Türkiye, the Presidency of Strategy and Budget, with the mission of making development balanced and sustainable. | A member of the PSC with a role to link the project results to the national development policy and oversight for international agreements. | PSC Board Review of the project’s activities and outputs Participation in the SC (Steering Committee) is required when it is deemed necessary for decision-making and project coordination. | Method: E-mail Formal Letter Telephone Invitation Meeting Timeframe: Annual |
| Ministry of Foreign Affairs (MoFA) | MFA is responsible for conducting foreign relations of the Republic of Türkiye including diplomatic missions abroad and for the promotion of Turkish culture, as well as for implementing the country’s foreign policy in accordance with its national interests. | A member of the PSC with a role to link the project results to the national development policy and oversight for international agreements. | PSC Board Review of the project’s activities and outputs. Participation in the SC (Steering Committee) is required when it is deemed necessary for decision-making and project coordination. | Method: E-mail Formal Letter Telephone Invitation Meeting Timeframe: Annual |
| Presidency of Migration Management (PMM) | Responsible for migration management in Türkiye | A member of the PSC with a role to link the project results to migration management and social inclusion policies of Türkiye. | PSC Board Participation in the SC (Steering Committee) is required when it is deemed necessary for decision-making and project coordination. | Method: E-mail Formal Letter Telephone Invitation Meeting Timeframe: Annual |
| Others |  |  |  |  |
| Private Sector Companies (RE Sector) | Access to skilled workforce relevant to industry needs; sector growth. | Key informants for needs assessment (Act 1.1); provide sector insights; potentially advise on module relevance (Act 2.2). | Project objectives; Relevant findings from needs assessment; Draft module outlines (for feedback). | Method: Meetings, Consultations Timeframe: Primarily during Act 1.1 & Act 1.2 |
| Industry Associations (RE Sector - e.g., GENSED, TÜREB, GÜNDER, ENSİA) | Representing sector interests; setting standards; understanding workforce needs. | Key informants for needs assessment (Act 1.1); provide sector insights; potentially advise on module relevance (Act 2.2). | Project objectives; Relevant findings from needs assessment; Draft module outlines (for feedback). | Method: Meetings, Consultations Timeframe: Primarily during Act 1.1 & Act 2.2 development |
| Chambers of Commerce and Industry | Local economic development; supporting member businesses; linking employers and job seekers. | Inform needs assessment (local context, Act 1.1); facilitate connections with local businesses for job matching/mentorship (Act 1.2). | Project objectives; Details of employability support service; Collaboration opportunities. | Method: Meetings, Consultations Timeframe: Primarily during Act 1.1 & Act 1.2 |
| CSOs / NGOs | Supporting groups (SuTP, Turkish Citizens, women, PwD); community outreach; thematic expertise (e.g., inclusion, livelihoods). | Inform needs assessment (beneficiary perspective, Act 1.1); potential partners for outreach, specific activities (e.g., inclusion). | Project objectives; Relevant activities & findings; Collaboration opportunities. | Method: Meetings, Consultations, Information sharing Timeframe: As relevant, esp. Act 1.1 |
| Populations |  |  |  |  |
| Local Communities |  | Final beneficiary | Dissemination of Project Outputs | Method: Social Media UNDP website Timeframe: As per Annual Work Plan |
| Refugee Populations |  | Final beneficiary | Dissemination of Project Outputs | Method: Social Media UNDP website Timeframe: As per Annual Work Plan |

Digital Solutions

Within the scope of the project, soft skill courses will be offered to the beneficiaries via digital tools. Accordingly, the Project will provide a contribution to MoNE digital capacities. The modules and the Learning Management Systems will be produced and transferred to MoNE.

Graduates of Phase 1 trainings will be reached out via phone for provision of information on the support and trainings provided through the Project.

Due to UNDP’s global work, a formal approach to the data lifecycle must be adapted within the Project. According to the data Principles that every project must adhere to, the project will safeguard personal data, uphold the highest ethical standards and manage data responsibly. The information of beneficiaries using the system will be stored within the system and not shared with any other parties without user consent.

The critical risks with data collection such as security issues and vulnerabilities that leak data to malicious third parties, collecting unnecessary personal data that is used, oversharing collected data with authorised third parties, breaking local privacy laws in the country, will be reminded to the responsible parties for these digital tools.

The parties will be clear towards the beneficiaries about who owns the data, who can access and manage it, what it can and cannot be used for, where, how, and with whom it will be shared, how it will be collected continuously. Specific consent will be asked from the users, and they will be allowed to request removal of their data entirely.

Knowledge

The project will produce several knowledge products which are listed below.

| Knowledge Products | Timing | Expected Content |
| --- | --- | --- |
| Gaps and Needs Assessment on the Labour Supply and Demand in the RE Sector | By the 4th month of the Project. | Information/data collected during assessment activities (desk review, consultations, focus groups); Analysis of Phase I graduate status, skills, barriers (including women targeted perspective), and aspirations; Analysis of employer needs, hiring challenges, and matchmaking effectiveness; Identification of potential entrepreneurship niches; Suggestions/recommendations on targeted employability support mechanisms and the content/focus of RE training materials to be developed (Activity 2.2). |
| RE Training Modules | By the completion of the Project | Customised RE training modules and materials developed based on the Activity 1.1 assessment and specific industry needs (e.g., manufacturing, new tech, vocational qualification certification alignment), detailing the scope and content for potential future training delivery. |
| Soft Skills Training Programme | By the 6th month of the Project | An online platform (LMS) hosting selected existing soft skills content (from FRIT Project) chosen based on the findings of the needs assessment (Activity 1.1), to be delivered via the online platform. |

Sustainability and Scaling Up

The project’s sustainability and exit strategy focus on embedding the advancements within Türkiye’s existing vocational education and employment infrastructure, ensuring benefits extend beyond the project's implementation period and contributing to national climate and development goals. A key element of sustainability is the development and transfer customized training modules and associated Learning Management Systems into the MoNE’s system into potential integration into existing renewable energy curricula. These modules, informed by the findings of the needs assessment conducted under the project, will be tailored to address specific skill gaps identified by businesses in the sector. By aligning these additions with industry demands and national priorities including the development of a skilled workforce for the green transition as emphasized in Türkiye's Climate Change Mitigation Strategy and Action Plan (2024-2030), the project aims to ensure that vocational education remains responsive to labour market needs, increasing the long-term employability of future trainees. The transfer of these accessible online vocational training resources, developed through collaboration between non-formal education structures (MoNE) and academia represents a core part of the exit strategy, ensuring lasting assets within the national system which can be utilized by MoNE to contribute to the national goal of enhancing skills in the expanding RE sector. This handover process builds upon the successful transfer of outputs to MoNE in Phase I.

Beyond curriculum support, the project contributes to sustainability through enhancing employment facilitation mechanisms for Phase I graduates. The supported registration of selected, job-ready individuals in national employment system’s Job Seekers Database will increase their visibility to employers while leveraging Türkiye’s existing public employment services. The targeted mentorship and placement support provided in Phase II further aims to create sustainable employment links.

The project’s sustainability is further reinforced by its engagement with private sector actors, including RE companies, industry associations, and employer networks during the assessment and employability support phases. Since the new modules are developed based on business needs, their continued relevance will encourage ongoing employer participation in skills development initiatives. This structured collaboration fosters a self-sustaining cycle, where vocational training continuously evolves to match industry requirements.

Another aspect of sustainability lies in the project’s emphasis on formal employment pathways and potential entrepreneurship. By facilitating connections for Phase I graduates and developing resources aligned with potential certifications, the initiative aims to reduce reliance on informal job markets, enabling beneficiaries to be integrated into stable, regulated employment opportunities in the RE sector, contributing to the Just Transition objectives outlined in the national climate action plans.

Furthermore, the project’s commitment to inclusion of women strengthens its long-term impact. By addressing barriers to women's participation and ensuring that training delivery methods are accessible and inclusive, the initiative fosters greater women participation in the workforce. Over time, this is expected to contribute to systemic changes that promote women’s increased participation in the RE sector, enhancing diversity and sustainability within the industry.

Through its integration into national education and employment systems, alignment with private sector needs, links to national climate strategy goals, and commitment to formal workforce development and equality, the project lays the foundation for a long-lasting impact. By ensuring that vocational training remains relevant, employment facilitation mechanisms are strengthened, and industry partnerships are sustained, the project contributes to the ongoing growth of Türkiye’s RE workforce beyond the project life cycle.

# Project Management

Cost Efficiency and Effectiveness

The Project will build on existing national and local structures and capacities in Türkiye especially those of MoNE. This will enable the project implementation unit to have an efficiency in project management in terms of cost efficiency and effectiveness. Moreover, UNDP will adopt a programmatic approach in line with its new structure, whereas staffing will be made to serve for and to be costed to more than one project where possible.

The project will be implemented as part of UNDP’s Crisis Preparedness Response and Resilience Programme and will thereby leverage on existing management and staff capacities as well as learnings from other relevant projects funded under the programme by other donors. Specifically, for the soft skills activity, the project will achieve significant cost efficiency by leveraging and utilizing existing online training content previously developed for the EU-funded FRIT Project, thereby minimizing costs associated with new content creation. Furthermore, synergies will be sought with other UNDP initiatives focusing on women groups and employability, such as the Sabancı Foundation-funded "Young Women Building Their Future" project which targets NEET women, potentially leveraging shared knowledge, outreach mechanisms, or mentorship approaches to enhance overall effectiveness and reach. The project will also build on existing experience under Phase 1 and the wider programme with the development and delivery of vocational trainings and associated digital platforms (LMS). Following a programmatic approach will also be relevant for procurement and other administrative issues, increasing cost efficiency of the project.

The current project is based on UNDP’s resilience-based development approach, which has been UNDP’s flagship response in several countries affected by the Syria crisis, including Jordan, Lebanon and Iraq. UNDP Türkiye works in close partnership with its partner offices in those countries to share lessons learned

Project Management

UNDP will deploy its in-house experience (i.e. relevant programme and operations staff) as well as mobilize other capacities in the form of Service Contracts and individual contracts. For this project, UNDP will avail the capacities of a part-time Project Manager and relevant administrative and operational support staff, with oversight of the Crisis Preparedness Response and Resilience Programme Manager.

UNDP will provide direct country office support services (including for the functions of procurement, human resources, administrative services, communication, office space), and direct project costing will apply in line with UNDP’s cost recovery policy. Financial transactions and financial statements shall be subject to internal and external auditing procedures laid down in the Rules and Regulations of UNDP, whereby the cost of audit will be charged against the relevant budget line in project budget.

Using programme and country office staff allows UNDP to build on the existing mechanisms and exploit synergies with other ongoing projects, leading to increased efficiencies in project and budget management and procurement. The direct cost of such support will be included in the project budget and pro-rated as per UNDP’s regulations.

| Project Team & Task Team members | Delivery Enabling Services |
| --- | --- |
| Project Manager | The part-time Project Manager will be employed for the project implementation duration. S/he will be reporting to the Programme Manager and in charge of managing, coordinating, and supervising project implementation to ensure the overall project relevance and performance. S/he’ll ensure proper execution of all administrative activities associated with project implementation. S/he will provide technical support to the implementing partners and act as a liaison between UNDP and the partners; ensure project reports capture results, lessons learned and good practices for possible wider application. S/he will also monitor project risks, including social and environmental risks, initially identified and submit new risks to appropriate project governing bodies for consideration and decision on possible actions. |
| Project Associate | The Project Associate will be employed for the project implementation duration. Project Associate will support the project team to ensure effective project planning and implementation. S/he is expected to compile and summarize information and data for the formulation of project work plans, draft annual/quarterly budgets, proposals on implementation arrangements, and other specific project-related topics or issues. S/he will also provide comprehensive support in all aspects of project implementation in accordance with the project document, annual work plans, and other agreements between UNDP and responsible partners. Additionally, s/he will ensure the quality of delivery by consultants, beneficiaries, and contracted companies, and communicate findings. They will be responsible for ensuring compliance with project business processes, including UNDP Project Operational Policies and Procedures (POPP) and UNDP Standard Operating Procedures (SOP). Furthermore, s/he will provide administrative and logistical support to ensure successful project delivery, which includes organizing/coordinating project events and selecting appropriate venues, coordinating project procurement procedures, maintaining project records and files, recruiting project team members, and supporting contracting activities. |
| Project Assistant | The part-time Project Assistant will be employed for the project implementation duration. Project Assistant will support the project team to ensure effective project planning and implementation. S/he will assist in compiling and summarizing information and data for the formulation of project work plans, and in consultation with the project team, draft annual/quarterly budgets, proposals on implementation arrangements, and other specific project-related topics or issues. S/he will support project implementation in accordance with the project documents, annual work plans, and other agreements between UNDP and responsible partners. S/he will review project documents for completeness and compliance with relevant rules and procedures, identifying inconsistencies for referral to the supervisor. S/he will compile, summarize, and present basic information/data on specific projects and related topics or issues. Additionally, s/he will provide administrative and logistical support to ensure successful project delivery, which includes organizing/coordinating project events, procurement and finance-related activities, contract management, recruitment, and coordination of field visits and project-related missions. The Project Assistant will also be responsible for drafting correspondence and documents, supporting the finalization of administrative correspondence, handling telephone inquiries, fax, post, and e-mail transmissions, and coordinating appointments. S/he will provide interpretation during project-related meetings and events and translate documents from English to Turkish or from Turkish to English as needed. |

# Results Framework

Intended Outcome as stated in the UNSDCF/Country [or Regional] Programme Results and Resource Framework: Outcome #1.3: By 2025, people under the Law on Foreigners and International Protection are supported towards self-reliance.

Outcome indicators as stated in the Country Programme [or Regional] Results and Resources Framework, including baseline and targets: Output 1.1. Displaced populations are equipped with the knowledge and skills to engage in the socioeconomic life of their host community. Number of people benefiting from jobs and improved livelihoods in crisis or post-crisis settings, disaggregated by sex Baseline (2021): 68,969 Target (2025): 76,169 Output 1.4. Sustainable job opportunities created for displaced populations and host communities. Number of interventions to increase labour absorption capacity of businesses to accommodate displaced populations Baseline (2021): 17 Target (2025): 29

Applicable Output(s) from the UNDP Strategic Plan: Output 3.4 Integrated development solutions implemented to address the drivers of irregular and forced migration, enhance the resilience of migrants, forcibly displaced and host communities, and expand the benefits of human mobility

Project title and Quantum Project Number: Increasing Employability for Syrian Refugees and Turkish Citizens in the Renewable Energy Sector Project Phase II

| EXPECTED OUTPUTS | OUTPUT INDICATORS | DATA SOURCE | BASELINE |  | ## TARGETS (by frequency of data collection) |  |  | ## DATA COLLECTION METHODS & RISKS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Value | Year | Year 1 | Year 2 | ## FINAL |  |
| Output 1: Employability of Job Seekers is Enhanced Through Labour Market Analysis and Job Counselling Support | 1.1.1 Needs and Gaps Assessment Report completed, identifying labour market dynamics, graduate status/barriers, skill shortages and employer | Project Reports, LMS platform status | No | 2025 | Yes | No | Yes | Project Monitoring and Evaluation (M&E) tools, no identified risk in data collection |
|  | 1.1.2 Number and percentage of profiled Phase I graduates supported for registration in national employment system's Job Seekers Database | LMS database | 0 | 2025 | a)Total: 150 b) Female: 40% c) SuTP: 40% | a)Total: 450 b) Female: 40% c) SuTP: 40% | a)Total: 600 b) Female: 40% c) SuTP: 40% | Project Monitoring and Evaluation (M&E) tools, no identified risk in data collection |
|  | 1.1.3. Number and percentage of profiled Phase I graduates receiving targeted mentorship and job counselling | Project reports | 1 | 2025 | a)Total: 25 b) Female: 40% c) SuTP: 40% | a)Total: 75 b) Female: 40% c) SuTP: 40% | a)Total: 100 b) Female: 40% c) SuTP: 40% | Project Monitoring and Evaluation (M&E) tools, no identified risk in data collection |
|  | 1.1.4 Percentage of female participants reporting increased confidence level as a result of mentoring/coaching |  |  |  | Total: 70% |  |  |  |
| Output 2: Learning Management System Updated to Support Access to the Renewable Energy Sector. | 2.1.1 Soft Skills Training Platform Developed | Project Reports | No | 2025 | Yes |  | Yes |  |
|  | 2.1.2 Number and percentage of beneficiaries who completed the soft skills training program via LMS | Project reports, Project M&E tools and systems | 0 | 2025 | a)Total: 150 b) Female: 40% c) SuTP: 40% | a)Total: 450 b) Female: 40% c) SuTP: 40% | a)Total: 600 b) Female: 40% c) SuTP: 40% |  |
|  | 2.1.3 Percentage of female participants reporting increased confidence level as a result of soft skills programs | Project Reports | 0 | 2025 | Total: 70% |  |  |  |
|  | 2.1.4 Percentage point increase in the knowledge and skills of the soft skills training participants (between pre and post tests) | Project reports, tests to participants (pre/post) | 0 | 2025 | Total: 30% |  |  |  |
|  | 2.1.5 RE vocational training modules (via blended learning) updated and operationalized | Project reports, Consultant reports | 2 | 2025 | 2 | 3 | 5 |  |

# Monitoring And Evaluation

In accordance with UNDP’s programming policies and procedures, the project will be monitored through the following monitoring and evaluation plans: [Note: monitoring and evaluation plans should be adapted to project context, as needed]

Monitoring Plan

| Monitoring Activity | Purpose | Frequency | Expected Action | Partners (if joint) |
| --- | --- | --- | --- | --- |
| Track results progress | Progress data against the results indicators in the RRF will be collected and analysed to assess the progress of the project in achieving the agreed outputs. | Yearly, or in the frequency required for each indicator. | Slower than expected progress will be addressed by project management. | N/A |
| Monitor and Manage Risk | Identify specific risks that may threaten achievement of intended results. Identify and monitor risk management actions using a risk log. This includes monitoring measures and plans that may have been required as per UNDP’s Social and Environmental Standards. Audits will be conducted in accordance with UNDP’s audit policy to manage financial risk. | At least annually | Risks are identified by project management and actions are taken to manage risk. The risk log is actively maintained to keep track of identified risks and actions taken. | N/A |
| Learn | Knowledge, good practices and lessons will be captured regularly, as well as actively sourced from other projects and partners and integrated back into the project. | At least annually | Relevant lessons are captured by the project team and used to inform management decisions. | N/A |
| Annual Project Quality Assurance | The quality of the project will be assessed against UNDP’s quality standards to identify project strengths and weaknesses and to inform management decision making to improve the project. | At the design and closure stage of the project | Areas of strength and weakness will be reviewed by project management and used to inform decisions to improve project performance. | N/A |
| Review and Make Course Corrections | Internal review of data and evidence from all monitoring actions to inform decision making. | At least annually | Performance data, risks, lessons and quality will be discussed by the project board and used to make course corrections. | N/A |
| Project Report | A progress report will be presented to the Project Board and key stakeholders, consisting of progress data showing the results achieved against pre-defined annual targets at the output level, the annual project quality rating summary, an updated risk long with mitigation measures, and any evaluation or review reports prepared over the period. | Annually |  | N/A |
| Project Review (Project Board) | The project’s governance mechanism (i.e., project board) will hold regular project reviews to assess the performance of the project and review the Multi-Year Work Plan to ensure realistic budgeting over the life of the project. In the project’s final year, the Project Board shall hold an end-of project review to capture lessons learned and discuss opportunities for scaling up and to socialize project results and lessons learned with relevant audiences. | Annually | Any quality concerns or slower than expected progress should be discussed by the project board and management actions agreed to address the issues identified. | N/A |

# Multi-Year Work Plan

| EXPECTED OUTPUTS | PLANNED ACTIVITIES | PLANNED BUDGET BY YEAR |  | RESPONSIBLE PARTY | PLANNED BUDGET |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Y1 | Y2 |  | Funding Source | Budget Description | Amount |
| Output 1: Employability of Job Seekers is Enhanced Through Labour Market Analysis and Job Counselling Support. | 0.2. Kick-off meeting |  |  | UNDP&MoNE | Gov. of Korea | 71400 Contractual Services – Individual 72100 Contractual Services-Companies 75700 Training, Workshops and Confer 71600 Travel 71300 Short-term consultants 74100 Professional services 74200 Audio Visual&Printing Costs 72800 Information Technology Equipment 73100 Rental and Maintenance Premises 74596 Delivery Enabling Services | $ 138.600,00 $ 235.000,00 $ 20.000,00 $ 30.000,00 $ 37.000,00 $ 3.500,00 $ 6.000,00 $ 10.000,00 $ 23.000,00 $ 14.378,44 |
|  | 1. Comprehensive Assessment of RE Labour Market Dynamics and Phase I Graduate Employability | X |  |  |  |  |  |
|  | 2.Targeted Employability Support and Mentorship Service for Phase I Graduates | X | X |  |  |  |  |
| Output 2: Learning Management System Updated to Support Access to the Renewable Energy Sector | 1.Learning Management System Development for Soft Skills | X | X | UNDP&MoNE | Gov. of Korea |  |  |
|  | 2. Learning Management System Development for RE Training Modules | X |  |  |  |  |  |
|  | 3. Development of Course Content | X |  |  |  |  |  |
| Subtotal Direct Eligible Cost |  |  |  |  |  |  | $517.478,44 |
| General Management Support (%8) |  |  |  |  |  |  | $41.398,28 |
| Levy (%1) |  |  |  |  |  |  | $5.650,00 |
| Total Project Budget |  |  |  |  |  |  | $564.526,72 |

# Governance and Management Arrangements

Figure: Project Management Structure

Project Board

End Recipient

Ministry of National Education

Donor

Government of Korea

Organization

UNDP Türkiye CO

Natural Members of PB

PSB*, MFA*

Project Technical Management Team

MoNE

UNDP

Project Management Structure

Project Implementation Team

Project Manager (Ankara)

Project Associate (Ankara)

Project Assistant (Ankara)

Project Assistant (Ankara at the MoNE)

UNDP Assistant Resident Representative (Programme)

Preparedness, Response and Resilience Programme Manager

Monitoring and Knowledge Management Officer

Partnership and Quality Assurance

This project will be implemented through a national implementation modality (NIM), with MoNE as the implementing partner. UNDP’s rules and regulations for program management will apply throughout the project and UNDP will also provide direct project management support including procurement, financial management and strategic support.

The Project Support role provides administration, management and technical support to the Project Manager as required by the needs of the Project Manager. The provision of any Project Support on a formal basis is optional.  In most projects, project support includes HR, procurement and PSC (Program Service Centre) services.

A Project Board (PB, also called Project Steering Committee) with representation from MoNE, Presidency of Strategy Budget, Ministry of Foreign Affairs, Ministry of Labour and Social Security, Presidency of Migration Management, EUD and UNDP will be set up to guide and oversee the implementation of the project. The PB will jointly decide on the critical aspects of the project, including possible synergies with other ongoing initiatives in the region. PB will also be monitoring the results achieved with the project.

The Donor, which is the Government of Korea for this project, becomes a natural member of the Project Board. In addition to the donor of the Project, the Presidency of the Republic of Türkiye, the Presidency of Strategy and Budget (PSB) & Ministry of Foreign Affairs are also natural members of the Project Board. PSB is the Government coordinating agency of the UNDP in Turkey and ensures that all UNDP programmes are designed/implemented in line with national priorities. Ministry of Foreign Affairs gives final approval to all UNDP implemented projects, hence has an overall oversight function under each project.

In case consensus cannot be reached within the Board, the UNDP Resident Representative (or their designate) will mediate to find consensus and, if this cannot be found, will take the final decision to ensure project implementation is not unduly delayed.

The Project Board will:

When project is initiated:

- Provide general, high-level, strategic oversight to the project activities including financial oversight

- Agree on the Project Manager responsibilities, as well as the responsibilities of the other members of the Project team

- Delegate any Project Assurance function as appropriate.

- Review and appraise detailed Project Plans and AWP, including the risk log and the monitoring and communication plan.

During the implementation / running of the project, specific roles of the PB will include:

- Provide project and policy implementation oversight

- Provide overall guidance and direction to the project, ensuring it remains within specified constraints

- Approve annual work plans and budgets; and based on the approved annual work plans (AWP) authorize any major deviation from the approved work plans and budgets.

- Conduct meetings at least twice a year to review Project Progress Reports and provide direction and recommendations to ensure agreed deliverables are produced satisfactorily according to plans.

- Approve changes and amendments to the existing project document

- Consider recommendations from the Technical Working Group (if any).

- Monitor progressive achievement of project objectives and provide guidance on long term sustainability of the project’s achievements

- Provide high-level quality assurance for project results and input and advice to on-going risk analysis.

- Undertake mobilization of funding for the project and consider funding for emerging issues.

- Invite representatives of other project beneficiaries to inform on their specific activities and needs.

- Provide overall guidance and direction to the project.

- Address project issues as raised by the Project Manager

- Provide guidance and agree on possible management actions to address specific risks.

- Agree on Project Manager’s tolerances within the AWP.

- Conduct regular meetings to review the Project Annual Progress Report and provide direction and recommendations to ensure that the agreed deliverables are produced satisfactorily according to plans.

- Review Combined Delivery Reports (CDR) prior to certification by the Implementing Partner.

- Appraise the Project Annual Review Report, make recommendations for the next AWP, and inform the Outcome Board about the results of the review.

- Provide ad-hoc direction and advice for exception situations when project manager’s tolerances are exceeded.

- Assess and decide on project changes through revisions.

When the project is being closed:

- Review and approve the Final Project Review Report, including lessons learned.

- Commission project evaluation when required.

- Assure that all Project deliverables have been produced satisfactorily.

- Review and approve the Final Project Review Report, including Lessons-learned.

- Make recommendations for follow-on actions to be submitted to the Outcome Board.

- Commission project evaluation if it is required.

- Notify operational completion of the project to the Outcome Board

The PB will meet quarterly throughout project period. One of the quarterly meetings of the Project Board will be held together with the Advisory Committee to elaborate the initial results of the activities.

Senior Supplier (UNDP)

The Senior Supplier, who is UNDP for this project, represents the interests of the parties which provide funding and/or technical expertise to the development project. UNDP’s primary function within the Project Board is to provide guidance regarding the technical feasibility of the project. The main responsibilities are as follows;

- to make sure that progress towards the outputs remains consistent from the UNDP’s perspective,

- to promote and maintain focus on the expected output(s)

- to ensure that the UNDP resources required for the project are made available,

- to contribute UNDP opinions on PB decisions on whether to implement recommendations on proposed changes, and

- to arbitrate on, and ensure resolution of, any UNDP priority or resource conflicts.

Implementation Partners

The implementation partners will be MoNE and UNDP and will be responsible for, among others, contributing to the initiating of the Project and further carrying out all activities in line with the Project work plan, following and monitoring the proper implementation of activities of the Project and review the reporting to the Project Steering Committee (PSC), mobilizing and coordinating other institutions involved in the Project, ensuring proper participation and representation of relevant Turkish institutions in activities organized within the Project, reviewing and approving, in a timely manner, the Project outputs.

Project Assurance

The Project Assurance role supports the Project Board by carrying out objective and independent project oversight and monitoring functions. This role ensures appropriate project management milestones are managed and completed.

Project Assurance has to be independent of the Project Manager; therefore, the Project Board cannot delegate any of its assurance responsibilities to the Project Manager. At UNDP Project Assurance function belongs to ARR/P, Portfolio Manager, M&E and KM Analyst and M&E Advisor Portfolio with a clear mandate for oversight and monitoring functions.

Project assurance can also include key staff in Beneficiary institutions that have a stake in the quality execution of the project. However, project assurance function cannot be assumed by Senior Executive since assurance function is to be carried out by an impartial party.

The Project will be led by a project manager who will be responsible for the day-to-day management of project implementation including administration and project finance. The Project Manager will be responsible for overall team management and supervision in both Ankara and field locations. The Project Manager will be the first responsible for project level reporting and support project specific donor engagement. Project Managers are also focal points for respective national level Government implementing partner.

Project’s day-to-day implementation will be carried out by the Project team as well as UNDP staff providing direct project support.

UNDP has received total budget (USD 500,000) from the donor, Government of Korea, and will be responsible of making payments according to the needs of project activities (as outlined in budget section). UNDP will also provide direct project implementation support for procurement, contract management and budget/financial management as well as content. UNDP’s direct costs will be charged in line with its rules and regulations, as outlined in the project document and budget. Financial transactions and financial statements shall be subject to the internal and external auditing procedures laid down in the Regulations and Rules of UNDP.

# Legal Context

Türkiye is a signatory of a basic agreement to govern the United Nations Development Programme’s (UNDP) assistance to the country, being the provisions of the Revised Standard Agreement signed between the Government and the Technical Assistance Board, which is one of the predecessor entities of UNDP (the “Basic Agreement”) on 21 October 1965.

In this regard, the project document shall be the instrument envisaged and defined in the Supplemental Provisions,(https://popp.undp.org/_layouts/15/WopiFrame.aspx?sourcedoc=/UNDP_POPP_DOCUMENT_LIBRARY/Public/FRM_Pipeline%20and%20Revenue%20Management_Annexure%208%20-%20SBAA_Standard%20Annex%20to%20Project%20Document.doc&action=default&DefaultItemOpen=1) to the Project Document, attached hereto and forming an integral part hereof, as “the Project Document”.

This project will be implemented by Ministry of National Education (MoNE) (“Implementing Partner”) in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

# Risk Management

Government Entity (NIM)

- Consistent with the Article III of the SBAA [or the Supplemental Provisions to the Project Document], the responsibility for the safety and security of the Implementing Partner and its personnel and property, and of UNDP’s property in the Implementing Partner’s custody, rests with the Implementing Partner.  To this end, the Implementing Partner shall:

- put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

- assume all risks and liabilities related to the Implementing Partner’s security, and the full implementation of the security plan.

- UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the Implementing Partner’s obligations under this Project Document.

- The Implementing Partner agrees to undertake all reasonable efforts to ensure that no UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism, that the recipients of any amounts provided by UNDP hereunder do not appear on the United Nations Security Council Consolidated Sanctions List, and that no UNDP funds received pursuant to the Project Document are used for money laundering activities. The United Nations Security Council Consolidated Sanctions List can be accessed via https://www.un.org/securitycouncil/content/un-sc-consolidated-list.

- The Implementing Partner acknowledges and agrees that UNDP will not tolerate sexual harassment and sexual exploitation and abuse of anyone by the Implementing Partner, and each of its responsible parties, their respective sub-recipients and other entities involved in Project implementation, either as contractors or subcontractors and their personnel, and any individuals performing services for them under the Project Document.

(a) In the implementation of the activities under this Project Document, the Implementing Partner, and each of its sub-parties referred to above, shall comply with the standards of conduct set forth in the Secretary General’s Bulletin ST/SGB/2003/13 of 9 October 2003, concerning “Special measures for protection from sexual exploitation and sexual abuse” (“SEA”).

(b) Moreover, and without limitation to the application of other regulations, rules, policies and procedures bearing upon the performance of the activities under this Project Document, in the implementation of activities, the Implementing Partner, and each of its sub-parties referred to above, shall not engage in any form of sexual harassment (“SH”). SH is defined as any unwelcome conduct of a sexual nature that might reasonably be expected or be perceived to cause offense or humiliation, when such conduct interferes with work, is made a condition of employment or creates an intimidating, hostile or offensive work environment. SH may occur in the workplace or in connection with work. While typically involving a pattern of conduct, SH may take the form of a single incident. In assessing the reasonableness of expectations or perceptions, the perspective of the person who is the target of the conduct shall be considered.

- a) In the performance of the activities under this Project Document, the Implementing Partner shall (with respect to its own activities), and shall require from its sub-parties referred to in paragraph 4 (with respect to their activities) that they, have minimum standards and procedures in place, or a plan to develop and/or improve such standards and procedures in order to be able to take effective preventive and investigative action. These should include: policies on sexual harassment and sexual exploitation and abuse; policies on whistleblowing/protection against retaliation; and complaints, disciplinary and investigative mechanisms. In line with this, the Implementing Partner will and will require that such sub-parties will take all appropriate measures to:

  - Prevent its employees, agents or any other persons engaged to perform any services under this Project Document, from engaging in SH or SEA;

  - Offer employees and associated personnel training on prevention and response to SH and SEA, where the Implementing Partner and its sub-parties referred to in paragraph 4 have not put in place its own training regarding the prevention of SH and SEA, the Implementing Partner and its sub-parties may use the training material available at UNDP;

  - Report and monitor allegations of SH and SEA of which the Implementing Partner and its sub-parties referred to in paragraph 4 have been informed or have otherwise become aware, and status thereof;

  - Refer victims/survivors of SH and SEA to safe and confidential victim assistance; and

  - Promptly and confidentially record and investigate any allegations credible enough to warrant an investigation of SH or SEA. The Implementing Partner shall advise UNDP of any such allegations received and investigations being conducted by itself or any of its sub-parties referred to in paragraph 4 with respect to their activities under the Project Document, and shall keep UNDP informed during the investigation by it or any of such sub-parties, to the extent that such notification (i) does not jeopardize the conduct of the investigation, including but not limited to the safety or security of persons, and/or (ii) is not in contravention of any laws applicable to it. Following the investigation, the Implementing Partner shall advise UNDP of any actions taken by it or any of the other entities further to the investigation.

b) The Implementing Partner shall establish that it has complied with the foregoing, to the satisfaction of UNDP, when requested by UNDP or any party acting on its behalf to provide such confirmation. Failure of the Implementing Partner, and each of its sub-parties referred to in paragraph 4, to comply of the foregoing, as determined by UNDP, shall be considered grounds for suspension or termination of the Project.

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

- The Implementing Partner shall: (a) conduct project and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

- All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any programme or project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

- The Implementing Partner will take appropriate steps to prevent misuse of funds, fraud or corruption, by its officials, consultants, responsible parties, subcontractors and sub-recipients in implementing the project or using UNDP funds.

- In the implementation of the activities under this Project Document, UNDP places reasonable reliance upon the Implementing Partner for it to apply its laws, regulations and processes, and applicable international laws regarding anti money laundering and countering the financing of terrorism, to ensure consistency with the principles of then in force the UNDP Anti-Money Laundering and Countering the Financing of Terrorism Policy.

- The Implementing Partner will ensure that its financial management, anti-corruption, anti-fraud and anti money laundering and countering the financing of terrorism policies are in place and enforced for all funding received from or through UNDP.

- The requirements of the following documents, then in force at the time of signature of the Project Document, apply to the Implementing Partner: (a)UNDP Policy on Fraud and other Corrupt Practices and (b)UNDP Office of Audit and Investigations Investigation Guidelines. The Implementing Partner agrees to the requirements of the above documents, which are an integral part of this Project Document and are available online at www.undp.org.

- In the event that an investigation is required, UNDP has the obligation to conduct investigations relating to any aspect of UNDP projects and programmes in accordance with UNDP’s regulations, rules, policies and procedures. The Implementing Partner shall provide its full cooperation, including making available personnel, relevant documentation, and granting access to the Implementing Partner’s (and its consultants’, responsible parties’, subcontractors’ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with the Implementing Partner to find a solution.

- The signatories to this Project Document will promptly inform one another in case of any incidence of inappropriate use of funds, credible allegation of fraud or corruption or other financial irregularities with due confidentiality.

Where the Implementing Partner becomes aware that a UNDP project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption, the Implementing Partner will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). The Implementing Partner shall provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

- The Implementing Partner agrees that, where applicable, donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities which are the subject of this Project Document, may seek recourse to the Implementing Partner for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud, corruption or other financial irregularity, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Note:  The term “Project Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Project Document, including those with responsible parties, subcontractors, and sub-recipients.

- Each contract issued by the Implementing Partner in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from the Implementing Partner shall cooperate with any and all investigations and post-payment audits.

- Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the project, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

- The Implementing Partner shall ensure that all of its obligations set forth under this section entitled “Risk Management” are passed on to each responsible party, subcontractor and sub-recipient and that all the clauses under this section entitled “Risk Management Standard Clauses” are included, mutatis mutandis, in all sub-contracts or sub-agreements entered into further to this Project Document.

# ANNEXES

# Social and Environmental Screening Template

# UNDP Social and Environmental Screening Template (v. July 2022)

The completed template, which constitutes the Social and Environmental Screening Report, must be included as an annex to the Project Document at the design stage. Note: this template will be converted into an online tool. The online version will guide users through the process and will embed relevant guidance.

### Project Information

| Project Information |  |
| --- | --- |
| 1. Project Title | Increasing Employability in the Renewable Energy Sector Project Phase II |
| 2. Project Number (i.e. Quantum project ID, PIMS+) |  |
| 3. Location (Global/Region/Country) | Country |
| 4. Project stage (Design or Implementation) | Design |
| 5. Date | 29/04/2025 |

Part A. Integrating Programming Principles to Strengthen Social and Environmental Sustainability

QUESTION 1: How Does the Project Integrate the Programming Principles in Order to Strengthen Social and Environmental Sustainability?

Briefly describe in the space below how the project mainstreams the human rights-based approach

While this project is not strictly a humanitarian intervention, it aligns with human rights principles by ensuring equitable access to vocational training and employment facilitation for Syrians under Temporary Protection (SuTP) and host community members. The project adheres to UNDP’s rights-based approach, emphasizing non-discrimination, equal opportunity, and social inclusion by addressing barriers to formal employment and providing industry-recognized skills development. A key objective of the project is to support decent work and the formalization of employment pathways, reducing reliance on informal labour. By ensuring that beneficiaries are registered in İŞKUR’s Job Seekers Database, the project helps connect them to structured employment services within Türkiye’s national workforce system. The project also aligns with key international and regional frameworks, including the 2030 Agenda for Sustainable Development, by contributing to SDG 4 (Quality Education), SDG 5 (Gender Equality), and SDG 8 (Decent Work and Economic Growth). Additionally, the project’s focus on enhancing employability for refugees and Turkish Citizens supports the objectives of the Global Compact on Refugees, particularly in reducing pressures on Turkish Citizens and promoting refugee self-reliance.

Briefly describe in the space below how the project is likely to improve gender equality and women’s empowerment

The project aims to enhance women’s participation in the workforce, particularly by improving their access to vocational training and on-the-job training, with a specific focus on NEET (Not in Education, Employment, or Training) young women. The Women’s Empowerment Strategy Document (2024-2028) prioritizes vocational training and skill-building as key pathways to dignified employment opportunities for women, aligning directly with the project’s objectives. Recognizing the existing inequalities that limit women’s participation in the labour market, the project integrates women-sensitive strategies throughout its design and implementation. This includes ensuring equal access to training and employment facilitation services, addressing structural barriers that disproportionately affect women, and promoting inclusive learning environments. The curriculum design and training delivery methods will incorporate responsive approaches, ensuring that women are equipped with the necessary skills to enter and succeed in the renewable energy workforce. By registering female beneficiaries in the Job Seekers Database, the project enhances their visibility to potential employers and supports their long-term employability. Furthermore, the project aligns with key policy frameworks, including Türkiye’s 12th National Development Plan, the EU Gender Equality Strategy (2020-2025), and UNDP’s Gender Equality Strategy (2022-2025), reinforcing its commitment to closing women and men gaps in vocational training and employment.

Briefly describe in the space below how the project mainstreams sustainability and resilience

The project is designed to ensure the long-term sustainability of its impact by embedding its outputs within existing national education and employment systems. A major sustainability factor is the integration of two new training modules into MoNE’s renewable energy curriculum, ensuring that the content remains available and relevant beyond the project’s duration. By aligning these modules with sector-specific needs identified through the project’s Needs and Gaps Assessment, the training remains directly responsive to market demands, increasing the employability of future trainees. Beyond training, sustainability is reinforced through institutional collaboration with İŞKUR, ensuring that beneficiaries are registered in the Job Seekers Database and connected to structured employment support mechanisms. By strengthening formal employment pathways, the project reduces reliance on informal labour markets and enhances economic resilience for both refugees and host community members. The project also contributes to labour market resilience by equipping individuals with future-proof skills in the growing renewable energy sector, an industry expected to expand significantly in Türkiye. This ensures that both SuTP and host community members benefit from sustainable employment opportunities that align with Türkiye’s green transition goals.

Briefly describe in the space below how the project strengthens accountability to stakeholders

The project strengthens accountability to stakeholders through inclusive and transparent implementation, engaging key national institutions, private sector actors, and beneficiaries throughout the process. The Needs and Gaps Assessment ensures that training content remains aligned with employer expectations, making the project responsive to real labour market demands. By working closely with MoNE and İŞKUR, the project integrates into existing national systems, ensuring that its outputs—particularly training curricula and employment facilitation mechanisms—remain accessible and sustainable after the project’s completion. Monitoring and evaluation mechanisms will be applied to track beneficiary registration in the Job Seekers Database, completion of training programs, and employment outcomes. Regular reporting to stakeholders, including relevant government bodies and international partners, will ensure transparency and accountability in project implementation. Additionally, the project will maintain direct engagement with beneficiaries, ensuring that they have access to information, guidance, and support throughout their participation. This approach fosters trust, ownership, and stakeholder alignment, reinforcing the project’s credibility and effectiveness.

Part B. Identifying and Managing Social and Environmental Risks

| QUESTION 2: What are the Potential Social and Environmental Risks? Note: Complete SESP Attachment 1 before responding to Question 2. | QUESTION 3: What is the level of significance of the potential social and environmental risks? Note: Respond to Questions 4 and 5below before proceeding to Question 5 |  |  |  | QUESTION 6: Describe the assessment and management measures for each risk rated Moderate, Substantial or High |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Description (broken down by event, cause, impact) | Impact and Likelihood (1-5) | Significance (Low, Moderate Substantial, High) | Comments (optional) |  | Description of assessment and management measures for risks rated as Moderate, Substantial or High |  |  |
| There is a risk that graduates of the project's training programs may remain unemployed due to a misalignment between the skills taught and the actual demands of the local labor market ; insufficient engagement with employers which may result in reduced effectiveness of the project in improving livelihoods and potential disillusionment among participants | I= 3 P= 1 | Low |  |  | UNDP will conduct a labor market needs assessment before finalizing training curricula. Partnership with local employers and industry groups will be established. Entrepreneurship and job placement support services will be integrated. |  |  |
| There is a risk that lack of an effective or accessible grievance mechanism for potential beneficiaries may occur due to inadequate resource allocation or unclear communication channels, which may result in grievances going unreported or unresolved, leading to decreased beneficiary trust, reputational damage, and reduced project credibility. | I= 3 P= 1 | Low |  |  | UNDP will conduct a clear grievance mechanism. Contact information of the project official/focal will be announced on the UNDP Türkiye project page. UNDP will conduct a clear grievance mechanism. Contact information of the project official/focal will be announced on the UNDP Türkiye project page. Received grievances will be monitored and responded in a timely manner. |  |  |
| There is risk that participation and success rates among women can remain low, which may occur according to the societal norms, caregiving responsibilities and lack of targeted support which may result in women empowerment objectives undermined and existing disparities perpetuated. | I=3 P=2 | Low |  |  | UNDP will implement targeted outreach and support programs for women. Flexible training schedules and tailored support will be provided. Women sensitive content and mentorship opportunities will be incorporated. |  |  |
| There is a risk that the Ministry of National Education (MoNE) may face challenges in effectively implementing and sustaining the new training modules introduced, which may occur due to limited resources, technical expertise, and infrastructure, resulting in compromised quality and longevity of the training programs, affecting the scalability and sustainability of project outcomes. | I=4 P=1 | Low |  |  | UNDP will provide capacity-building and technical assistance to MoNE staff. UNDP will support MoNE with resources for infrastructure and technological upgrades. Monitoring systems will be established to ensure equality and sustainability. |  |  |
|  | QUESTION 4: What is the overall project risk categorization? |  |  |  |  |  |  |
|  | Low Risk |  |  | X |  |  |  |
|  | Moderate Risk |  |  | ☐ |  |  |  |
|  | Substantial Risk |  |  | ☐ |  |  |  |
|  | High Risk |  |  | ☐ |  |  |  |
|  | QUESTION 5: Based on the identified risks and risk categorization, what requirements of the SES are triggered? (check all that apply) |  |  |  |  |  |  |
|  | Question only required for Moderate, Substantial and High Risk projects |  |  |  |  |  |  |
|  | Is assessment required? (check if “yes”) |  |  | ☐ |  |  | Status? (completed, planned) |
|  | if yes, indicate overall type and status |  |  |  | ☐ | Targeted assessment(s) |  |
|  |  |  |  |  | ☐ | ESIA (Environmental and Social Impact Assessment) |  |
|  |  |  |  |  | ☐ | SESA (Strategic Environmental and Social Assessment) |  |
|  | Are management plans required? (check if “yes) |  |  | ☐ |  |  |  |
|  | If yes, indicate overall type |  |  |  | ☐ | Targeted management plans (e.g. women empowerment Action Plan, Emergency Response Plan, Waste Management Plan, others) |  |

|  |  |  | ☐ | ESMP (Environmental and Social Management Plan which may include range of targeted plans) |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | ☐ | ESMF (Environmental and Social Management Framework) |  |
|  | Based on identified risks, which Principles/Project- level Standards triggered? |  | Comments (not required) |  |  |
|  | Overarching Principle: Leave No One Behind |  |  |  |  |
|  | Human Rights | X |  |  |  |
|  | Gender Equality and Women’s Empowerment | ☐ |  |  |  |
|  | Accountability | X |  |  |  |
|  | 1. Biodiversity Conservation and Sustainable Natural Resource Management | ☐ |  |  |  |
|  | 2. Climate Change and Disaster Risks | ☐ |  |  |  |
|  | 3. Community Health, Safety and Security | ☐ |  |  |  |
|  | 4. Cultural Heritage | ☐ |  |  |  |
|  | 5. Displacement and Resettlement | ☐ |  |  |  |
|  | 6. Indigenous Peoples | ☐ |  |  |  |
|  | 7. Labour and Working Conditions | ☐ |  |  |  |
|  | 8. Pollution Prevention and Resource Efficiency | ☐ |  |  |  |

#### SESP Attachment 1. Social and Environmental Risk Screening Checklist

| Checklist Potential Social and Environmental Risks |  |  |
| --- | --- | --- |
| INSTRUCTIONS: The risk screening checklist will assist in answering Questions 2-6 of the Screening Template. Answers to the checklist questions help to (1) identify potential risks, (2) determine the overall risk categorization of the project, and (3) determine required level of assessment and management measures. Refer to the SES toolkit for further guidance on addressing screening questions. |  |  |
| Overarching Principle: Leave No One Behind Human Rights |  | Answer (Yes/No) |
| P.1 | Have local communities or individuals raised human rights concerns regarding the project (e.g. during the stakeholder engagement process, grievance processes, public statements)? | No |
| P.2 | Is there a risk that duty-bearers (e.g. government agencies) do not have the capacity to meet their obligations in the project? | Yes |
| P.3 | Is there a risk that rights-holders (e.g. project-affected persons) do not have the capacity to claim their rights? | No |
| Would the project potentially involve or lead to: |  |  |
| P.4 | adverse impacts on enjoyment of the human rights (civil, political, economic, social or cultural) of the affected population and particularly of marginalized groups? | No |
| P.5 | inequitable or discriminatory impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups, including persons with disabilities? | No |
| P.6 | restrictions in availability, quality of and/or access to resources or basic services, in particular to marginalized individuals or groups, including persons with disabilities? | No |
| P.7 | exacerbation of conflicts among and/or the risk of violence to project-affected communities and individuals? | No |
| Gender Equality and Women’s Empowerment |  |  |
| P.8 | Have women’s groups/leaders raised gender equality concerns regarding the project, (e.g. during the stakeholder engagement process, grievance processes, public statements)? | No |
| Would the project potentially involve or lead to: |  |  |
| P.9 | adverse impacts on gender equality and/or the situation of women and girls? | No |
| P.10 reproducing discriminations against women based on gender, especially regarding participation in design and implementation or access to opportunities and benefits? |  | No |
| P.11 limitations on women’s ability to use, develop and protect natural resources, taking into account different roles and positions of women and men in accessing environmental goods and services? For example, activities that could lead to natural resources degradation or depletion in communities who depend on these resources for their livelihoods and well being |  | No |
| P.12 exacerbation of risks of gender-based violence? For example, through the influx of workers to a community, changes in community and household power dynamics, increased exposure to unsafe public places and/or transport, etc. |  | No |

16 Prohibited grounds of discrimination include race, ethnicity, sex, age, language, disability, sexual orientation, gender identity, religion, political or other opinion, national or social or geographical origin, property, birth or other status including as an indigenous person or as a member of a minority. References to “women and men” or similar is understood to include women and men, boys and girls, and other groups discriminated against based on their gender identities, such as transgender and transsexual people.

| Sustainability and Resilience: Screening questions regarding risks associated with sustainability and resilience are encompassed by the Standard-specific questions below |  |
| --- | --- |
| Accountability |  |
| Would the project potentially involve or lead to: |  |
| P.13 exclusion of any potentially affected stakeholders, in particular marginalized groups and excluded individuals (including persons with disabilities), from fully participating in decisions that may affect them? | Yes |
| P.14 grievances or objections from potentially affected stakeholders? | No |
| P.15 risks of retaliation or reprisals against stakeholders who express concerns or grievances, or who seek to participate in or to obtain information on the project? | No |
| Project-Level Standards |  |
| Standard 1: Biodiversity Conservation and Sustainable Natural Resource Management |  |
| Would the project potentially involve or lead to: |  |
| 1.1 adverse impacts to habitats (e.g. modified, natural, and critical habitats) and/or ecosystems and ecosystem services? For example, through habitat loss, conversion or degradation, fragmentation, hydrological changes | No |
| 1.2 activities within or adjacent to critical habitats and/or environmentally sensitive areas, including (but not limited to) legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities? | No |
| 1.3 changes to the use of lands and resources that may have adverse impacts on habitats, ecosystems, and/or livelihoods? (Note: if restrictions and/or limitations of access to lands would apply, refer to Standard 5) | No |
| 1.4 risks to endangered species (e.g. reduction, encroachment on habitat)? | No |
| 1.5 exacerbation of illegal wildlife trade? | No |
| 1.6 introduction of invasive alien species? | No |
| 1.7 adverse impacts on soils? | No |
| 1.8 harvesting of natural forests, plantation development, or reforestation? | No |
| 1.9 significant agricultural production? | No |
| 1.10 animal husbandry or harvesting of fish populations or other aquatic species? | No |
| 1.11 significant extraction, diversion or containment of surface or ground water? For example, construction of dams, reservoirs, river basin developments, groundwater extraction | No |
| 1.12 handling or utilization of genetically modified organisms/living modified organisms?17 | No |
| 1.13 utilization of genetic resources? (e.g. collection and/or harvesting, commercial development)18 | No |
| 1.14 adverse transboundary or global environmental concerns? | No |
| Standard 2: Climate Change and Disaster Risks |  |
| Would the project potentially involve or lead to: |  |

17 See the Convention on Biological Diversityhttps://www.cbd.int/and its Cartagena Protocol on Biosafety.

18 See the Convention on Biological Diversityhttps://www.cbd.int/and its Nagoya Protocolhttps://www.cbd.int/abs/on access and benefit sharing from use of genetic resources.

| 2.1 areas subject to hazards such as earthquakes, floods, landslides, severe winds, storm surges, tsunami or volcanic eruptions? | No |
| --- | --- |
| 2.2 outputs and outcomes sensitive or vulnerable to potential impacts of climate change or disasters? For example, through increased precipitation, drought, temperature, salinity, extreme events, earthquakes | No |
| 2.3 increases in vulnerability to climate change impacts or disaster risks now or in the future (also known as maladaptive or negative coping practices)? For example, changes to land use planning may encourage further development of floodplains, potentially increasing the population’s vulnerability to climate change, specifically flooding | No |
| 2.4 increases of greenhouse gas emissions, black carbon emissions or other drivers of climate change? | No |
| Standard 3: Community Health, Safety and Security |  |
| Would the project potentially involve or lead to: |  |
| 3.1 construction and/or infrastructure development (e.g. roads, buildings, dams)? (Note: the GEF does not finance projects that would involve the construction or rehabilitation of large or complex dams) | No |
| 3.2 air pollution, noise, vibration, traffic, injuries, physical hazards, poor surface water quality due to runoff, erosion, sanitation? | No |
| 3.3 harm or losses due to failure of structural elements of the project (e.g. collapse of buildings or infrastructure)? | No |
| 3.4 risks of water-borne or other vector-borne diseases (e.g. temporary breeding habitats), communicable and noncommunicable diseases, nutritional disorders, mental health? | No |
| 3.5 transport, storage, and use and/or disposal of hazardous or dangerous materials (e.g. explosives, fuel and other chemicals during construction and operation)? | No |
| 3.6 adverse impacts on ecosystems and ecosystem services relevant to communities’ health (e.g. food, surface water purification, natural buffers from flooding)? | No |
| 3.7 influx of project workers to project areas? | No |
| 3.8 engagement of security personnel to protect facilities and property or to support project activities? | No |
| Standard 4: Cultural Heritage |  |
| Would the project potentially involve or lead to: | No |
| 4.1 activities adjacent to or within a Cultural Heritage site? | No |
| 4.2 significant excavations, demolitions, movement of earth, flooding or other environmental changes? | No |
| 4.3 adverse impacts to sites, structures, or objects with historical, cultural, artistic, traditional or religious values or intangible forms of culture (e.g. knowledge, innovations, practices)? (Note: projects intended to protect and conserve Cultural Heritage may also have inadvertent adverse impacts) | No |
| 4.4 alterations to landscapes and natural features with cultural significance? | No |
| 4.5 utilization of tangible and/or intangible forms (e.g. practices, traditional knowledge) of Cultural Heritage for commercial or other purposes? | No |
| Standard 5: Displacement and Resettlement |  |
| Would the project potentially involve or lead to: |  |
| 5.1 temporary or permanent and full or partial physical displacement (including people without legally recognizable claims to land)? | No |
| 5.2 economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation)? | No |
| 5.3 risk of forced evictions?19 | No |
| 5.4 impacts on or changes to land tenure arrangements and/or community based property rights/customary rights to land, territories and/or resources? | No |
| Standard 6: Indigenous Peoples |  |
| Would the project potentially involve or lead to: |  |
| 6.1 areas where indigenous peoples are present (including project area of influence)? | No |
| 6.2 activities located on lands and territories claimed by indigenous peoples? | No |
| 6.3 impacts (positive or negative) to the human rights, lands, natural resources, territories, and traditional livelihoods of indigenous peoples (regardless of whether indigenous peoples possess the legal titles to such areas, whether the project is located within or outside of the lands and territories inhabited by the affected peoples, or whether the indigenous peoples are recognized as indigenous peoples by the country in question)? If the answer to screening question 6.3 is “yes”, then Standard 6 requirements apply, and the potential significance of risks related to impacts on indigenous peoples must be Moderate or above.* | No |
| 6.4 the absence of culturally appropriate consultations carried out with the objective of achieving FPIC on matters that may affect the rights and interests, lands, resources, territories and traditional livelihoods of the indigenous peoples concerned? | No |
| 6.5 the utilization and/or commercial development of natural resources on lands and territories claimed by indigenous peoples? | No |
| 6.6 forced eviction or the whole or partial physical or economic displacement of indigenous peoples, including through access restrictions to lands, territories, and resources? Consider, and where appropriate ensure, consistency with the answers under Standard 5 above | No |
| 6.7 adverse impacts on the development priorities of indigenous peoples as defined by them? |  |
| 6.8 risks to the physical and cultural survival of indigenous peoples? | No |
| 6.9 impacts on the Cultural Heritage of indigenous peoples, including through the commercialization or use of their traditional knowledge and practices? Consider, and where appropriate ensure, consistency with the answers under Standard 4 above. | No |
| Standard 7: Labour and Working Conditions |  |
| Would the project potentially involve or lead to: (note: applies to project and contractor workers) |  |
| 7.1 working conditions that do not meet national labour laws and international commitments? | No |
| 7.2 working conditions that may deny freedom of association and collective bargaining? | No |

| 7.3 use of child labour? | No |
| --- | --- |
| 7.4 use of forced labour? | No |
| 7.5 discriminatory working conditions and/or lack of equal opportunity? | No |
| 7.6 occupational health and safety risks due to physical, chemical, biological and psychosocial hazards (including violence and harassment) throughout the project life-cycle? | No |

| Standard 8: Pollution Prevention and Resource Efficiency |  |
| --- | --- |
| Would the project potentially involve or lead to: |  |
| 8.1 the release of pollutants to the environment due to routine or non-routine circumstances with the potential for adverse local, regional, and/or transboundary impacts? | No |
| 8.2 the generation of waste (both hazardous and non-hazardous)? | No |
| 8.3 the manufacture, trade, release, and/or use of hazardous materials and/or chemicals? | No |
| 8.4 the use of chemicals or materials subject to international bans or phase-outs? For example, DDT, PCBs and other chemicals listed in international conventions such as the MontrealProtocol, Minamata Convention, Basel Convention, Rotterdam Convention, Stockholm Convention | No |
| 8.5 the application of pesticides that may have a negative effect on the environment or human health? | No |
| 8.6 significant consumption of raw materials, energy, and/or water? | No |

Risk Analysis

| Project Title: Increasing Employability in the Renewable Energy Sector Project Phase II | Project Number: | Date: 29-Apr-25 |
| --- | --- | --- |

| # | Event | Cause | Impact(s) | Risk Category and Sub-category (including Risk Appetite) | Impact, Likelihood & Risk Level (see Annex 3 Risk Matrix) | Risk Valid From/To | Risk Owner (individual accountable for managing the risk) | Risk Treatment and Treatment Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | There is a risk that, Government of Türkiye may change its policies towards SuTP drastically, following the developments in the political situation in Syria including ending of the temporary protection regime or stricter conditions for entry into formal labour market | Due to normalization of political and social conditions in Syria. | Which will cause reduced number of potential beneficiaries. | 6. REGULATORY (6.1. Changes in the regulatory framework within the country of operation) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 2 - Low likelihood Impact: 4 - Extensive Risk level: MODERATE (equates to a risk appetite of EXPLORATORY) | From: 01-Jun-25 To: 31-Dec-26 | Project Manager | Risk Treatment 1.1: UNDP will ensure regular coordination with MoNE and other stakeholders through establishing a joint coordination group. When such a policy change is identified relevancy of the outputs under the new policies will be reassessed and content and tools will be revised accordingly. Risk Treatment Owner: Project Manager |
| 2 | There is a risk that not being able to reach out to desired number of Phase 1 graduates | Due to potential difficulties in reaching beneficiaries graduated in the early phases of the previous project. | Which will result in reduced participation levels and weaken impact of the overall project outputs. | 4. ORGANIZATIONAL (4.1. Governance) - UNDP Risk Appetite: EXPLORATORY TO OPEN | Likelihood: 2 - Low likelihood Impact: 3 - Intermediate Risk level: MODERATE (equates to a risk appetite of EXPLORATORY) | From: 01-Jun-25 To: 31-Dec-26 | Project Manager | Risk Treatment 2.1: UNDP will conduct robust outreach strategy (multiple channels: phone, SMS, social media, etc.); update contact database; clearly communicate benefits of follow-up Risk Treatment Owner: Project Manager |
| 3 | There is a risk that the Ministry of National Education (MoNE) may face challenges in effectively implementing and sustaining the new training modules introduced | Due to limited resources, technical expertise, and infrastructure | Which may result in reduced usage of the developed modules, and missed opportunities for scaling up and sustaining the project’s impact within the national education system. | 1. SOCIAL AND ENVIRONMENTAL (1.12. Stakeholder engagement) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 1 - Not likely Impact: 4 - Extensive Risk level: LOW (equates to a risk appetite of CAUTIOUS) | From: 01-Jun-25 To: 31-Dec-26 | Project Manager | Risk treatment 3.1 UNDP will promote MoNE officials to review and validate the training modules, ensuring alignment with national curricula, standards, and MoNE's strategic priorities. Risk treatment 3.2 UNDP will facilitate an official validation process with MoNE (e.g., through Memorandums of Understanding, formal approvals, or board meetings). Risk Treatment Owner: Project Manager |
| 4 | There is a risk that lack of an effective or accessible grievance mechanism for potential beneficiaries | Due to inadequate resource allocation or unclear communication channels | Which may result in grievances going unreported or unresolved, leading to decreased beneficiary trust, reputational damage, and reduced project credibility. | 1. SOCIAL AND ENVIRONMENTAL (1.3. Grievances (Accountability to stakeholders)) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 1 - Not likely Impact: 3 - Intermediate Risk level: LOW (equates to a risk appetite of CAUTIOUS) | From: 01-Jun-25 To: 31-Dec-26 | Project Manager | Risk Treatment 4.1: UNDP will conduct a clear grievance mechanism. Contact information of the project official/focal will be announced on the UNDP Türkiye project page. Risk treatment 4.2: Received grievances will be monitored and responded in a timely manner. Risk Treatment Owner: Project Manager |
| 5 | There is a risk that graduates of the project's training programs may remain unemployed | Due to a misalignment between the skills taught and the actual demands of the local labor market ; insufficient engagement with employers | Which may result in reduced effectiveness of the project in improving livelihoods and potential disillusionment among participants | 1. SOCIAL AND ENVIRONMENTAL (1.1. Human rights) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 1 - Not likely Impact: 3 - Intermediate Risk level: LOW (equates to a risk appetite of CAUTIOUS) | From: 01-Jun-25 To: 31-Dec-26 | Project Manager | Risk Treatment 5.1: UNDP will conduct a labor market needs assessment before finalizing training curricula. Risk Treatment 5.2: Partnership with local employers and industry groups will be established. Risk Treatment 5.3: Entrepreneurship and job placement support services will be integrated. Risk Treatment Owner: Project Manager |
| 6 | There is risk that participation and success rates among women can remain low | Which may occur according to the societal norms, caregiving responsibilities and lack of targeted support | Which may result in gender equality objectives undermined and existing disparities perpetuated. | 1. SOCIAL AND ENVIRONMENTAL (1.2. Gender equality and women’s empowerment) - UNDP Risk Appetite: CAUTIOUS | Likelihood: 1 - Not likely Impact: 3 - Intermediate Risk level: LOW (equates to a risk appetite of CAUTIOUS) | From: 01-Jun-25 To: 31-Dec-26 | Project Manager | Risk Treatment 6.1:UNDP will implement targeted outreach and support programs for women. Risk Treatment 6.2:Flexible training schedules and tailored support will be provided. Risk Treatment 6.3: Gender sensitive content and mentorship opportunities will be incorporated. |

Standard Letter of Agreement for Provision of Services Provided by UNDP

This Annex ensures that information provided through the attachments of “Standard Letter of Agreement Between the United Nations Development Programme and Republic of Türkiye Ministry Of Foreign Affairs to carry out activities when UNDP provides support services to the “Skills Development for Improved Employability”are contained in the Project Document.

In view of above and in the context of “Standard Letter of Agreement signed on 22 January 2002 between the Turkish Government and the UNDP is ratified by the decision of Council of Ministries No. 2003/6090 dated 22 August 2003”;

i)   The manner and the method of cost recovery by UNDP Country Office in providing the support services is stated in the project document “Heading VII - Multi-year Workplan” in line with UNDP’s Executive Board approved Cost Recovery Policy.

ii)   The results to be achieved and works to be performed by the Implementing Partner and inputs to be provided in the context of “Description of Activities” are available in the Project Document.

iii)  Information concerning “Outputs, Planned Activities, Timeframe, Planned Budget, Schedule of Payments (to be further agreed in the Project Board)” is provided in the Project Document.

iv)  Model UNDP Expenditure Report is presented as below:

Period _______

| EXPECTED CP OUTPUTS ### and indicators including annual targets | PLANNED ACTIVITIES List all activities to be undertaken during the year towards stated outputs | Planned Budget |  | Payments and Expenditures |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Budget Description | Amount | Payments received | Expenditures | Balance |
|  |  | ### Total |  |  |  |  |

UNDP TURKIYE CO

TERMS OF REFERENCE FOR PROJECT BOARD

The Project Board is the group responsible for making, by consensus, management decisions for a development project when guidance is required by the Project Manager (PM), including recommendation for UNDP/Implementing Partner approval of plans and revisions.  The Project Board is chaired by the Senior Executive (Implementing Partners) or co-chaired by UNDP.  It depends on the arrangements agreed with all parties and the Donor in design stage of the Project.  From UNDP side, the Deputy Resident Representative DRR chairs the PB meetings.  Presidency of Republic of Türkiye Strategy and Budget Office (PSB) & Ministry of Foreign Affairs (MFA) are natural members of each Project Board.

In order to ensure UNDP’s ultimate accountability, Project Board decisions should be made in accordance to standards that shall ensure best value for money, fairness, integrity transparency and effective international competition. Reviews by this group are made at designated decision points during the running of the development project, or as necessary when raised by the PM.

Based on the approved annual work plan (AWP), the Project Board may review and approve the annual plans when required and authorizes any major deviation from these agreed quarterly plans. It is the authority that signs off the completion of each annual plan as well as authorizes the start of the next annual plan. It ensures that required resources are committed and arbitrates on any conflicts within the development project or negotiates a solution to any problems between the PM and external bodies. In addition, it approves the appointment and responsibilities of the PM and any delegation of its Project Assurance responsibilities.

The Project Board must meet one time annually at a minimum. It is recommended that the timing of board meetings be agreed upon in advance and corresponds to key project reporting or work planning milestones. This Project Board will meet 6 times annually according to this provisional schedule.

Specific responsibilities of the Project Board:

- Provide overall guidance and direction to the project, ensuring it remains within any specified constraints, and promote gender equality and social inclusion (LNOB) in the project implementation;

- Review project performance based on monitoring, evaluation and reporting, including standard quality assurance checks, progress reports, risk logs, spot checks/audit reports and the combined delivery report;

- Address any high-level project issues as raised by the project manager and project assurance;

- Provide guidance on emerging and/or pressing project risks and agree on possible mitigation and management actions to address specific risks (including ensuring compliance with UNDP’s Social and Environmental Standards, Fraud/corruption, Sexual Exploitation and Abuse and Sexual Harassment);

- Agree or decide on project manager’s tolerances as required, within the parameters set by UNDP (Manage Change in the PPM) and the donor, and provide direction and decisions for exceptional situations when the project manager’s tolerances are exceeded;

- Advise on major and minor amendments to the project within the parameters set by UNDP and the donor;

- Agree or decide on a project suspension or cancellation, if required; (note that for GEF and GCF projects it is UNDP that decides to suspend or cancel and project and the [Project Board or Project Steering Committee] is informed/consulted only).

- Provide high-level direction and recommendations to the project management unit to ensure that the agreed deliverables are produced satisfactorily according to plans.

- Receive and address project level grievance, including overseeing whatever specific compliance and stakeholder response (or grievance) mechanisms have been put in place so that individuals and communities potentially affected by the project have access to effective mechanisms and procedures for raising concerns about the social and environmental performance of the project.

- Engage in the low value grant selection process where there is no Grant Selection Committee, as guided by the Low Value Grants – UNDP Operational Guide.

Additional responsibilities of the Project Board can include, but are not limited to, the following:

- Ensure coordination between the various donors and government-funded projects and programmes;

- Report to relevant inter-ministerial bodies or higher-level oversight bodies;

- Ensure coordination with multiple government agencies and their participation in project activities;

- Track and monitor co-financing for this project;

- Appraise the annual project implementation report, including the quality assessment rating report;

- Ensure commitment of human resources to support project implementation, arbitrating any issues within the project;

- Act as an informal consultation mechanism for stakeholders;

- Approve the Project Inception Report, Mid-term Review and Terminal Evaluation reports and corresponding management responses;

- Review the final project report package during an end-of-project review meeting to discuss lessons learned and opportunities for scaling up;

- Providing guidance or reporting protocols to technical committees or sub-bodies reporting to the Board (if applicable);

Senior Executive (Executing/Implementing Partner)

The Executive is ultimately responsible for the project implementation, supported by the Senior Supplier. The Executive’s role is to ensure that the development project is focused throughout its life cycle on achieving its objectives and delivering outputs that will contribute to higher level outcomes. The Executive must ensure that the project gives value for money, ensuring a cost-conscious approach to the project, balancing the demands of supplier.

Specific Responsibilities (as part of the above responsibilities for the Project Board)

- Ensure that there is a coherent management organisation structure and logical set of plans

- Set tolerances in the AWP and other plans as required for the Project Manager

- Monitor and control the progress of the development project at a strategic level

- Ensure that risks are being tracked and mitigated as effectively as possible

- Brief relevant stakeholders about development project’s progress

- Organise and chair Project Board meetings

The Executive is responsible for overall assurance of the development project as described below.  If the project document warrants it, the Executive may delegate some responsibility for the project assurance functions.

Senior Beneficiary

This role requires representing the interests of the institution who will ultimately benefit from the project. The Senior Beneficiary’s primary function within the Board will be to ensure the realization of project results from the perspective of project beneficiaries. This role will rest with the other institutions (key national governmental and non-governmental agencies, and appropriate local level representatives) represented on the Project Board, who are stakeholders in the project.

Senior Supplier (UNDP)

The Senior Supplier represents the interests of the parties which provide funding and/or technical expertise to the development project. The Senior Supplier’s primary function within the Project Board is to provide guidance regarding the technical feasibility of the development project.  The Senior Supplier role must have the authority to commit or acquire supplier resources required. If necessary, more than one person may be required for this role.

Specific Responsibilities (as part of the above responsibilities for the Project Board)

- Make sure that progress towards the outputs remains consistent from the supplier perspective

- Promote and maintain focus on the expected output(s) from the point of view of supplier management

- Ensure that the supplier resources required for the project are made available

- Contribute supplier opinions on Project Board decisions on whether to implement recommendations on proposed changes

- Arbitrate on, and ensure resolution of, any supplier priority or resource conflicts

Donor

The Donor which is funding the project becomes a natural member of the Project Board.

Presidency of Republic of Türkiye Strategy and Budget Office (SBO) & Ministry of Foreign Affairs

These two offices are natural members of each Project Board.

SBO is the Government coordinating agency of the UNDP in Türkiye and ensures that all UNDP programmes are designed/implemented in line with National priorities.

Ministry of Foreign Affairs gives final approval to all UNDP implemented projects, hence has an overall oversight function under each project.

Project Assurance

The Project Assurance role supports the Project Board by carrying out objective and independent project oversight and monitoring functions. This role ensures appropriate project management milestones are managed and completed.

Project Assurance has to be independent of the Project Manager; therefore, the Project Board cannot delegate any of its assurance responsibilities to the Project Manager. At UNDP Project Assurance function belongs to DRR, Portfolio Manager and M&E and KM Analyst with a clear mandate for oversight and monitoring functions.

Project assurance can also include key staff in Beneficiary institutions that have a stake in the quality execution of the project. However, project assurance function cannot be assumed by Senior Executive since assurance function is to be carried out by an impartial party.

Project Management Unit

A Project Management Unit (PMU) will be established comprising permanent staff including:  Project Manager (PM) and any other support staff appointed for successful completion of this project i.e. Project Associate, Project Finance and Procurement Officer, Portfolio Administrator as well as Project Support Unit. The PMU will assist Senior Executive in performing its role as implementing partner. PMI also includes any technical expert/consultant hired for the successful implementation of the project. PM will be responsible from close surveillance of performance of technical experts if any. The PMU also includes any technical teams in pilot provinces which report directly to PM.

i.Project Manager

The Project Manager has the authority to run the project on a day-to-day basis on behalf of the Implementing Partner within the constraints laid down by the Board. The Project Manager’s prime responsibility is to ensure that the project produces the results specified in the project document, to the required standard of quality and within the specified constraints of time and cost. The PM will be recruited in accordance with UNDP regulations and will be based in Ankara. S/he will report to the relevant UNDP Portfolio Manager. The PM will be responsible for overall project coordination and implementation, consolidation of work plans and project papers, preparation of quarterly progress reports, reporting to the project supervisory bodies, and supervising the work of the project experts and other project staff. The PM will also closely coordinate project activities with relevant Government institutions (if applicable) and hold regular consultations with other project stakeholders and partners. Under the direct supervision of the PM, the Project Associate will be responsible for administrative issues while Project Finance and Procurement Officer will be responsible for financial issues and will get support from UNDPCO administration.

ii. Project Support

Overall responsibilities:  The Project Support role provides administration, management and technical support to the Project Manager as required by the needs of the Project Manager. The provision of any Project Support on a formal basis is optional.  In most projects, project support includes HR, procurement and PSC (Program Service Center) services

Capacity Assessment: Results of capacity assessments of Implementing Partner (including Partner Capacity Assessment Tool (PCAT) and HACT Micro Assessment)

The word Gender in this document refers to men and women only.

UNHCR, Inter-Agency Protection Needs Assessment Round 7, p. 20: https://reliefweb.int/attachments/d66fd570-4d41-4af0-9fb8-ba75de2503d8/Inter-Agency%20Protection%20Needs%20Assessment%20Round%207%20Report%20%28August%202023%29.pdf.

Tracking SDG7 Energy Progress Report 2024 - https://www.irena.org/-/media/Files/IRENA/Agency/Publication/2024/Jun/IRENA_Tracking_SDG7_energy_progress_2024.pdf

World Energy Outlook 2024 - https://www.iea.org/reports/world-energy-outlook-2024

Net Zero 2053: A Roadmap for the Turkish Electricity Sector - https://shura.org.tr/wp-content/uploads/2024/12/SHURA-2023-02-Net-Zero-2053-EN-1.pdf Net Zero 2053: A Roadmap for the Turkish Electricity Sector - https://shura.org.tr/wp-content/uploads/2024/12/SHURA-2023-02-Net-Zero-2053-EN-1.pdf

https://www.globalwomennet.org/wp-content/uploads/2023/02/TWRE_REMI_Gender-Equality-in-Energy-Industry-Report_2022.pdf

https://iicec.sabanciuniv.edu/event/women-leaders-clean-energy-science-and-technology-conference

https://enlargement.ec.europa.eu/document/download/99c1bfa3-1853-42ff-ae3b-59622f7bdab1_en?filename=EU%20support%20to%20refugees%20in%20TR_Theory%20of%20Change%202024.pdf

Twelfth Development Plan 2024-2028 https://www.sbb.gov.tr/wp-content/uploads/2024/06/Twelfth-Development-Plan_2024-2028.pdf

Please see the Guideline “Embedding Digital in Project Design”.

https://iklim.gov.tr/db/turkce/icerikler/files/İklim%20Değişikliği%20Azaltım%20Stratejisi%20ve%20Eylem%20Planı%20(2024-2030).pdf

UNDP publishes its project information (indicators, baselines, targets and results) to meet the International Aid Transparency Initiative (IATI) standards.  Make sure that indicators are S.M.A.R.T. (Specific, Measurable, Attainable, Relevant and Time-bound), provide accurate baselines and targets underpinned by reliable evidence and data, and avoid acronyms so that external audience clearly understand the results of the project.

It is recommended that projects use output indicators from the Strategic Plan IRRF, as relevant, in addition to project-specific results indicators. Indicators should be disaggregated by sex or for other targeted groups where relevant.

19 Forced eviction is defined here as the permanent or temporary removal against their will of individuals, families or communities from the homes and/or land which they occupy, without the provision of, and access to, appropriate forms of legal or other protection. Forced evictions constitute gross violations of a range of internationally recognized human rights.

Note: revised July 2022 modifying presumption of risk significance from Substantial or higher to Moderate or higher.

The responsibilities of the board in this regard should follow UNDP’s Social and Environmental Standards (SES) as codified in the PPM. It should be noted that while a project board can play a role in addressing or assisting with the compliance and stakeholder response (or grievance) mechanisms put in in place for a given project (as part of their quality assurance and oversight function), this will be in addition to and does not substitute for UNDP’s core responsibility to ensure compliance with the SES throughout the project management cycle as part of UNDP’s Programming Quality Assurance system.