Project Document

Ending the Denial of Legal Capacity of Persons with Disabilities

in Montenegro

UNDP and OHCHR

May 2025

# Cover page

| Basic information about the intervention. |  |
| --- | --- |
| Name of the intervention | Ending the Denial of Legal Capacity of Persons with Disabilities in Montenegro |
| Relevant Cooperation Framework 2023-2027 Outcome | Outcome 4 - By 2027, all people, especially the vulnerable, benefit from improved social cohesion, increased realization of human rights and rule of law and accountable, gender-responsive institutions |
| Participating UN Organisations (highlighting the lead organisation) | UNDP, OHCHR |
| Contact details | ekaterina.paniklova@undp.org |
| Duration of the intervention | 24 months |
| Anticipated start and end dates | 1 September 2025 - 31 August 2027 |

| Basic budget information |  |
| --- | --- |
| Total estimated budget | 400.000 USD |
| Funded | 0 |
| Unfunded | 400.000 USD |
| Source of funds | MAF only |
| Government | none |
| PUNO * | none |
| Donor * | Montenegro SDG Acceleration Fund |

# Declaration of commitment

By signing this Joint Programme document, all signatories commit to work together in a spirit of partnership to achieve the results identified in the results framework, work plan and budget.

| Co-chairs of the Steering Committee |  |
| --- | --- |
| Government | United Nations |
| Jelena Grdinić Signature: Ministry of Justice, Directorate for Criminal and Civil Legislation Date: | Ekaterina Paniklova Signature UNDP Resident Representative in Montenegro Date: |
| Participating UN Organisations |  |
| Ekaterina Paniklova Signature UNDP Resident Representative in Montenegro Date: | Kim L. Taylor Signature Chief, Human Resources, Office of the High Commissioner for Human Rights Date: |

# Introduction

Information about the context and the background of the project:

Legal capacity is a key element of the inherent right of every individual to be recognized before the law, make decisions, and act on one’s own behalf. Without legal capacity, an individual cannot make legally binding decisions, such as entering into marriage, signing contracts, freely consent to medical treatment and care, and faces significant obstacles to access justice. Legal capacity is key for full participation in all aspects of life.

For centuries, authorities denied legal capacity to certain groups, particularly women, ethnic minorities and persons with disabilities. This resulted, for instance, in women not being allowed to vote. These practices have largely been abolished today, though in many countries, persist for persons with disabilities. Restricting or denying legal capacity based on personal characteristics — such as gender in the past or disability today — is discrimination. The person is treated as "non-existent" before the law and third parties make decisions on their behalf. In legal terms, this is often described as ‘civil death’.

While all persons with disabilities can be subject to denial of legal capacity, in practice the most affected are persons with intellectual or psychosocial disabilities, persons with complex support requirements, women and older persons with disabilities. This is also the case in Montenegro. Just in 2022-2023, courts have removed the legal capacity of almost 1,000 individuals, most of whom with psychosocial or intellectual disabilities. Article 235 of the Family Law provides the basis for this measure, as it stipulates that “an adult who, due to mental illness, intellectual disability, or any other cause, is deemed incapable of managing their own rights and interests, may be fully deprived of legal capacity.” The current practice is discriminatory, perpetuates exclusion, contributes to human rights violations and reinforces societal attitudes that persons with disabilities are incapable.

Article 12 of the UN Convention on the Rights of Persons with Disabilities (CRPD) reaffirms that “persons with disabilities have the right to recognition everywhere as persons before the law” without discrimination and “enjoy legal capacity on an equal basis with others in all aspects of life”. The right to equality before the law is also guaranteed by the Universal Declaration of Human Rights (UDHR), the International Covenant on Civil and Political Rights (ICCPR), the UN Convention on the Elimination of All Forms of Discrimination Against Women (CEDAW) and the Convention on the Rights of the Child (CRC). The UN Committee on the Rights of Persons With Disabilities (CRPD Committee) has found that persons denied of legal capacity are deprived of many fundamental rights – including the right to vote, to marry and found a family, reproductive rights, parental rights, the right to give consent for intimate relationships and medical treatment, and even the right to liberty, as many persons deprived of legal capacity are placed in institutions.  Instead of denying legal  capacity, States need to establish a system of supported decision-making for persons with disabilities who may face challenges in making decisions independently. Supported decision-making must consistently reflect and respond to the will and preferences of the person utilising support.

Denial of legal capacity affects women with disabilities even more severely than men, as they cannot make autonomous decisions about – and thus have no control over – their reproductive and sexual health and rights. This results in highly discriminatory and harmful practices, that include forced sterilization. The CRPD Committee expressed serious concern about the use of forced institutionalization, medical treatment, and physical restraints, considering these practices to amount to torture or cruel treatment. It recommended the urgent prohibition of all forms of involuntary detention or hospitalization based on disability, forced sterilization and other non-consensual measures (such as restraints). This recommendation resulted in legal changes that prohibit forced sterilization. While there are no official records of such cases, OPDs report that there have been instances in earlier years where women with intellectual disabilities were sterilized without their informed consent, often at the request of legal guardian.

Montenegro’s legal framework on deprivation of legal capacity does not align with international standards on human rights, including CRPD. Based on the Family Law and the Law on Non-Contentious Proceedings, courts can fully or partially remove an adult's legal capacity based on disability, with partial removal being rare - only in four percent of the cases. Many actors can initiate this procedure (the guardianship authority, family members such as spouse, partner, parent, child, grandparent, sibling, or grandchild, or even the person concerned if s/hey understands the legal implications). The legal terminology used is discriminatory and stigmatizing (like “mental retardation"), reflecting a negative attitude towards persons with disabilities, especially those with intellectual and psychosocial disabilities, who are most at risk of having their legal capacity removed.

The CRPD Committee notes that “concepts of mental and legal capacity have been conflated [by governments], so that where a person is considered to have impaired decision-making skills, often because of a cognitive or psychosocial disability, his or her legal capacity to make a particular decision is consequently removed”. This constitutes discrimination against persons with disabilities. Any claims of “unsoundness of mind” and other discriminatory labels are not legitimate reasons for the denial of legal capacity.

In its most recent review of Montenegro in 2017, the CRPD Committee expressed concern about the substituted decision-making and guardianship regime that is imposed by law in Montenegro, and that this applies to a high number of persons. It recommended that Montenegro establishes a system of supported decision-making and sets up transparent and effective remedies for persons with disabilities whose legal capacity has been removed. While eight years have passed since the 2017 review by the Committee, the situation persists today. The European Commission in its 2024 progress report on Montenegro highlighted that this CRPD Committee recommendation has yet to be fulfilled.

Assessment of the implementation of the National Strategy for the Protection of Persons with Disabilities from Discrimination and the Promotion of Equality (2022-2027) conducted in 2024, also found that in this area, results were the weakest. This is also recognized in the first National Strategy on Deinstitutionalization (2025-2028), adopted in December 2024. Addressing legal capacity deprivation is crucial for implementing the deinstitutionalization strategy, as most persons with disabilities in institutions have been denied legal capacity. Finally, although deprivation of legal capacity is not explicitly mentioned in the Strategy for Gender Equality (2021–2025) and in the Law on the Prohibition of Discrimination, provisions on gender equality and non-discrimination recognize and protect the intersectionality of rights of women and girls with disabilities, who are disproportionately affected by discriminatory legal and institutional practices.

# Information about the project

## Key expected results

What are the key expected results of the intervention? How will people, and especially vulnerable groups, benefit?

The programme seeks to facilitate system-level change in Montenegro by proposing amendments to a legal framework that violates rights and by establishing a system that supports persons with disabilities to exercise their rights. It seeks to address harmful practices and significantly reduce cases of legal capacity denial for persons with disabilities. Thereby, it will end the discrimination persons with disabilities face and empower them to exercise their human rights. A new service for supported decision-making will be designed and piloted to drive system-level change. The project will establish a scalable model to enable persons with disabilities, particularly those with intellectual and psychosocial disabilities, to access structured, sustainable support mechanisms that enable them to make decisions on an equal basis with others.

More specifically, the intervention seeks to achieve the following:

a) 	Amendments to the legal framework proposed and current practices changed to abolish the institute of deprivation of legal capacity based solely on disability;

b)  System of supported decision-making services for persons with disabilities, including those with psychosocial and intellectual disabilities, designed and one service piloted;

c)	Capacity strengthened and attitudes changed of decision-makers, judiciary, and social protection professionals to replace the current medical approach to disability with the rights-based approach in line with standards and developments in international legislation and human rights practices on legal capacity.

To achieve these results, the intervention foresees the following outputs and will undertake the following

activities:

Output 1: Legislative amendments drafted, and practical gender responsive guidelines developed to eliminate the deprivation of legal capacity based solely on disability, aligned with international human rights standards.

This output will be achieved through a combination of legal expertise, stakeholder engagement, and the development of practical tools. A legal expert will be engaged to draft amendments to national legislation. While legal changes are being pursued, the project will work with judicial and social welfare institutions to curtail ongoing practices of full legal capacity deprivation by developing interim protocols and guidelines that apply supported decision-making principles in individual cases, including the use of partial capacity measures, in line with CRPD Committee’s General Comment No. 1. Inclusive consultations will be held to validate all proposals and tools, ensuring the active and meaningful participation of persons with disabilities, with a strong emphasis on the inclusion of women with disabilities. These combined efforts will demonstrate an immediate shift toward a human rights-based approach and lay the groundwork for broader systemic reform.

Key activities:

- 1.1: Engage a legal expert to draft gender responsive amendments to national legislation concerning legal capacity;

- 1.2: Develop guidelines to improve judicial practice, aligning it with legal reforms and international human rights standards;

- 1.3: Conduct an analysis of the practices of guardianship authorities and develop guidelines to align them with legal reforms and human rights standards;

- 1.4: Organize inclusive consultations with relevant stakeholders on the proposed amendments, procedures, and guidelines;

Output 2: A national model for supported decision-making is co-designed, and a pilot community-based service implemented to enable persons with disabilities, particularly those with intellectual and/or psychosocial disabilities, to exercise their legal capacity on an equal basis with others.

This output will be implemented through participatory model development, knowledge exchange, and piloting of an innovative service. A consultant will be engaged to co-design a supported decision-making model, including service standards, in close consultation with persons with disabilities – particularly women and persons with intellectual and/or psychosocial disabilities - and other relevant stakeholders. A study visit to a country with an established system will be organized for key stakeholders including relevant government institutions and OPDs, to inform the model's design and capacity building. The model will be piloted through a local service provider, offering structured, community-based support tailored to the will and preferences of beneficiaries. An inclusive evaluation process — with data disaggregated by gender, age, and type of disability — will inform the refinement of the model and the development of a strategy for national scale-up. These efforts will demonstrate how supported decision-making can serve as a practical alternative to guardianship and promote autonomy, equality, and dignity for persons with disabilities.

Key activities:

- 2.1: Recruit a consultant to lead the design a comprehensive supported decision-making model, including service standards, in consultation with persons with disabilities and relevant stakeholders;

- 2.2: Facilitate a study visit to a country with an established supported decision-making system to inform model development and capacity building;

- 2.3: Provide a grant to a local service provider to pilot supported decision-making service;

- 2.4: Conduct a participatory evaluation of the pilot service, ensuring data is disaggregated by disability, gender and age;

- 2.5: Refine the supported decision-making model and develop a road map for national scale-up based on evaluation findings.

Output 3: Capacity of judicial, social protection, and policy stakeholders strengthened to apply a human rights-based approach to legal capacity, replacing the medical model with CRPD-aligned practices.

This output will be achieved through targeted capacity-building, institutional engagement, and awareness-raising. A comprehensive training curriculum will be developed and delivered in partnership with national institutions to equip legal, social, and policy actors with the knowledge and tools to apply a human rights-based approach to legal capacity. Special attention will be given to improving the understanding of the specific situation of women with disabilities and the disproportionate negative impact that denial of legal capacity has on their lives, highlighting the importance of eliminating such discriminatory practices. High-level dialogues will foster political will and commitment to reform, while public awareness efforts will promote understanding and reduce stigma, particularly toward persons with intellectual and psychosocial disabilities. The campaign will feature human interest stories to illustrate the impact of supported decision-making on persons with disabilities, including women with disabilities/and highlight the importance of gender inclusion. These efforts will contribute to a more enabling environment for the effective and sustainable implementation of legal capacity reforms.

Key activities:

- 3.1: Develop a comprehensive gender sensitive training curriculum on legal capacity and human rights for judges, prosecutors, social protection professionals, and policymakers, with a focus on replacing the medical model of disability with CRPD-aligned, rights-based practices;

- 3.2: Deliver targeted training sessions in collaboration with national institutions to build the capacity of legal and social sector professionals to apply a human rights-based approach to legal capacity, including through using practical tools and case-based learning;

- 3.3: Organize a high-level policy dialogue for senior decision-makers to promote understanding and commitment to legal capacity reform in line with international standards;

- 3.4: Implement a campaign featuring human interest stories that highlight the benefits of supported decision-making, with a focus on gender inclusion and reducing stigma toward persons with intellectual and psychosocial disabilities;

## Links with the EU Accession process and the 2030 Agenda for Sustainable Development

How is the intervention linked with the EU Accession process and the 2030 Agenda for Sustainable Development, with the focus on how the intervention accelerates implementation of both agendas?

What is the development / policy area in the intersection between the EU Accession and the 2030 Agenda for Sustainable Development that is actually being accelerated? Please cite specific recommendations from Progress report and targets from 2030 Agenda (or National Strategy for Sustainable Development 2030).

What problems within the EU Accession agenda and the implementation of the 2030 Agenda for Sustainable Development are solved by the intervention? What is the system-level change that the programme will deliver?

Has it been recognized in the Common Country Analysis (CCA)?

EU Accession

The proposed intervention directly supports Montenegro’s EU accession process, contributing to fulfilling three final benchmarks under Chapters 23 of the EU Acquis:

- Implementation of a deinstitutionalisation strategy for persons with disabilities;

- Establishment of a credible track record implementing provisions on non-discrimination, in line with the EU acquis and European standards, and provides effective mechanisms for redress and assistance to victims.

- Ensuring the effective implementation and enforcement of the rights and freedoms set out in the European Convention on Human Rights (ECHR).

The rights enshrined in the ECHR are closely aligned with Montenegro's obligations under the CRPD. Moreover, deinstitutionalization is a priority in the Government’s Reform Agenda prepared under the EU Growth Plan. The European Commission has highlighted Montenegro’s failure to reform guardianship and substituted decision-making in its latest Reports (2023, 2024), underscoring the urgency and importance of this intervention.

2030 Agenda for Sustainable Development

The project contributes to the 2030 Agenda by addressing systemic discrimination against persons with disabilities, a group left behind in Montenegro, and within that group, persons with psychosocial and intellectual disabilities and women, as they are particularly marginalized and face intersecting discrimination. Specifically, the intervention advances:

- SDG 5: Gender Equality – targets 5.1, 5.2, 5.5, 5.6, 5.7 and 5.9 on discrimination, violence, participation in decision-making, health, employment, legislation and policies;

- SDG 10.3: Ensure equal opportunity and reduce inequalities of outcome, by eliminating discriminatory laws and practices;

- SDG 16.3: Promote the rule of law and ensure equal access to justice for all.

By transforming the legal and service systems that deny persons with disabilities their legal capacity, the programme operationalizes the “Leave No One Behind” principle.

The intervention lies at the intersection of EU Accession and the 2030 Agenda through its focus on legal capacity reform and deinstitutionalization — core areas where human rights obligations, European legal standards, and sustainable development goals converge.

System level change

The intervention will address the following persistent obstacles to implementation of human rights obligations, the 2030 and the EU agenda:

- The absence of supported decision-making services;

- The continued use of guardianship and substituted decision-making;

- Limited institutional capacity for CRPD implementation;

- Weak mechanisms for accountability and redress.

Through legal reform, the design and piloting of a supported decision-making model, and targeted institutional capacity-building, the programme aims to deliver system-level change. This includes a shift from a medical and charity to a rights-based approach to legal capacity, and the creation of scalable, sustainable support services aligned with international standards.

UNCT Montenegro Common Country Analysis (CCA)

The 2021 CCA and the 2023 CCA update identify the denial of legal capacity as a key challenge persons with disabilities face in Montenegro to exercise their rights on an equal basis with others. The programme will contribute to the SDCF’s output 4.1 – as it will strengthen the capacity of the system to provide justice to the most excluded, and output 4.3 – for enhancing the capacity of the most vulnerable groups of citizens to exercise their rights on an equal basis as others.

## Innovative and catalytic nature of the intervention

What is the innovative component and approach of the intervention? How is it different to what the United Nations in Montenegro are doing, and how is it different to the current approaches in the sector? How is the catalytic component of the intervention ensured?

Innovation

This is the first UN-backed initiative in Montenegro that specifically targets persons with intellectual and psychosocial disabilities, a group historically excluded from decision-making and facing multiple forms of discrimination. By focusing on the most marginalized within an already vulnerable community, the initiative ensures that those most in need are given the attention and support they deserve, creating a foundation for inclusive policy development and social transformation.

The initiative will support a paradigm shift from a medical and charity-based approach to a rights-based approach to disability, fully aligned with the CRPD. It emphasizes legal capacity, autonomy, and supported decision-making, instead of traditional guardianship and substituted decision-making. This approach challenges deep-seated societal biases and empowers persons with disabilities to reclaim their decision-making rights and participate meaningfully in society. The shift will foster a societal mindset that recognizes persons with disabilities as active, capable contributors to their communities.

A key innovation is the design and piloting of Montenegro’s first community-based supported decision-making service. This service will empower individuals with intellectual and psychosocial disabilities to make their own decisions in all aspects of their lives, from healthcare to finances, with tailored, rights-respecting support. Unlike institutional or guardian-controlled decision-making, this model ensures that support aligns with the individual’s preferences, promoting self-determination and inclusion while reducing reliance on institutional care.

The community-based service model will serve as a blueprint for future services, with the potential to influence legal and policy reforms at the national level. By demonstrating success in the community, the initiative can drive broader progress in implementation of Montenegro’s strategies on deinstitutionalization and disability inclusion. The project aims to inspire a long-term shift in both legal and social frameworks to fully align with international human rights standards.

This initiative is thus not only groundbreaking in its focus on one of the most marginalized groups in Montenegro, but it also introduces a transformative, rights-based approach to disability, builds an innovative service model, and reshapes societal attitudes. Its potential for scalability ensures that its impact will extend beyond the pilot phase, influencing national policies and contributing to lasting change for persons with intellectual and psychosocial disabilities.

Difference from other UN interventions and other approaches in the sector

The project is unique in its objectives and scope and is the first full-fledged joint UN intervention to support ending denial of legal capacity in Montenegro. The intervention builds on lessons learned from current work under the joint UN project, implemented by UNDP, OHCHR and UNICEF, ‘Accelerating disability inclusion of children and adults with disabilities, phase 2’, funded by the UN Partnership on the Rights of Persons with Disabilities. This intervention will use the findings from an analysis of laws and practices regarding denial of legal capacity and a roadmap for action to supported decision-making in Montenegro, undertaken under the joint project in the first half of 2025.

Catalytic

This intervention is catalytic and expected to spark broader systemic change beyond the project’s duration. By demonstrating how supported decision-making can function effectively in practice, it will provide a practical model for national scale-up. Aligned with Montenegro’s Deinstitutionalization Strategy and EU accession priorities, the project may attract future EU and domestic funding. Through institutional partnerships, embedded training, and active engagement of organizations of persons with disabilities, the project will build national ownership and capacity. These elements ensure that the intervention not only delivers immediate results but also triggers long-term reform in law, policy, and service delivery aligned with international human rights standards.

## Key target groups

What are the key target groups of the intervention? Who will benefit and how? How is the intervention addressing the obligatory Gender and Human Rights markers?

Key target groups

The intervention’s main beneficiaries are persons with intellectual and psychosocial disabilities, who are among the most marginalized in Montenegro. Particular attention will be given to women and girls, who face intersecting discrimination and barriers to exercising their rights. The project will empower women with disabilities to make independent decisions in areas such as health (including reproductive autonomy), education, employment, access to justice, family life, and political participation. It seeks to reduce their exposure to violence, institutionalization, and legal exclusion.

Direct beneficiaries are persons with disabilities, who will access supported decision-making services and gain autonomy in their lives. Indirect beneficiaries are professionals from the judiciary and social welfare sector whose capacity will be strengthened to implement rights-based reforms, and families of persons with disabilities.

Gender marker - (Score: 2 – Fully Gender Responsive)

Changes to legislation and practices will result in fewer cases denial of legal capacity of women with disabilities, particularly those with psychosocial and intellectual disabilities. One supported decision-making service will be established and empower women to make independent decisions about their live in areas like health, education, employment, and family matters. This will contribute to their autonomy, enabling them to participate in the society and reduce their risk to exploitation and abuse. Capacity building activities will challenge discriminatory attitudes and practices that disproportionately affect women with disabilities, fostering greater gender equality and advancing rights in line with international human rights framework particularly CRPD. The intervention contributes to SDG 5 (Gender Equality) and its six targets (as noted under 2.2). It will systematically disaggregate data by gender, age, and disability, ensuring evidence-based monitoring of gender outcomes. Overall, the project will promote the dignity, agency, and inclusion of women with disabilities, enhancing their overall well-being and equal opportunities for participation.

Human Rights Marker - (Score: 2 – Human Rights is the Principal Objective)

The programme has been designed based on information from persons with disabilities and will be implemented and evaluated in collaboration with persons with disabilities. The project furthers international human rights standards and the human rights principles of equality, non-discrimination and participation. It will support laws and practices to align with UN, European standards and national legislation on human rights, particularly the CRPD, and with national strategies on the rights of persons with disabilities and on deinstitutionalization. The programme supports Montenegro to implement various UN human rights recommendations, most recent ones made:

- by the UN Committee on the Rights of Persons with Disabilities, on ending legal capacity denial and adopting a human rights approach in legislation (CRPD/C/MNE/CO/1, paragraphs 7 and 25, 2017);

- by the CEDAW Committee, on decision-making and bodily autonomy of women with disabilities (CEDAW/C/MNE/CO/3, paragraph 42, 2024);

- During the Universal Periodic Review on aligning legislation on disability with human rights standards and on deinstitutionalization (A/HRC/54/14, paragraphs 131.184-185 and 131.187, 2023), recommendations which were accepted by Montenegro.

When piloting the supported decision-making service, the project will ensure that data on beneficiaries is disaggregated by gender, age and type of disability. The intervention furthers indicators 3, 5 and 8 of UN Disability Including Strategy, as it uses analysis on disability from the CCA; the project is designed and will be implemented in consultation with persons with disabilities; and is a joint program specifically focused on the rights of persons with disabilities.

# Project implementation and sustainability

## Implementation strategy

What is the intervention strategy and why will the intervention achieve success? What are the major assumptions, risks and risk mitigation measures?

The intervention strategy furthers implementation of UN standards, builds on findings and recommendations from prior UN-supported research and from UN human rights bodies, thus providing a strong normative and evidence base for the reform. Based on these standards, analysis and inputs from relevant sectors, the transition from substituted to supported decision-making is designed to be gradual and phased, thereby minimizing potential negative impacts on end beneficiaries.

In line with the principle of “Nothing about us without us” and Article 4(3) of the CRPD, the intervention will be implemented with the active and meaningful participation of persons with disabilities, particularly those most affected by the denial of legal capacity, in all phases of the project. This is critical to ensuring that the supported decision-making system and broader reform efforts are responsive to the needs, preferences, and lived experiences of those who require decision-making support.

The intervention strategy is structured around three complementary pillars: (1) legal and policy reform, (2) the design and piloting of a supported decision-making model, and (3) capacity building and awareness-raising to shift institutional and societal attitudes. These components aim to establish the legal, institutional, and social foundations necessary for a comprehensive reform that enables a paradigm shift from a medical to a rights-based approach to legal capacity for persons with disabilities in Montenegro.

Legal expertise will be engaged to draft amendments to current, discriminatory legislation that allows for the deprivation of legal capacity based solely on disability. As legislative change takes time, the programme will simultaneously support improved practices within the judiciary and social services by developing interim protocols that apply supported decision-making principles. Additionally, a supported decision-making service model will be co-designed with persons with disabilities and piloted through a local service provider. This model will serve as a scalable alternative to guardianship, with a national roll-out strategy developed based on the evaluation of the pilot.

Capacity-building will be conducted in partnership with two national training bodies - the Centre for Judicial and Prosecutorial Training and the Institute for Social and Child Protection - to ensure long-term sustainability. Training sessions will target judges, prosecutors, social workers, and policymakers, promoting a shift from the outdated medical model to CRPD-compliant, human rights-based practices. Public awareness activities, including a campaign featuring human interest stories, will complement these efforts, to reduce stigma towards persons with intellectual and psychosocial disabilities, and to promote broader societal acceptance of legal capacity reform.

The intervention is expected to succeed due to several enabling factors. The Government recognizes that addressing denial of legal capacity is essential for implementing the National Strategy on Deinstitutionalization and meeting EU accession benchmarks under Chapter 23. Moreover, the project is fully aligned with Montenegro’s international human rights obligations, national reform priorities, and the 2030 Agenda. The active engagement of key institutions — including the Ministry of Justice, Ministry of Social Welfare, Family Care and Demography, Ministry of Human and Minority Rights, Protector of Human Rights and Freedoms, the judiciary, and organizations of persons with disabilities — will ensure national ownership. The participatory and gender-responsive approach applied throughout the project will further ensure the intervention’s relevance, long-term impact, and sustainability.

Major Assumptions:

- Collaborative stakeholder engagement: the key national stakeholders — the Ministry of Justice, Ministry of Social Welfare, Family Care and Demography, Ministry of Human and Minority Rights, judiciary, social welfare sector, and organizations of persons with disabilities — will maintain a collaborative approach throughout the intervention. Their shared commitment is essential to ensure legal, institutional, and social alignment with the reform agenda.

- Active political support and continuity: The intervention assumes sustained political will and leadership support from relevant ministries and policymakers, particularly in aligning the reform with EU accession priorities (Chapter 23) and national strategies.

- Meaningful participation of persons with disabilities: It is assumed that persons with disabilities, especially those with intellectual and psychosocial disabilities, will be actively engaged throughout the project cycle, in line with the principle of "Nothing about us without us" and Article 4(3) of the CRPD.

Risks and Mitigation Measures:

- Resistance to change in professional sectors:

Resistance from the judiciary, medical, or social welfare professionals — driven by long-standing substitute decision-making practices and traditional perceptions of disability — may hinder the acceptance and application of supported decision-making.

Mitigation: Targeted capacity-building, co-development of practical tools, and early piloting of supported decision-making services will promote professional buy-in and facilitate a shift in institutional mindsets.

- Delays in legislative reform:

The complexity of drafting legal amendments, combined with potentially lengthy parliamentary review and approval procedures, may lead to delays in the formal adoption of the necessary legal reforms.

Mitigation: The project will introduce interim practice guidelines and protocols to enable courts and social services to begin applying supported decision-making principles, ensuring that reform implementation is not dependent solely on legislative timelines.

- Insufficient public understanding and stigma:

Low public awareness and persistent stigma surrounding persons with intellectual and psychosocial disabilities may reduce societal support for reform.

Mitigation: Awareness raising campaign featuring personal narratives and human-interest stories will increase understanding, reduce stigma, and build broad-based support for legal capacity reform.

- Limited institutional capacity for implementation:

Certain institutions may face gaps in technical expertise and operational infrastructure, which could hinder the effective implementation of supported decision-making reforms.

Mitigation: The project will strengthen institutional capacity through strategic partnerships, tailored training programmes, and the development of a scalable and sustainable supported decision-making service model.

- Limited participation of persons with disabilities:

Without proactive and inclusive measures, there is a risk that persons with disabilities will not be meaningfully engaged in project design, implementation, or monitoring.

Mitigation: The project will apply inclusive facilitation practices, ensure all materials and processes are accessible, and actively involve representative organizations of persons with disabilities throughout all phases of the project cycle, in line with the CRPD and the principle of "Nothing about us without us."

## Theory of change

What is the dominant theory of change and how is it related to the Cooperation Framework, 2030 Agenda for Sustainable Development and the EU accession process?

The Theory of Change of the intervention is as follows:

IF discriminatory legislation and procedures that allow for the denial of legal capacity based on disability are repealed or amended in line with international human rights standards;

AND IF legal, social protection professionals, and families of persons with disabilities enhance their understanding of disability and gender equality rights and shift their attitudes and practices from a medical or charity-based model to a human rights-based approach;

AND IF an inclusive and gender-responsive community-based supported decision-making service is developed, accessible, and tailored to the needs of persons with intellectual and psychosocial disabilities;

THEN persons with disabilities - especially those with intellectual and psychosocial disability, including women - will be able to exercise their legal capacity on an equal basis with others, supported by adequate, rights-based mechanisms that enable autonomous decision-making in all areas of life.

BECAUSE the structural and practical barriers that deny persons with disabilities their right to legal capacity will be eliminated, policy and institutions will be reformed, attitudes will be changed and professional capacity will be built, and a sustainable support service will be available, grounded in international standards.

This Theory of Change is directly aligned with UNSDCF Output 4.1 as the capacity of the system to provide justice to the most excluded will be built, in a manner that respects international human rights standards. It contributes to Output 4.3 on civic space, as legal capacity will be restored, empowering the most vulnerable to make decisions on their own behalf and exercise their rights. It supports Montenegro’s progress on SDG 10, target 10.3 as inequalities that persons with disabilities experience will be reduced and equal opportunities enhanced, on SDG 16, 16.3 on the rule of law and ensuring equal access to justice for all, and various targets under SDG 5 on Gender Equality as particular focus will be on restoring the rights of women with disabilities. The Theory of Change aligns with three benchmarks under Chapter 23 of the EU accession process, as it addresses discrimination, deinstitutionalization, and will further implementation of the standards in the European Convention on Human Rights (ECHR) since these align with international human rights law.

## Expected impact

What is the long term impact of the intervention?  How does the intervention contribute to the achievement of outcome indicators as defined in the results framework? Please explain, regardless of the status of the indicators.

This intervention will contribute to a fundamental shift from a medical approach to disability to one that is rights-based. It will empower persons with disabilities, particularly those with psychosocial and intellectual disabilities, who have long been denied their rights. By restoring their legal capacity, they will exercise decision-making authority, receiving the support they are entitled to. This will enable them to contribute meaningfully to their communities. The intervention is expected to foster long-term cultural and institutional changes in attitudes, practices, and approaches among professionals, families, and the broader public towards persons with disabilities who will be recognized for their autonomy and active participation in society.

The intervention is expected to significantly reduce instances of full or partial denial of legal capacity for persons with disabilities. It seeks to ensure that eventually the denial of legal capacity solely based on disability, in law and in practice, will be abolished. Since denial of legal capacity constitutes a violation of Article 12 of the CRPD and of equality before the law, the intervention will directly contribute to the achievement of SDCF Outcome Indicator 4.4(b) that deals with equality before the law.

## Partnerships

Who are the key partners for implementing the intervention? How results and strategies complement the efforts of other development partners and programmes working on the same problems? Does this programme envisage new strategic partnerships? Describe how the strategic partnerships will be ensured beyond the project.

The successful implementation of this project relies on strong collaboration with government, judicial, and civil society partners. Key government counterparts will be the Ministry of Justice (Directorate for Criminal and Civil Legislation), the Ministry of Human and Minority Rights (Directorate for Protection and Equality of Persons with Disabilities), and the Ministry of Social Welfare, Family Care and Demography. These institutions play a central role in legislative reform, policy development, and service delivery. The programme will also engage judicial institutions—particularly the Centre for Judicial and Prosecutorial Training, basic courts, court experts, and social welfare institutions, including the Institute for Social and Child Protection and social welfare centres, which serve as guardianship authorities.

The project builds on long-standing collaboration between UNDP, OHCHR, and organizations of persons with disabilities (OPDs) in Montenegro. OPDs will be meaningfully engaged in all phases of the programme, including co-designing activities, participating in consultations and trainings, raising public awareness, and monitoring implementation. This approach ensures that all interventions are grounded in the lived experiences and rights of persons with disabilities, in line with the CRPD and the principle of “Nothing about us without us.”

The project also leverages the UN’s cooperation with the Protector of Human Rights and Freedoms, Montenegro’s national human rights institution. Under the first phase of the UNPRPD funded JP Accelerating Disability Inclusion of Children and Adults with Disabilities, the UN supported the establishment of the country’s first Independent Monitoring Mechanism (IMM) to oversee CRPD implementation. Comprising the Protector and ten OPDs, the IMM will contribute to the programme through independent monitoring and reinforcing national accountability for legal capacity reform.

Complementarity with other development initiatives — on deinstitutionalization, access to justice, and broader human rights efforts — will be ensured through close coordination with national stakeholders, UN agencies, and development partners. This collaboration will promote coherence and help avoid duplication of efforts.

To ensure sustainability beyond the project’s duration, the project embeds capacity-building in national training institutions, strengthens local service delivery systems, and supports OPDs to continue advocacy and oversight. This multi-stakeholder, inclusive approach promotes national ownership, long-term accountability, and systemic change — and aligns with the UN’s commitment to leave no one behind.

## Scalability and sustainability

A brief description about how expected results will be sustained beyond the timeline of the intervention? What is the catalytic component of the intervention, and what is the potential for scale up of the intervention?

The intervention is designed so that results are integrated in national systems and institutional frameworks, to sustain impact beyond the project. Key to this sustainability strategy is the integration of supported decision-making principles and CRPD-aligned practices in the regular operations of judicial and social protection institutions. Training curricula will be institutionalized in the Centre for Judicial and Prosecutorial Training and the Institute for Social and Child Protection, to ensure future continuous knowledge transfer to professionals. Furthermore, the capacity of OPDs will be strengthened to lead ongoing advocacy, monitoring, and service delivery, reinforcing their long-term role in reform implementation.

The catalytic component of the intervention lies in the piloting of Montenegro’s first supported decision-making service, co-designed with persons with disabilities. This model will serve as a practical and scalable alternative to guardianship, demonstrating how legal capacity can be respected in practice. Through evaluation, refinement, and the development of a scale-up road map, the pilot will generate an evidence base and operational blueprint for broader national replication. In parallel, legal amendments and interim protocols will lay the foundation for systemic transformation in law and practice.

The programme’s alignment with Montenegro’s obligations under the CRPD, the National Strategy on Deinstitutionalization, and EU accession requirements under Chapter 23 further enhances scalability and relevance. By anchoring reforms in legal frameworks, service models, and stronger institutional capacities, the intervention offers a replicable approach to transforming how the rights of persons with disabilities are realized — ensuring long-term impact and enabling national scale-up.

The programme is expected to directly impact on around 1000 persons with intellectual and psycho-social disabilities, currently denied legal capacity. It will also directly benefit 100 officials in the judiciary, social welfare centres and partners, who will learn about the equal rights of persons with disabilities and about the right to supported instead of substituted decision-making. In addition, all other persons with disabilities in Montenegro will directly benefit from the activities as these will contribute to shifting officials’ and public attitudes towards persons with disabilities away from persons who deserve pity and charity to being persons who equal rights to legal capacity and decision-making. Thus, the initiative reaches a significant group of one of the most discriminated groups, but also duty bearers, and even the public at large.

## Governance structure

Who will implement the intervention and how?

UNDP and OHCHR will jointly implement the programme, in line with the Terms of Reference of the Montenegro SDG Acceleration Fund.

The project will draw on each agency’s mandate and expertise to achieve project goals and support the Fund’s purpose. UNDP will act as the lead Participating UN Organization (PUNO), providing programmatic leadership, coordination, and reporting. Both PUNOs will be individually accountable to manage allocated funds according to their internal regulations.

A Project Steering Committee (PSC) will provide overall governance and strategic direction. The PSC will include representatives of UNDP and OHCHR, government bodies including Ministry of Justice, Ministry of Human and Minority Rights and Ministry of Social Welfare, Family Care and Demography, the Protector for Human Rights and Freedoms and OPDs. The Ministry of Justice will be invited to co-chair the PSC together with UNDP. The PSC will provide strategic guidance, oversee progress, support risk management, and help ensure coherence of efforts of stakeholders. It will meet annually, with ad hoc meetings convened as needed. Its ToR will be finalized at the first meeting. The main functions of the PSC include:

- Providing overall guidance and strategic direction to the project, ensuring alignment with agreed objectives and promoting gender equality and social inclusion (Leave No One Behind – LNOB) in implementation;

- Discussing critical issues or bottlenecks that may hinder project implementation;

- Proposing and reviewing actions to address identified challenges;

- Endorsing project reports and other key strategic documents.

A Joint Implementation Team (JIT), consisting of representatives from UNDP as the lead PUNO and OHCHR as the second PUNO, will oversee the daily implementation of the project. On the UNDP side, the team will include programme officer, administrative officer, and a communications officer. The OHCHR component will be undertaken by Human Rights Adviser who will be a member of the JIT. UNDP will provide procurement and financial support for the execution of all activities. The team will ensure information exchange and optimize implementation through bi-monthly or as-needed meetings. Project objectives and key activities will be shared publicly and with partners in accessible formats. Regular consultations will be held with stakeholders throughout the design, implementation, and monitoring phases.

Quality assurance of the project will be supported by a Quality Assurer, whose function is to assess the quality of the project against UNDP’s corporate standard criteria. This function is typically performed by a UNDP Monitoring and Evaluation Officer, in order to maintain independence from the Project Manager, regardless of the project’s implementation modality.

## Monitoring, learning and reporting

How will you organise to monitor results and risks of the intervention and respond to the Montenegro SDG Acceleration Fund reporting requirements (more information available in the respective Terms of Reference of the Fund)?

Both PUNOs will carry out continuous monitoring of progress and performance throughout project implementation of the Project, in line with the Montenegro Acceleration Fund ToR. They will collect and analyse information to track progress, record outcomes, identify bottlenecks and facilitate effective adjustments to projects activities as needed. The basis for monitoring of the project will be the Results Framework (RF), while progress of implementation will be tracked against Annual Work Plans designed by UNDP and OHCHR and validated by the Joint Steering Committee.

Both PUNOs will document lessons and best practices, present these to the JSC and use these for improving project interventions, as relevant.

In line with the MPTF’s Memorandum of Understanding (MoU), the project will produce an annual and final reports on activities and expenditures according to the common format designed for the MPTF. In addition

The project will prepare ad hoc periodic reports if requested by the JSC. UNDP will submit these reports to the MAF Secretariat in accordance with the set timeframes.

Monitoring Plan

| Monitoring Activity | Purpose | Frequency | Expected Action |
| --- | --- | --- | --- |
| Track results progress | Progress data against the results indicators in the RRF will be collected and analysed to assess the progress of the project in achieving the agreed outputs. | Quarterly, or in the frequency required for each indicator. | Slower than expected progress will be addressed by project management. |
| Monitor and Manage Risk | Identify specific risks that may threaten achievement of intended results. Identify and monitor risk management actions using a risk log. This includes monitoring measures and plans that may have been required as per UNDP’s Social and Environmental Standards. Audits will be conducted in accordance with UNDP’s audit policy to manage financial risk. | Quarterly | Risks are identified by project management and actions are taken to manage risk. The risk log is actively maintained to keep track of identified risks and actions taken. |
| Learn | Knowledge, good practices and lessons will be captured regularly, as well as actively sourced from other projects and partners and integrated back into the project. | At least annually | Relevant lessons are captured by the project team and used to inform management decisions. |
| Annual Project Quality Assurance | The quality of the project will be assessed against UNDP’s quality standards to identify project strengths and weaknesses and to inform management decision making to improve the project. | Annually | Areas of strength and weakness will be reviewed by project management and used to inform decisions to improve project performance. |
| Review and Make Course Corrections | Internal review of data and evidence from all monitoring actions to inform decision making. | At least annually | Performance data, risks, lessons and quality will be discussed by the project board and used to make course corrections. |
| Project Report | A progress report will be presented to the Project Board and key stakeholders, consisting of progress data showing the results achieved against pre-defined annual targets at the output level, the annual project quality rating summary, an updated risk long with mitigation measures, and any evaluation or review reports prepared over the period. | Annually, and at the end of the project (final report) |  |
| Project Review (Project Board) | The project’s governance mechanism (i.e., project board) will hold regular project reviews to assess the performance of the project and review the Multi-Year Work Plan to ensure realistic budgeting over the life of the project. In the project’s final year, the Project Board shall hold an end-of project review to capture lessons learned and discuss opportunities for scaling up and to socialize project results and lessons learned with relevant audiences. | Specify frequency (i.e., at least annually) | Any quality concerns or slower than expected progress should be discussed by the project board and management actions agreed to address the issues identified. |

# Results framework

(pls use the attached excel file, Sheet 1)

# Financing of the intervention

Information about the planned budget using the standard UN Sustainable Development Group budget categories, including own contributions (filled-in sheet 2 from the excel template)

# Gender marker scoring

Please attach the filled-in template for Gender marker scoring (download the template from here)

SCORING Template for Joint Program submission3 (pages 4-6)

JOINT PROGRAM TITLE: ENDING THE DENIAL OF LEGAL CAPACITY OF PERSONS WITH DISABILITIES In MONTENEGRO

IMPLEMENTING UN AGENCIES: UNDP & OHCHR 
NAME, SURNAME AND POSITION OF THE PERSON FILLING IN THE TEMPLATE:

SANJA ZINDOVIĆ, PROJECT MANAGER, undp and ANJET LANTING, LEGAL ANALYST, ohchr

Dimension 1: Joint Program Problem/Context Analysis

| Questions | Yes (1) | No (0) |
| --- | --- | --- |
| - Does JP include gender equality in the context/problem analysis, including presentation of relevant gender equality areas using gender sensitive/disaggregated data? | 1 |  |
| 1.2. Does context/problem analysis refer to the key normative standards for gender equality, including CEDAW, the Istanbul Convention, BPfA, SDG5 and other SDGs relevant for gender equality and EU gender equality standards? If yes, explain which ones: The context analysis explicitly refers to key international normative standards for gender equality and human rights. It highlights the disproportionate impact of legal capacity denial on women with disabilities, particularly in relation to sexual and reproductive health and rights, and the risk of harmful practices such as forced sterilization, thereby addressing the obligations under the Convention on the Elimination of All Forms of Discrimination Against Women (CEDAW). The analysis also references relevant provisions of the Convention on the Rights of Persons with Disabilities (CRPD), especially Article 12 on equal recognition before the law, and aligns with principles outlined in the Universal Declaration of Human Rights (UDHR) and the International Covenant on Civil and Political Rights (ICCPR). While the Istanbul Convention and Beijing Platform for Action (BPfA) are not explicitly mentioned, the text addresses core issues they cover—such as gender-based violence, bodily autonomy, and non-discrimination—particularly for women with intellectual and psychosocial disabilities. The intervention’s focus on ending legal capacity denial directly contributes to SDG 5 (Gender Equality) and SDG 10 (Reduced Inequalities), making it highly relevant for both the 2030 Agenda and EU gender equality standards. | 1 |  |
| 1.3. Does context/problem analysis refer to the key national gender equality laws and policies? If yes, explain which ones: The context analysis refers to the Strategy for Gender Equality (2021–2025) and the Law on the Prohibition of Discrimination. Both documents recognize and protect the intersectionality of the rights of women and girls with disabilities, who are disproportionately affected by discriminatory legal and institutional practices. | 1 |  |

Dimension 2: Joint Programme Results

| Questions | 50% or more of the JP Outcome/output indicators are gender- responsive (1 point) |  | At least 30% of the JP Outcome/output indicators are gender- responsive (0.5 point) |  | Less than 30% of the JP outcome/output indicators are gender- responsive (0 point) |  |
| --- | --- | --- | --- | --- | --- | --- |
| 2.1. What percentage of the JP outcome indicators are gender responsive, i.e. indicators that measure changes in the situation of women and men and a reduction in the inequalities between them? | 1 |  |  |  |  |  |
| 2.2. What percentage of JP output indicators are gender - responsive? | 1 |  |  |  |  |  |
| 2.3. Does JP Theory of Change define assumptions, causality and chains of intervention effects taking into account gender equality context, factors that might influence achievement of results and impact on gender equality? | Yes (1) |  |  | No (0) |  |  |
|  | 1 |  |  |  |  |  |
| 2.4. Does the primary goal of the JP focus on addressing root causes of gender inequalities (e.g., harmful norms/practices, unequal distribution of power/resources etc) and strengthening women’s/girls’ empowerment? | Yes (2) |  |  | No (0) |  |  |
|  |  |  |  | 0 |  |  |

Dimension 3: Joint Program Partnerships

| Questions | Yes (1) | No (0) |
| --- | --- | --- |
| 3.1. Are gender equality national and sub-national mechanisms consulted in program design? | 1 |  |
| 3.2. Are gender equality national and sub-national mechanisms included as implementing partners and/or beneficiaries? | 1 |  |
| 3.3. Are women’s, feminists, LGBTI or gender equality organisations consulted in the JP program design? |  | 0 |
| 3.4. Are women’s, feminists, LGBTI or gender equality organisations included (intended to be included) as partners and/or beneficiaries (e.g. in terms of their capacity building and advocacy support) | 1 |  |

Dimension 4: Gender responsive M&E

| Questions | Yes (1) | No (0) |
| --- | --- | --- |
| 4.1. Does JP monitoring framework include quantitative and qualitative gender disaggregated data to assess progress? | 1 |  |
| 4.2. Does JP include plans for carrying gender responsive evaluation? | 1 |  |

TOTAL SCORE: 11

ASSIGNED GENDER MARKER: UNCT-GEM 2

The Strategy on Deinstitutionalization (2025-2028) notes that the court denied full legal capacity of 948 persons (493 male and 455 female) and partially in only 38 cases. Only in three cases, courts restored legal capacity. Data for 2022-2023. The Strategy foresees a reduction of cases of legal capacity denial.

See Committee on the Rights of Persons with Disabilities (CPRD Committee), General Comment no. 1 (2014) on Article 12: equal recognition before the law, and General Comment no. 6 (2018) on equality and non-discrimination.

CRPD, Art. 12.4.

CRPD Committee, Concluding observations on the initial report of Montenegro 2017, p. 10

Law on the Protection and Exercise of the Rights of the Mentally Ill, article 22

Strategy for the Protection of Persons with Disabilities from Discrimination and Promotion of Equality 2022-2027, p. 29.

Law on Non-Contentious Proceedings, article 30.

CRPD Committee, General Comment No. 1, para. 15.

CRPD Committee, General Comment No. 1, para. 13.

The Quality Assurer is not a formal member of the Project Board and may not attend all Board meetings, but provides independent inputs to support the Board’s quality assurance responsibilities.